## Task_Table1
UID | Task Name | Start | Finish | Predecessors | Successors | Constraint_Type | Constraint_Date | Duration | Total_Slack | Baseline_Start | Baseline_Finish | Baseline_Duration | Milestone | Actual_Start | Actual_Finish | Deadline | Percent Complete
1 | CARES V1 | April 1, 2021 8:00 AM | October 11, 2027 5:00 PM |  |  | As Soon As Possible | NA | 1638 | 0 | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 4/1/21 | NA | NA | 0.65000000000000002
4935 | Completed/In-flight Milestones | April 26, 2022 8:00 AM | January 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 944 | 425d | April 26, 2022 8:00 AM | January 30, 2026 5:00 PM | 944 days | No | 4/26/22 | NA | NA | 0.97999999999999998
4936 | Milestone 01: Service Provider Profile (CARESV1-526) | April 26, 2022 8:00 AM | February 6, 2023 5:00 PM |  |  | As Soon As Possible | NA | 196 | 0d | April 26, 2022 8:00 AM | February 6, 2023 5:00 PM | 196 days | No | 4/26/22 | 2/6/23 | NA | 1
4937 | M1: Research & Context Setting | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM |  |  | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4938 | M1: RC: Finalize Value Hypothesis | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM |  | 6SS,7SS,8SS,9SS,10SS,11SS,12SS | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4954 | M1: RC: Draft Service Maps | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 5SS | 7 | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4955 | M1: RC: Complete Legacy Analysis | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 5SS,6 | 8 | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4956 | M1: RC: Finalize Epics | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 5SS,7 | 9 | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4957 | M1: RC: Complete conceptual and epic-level Domain Model diagrams | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 5SS,8 | 10 | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4958 | M1: RC: Define User Story titles | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 5SS,9 | 11 | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4959 | M1: RC: Complete External Systems pre-analysis | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 5SS,10 | 12 | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4960 | M1: RC: Facilitate Inception | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 5SS,11 | 14FS-1d,1908SS+25d,2817SS-240d | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4961 | M1: BRC | June 1, 2022 8:00 AM | June 22, 2022 5:00 PM |  |  | As Soon As Possible | NA | 16 | 0d | June 1, 2022 8:00 AM | June 22, 2022 5:00 PM | 16 days | No | 6/1/22 | 6/22/22 | NA | 1
4962 | M1: B1: 21.01 Create/Update a Service Provider in Directory (CARESV1-66) | June 1, 2022 8:00 AM | June 22, 2022 5:00 PM | 12FS-1d | 16FS+6d | As Soon As Possible | NA | 16 | 0d | June 1, 2022 8:00 AM | June 22, 2022 5:00 PM | 16 days | No | 6/1/22 | 6/22/22 | NA | 1
4963 | M1: Design | July 1, 2022 8:00 AM | September 2, 2022 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | July 1, 2022 8:00 AM | September 2, 2022 5:00 PM | 45 days | No | 7/1/22 | 9/2/22 | NA | 1
4964 | M1: B1: 21.01 Create/Update a Service Provider in Directory (CARESV1-66) | July 1, 2022 8:00 AM | September 2, 2022 5:00 PM | 14FS+6d | 18FS-15d,2222 | As Soon As Possible | NA | 45 | 0d | July 1, 2022 8:00 AM | September 2, 2022 5:00 PM | 45 days | No | 7/1/22 | 9/2/22 | NA | 1
4965 | M1: Build | August 15, 2022 8:00 AM | December 29, 2022 5:00 PM |  |  | As Soon As Possible | NA | 94 | 0d | August 15, 2022 8:00 AM | December 29, 2022 5:00 PM | 94 days | No | 8/15/22 | 12/29/22 | NA | 1
4966 | M1: B1: 21.01 Create/Update a Service Provider in Directory (CARESV1-66) | August 15, 2022 8:00 AM | December 29, 2022 5:00 PM | 16FS-15d | 20SS+19d | As Soon As Possible | NA | 94 | 0d | August 15, 2022 8:00 AM | December 29, 2022 5:00 PM | 94 days | No | 8/15/22 | 12/29/22 | NA | 1
4967 | M1: SIT | September 12, 2022 8:00 AM | October 12, 2022 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | September 12, 2022 8:00 AM | October 12, 2022 5:00 PM | 23 days | No | 9/12/22 | 10/12/22 | NA | 1
4939 | M1: B1: 21.01 Create/Update a Service Provider in Directory (CARESV1-66) | September 12, 2022 8:00 AM | October 12, 2022 5:00 PM | 18SS+19d | 22FS-1d,1475 | As Soon As Possible | NA | 23 | 0d | September 12, 2022 8:00 AM | October 12, 2022 5:00 PM | 23 days | No | 9/12/22 | 10/12/22 | NA | 1
4940 | M1: QA | October 12, 2022 8:00 AM | February 6, 2023 5:00 PM |  |  | As Soon As Possible | NA | 78 | 0d | October 12, 2022 8:00 AM | February 6, 2023 5:00 PM | 78 days | No | 10/12/22 | 2/6/23 | NA | 1
4941 | M1: B1: 21.01 Create/Update a Service Provider in Directory (CARESV1-66) | October 12, 2022 8:00 AM | February 6, 2023 5:00 PM | 20FS-1d | 24SS+18d | As Soon As Possible | NA | 78 | 0d | October 12, 2022 8:00 AM | February 6, 2023 5:00 PM | 78 days | No | 10/12/22 | 2/6/23 | NA | 1
4942 | M1: Readiness for User Feedback | November 7, 2022 8:00 AM | December 5, 2022 5:00 PM |  |  | As Soon As Possible | NA | 18 | 0d | November 7, 2022 8:00 AM | December 5, 2022 5:00 PM | 18 days | No | 11/7/22 | 12/5/22 | NA | 1
4943 | M1: B1: 21.01 Create/Update a Service Provider in Directory (CARESV1-66) | November 7, 2022 8:00 AM | December 5, 2022 5:00 PM | 22SS+18d | 26SS | As Soon As Possible | NA | 18 | 0d | November 7, 2022 8:00 AM | December 5, 2022 5:00 PM | 18 days | No | 11/7/22 | 12/5/22 | NA | 1
4944 | M1: User Feedback | November 7, 2022 8:00 AM | December 5, 2022 5:00 PM |  |  | As Soon As Possible | NA | 18 | 0d | November 7, 2022 8:00 AM | December 5, 2022 5:00 PM | 18 days | No | 11/7/22 | 12/5/22 | NA | 1
4945 | M1: B1: 21.01 Create/Update a Service Provider in Directory (CARESV1-66) | November 7, 2022 8:00 AM | December 5, 2022 5:00 PM | 24SS | 27FS+17d | As Soon As Possible | NA | 18 | 0d | November 7, 2022 8:00 AM | December 5, 2022 5:00 PM | 18 days | No | 11/7/22 | 12/5/22 | NA | 1
4946 | Milestone 1 (Provider Profile) Jira # CARES V1-526 Complete | December 30, 2022 8:00 AM | December 30, 2022 8:00 AM | 26FS+17d |  | As Soon As Possible | NA | 0 | 0d | December 30, 2022 8:00 AM | December 30, 2022 8:00 AM | 0 days | Yes | 12/30/22 | 12/30/22 | NA | 1
4968 | Milestone 02: Services (CARESV1-525) | April 26, 2022 8:00 AM | February 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 197 | 0d | April 26, 2022 8:00 AM | February 7, 2023 5:00 PM | 197 days | No | 4/26/22 | 2/7/23 | NA | 1
4969 | M2: Research & Context Setting | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM |  |  | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4970 | M2: RC: Finalize Value Hypothesis | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM |  | 31SS,32SS,33SS,34SS,35SS,36SS,37SS | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4971 | M2: RC: Draft Service Maps | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 30SS | 32 | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4972 | M2: RC: Complete Legacy Analysis | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 30SS,31 | 33 | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4973 | M2: RC: Finalize Epics | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 30SS,32 | 34 | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4974 | M2: RC: Complete conceptual and epic-level Domain Model diagrams | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 30SS,33 | 35 | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4975 | M2: RC: Define User Story titles | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 30SS,34 | 36 | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4976 | M2: RC: Complete External Systems pre-analysis | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 30SS,35 | 37 | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4977 | M2: RC: Facilitate Inception | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 30SS,36 | 39FS-1d | As Soon As Possible | NA | 26 | 0d | April 26, 2022 8:00 AM | June 1, 2022 5:00 PM | 26 days | No | 4/26/22 | 6/1/22 | NA | 1
4978 | M2: BRC | June 1, 2022 8:00 AM | June 22, 2022 5:00 PM |  |  | As Soon As Possible | NA | 16 | 0d | June 1, 2022 8:00 AM | June 22, 2022 5:00 PM | 16 days | No | 6/1/22 | 6/22/22 | NA | 1
4979 | M2: B1: 18.03 Update/Manage Service Array (CARESV1-120) | June 1, 2022 8:00 AM | June 22, 2022 5:00 PM | 37FS-1d | 41FS+10d | As Soon As Possible | NA | 16 | 0d | June 1, 2022 8:00 AM | June 22, 2022 5:00 PM | 16 days | No | 6/1/22 | 6/22/22 | NA | 1
4980 | M2: Design | July 8, 2022 8:00 AM | August 11, 2022 5:00 PM |  |  | As Soon As Possible | NA | 25 | 0d | July 8, 2022 8:00 AM | August 11, 2022 5:00 PM | 25 days | No | 7/8/22 | 8/11/22 | NA | 1
4981 | M2: B1: 18.03 Update/Manage Service Array (CARESV1-120) | July 8, 2022 8:00 AM | August 11, 2022 5:00 PM | 39FS+10d | 43FS+1d,2226 | As Soon As Possible | NA | 25 | 0d | July 8, 2022 8:00 AM | August 11, 2022 5:00 PM | 25 days | No | 7/8/22 | 8/11/22 | NA | 1
4982 | M2: Build | August 15, 2022 8:00 AM | December 29, 2022 5:00 PM |  |  | As Soon As Possible | NA | 94 | 0d | August 15, 2022 8:00 AM | December 29, 2022 5:00 PM | 94 days | No | 8/15/22 | 12/29/22 | NA | 1
4983 | M2: B1: 18.03 Update/Manage Service Array (CARESV1-120) | August 15, 2022 8:00 AM | December 29, 2022 5:00 PM | 41FS+1d | 45SS-3d | As Soon As Possible | NA | 94 | 0d | August 15, 2022 8:00 AM | December 29, 2022 5:00 PM | 94 days | No | 8/15/22 | 12/29/22 | NA | 1
4984 | M2: SIT | August 10, 2022 8:00 AM | October 10, 2022 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | August 10, 2022 8:00 AM | October 10, 2022 5:00 PM | 43 days | No | 8/10/22 | 10/10/22 | NA | 1
4985 | M2: B1: 18.03 Update/Manage Service Array (CARESV1-120) | August 10, 2022 8:00 AM | October 10, 2022 5:00 PM | 43SS-3d | 47SS+16d,1475 | As Soon As Possible | NA | 43 | 0d | August 10, 2022 8:00 AM | October 10, 2022 5:00 PM | 43 days | No | 8/10/22 | 10/10/22 | NA | 1
4986 | M2: QA | September 1, 2022 8:00 AM | February 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 107 | 0d | September 1, 2022 8:00 AM | February 7, 2023 5:00 PM | 107 days | No | 9/1/22 | 2/7/23 | NA | 1
4987 | M2: B1: 18.03 Update/Manage Service Array (CARESV1-120) | September 1, 2022 8:00 AM | February 7, 2023 5:00 PM | 45SS+16d | 49SS+45d | As Soon As Possible | NA | 107 | 0d | September 1, 2022 8:00 AM | February 7, 2023 5:00 PM | 107 days | No | 9/1/22 | 2/7/23 | NA | 1
4988 | M2: Readiness for User Feedback | November 4, 2022 8:00 AM | December 5, 2022 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | November 4, 2022 8:00 AM | December 5, 2022 5:00 PM | 19 days | No | 11/4/22 | 12/5/22 | NA | 1
4989 | M2: B1: 18.03 Update/Manage Service Array (CARESV1-120) | November 4, 2022 8:00 AM | December 5, 2022 5:00 PM | 47SS+45d | 51SS | As Soon As Possible | NA | 19 | 0d | November 4, 2022 8:00 AM | December 5, 2022 5:00 PM | 19 days | No | 11/4/22 | 12/5/22 | NA | 1
4990 | M2: User Feedback | November 4, 2022 8:00 AM | December 5, 2022 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | November 4, 2022 8:00 AM | December 5, 2022 5:00 PM | 19 days | No | 11/4/22 | 12/5/22 | NA | 1
4991 | M2: B1: 18.03 Update/Manage Service Array (CARESV1-120) | November 4, 2022 8:00 AM | December 5, 2022 5:00 PM | 49SS | 52FS+17d | As Soon As Possible | NA | 19 | 0d | November 4, 2022 8:00 AM | December 5, 2022 5:00 PM | 19 days | No | 11/4/22 | 12/5/22 | NA | 1
4992 | Milestone 2 (Services) Jira # CARES V1-525 Complete | December 30, 2022 8:00 AM | December 30, 2022 8:00 AM | 51FS+17d |  | As Soon As Possible | NA | 0 | 0d | December 30, 2022 8:00 AM | December 30, 2022 8:00 AM | 0 days | Yes | 12/30/22 | 12/30/22 | NA | 1
5022 | Milestone 03: Screening (CARESV1-524) | May 3, 2022 8:00 AM | March 24, 2023 5:00 PM |  |  | As Soon As Possible | NA | 224 | 0d | May 3, 2022 8:00 AM | March 24, 2023 5:00 PM | 224 days | No | 5/3/22 | 3/24/23 | NA | 1
5023 | M3: Research & Context Setting | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM | 21 days | No | 5/3/22 | 6/1/22 | NA | 1
5024 | M3: RC: Finalize Value Hypothesis | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM |  | 56SS,57SS,58SS,59SS,60SS,61SS,62SS | As Soon As Possible | NA | 21 | 0d | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM | 21 days | No | 5/3/22 | 6/1/22 | NA | 1
5025 | M3: RC: Draft Service Maps | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM | 55SS | 57 | As Soon As Possible | NA | 21 | 0d | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM | 21 days | No | 5/3/22 | 6/1/22 | NA | 1
5026 | M3: RC: Complete Legacy Analysis | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM | 55SS,56 | 58 | As Soon As Possible | NA | 21 | 0d | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM | 21 days | No | 5/3/22 | 6/1/22 | NA | 1
5027 | M3: RC: Finalize Epics | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM | 55SS,57 | 59 | As Soon As Possible | NA | 21 | 0d | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM | 21 days | No | 5/3/22 | 6/1/22 | NA | 1
5028 | M3: RC: Complete conceptual and epic-level Domain Model diagrams | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM | 55SS,58 | 60 | As Soon As Possible | NA | 21 | 0d | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM | 21 days | No | 5/3/22 | 6/1/22 | NA | 1
5029 | M3: RC: Define User Story titles | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM | 55SS,59 | 61 | As Soon As Possible | NA | 21 | 0d | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM | 21 days | No | 5/3/22 | 6/1/22 | NA | 1
5030 | M3: RC: Complete External Systems pre-analysis | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM | 55SS,60 | 62 | As Soon As Possible | NA | 21 | 0d | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM | 21 days | No | 5/3/22 | 6/1/22 | NA | 1
5031 | M3: RC: Facilitate Inception | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM | 55SS,61 | 64FS+4d,65FS+4d,66FS+4d,67FS+4d,2478SS | As Soon As Possible | NA | 21 | 0d | May 3, 2022 8:00 AM | June 1, 2022 5:00 PM | 21 days | No | 5/3/22 | 6/1/22 | NA | 1
5032 | M3: BRC | June 8, 2022 8:00 AM | September 1, 2022 5:00 PM |  |  | As Soon As Possible | NA | 61 | 0d | June 8, 2022 8:00 AM | September 1, 2022 5:00 PM | 61 days | No | 6/8/22 | 9/1/22 | NA | 1
5033 | M3: B1: 01.04 Send to Selected Pathway (CARESV1-75) | June 8, 2022 8:00 AM | September 1, 2022 5:00 PM | 62FS+4d | 65 | As Soon As Possible | NA | 61 | 0d | June 8, 2022 8:00 AM | September 1, 2022 5:00 PM | 61 days | No | 6/8/22 | 9/1/22 | NA | 1
5034 | M3: B2: 01.02 Conduct Hotline (SDM) Assessment (CARESV1-85) | June 8, 2022 8:00 AM | September 1, 2022 5:00 PM | 62FS+4d,64 | 66 | As Soon As Possible | NA | 61 | 0d | June 8, 2022 8:00 AM | September 1, 2022 5:00 PM | 61 days | No | 6/8/22 | 9/1/22 | NA | 1
5035 | M3: B3: 01.01 Gather Person and Allegation Information determine decision (r1) (CARESV1-86) | June 8, 2022 8:00 AM | September 1, 2022 5:00 PM | 62FS+4d,65 | 67 | As Soon As Possible | NA | 61 | 0d | June 8, 2022 8:00 AM | September 1, 2022 5:00 PM | 61 days | No | 6/8/22 | 9/1/22 | NA | 1
5036 | M3: B4: 01.03 Supervisor dashboard, assess information, confirm responses - Screening (r2) (CARESV1-88) | June 8, 2022 8:00 AM | September 1, 2022 5:00 PM | 62FS+4d,66 | 69SS-8d | As Soon As Possible | NA | 61 | 0d | June 8, 2022 8:00 AM | September 1, 2022 5:00 PM | 61 days | No | 6/8/22 | 9/1/22 | NA | 1
5037 | M3: Design | May 26, 2022 8:00 AM | September 9, 2022 5:00 PM |  |  | As Soon As Possible | NA | 74 | 0d | May 26, 2022 8:00 AM | September 9, 2022 5:00 PM | 74 days | No | 5/26/22 | 9/9/22 | NA | 1
5038 | M3: B1: 01.04 Send to Selected Pathway (CARESV1-75) | May 26, 2022 8:00 AM | September 9, 2022 5:00 PM | 67SS-8d | 70SS,71SS,72SS | As Soon As Possible | NA | 74 | 0d | May 26, 2022 8:00 AM | September 9, 2022 5:00 PM | 74 days | No | 5/26/22 | 9/9/22 | NA | 1
5039 | M3: B2: 01.02 Conduct Hotline (SDM) Assessment (CARESV1-85) | May 26, 2022 8:00 AM | September 9, 2022 5:00 PM | 69SS | 71 | As Soon As Possible | NA | 74 | 0d | May 26, 2022 8:00 AM | September 9, 2022 5:00 PM | 74 days | No | 5/26/22 | 9/9/22 | NA | 1
5040 | M3: B3: 01.01 Gather Person and Allegation Information determine decision (r1) (CARESV1-86) | May 26, 2022 8:00 AM | September 9, 2022 5:00 PM | 69SS,70 | 72 | As Soon As Possible | NA | 74 | 0d | May 26, 2022 8:00 AM | September 9, 2022 5:00 PM | 74 days | No | 5/26/22 | 9/9/22 | NA | 1
5041 | M3: B4: 01.03 Supervisor dashboard, assess information, confirm responses - Screening (r2) (CARESV1-88) | May 26, 2022 8:00 AM | September 9, 2022 5:00 PM | 69SS,71 | 74FS-19d,2230 | As Soon As Possible | NA | 74 | 0d | May 26, 2022 8:00 AM | September 9, 2022 5:00 PM | 74 days | No | 5/26/22 | 9/9/22 | NA | 1
5042 | M3: Build | August 15, 2022 8:00 AM | January 6, 2023 5:00 PM |  |  | As Soon As Possible | NA | 99 | 0d | August 15, 2022 8:00 AM | January 6, 2023 5:00 PM | 99 days | No | 8/15/22 | 1/6/23 | NA | 1
5043 | M3: B1: 01.04 Send to Selected Pathway (CARESV1-75) | August 15, 2022 8:00 AM | January 6, 2023 5:00 PM | 72FS-19d | 75SS,76SS,77SS | As Soon As Possible | NA | 99 | 0d | August 15, 2022 8:00 AM | January 6, 2023 5:00 PM | 99 days | No | 8/15/22 | 1/6/23 | NA | 1
5044 | M3: B2: 01.02 Conduct Hotline (SDM) Assessment (CARESV1-85) | August 15, 2022 8:00 AM | January 6, 2023 5:00 PM | 74SS | 76 | As Soon As Possible | NA | 99 | 0d | August 15, 2022 8:00 AM | January 6, 2023 5:00 PM | 99 days | No | 8/15/22 | 1/6/23 | NA | 1
5045 | M3: B3: 01.01 Gather Person and Allegation Information determine decision (r1) (CARESV1-86) | August 15, 2022 8:00 AM | January 6, 2023 5:00 PM | 74SS,75 | 77 | As Soon As Possible | NA | 99 | 0d | August 15, 2022 8:00 AM | January 6, 2023 5:00 PM | 99 days | No | 8/15/22 | 1/6/23 | NA | 1
5046 | M3: B4: 01.03 Supervisor dashboard, assess information, confirm responses - Screening (r2) (CARESV1-88) | August 15, 2022 8:00 AM | January 6, 2023 5:00 PM | 74SS,76 | 79SS+6d,80SS+6d,81SS+6d,84SS+6d | As Soon As Possible | NA | 99 | 0d | August 15, 2022 8:00 AM | January 6, 2023 5:00 PM | 99 days | No | 8/15/22 | 1/6/23 | NA | 1
5047 | M3: SIT | August 23, 2022 8:00 AM | February 6, 2023 5:00 PM |  |  | As Soon As Possible | NA | 113 | 0d | August 23, 2022 8:00 AM | February 6, 2023 5:00 PM | 113 days | No | 8/23/22 | 2/6/23 | NA | 1
5048 | M3: B1: 01.04 Send to Selected Pathway (CARESV1-75) | August 23, 2022 8:00 AM | February 6, 2023 5:00 PM | 77SS+6d | 80 | As Soon As Possible | NA | 113 | 0d | August 23, 2022 8:00 AM | February 6, 2023 5:00 PM | 113 days | No | 8/23/22 | 2/6/23 | NA | 1
5049 | M3: B2: 01.02 Conduct Hotline (SDM) Assessment (CARESV1-85) | August 23, 2022 8:00 AM | February 6, 2023 5:00 PM | 77SS+6d,79 | 81 | As Soon As Possible | NA | 113 | 0d | August 23, 2022 8:00 AM | February 6, 2023 5:00 PM | 113 days | No | 8/23/22 | 2/6/23 | NA | 1
5050 | M3: B3: 01.01 Gather Person and Allegation Information determine decision (r1) (CARESV1-86) | August 23, 2022 8:00 AM | February 6, 2023 5:00 PM | 77SS+6d,80 | 84 | As Soon As Possible | NA | 113 | 0d | August 23, 2022 8:00 AM | February 6, 2023 5:00 PM | 113 days | No | 8/23/22 | 2/6/23 | NA | 1
4995 | M3: QA | August 23, 2022 8:00 AM | March 24, 2023 5:00 PM |  |  | As Soon As Possible | NA | 146 | 0d | September 6, 2022 8:00 AM | March 24, 2023 5:00 PM | 137 days | No | 8/23/22 | 3/24/23 | NA | 1
4996 | M3: B1: 01.04 Send to Selected Pathway (CARESV1-75) | September 6, 2022 8:00 AM | March 24, 2023 5:00 PM | 84SS+9d | 85 | As Soon As Possible | NA | 137 | 0d | September 6, 2022 8:00 AM | March 24, 2023 5:00 PM | 137 days | No | 9/6/22 | 3/24/23 | NA | 1
4994 | M3: B4: 01.03 Supervisor dashboard, assess information, confirm responses - Screening (r2) (CARESV1-88) | August 23, 2022 8:00 AM | February 6, 2023 5:00 PM | 77SS+6d,81 | 83SS+9d,85SS+9d,86SS+9d,87SS+9d | As Soon As Possible | NA | 113 | 0d | August 23, 2022 8:00 AM | February 6, 2023 5:00 PM | 113 days | No | 8/23/22 | 2/6/23 | NA | 1
4997 | M3: B2: 01.02 Conduct Hotline (SDM) Assessment (CARESV1-85) | September 6, 2022 8:00 AM | March 24, 2023 5:00 PM | 84SS+9d,83 | 86 | As Soon As Possible | NA | 137 | 0d | September 6, 2022 8:00 AM | March 24, 2023 5:00 PM | 137 days | No | 9/6/22 | 3/24/23 | NA | 1
4998 | M3: B3: 01.01 Gather Person and Allegation Information determine decision (r1) (CARESV1-86) | September 6, 2022 8:00 AM | March 24, 2023 5:00 PM | 84SS+9d,85 | 87 | As Soon As Possible | NA | 137 | 0d | September 6, 2022 8:00 AM | March 24, 2023 5:00 PM | 137 days | No | 9/6/22 | 3/24/23 | NA | 1
4999 | M3: B4: 01.03 Supervisor dashboard, assess information, confirm responses - Screening (r2) (CARESV1-88) | September 6, 2022 8:00 AM | March 24, 2023 5:00 PM | 84SS+9d,86 | 89SS+44d,90SS+44d,91SS+44d,92SS+44d,1484FF | As Soon As Possible | NA | 137 | 0d | September 6, 2022 8:00 AM | March 24, 2023 5:00 PM | 137 days | No | 9/6/22 | 3/24/23 | NA | 1
5000 | M3: Readiness for User Feedback | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM |  |  | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
5001 | M3: B1: 01.04 Send to Selected Pathway (CARESV1-75) | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 87SS+44d | 90 | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
5002 | M3: B2: 01.02 Conduct Hotline (SDM) Assessment (CARESV1-85) | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 87SS+44d,89 | 91 | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
5003 | M3: B3: 01.01 Gather Person and Allegation Information determine decision (r1) (CARESV1-86) | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 87SS+44d,90 | 92 | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
5004 | M3: B4: 01.03 Supervisor dashboard, assess information, confirm responses - Screening (r2) (CARESV1-88) | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 87SS+44d,91 | 94SS,95SS,96SS,97SS | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
5005 | M3: User Feedback | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM |  |  | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
5006 | M3: B1: 01.04 Send to Selected Pathway (CARESV1-75) | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 92SS | 95 | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
5007 | M3: B2: 01.02 Conduct Hotline (SDM) Assessment (CARESV1-85) | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 92SS,94 | 96 | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
5008 | M3: B3: 01.01 Gather Person and Allegation Information determine decision (r1) (CARESV1-86) | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 92SS,95 | 97 | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
5009 | M3: B4: 01.03 Supervisor dashboard, assess information, confirm responses - Screening (r2) (CARESV1-88) | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 92SS,96 | 98FS+14d | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
5010 | Milestone 3 (Screening) Jira # CARES V1-524 Complete | March 17, 2023 8:00 AM | March 17, 2023 8:00 AM | 97FS+14d | 1484 | As Soon As Possible | NA | 0 | 0d | March 17, 2023 8:00 AM | March 17, 2023 8:00 AM | 0 days | Yes | 3/17/23 | 3/17/23 | NA | 1
5051 | Milestone 04: Investigations: Engagement (CARESV1-527) | June 1, 2022 8:00 AM | July 25, 2023 5:00 PM |  |  | As Soon As Possible | NA | 288 | 0d | June 1, 2022 8:00 AM | July 25, 2023 5:00 PM | 288 days | No | 6/1/22 | 7/25/23 | NA | 1
5052 | M4: Research & Context Setting | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM | 41 days | No | 6/1/22 | 7/28/22 | NA | 1
5053 | M4: RC: Finalize Value Hypothesis | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM |  | 102SS,103SS,104SS,105SS,106SS,107SS,108SS | As Soon As Possible | NA | 41 | 0d | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM | 41 days | No | 6/1/22 | 7/28/22 | NA | 1
5054 | M4: RC: Draft Service Maps | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM | 101SS | 103 | As Soon As Possible | NA | 41 | 0d | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM | 41 days | No | 6/1/22 | 7/28/22 | NA | 1
5055 | M4: RC: Complete Legacy Analysis | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM | 101SS,102 | 104 | As Soon As Possible | NA | 41 | 0d | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM | 41 days | No | 6/1/22 | 7/28/22 | NA | 1
5056 | M4: RC: Finalize Epics | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM | 101SS,103 | 105 | As Soon As Possible | NA | 41 | 0d | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM | 41 days | No | 6/1/22 | 7/28/22 | NA | 1
5057 | M4: RC: Complete conceptual and epic-level Domain Model diagrams | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM | 101SS,104 | 106 | As Soon As Possible | NA | 41 | 0d | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM | 41 days | No | 6/1/22 | 7/28/22 | NA | 1
5058 | M4: RC: Define User Story titles | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM | 101SS,105 | 107 | As Soon As Possible | NA | 41 | 0d | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM | 41 days | No | 6/1/22 | 7/28/22 | NA | 1
5059 | M4: RC: Complete External Systems pre-analysis | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM | 101SS,106 | 108 | As Soon As Possible | NA | 41 | 0d | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM | 41 days | No | 6/1/22 | 7/28/22 | NA | 1
5060 | M4: RC: Facilitate Inception | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM | 101SS,107 | 110FS+3d,111FS+3d,112FS+3d,113FS+3d | As Soon As Possible | NA | 41 | 0d | June 1, 2022 8:00 AM | July 28, 2022 5:00 PM | 41 days | No | 6/1/22 | 7/28/22 | NA | 1
5061 | M4: BRC | August 3, 2022 8:00 AM | November 15, 2022 5:00 PM |  |  | As Soon As Possible | NA | 73 | 0d | August 3, 2022 8:00 AM | November 15, 2022 5:00 PM | 73 days | No | 8/3/22 | 11/15/22 | NA | 1
5062 | M4: B1: 02.08 Associate Referrals (CARESV1-4) | August 3, 2022 8:00 AM | November 15, 2022 5:00 PM | 108FS+3d | 111 | As Soon As Possible | NA | 73 | 0d | August 3, 2022 8:00 AM | November 15, 2022 5:00 PM | 73 days | No | 8/3/22 | 11/15/22 | NA | 1
5063 | M4: B2: 01.05 Assign Referral to Worker-Investigator (r1) (CARESV1-80) | August 3, 2022 8:00 AM | November 15, 2022 5:00 PM | 108FS+3d,110 | 112 | As Soon As Possible | NA | 73 | 0d | August 3, 2022 8:00 AM | November 15, 2022 5:00 PM | 73 days | No | 8/3/22 | 11/15/22 | NA | 1
5064 | M4: B3: 02.02 Conducting Interview (CARESV1-82) | August 3, 2022 8:00 AM | November 15, 2022 5:00 PM | 108FS+3d,111 | 113 | As Soon As Possible | NA | 73 | 0d | August 3, 2022 8:00 AM | November 15, 2022 5:00 PM | 73 days | No | 8/3/22 | 11/15/22 | NA | 1
5065 | M4: B4: 02.01 Prepare for Interview (CARESV1-83) | August 3, 2022 8:00 AM | November 15, 2022 5:00 PM | 108FS+3d,112 | 115FS-28d,116FS-28d,117FS-28d,118FS-28d | As Soon As Possible | NA | 73 | 0d | August 3, 2022 8:00 AM | November 15, 2022 5:00 PM | 73 days | No | 8/3/22 | 11/15/22 | NA | 1
5066 | M4: Design | October 6, 2022 8:00 AM | May 24, 2023 5:00 PM |  |  | As Soon As Possible | NA | 157 | 0d | October 6, 2022 8:00 AM | May 24, 2023 5:00 PM | 157 days | No | 10/6/22 | 5/24/23 | NA | 1
5067 | M4: B1: 02.08 Associate Referrals (CARESV1-4) | October 6, 2022 8:00 AM | May 24, 2023 5:00 PM | 113FS-28d | 116 | As Soon As Possible | NA | 157 | 0d | October 6, 2022 8:00 AM | May 24, 2023 5:00 PM | 157 days | No | 10/6/22 | 5/24/23 | NA | 1
5068 | M4: B2: 01.05 Assign Referral to Worker-Investigator (r1) (CARESV1-80) | October 6, 2022 8:00 AM | May 24, 2023 5:00 PM | 113FS-28d,115 | 117 | As Soon As Possible | NA | 157 | 0d | October 6, 2022 8:00 AM | May 24, 2023 5:00 PM | 157 days | No | 10/6/22 | 5/24/23 | NA | 1
5069 | M4: B3: 02.02 Conducting Interview (CARESV1-82) | October 6, 2022 8:00 AM | May 24, 2023 5:00 PM | 113FS-28d,116 | 118 | As Soon As Possible | NA | 157 | 0d | October 6, 2022 8:00 AM | May 24, 2023 5:00 PM | 157 days | No | 10/6/22 | 5/24/23 | NA | 1
5070 | M4: B4: 02.01 Prepare for Interview (CARESV1-83) | October 6, 2022 8:00 AM | May 24, 2023 5:00 PM | 113FS-28d,117 | 120SS+22d,121SS+22d,122SS+22d,123SS+22d,2234 | As Soon As Possible | NA | 157 | 0d | October 6, 2022 8:00 AM | May 24, 2023 5:00 PM | 157 days | No | 10/6/22 | 5/24/23 | NA | 1
5071 | M4: Build | November 7, 2022 8:00 AM | June 29, 2023 5:00 PM |  | 2985 | As Soon As Possible | NA | 160 | 0d | November 7, 2022 8:00 AM | June 29, 2023 5:00 PM | 160 days | No | 11/7/22 | 6/29/23 | NA | 1
5072 | M4: B1: 02.08 Associate Referrals (CARESV1-4) | November 7, 2022 8:00 AM | June 29, 2023 5:00 PM | 118SS+22d | 121 | As Soon As Possible | NA | 160 | 0d | November 7, 2022 8:00 AM | June 29, 2023 5:00 PM | 160 days | No | 11/7/22 | 6/29/23 | NA | 1
5073 | M4: B2: 01.05 Assign Referral to Worker-Investigator (r1) (CARESV1-80) | November 7, 2022 8:00 AM | June 29, 2023 5:00 PM | 118SS+22d,120 | 122 | As Soon As Possible | NA | 160 | 0d | November 7, 2022 8:00 AM | June 29, 2023 5:00 PM | 160 days | No | 11/7/22 | 6/29/23 | NA | 1
5074 | M4: B3: 02.02 Conducting Interview (CARESV1-82) | November 7, 2022 8:00 AM | June 29, 2023 5:00 PM | 118SS+22d,121 | 123 | As Soon As Possible | NA | 160 | 0d | November 7, 2022 8:00 AM | June 29, 2023 5:00 PM | 160 days | No | 11/7/22 | 6/29/23 | NA | 1
5075 | M4: B4: 02.01 Prepare for Interview (CARESV1-83) | November 7, 2022 8:00 AM | June 29, 2023 5:00 PM | 118SS+22d,122 | 125SS,126SS,127SS,128SS | As Soon As Possible | NA | 160 | 0d | November 7, 2022 8:00 AM | June 29, 2023 5:00 PM | 160 days | No | 11/7/22 | 6/29/23 | NA | 1
5076 | M4: SIT | November 7, 2022 8:00 AM | July 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 165 | 0d | November 7, 2022 8:00 AM | July 7, 2023 5:00 PM | 165 days | No | 11/7/22 | 7/7/23 | NA | 1
5077 | M4: B1: 02.08 Associate Referrals (CARESV1-4) | November 7, 2022 8:00 AM | July 7, 2023 5:00 PM | 123SS | 126 | As Soon As Possible | NA | 165 | 0d | November 7, 2022 8:00 AM | July 7, 2023 5:00 PM | 165 days | No | 11/7/22 | 7/7/23 | NA | 1
5078 | M4: B2: 01.05 Assign Referral to Worker-Investigator (r1) (CARESV1-80) | November 7, 2022 8:00 AM | July 7, 2023 5:00 PM | 123SS,125 | 127 | As Soon As Possible | NA | 165 | 0d | November 7, 2022 8:00 AM | July 7, 2023 5:00 PM | 165 days | No | 11/7/22 | 7/7/23 | NA | 1
5079 | M4: B3: 02.02 Conducting Interview (CARESV1-82) | November 7, 2022 8:00 AM | July 7, 2023 5:00 PM | 123SS,126 | 128 | As Soon As Possible | NA | 165 | 0d | November 7, 2022 8:00 AM | July 7, 2023 5:00 PM | 165 days | No | 11/7/22 | 7/7/23 | NA | 1
5080 | M4: B4: 02.01 Prepare for Interview (CARESV1-83) | November 7, 2022 8:00 AM | July 7, 2023 5:00 PM | 123SS,127,1241SS | 130SS+17d,131SS+17d,132SS+17d,133SS+17d | As Soon As Possible | NA | 165 | 0d | November 7, 2022 8:00 AM | July 7, 2023 5:00 PM | 165 days | No | 11/7/22 | 7/7/23 | NA | 1
5081 | M4: QA | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM |  |  | As Soon As Possible | NA | 160 | 0d | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 160 days | No | 12/5/22 | 7/25/23 | NA | 1
5082 | M4: B1: 02.08 Associate Referrals (CARESV1-4) | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 128SS+17d | 131 | As Soon As Possible | NA | 160 | 0d | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 160 days | No | 12/5/22 | 7/25/23 | NA | 1
5083 | M4: B2: 01.05 Assign Referral to Worker-Investigator (r1) (CARESV1-80) | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 128SS+17d,130 | 132 | As Soon As Possible | NA | 160 | 0d | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 160 days | No | 12/5/22 | 7/25/23 | NA | 1
5084 | M4: B3: 02.02 Conducting Interview (CARESV1-82) | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 128SS+17d,131 | 133 | As Soon As Possible | NA | 160 | 0d | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 160 days | No | 12/5/22 | 7/25/23 | NA | 1
5011 | M4: B4: 02.01 Prepare for Interview (CARESV1-83) | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 128SS+17d,132 | 135SS,136SS,137SS,138SS,1484FF | As Soon As Possible | NA | 160 | 0d | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 160 days | No | 12/5/22 | 7/25/23 | NA | 1
5012 | M4: Readiness for User Feedback | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM |  |  | As Soon As Possible | NA | 160 | 0d | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 160 days | No | 12/5/22 | 7/25/23 | NA | 1
5013 | M4: B1: 02.08 Associate Referrals (CARESV1-4) | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 133SS | 136 | As Soon As Possible | NA | 160 | 0d | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 160 days | No | 12/5/22 | 7/25/23 | NA | 1
5014 | M4: B2: 01.05 Assign Referral to Worker-Investigator (r1) (CARESV1-80) | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 133SS,135 | 137 | As Soon As Possible | NA | 160 | 0d | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 160 days | No | 12/5/22 | 7/25/23 | NA | 1
5015 | M4: B3: 02.02 Conducting Interview (CARESV1-82) | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 133SS,136 | 138 | As Soon As Possible | NA | 160 | 0d | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 160 days | No | 12/5/22 | 7/25/23 | NA | 1
5016 | M4: B4: 02.01 Prepare for Interview (CARESV1-83) | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 133SS,137 | 140SS,141SS,142SS,143SS | As Soon As Possible | NA | 160 | 0d | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 160 days | No | 12/5/22 | 7/25/23 | NA | 1
5017 | M4: User Feedback | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM |  |  | As Soon As Possible | NA | 160 | 0d | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 160 days | No | 12/5/22 | 7/25/23 | NA | 1
5018 | M4: B1: 02.08 Associate Referrals (CARESV1-4) | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 138SS | 141 | As Soon As Possible | NA | 160 | 0d | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 160 days | No | 12/5/22 | 7/25/23 | NA | 1
5019 | M4: B2: 01.05 Assign Referral to Worker-Investigator (r1) (CARESV1-80) | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 138SS,140 | 142 | As Soon As Possible | NA | 160 | 0d | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 160 days | No | 12/5/22 | 7/25/23 | NA | 1
5020 | M4: B3: 02.02 Conducting Interview (CARESV1-82) | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 138SS,141 | 143 | As Soon As Possible | NA | 160 | 0d | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 160 days | No | 12/5/22 | 7/25/23 | NA | 1
5021 | M4: B4: 02.01 Prepare for Interview (CARESV1-83) | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 138SS,142 | 144FF | As Soon As Possible | NA | 160 | 0d | December 5, 2022 8:00 AM | July 25, 2023 5:00 PM | 160 days | No | 12/5/22 | 7/25/23 | NA | 1
4948 | Milestone 4 (Investigations: Engagement) Jira # CARES V1-527 Complete | July 25, 2023 5:00 PM | July 25, 2023 5:00 PM | 143FF | 1484 | As Soon As Possible | NA | 0 | 0d | July 25, 2023 5:00 PM | July 25, 2023 5:00 PM | 0 days | Yes | 7/25/23 | 7/25/23 | NA | 1
5416 | Milestone 05: Investigations: Determination (CARESV1-519) | July 18, 2022 8:00 AM | August 17, 2023 5:00 PM |  |  | As Soon As Possible | NA | 273 | 0d | July 18, 2022 8:00 AM | August 17, 2023 5:00 PM | 273 days | No | 7/18/22 | 8/17/23 | NA | 1
5417 | M5: Research & Context Setting | July 18, 2022 8:00 AM | September 12, 2022 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | July 18, 2022 8:00 AM | September 12, 2022 5:00 PM | 40 days | No | 7/18/22 | 9/12/22 | NA | 1
5418 | M5: RC: Finalize Value Hypothesis | July 18, 2022 8:00 AM | July 29, 2022 5:00 PM |  | 148 | As Soon As Possible | NA | 10 | 0d | July 18, 2022 8:00 AM | July 29, 2022 5:00 PM | 10 days | No | 7/18/22 | 7/29/22 | NA | 1
5419 | M5: RC: Draft Service Maps | August 1, 2022 8:00 AM | August 12, 2022 5:00 PM | 147 | 149 | As Soon As Possible | NA | 10 | 0d | August 1, 2022 8:00 AM | August 12, 2022 5:00 PM | 10 days | No | 8/1/22 | 8/12/22 | NA | 1
5420 | M5: RC: Complete Legacy Analysis | August 15, 2022 8:00 AM | August 19, 2022 5:00 PM | 148 | 150 | As Soon As Possible | NA | 5 | 0d | August 15, 2022 8:00 AM | August 19, 2022 5:00 PM | 5 days | No | 8/15/22 | 8/19/22 | NA | 1
5421 | M5: RC: Finalize Epics | August 22, 2022 8:00 AM | September 2, 2022 5:00 PM | 149,1216 | 151SS-25d | As Soon As Possible | NA | 10 | 0d | August 22, 2022 8:00 AM | September 2, 2022 5:00 PM | 10 days | No | 8/22/22 | 9/2/22 | NA | 1
5422 | M5: RC: Complete conceptual and epic-level Domain Model diagrams | July 18, 2022 8:00 AM | July 29, 2022 5:00 PM | 150SS-25d | 152 | As Soon As Possible | NA | 10 | 0d | July 18, 2022 8:00 AM | July 29, 2022 5:00 PM | 10 days | No | 7/18/22 | 7/29/22 | NA | 1
5423 | M5: RC: Define User Story titles | August 1, 2022 8:00 AM | August 12, 2022 5:00 PM | 151 | 153 | As Soon As Possible | NA | 10 | 0d | August 1, 2022 8:00 AM | August 12, 2022 5:00 PM | 10 days | No | 8/1/22 | 8/12/22 | NA | 1
5424 | M5: RC: Complete External Systems pre-analysis | August 15, 2022 8:00 AM | August 26, 2022 5:00 PM | 152 | 154 | As Soon As Possible | NA | 10 | 0d | August 15, 2022 8:00 AM | August 26, 2022 5:00 PM | 10 days | No | 8/15/22 | 8/26/22 | NA | 1
5425 | M5: RC: Facilitate Inception | August 29, 2022 8:00 AM | September 12, 2022 5:00 PM | 153 | 156FS-1d,157FS-1d,158FS-1d,159FS-1d,160FS-1d,161FS-1d,2485SS+15d | As Soon As Possible | NA | 10 | 0d | August 29, 2022 8:00 AM | September 12, 2022 5:00 PM | 10 days | No | 8/29/22 | 9/12/22 | NA | 1
5426 | M5: BRC | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 40 days | No | 9/12/22 | 11/4/22 | NA | 1
5427 | M5: B1: 02.03 SDM Risk& Safety Assessments (CARESV1-79) | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 154FS-1d | 157 | As Soon As Possible | NA | 40 | 0d | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 40 days | No | 9/12/22 | 11/4/22 | NA | 1
5428 | M5: B2: 02.05 Determine Investigation Disposition (CARESV1-91) | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 154FS-1d,156 | 158 | As Soon As Possible | NA | 40 | 0d | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 40 days | No | 9/12/22 | 11/4/22 | NA | 1
5429 | M5: B3: 02.04 Determine Allegation Conclusion (CARESV1-92) | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 154FS-1d,157 | 159 | As Soon As Possible | NA | 40 | 0d | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 40 days | No | 9/12/22 | 11/4/22 | NA | 1
5430 | M5: B4: 02.06 Create and Send Cross Reports (CARESV1-107) | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 154FS-1d,158 | 160 | As Soon As Possible | NA | 40 | 0d | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 40 days | No | 9/12/22 | 11/4/22 | NA | 1
5431 | M5: B5: 02.07 Conduct Supervisor Review and Approval-(Investigation) (r3) (CARESV1-135) | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 154FS-1d,159 | 161 | As Soon As Possible | NA | 40 | 0d | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 40 days | No | 9/12/22 | 11/4/22 | NA | 1
5432 | M5: B6: Foundational Services (F3) - Data Conversion - CWS/CMS (CARESV1-4955) | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 154FS-1d,160 | 163SS+20d,164SS+20d,165SS+20d,166SS+20d,167SS+20d,168SS+20d | As Soon As Possible | NA | 40 | 0d | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 40 days | No | 9/12/22 | 11/4/22 | NA | 1
5433 | M5: Design | October 10, 2022 8:00 AM | December 7, 2022 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | October 10, 2022 8:00 AM | December 7, 2022 5:00 PM | 40 days | No | 10/10/22 | 12/7/22 | NA | 1
5434 | M5: B1: 02.03 SDM Risk& Safety Assessments (CARESV1-79) | October 10, 2022 8:00 AM | December 7, 2022 5:00 PM | 161SS+20d,2108 | 164 | As Soon As Possible | NA | 40 | 0d | October 10, 2022 8:00 AM | December 7, 2022 5:00 PM | 40 days | No | 10/10/22 | 12/7/22 | NA | 1
5435 | M5: B2: 02.05 Determine Investigation Disposition (CARESV1-91) | October 10, 2022 8:00 AM | December 7, 2022 5:00 PM | 161SS+20d,163 | 165 | As Soon As Possible | NA | 40 | 0d | October 10, 2022 8:00 AM | December 7, 2022 5:00 PM | 40 days | No | 10/10/22 | 12/7/22 | NA | 1
5436 | M5: B3: 02.04 Determine Allegation Conclusion (CARESV1-92) | October 10, 2022 8:00 AM | December 7, 2022 5:00 PM | 161SS+20d,164 | 166 | As Soon As Possible | NA | 40 | 0d | October 10, 2022 8:00 AM | December 7, 2022 5:00 PM | 40 days | No | 10/10/22 | 12/7/22 | NA | 1
5437 | M5: B4: 02.06 Create and Send Cross Reports (CARESV1-107) | October 10, 2022 8:00 AM | December 7, 2022 5:00 PM | 161SS+20d,165 | 167 | As Soon As Possible | NA | 40 | 0d | October 10, 2022 8:00 AM | December 7, 2022 5:00 PM | 40 days | No | 10/10/22 | 12/7/22 | NA | 1
5438 | M5: B5: 02.07 Conduct Supervisor Review and Approval-(Investigation) (r3) (CARESV1-135) | October 10, 2022 8:00 AM | December 7, 2022 5:00 PM | 161SS+20d,166 | 168 | As Soon As Possible | NA | 40 | 0d | October 10, 2022 8:00 AM | December 7, 2022 5:00 PM | 40 days | No | 10/10/22 | 12/7/22 | NA | 1
5439 | M5: B6: Foundational Services (F3) - Data Conversion - CWS/CMS (CARESV1-4955) | October 10, 2022 8:00 AM | December 7, 2022 5:00 PM | 161SS+20d,167 | 170FS+16d,171FS+16d,172FS+16d,173FS+16d,174FS+16d,175FS+16d,2238 | As Soon As Possible | NA | 40 | 0d | October 10, 2022 8:00 AM | December 7, 2022 5:00 PM | 40 days | No | 10/10/22 | 12/7/22 | NA | 1
5440 | M5: Build | January 3, 2023 8:00 AM | July 21, 2023 5:00 PM |  | 2986 | As Soon As Possible | NA | 139 | 0d | January 3, 2023 8:00 AM | July 21, 2023 5:00 PM | 139 days | No | 1/3/23 | 7/21/23 | NA | 1
5441 | M5: B1: 02.03 SDM Risk& Safety Assessments (CARESV1-79) | January 3, 2023 8:00 AM | July 21, 2023 5:00 PM | 168FS+16d | 171 | As Soon As Possible | NA | 139 | 0d | January 3, 2023 8:00 AM | July 21, 2023 5:00 PM | 139 days | No | 1/3/23 | 7/21/23 | NA | 1
5442 | M5: B2: 02.05 Determine Investigation Disposition (CARESV1-91) | January 3, 2023 8:00 AM | July 21, 2023 5:00 PM | 168FS+16d,170 | 172 | As Soon As Possible | NA | 139 | 0d | January 3, 2023 8:00 AM | July 21, 2023 5:00 PM | 139 days | No | 1/3/23 | 7/21/23 | NA | 1
5443 | M5: B3: 02.04 Determine Allegation Conclusion (CARESV1-92) | January 3, 2023 8:00 AM | July 21, 2023 5:00 PM | 168FS+16d,171 | 173 | As Soon As Possible | NA | 139 | 0d | January 3, 2023 8:00 AM | July 21, 2023 5:00 PM | 139 days | No | 1/3/23 | 7/21/23 | NA | 1
5444 | M5: B4: 02.06 Create and Send Cross Reports (CARESV1-107) | January 3, 2023 8:00 AM | July 21, 2023 5:00 PM | 168FS+16d,172 | 174 | As Soon As Possible | NA | 139 | 0d | January 3, 2023 8:00 AM | July 21, 2023 5:00 PM | 139 days | No | 1/3/23 | 7/21/23 | NA | 1
5445 | M5: B5: 02.07 Conduct Supervisor Review and Approval-(Investigation) (r3) (CARESV1-135) | January 3, 2023 8:00 AM | July 21, 2023 5:00 PM | 168FS+16d,173 | 175 | As Soon As Possible | NA | 139 | 0d | January 3, 2023 8:00 AM | July 21, 2023 5:00 PM | 139 days | No | 1/3/23 | 7/21/23 | NA | 1
5446 | M5: B6: Foundational Services (F3) - Data Conversion - CWS/CMS (CARESV1-4955) | January 3, 2023 8:00 AM | July 21, 2023 5:00 PM | 168FS+16d,174 | 177SS,178SS,179SS,180SS,181SS,182SS | As Soon As Possible | NA | 139 | 0d | January 3, 2023 8:00 AM | July 21, 2023 5:00 PM | 139 days | No | 1/3/23 | 7/21/23 | NA | 1
5447 | M5: SIT | January 3, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 144 | 0d | January 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 144 days | No | 1/3/23 | 7/28/23 | NA | 1
5448 | M5: B1: 02.03 SDM Risk& Safety Assessments (CARESV1-79) | January 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 175SS | 178 | As Soon As Possible | NA | 144 | 0d | January 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 144 days | No | 1/3/23 | 7/28/23 | NA | 1
5449 | M5: B2: 02.05 Determine Investigation Disposition (CARESV1-91) | January 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 175SS,177 | 179 | As Soon As Possible | NA | 144 | 0d | January 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 144 days | No | 1/3/23 | 7/28/23 | NA | 1
5450 | M5: B3: 02.04 Determine Allegation Conclusion (CARESV1-92) | January 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 175SS,178 | 180 | As Soon As Possible | NA | 144 | 0d | January 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 144 days | No | 1/3/23 | 7/28/23 | NA | 1
5451 | M5: B4: 02.06 Create and Send Cross Reports (CARESV1-107) | January 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 175SS,179 | 181 | As Soon As Possible | NA | 144 | 0d | January 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 144 days | No | 1/3/23 | 7/28/23 | NA | 1
5452 | M5: B5: 02.07 Conduct Supervisor Review and Approval-(Investigation) (r3) (CARESV1-135) | January 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 175SS,180 | 182 | As Soon As Possible | NA | 144 | 0d | January 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 144 days | No | 1/3/23 | 7/28/23 | NA | 1
5453 | M5: B6: Foundational Services (F3) - Data Conversion - CWS/CMS (CARESV1-4955) | January 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 175SS,181 | 184SS+12d,185SS+12d,186SS+12d,187SS+12d,188SS+12d,189SS+12d | As Soon As Possible | NA | 144 | 0d | January 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 144 days | No | 1/3/23 | 7/28/23 | NA | 1
5454 | M5: QA | January 20, 2023 8:00 AM | August 17, 2023 5:00 PM |  |  | As Soon As Possible | NA | 146 | 0d | January 20, 2023 8:00 AM | August 17, 2023 5:00 PM | 146 days | No | 1/20/23 | 8/17/23 | NA | 1
5455 | M5: B1: 02.03 SDM Risk& Safety Assessments (CARESV1-79) | January 20, 2023 8:00 AM | August 17, 2023 5:00 PM | 182SS+12d | 185 | As Soon As Possible | NA | 146 | 0d | January 20, 2023 8:00 AM | August 17, 2023 5:00 PM | 146 days | No | 1/20/23 | 8/17/23 | NA | 1
5456 | M5: B2: 02.05 Determine Investigation Disposition (CARESV1-91) | January 20, 2023 8:00 AM | August 17, 2023 5:00 PM | 182SS+12d,184 | 186 | As Soon As Possible | NA | 146 | 0d | January 20, 2023 8:00 AM | August 17, 2023 5:00 PM | 146 days | No | 1/20/23 | 8/17/23 | NA | 1
5457 | M5: B3: 02.04 Determine Allegation Conclusion (CARESV1-92) | January 20, 2023 8:00 AM | August 17, 2023 5:00 PM | 182SS+12d,185 | 187 | As Soon As Possible | NA | 146 | 0d | January 20, 2023 8:00 AM | August 17, 2023 5:00 PM | 146 days | No | 1/20/23 | 8/17/23 | NA | 1
5458 | M5: B4: 02.06 Create and Send Cross Reports (CARESV1-107) | January 20, 2023 8:00 AM | August 17, 2023 5:00 PM | 182SS+12d,186 | 188 | As Soon As Possible | NA | 146 | 0d | January 20, 2023 8:00 AM | August 17, 2023 5:00 PM | 146 days | No | 1/20/23 | 8/17/23 | NA | 1
5459 | M5: B5: 02.07 Conduct Supervisor Review and Approval-(Investigation) (r3) (CARESV1-135) | January 20, 2023 8:00 AM | August 17, 2023 5:00 PM | 182SS+12d,187 | 189 | As Soon As Possible | NA | 146 | 0d | January 20, 2023 8:00 AM | August 17, 2023 5:00 PM | 146 days | No | 1/20/23 | 8/17/23 | NA | 1
5460 | M5: B6: Foundational Services (F3) - Data Conversion - CWS/CMS (CARESV1-4955) | January 20, 2023 8:00 AM | August 17, 2023 5:00 PM | 182SS+12d,188 | 191SS+6d,192SS+6d,193SS+6d,194SS+6d,195SS+6d,196SS+6d,1484FF | As Soon As Possible | NA | 146 | 0d | January 20, 2023 8:00 AM | August 17, 2023 5:00 PM | 146 days | No | 1/20/23 | 8/17/23 | NA | 1
5461 | M5: Readiness for User Feedback | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM |  |  | As Soon As Possible | NA | 120 | 0d | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 120 days | No | 1/30/23 | 7/20/23 | NA | 1
5462 | M5: B1: 02.03 SDM Risk& Safety Assessments (CARESV1-79) | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 189SS+6d | 192 | As Soon As Possible | NA | 120 | 0d | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 120 days | No | 1/30/23 | 7/20/23 | NA | 1
5463 | M5: B2: 02.05 Determine Investigation Disposition (CARESV1-91) | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 189SS+6d,191 | 193 | As Soon As Possible | NA | 120 | 0d | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 120 days | No | 1/30/23 | 7/20/23 | NA | 1
5464 | M5: B3: 02.04 Determine Allegation Conclusion (CARESV1-92) | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 189SS+6d,192 | 194 | As Soon As Possible | NA | 120 | 0d | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 120 days | No | 1/30/23 | 7/20/23 | NA | 1
5465 | M5: B4: 02.06 Create and Send Cross Reports (CARESV1-107) | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 189SS+6d,193 | 195 | As Soon As Possible | NA | 120 | 0d | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 120 days | No | 1/30/23 | 7/20/23 | NA | 1
5466 | M5: B5: 02.07 Conduct Supervisor Review and Approval-(Investigation) (r3) (CARESV1-135) | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 189SS+6d,194 | 196 | As Soon As Possible | NA | 120 | 0d | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 120 days | No | 1/30/23 | 7/20/23 | NA | 1
5467 | M5: B6: Foundational Services (F3) - Data Conversion - CWS/CMS (CARESV1-4955) | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 189SS+6d,195 | 198SS,199SS,200SS,201SS,202SS,203SS | As Soon As Possible | NA | 120 | 0d | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 120 days | No | 1/30/23 | 7/20/23 | NA | 1
5468 | M5: User Feedback | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM |  |  | As Soon As Possible | NA | 120 | 0d | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 120 days | No | 1/30/23 | 7/20/23 | NA | 1
5469 | M5: B1: 02.03 SDM Risk& Safety Assessments (CARESV1-79) | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 196SS | 199 | As Soon As Possible | NA | 120 | 0d | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 120 days | No | 1/30/23 | 7/20/23 | NA | 1
5470 | M5: B2: 02.05 Determine Investigation Disposition (CARESV1-91) | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 196SS,198 | 200 | As Soon As Possible | NA | 120 | 0d | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 120 days | No | 1/30/23 | 7/20/23 | NA | 1
5471 | M5: B3: 02.04 Determine Allegation Conclusion (CARESV1-92) | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 196SS,199 | 201 | As Soon As Possible | NA | 120 | 0d | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 120 days | No | 1/30/23 | 7/20/23 | NA | 1
5472 | M5: B4: 02.06 Create and Send Cross Reports (CARESV1-107) | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 196SS,200 | 202 | As Soon As Possible | NA | 120 | 0d | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 120 days | No | 1/30/23 | 7/20/23 | NA | 1
5473 | M5: B5: 02.07 Conduct Supervisor Review and Approval-(Investigation) (r3) (CARESV1-135) | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 196SS,201 | 203 | As Soon As Possible | NA | 120 | 0d | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 120 days | No | 1/30/23 | 7/20/23 | NA | 1
5474 | M5: B6: Foundational Services (F3) - Data Conversion - CWS/CMS (CARESV1-4955) | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 196SS,202 | 204FF | As Soon As Possible | NA | 120 | 0d | January 30, 2023 8:00 AM | July 20, 2023 5:00 PM | 120 days | No | 1/30/23 | 7/20/23 | NA | 1
5475 | Milestone 5 (Investigations: Determination) Jira # CARES V1-519 Complete | July 20, 2023 5:00 PM | July 20, 2023 5:00 PM | 203FF | 1484 | As Soon As Possible | NA | 0 | 0d | July 20, 2023 5:00 PM | July 20, 2023 5:00 PM | 0 days | Yes | 7/20/23 | 7/20/23 | NA | 1
5085 | Milestone 06: Case Management: Engagement (CARESV1-520) | July 18, 2022 8:00 AM | December 11, 2023 5:00 PM |  |  | As Soon As Possible | NA | 351 | 0d | July 18, 2022 8:00 AM | December 11, 2023 5:00 PM | 351 days | No | 7/18/22 | 12/11/23 | NA | 1
5086 | M6: Research & Context Setting | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM |  |  | As Soon As Possible | NA | 75 | 0d | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM | 75 days | No | 7/18/22 | 10/31/22 | NA | 1
5087 | M6: RC: Finalize Value Hypothesis | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM |  | 208SS,209SS,210SS,211SS,212SS,213SS,214SS | As Soon As Possible | NA | 75 | 0d | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM | 75 days | No | 7/18/22 | 10/31/22 | NA | 1
5088 | M6: RC: Draft Service Maps | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM | 207SS | 209 | As Soon As Possible | NA | 75 | 0d | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM | 75 days | No | 7/18/22 | 10/31/22 | NA | 1
5089 | M6: RC: Complete Legacy Analysis | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM | 207SS,208 | 210 | As Soon As Possible | NA | 75 | 0d | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM | 75 days | No | 7/18/22 | 10/31/22 | NA | 1
5090 | M6: RC: Finalize Epics | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM | 207SS,209 | 211 | As Soon As Possible | NA | 75 | 0d | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM | 75 days | No | 7/18/22 | 10/31/22 | NA | 1
5119 | M6: RC: Complete conceptual and epic-level Domain Model diagrams | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM | 207SS,210 | 212 | As Soon As Possible | NA | 75 | 0d | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM | 75 days | No | 7/18/22 | 10/31/22 | NA | 1
5120 | M6: RC: Define User Story titles | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM | 207SS,211 | 213 | As Soon As Possible | NA | 75 | 0d | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM | 75 days | No | 7/18/22 | 10/31/22 | NA | 1
5121 | M6: RC: Complete External Systems pre-analysis | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM | 207SS,212 | 214 | As Soon As Possible | NA | 75 | 0d | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM | 75 days | No | 7/18/22 | 10/31/22 | NA | 1
5122 | M6: RC: Facilitate Inception | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM | 207SS,213 | 216FS-5d,217FS-5d,218FS-5d,219FS-5d,2492SS+55d | As Soon As Possible | NA | 75 | 0d | July 18, 2022 8:00 AM | October 31, 2022 5:00 PM | 75 days | No | 7/18/22 | 10/31/22 | NA | 1
5123 | M6: BRC | October 25, 2022 8:00 AM | April 12, 2023 5:00 PM |  |  | As Soon As Possible | NA | 114 | 0d | October 25, 2022 8:00 AM | April 12, 2023 5:00 PM | 114 days | No | 10/25/22 | 4/12/23 | NA | 1
5124 | M6: B1: 05.01 Create or Update Person Profile (CARESV1-20) | October 25, 2022 8:00 AM | April 12, 2023 5:00 PM | 214FS-5d | 217 | As Soon As Possible | NA | 114 | 0d | October 25, 2022 8:00 AM | April 12, 2023 5:00 PM | 114 days | No | 10/25/22 | 4/12/23 | NA | 1
5125 | M6: B2: 04.01 Open and Assign Case (CARESV1-57) | October 25, 2022 8:00 AM | March 30, 2023 5:00 PM | 214FS-5d,216 | 218 | As Soon As Possible | NA | 106 | 0d | October 25, 2022 8:00 AM | March 30, 2023 5:00 PM | 106 days | No | 10/25/22 | 3/30/23 | NA | 1
5126 | M6: B3: 05.11 Conduct In-Person Contact Visit (CARESV1-58) | October 25, 2022 8:00 AM | March 30, 2023 5:00 PM | 214FS-5d,217 | 219 | As Soon As Possible | NA | 106 | 0d | October 25, 2022 8:00 AM | March 30, 2023 5:00 PM | 106 days | No | 10/25/22 | 3/30/23 | NA | 1
5127 | M6: B4: 04.02 Conduct Supervisor Review and Approval (r1) (CARESV1-60) | October 25, 2022 8:00 AM | March 30, 2023 5:00 PM | 214FS-5d,218 | 221FS-39d,222FS-39d,223FS-39d,224FS-39d | As Soon As Possible | NA | 106 | 0d | October 25, 2022 8:00 AM | March 30, 2023 5:00 PM | 106 days | No | 10/25/22 | 3/30/23 | NA | 1
5128 | M6: Design | February 3, 2023 8:00 AM | June 21, 2023 5:00 PM |  |  | As Soon As Possible | NA | 96 | 0d | February 3, 2023 8:00 AM | June 21, 2023 5:00 PM | 96 days | No | 2/3/23 | 6/21/23 | NA | 1
5129 | M6: B1: 05.01 Create or Update Person Profile (CARESV1-20) | February 3, 2023 8:00 AM | June 21, 2023 5:00 PM | 219FS-39d | 222 | As Soon As Possible | NA | 96 | 0d | February 3, 2023 8:00 AM | June 21, 2023 5:00 PM | 96 days | No | 2/3/23 | 6/21/23 | NA | 1
5130 | M6: B2: 04.01 Open and Assign Case (CARESV1-57) | February 3, 2023 8:00 AM | June 21, 2023 5:00 PM | 219FS-39d,221 | 223 | As Soon As Possible | NA | 96 | 0d | February 3, 2023 8:00 AM | June 21, 2023 5:00 PM | 96 days | No | 2/3/23 | 6/21/23 | NA | 1
5131 | M6: B3: 05.11 Conduct In-Person Contact Visit (CARESV1-58) | February 3, 2023 8:00 AM | June 21, 2023 5:00 PM | 219FS-39d,222 | 224 | As Soon As Possible | NA | 96 | 0d | February 3, 2023 8:00 AM | June 21, 2023 5:00 PM | 96 days | No | 2/3/23 | 6/21/23 | NA | 1
5132 | M6: B4: 04.02 Conduct Supervisor Review and Approval (r1) (CARESV1-60) | February 3, 2023 8:00 AM | June 21, 2023 5:00 PM | 219FS-39d,223 | 226SS+35d,227SS+35d,228SS+35d,229SS+35d,2242 | As Soon As Possible | NA | 96 | 0d | February 3, 2023 8:00 AM | June 21, 2023 5:00 PM | 96 days | No | 2/3/23 | 6/21/23 | NA | 1
5133 | M6: Build | March 27, 2023 8:00 AM | September 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 121 | 0d | March 27, 2023 8:00 AM | September 15, 2023 5:00 PM | 121 days | No | 3/27/23 | 9/15/23 | NA | 1
5134 | M6: B1: 05.01 Create or Update Person Profile (CARESV1-20) | March 27, 2023 8:00 AM | September 15, 2023 5:00 PM | 224SS+35d | 227 | As Soon As Possible | NA | 121 | 0d | March 27, 2023 8:00 AM | September 15, 2023 5:00 PM | 121 days | No | 3/27/23 | 9/15/23 | NA | 1
5135 | M6: B2: 04.01 Open and Assign Case (CARESV1-57) | March 27, 2023 8:00 AM | September 15, 2023 5:00 PM | 224SS+35d,226 | 228 | As Soon As Possible | NA | 121 | 0d | March 27, 2023 8:00 AM | September 15, 2023 5:00 PM | 121 days | No | 3/27/23 | 9/15/23 | NA | 1
5136 | M6: B3: 05.11 Conduct In-Person Contact Visit (CARESV1-58) | March 27, 2023 8:00 AM | September 15, 2023 5:00 PM | 224SS+35d,227 | 229 | As Soon As Possible | NA | 121 | 0d | March 27, 2023 8:00 AM | September 15, 2023 5:00 PM | 121 days | No | 3/27/23 | 9/15/23 | NA | 1
5137 | M6: B4: 04.02 Conduct Supervisor Review and Approval (r1) (CARESV1-60) | March 27, 2023 8:00 AM | September 15, 2023 5:00 PM | 224SS+35d,228 | 231SS,232SS,233SS,234SS | As Soon As Possible | NA | 121 | 0d | March 27, 2023 8:00 AM | September 15, 2023 5:00 PM | 121 days | No | 3/27/23 | 9/15/23 | NA | 1
5138 | M6: SIT | March 27, 2023 8:00 AM | October 12, 2023 5:00 PM |  |  | As Soon As Possible | NA | 140 | 0d | March 27, 2023 8:00 AM | October 12, 2023 5:00 PM | 140 days | No | 3/27/23 | 10/12/23 | NA | 1
5139 | M6: B1: 05.01 Create or Update Person Profile (CARESV1-20) | March 27, 2023 8:00 AM | October 12, 2023 5:00 PM | 229SS | 232 | As Soon As Possible | NA | 140 | 0d | March 27, 2023 8:00 AM | October 12, 2023 5:00 PM | 140 days | No | 3/27/23 | 10/12/23 | NA | 1
5140 | M6: B2: 04.01 Open and Assign Case (CARESV1-57) | March 27, 2023 8:00 AM | October 12, 2023 5:00 PM | 229SS,231 | 233 | As Soon As Possible | NA | 140 | 0d | March 27, 2023 8:00 AM | October 12, 2023 5:00 PM | 140 days | No | 3/27/23 | 10/12/23 | NA | 1
5091 | M6: B3: 05.11 Conduct In-Person Contact Visit (CARESV1-58) | March 27, 2023 8:00 AM | October 12, 2023 5:00 PM | 229SS,232 | 234 | As Soon As Possible | NA | 140 | 0d | March 27, 2023 8:00 AM | October 12, 2023 5:00 PM | 140 days | No | 3/27/23 | 10/12/23 | NA | 1
5092 | M6: B4: 04.02 Conduct Supervisor Review and Approval (r1) (CARESV1-60) | March 27, 2023 8:00 AM | October 12, 2023 5:00 PM | 229SS,233 | 236SS+29d,237SS+29d,238SS+29d,239SS+29d,4385FS+266d,1475 | As Soon As Possible | NA | 140 | 0d | March 27, 2023 8:00 AM | October 12, 2023 5:00 PM | 140 days | No | 3/27/23 | 10/12/23 | NA | 1
5093 | M6: QA | May 8, 2023 8:00 AM | December 11, 2023 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | May 8, 2023 8:00 AM | December 11, 2023 5:00 PM | 150 days | No | 5/8/23 | 12/11/23 | NA | 1
5094 | M6: B1: 05.01 Create or Update Person Profile (CARESV1-20) | May 8, 2023 8:00 AM | December 11, 2023 5:00 PM | 234SS+29d | 237 | As Soon As Possible | NA | 150 | 0d | May 8, 2023 8:00 AM | December 11, 2023 5:00 PM | 150 days | No | 5/8/23 | 12/11/23 | NA | 1
5095 | M6: B2: 04.01 Open and Assign Case (CARESV1-57) | May 8, 2023 8:00 AM | December 11, 2023 5:00 PM | 234SS+29d,236 | 238 | As Soon As Possible | NA | 150 | 0d | May 8, 2023 8:00 AM | December 11, 2023 5:00 PM | 150 days | No | 5/8/23 | 12/11/23 | NA | 1
5096 | M6: B3: 05.11 Conduct In-Person Contact Visit (CARESV1-58) | May 8, 2023 8:00 AM | December 11, 2023 5:00 PM | 234SS+29d,237 | 239 | As Soon As Possible | NA | 150 | 0d | May 8, 2023 8:00 AM | December 11, 2023 5:00 PM | 150 days | No | 5/8/23 | 12/11/23 | NA | 1
5097 | M6: B4: 04.02 Conduct Supervisor Review and Approval (r1) (CARESV1-60) | May 8, 2023 8:00 AM | December 11, 2023 5:00 PM | 234SS+29d,238 | 241SS-10d,242SS-10d,243SS-10d,244SS-10d | As Soon As Possible | NA | 150 | 0d | May 8, 2023 8:00 AM | December 11, 2023 5:00 PM | 150 days | No | 5/8/23 | 12/11/23 | NA | 1
5098 | M6: Readiness for User Feedback | April 24, 2023 8:00 AM | December 11, 2023 5:00 PM |  |  | As Soon As Possible | NA | 160 | 0d | April 24, 2023 8:00 AM | December 11, 2023 5:00 PM | 160 days | No | 4/24/23 | 12/11/23 | NA | 1
5099 | M6: B1: 05.01 Create or Update Person Profile (CARESV1-20) | April 24, 2023 8:00 AM | December 11, 2023 5:00 PM | 239SS-10d | 242 | As Soon As Possible | NA | 160 | 0d | April 24, 2023 8:00 AM | December 11, 2023 5:00 PM | 160 days | No | 4/24/23 | 12/11/23 | NA | 1
5100 | M6: B2: 04.01 Open and Assign Case (CARESV1-57) | April 24, 2023 8:00 AM | December 11, 2023 5:00 PM | 239SS-10d,241 | 243 | As Soon As Possible | NA | 160 | 0d | April 24, 2023 8:00 AM | December 11, 2023 5:00 PM | 160 days | No | 4/24/23 | 12/11/23 | NA | 1
5101 | M6: B3: 05.11 Conduct In-Person Contact Visit (CARESV1-58) | April 24, 2023 8:00 AM | December 11, 2023 5:00 PM | 239SS-10d,242 | 244 | As Soon As Possible | NA | 160 | 0d | April 24, 2023 8:00 AM | December 11, 2023 5:00 PM | 160 days | No | 4/24/23 | 12/11/23 | NA | 1
5102 | M6: B4: 04.02 Conduct Supervisor Review and Approval (r1) (CARESV1-60) | April 24, 2023 8:00 AM | December 11, 2023 5:00 PM | 239SS-10d,243 | 245FF | As Soon As Possible | NA | 160 | 0d | April 24, 2023 8:00 AM | December 11, 2023 5:00 PM | 160 days | No | 4/24/23 | 12/11/23 | NA | 1
5108 | Milestone 6 (Case Management: Engagement) Jira # CARES V1-520 Complete | December 11, 2023 5:00 PM | December 11, 2023 5:00 PM | 244FF |  | As Soon As Possible | NA | 0 | 0d | December 11, 2023 5:00 PM | December 11, 2023 5:00 PM | 0 days | Yes | 12/11/23 | 12/11/23 | NA | 1
5141 | Milestone 08: Placement (CARESV1-523) | October 10, 2022 8:00 AM | April 19, 2024 5:00 PM |  |  | As Soon As Possible | NA | 381 | 0d | October 10, 2022 8:00 AM | April 19, 2024 5:00 PM | 381 days | No | 10/10/22 | 4/19/24 | NA | 1
5142 | M8: Research & Context Setting | October 10, 2022 8:00 AM | February 6, 2023 5:00 PM |  |  | As Soon As Possible | NA | 80 | 0d | October 10, 2022 8:00 AM | February 6, 2023 5:00 PM | 80 days | No | 10/10/22 | 2/6/23 | NA | 1
5143 | M8: RC: Finalize Value Hypothesis | October 10, 2022 8:00 AM | January 27, 2023 5:00 PM |  | 249SS,250SS,251SS,252SS,253SS,254SS,255SS | As Soon As Possible | NA | 74 | 0d | October 10, 2022 8:00 AM | January 27, 2023 5:00 PM | 74 days | No | 10/10/22 | 1/27/23 | NA | 1
5144 | M8: RC: Draft Service Maps | October 10, 2022 8:00 AM | January 27, 2023 5:00 PM | 248SS | 250 | As Soon As Possible | NA | 74 | 0d | October 10, 2022 8:00 AM | January 27, 2023 5:00 PM | 74 days | No | 10/10/22 | 1/27/23 | NA | 1
5178 | M8: RC: Complete Legacy Analysis | October 10, 2022 8:00 AM | February 6, 2023 5:00 PM | 248SS,249 | 251 | As Soon As Possible | NA | 80 | 0d | October 10, 2022 8:00 AM | February 6, 2023 5:00 PM | 80 days | No | 10/10/22 | 2/6/23 | NA | 1
5179 | M8: RC: Finalize Epics | October 10, 2022 8:00 AM | February 6, 2023 5:00 PM | 248SS,250 | 252 | As Soon As Possible | NA | 80 | 0d | October 10, 2022 8:00 AM | February 6, 2023 5:00 PM | 80 days | No | 10/10/22 | 2/6/23 | NA | 1
5180 | M8: RC: Complete conceptual and epic-level Domain Model diagrams | October 10, 2022 8:00 AM | February 6, 2023 5:00 PM | 248SS,251 | 253 | As Soon As Possible | NA | 80 | 0d | October 10, 2022 8:00 AM | February 6, 2023 5:00 PM | 80 days | No | 10/10/22 | 2/6/23 | NA | 1
5181 | M8: RC: Define User Story titles | October 10, 2022 8:00 AM | February 6, 2023 5:00 PM | 248SS,252 | 254 | As Soon As Possible | NA | 80 | 0d | October 10, 2022 8:00 AM | February 6, 2023 5:00 PM | 80 days | No | 10/10/22 | 2/6/23 | NA | 1
5182 | M8: RC: Complete External Systems pre-analysis | October 10, 2022 8:00 AM | February 6, 2023 5:00 PM | 248SS,253 | 255 | As Soon As Possible | NA | 80 | 0d | October 10, 2022 8:00 AM | February 6, 2023 5:00 PM | 80 days | No | 10/10/22 | 2/6/23 | NA | 1
5183 | M8: RC: Facilitate Inception | October 10, 2022 8:00 AM | February 6, 2023 5:00 PM | 248SS,254 | 257FS+8d,258FS+8d,259FS+8d,260FS+8d,261FS+8d,2513SS | As Soon As Possible | NA | 80 | 0d | October 10, 2022 8:00 AM | February 6, 2023 5:00 PM | 80 days | No | 10/10/22 | 2/6/23 | NA | 1
5184 | M8: BRC | February 17, 2023 8:00 AM | May 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 71 | 0d | February 17, 2023 8:00 AM | May 31, 2023 5:00 PM | 71 days | No | 2/17/23 | 5/31/23 | NA | 1
5185 | M8: B1: 06.01 Make Placement (CARESV1-59) | February 17, 2023 8:00 AM | May 31, 2023 5:00 PM | 255FS+8d | 258 | As Soon As Possible | NA | 71 | 0d | February 17, 2023 8:00 AM | May 31, 2023 5:00 PM | 71 days | No | 2/17/23 | 5/31/23 | NA | 1
5186 | M8: B2: 06.02 Monitor the Placement (CARESV1-74) | February 17, 2023 8:00 AM | May 31, 2023 5:00 PM | 255FS+8d,257 | 259 | As Soon As Possible | NA | 71 | 0d | February 17, 2023 8:00 AM | May 31, 2023 5:00 PM | 71 days | No | 2/17/23 | 5/31/23 | NA | 1
5187 | M8: B3: 18.02 Make Update to Organization Directory (CARESV1-115) | February 17, 2023 8:00 AM | May 31, 2023 5:00 PM | 255FS+8d,258 | 260 | As Soon As Possible | NA | 71 | 0d | February 17, 2023 8:00 AM | May 31, 2023 5:00 PM | 71 days | No | 2/17/23 | 5/31/23 | NA | 1
5188 | M8: B4: California Department of Education (CDE) Interface (CARESV1-13685) | February 17, 2023 8:00 AM | May 31, 2023 5:00 PM | 255FS+8d,259 | 261 | As Soon As Possible | NA | 71 | 0d | February 17, 2023 8:00 AM | May 31, 2023 5:00 PM | 71 days | No | 2/17/23 | 5/31/23 | NA | 1
5189 | M8: B5: Department of Developmental Services (DDS) Interface (CARESV1-13688) | February 17, 2023 8:00 AM | May 31, 2023 5:00 PM | 255FS+8d,260 | 263FS-38d,264FS-38d,265FS-38d,266FS-38d,267FS-38d | As Soon As Possible | NA | 71 | 0d | February 17, 2023 8:00 AM | May 31, 2023 5:00 PM | 71 days | No | 2/17/23 | 5/31/23 | NA | 1
5190 | M8: Design | April 7, 2023 8:00 AM | July 18, 2023 5:00 PM |  |  | As Soon As Possible | NA | 71 | 0d | April 7, 2023 8:00 AM | July 18, 2023 5:00 PM | 71 days | No | 4/7/23 | 7/18/23 | NA | 1
5191 | M8: B1: 06.01 Make Placement (CARESV1-59) | April 7, 2023 8:00 AM | July 18, 2023 5:00 PM | 261FS-38d | 264 | As Soon As Possible | NA | 71 | 0d | April 7, 2023 8:00 AM | July 18, 2023 5:00 PM | 71 days | No | 4/7/23 | 7/18/23 | NA | 1
5192 | M8: B2: 06.02 Monitor the Placement (CARESV1-74) | April 7, 2023 8:00 AM | July 18, 2023 5:00 PM | 261FS-38d,263 | 265 | As Soon As Possible | NA | 71 | 0d | April 7, 2023 8:00 AM | July 18, 2023 5:00 PM | 71 days | No | 4/7/23 | 7/18/23 | NA | 1
5193 | M8: B3: 18.02 Make Update to Organization Directory (CARESV1-115) | April 7, 2023 8:00 AM | July 18, 2023 5:00 PM | 261FS-38d,264 | 266 | As Soon As Possible | NA | 71 | 0d | April 7, 2023 8:00 AM | July 18, 2023 5:00 PM | 71 days | No | 4/7/23 | 7/18/23 | NA | 1
5194 | M8: B4: California Department of Education (CDE) Interface (CARESV1-13685) | April 7, 2023 8:00 AM | July 18, 2023 5:00 PM | 261FS-38d,265 | 267 | As Soon As Possible | NA | 71 | 0d | April 7, 2023 8:00 AM | July 18, 2023 5:00 PM | 71 days | No | 4/7/23 | 7/18/23 | NA | 1
5195 | M8: B5: Department of Developmental Services (DDS) Interface (CARESV1-13688) | April 7, 2023 8:00 AM | July 18, 2023 5:00 PM | 261FS-38d,266 | 269FS-21d,270FS-21d,271FS-21d,272FS-21d,273FS-21d,2254SS | As Soon As Possible | NA | 71 | 0d | April 7, 2023 8:00 AM | July 18, 2023 5:00 PM | 71 days | No | 4/7/23 | 7/18/23 | NA | 1
5197 | M8: Build | June 19, 2023 8:00 AM | October 9, 2023 5:00 PM |  |  | As Soon As Possible | NA | 79 | 0d | June 19, 2023 8:00 AM | October 9, 2023 5:00 PM | 79 days | No | 6/19/23 | 10/9/23 | NA | 1
5198 | M8: B1: 06.01 Make Placement (CARESV1-59) | June 19, 2023 8:00 AM | October 9, 2023 5:00 PM | 267FS-21d | 270 | As Soon As Possible | NA | 79 | 0d | June 19, 2023 8:00 AM | October 9, 2023 5:00 PM | 79 days | No | 6/19/23 | 10/9/23 | NA | 1
5199 | M8: B2: 06.02 Monitor the Placement (CARESV1-74) | June 19, 2023 8:00 AM | October 9, 2023 5:00 PM | 267FS-21d,269 | 271 | As Soon As Possible | NA | 79 | 0d | June 19, 2023 8:00 AM | October 9, 2023 5:00 PM | 79 days | No | 6/19/23 | 10/9/23 | NA | 1
5200 | M8: B3: 18.02 Make Update to Organization Directory (CARESV1-115) | June 19, 2023 8:00 AM | October 9, 2023 5:00 PM | 267FS-21d,270 | 272 | As Soon As Possible | NA | 79 | 0d | June 19, 2023 8:00 AM | October 9, 2023 5:00 PM | 79 days | No | 6/19/23 | 10/9/23 | NA | 1
5201 | M8: B4: California Department of Education (CDE) Interface (CARESV1-13685) | June 19, 2023 8:00 AM | October 9, 2023 5:00 PM | 267FS-21d,271 | 273 | As Soon As Possible | NA | 79 | 0d | June 19, 2023 8:00 AM | October 9, 2023 5:00 PM | 79 days | No | 6/19/23 | 10/9/23 | NA | 1
5145 | M8: B5: Department of Developmental Services (DDS) Interface (CARESV1-13688) | June 19, 2023 8:00 AM | October 9, 2023 5:00 PM | 267FS-21d,272 | 275SS,276SS,277SS,278SS,279SS,2517SS | As Soon As Possible | NA | 79 | 0d | June 19, 2023 8:00 AM | October 9, 2023 5:00 PM | 79 days | No | 6/19/23 | 10/9/23 | NA | 1
5146 | M8: SIT | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM |  |  | As Soon As Possible | NA | 77 | 0d | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM | 77 days | No | 6/19/23 | 10/5/23 | NA | 1
5147 | M8: B1: 06.01 Make Placement (CARESV1-59) | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM | 273SS | 276 | As Soon As Possible | NA | 77 | 0d | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM | 77 days | No | 6/19/23 | 10/5/23 | NA | 1
5148 | M8: B2: 06.02 Monitor the Placement (CARESV1-74) | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM | 273SS,275 | 277 | As Soon As Possible | NA | 77 | 0d | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM | 77 days | No | 6/19/23 | 10/5/23 | NA | 1
5149 | M8: B3: 18.02 Make Update to Organization Directory (CARESV1-115) | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM | 273SS,276 | 278 | As Soon As Possible | NA | 77 | 0d | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM | 77 days | No | 6/19/23 | 10/5/23 | NA | 1
5150 | M8: B4: California Department of Education (CDE) Interface (CARESV1-13685) | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM | 273SS,277 | 279 | As Soon As Possible | NA | 77 | 0d | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM | 77 days | No | 6/19/23 | 10/5/23 | NA | 1
5151 | M8: B5: Department of Developmental Services (DDS) Interface (CARESV1-13688) | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM | 273SS,278 | 281SS,282SS,283SS,284SS,285SS,4397FS+271d,1475 | As Soon As Possible | NA | 77 | 0d | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM | 77 days | No | 6/19/23 | 10/5/23 | NA | 1
5152 | M8: QA | June 19, 2023 8:00 AM | December 29, 2023 5:00 PM |  |  | As Soon As Possible | NA | 134 | 0d | June 19, 2023 8:00 AM | December 29, 2023 5:00 PM | 134 days | No | 6/19/23 | 12/29/23 | NA | 1
5153 | M8: B1: 06.01 Make Placement (CARESV1-59) | June 19, 2023 8:00 AM | December 29, 2023 5:00 PM | 279SS | 282 | As Soon As Possible | NA | 134 | 0d | June 19, 2023 8:00 AM | December 29, 2023 5:00 PM | 134 days | No | 6/19/23 | 12/29/23 | NA | 1
5154 | M8: B2: 06.02 Monitor the Placement (CARESV1-74) | June 19, 2023 8:00 AM | December 29, 2023 5:00 PM | 279SS,281 | 283 | As Soon As Possible | NA | 134 | 0d | June 19, 2023 8:00 AM | December 29, 2023 5:00 PM | 134 days | No | 6/19/23 | 12/29/23 | NA | 1
5155 | M8: B3: 18.02 Make Update to Organization Directory (CARESV1-115) | June 19, 2023 8:00 AM | December 29, 2023 5:00 PM | 279SS,282 | 284 | As Soon As Possible | NA | 134 | 0d | June 19, 2023 8:00 AM | December 29, 2023 5:00 PM | 134 days | No | 6/19/23 | 12/29/23 | NA | 1
5156 | M8: B4: California Department of Education (CDE) Interface (CARESV1-13685) | June 19, 2023 8:00 AM | December 29, 2023 5:00 PM | 279SS,283 | 2518SS | As Soon As Possible | NA | 134 | 0d | June 19, 2023 8:00 AM | December 29, 2023 5:00 PM | 134 days | No | 6/19/23 | 12/29/23 | NA | 1
5157 | M8: B5: Department of Developmental Services (DDS) Interface (CARESV1-13688) | June 19, 2023 8:00 AM | December 29, 2023 5:00 PM | 279SS | 287FS+57d,288FS+57d,289FS+57d,290FS+57d,291FS+57d | As Soon As Possible | NA | 134 | 0d | June 19, 2023 8:00 AM | December 29, 2023 5:00 PM | 134 days | No | 6/19/23 | 12/29/23 | NA | 1
5158 | M8: Readiness for User Feedback | March 25, 2024 8:00 AM | April 19, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | March 25, 2024 8:00 AM | April 19, 2024 5:00 PM | 19 days | No | 3/25/24 | 4/19/24 | NA | 1
5159 | M8: B1: 06.01 Make Placement (CARESV1-59) | March 25, 2024 8:00 AM | April 19, 2024 5:00 PM | 285FS+57d | 288 | As Soon As Possible | NA | 19 | 0d | March 25, 2024 8:00 AM | April 19, 2024 5:00 PM | 19 days | No | 3/25/24 | 4/19/24 | NA | 1
5160 | M8: B2: 06.02 Monitor the Placement (CARESV1-74) | March 25, 2024 8:00 AM | April 19, 2024 5:00 PM | 285FS+57d,287 | 289 | As Soon As Possible | NA | 19 | 0d | March 25, 2024 8:00 AM | April 19, 2024 5:00 PM | 19 days | No | 3/25/24 | 4/19/24 | NA | 1
5161 | M8: B3: 18.02 Make Update to Organization Directory (CARESV1-115) | March 25, 2024 8:00 AM | April 19, 2024 5:00 PM | 285FS+57d,288 | 290 | As Soon As Possible | NA | 19 | 0d | March 25, 2024 8:00 AM | April 19, 2024 5:00 PM | 19 days | No | 3/25/24 | 4/19/24 | NA | 1
5162 | M8: B4: California Department of Education (CDE) Interface (CARESV1-13685) | March 25, 2024 8:00 AM | April 19, 2024 5:00 PM | 285FS+57d,289 | 291 | As Soon As Possible | NA | 19 | 0d | March 25, 2024 8:00 AM | April 19, 2024 5:00 PM | 19 days | No | 3/25/24 | 4/19/24 | NA | 1
5163 | M8: B5: Department of Developmental Services (DDS) Interface (CARESV1-13688) | March 25, 2024 8:00 AM | April 19, 2024 5:00 PM | 285FS+57d,290 | 292FF | As Soon As Possible | NA | 19 | 0d | March 25, 2024 8:00 AM | April 19, 2024 5:00 PM | 19 days | No | 3/25/24 | 4/19/24 | NA | 1
5170 | Milestone 8 (Placement) Jira # CARES V1-523 Complete | April 19, 2024 5:00 PM | April 19, 2024 5:00 PM | 291FF |  | As Soon As Possible | NA | 0 | 0d | April 19, 2024 5:00 PM | April 19, 2024 5:00 PM | 0 days | Yes | 4/19/24 | 4/19/24 | NA | 1
11022 | Milestone 06.1: Prevention Services (CARESV1-510) | March 27, 2023 8:00 AM | October 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 403 | 0d | March 27, 2023 8:00 AM | December 30, 2025 5:00 PM | 694 days | No | 3/27/23 | 10/29/24 | NA | 1
11246 | M6.1: Research & Context Setting | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM |  |  | As Soon As Possible | NA | 77 | 0d | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 77 days | No | 3/27/23 | 7/14/23 | NA | 1
11036 | M6.1: RC: Finalize Value Hypothesis | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM |  | 296SS,297SS,298SS,299SS,300SS,301SS,302SS | Must Start On | 9/11/23 | 77 | 0d | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 77 days | No | 3/27/23 | 7/14/23 | NA | 1
11037 | M6.1: RC: Draft Service Maps | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 295SS | 297 | As Soon As Possible | NA | 77 | 0d | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 77 days | No | 3/27/23 | 7/14/23 | NA | 1
11038 | M6.1: RC: Complete Legacy Analysis | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 295SS,296 | 298 | As Soon As Possible | NA | 77 | 0d | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 77 days | No | 3/27/23 | 7/14/23 | NA | 1
11039 | M6.1: RC: Finalize Epics | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 295SS,297 | 299 | As Soon As Possible | NA | 77 | 0d | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 77 days | No | 3/27/23 | 7/14/23 | NA | 1
11040 | M6.1: RC: Complete conceptual and epic-level Domain Model diagrams | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 295SS,298 | 300 | As Soon As Possible | NA | 77 | 0d | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 77 days | No | 3/27/23 | 7/14/23 | NA | 1
11041 | M6.1: RC: Define User Story titles | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 295SS,299 | 301 | As Soon As Possible | NA | 77 | 0d | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 77 days | No | 3/27/23 | 7/14/23 | NA | 1
11042 | M6.1: RC: Complete External Systems pre-analysis | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 295SS,300 | 302 | As Soon As Possible | NA | 77 | 0d | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 77 days | No | 3/27/23 | 7/14/23 | NA | 1
11043 | M6.1: RC: Facilitate Inception | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 295SS,301 | 304 | As Soon As Possible | NA | 77 | 0d | March 27, 2023 8:00 AM | July 14, 2023 5:00 PM | 77 days | No | 3/27/23 | 7/14/23 | NA | 1
11247 | M6.1: BRC | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM |  |  | As Soon As Possible | NA | 94 | 0d | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 94 days | No | 9/11/23 | 1/26/24 | NA | 1
11248 | Milestone 06.1: B:05:04 Request and Provide Services | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 302 | 306 | As Soon As Possible | NA | 94 | 0d | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 94 days | No | 9/11/23 | 1/26/24 | NA | 1
11249 | M6.1: Design | January 29, 2024 8:00 AM | October 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 193 | 0d | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 176 days | No | 1/29/24 | 10/29/24 | NA | 1
11250 | Milestone 06.1: B:05:04 Request and Provide Services | January 29, 2024 8:00 AM | October 29, 2024 5:00 PM | 304 | 308SS,619FS+1d | As Soon As Possible | NA | 193 | 0d | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 176 days | No | 1/29/24 | 10/29/24 | NA | 1
11251 | M6.1: Build | January 29, 2024 8:00 AM | October 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 193 | 0d | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 days | No | 1/29/24 | 10/29/24 | NA | 1
11252 | Milestone 06.1: B:05:04 Request and Provide Services | January 29, 2024 8:00 AM | October 29, 2024 5:00 PM | 306SS | 1960FS+102d,1961SS,1962SS,1963SS,1964SS,1965SS,1966SS,310SS,620SS+19d,4455FS+193d | As Soon As Possible | NA | 193 | 0d | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 days | No | 1/29/24 | 10/29/24 | NA | 1
11253 | M6.1: SIT | January 29, 2024 8:00 AM | October 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 193 | 0d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 1/29/24 | 10/29/24 | NA | 1
11254 | Milestone 06.1: B:05:04 Request and Provide Services | January 29, 2024 8:00 AM | October 29, 2024 5:00 PM | 308SS | 312SS+22d,621SS+22d,4455FS+193d | As Soon As Possible | NA | 193 | 0d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 1/29/24 | 10/29/24 | NA | 1
11256 | M6.1: State QA | February 29, 2024 8:00 AM | October 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 171 | 0d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 2/29/24 | 10/29/24 | NA | 1
11257 | Milestone 06.1: B:05:04 Request and Provide Services | February 29, 2024 8:00 AM | October 29, 2024 5:00 PM | 310SS+22d | 314SS,622SS | As Soon As Possible | NA | 171 | 0d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 2/29/24 | 10/29/24 | NA | 1
11258 | M6.1: Joint Review | February 29, 2024 8:00 AM | October 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 171 | 0d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 2/29/24 | 10/29/24 | NA | 1
11259 | Milestone 06.1: B:05:04 Request and Provide Services | February 29, 2024 8:00 AM | October 29, 2024 5:00 PM | 312SS | 315FF | As Soon As Possible | NA | 171 | 0d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 2/29/24 | 10/29/24 | NA | 1
11585 | Milestone 06.1: Prevention Services Complete | October 29, 2024 5:00 PM | October 29, 2024 5:00 PM | 314FF | 628FF | As Soon As Possible | NA | 0 | 0d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | 10/29/24 | 10/29/24 | NA | 1
11299 | Milestone 9: Engagement & Services (CARESV1-521) | December 5, 2022 8:00 AM | September 18, 2024 5:00 PM |  |  | As Soon As Possible | NA | 450 | 0d | December 5, 2022 8:00 AM | December 30, 2025 5:00 PM | 770 days | No | 12/5/22 | 9/18/24 | NA | 1
11313 | M9: Research & Context Setting | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM |  |  | As Soon As Possible | NA | 28 | 0d | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 28 days | No | 12/5/22 | 1/13/23 | NA | 1
11300 | M9: RC: Finalize Value Hypothesis | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM |  | 2520SS,319SS | Must Start On | 12/5/22 | 28 | 0d | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 28 days | No | 12/5/22 | 1/13/23 | NA | 1
11301 | M9: RC: Draft Service Maps | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 318SS | 320SS | As Soon As Possible | NA | 28 | 0d | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 28 days | No | 12/5/22 | 1/13/23 | NA | 1
11302 | M9: RC: Complete Legacy Analysis | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 319SS | 321SS | As Soon As Possible | NA | 28 | 0d | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 28 days | No | 12/5/22 | 1/13/23 | NA | 1
11303 | M9: RC: Finalize Epics | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 320SS | 322SS | As Soon As Possible | NA | 28 | 0d | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 28 days | No | 12/5/22 | 1/13/23 | NA | 1
11304 | M9: RC: Complete conceptual and epic-level Domain Model diagrams | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 321SS | 323SS | As Soon As Possible | NA | 28 | 0d | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 28 days | No | 12/5/22 | 1/13/23 | NA | 1
11305 | M9: RC: Define User Story titles | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 322SS | 324SS | As Soon As Possible | NA | 28 | 0d | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 28 days | No | 12/5/22 | 1/13/23 | NA | 1
11306 | M9: RC: Complete External Systems pre-analysis | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 323SS | 325SS | As Soon As Possible | NA | 28 | 0d | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 28 days | No | 12/5/22 | 1/13/23 | NA | 1
11307 | M9: RC: Facilitate Inception | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 324SS | 327FS+62d,328FS+62d,329FS+62d,330FS+62d,331FS+62d | As Soon As Possible | NA | 28 | 0d | December 5, 2022 8:00 AM | January 13, 2023 5:00 PM | 28 days | No | 12/5/22 | 1/13/23 | NA | 1
11308 | M9: BRC | April 17, 2023 8:00 AM | June 23, 2023 5:00 PM |  |  | As Soon As Possible | NA | 49 | 0d | April 17, 2023 8:00 AM | June 23, 2023 5:00 PM | 49 days | No | 4/17/23 | 6/23/23 | NA | 1
11315 | M9: B1 05.05 Prepare for Visitation (CARESV1-41) | April 17, 2023 8:00 AM | June 23, 2023 5:00 PM | 325FS+62d | 328 | As Soon As Possible | NA | 49 | 0d | April 17, 2023 8:00 AM | June 23, 2023 5:00 PM | 49 days | No | 4/17/23 | 6/23/23 | NA | 1
11316 | M9: B2 05.06 Conduct& Document Visitation (CARESV1-48) | April 17, 2023 8:00 AM | June 23, 2023 5:00 PM | 325FS+62d,327 | 329 | As Soon As Possible | NA | 49 | 0d | April 17, 2023 8:00 AM | June 23, 2023 5:00 PM | 49 days | No | 4/17/23 | 6/23/23 | NA | 1
11317 | M9: B3 05.08 Initiate and Update Family Finding (CARESV1-61) | April 17, 2023 8:00 AM | June 23, 2023 5:00 PM | 325FS+62d,328 | 330 | As Soon As Possible | NA | 49 | 0d | April 17, 2023 8:00 AM | June 23, 2023 5:00 PM | 49 days | No | 4/17/23 | 6/23/23 | NA | 1
11318 | M9: B4 05.02 Conduct Assessments (CARESV1-69) | April 17, 2023 8:00 AM | June 23, 2023 5:00 PM | 325FS+62d,329 | 331 | As Soon As Possible | NA | 49 | 0d | April 17, 2023 8:00 AM | June 23, 2023 5:00 PM | 49 days | No | 4/17/23 | 6/23/23 | NA | 1
11319 | M9: B5 05.09 Convene Child and Family Team (CARESV1-70) | April 17, 2023 8:00 AM | June 23, 2023 5:00 PM | 325FS+62d,330 | 333FS-16d | As Soon As Possible | NA | 49 | 0d | April 17, 2023 8:00 AM | June 23, 2023 5:00 PM | 49 days | No | 4/17/23 | 6/23/23 | NA | 1
11309 | M9: Design | June 2, 2023 8:00 AM | August 11, 2023 5:00 PM |  |  | As Soon As Possible | NA | 50 | 0d | June 2, 2023 8:00 AM | August 11, 2023 5:00 PM | 50 days | No | 6/2/23 | 8/11/23 | NA | 1
11320 | M9: B1 05.05 Prepare for Visitation (CARESV1-41) | June 2, 2023 8:00 AM | August 11, 2023 5:00 PM | 331FS-16d | 334SS | As Soon As Possible | NA | 50 | 0d | June 2, 2023 8:00 AM | August 11, 2023 5:00 PM | 50 days | No | 6/2/23 | 8/11/23 | NA | 1
11321 | M9: B2 05.06 Conduct& Document Visitation (CARESV1-48) | June 2, 2023 8:00 AM | August 11, 2023 5:00 PM | 333SS | 335SS | As Soon As Possible | NA | 50 | 0d | June 2, 2023 8:00 AM | August 11, 2023 5:00 PM | 50 days | No | 6/2/23 | 8/11/23 | NA | 1
11322 | M9: B3 05.08 Initiate and Update Family Finding (CARESV1-61) | June 2, 2023 8:00 AM | August 11, 2023 5:00 PM | 334SS | 336SS | As Soon As Possible | NA | 50 | 0d | June 2, 2023 8:00 AM | August 11, 2023 5:00 PM | 50 days | No | 6/2/23 | 8/11/23 | NA | 1
11323 | M9: B4 05.02 Conduct Assessments (CARESV1-69) | June 2, 2023 8:00 AM | August 11, 2023 5:00 PM | 335SS | 337SS | As Soon As Possible | NA | 50 | 0d | June 2, 2023 8:00 AM | August 11, 2023 5:00 PM | 50 days | No | 6/2/23 | 8/11/23 | NA | 1
11324 | M9: B5 05.09 Convene Child and Family Team (CARESV1-70) | June 2, 2023 8:00 AM | August 11, 2023 5:00 PM | 336SS | 339,624FF | As Soon As Possible | NA | 50 | 0d | June 2, 2023 8:00 AM | August 11, 2023 5:00 PM | 50 days | No | 6/2/23 | 8/11/23 | NA | 1
11310 | M9: Build | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM |  |  | As Soon As Possible | NA | 97 | 0d | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 97 days | No | 8/14/23 | 1/3/24 | NA | 1
11325 | M9: B1 05.05 Prepare for Visitation (CARESV1-41) | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 337 | 2260SS,340SS,345SS,4485FS+402d | As Soon As Possible | NA | 97 | 0d | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 97 days | No | 8/14/23 | 1/3/24 | NA | 1
11326 | M9: B2 05.06 Conduct& Document Visitation (CARESV1-48) | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 339SS | 341SS,4485FS+402d | As Soon As Possible | NA | 97 | 0d | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 97 days | No | 8/14/23 | 1/3/24 | NA | 1
11327 | M9: B3 05.08 Initiate and Update Family Finding (CARESV1-61) | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 340SS | 342SS,4485FS+402d | As Soon As Possible | NA | 97 | 0d | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 97 days | No | 8/14/23 | 1/3/24 | NA | 1
11328 | M9: B4 05.02 Conduct Assessments (CARESV1-69) | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 341SS | 343SS,4485FS+402d | As Soon As Possible | NA | 97 | 0d | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 97 days | No | 8/14/23 | 1/3/24 | NA | 1
11329 | M9: B5 05.09 Convene Child and Family Team (CARESV1-70) | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 342SS | 2524SS,625FF,4485FS+402d | As Soon As Possible | NA | 97 | 0d | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 97 days | No | 8/14/23 | 1/3/24 | NA | 1
11311 | M9: SIT | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM |  |  | As Soon As Possible | NA | 97 | 0d | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 97 days | No | 8/14/23 | 1/3/24 | NA | 1
11330 | M9: B1 05.05 Prepare for Visitation (CARESV1-41) | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 339SS | 346SS,1479,4485FS+402d | As Soon As Possible | NA | 97 | 0d | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 97 days | No | 8/14/23 | 1/3/24 | NA | 1
11331 | M9: B2 05.06 Conduct& Document Visitation (CARESV1-48) | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 345SS | 347SS,4485FS+402d | As Soon As Possible | NA | 97 | 0d | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 97 days | No | 8/14/23 | 1/3/24 | NA | 1
11332 | M9: B3 05.08 Initiate and Update Family Finding (CARESV1-61) | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 346SS | 348SS,4485FS+402d | As Soon As Possible | NA | 97 | 0d | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 97 days | No | 8/14/23 | 1/3/24 | NA | 1
11333 | M9: B4 05.02 Conduct Assessments (CARESV1-69) | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 347SS | 349SS,4485FS+402d | As Soon As Possible | NA | 97 | 0d | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 97 days | No | 8/14/23 | 1/3/24 | NA | 1
11334 | M9: B5 05.09 Convene Child and Family Team (CARESV1-70) | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 348SS | 4484FS+330d,351SS,626FF,4485FS+402d | As Soon As Possible | NA | 97 | 0d | August 14, 2023 8:00 AM | January 3, 2024 5:00 PM | 97 days | No | 8/14/23 | 1/3/24 | NA | 1
11312 | M9: State QA | August 14, 2023 8:00 AM | January 26, 2024 5:00 PM |  |  | As Soon As Possible | NA | 113 | 0d | August 14, 2023 8:00 AM | January 26, 2024 5:00 PM | 113 days | No | 8/14/23 | 1/26/24 | NA | 1
11335 | M9: B1 05.05 Prepare for Visitation (CARESV1-41) | August 14, 2023 8:00 AM | January 26, 2024 5:00 PM | 349SS | 2525SS,4490,352SS | As Soon As Possible | NA | 113 | 0d | August 14, 2023 8:00 AM | January 26, 2024 5:00 PM | 113 days | No | 8/14/23 | 1/26/24 | NA | 1
11336 | M9: B2 05.06 Conduct& Document Visitation (CARESV1-48) | August 14, 2023 8:00 AM | January 26, 2024 5:00 PM | 351SS | 4490,353SS | Finish No Earlier Than | 1/26/24 | 113 | 0d | August 14, 2023 8:00 AM | January 26, 2024 5:00 PM | 113 days | No | 8/14/23 | 1/26/24 | NA | 1
11337 | M9: B3 05.08 Initiate and Update Family Finding (CARESV1-61) | August 14, 2023 8:00 AM | January 26, 2024 5:00 PM | 352SS | 4490,354SS | Finish No Earlier Than | 1/26/24 | 113 | 0d | August 14, 2023 8:00 AM | January 26, 2024 5:00 PM | 113 days | No | 8/14/23 | 1/26/24 | NA | 1
11338 | M9: B4 05.02 Conduct Assessments (CARESV1-69) | August 14, 2023 8:00 AM | January 26, 2024 5:00 PM | 353SS | 4490,355SS | Finish No Earlier Than | 1/26/24 | 113 | 0d | August 14, 2023 8:00 AM | January 26, 2024 5:00 PM | 113 days | No | 8/14/23 | 1/26/24 | NA | 1
11339 | M9: B5 05.09 Convene Child and Family Team (CARESV1-70) | August 14, 2023 8:00 AM | January 26, 2024 5:00 PM | 354SS | 5426,4490,357FS-84d,627FF | Finish No Earlier Than | 1/26/24 | 113 | 0d | August 14, 2023 8:00 AM | January 26, 2024 5:00 PM | 113 days | No | 8/14/23 | 1/26/24 | NA | 1
11314 | M9: Joint Review | September 25, 2023 8:00 AM | September 18, 2024 5:00 PM |  |  | As Soon As Possible | NA | 248 | 0d | September 25, 2023 8:00 AM | December 30, 2025 5:00 PM | 568 days | No | 9/25/23 | 9/18/24 | NA | 1
11340 | M9: B1 05.05 Prepare for Visitation (CARESV1-41) | September 25, 2023 8:00 AM | September 18, 2024 5:00 PM | 355FS-84d | 358SS | As Soon As Possible | NA | 248 | 0d | September 25, 2023 8:00 AM | December 30, 2025 5:00 PM | 568 days | No | 9/25/23 | 9/18/24 | NA | 1
11341 | M9: B2 05.06 Conduct& Document Visitation (CARESV1-48) | September 25, 2023 8:00 AM | July 23, 2024 5:00 PM | 357SS | 359SS | As Soon As Possible | NA | 207 | 0d | September 25, 2023 8:00 AM | December 30, 2025 5:00 PM | 568 days | No | 9/25/23 | 7/23/24 | NA | 1
11345 | M9: B3 05.08 Initiate and Update Family Finding (CARESV1-61) | September 25, 2023 8:00 AM | April 29, 2024 5:00 PM | 358SS | 360SS,634FF | As Soon As Possible | NA | 148 | 0d | September 25, 2023 8:00 AM | December 30, 2025 5:00 PM | 568 days | No | 9/25/23 | 4/29/24 | NA | 1
11342 | M9: B4 05.02 Conduct Assessments (CARESV1-69) | September 25, 2023 8:00 AM | August 26, 2024 5:00 PM | 359SS | 361SS | As Soon As Possible | NA | 231 | 0d | September 25, 2023 8:00 AM | December 30, 2025 5:00 PM | 568 days | No | 9/25/23 | 8/26/24 | NA | 1
11343 | M9: B5 05.09 Convene Child and Family Team (CARESV1-70) | September 25, 2023 8:00 AM | September 18, 2024 5:00 PM | 360SS | 362FF | As Soon As Possible | NA | 248 | 0d | September 25, 2023 8:00 AM | December 30, 2025 5:00 PM | 568 days | No | 9/25/23 | 9/18/24 | NA | 1
11344 | Milestone 9 (Case Management: Engagement and services) Jira # CARES V1-521 Complete | September 18, 2024 5:00 PM | September 18, 2024 5:00 PM | 361FF | 628FF | As Soon As Possible | NA | 0 | 0d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | 9/18/24 | 9/18/24 | NA | 1
11260 | Milestone 10: Case Closure (CARESV1-532) | February 27, 2023 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 693 | 467d | February 27, 2023 8:00 AM | December 30, 2025 5:00 PM | 714 days | No | 2/27/23 | NA | NA | 0.93999999999999995
11283 | M10: Research & Context Setting | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM |  |  | As Soon As Possible | NA | 80 | 0d | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 80 days | No | 2/27/23 | 6/20/23 | NA | 1
11261 | M10: RC: Finalize Value Hypothesis | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM |  | 366SS | Must Start On | 2/27/23 | 80 | 0d | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 80 days | No | 2/27/23 | 6/20/23 | NA | 1
11262 | M10: RC: Draft Service Maps | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 365SS | 367SS | As Soon As Possible | NA | 80 | 0d | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 80 days | No | 2/27/23 | 6/20/23 | NA | 1
11263 | M10: RC: Complete Legacy Analysis | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 366SS | 368SS | As Soon As Possible | NA | 80 | 0d | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 80 days | No | 2/27/23 | 6/20/23 | NA | 1
11264 | M10: RC: Finalize Epics | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 367SS | 369SS | As Soon As Possible | NA | 80 | 0d | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 80 days | No | 2/27/23 | 6/20/23 | NA | 1
11265 | M10: RC: Complete conceptual and epic-level Domain Model diagrams | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 368SS | 370SS | As Soon As Possible | NA | 80 | 0d | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 80 days | No | 2/27/23 | 6/20/23 | NA | 1
11266 | M10: RC: Define User Story titles | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 369SS | 371SS | As Soon As Possible | NA | 80 | 0d | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 80 days | No | 2/27/23 | 6/20/23 | NA | 1
11267 | M10: RC: Complete External Systems pre-analysis | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 370SS | 372SS | As Soon As Possible | NA | 80 | 0d | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 80 days | No | 2/27/23 | 6/20/23 | NA | 1
11268 | M10: RC: Facilitate Inception | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 371SS | 2527SS,374FS+12d | As Soon As Possible | NA | 80 | 0d | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 80 days | No | 2/27/23 | 6/20/23 | NA | 1
11269 | M10: BRC | July 10, 2023 8:00 AM | May 17, 2024 5:00 PM |  |  | As Soon As Possible | NA | 216 | 0d | July 10, 2023 8:00 AM | May 17, 2024 5:00 PM | 216 days | No | 7/10/23 | 5/17/24 | NA | 1
11284 | M10: B1 08.02 Perform Case Closure (CARESV1-14) | July 10, 2023 8:00 AM | May 17, 2024 5:00 PM | 372FS+12d | 375SS | As Soon As Possible | NA | 216 | 0d | July 10, 2023 8:00 AM | May 17, 2024 5:00 PM | 216 days | No | 7/10/23 | 5/17/24 | NA | 1
11285 | M10: B2 08.01 Assess for Case Closure (CARESV1-15) | July 10, 2023 8:00 AM | May 17, 2024 5:00 PM | 374SS |  | As Soon As Possible | NA | 216 | 0d | July 10, 2023 8:00 AM | May 17, 2024 5:00 PM | 216 days | No | 7/10/23 | 5/17/24 | NA | 1
11270 | M10: Design | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 200 | 0d | October 21, 2024 8:00 AM | April 11, 2025 5:00 PM | 242 days | No | 10/21/24 | 8/8/25 | NA | 1
11287 | M10: B1 08.02 Perform Case Closure (CARESV1-14) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 608SS | 378SS | As Soon As Possible | NA | 200 | 0d | October 21, 2024 8:00 AM | April 11, 2025 5:00 PM | 242 days | No | 10/21/24 | 8/8/25 | NA | 1
11288 | M10: B2 08.01 Assess for Case Closure (CARESV1-15) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 377SS | 380 | As Soon As Possible | NA | 200 | 0d | October 21, 2024 8:00 AM | April 11, 2025 5:00 PM | 242 days | No | 10/21/24 | 8/8/25 | NA | 1
11271 | M10: Build | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 39 | 505d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | NA | NA | 0.91000000000000003
11290 | M10: B1 08.02 Perform Case Closure (CARESV1-14) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 378 | 2264SS,2529SS,381SS | As Soon As Possible | NA | 39 | 505d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | NA | NA | 0.91000000000000003
11291 | M10: B2 08.01 Assess for Case Closure (CARESV1-15) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 380SS | 383SS,631FF | As Soon As Possible | NA | 39 | 150d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | NA | NA | 0.91000000000000003
11272 | M10: SIT | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 39 | 63d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | 8/11/25 | NA | NA | 0.89000000000000001
11293 | M10: B1 08.02 Perform Case Closure (CARESV1-14) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 381SS | 386,384SS | As Soon As Possible | NA | 39 | 26.98d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | 8/11/25 | NA | NA | 0.89000000000000001
11294 | M10: B2 08.01 Assess for Case Closure (CARESV1-15) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 383SS | 4510FF,632FF | As Soon As Possible | NA | 39 | 63d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | 8/11/25 | NA | NA | 0.89000000000000001
11273 | M10: State QA | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 38 | 467d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | 10/6/25 | NA | NA | 0.81999999999999995
11296 | M10: B1 08.02 Perform Case Closure (CARESV1-14) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 383 | 2530SS,4512SS,389SS,387SS | As Soon As Possible | NA | 38 | 467d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | 10/6/25 | NA | NA | 0.70999999999999996
11297 | M10: B2 08.01 Assess for Case Closure (CARESV1-15) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 386SS | 4512SS,633FF | As Soon As Possible | NA | 38 | 112d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | 10/6/25 | NA | NA | 0.93000000000000005
11274 | M10: Joint Review | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 38 | 4.72d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
11275 | M10: B1 08.02 Perform Case Closure (CARESV1-14) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 386SS | 2531SS,390SS | As Soon As Possible | NA | 38 | 4.72d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
11276 | M10: B2 08.01 Assess for Case Closure (CARESV1-15) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 389SS | 391 | As Soon As Possible | NA | 38 | 467d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
11277 | Milestone 10 (Case Closure) Jira # CARES V1-532 Complete | November 28, 2025 5:00 PM | November 28, 2025 5:00 PM | 390 |  | As Soon As Possible | NA | 0 | 467d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
5227 | Milestone 14: Warrants (CARESV1-529) | January 3, 2023 8:00 AM | December 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 500 | 0d | January 3, 2023 8:00 AM | December 30, 2024 5:00 PM | 500 days | No | 1/3/23 | 12/30/24 | NA | 1
5228 | M14: Research & Context Setting | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 119 | 0d | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 119 days | No | 1/3/23 | 6/22/23 | NA | 1
5229 | M14: RC: Finalize Value Hypothesis | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM |  | 395SS,396SS,397SS,398SS,399SS,400SS,401SS | As Soon As Possible | NA | 119 | 0d | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 119 days | No | 1/3/23 | 6/22/23 | NA | 1
5262 | M14: RC: Draft Service Maps | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 394SS | 396 | As Soon As Possible | NA | 119 | 0d | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 119 days | No | 1/3/23 | 6/22/23 | NA | 1
5263 | M14: RC: Complete Legacy Analysis | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 394SS,395 | 397 | As Soon As Possible | NA | 119 | 0d | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 119 days | No | 1/3/23 | 6/22/23 | NA | 1
5264 | M14: RC: Finalize Epics | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 394SS,396 | 398 | As Soon As Possible | NA | 119 | 0d | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 119 days | No | 1/3/23 | 6/22/23 | NA | 1
5265 | M14: RC: Complete conceptual and epic-level Domain Model diagrams | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 394SS,397 | 399 | As Soon As Possible | NA | 119 | 0d | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 119 days | No | 1/3/23 | 6/22/23 | NA | 1
5266 | M14: RC: Define User Story titles | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 394SS,398 | 400 | As Soon As Possible | NA | 119 | 0d | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 119 days | No | 1/3/23 | 6/22/23 | NA | 1
5267 | M14: RC: Complete External Systems pre-analysis | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 394SS,399 | 401 | As Soon As Possible | NA | 119 | 0d | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 119 days | No | 1/3/23 | 6/22/23 | NA | 1
5268 | M14: RC: Facilitate Inception | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 394SS,400 | 403FS-23d,2545SS | As Soon As Possible | NA | 119 | 0d | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 119 days | No | 1/3/23 | 6/22/23 | NA | 1
5269 | M14: BRC | May 22, 2023 8:00 AM | September 8, 2023 5:00 PM |  |  | As Soon As Possible | NA | 77 | 0d | May 22, 2023 8:00 AM | September 8, 2023 5:00 PM | 77 days | No | 5/22/23 | 9/8/23 | NA | 1
5270 | M14: B1 09.10 Create Warrants (CARESV1-35) | May 22, 2023 8:00 AM | September 8, 2023 5:00 PM | 401FS-23d | 405FS+20d,2278SS | As Soon As Possible | NA | 77 | 0d | May 22, 2023 8:00 AM | September 8, 2023 5:00 PM | 77 days | No | 5/22/23 | 9/8/23 | NA | 1
5271 | M14: Design | October 9, 2023 8:00 AM | February 23, 2024 5:00 PM |  |  | As Soon As Possible | NA | 93 | 0d | October 9, 2023 8:00 AM | February 23, 2024 5:00 PM | 93 days | No | 10/9/23 | 2/23/24 | NA | 1
5272 | M14: B1 09.10 Create Warrants (CARESV1-35) | October 9, 2023 8:00 AM | February 23, 2024 5:00 PM | 403FS+20d | 407SS+20d,2279SS,2546SS,2547SS,2548SS | As Soon As Possible | NA | 93 | 0d | October 9, 2023 8:00 AM | February 23, 2024 5:00 PM | 93 days | No | 10/9/23 | 2/23/24 | NA | 1
5274 | M14: Build | November 6, 2023 8:00 AM | March 22, 2024 5:00 PM |  |  | As Soon As Possible | NA | 93 | 0d | November 6, 2023 8:00 AM | March 22, 2024 5:00 PM | 93 days | No | 11/6/23 | 3/22/24 | NA | 1
5275 | M14: B1 09.10 Create Warrants (CARESV1-35) | November 6, 2023 8:00 AM | March 22, 2024 5:00 PM | 405SS+20d | 409SS,2280SS,2549SS | As Soon As Possible | NA | 93 | 0d | November 6, 2023 8:00 AM | March 22, 2024 5:00 PM | 93 days | No | 11/6/23 | 3/22/24 | NA | 1
5276 | M14: SIT | November 6, 2023 8:00 AM | March 22, 2024 5:00 PM |  |  | As Soon As Possible | NA | 93 | 0d | November 6, 2023 8:00 AM | March 22, 2024 5:00 PM | 93 days | No | 11/6/23 | 3/22/24 | NA | 1
5277 | M14: B1 09.10 Create Warrants (CARESV1-35) | November 6, 2023 8:00 AM | March 22, 2024 5:00 PM | 407SS | 411SS+22d,4551FS+289d | As Soon As Possible | NA | 93 | 0d | November 6, 2023 8:00 AM | March 22, 2024 5:00 PM | 93 days | No | 11/6/23 | 3/22/24 | NA | 1
5278 | M14: State QA | December 11, 2023 8:00 AM | April 9, 2024 5:00 PM |  |  | As Soon As Possible | NA | 82 | 0d | December 11, 2023 8:00 AM | April 9, 2024 5:00 PM | 82 days | No | 12/11/23 | 4/9/24 | NA | 1
5279 | M14: B1 09.10 Create Warrants (CARESV1-35) | December 11, 2023 8:00 AM | April 9, 2024 5:00 PM | 409SS+22d | 5457,2550SS,4556SS,413SS | As Soon As Possible | NA | 82 | 0d | December 11, 2023 8:00 AM | April 9, 2024 5:00 PM | 82 days | No | 12/11/23 | 4/9/24 | NA | 1
5280 | M14: Joint Review | December 11, 2023 8:00 AM | December 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 265 | 0d | December 11, 2023 8:00 AM | December 30, 2024 5:00 PM | 265 days | No | 12/11/23 | 12/30/24 | NA | 1
5281 | M14: B1 09.10 Create Warrants (CARESV1-35) | December 11, 2023 8:00 AM | December 30, 2024 5:00 PM | 411SS | 2551SS,414FF | As Soon As Possible | NA | 265 | 0d | December 11, 2023 8:00 AM | December 30, 2024 5:00 PM | 265 days | No | 12/11/23 | 12/30/24 | NA | 1
5284 | Milestone 14 (Warrants) Jira # CARES V1-529 Complete | December 30, 2024 5:00 PM | December 30, 2024 5:00 PM | 413FF |  | As Soon As Possible | NA | 0 | 0d | December 30, 2024 5:00 PM | December 30, 2024 5:00 PM | 0 days | Yes | 12/30/24 | 12/30/24 | NA | 1
11474 | Milestone 15: Court Hearing Framework (CARESV1-528) | January 30, 2023 8:00 AM | December 5, 2024 5:00 PM |  |  | As Soon As Possible | NA | 466 | 0d | January 30, 2023 8:00 AM | February 28, 2025 5:00 PM | 523 days | No | 1/30/23 | 12/5/24 | NA | 1
4557 | M15: Research & Context Setting | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 85 | 0d | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 85 days | No | 1/30/23 | 5/31/23 | NA | 1
4558 | M15: RC: Finalize Value Hypothesis | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM |  | 418SS | Must Start On | 1/30/23 | 85 | 0d | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 85 days | No | 1/30/23 | 5/31/23 | NA | 1
4559 | M15: RC: Draft Service Maps | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 417SS | 419SS | As Soon As Possible | NA | 85 | 0d | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 85 days | No | 1/30/23 | 5/31/23 | NA | 1
4560 | M15: RC: Complete Legacy Analysis | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 418SS | 420SS | As Soon As Possible | NA | 85 | 0d | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 85 days | No | 1/30/23 | 5/31/23 | NA | 1
4561 | M15: RC: Finalize Epics | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 419SS | 421SS | As Soon As Possible | NA | 85 | 0d | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 85 days | No | 1/30/23 | 5/31/23 | NA | 1
4562 | M15: RC: Complete conceptual and epic-level Domain Model diagrams | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 420SS | 422SS | As Soon As Possible | NA | 85 | 0d | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 85 days | No | 1/30/23 | 5/31/23 | NA | 1
4563 | M15: RC: Define User Story titles | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 421SS | 423SS | As Soon As Possible | NA | 85 | 0d | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 85 days | No | 1/30/23 | 5/31/23 | NA | 1
4564 | M15: RC: Complete External Systems pre-analysis | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 422SS | 424SS | As Soon As Possible | NA | 85 | 0d | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 85 days | No | 1/30/23 | 5/31/23 | NA | 1
4565 | M15: RC: Facilitate Inception | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 423SS | 426,2553SS | As Soon As Possible | NA | 85 | 0d | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 85 days | No | 1/30/23 | 5/31/23 | NA | 1
4566 | Milestone 15: BRC | June 1, 2023 8:00 AM | April 19, 2024 5:00 PM |  |  | As Soon As Possible | NA | 222 | 0d | June 1, 2023 8:00 AM | April 19, 2024 5:00 PM | 222 days | No | 6/1/23 | 4/19/24 | NA | 1
4567 | M15: B1 09.13 Process Court Results (CARESV1-68) | June 1, 2023 8:00 AM | April 19, 2024 5:00 PM | 424 | 427SS,1413SS-2d | As Soon As Possible | NA | 222 | 0d | June 1, 2023 8:00 AM | April 19, 2024 5:00 PM | 222 days | No | 6/1/23 | 4/19/24 | NA | 1
4568 | M15: B2 09.01 Prepare for Petition Hearing (CARESV1-90) | June 1, 2023 8:00 AM | April 19, 2024 5:00 PM | 426SS | 428SS | As Soon As Possible | NA | 222 | 0d | June 1, 2023 8:00 AM | April 19, 2024 5:00 PM | 222 days | No | 6/1/23 | 4/19/24 | NA | 1
4569 | M15: B3 JNET Interface (CARESV1-13969) | June 1, 2023 8:00 AM | April 19, 2024 5:00 PM | 427SS | 430SS+51d | As Soon As Possible | NA | 222 | 0d | June 1, 2023 8:00 AM | April 19, 2024 5:00 PM | 222 days | No | 6/1/23 | 4/19/24 | NA | 1
4575 | Milestone 15: Design | August 14, 2023 8:00 AM | July 12, 2024 5:00 PM |  |  | As Soon As Possible | NA | 229 | 0d | August 14, 2023 8:00 AM | July 12, 2024 5:00 PM | 229 days | No | 8/14/23 | 7/12/24 | NA | 1
4576 | M15: B1 09.13 Process Court Results (CARESV1-68) | August 14, 2023 8:00 AM | July 12, 2024 5:00 PM | 428SS+51d | 431SS,1347SS | As Soon As Possible | NA | 229 | 0d | August 14, 2023 8:00 AM | July 12, 2024 5:00 PM | 229 days | No | 8/14/23 | 7/12/24 | NA | 1
4577 | M15: B2 09.01 Prepare for Petition Hearing (CARESV1-90) | August 14, 2023 8:00 AM | July 12, 2024 5:00 PM | 430SS | 433FS+60d,1414SS+113d | As Soon As Possible | NA | 229 | 0d | August 14, 2023 8:00 AM | July 12, 2024 5:00 PM | 229 days | No | 8/14/23 | 7/12/24 | NA | 1
4581 | Milestone 15: Build | October 7, 2024 8:00 AM | December 5, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM | 76 days | No | 10/7/24 | 12/5/24 | NA | 1
4582 | M15: B1 09.13 Process Court Results (CARESV1-68) | October 7, 2024 8:00 AM | December 5, 2024 5:00 PM | 431FS+60d | 434FF,2284SS,2557SS,1348SS | As Soon As Possible | NA | 41 | 0d | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM | 76 days | No | 10/7/24 | 12/5/24 | NA | 1
4583 | M15: B2 09.01 Prepare for Petition Hearing (CARESV1-90) | October 7, 2024 8:00 AM | December 5, 2024 5:00 PM | 433FF | 436SS+20d | As Soon As Possible | NA | 41 | 0d | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM | 76 days | No | 10/7/24 | 12/5/24 | NA | 1
4916 | Milestone 15: SIT | November 4, 2024 8:00 AM | December 5, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | November 4, 2024 8:00 AM | January 28, 2025 5:00 PM | 56 days | No | 11/4/24 | 12/5/24 | NA | 1
4917 | M15: B1 09.13 Process Court Results (CARESV1-68) | November 4, 2024 8:00 AM | December 5, 2024 5:00 PM | 434SS+20d | 437FF,439SS,440SS,442SS,443SS | As Soon As Possible | NA | 21 | 0d | November 4, 2024 8:00 AM | January 28, 2025 5:00 PM | 56 days | No | 11/4/24 | 12/5/24 | NA | 1
4918 | M15: B2 09.01 Prepare for Petition Hearing (CARESV1-90) | November 4, 2024 8:00 AM | December 5, 2024 5:00 PM | 436FF | 4410FF | As Soon As Possible | NA | 21 | 0d | November 4, 2024 8:00 AM | January 28, 2025 5:00 PM | 56 days | No | 11/4/24 | 12/5/24 | NA | 1
4586 | Milestone 15: QA | November 4, 2024 8:00 AM | December 5, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | December 5, 2024 8:00 AM | February 28, 2025 5:00 PM | 58 days | No | 11/4/24 | 12/5/24 | NA | 1
4587 | M15: B1 09.13 Process Court Results (CARESV1-68) | November 4, 2024 8:00 AM | December 5, 2024 5:00 PM | 436SS | 2558SS,1349SS | As Soon As Possible | NA | 21 | 0d | December 5, 2024 8:00 AM | February 28, 2025 5:00 PM | 58 days | No | 11/4/24 | 12/5/24 | NA | 1
4588 | M15: B2 09.01 Prepare for Petition Hearing (CARESV1-90) | November 4, 2024 8:00 AM | December 5, 2024 5:00 PM | 436SS | 5395 | As Soon As Possible | NA | 21 | 0d | December 5, 2024 8:00 AM | February 28, 2025 5:00 PM | 58 days | No | 11/4/24 | 12/5/24 | NA | 1
4591 | Milestone 15: Joint Review | November 4, 2024 8:00 AM | December 5, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | December 5, 2024 8:00 AM | February 28, 2025 5:00 PM | 58 days | No | 11/4/24 | 12/5/24 | NA | 1
4592 | M15: B1 09.13 Process Court Results (CARESV1-68) | November 4, 2024 8:00 AM | December 5, 2024 5:00 PM | 436SS | 2559SS | As Soon As Possible | NA | 21 | 0d | December 5, 2024 8:00 AM | February 28, 2025 5:00 PM | 58 days | No | 11/4/24 | 12/5/24 | NA | 1
4593 | M15: B2 09.01 Prepare for Petition Hearing (CARESV1-90) | November 4, 2024 8:00 AM | December 5, 2024 5:00 PM | 436SS | 444FF | As Soon As Possible | NA | 21 | 0d | December 5, 2024 8:00 AM | February 28, 2025 5:00 PM | 58 days | No | 11/4/24 | 12/5/24 | NA | 1
10451 | Milestone 15: Court Hearing Framework (CARESV1-528) Complete | December 5, 2024 5:00 PM | December 5, 2024 5:00 PM | 443FF |  | As Soon As Possible | NA | 0 | 0d | February 28, 2025 5:00 PM | February 28, 2025 5:00 PM | 0 days | Yes | 12/5/24 | 12/5/24 | NA | 1
5285 | Milestone 19: Request Initial Determination (CARESV1-515) | November 7, 2022 8:00 AM | November 18, 2024 5:00 PM |  |  | As Soon As Possible | NA | 509 | 0d | November 7, 2022 8:00 AM | February 27, 2025 5:00 PM | 576 days | No | 11/7/22 | 11/18/24 | NA | 1
5286 | M19: Research & Context Setting | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM |  |  | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
5287 | M19: RC: Finalize Value Hypothesis | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM |  | 448SS,449SS,450SS,451SS,452SS,453SS,454SS,2579SS | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
5288 | M19: RC: Draft Service Maps | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 447SS | 449 | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
5289 | M19: RC: Complete Legacy Analysis | November 7, 2022 8:00 AM | November 30, 2022 5:00 PM | 447SS,448 | 450 | As Soon As Possible | NA | 15 | 0d | November 7, 2022 8:00 AM | November 30, 2022 5:00 PM | 15 days | No | 11/7/22 | 11/30/22 | NA | 1
5304 | M19: RC: Finalize Epics | November 7, 2022 8:00 AM | November 11, 2022 5:00 PM | 447SS,449 | 451 | As Soon As Possible | NA | 5 | 0d | November 7, 2022 8:00 AM | November 11, 2022 5:00 PM | 5 days | No | 11/7/22 | 11/11/22 | NA | 1
5305 | M19: RC: Complete conceptual and epic-level Domain Model diagrams | November 7, 2022 8:00 AM | December 21, 2022 5:00 PM | 447SS,450 | 452 | As Soon As Possible | NA | 30 | 0d | November 7, 2022 8:00 AM | December 21, 2022 5:00 PM | 30 days | No | 11/7/22 | 12/21/22 | NA | 1
5306 | M19: RC: Define User Story titles | November 7, 2022 8:00 AM | November 21, 2022 5:00 PM | 447SS,451 | 453 | As Soon As Possible | NA | 10 | 0d | November 7, 2022 8:00 AM | November 21, 2022 5:00 PM | 10 days | No | 11/7/22 | 11/21/22 | NA | 1
5307 | M19: RC: Complete External Systems pre-analysis | November 7, 2022 8:00 AM | December 7, 2022 5:00 PM | 447SS,452 | 454 | As Soon As Possible | NA | 20 | 0d | November 7, 2022 8:00 AM | December 7, 2022 5:00 PM | 20 days | No | 11/7/22 | 12/7/22 | NA | 1
5308 | M19: RC: Facilitate Inception | November 7, 2022 8:00 AM | December 7, 2022 5:00 PM | 447SS,453 | 456FS+34d | As Soon As Possible | NA | 20 | 0d | November 7, 2022 8:00 AM | December 7, 2022 5:00 PM | 20 days | No | 11/7/22 | 12/7/22 | NA | 1
5309 | M19: BRC | January 30, 2023 8:00 AM | February 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 254 | 0d | January 30, 2023 8:00 AM | February 2, 2024 5:00 PM | 254 days | No | 1/30/23 | 2/2/24 | NA | 1
5310 | M19: B1 19.01 Request Initial Eligibility Determination (CARESV1-5) | January 30, 2023 8:00 AM | February 2, 2024 5:00 PM | 454FS+34d | 457SS,2298SS | As Soon As Possible | NA | 254 | 0d | January 30, 2023 8:00 AM | February 2, 2024 5:00 PM | 254 days | No | 1/30/23 | 2/2/24 | NA | 1
5311 | M19: B2 FCED (Foster Care Eligibility Determination) Interface - Determine Eligibility (CARESV1-13926) | January 30, 2023 8:00 AM | February 2, 2024 5:00 PM | 456SS | 459FS-138d | As Soon As Possible | NA | 254 | 0d | January 30, 2023 8:00 AM | February 2, 2024 5:00 PM | 254 days | No | 1/30/23 | 2/2/24 | NA | 1
5312 | M19: Design | July 17, 2023 8:00 AM | February 23, 2024 5:00 PM |  |  | As Soon As Possible | NA | 152 | 0d | July 17, 2023 8:00 AM | February 23, 2024 5:00 PM | 152 days | No | 7/17/23 | 2/23/24 | NA | 1
5313 | M19: B1 19.01 Request Initial Eligibility Determination (CARESV1-5) | July 17, 2023 8:00 AM | February 23, 2024 5:00 PM | 457FS-138d | 460SS,2299SS,2580SS,2581SS,2582SS | As Soon As Possible | NA | 152 | 0d | July 17, 2023 8:00 AM | February 23, 2024 5:00 PM | 152 days | No | 7/17/23 | 2/23/24 | NA | 1
5314 | M19: B2 FCED (Foster Care Eligibility Determination) Interface - Determine Eligibility (CARESV1-13926) | July 17, 2023 8:00 AM | February 23, 2024 5:00 PM | 459SS | 462SS+309d | As Soon As Possible | NA | 152 | 0d | July 17, 2023 8:00 AM | February 23, 2024 5:00 PM | 152 days | No | 7/17/23 | 2/23/24 | NA | 1
5316 | M19: Build | October 7, 2024 8:00 AM | November 18, 2024 5:00 PM |  |  | As Soon As Possible | NA | 30 | 0d | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM | 76 days | No | 10/7/24 | 11/18/24 | NA | 1
5317 | M19: B1 19.01 Request Initial Eligibility Determination (CARESV1-5) | October 7, 2024 8:00 AM | November 18, 2024 5:00 PM | 460SS+309d | 463SS,2300SS,511SS-28d | As Soon As Possible | NA | 30 | 0d | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM | 76 days | No | 10/7/24 | 11/18/24 | NA | 1
5318 | M19: B2 FCED (Foster Care Eligibility Determination) Interface - Determine Eligibility (CARESV1-13926) | October 7, 2024 8:00 AM | November 18, 2024 5:00 PM | 462SS | 465SS+20d,2996 | As Soon As Possible | NA | 30 | 0d | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM | 76 days | No | 10/7/24 | 11/18/24 | NA | 1
5319 | M19: SIT | November 4, 2024 8:00 AM | November 18, 2024 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | November 4, 2024 8:00 AM | January 28, 2025 5:00 PM | 56 days | No | 11/4/24 | 11/18/24 | NA | 1
5320 | M19: B1 19.01 Request Initial Eligibility Determination (CARESV1-5) | November 4, 2024 8:00 AM | November 18, 2024 5:00 PM | 463SS+20d | 466SS,468SS,469SS | As Soon As Possible | NA | 10 | 0d | November 4, 2024 8:00 AM | January 28, 2025 5:00 PM | 56 days | No | 11/4/24 | 11/18/24 | NA | 1
5321 | M19: B2 FCED (Foster Care Eligibility Determination) Interface - Determine Eligibility (CARESV1-13926) | November 4, 2024 8:00 AM | November 18, 2024 5:00 PM | 465SS | 4421FF | As Soon As Possible | NA | 10 | 0d | November 4, 2024 8:00 AM | January 28, 2025 5:00 PM | 56 days | No | 11/4/24 | 11/18/24 | NA | 1
5322 | M19: State QA | November 4, 2024 8:00 AM | November 18, 2024 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | December 9, 2024 8:00 AM | February 27, 2025 5:00 PM | 55 days | No | 11/4/24 | 11/18/24 | NA | 1
5323 | M19: B1 19.01 Request Initial Eligibility Determination (CARESV1-5) | November 4, 2024 8:00 AM | November 18, 2024 5:00 PM | 465SS | 471SS,4422SS | As Soon As Possible | NA | 10 | 0d | December 9, 2024 8:00 AM | February 27, 2025 5:00 PM | 55 days | No | 11/4/24 | 11/18/24 | NA | 1
5324 | M19: B2 FCED (Foster Care Eligibility Determination) Interface - Determine Eligibility (CARESV1-13926) | November 4, 2024 8:00 AM | November 18, 2024 5:00 PM | 465SS | 5401,4422SS | As Soon As Possible | NA | 10 | 0d | December 9, 2024 8:00 AM | February 27, 2025 5:00 PM | 55 days | No | 11/4/24 | 11/18/24 | NA | 1
5325 | M19: Joint Review | November 4, 2024 8:00 AM | November 18, 2024 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | December 9, 2024 8:00 AM | February 27, 2025 5:00 PM | 55 days | No | 11/4/24 | 11/18/24 | NA | 1
5326 | M19: B1 19.01 Request Initial Eligibility Determination (CARESV1-5) | November 4, 2024 8:00 AM | November 18, 2024 5:00 PM | 468SS | 472SS | As Soon As Possible | NA | 10 | 0d | December 9, 2024 8:00 AM | February 27, 2025 5:00 PM | 55 days | No | 11/4/24 | 11/18/24 | NA | 1
5327 | M19: B2 FCED (Foster Care Eligibility Determination) Interface - Determine Eligibility (CARESV1-13926) | November 4, 2024 8:00 AM | November 18, 2024 5:00 PM | 471SS | 473 | As Soon As Possible | NA | 10 | 0d | December 9, 2024 8:00 AM | February 27, 2025 5:00 PM | 55 days | No | 11/4/24 | 11/18/24 | NA | 1
5331 | Milestone 19 (Request Determination) Jira # CARES V1-515 Complete | November 18, 2024 5:00 PM | November 18, 2024 5:00 PM | 472 |  | As Soon As Possible | NA | 0 | 0d | February 27, 2025 5:00 PM | February 27, 2025 5:00 PM | 0 days | Yes | 11/18/24 | 11/18/24 | NA | 1
5339 | Milestone 20: Redetermine Eligibility & Placement/ Information Change (CARESV1-512) | June 19, 2023 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 426 | 0d | June 19, 2023 8:00 AM | February 28, 2025 5:00 PM | 426 days | No | 6/19/23 | 2/28/25 | NA | 1
5340 | M20: Research & Context Setting | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM |  |  | As Soon As Possible | NA | 80 | 0d | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 days | No | 6/19/23 | 10/10/23 | NA | 1
5341 | M20: RC: Finalize Value Hypothesis | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM |  | 477SS,478SS,479SS,480SS,481SS,482SS,483SS | As Soon As Possible | NA | 80 | 0d | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 days | No | 6/19/23 | 10/10/23 | NA | 1
5342 | M20: RC: Draft Service Maps | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 476SS | 478 | As Soon As Possible | NA | 80 | 0d | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 days | No | 6/19/23 | 10/10/23 | NA | 1
5343 | M20: RC: Complete Legacy Analysis | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 476SS,477 | 479 | As Soon As Possible | NA | 80 | 0d | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 days | No | 6/19/23 | 10/10/23 | NA | 1
5344 | M20: RC: Finalize Epics | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 476SS,478 | 480 | As Soon As Possible | NA | 80 | 0d | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 days | No | 6/19/23 | 10/10/23 | NA | 1
5345 | M20: RC: Complete conceptual and epic-level Domain Model diagrams | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 476SS,479 | 481 | As Soon As Possible | NA | 80 | 0d | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 days | No | 6/19/23 | 10/10/23 | NA | 1
5346 | M20: RC: Define User Story titles | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 476SS,480 | 482 | As Soon As Possible | NA | 80 | 0d | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 days | No | 6/19/23 | 10/10/23 | NA | 1
5347 | M20: RC: Complete External Systems pre-analysis | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 476SS,481 | 483 | As Soon As Possible | NA | 80 | 0d | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 days | No | 6/19/23 | 10/10/23 | NA | 1
5348 | M20: RC: Facilitate Inception | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 476SS,482 | 485FS-6d | As Soon As Possible | NA | 80 | 0d | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 days | No | 6/19/23 | 10/10/23 | NA | 1
5349 | M20: BRC | October 3, 2023 8:00 AM | April 26, 2024 5:00 PM |  |  | As Soon As Possible | NA | 141 | 0d | October 3, 2023 8:00 AM | April 26, 2024 5:00 PM | 141 days | No | 10/3/23 | 4/26/24 | NA | 1
5350 | M20: B1 19.02 Exchange new information between CARES& CalSAWS (CARESV1-24) | October 3, 2023 8:00 AM | April 26, 2024 5:00 PM | 483FS-6d | 486SS,2302SS | As Soon As Possible | NA | 141 | 0d | October 3, 2023 8:00 AM | April 26, 2024 5:00 PM | 141 days | No | 10/3/23 | 4/26/24 | NA | 1
5351 | M20: B2 19.04 Re-determine eligibility (CARESV1-7) | October 3, 2023 8:00 AM | April 26, 2024 5:00 PM | 485SS | 487SS | As Soon As Possible | NA | 141 | 0d | October 3, 2023 8:00 AM | April 26, 2024 5:00 PM | 141 days | No | 10/3/23 | 4/26/24 | NA | 1
5352 | M20: B3 FCED (Foster Care Eligibility Determination) Interface - Re-determine Eligibility (CARESV1-13929) | October 3, 2023 8:00 AM | April 26, 2024 5:00 PM | 486SS | 489FS-58d | As Soon As Possible | NA | 141 | 0d | October 3, 2023 8:00 AM | April 26, 2024 5:00 PM | 141 days | No | 10/3/23 | 4/26/24 | NA | 1
5353 | M20: Design | February 5, 2024 8:00 AM | May 21, 2024 5:00 PM |  |  | As Soon As Possible | NA | 75 | 0d | February 5, 2024 8:00 AM | May 21, 2024 5:00 PM | 75 days | No | 2/5/24 | 5/21/24 | NA | 1
5354 | M20: B1 19.02 Exchange new information between CARES& CalSAWS (CARESV1-24) | February 5, 2024 8:00 AM | May 21, 2024 5:00 PM | 487FS-58d | 490SS,2303SS | As Soon As Possible | NA | 75 | 0d | February 5, 2024 8:00 AM | May 21, 2024 5:00 PM | 75 days | No | 2/5/24 | 5/21/24 | NA | 1
5355 | M20: B2 19.04 Re-determine eligibility (CARESV1-7) | February 5, 2024 8:00 AM | May 21, 2024 5:00 PM | 489SS | 491SS | As Soon As Possible | NA | 75 | 0d | February 5, 2024 8:00 AM | May 21, 2024 5:00 PM | 75 days | No | 2/5/24 | 5/21/24 | NA | 1
5356 | M20: B3 FCED (Foster Care Eligibility Determination) Interface - Re-determine Eligibility (CARESV1-13929) | February 5, 2024 8:00 AM | May 21, 2024 5:00 PM | 490SS | 493FS+96d | As Soon As Possible | NA | 75 | 0d | February 5, 2024 8:00 AM | May 21, 2024 5:00 PM | 75 days | No | 2/5/24 | 5/21/24 | NA | 1
5358 | M20: Build | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 76 | 0d | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM | 76 days | No | 10/7/24 | 1/28/25 | NA | 1
5359 | M20: B1 19.02 Exchange new information between CARES& CalSAWS (CARESV1-24) | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM | 491FS+96d | 494SS,2304SS | As Soon As Possible | NA | 76 | 0d | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM | 76 days | No | 10/7/24 | 1/28/25 | NA | 1
5360 | M20: B2 19.04 Re-determine eligibility (CARESV1-7) | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM | 493SS | 495SS,497SS+20d | As Soon As Possible | NA | 76 | 0d | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM | 76 days | No | 10/7/24 | 1/28/25 | NA | 1
5361 | M20: B3 FCED (Foster Care Eligibility Determination) Interface - Re-determine Eligibility (CARESV1-13929) | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM | 494SS |  | As Soon As Possible | NA | 76 | 0d | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM | 76 days | No | 10/7/24 | 1/28/25 | NA | 1
5362 | M20: SIT | November 4, 2024 8:00 AM | January 28, 2025 5:00 PM |  | 2995,2999 | As Soon As Possible | NA | 56 | 0d | November 4, 2024 8:00 AM | January 28, 2025 5:00 PM | 56 days | No | 11/4/24 | 1/28/25 | NA | 1
5363 | M20: B1 19.02 Exchange new information between CARES& CalSAWS (CARESV1-24) | November 4, 2024 8:00 AM | January 28, 2025 5:00 PM | 494SS+20d | 498SS | As Soon As Possible | NA | 56 | 0d | November 4, 2024 8:00 AM | January 28, 2025 5:00 PM | 56 days | No | 11/4/24 | 1/28/25 | NA | 1
5364 | M20: B2 19.04 Re-determine eligibility (CARESV1-7) | November 4, 2024 8:00 AM | January 28, 2025 5:00 PM | 497SS | 499SS | As Soon As Possible | NA | 56 | 0d | November 4, 2024 8:00 AM | January 28, 2025 5:00 PM | 56 days | No | 11/4/24 | 1/28/25 | NA | 1
5365 | M20: B3 FCED (Foster Care Eligibility Determination) Interface - Re-determine Eligibility (CARESV1-13929) | November 4, 2024 8:00 AM | January 28, 2025 5:00 PM | 498SS | 501SS+22d,4432FF,1495SS-1d | As Soon As Possible | NA | 56 | 0d | November 4, 2024 8:00 AM | January 28, 2025 5:00 PM | 56 days | No | 11/4/24 | 1/28/25 | NA | 1
5366 | M20: State QA | December 9, 2024 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 56 | 0d | December 9, 2024 8:00 AM | February 28, 2025 5:00 PM | 56 days | No | 12/9/24 | 2/28/25 | NA | 1
5367 | M20: B1 19.02 Exchange new information between CARES& CalSAWS (CARESV1-24) | December 9, 2024 8:00 AM | February 28, 2025 5:00 PM | 499SS+22d | 502SS,503SS,4433SS | As Soon As Possible | NA | 56 | 0d | December 9, 2024 8:00 AM | February 28, 2025 5:00 PM | 56 days | No | 12/9/24 | 2/28/25 | NA | 1
5368 | M20: B2 19.04 Re-determine eligibility (CARESV1-7) | December 9, 2024 8:00 AM | February 28, 2025 5:00 PM | 501SS | 4433SS | As Soon As Possible | NA | 56 | 0d | December 9, 2024 8:00 AM | February 28, 2025 5:00 PM | 56 days | No | 12/9/24 | 2/28/25 | NA | 1
5369 | M20: B3 FCED (Foster Care Eligibility Determination) Interface - Re-determine Eligibility (CARESV1-13929) | December 9, 2024 8:00 AM | February 28, 2025 5:00 PM | 501SS | 505SS,506SS,507SS,5407,4433SS | As Soon As Possible | NA | 56 | 0d | December 9, 2024 8:00 AM | February 28, 2025 5:00 PM | 56 days | No | 12/9/24 | 2/28/25 | NA | 1
5370 | M20: Joint Review | December 9, 2024 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 56 | 0d | December 9, 2024 8:00 AM | February 28, 2025 5:00 PM | 56 days | No | 12/9/24 | 2/28/25 | NA | 1
5371 | M20: B1 19.02 Exchange new information between CARES& CalSAWS (CARESV1-24) | December 9, 2024 8:00 AM | February 28, 2025 5:00 PM | 503SS | 506FS-48d | As Soon As Possible | NA | 56 | 0d | December 9, 2024 8:00 AM | February 28, 2025 5:00 PM | 56 days | No | 12/9/24 | 2/28/25 | NA | 1
5372 | M20: B2 19.04 Re-determine eligibility (CARESV1-7) | December 9, 2024 8:00 AM | February 28, 2025 5:00 PM | 503SS,505FS-48d | 507FS-48d | As Soon As Possible | NA | 56 | 0d | December 9, 2024 8:00 AM | February 28, 2025 5:00 PM | 56 days | No | 12/9/24 | 2/28/25 | NA | 1
5373 | M20: B3 FCED (Foster Care Eligibility Determination) Interface - Re-determine Eligibility (CARESV1-13929) | December 9, 2024 8:00 AM | February 28, 2025 5:00 PM | 503SS,506FS-48d | 508FF | As Soon As Possible | NA | 56 | 0d | December 9, 2024 8:00 AM | February 28, 2025 5:00 PM | 56 days | No | 12/9/24 | 2/28/25 | NA | 1
5332 | Milestone 20 (Redetermine Eligibility) Jira # CARES V1-512 Complete | February 28, 2025 5:00 PM | February 28, 2025 5:00 PM | 507FF |  | As Soon As Possible | NA | 0 | 0d | February 28, 2025 5:00 PM | February 28, 2025 5:00 PM | 0 days | Yes | 2/28/25 | 2/28/25 | NA | 1
6702 | Milestone 29: Federal Reports (CARESV1-503) | August 28, 2024 8:00 AM | January 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 357 | 425d | August 28, 2024 8:00 AM | January 30, 2026 5:00 PM | 357 days | No | 8/28/24 | NA | NA | 0.40000000000000002
6836 | M29: Context Setting | August 28, 2024 8:00 AM | November 26, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | August 28, 2024 8:00 AM | November 26, 2024 5:00 PM | 64 days | No | 8/28/24 | 11/26/24 | NA | 1
6706 | M29: RC: Finalize Epics | August 28, 2024 8:00 AM | September 3, 2024 5:00 PM | 462SS-28d | 512,537FS+9d | As Soon As Possible | NA | 5 | 0d | August 28, 2024 8:00 AM | September 3, 2024 5:00 PM | 5 days | No | 8/28/24 | 9/3/24 | NA | 1
6707 | M29: RC: Complete conceptual and epic-level Domain Model diagrams | September 4, 2024 8:00 AM | October 1, 2024 5:00 PM | 511 | 513 | As Soon As Possible | NA | 20 | 0d | September 4, 2024 8:00 AM | October 1, 2024 5:00 PM | 20 days | No | 9/4/24 | 10/1/24 | NA | 1
6708 | M29: RC: Define User Story titles | October 2, 2024 8:00 AM | October 22, 2024 5:00 PM | 512 | 514 | As Soon As Possible | NA | 15 | 0d | October 2, 2024 8:00 AM | October 22, 2024 5:00 PM | 15 days | No | 10/2/24 | 10/22/24 | NA | 1
6709 | M29: RC: Complete External Systems pre-analysis | October 23, 2024 8:00 AM | November 13, 2024 5:00 PM | 513 | 515 | As Soon As Possible | NA | 15 | 0d | October 23, 2024 8:00 AM | November 13, 2024 5:00 PM | 15 days | No | 10/23/24 | 11/13/24 | NA | 1
6710 | M29: RC: Facilitate Inception | November 14, 2024 8:00 AM | November 26, 2024 5:00 PM | 514 | 517SS-7d | As Soon As Possible | NA | 9 | 0d | November 14, 2024 8:00 AM | November 26, 2024 5:00 PM | 9 days | No | 11/14/24 | 11/26/24 | NA | 1
6837 | M29: BRC | November 4, 2024 8:00 AM | December 27, 2024 5:00 PM |  |  | As Soon As Possible | NA | 36 | 0d | November 4, 2024 8:00 AM | December 27, 2024 5:00 PM | 36 days | No | 11/4/24 | 12/27/24 | NA | 1
6838 | M29: B1: 22.01 Generate Federal Data Extracts (for exchange with CDSS RAD Division, counties, other data partners) (CARESV1-93) | November 4, 2024 8:00 AM | December 27, 2024 5:00 PM | 515SS-7d | 518SS | As Soon As Possible | NA | 36 | 0d | November 4, 2024 8:00 AM | December 27, 2024 5:00 PM | 36 days | No | 11/4/24 | 12/27/24 | NA | 1
6839 | M29: B2: 22.02 Generate Federal (Statewide) Indicators (CARESV1-109) | November 4, 2024 8:00 AM | December 27, 2024 5:00 PM | 517SS | 520FS+125d | As Soon As Possible | NA | 36 | 0d | November 4, 2024 8:00 AM | December 27, 2024 5:00 PM | 36 days | No | 11/4/24 | 12/27/24 | NA | 1
6840 | M29: Design | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 29 | 0d | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 days | No | 6/30/25 | 8/8/25 | NA | 1
6841 | M29: B1: 22.01 Generate Federal Data Extracts (for exchange with CDSS RAD Division, counties, other data partners) (CARESV1-93) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 518FS+125d | 521SS,557SS | As Soon As Possible | NA | 29 | 0d | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 days | No | 6/30/25 | 8/8/25 | NA | 1
6842 | M29: B2: 22.02 Generate Federal (Statewide) Indicators (CARESV1-109) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 520SS |  | As Soon As Possible | NA | 29 | 0d | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 days | No | 6/30/25 | 8/8/25 | NA | 1
6843 | M29: Build | September 10, 2025 8:00 AM | December 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 77 | 446d | September 10, 2025 8:00 AM | December 30, 2025 5:00 PM | 77 days | No | 9/10/25 | NA | NA | 0.29999999999999999
6844 | M29: B1: 22.01 Generate Federal Data Extracts (for exchange with CDSS RAD Division, counties, other data partners) (CARESV1-93) | September 10, 2025 8:00 AM | December 30, 2025 5:00 PM | 1433FF+21d,1148FF+6d | 524SS,4712SS+37d | As Soon As Possible | NA | 77 | 446d | September 10, 2025 8:00 AM | December 30, 2025 5:00 PM | 77 days | No | 9/10/25 | NA | NA | 0.29999999999999999
6845 | M29: B2: 22.02 Generate Federal (Statewide) Indicators (CARESV1-109) | September 10, 2025 8:00 AM | December 30, 2025 5:00 PM | 523SS | 526SS+19d,4712SS+37d | As Soon As Possible | NA | 77 | 446d | September 10, 2025 8:00 AM | December 30, 2025 5:00 PM | 77 days | No | 9/10/25 | NA | NA | 0.29999999999999999
6846 | M29: SIT | October 7, 2025 8:00 AM | December 30, 2025 5:00 PM |  | 1842FS-3d,1843 | As Soon As Possible | NA | 58 | 0d | October 7, 2025 8:00 AM | December 30, 2025 5:00 PM | 58 days | No | 10/7/25 | NA | NA | 7.0000000000000007E-2
6847 | M29: B1: 22.01 Generate Federal Data Extracts (for exchange with CDSS RAD Division, counties, other data partners) (CARESV1-93) | October 7, 2025 8:00 AM | December 30, 2025 5:00 PM | 524SS+19d | 527SS | As Soon As Possible | NA | 58 | -13d | October 7, 2025 8:00 AM | December 30, 2025 5:00 PM | 58 days | No | 10/7/25 | NA | NA | 7.0000000000000007E-2
6848 | M29: B2: 22.02 Generate Federal (Statewide) Indicators (CARESV1-109) | October 7, 2025 8:00 AM | December 30, 2025 5:00 PM | 526SS | 529SS+22d | As Soon As Possible | NA | 58 | -13d | October 7, 2025 8:00 AM | December 30, 2025 5:00 PM | 58 days | No | 10/7/25 | NA | NA | 7.0000000000000007E-2
6849 | M29: State QA | November 6, 2025 8:00 AM | January 30, 2026 5:00 PM |  | 1850FS-1d | As Soon As Possible | NA | 57 | 0d | November 6, 2025 8:00 AM | January 30, 2026 5:00 PM | 57 days | No | 11/6/25 | NA | NA | 0.25
6850 | M29: B1: 22.01 Generate Federal Data Extracts (for exchange with CDSS RAD Division, counties, other data partners) (CARESV1-93) | November 6, 2025 8:00 AM | January 30, 2026 5:00 PM | 527SS+22d | 530SS,532SS,4717SS | As Soon As Possible | NA | 57 | -1d | November 6, 2025 8:00 AM | January 30, 2026 5:00 PM | 57 days | No | 11/6/25 | NA | NA | 0.5
6851 | M29: B2: 22.02 Generate Federal (Statewide) Indicators (CARESV1-109) | November 6, 2025 8:00 AM | January 30, 2026 5:00 PM | 529SS | 4717SS | As Soon As Possible | NA | 57 | -1d | November 6, 2025 8:00 AM | January 30, 2026 5:00 PM | 57 days | No | NA | NA | NA | 0
6852 | M29: Joint Review | November 6, 2025 8:00 AM | January 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 57 | 127d | November 6, 2025 8:00 AM | January 30, 2026 5:00 PM | 57 days | No | NA | NA | NA | 0
6853 | M29: B1: 22.01 Generate Federal Data Extracts (for exchange with CDSS RAD Division, counties, other data partners) (CARESV1-93) | November 6, 2025 8:00 AM | January 30, 2026 5:00 PM | 529SS | 533SS | As Soon As Possible | NA | 57 | 127d | November 6, 2025 8:00 AM | January 30, 2026 5:00 PM | 57 days | No | NA | NA | NA | 0
6854 | M29: B2: 22.02 Generate Federal (Statewide) Indicators (CARESV1-109) | November 6, 2025 8:00 AM | January 30, 2026 5:00 PM | 532SS | 534FF | As Soon As Possible | NA | 57 | 127d | November 6, 2025 8:00 AM | January 30, 2026 5:00 PM | 57 days | No | NA | NA | NA | 0
10445 | Milestone 29: Federal Reports (CARESV1-503) Complete | January 30, 2026 5:00 PM | January 30, 2026 5:00 PM | 533FF | 5618 | As Soon As Possible | NA | 0 | 127d | January 30, 2026 5:00 PM | January 30, 2026 5:00 PM | 0 days | Yes | NA | NA | NA | 0
6711 | Milestone 30: State Reports (CARESV1-502) | September 17, 2024 8:00 AM | January 27, 2026 5:00 PM |  |  | As Soon As Possible | NA | 340 | 428d | September 17, 2024 8:00 AM | January 27, 2026 5:00 PM | 340 days | No | 9/17/24 | NA | NA | 0.48999999999999999
6876 | M30: Context Setting | September 17, 2024 8:00 AM | November 27, 2024 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | September 17, 2024 8:00 AM | November 27, 2024 5:00 PM | 51 days | No | 9/17/24 | 11/27/24 | NA | 1
6715 | M30: RC: Finalize Epics | September 17, 2024 8:00 AM | September 23, 2024 5:00 PM | 511FS+9d | 538 | As Soon As Possible | NA | 5 | 0d | September 17, 2024 8:00 AM | September 23, 2024 5:00 PM | 5 days | No | 9/17/24 | 9/23/24 | NA | 1
6716 | M30: RC: Complete conceptual and epic-level Domain Model diagrams | September 24, 2024 8:00 AM | October 21, 2024 5:00 PM | 537 | 539SS+5d | As Soon As Possible | NA | 20 | 0d | September 24, 2024 8:00 AM | October 21, 2024 5:00 PM | 20 days | No | 9/24/24 | 10/21/24 | NA | 1
6717 | M30: RC: Define User Story titles | October 1, 2024 8:00 AM | October 21, 2024 5:00 PM | 538SS+5d | 540 | As Soon As Possible | NA | 15 | 0d | October 1, 2024 8:00 AM | October 21, 2024 5:00 PM | 15 days | No | 10/1/24 | 10/21/24 | NA | 1
6718 | M30: RC: Complete External Systems pre-analysis | October 22, 2024 8:00 AM | November 12, 2024 5:00 PM | 539 | 541 | As Soon As Possible | NA | 15 | 0d | October 22, 2024 8:00 AM | November 12, 2024 5:00 PM | 15 days | No | 10/22/24 | 11/12/24 | NA | 1
6719 | M30: RC: Facilitate Inception | November 13, 2024 8:00 AM | November 27, 2024 5:00 PM | 540 | 543FS-4d | As Soon As Possible | NA | 11 | 0d | November 13, 2024 8:00 AM | November 27, 2024 5:00 PM | 11 days | No | 11/13/24 | 11/27/24 | NA | 1
6856 | M30: BRC | November 22, 2024 8:00 AM | January 24, 2025 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | November 22, 2024 8:00 AM | January 24, 2025 5:00 PM | 41 days | No | 11/22/24 | 1/24/25 | NA | 1
6857 | M30: B1: 22.03 Generate State Metrics (CARESV1-76) | November 22, 2024 8:00 AM | January 24, 2025 5:00 PM | 541FS-4d | 545FS+125d | As Soon As Possible | NA | 41 | 0d | November 22, 2024 8:00 AM | January 24, 2025 5:00 PM | 41 days | No | 11/22/24 | 1/24/25 | NA | 1
6858 | M30: Design | July 25, 2025 8:00 AM | September 4, 2025 5:00 PM |  |  | As Soon As Possible | NA | 29 | 26.18d | July 25, 2025 8:00 AM | September 4, 2025 5:00 PM | 29 days | No | 7/25/25 | NA | NA | 0.83999999999999997
6859 | M30: B1: 22.03 Generate State Metrics (CARESV1-76) | July 25, 2025 8:00 AM | September 4, 2025 5:00 PM | 543FS+125d | 547,4712SS+37d | As Soon As Possible | NA | 29 | 26.18d | July 25, 2025 8:00 AM | September 4, 2025 5:00 PM | 29 days | No | 7/25/25 | NA | NA | 0.83999999999999997
6860 | M30: Build | September 5, 2025 8:00 AM | December 24, 2025 5:00 PM |  |  | As Soon As Possible | NA | 77 | 449d | September 5, 2025 8:00 AM | December 24, 2025 5:00 PM | 77 days | No | 9/5/25 | NA | NA | 0.34000000000000002
6861 | M30: B1: 22.03 Generate State Metrics (CARESV1-76) | September 5, 2025 8:00 AM | December 24, 2025 5:00 PM | 545 | 549SS+19d | As Soon As Possible | NA | 77 | 449d | September 5, 2025 8:00 AM | December 24, 2025 5:00 PM | 77 days | No | 9/5/25 | NA | NA | 0.34000000000000002
6862 | M30: SIT | October 2, 2025 8:00 AM | December 24, 2025 5:00 PM |  | 1842FS-3d,1843 | As Soon As Possible | NA | 58 | 0d | October 2, 2025 8:00 AM | December 24, 2025 5:00 PM | 58 days | No | 10/2/25 | NA | NA | 0.12
6863 | M30: B1: 22.03 Generate State Metrics (CARESV1-76) | October 2, 2025 8:00 AM | December 24, 2025 5:00 PM | 547SS+19d | 551SS+22d,4716FS-12d | As Soon As Possible | NA | 58 | -13d | October 2, 2025 8:00 AM | December 24, 2025 5:00 PM | 58 days | No | 10/2/25 | NA | NA | 0.12
6864 | M30: State QA | November 3, 2025 8:00 AM | January 27, 2026 5:00 PM |  | 1850FS-1d | As Soon As Possible | NA | 57 | 2d | November 3, 2025 8:00 AM | January 27, 2026 5:00 PM | 57 days | No | 11/3/25 | NA | NA | 0.44
6865 | M30: B1:22.03 Generate State Metrics (CARESV1-76) | November 3, 2025 8:00 AM | January 27, 2026 5:00 PM | 549SS+22d | 553SS,4717SS | As Soon As Possible | NA | 57 | 2d | November 3, 2025 8:00 AM | January 27, 2026 5:00 PM | 57 days | No | 11/3/25 | NA | NA | 0.44
6866 | M30: Joint Review | November 3, 2025 8:00 AM | January 27, 2026 5:00 PM |  |  | As Soon As Possible | NA | 57 | 73d | November 3, 2025 8:00 AM | January 27, 2026 5:00 PM | 57 days | No | NA | NA | NA | 0
6867 | M30: B1: 22.03 Generate State Metrics (CARESV1-76) | November 3, 2025 8:00 AM | January 27, 2026 5:00 PM | 551SS | 554FF | As Soon As Possible | NA | 57 | 73d | November 3, 2025 8:00 AM | January 27, 2026 5:00 PM | 57 days | No | NA | NA | NA | 0
10446 | Milestone 30: State Reports (CARESV1-502) Complete | January 27, 2026 5:00 PM | January 27, 2026 5:00 PM | 553FF | 5618,5623 | As Soon As Possible | NA | 0 | 73d | January 27, 2026 5:00 PM | January 27, 2026 5:00 PM | 0 days | Yes | NA | NA | NA | 0
6720 | Milestone 31: Adhoc Reports (CARESV1-501) | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 106 | 467d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | 6/30/25 | NA | NA | 0.62
6880 | M31: Design | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 29 | 0d | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 days | No | 6/30/25 | 8/8/25 | NA | 1
6881 | M31: B1: 22.04 Build and Share Ad-hoc Queries, Graphs (Visualizations) and Dashboards (CARESV1-28) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 520SS | 559,2442SS,2421FF,2422SS,2423SS,2424SS | Must Start On | 6/30/25 | 29 | 0d | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 days | No | 6/30/25 | 8/8/25 | NA | 1
6882 | M31: Build | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 77 | 467d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | 8/11/25 | NA | NA | 0.56999999999999995
6883 | M31: B1: 22.04 Build and Share Ad-hoc Queries, Graphs (Visualizations) and Dashboards (CARESV1-28) | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 557 | 2440FF-1d,2425SS,560SS | As Soon As Possible | NA | 77 | 163d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | 8/11/25 | NA | NA | 0.56999999999999995
7005 | CARESV1-34751 Technical Analytical Training (LOE) | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 559SS | 561SS | Start No Earlier Than | 8/11/25 | 77 | 467d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | 8/11/25 | NA | NA | 0.56999999999999995
7006 | CARESV1-34752 Data Architecture (LOE) | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 560SS | 562FF | Start No Earlier Than | 8/11/25 | 77 | 112d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | 8/11/25 | NA | NA | 0.56999999999999995
10447 | Milestone 31: Adhoc Reports (CARESV1-501) Complete | November 28, 2025 5:00 PM | November 28, 2025 5:00 PM | 561FF | 5618,5623 | As Soon As Possible | NA | 0 | 112d | November 28, 2025 5:00 PM | November 28, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
2 | Process Areas | November 3, 2022 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 873 | 362d | November 30, 2022 8:00 AM | May 1, 2026 5:00 PM | 857 days | No | 11/3/22 | NA | NA | 0.87
195 | Case Management | November 30, 2022 8:00 AM | December 30, 2025 5:00 PM |  | 5623 | As Soon As Possible | NA | 773 | 91d | November 30, 2022 8:00 AM | December 30, 2025 5:00 PM | 773 days | No | 11/30/22 | NA | NA | 0.91000000000000003
2554 | Walkthrough | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM |  |  | As Soon As Possible | NA | 97 | 0d | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM | 97 days | No | 2/26/24 | 7/12/24 | NA | 1
1304 | Milestone 06: Case Management: Engagement (CARESV1-520) | February 26, 2024 8:00 AM | April 19, 2024 5:00 PM |  |  | As Soon As Possible | NA | 39 | 0d | February 26, 2024 8:00 AM | April 19, 2024 5:00 PM | 39 days | No | 2/26/24 | 4/19/24 | NA | 1
4479 | Case Management - Milestone 06 - Conduct Walkthrough | February 26, 2024 8:00 AM | March 8, 2024 5:00 PM |  | 568FS+19d | As Soon As Possible | NA | 10 | 0d | February 26, 2024 8:00 AM | March 8, 2024 5:00 PM | 10 days | No | 2/26/24 | 3/8/24 | NA | 1
1303 | Case Management - Milestone 06 - Document and Confirm Requirements | April 8, 2024 8:00 AM | April 19, 2024 5:00 PM | 567FS+19d | 1476 | As Soon As Possible | NA | 10 | 0d | April 8, 2024 8:00 AM | April 19, 2024 5:00 PM | 10 days | No | 4/8/24 | 4/19/24 | NA | 1
1306 | Milestone 08: Case Management: Placement (CARESV1-523) | May 13, 2024 8:00 AM | July 12, 2024 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | May 13, 2024 8:00 AM | July 12, 2024 5:00 PM | 43 days | No | 5/13/24 | 7/12/24 | NA | 1
4481 | Case Management - Milestone 08 - Conduct Walkthrough | May 13, 2024 8:00 AM | May 24, 2024 5:00 PM |  | 571 | As Soon As Possible | NA | 10 | 0d | May 13, 2024 8:00 AM | May 24, 2024 5:00 PM | 10 days | No | 5/13/24 | 5/24/24 | NA | 1
1307 | Case Management - Milestone 08 - Document and Confirm Requirements | May 28, 2024 8:00 AM | July 12, 2024 5:00 PM | 570 | 1476FS-19d | Finish No Earlier Than | 7/12/24 | 33 | 0d | May 28, 2024 8:00 AM | July 12, 2024 5:00 PM | 33 days | No | 5/28/24 | 7/12/24 | NA | 1
1311 | Milestone 09: Case Management: Engagement & Services (CARESV1-521) | April 22, 2024 8:00 AM | May 3, 2024 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | April 22, 2024 8:00 AM | May 3, 2024 5:00 PM | 10 days | No | 4/22/24 | 5/3/24 | NA | 1
4482 | Case Management - Milestone 09 -Conduct Walkthrough | April 22, 2024 8:00 AM | May 3, 2024 5:00 PM |  | 588 | As Soon As Possible | NA | 10 | 0d | April 22, 2024 8:00 AM | May 3, 2024 5:00 PM | 10 days | No | 4/22/24 | 5/3/24 | NA | 1
1320 | Case Management: Holistic Design Milestones (1, 2, 6, 8, 6.1, 7, 9, 10, 11, 13, 15, 19, 20) | November 30, 2022 8:00 AM | December 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 773 | 91d | November 30, 2022 8:00 AM | December 30, 2025 5:00 PM | 773 days | No | 11/30/22 | NA | NA | 0.91000000000000003
6481 | Group 1 Placement (Milestone 1, 2, 6, 8, 15, 19, 20) | September 2, 2024 8:00 AM | March 14, 2025 5:00 PM |  |  | As Soon As Possible | NA | 133 | 0d | September 2, 2024 8:00 AM | March 14, 2025 5:00 PM | 133 days | No | 9/2/24 | 3/14/25 | NA | 1
6482 | Design Cycle 2 | September 2, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 63 | 0d | September 2, 2024 8:00 AM | September 27, 2024 5:00 PM | 20 days | No | 9/2/24 | 12/2/24 | NA | 1
6483 | Case Management - Group 1 - Design Cycle 2 - Prepare Walkthrough | September 2, 2024 8:00 AM | September 10, 2024 5:00 PM |  | 578,2514SS,2515SS,2516SS,2554SS,2555SS,2556SS,1386SS-31d | Must Start On | 9/2/24 | 7 | 0d | September 2, 2024 8:00 AM | September 10, 2024 5:00 PM | 7 days | No | 9/2/24 | 9/10/24 | NA | 1
6484 | Case Management Group 1 Design Cycle 2 - Conduct Pre-build Prototype Demo | September 11, 2024 8:00 AM | October 31, 2024 5:00 PM | 577 | 579SS+7d | As Soon As Possible | NA | 37 | 0d | September 11, 2024 8:00 AM | September 19, 2024 5:00 PM | 7 days | No | 9/11/24 | 10/31/24 | NA | 1
6485 | Case Management Group 1 Design Cycle 2 - Review & implement Pre-build Prototype Demo Observations | September 20, 2024 8:00 AM | December 2, 2024 5:00 PM | 578SS+7d | 4381SS+29d,4405SS+40d,4417FS+1d,4428FS+1d,581FS-1d | As Soon As Possible | NA | 49 | 0d | September 20, 2024 8:00 AM | September 27, 2024 5:00 PM | 6 days | No | 9/20/24 | 12/2/24 | NA | 1
11509 | Case Management Group 1 - User Feedback (8, 15, 19, 20) | December 2, 2024 8:00 AM | March 14, 2025 5:00 PM |  |  | As Soon As Possible | NA | 71 | 0d | December 2, 2024 8:00 AM | March 14, 2025 5:00 PM | 71 days | No | 12/2/24 | 3/14/25 | NA | 1
11519 | Case Management Group 1 - User Feedback - Identify User Feedback Scenarios | December 2, 2024 8:00 AM | December 30, 2024 5:00 PM | 579FS-1d | 582SS | Start No Earlier Than | 12/2/24 | 20 | 0d | December 2, 2024 8:00 AM | December 30, 2024 5:00 PM | 20 days | No | 12/2/24 | 12/30/24 | NA | 1
11518 | Case Management Group 1 - User Feedback - Confirm User Feedback Environment Readiness | December 2, 2024 8:00 AM | December 30, 2024 5:00 PM | 581SS | 583FS+3d | As Soon As Possible | NA | 20 | 0d | December 2, 2024 8:00 AM | December 30, 2024 5:00 PM | 20 days | No | 12/2/24 | 12/30/24 | NA | 1
11514 | Case Management Group 1 - User Feedback - Conduct and Gather User Feedback | January 6, 2025 8:00 AM | January 17, 2025 5:00 PM | 582FS+3d | 584SS | Start No Earlier Than | 1/6/25 | 10 | 0d | January 6, 2025 8:00 AM | January 17, 2025 5:00 PM | 10 days | No | 1/6/25 | 1/17/25 | NA | 1
11515 | Case Management Group 1 - User Feedback - Capture and Document in JIRA | January 6, 2025 8:00 AM | January 24, 2025 5:00 PM | 583SS | 585 | Start No Earlier Than | 1/6/25 | 14 | 0d | January 6, 2025 8:00 AM | January 24, 2025 5:00 PM | 14 days | No | 1/6/25 | 1/24/25 | NA | 1
11516 | Case Management Group 1 - User Feedback - Complete Build / SIT | January 27, 2025 8:00 AM | March 7, 2025 5:00 PM | 584 | 586SS+21d | As Soon As Possible | NA | 29 | 0d | January 27, 2025 8:00 AM | March 7, 2025 5:00 PM | 29 days | No | 1/27/25 | 3/7/25 | NA | 1
11517 | Case Management Group 1 - User Feedback - State QA | February 26, 2025 8:00 AM | March 14, 2025 5:00 PM | 585SS+21d |  | As Soon As Possible | NA | 13 | 0d | February 26, 2025 8:00 AM | March 14, 2025 5:00 PM | 13 days | No | 2/26/25 | 3/14/25 | NA | 1
2128 | Group 2 On-going Casework (Milestones 6.1, 7, 9) | July 1, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 187 | 0d | July 15, 2024 8:00 AM | March 28, 2025 5:00 PM | 178 days | No | 7/1/24 | 3/28/25 | NA | 1
2130 | Case Management Group 2 - Finalize Requirements Baseline | September 13, 2024 8:00 AM | September 30, 2024 5:00 PM | 674FF-14d,573 | 4393FS+22d,593SS-40d | Finish No Earlier Than | 9/30/24 | 12 | 0d | September 13, 2024 8:00 AM | September 30, 2024 5:00 PM | 12 days | No | 9/13/24 | 9/30/24 | NA | 1
4141 | Case Management: Holistic Design Artifacts | July 1, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 187 | 0d | July 15, 2024 8:00 AM | March 28, 2025 5:00 PM | 178 days | No | 7/1/24 | 3/28/25 | NA | 1
4146 | Design Cycle 1 | July 1, 2024 8:00 AM | October 28, 2024 5:00 PM |  | 4532,4534 | As Soon As Possible | NA | 85 | 0d | July 15, 2024 8:00 AM | October 28, 2024 5:00 PM | 76 days | No | 7/1/24 | 10/28/24 | NA | 1
11594 | Case Management Group 2 Design Cycle 1 - Draft & Review Application Flow | July 1, 2024 8:00 AM | July 30, 2024 5:00 PM |  | 4532,4534 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/30/24 | NA | 1
11595 | Case Management Group 2 Design Cycle 1 - Implementation Artifacts Review | July 25, 2024 8:00 AM | July 30, 2024 5:00 PM |  | 4532,4534 | As Soon As Possible | NA | 4 | 0d | NA | NA | 0 days? | No | 7/25/24 | 7/30/24 | NA | 1
4147 | Case Management Group 2 Design Cycle 1 - Prepare Blueprint | July 15, 2024 8:00 AM | October 14, 2024 5:00 PM | 588SS-40d | 594SS+10d,2246SS,2258SS,2250SS,2521SS,2522SS,1319SS,1323SS,1335SS,4532,4534 | Start No Earlier Than | 7/15/24 | 66 | 0d | July 15, 2024 8:00 AM | October 14, 2024 5:00 PM | 66 days | No | 7/15/24 | 10/14/24 | NA | 1
4148 | Case Management Group 2 Design Cycle 1 - Review Blueprint | July 29, 2024 8:00 AM | October 21, 2024 5:00 PM | 593SS+10d | 595SS+5d,4532,4534 | As Soon As Possible | NA | 61 | 0d | July 29, 2024 8:00 AM | October 21, 2024 5:00 PM | 61 days | No | 7/29/24 | 10/21/24 | NA | 1
4149 | Case Management Group 2 Design Cycle 1 - Revise and Finalize Blueprint | August 5, 2024 8:00 AM | October 28, 2024 5:00 PM | 594SS+5d | 599FS+44d,597FS-1d,598FS-1d,4532,4534 | As Soon As Possible | NA | 61 | 0d | August 5, 2024 8:00 AM | October 28, 2024 5:00 PM | 61 days | No | 8/5/24 | 10/28/24 | NA | 1
4150 | Design Cycle 2 | October 28, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 103 | 0d | October 28, 2024 8:00 AM | March 28, 2025 5:00 PM | 103 days | No | 10/28/24 | 3/28/25 | NA | 1
11477 | Case Management Group 2 Design Cycle 2 - Perform Pre-Build activities | October 28, 2024 8:00 AM | March 7, 2025 5:00 PM | 595FS-1d | 600SS+5d,2247SS,2259SS,2251SS,2508SS,2523SS,4521,4523 | Finish No Earlier Than | 3/7/25 | 88 | 0d | October 28, 2024 8:00 AM | March 7, 2025 5:00 PM | 88 days | No | 10/28/24 | 3/7/25 | NA | 1
11478 | Case Management Group 2 Design Cycle 2 - Perform Pre-Build QA (with VPOD) and Address Findings | November 18, 2024 8:00 AM | March 7, 2025 5:00 PM | 595FS-1d | 600SS+5d,2247SS,2259SS,2251SS,2508SS,2523SS,4521,4523 | Finish No Earlier Than | 3/7/25 | 74 | 0d | November 18, 2024 8:00 AM | March 7, 2025 5:00 PM | 74 days | No | 11/18/24 | 3/7/25 | NA | 1
4153 | Case Management Group 2 Design Cycle 2 - Prepare for Walkthrough with Core Constituents | January 6, 2025 8:00 AM | March 7, 2025 5:00 PM | 595FS+44d | 600SS+5d,2247SS,2259SS,2251SS,2508SS,2523SS,4521,4523 | Finish No Earlier Than | 3/7/25 | 43 | 0d | January 6, 2025 8:00 AM | March 7, 2025 5:00 PM | 43 days | No | 1/6/25 | 3/7/25 | NA | 1
6331 | Case Management Group 2 Design Cycle 2 - Conduct Design Walkthrough with Core Constituents | January 13, 2025 8:00 AM | March 14, 2025 5:00 PM | 599SS+5d,597SS+5d,598SS+5d | 601SS+5d | As Soon As Possible | NA | 43 | 0d | January 13, 2025 8:00 AM | March 14, 2025 5:00 PM | 43 days | No | 1/13/25 | 3/14/25 | NA | 1
6332 | Case Management Group 2 Design Cycle 2 - Final Review and Design Baseline | January 21, 2025 8:00 AM | March 28, 2025 5:00 PM | 600SS+5d | 682FF,4465,4480,4450,618FF | As Soon As Possible | NA | 48 | 0d | January 21, 2025 8:00 AM | March 28, 2025 5:00 PM | 48 days | No | 1/21/25 | 3/28/25 | NA | 1
6167 | Group 3 Finish a Case (Milestone 10, 11, 13) | October 3, 2024 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 163 | 0d | October 3, 2024 8:00 AM | May 30, 2025 5:00 PM | 163 days | No | 10/3/24 | 5/30/25 | NA | 1
6168 | Case Management Group 3 - Finalize Requirements Baseline | October 3, 2024 8:00 AM | November 8, 2024 5:00 PM | 661FF,674FS-12d | 608SS+12d,606FS-18d | Finish No Earlier Than | 11/8/24 | 27 | 0d | October 3, 2024 8:00 AM | November 8, 2024 5:00 PM | 12 days | No | 10/3/24 | 11/8/24 | NA | 1
6169 | Case Management: Holistic Design Artifacts | October 16, 2024 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 154 | 0d | October 21, 2024 8:00 AM | May 30, 2025 5:00 PM | 151 days | No | 10/16/24 | 5/30/25 | NA | 1
6174 | Design Cycle 1 | October 16, 2024 8:00 AM | February 27, 2025 5:00 PM |  |  | As Soon As Possible | NA | 90 | 0d | October 21, 2024 8:00 AM | February 27, 2025 5:00 PM | 87 days | No | 10/16/24 | 2/27/25 | NA | 1
11596 | Case Management Group 3 Design Cycle 1 - Draft & Review Application Flow | October 16, 2024 8:00 AM | November 27, 2024 5:00 PM | 603FS-18d | 607SS | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 10/16/24 | 11/27/24 | NA | 1
11597 | Case Management Group 3 Design Cycle 1 - Implementation Artifacts Review | October 16, 2024 8:00 AM | November 15, 2024 5:00 PM | 606SS |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/16/24 | 11/15/24 | NA | 1
6175 | Case Management Group 3 Design Cycle 1 - Prepare Blueprint | October 21, 2024 8:00 AM | February 14, 2025 5:00 PM | 603SS+12d | 609SS+10d,2262SS,2270SS,2274SS,1327SS,1339SS,1359SS,1373SS,1351SS,630SS,377SS,689SS,696SS | Start No Earlier Than | 10/21/24 | 79 | 0d | October 21, 2024 8:00 AM | February 14, 2025 5:00 PM | 79 days | No | 10/21/24 | 2/14/25 | NA | 1
6176 | Case Management Group 3 Design Cycle 1 - Review Blueprint | November 4, 2024 8:00 AM | February 21, 2025 5:00 PM | 608SS+10d | 610SS+4d | As Soon As Possible | NA | 73 | 0d | November 4, 2024 8:00 AM | February 21, 2025 5:00 PM | 73 days | No | 11/4/24 | 2/21/25 | NA | 1
6177 | Case Management Group 3 Design Cycle 1 - Revise and Finalize Blueprint | November 8, 2024 8:00 AM | February 27, 2025 5:00 PM | 609SS+4d | 612 | As Soon As Possible | NA | 73 | 0d | November 8, 2024 8:00 AM | February 27, 2025 5:00 PM | 73 days | No | 11/8/24 | 2/27/25 | NA | 1
6178 | Design Cycle 2 | March 3, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 63 | 0d | March 3, 2025 8:00 AM | May 30, 2025 5:00 PM | 63 days | No | 3/3/25 | 5/30/25 | NA | 1
11482 | Case Management Group 3 Design Cycle 2 - Perform Pre-Build activities | March 3, 2025 8:00 AM | May 9, 2025 5:00 PM | 610 | 615SS+5d,2263SS,2271SS,2275SS,2528SS,2534SS,2540SS,613SS+10d | Finish No Earlier Than | 5/9/25 | 49 | 0d | March 3, 2025 8:00 AM | May 9, 2025 5:00 PM | 49 days | No | 3/3/25 | 5/9/25 | NA | 1
11481 | Case Management Group 3 Design Cycle 2 - Perform Pre-Build QA (with VPOD) and Address Findings | March 17, 2025 8:00 AM | May 9, 2025 5:00 PM | 612SS+10d | 615SS+5d,2263SS,2271SS,2275SS,2528SS,2534SS,2540SS,614SS+10d | Finish No Earlier Than | 5/9/25 | 39 | 0d | March 17, 2025 8:00 AM | May 9, 2025 5:00 PM | 39 days | No | 3/17/25 | 5/9/25 | NA | 1
6179 | Case Management Group 3 Design Cycle 2 - Prepare for Walkthrough with Core Constituents | April 1, 2025 8:00 AM | May 9, 2025 5:00 PM | 613SS+10d | 615SS+5d,2263SS,2271SS,2275SS,2528SS,2534SS,2540SS | Start No Earlier Than | 2/28/25 | 29 | 0d | April 1, 2025 8:00 AM | May 9, 2025 5:00 PM | 29 days | No | 4/1/25 | 5/9/25 | NA | 1
6180 | Case Management Group 3 Design Cycle 2 - Conduct Design Walkthrough with Core Constituents | April 8, 2025 8:00 AM | May 16, 2025 5:00 PM | 614SS+5d,613SS+5d,612SS+5d | 616SS+5d | As Soon As Possible | NA | 29 | 0d | April 8, 2025 8:00 AM | May 16, 2025 5:00 PM | 29 days | No | 4/8/25 | 5/16/25 | NA | 1
6181 | Case Management Group 3 Design Cycle 2 - Final Review and Design Baseline | April 15, 2025 8:00 AM | May 30, 2025 5:00 PM | 615SS+5d | 1390FS-1d,1391FS-1d | As Soon As Possible | NA | 33 | 0d | April 15, 2025 8:00 AM | May 30, 2025 5:00 PM | 33 days | No | 4/15/25 | 5/30/25 | NA | 1
11346 | Milestone 06.1: Prevention Services | July 17, 2024 8:00 AM | December 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 366 | 0d | July 17, 2024 8:00 AM | December 30, 2025 5:00 PM | 366 days | No | 7/17/24 | 12/30/25 | NA | 1
11347 | M6.1: Design | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 601FF | 619 | As Soon As Possible | NA | 176 | 0d | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 176 days | No | 7/17/24 | 3/28/25 | NA | 1
11348 | M6.1: Build | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 306FS+1d,618 | 620SS+18d | As Soon As Possible | NA | 168 | 0d | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 days | No | 4/2/25 | 11/28/25 | NA | 1
11349 | M6.1: SIT | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 308SS+19d,619SS+18d | 621FS-127d | As Soon As Possible | NA | 149 | 0d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 4/29/25 | 11/28/25 | NA | 1
11350 | M6.1: State QA | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 310SS+22d,620FS-127d | 622SS | As Soon As Possible | NA | 148 | 0d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 5/30/25 | 12/30/25 | NA | 1
11351 | M6.1: Joint Review | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 312SS,621SS | 1923 | As Soon As Possible | NA | 148 | 0d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 5/30/25 | 12/30/25 | NA | 1
11354 | Milestone 9: Engagement & Services (CARESV1-521) | November 30, 2022 8:00 AM | October 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 482 | 0d | November 30, 2022 8:00 AM | December 30, 2025 5:00 PM | 773 days | No | 11/30/22 | 10/29/24 | NA | 1
11355 | M9: Design | November 30, 2022 8:00 AM | August 11, 2023 5:00 PM | 337FF | 625FF-90d | As Soon As Possible | NA | 176 | 0d | November 30, 2022 8:00 AM | August 11, 2023 5:00 PM | 176 days | No | 11/30/22 | 8/11/23 | NA | 1
11356 | M9: Build | May 2, 2023 8:00 AM | January 3, 2024 5:00 PM | 343FF,624FF-90d | 626SS+20d | As Soon As Possible | NA | 169 | 0d | May 2, 2023 8:00 AM | January 3, 2024 5:00 PM | 169 days | No | 5/2/23 | 1/3/24 | NA | 1
11357 | M9: SIT | May 31, 2023 8:00 AM | January 3, 2024 5:00 PM | 349FF,625SS+20d | 627SS+20d | As Soon As Possible | NA | 149 | 0d | May 31, 2023 8:00 AM | January 3, 2024 5:00 PM | 149 days | No | 5/31/23 | 1/3/24 | NA | 1
11358 | M9: State QA | June 23, 2023 8:00 AM | January 26, 2024 5:00 PM | 355FF,626SS+20d | 628SS-18d | As Soon As Possible | NA | 148 | 0d | June 23, 2023 8:00 AM | January 26, 2024 5:00 PM | 148 days | No | 6/23/23 | 1/26/24 | NA | 1
11359 | M9: Joint Review | April 3, 2024 8:00 AM | October 29, 2024 5:00 PM | 362FF,627SS-18d,315FF | 1923 | As Soon As Possible | NA | 148 | 0d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 4/3/24 | 10/29/24 | NA | 1
11360 | Milestone 10: Case Closure (CARESV1-532) | October 21, 2024 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 277 | 112d | October 21, 2024 8:00 AM | December 30, 2025 5:00 PM | 423 days | No | 10/21/24 | NA | NA | 0.84999999999999998
11361 | M10: Design | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 608SS | 631 | As Soon As Possible | NA | 198 | 0d | October 21, 2024 8:00 AM | April 10, 2025 5:00 PM | 239 days | No | 10/21/24 | 8/8/25 | NA | 1
11362 | M10: Build | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 381FF,630 | 632SS,4506FF | As Soon As Possible | NA | 39 | 150d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | NA | NA | 0.91000000000000003
11363 | M10: SIT | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 384FF,631SS | 633SS,4506FF,4511,4512 | As Soon As Possible | NA | 39 | 63d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | 8/11/25 | NA | NA | 0.89000000000000001
11364 | M10: State QA | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 387FF,632SS | 634SS | As Soon As Possible | NA | 38 | 112d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | 10/6/25 | NA | NA | 0.81999999999999995
11365 | M10: Joint Review | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 359FF,633SS | 1923 | As Soon As Possible | NA | 38 | 112d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
209 | Case Management: Context Setting | September 11, 2023 8:00 AM | October 11, 2024 5:00 PM |  |  | As Soon As Possible | NA | 275 | 0d | September 11, 2023 8:00 AM | October 11, 2024 5:00 PM | 275 days | No | 9/11/23 | 10/11/24 | NA | 1
11407 | Milestone 07: Case Plan (CARESV1-522) | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM |  |  | As Soon As Possible | NA | 94 | 0d | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 94 days | No | 9/11/23 | 1/26/24 | NA | 1
11408 | M7: RC: Finalize Value Hypothesis | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM |  | 638SS | Must Start On | 9/11/23 | 94 | 0d | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 94 days | No | 9/11/23 | 1/26/24 | NA | 1
11409 | M7: RC: Draft Service Maps | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 637SS | 639SS | As Soon As Possible | NA | 94 | 0d | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 94 days | No | 9/11/23 | 1/26/24 | NA | 1
11410 | M7: RC: Complete Legacy Analysis | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 638SS | 640SS | As Soon As Possible | NA | 94 | 0d | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 94 days | No | 9/11/23 | 1/26/24 | NA | 1
11411 | M7: RC: Finalize Epics | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 639SS | 641SS | As Soon As Possible | NA | 94 | 0d | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 94 days | No | 9/11/23 | 1/26/24 | NA | 1
11412 | M7: RC: Complete conceptual and epic-level Domain Model diagrams | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 640SS | 642SS | As Soon As Possible | NA | 94 | 0d | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 94 days | No | 9/11/23 | 1/26/24 | NA | 1
11413 | M7: RC: Define User Story titles | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 641SS | 643SS | As Soon As Possible | NA | 94 | 0d | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 94 days | No | 9/11/23 | 1/26/24 | NA | 1
11414 | M7: RC: Complete External Systems pre-analysis | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 642SS | 644SS | As Soon As Possible | NA | 94 | 0d | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 94 days | No | 9/11/23 | 1/26/24 | NA | 1
11415 | M7: RC: Facilitate Inception | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 643SS | 663,2507,646FS+136d | As Soon As Possible | NA | 94 | 0d | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 94 days | No | 9/11/23 | 1/26/24 | NA | 1
11416 | Milestone 13: Adoption (CARESV1-531) | May 28, 2024 8:00 AM | October 11, 2024 5:00 PM |  |  | As Soon As Possible | NA | 98 | 0d | May 28, 2024 8:00 AM | October 11, 2024 5:00 PM | 98 days | No | 5/28/24 | 10/11/24 | NA | 1
11417 | M13: B1 07.06 Provide Post Adoption Services (CARESV1-34) | August 12, 2024 8:00 AM | October 11, 2024 5:00 PM | 644FS+136d | 647SS-54d | Start No Earlier Than | 8/12/24 | 45 | 0d | August 12, 2024 8:00 AM | October 11, 2024 5:00 PM | 45 days | No | 8/12/24 | 10/11/24 | NA | 1
11418 | M13: B2 07.01 Conduct Preliminary Adoption Assessment (CARESV1-12) | May 28, 2024 8:00 AM | June 25, 2024 5:00 PM | 646SS-54d |  | Start No Earlier Than | 5/27/24 | 21 | 0d | May 28, 2024 8:00 AM | June 25, 2024 5:00 PM | 21 days | No | 5/28/24 | 6/25/24 | NA | 1
11420 | M13: B4 07.03 Conduct Activities to Finalize Adoption (CARESV1-8) | June 19, 2024 8:00 AM | August 30, 2024 5:00 PM |  | 649 | As Soon As Possible | NA | 52 | 0d | June 19, 2024 8:00 AM | August 30, 2024 5:00 PM | 52 days | No | 6/19/24 | 8/30/24 | NA | 1
11421 | M13: B5 07.04 Voluntary Relinquishment of Parental Rights (CARESV1-13) | September 2, 2024 8:00 AM | September 16, 2024 5:00 PM | 648 | 651FS-1d,650SS | As Soon As Possible | NA | 11 | 0d | September 2, 2024 8:00 AM | September 16, 2024 5:00 PM | 11 days | No | 9/2/24 | 9/16/24 | NA | 1
11593 | M13: Start of BRC/JIRA Inception date | September 2, 2024 8:00 AM | September 2, 2024 5:00 PM | 649SS |  | As Soon As Possible | NA | 1 | 0d | September 2, 2024 8:00 AM | September 2, 2024 5:00 PM | 0 s | No | 9/2/24 | 9/2/24 | NA | 1
11422 | M13: B6 07.05 Conduct Adoption Set Aside Investigation (CARESV1-84) | September 16, 2024 8:00 AM | September 27, 2024 5:00 PM | 649FS-1d | 670SS-10d,2539SS-151d | As Soon As Possible | NA | 10 | 0d | September 16, 2024 8:00 AM | September 27, 2024 5:00 PM | 10 days | No | 9/16/24 | 9/27/24 | NA | 1
11425 | Milestone 11: Aftercare & Re-Entry (CARESV1-533) | December 4, 2023 8:00 AM | May 3, 2024 5:00 PM |  |  | As Soon As Possible | NA | 105 | 0d | December 4, 2023 8:00 AM | May 3, 2024 5:00 PM | 105 days | No | 12/4/23 | 5/3/24 | NA | 1
11426 | M11: RC: Finalize Value Hypothesis | December 4, 2023 8:00 AM | February 7, 2024 5:00 PM |  | 654SS+5d | Start No Earlier Than | 12/4/23 | 45 | 0d | December 4, 2023 8:00 AM | February 7, 2024 5:00 PM | 45 days | No | 12/4/23 | 2/7/24 | NA | 1
11427 | M11: RC: Draft Service Maps | December 11, 2023 8:00 AM | January 24, 2024 5:00 PM | 653SS+5d | 655 | As Soon As Possible | NA | 30 | 0d | December 11, 2023 8:00 AM | January 24, 2024 5:00 PM | 30 days | No | 12/11/23 | 1/24/24 | NA | 1
11428 | M11: RC: Complete Legacy Analysis | January 25, 2024 8:00 AM | February 22, 2024 5:00 PM | 654 | 656,657SS-5d | As Soon As Possible | NA | 20 | 0d | January 25, 2024 8:00 AM | February 22, 2024 5:00 PM | 20 days | No | 1/25/24 | 2/22/24 | NA | 1
11429 | M11: RC: Finalize Epics | February 23, 2024 8:00 AM | February 29, 2024 5:00 PM | 655 | 658FS+10d | As Soon As Possible | NA | 5 | 0d | February 23, 2024 8:00 AM | February 29, 2024 5:00 PM | 5 days | No | 2/23/24 | 2/29/24 | NA | 1
11430 | M11: RC: Complete conceptual and epic-level Domain Model diagrams | January 18, 2024 8:00 AM | March 14, 2024 5:00 PM | 655SS-5d | 658 | As Soon As Possible | NA | 40 | 0d | January 18, 2024 8:00 AM | March 14, 2024 5:00 PM | 40 days | No | 1/18/24 | 3/14/24 | NA | 1
11431 | M11: RC: Define User Story titles | March 15, 2024 8:00 AM | March 28, 2024 5:00 PM | 656FS+10d,657 | 659 | As Soon As Possible | NA | 10 | 0d | March 15, 2024 8:00 AM | March 28, 2024 5:00 PM | 10 days | No | 3/15/24 | 3/28/24 | NA | 1
11432 | M11: RC: Complete External Systems pre-analysis | March 29, 2024 8:00 AM | April 19, 2024 5:00 PM | 658 | 660SS | As Soon As Possible | NA | 15 | 0d | March 29, 2024 8:00 AM | April 19, 2024 5:00 PM | 15 days | No | 3/29/24 | 4/19/24 | NA | 1
11433 | M11: RC: Facilitate Inception | March 29, 2024 8:00 AM | May 3, 2024 5:00 PM | 659SS | 676,2533 | As Soon As Possible | NA | 25 | 0d | March 29, 2024 8:00 AM | May 3, 2024 5:00 PM | 25 days | No | 3/29/24 | 5/3/24 | NA | 1
237 | Case Management: BRC | February 26, 2024 8:00 AM | October 18, 2024 5:00 PM |  | 603FF | As Soon As Possible | NA | 167 | 0d | February 26, 2024 8:00 AM | October 18, 2024 5:00 PM | 167 days | No | 2/26/24 | 10/18/24 | NA | 1
417 | Milestone 07: Case Plan (CARESV1-522) | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM |  |  | As Soon As Possible | NA | 97 | 0d | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM | 68 days | No | 2/26/24 | 7/12/24 | NA | 1
418 | M7: B1: 05.12 Initiate and Update Concurrent Plan (CARESV1-81) | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM | 644 | 664SS | Must Start On | 2/26/24 | 97 | 0d | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM | 68 days | No | 2/26/24 | 7/12/24 | NA | 1
419 | M7: B2: 18.01 Provide Prevention Services (aka FFPSA) (CARESV1-55) | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM | 663SS | 665SS | As Soon As Possible | NA | 97 | 0d | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM | 68 days | No | 2/26/24 | 7/12/24 | NA | 1
420 | M7: B3: 05.03 Create & Update Case Plan (r1) (CARESV1-33) | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM | 664SS | 666SS | As Soon As Possible | NA | 97 | 0d | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM | 68 days | No | 2/26/24 | 7/12/24 | NA | 1
421 | M7: B4: 05.07 Provide ILP Services (Early ILP and Transitional Age Youth) (CARESV1-130) | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM | 665SS | 667SS | As Soon As Possible | NA | 97 | 0d | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM | 68 days | No | 2/26/24 | 7/12/24 | NA | 1
422 | M7: B5: Case Management Assessment Interface (CARESV1-13935) | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM | 666SS | 668SS | As Soon As Possible | NA | 97 | 0d | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM | 68 days | No | 2/26/24 | 7/12/24 | NA | 1
423 | M7: B6: Milestone 7 Refinement Stories | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM | 667SS | 1419SS+63d | As Soon As Possible | NA | 97 | 0d | February 26, 2024 8:00 AM | July 12, 2024 5:00 PM | 68 days | No | 2/26/24 | 7/12/24 | NA | 1
424 | Milestone 13: Adoption (CARESV1-531) | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM |  |  | As Soon As Possible | NA | 35 | 0d | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM | 83 days | No | 9/2/24 | 10/18/24 | NA | 1
425 | M13: B1 07.06 Provide Post Adoption Services (CARESV1-34) | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM | 651SS-10d | 671SS | Start No Earlier Than | 9/2/24 | 35 | 0d | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM | 6 days | No | 9/2/24 | 10/18/24 | NA | 1
426 | M13: B2 07.01 Conduct Preliminary Adoption Assessment (CARESV1-12) | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM | 670SS | 672SS | Start No Earlier Than | 9/2/24 | 35 | 0d | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM | 83 days | No | 9/2/24 | 10/18/24 | NA | 1
428 | M13: B4 07.03 Conduct Activities to Finalize Adoption (CARESV1-8) | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM | 671SS | 673SS | Start No Earlier Than | 9/2/24 | 35 | 0d | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM | 36 days | No | 9/2/24 | 10/18/24 | NA | 1
429 | M13: B5 07.04 Voluntary Relinquishment of Parental Rights (CARESV1-13) | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM | 672SS | 674SS | Start No Earlier Than | 9/2/24 | 35 | 0d | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM | 25 days | No | 9/2/24 | 10/18/24 | NA | 1
430 | M13: B6 07.05 Conduct Adoption Set Aside Investigation (CARESV1-84) | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM | 673SS | 588FF-14d,679FF,1406SS-500d,603FS-12d,4501SS+22d | Start No Earlier Than | 9/2/24 | 35 | 0d | September 2, 2024 8:00 AM | October 18, 2024 5:00 PM | 16 days | No | 9/2/24 | 10/18/24 | NA | 1
431 | Milestone 11: Aftercare & Re-Entry (CARESV1-533) | May 6, 2024 8:00 AM | July 5, 2024 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | May 6, 2024 8:00 AM | July 5, 2024 5:00 PM | 43 days | No | 5/6/24 | 7/5/24 | NA | 1
432 | M11: B1: 08.03 Plan Aftercare Services Meeting (CARESV1-2) | May 6, 2024 8:00 AM | July 5, 2024 5:00 PM | 660 | 677SS | Start No Earlier Than | 5/6/24 | 43 | 0d | May 6, 2024 8:00 AM | July 5, 2024 5:00 PM | 43 days | No | 5/6/24 | 7/5/24 | NA | 1
433 | M11: B2: 08.04 Conduct and Document Aftercare Services Meeting (CARESV1-1) | May 6, 2024 8:00 AM | July 5, 2024 5:00 PM | 676SS | 678SS | Start No Earlier Than | 5/6/24 | 43 | 0d | May 6, 2024 8:00 AM | July 5, 2024 5:00 PM | 43 days | No | 5/6/24 | 7/5/24 | NA | 1
434 | M11: B3: 05.10 Conduct Initial or Re-Entry into Extended Foster Care (CARESV1-78) | May 6, 2024 8:00 AM | July 5, 2024 5:00 PM | 677SS | 696 | As Soon As Possible | NA | 43 | 0d | May 6, 2024 8:00 AM | July 5, 2024 5:00 PM | 43 days | No | 5/6/24 | 7/5/24 | NA | 1
251 | Case Management BRC Milestone Completion | October 18, 2024 5:00 PM | October 18, 2024 5:00 PM | 674FF | 682SS-61d | As Soon As Possible | NA | 0 | 0d | October 11, 2024 5:00 PM | October 11, 2024 5:00 PM | 0 days | Yes | 10/18/24 | 10/18/24 | NA | 1
252 | Case Management: Design | July 17, 2024 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 268 | 0d | July 16, 2024 8:00 AM | May 30, 2025 5:00 PM | 220 days | No | 7/17/24 | 8/8/25 | NA | 1
464 | Milestone 07: Case Plan (CARESV1-522) | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 176 | 0d | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 176 days | No | 7/17/24 | 3/28/25 | NA | 1
465 | M7: B1: 05.12 Initiate and Update Concurrent Plan (CARESV1-81) | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 601FF,679SS-61d | 683SS | As Soon As Possible | NA | 175 | 0d | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 175 days | No | 7/17/24 | 3/28/25 | NA | 1
466 | M7: B2: 18.01 Provide Prevention Services (aka FFPSA) (CARESV1-55) | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 682SS | 684SS | As Soon As Possible | NA | 176 | 0d | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 176 days | No | 7/17/24 | 3/28/25 | NA | 1
467 | M7: B3: 05.03 Create & Update Case Plan (r1) (CARESV1-33) | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 683SS | 685SS | As Soon As Possible | NA | 176 | 0d | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 176 days | No | 7/17/24 | 3/28/25 | NA | 1
468 | M7: B4: 05.07 Provide ILP Services (Early ILP and Transitional Age Youth) (CARESV1-130) | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 684SS | 686SS | As Soon As Possible | NA | 176 | 0d | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 176 days | No | 7/17/24 | 3/28/25 | NA | 1
469 | M7: B5: Case Management Assessment Interface (CARESV1-13935) | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 685SS | 687SS | As Soon As Possible | NA | 176 | 0d | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 176 days | No | 7/17/24 | 3/28/25 | NA | 1
470 | M7: B6: Milestone 7 Refinement Stories | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 686SS | 702,1420SS+58d | As Soon As Possible | NA | 176 | 0d | July 17, 2024 8:00 AM | March 28, 2025 5:00 PM | 176 days | No | 7/17/24 | 3/28/25 | NA | 1
471 | Milestone 13: Adoption (CARESV1-531) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 200 | 0d | April 15, 2025 8:00 AM | May 30, 2025 5:00 PM | 33 days | No | 10/21/24 | 8/8/25 | NA | 1
472 | M13: B1 07.06 Provide Post Adoption Services (CARESV1-34) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 608SS | 690SS | As Soon As Possible | NA | 200 | 0d | April 15, 2025 8:00 AM | May 30, 2025 5:00 PM | 33 days | No | 10/21/24 | 8/8/25 | NA | 1
473 | M13: B2 07.01 Conduct Preliminary Adoption Assessment (CARESV1-12) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 689SS | 691SS | As Soon As Possible | NA | 200 | 0d | April 15, 2025 8:00 AM | May 30, 2025 5:00 PM | 33 days | No | 10/21/24 | 8/8/25 | NA | 1
474 | M13: B3 07.02 Find Potential Adoptive Matches and Make Placement (CARESV1-9) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 690SS | 692SS | As Soon As Possible | NA | 200 | 0d | April 15, 2025 8:00 AM | May 30, 2025 5:00 PM | 33 days | No | 10/21/24 | 8/8/25 | NA | 1
475 | M13: B4 07.03 Conduct Activities to Finalize Adoption (CARESV1-8) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 691SS | 693SS | As Soon As Possible | NA | 200 | 0d | April 15, 2025 8:00 AM | May 30, 2025 5:00 PM | 33 days | No | 10/21/24 | 8/8/25 | NA | 1
476 | M13: B5 07.04 Voluntary Relinquishment of Parental Rights (CARESV1-13) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 692SS | 694SS | As Soon As Possible | NA | 200 | 0d | April 15, 2025 8:00 AM | May 30, 2025 5:00 PM | 33 days | No | 10/21/24 | 8/8/25 | NA | 1
477 | M13: B6 07.05 Conduct Adoption Set Aside Investigation (CARESV1-84) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 693SS | 709,1407SS-417d | As Soon As Possible | NA | 200 | 0d | April 15, 2025 8:00 AM | May 30, 2025 5:00 PM | 33 days | No | 10/21/24 | 8/8/25 | NA | 1
478 | Milestone 11: Aftercare & Re-Entry (CARESV1-533) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 200 | 0d | July 16, 2024 8:00 AM | May 30, 2025 5:00 PM | 220 days | No | 10/21/24 | 8/8/25 | NA | 1
479 | M11: B1: 08.03 Plan Aftercare Services Meeting (CARESV1-2) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 678,608SS | 697SS | As Soon As Possible | NA | 200 | 0d | July 16, 2024 8:00 AM | May 30, 2025 5:00 PM | 220 days | No | 10/21/24 | 8/8/25 | NA | 1
480 | M11: B2: 08.04 Conduct and Document Aftercare Services Meeting (CARESV1-1) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 696SS | 698SS | As Soon As Possible | NA | 200 | 0d | July 16, 2024 8:00 AM | May 30, 2025 5:00 PM | 220 days | No | 10/21/24 | 8/8/25 | NA | 1
481 | M11: B3: 05.10 Conduct Initial or Re-Entry into Extended Foster Care (CARESV1-78) | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 697SS | 699FF,715 | As Soon As Possible | NA | 200 | 0d | July 16, 2024 8:00 AM | May 30, 2025 5:00 PM | 220 days | No | 10/21/24 | 8/8/25 | NA | 1
266 | Case Management Design Milestone Completion | August 8, 2025 5:00 PM | August 8, 2025 5:00 PM | 698FF | 4506FS+18d | As Soon As Possible | NA | 0 | 0d | May 30, 2025 5:00 PM | May 30, 2025 5:00 PM | 0 days | Yes | 8/8/25 | 8/8/25 | NA | 1
514 | Case Management: Build | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 169 | 112d | April 2, 2025 8:00 AM | December 30, 2025 5:00 PM | 189 days | No | 4/1/25 | NA | NA | 0.93999999999999995
539 | Milestone 07: Case Plan (CARESV1-522) | April 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 92 | 0d | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 days | No | 4/1/25 | 8/8/25 | NA | 1
540 | M7: B1: 05.12 Initiate and Update Concurrent Plan (CARESV1-81) | April 1, 2025 8:00 AM | June 27, 2025 5:00 PM | 687 | 703SS,2248SS,2252SS,2509SS,4470 | As Soon As Possible | NA | 63 | 0d | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 days | No | 4/1/25 | 6/27/25 | NA | 1
541 | M7: B2: 18.01 Provide Prevention Services (aka FFPSA) (CARESV1-55) | April 1, 2025 8:00 AM | August 8, 2025 5:00 PM | 702SS | 704SS,748,4470 | As Soon As Possible | NA | 92 | 0d | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 days | No | 4/1/25 | 8/8/25 | NA | 1
542 | M7: B3: 05.03 Create& Update Case Plan (r1) (CARESV1-33) | April 1, 2025 8:00 AM | June 27, 2025 5:00 PM | 703SS | 705SS,4470 | As Soon As Possible | NA | 63 | 0d | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 days | No | 4/1/25 | 6/27/25 | NA | 1
543 | M7: B4: 05.07 Provide ILP Services (Early ILP and Transitional Age Youth) (CARESV1-130) | April 1, 2025 8:00 AM | June 27, 2025 5:00 PM | 704SS | 706SS,4470 | As Soon As Possible | NA | 63 | 0d | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 days | No | 4/1/25 | 6/27/25 | NA | 1
544 | M7: B5: Case Management Assessment Interface (CARESV1-13935) | April 1, 2025 8:00 AM | June 27, 2025 5:00 PM | 705SS | 707SS,4470 | As Soon As Possible | NA | 63 | 0d | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 days | No | 4/1/25 | 6/27/25 | NA | 1
545 | M7: B6: Milestone 7 Refinement Stories | April 1, 2025 8:00 AM | June 27, 2025 5:00 PM | 706SS | 1480FF,730SS,4470 | As Soon As Possible | NA | 63 | 0d | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 days | No | 4/1/25 | 6/27/25 | NA | 1
546 | Milestone 13: Adoption (CARESV1-531) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 39 | 150d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | NA | NA | 0.98999999999999999
547 | M13: B1 07.06 Provide Post Adoption Services (CARESV1-34) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 694 | 710SS,2276SS,2541SS,1360SS,1374SS,1352SS,4528FS-21d | As Soon As Possible | NA | 39 | 0d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | 10/3/25 | NA | 1
548 | M13: B2 07.01 Conduct Preliminary Adoption Assessment (CARESV1-12) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 709SS | 4528FS-21d | As Soon As Possible | NA | 39 | 0d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | 10/3/25 | NA | 1
550 | M13: B4 07.03 Conduct Activities to Finalize Adoption (CARESV1-8) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  | 712SS,4528FF+5d | As Soon As Possible | NA | 39 | 150d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | NA | NA | 0.95999999999999996
551 | M13: B5 07.04 Voluntary Relinquishment of Parental Rights (CARESV1-13) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 711SS | 713SS,4528FF+5d | As Soon As Possible | NA | 39 | 0d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | 10/3/25 | NA | 1
552 | M13: B6 07.05 Conduct Adoption Set Aside Investigation (CARESV1-84) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 712SS | 1480FF,737SS,4528FF+5d | As Soon As Possible | NA | 39 | 0d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | 10/3/25 | NA | 1
553 | Milestone 11: Aftercare & Re-Entry (CARESV1-533) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 39 | 0d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | 10/3/25 | NA | 1
554 | M11: B1: 08.03 Plan Aftercare Services Meeting (CARESV1-2) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 698 | 719SS+39d,716SS,2272SS,2535SS,4517FS-21d | As Soon As Possible | NA | 39 | 0d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | 10/3/25 | NA | 1
555 | M11: B2: 08.04 Conduct and Document Aftercare Services Meeting (CARESV1-1) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 715SS | 717SS,4517FS-21d | As Soon As Possible | NA | 39 | 0d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | 10/3/25 | NA | 1
556 | M11: B3: 05.10 Conduct Initial or Re-Entry into Extended Foster Care (CARESV1-78) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 716SS | 1480FF,743SS,4517FS-21d | As Soon As Possible | NA | 39 | 0d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | 10/3/25 | NA | 1
2824 | Case Management - User Feedback Session 1 (6.1, 7, 9, 10, 10.1, 11, 13) | October 6, 2025 8:00 AM | October 29, 2025 5:00 PM |  |  | As Soon As Possible | NA | 18 | 23.08d | July 29, 2025 8:00 AM | September 23, 2025 5:00 PM | 40 days | No | NA | NA | NA | 0
2825 | Case Management User Feedback Session 1 - Conduct and Gather User Feedback | October 6, 2025 8:00 AM | October 17, 2025 5:00 PM | 715SS+39d | 720,4475 | As Soon As Possible | NA | 10 | 23.08d | July 29, 2025 8:00 AM | August 11, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
2826 | Case Management User Feedback Session 1 - Capture and Document in JIRA | October 20, 2025 8:00 AM | October 21, 2025 5:00 PM | 719 | 724,721,4475 | As Soon As Possible | NA | 2 | 23.08d | August 12, 2025 8:00 AM | August 25, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
11205 | Case Management User Feedback Session 1 - Complete Build / SIT | October 22, 2025 8:00 AM | October 22, 2025 5:00 PM | 720 | 722FS-5d,4475 | As Soon As Possible | NA | 1 | 23.08d | August 26, 2025 8:00 AM | September 9, 2025 5:00 PM | 10 s | No | NA | NA | NA | 0
11207 | Case Management User Feedback Session 1 - State QA | October 16, 2025 8:00 AM | October 29, 2025 5:00 PM | 721FS-5d | 724,4475 | As Soon As Possible | NA | 10 | 23.08d | September 10, 2025 8:00 AM | September 23, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
2827 | User Feedback Session 2 (6.1, 7, 9, 10, 10.1, 11, 13) | October 30, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 20 | 112d | October 16, 2025 8:00 AM | December 30, 2025 5:00 PM | 51 days | No | NA | NA | NA | 0
2828 | Case Management User Feedback Session 2 - Conduct and Gather User Feedback | October 30, 2025 8:00 AM | November 13, 2025 5:00 PM | 720,722 | 725 | As Soon As Possible | NA | 10 | 112d | October 16, 2025 8:00 AM | October 29, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
2829 | Case Management User Feedback Session 2 - Capture and Document in JIRA | November 14, 2025 8:00 AM | November 17, 2025 5:00 PM | 724 | 726 | As Soon As Possible | NA | 2 | 112d | October 30, 2025 8:00 AM | November 13, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
11206 | Case Management User Feedback Session 2 - Complete Build / SIT | November 18, 2025 8:00 AM | November 18, 2025 5:00 PM | 725 | 727 | As Soon As Possible | NA | 1 | 112d | November 14, 2025 8:00 AM | November 28, 2025 5:00 PM | 10 s | No | NA | NA | NA | 0
11208 | Case Management User Feedback Session 2 - State QA | November 19, 2025 8:00 AM | November 28, 2025 5:00 PM | 759FS-10d,726 |  | As Soon As Possible | NA | 7 | 112d | December 1, 2025 8:00 AM | December 30, 2025 5:00 PM | 21 days | No | NA | NA | NA | 0
557 | Case Management: SIT | April 1, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 131 | 150d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 4/1/25 | NA | NA | 0.96999999999999997
582 | Milestone 07: Case Plan (CARESV1-522) | April 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 92 | 0d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 4/1/25 | 8/8/25 | NA | 1
583 | M7: B1: 05.12 Initiate and Update Concurrent Plan (CARESV1-81) | April 1, 2025 8:00 AM | June 27, 2025 5:00 PM | 707SS | 731SS,4470 | As Soon As Possible | NA | 63 | 0d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 4/1/25 | 6/27/25 | NA | 1
584 | M7: B2: 18.01 Provide Prevention Services (aka FFPSA) (CARESV1-55) | April 1, 2025 8:00 AM | August 8, 2025 5:00 PM | 730SS | 2989,732SS,4470,4474 | As Soon As Possible | NA | 92 | 0d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 4/1/25 | 8/8/25 | NA | 1
585 | M7: B3: 05.03 Create & Update Case Plan (r1) (CARESV1-33) | April 1, 2025 8:00 AM | June 27, 2025 5:00 PM | 731SS | 733SS,4470 | As Soon As Possible | NA | 63 | 0d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 4/1/25 | 6/27/25 | NA | 1
586 | M7: B4: 05.07 Provide ILP Services (Early ILP and Transitional Age Youth) (CARESV1-130) | April 1, 2025 8:00 AM | June 27, 2025 5:00 PM | 732SS | 734SS,4470 | As Soon As Possible | NA | 63 | 0d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 4/1/25 | 6/27/25 | NA | 1
587 | M7: B5: Case Management Assessment Interface (CARESV1-13935) | April 1, 2025 8:00 AM | June 27, 2025 5:00 PM | 733SS | 735SS,4470 | As Soon As Possible | NA | 63 | 0d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 4/1/25 | 6/27/25 | NA | 1
588 | M7: B6: Milestone 7 Refinement Stories | April 1, 2025 8:00 AM | June 27, 2025 5:00 PM | 734SS | 1480FF,748,4470 | As Soon As Possible | NA | 63 | 0d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 4/1/25 | 6/27/25 | NA | 1
589 | Milestone 13: Adoption (CARESV1-531) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 39 | 150d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | 8/11/25 | NA | NA | 0.90000000000000002
590 | M13: B1 07.06 Provide Post Adoption Services (CARESV1-34) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 713SS | 738SS,4528FF+5d | As Soon As Possible | NA | 39 | 150d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | 8/11/25 | NA | NA | 0.84999999999999998
591 | M13: B2 07.01 Conduct Preliminary Adoption Assessment (CARESV1-12) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 737SS | 2994,4528FF+5d | As Soon As Possible | NA | 39 | 4.92d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | 8/11/25 | NA | NA | 0.93999999999999995
593 | M13: B4 07.03 Conduct Activities to Finalize Adoption (CARESV1-8) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  | 740SS,4528FF+5d | As Soon As Possible | NA | 39 | 150d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | 8/11/25 | NA | NA | 0.78000000000000003
594 | M13: B5 07.04 Voluntary Relinquishment of Parental Rights (CARESV1-13) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 739SS | 741SS,4528FF+5d | As Soon As Possible | NA | 39 | 150d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | 8/11/25 | NA | NA | 0.93999999999999995
595 | M13: B6 07.05 Conduct Adoption Set Aside Investigation (CARESV1-84) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 740SS | 1480FF,755,4533FF,4528FF+5d | As Soon As Possible | NA | 39 | 0d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | 8/11/25 | 10/3/25 | NA | 1
596 | Milestone 11: Aftercare & Re-Entry (CARESV1-533) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 39 | 5d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | 8/11/25 | NA | NA | 0.98999999999999999
597 | M11: B1: 08.03 Plan Aftercare Services Meeting (CARESV1-2) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 717SS | 744SS,4517FS-21d | As Soon As Possible | NA | 39 | 0d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | 8/11/25 | 10/3/25 | NA | 1
598 | M11: B2: 08.04 Conduct and Document Aftercare Services Meeting (CARESV1-1) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 743SS | 745SS,2993,4517FS-21d | As Soon As Possible | NA | 39 | 0d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | 8/11/25 | 10/3/25 | NA | 1
599 | M11: B3: 05.10 Conduct Initial or Re-Entry into Extended Foster Care (CARESV1-78) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 744SS | 1480FF,761,4522FF,4517FS-21d | As Soon As Possible | NA | 39 | 5d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | 8/11/25 | NA | NA | 0.95999999999999996
600 | Case Management: State QA | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 77 | 112d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.27000000000000002
625 | Milestone 07: Case Plan (CARESV1-522) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 39 | 150d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.62
626 | M7: B1: 05.12 Initiate and Update Concurrent Plan (CARESV1-81) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 735,703 | 749SS,750SS,751SS,752SS,753SS,766SS,4475SS,4460SS | As Soon As Possible | NA | 39 | 0d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | 10/3/25 | NA | 1
627 | M7: B2: 18.01 Provide Prevention Services (aka FFPSA) (CARESV1-55) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 748SS | 4475SS,4460SS | As Soon As Possible | NA | 39 | 150d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 2.9999999999999999E-2
628 | M7: B3: 05.03 Create & Update Case Plan (r1) (CARESV1-33) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 748SS | 4475SS,4460SS | As Soon As Possible | NA | 39 | 150d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.69999999999999996
629 | M7: B4: 05.07 Provide ILP Services (Early ILP and Transitional Age Youth) (CARESV1-130) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 748SS | 4475SS,4460SS | As Soon As Possible | NA | 39 | 150d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.94999999999999996
630 | M7: B5: Case Management Assessment Interface (CARESV1-13935) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 748SS | 4475SS,4460SS | As Soon As Possible | NA | 39 | 150d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 2.9999999999999999E-2
631 | M7: B6: Milestone 7 Refinement Stories | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 748SS | 5420,4475SS,4460SS | As Soon As Possible | NA | 39 | 0d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | 10/3/25 | NA | 1
632 | Milestone 13: Adoption (CARESV1-531) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 38 | 112d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | 10/6/25 | NA | NA | 0
633 | M13: B1 07.06 Provide Post Adoption Services (CARESV1-34) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 741 | 774SS,756SS,757SS,758SS,759SS,4534SS | As Soon As Possible | NA | 38 | 0.76d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
634 | M13: B2 07.01 Conduct Preliminary Adoption Assessment (CARESV1-12) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 755SS | 4534SS | As Soon As Possible | NA | 38 | 112d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | 10/6/25 | NA | NA | 0.02
636 | M13: B4 07.03 Conduct Activities to Finalize Adoption (CARESV1-8) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 755SS | 4534SS | As Soon As Possible | NA | 38 | 51d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
637 | M13: B5 07.04 Voluntary Relinquishment of Parental Rights (CARESV1-13) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 755SS | 4534SS | As Soon As Possible | NA | 38 | 51d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
638 | M13: B6 07.05 Conduct Adoption Set Aside Investigation (CARESV1-84) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 755SS | 5449,4534SS,727FS-10d | As Soon As Possible | NA | 38 | 51d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
639 | Milestone 11: Aftercare & Re-Entry (CARESV1-533) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 38 | 5d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
640 | M11: B1: 08.03 Plan Aftercare Services Meeting (CARESV1-2) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 745 | 781SS,762SS,4523SS | As Soon As Possible | NA | 38 | 5d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
641 | M11: B2: 08.04 Conduct and Document Aftercare Services Meeting (CARESV1-1) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 761SS | 763SS,4523SS | As Soon As Possible | NA | 38 | 63d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
642 | M11: B3: 05.10 Conduct Initial or Re-Entry into Extended Foster Care (CARESV1-78) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 762SS | 5441,4523SS | As Soon As Possible | NA | 38 | 63d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
643 | Case Management: Joint Review | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 77 | 112d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.14000000000000001
668 | Milestone 07: Case Plan (CARESV1-522) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 39 | 150d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.33000000000000002
669 | M7: B1: 05.12 Initiate and Update Concurrent Plan (CARESV1-81) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 748SS | 767SS,2511SS | As Soon As Possible | NA | 39 | 150d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.82999999999999996
670 | M7: B2: 18.01 Provide Prevention Services (aka FFPSA) (CARESV1-55) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 766SS | 768SS | As Soon As Possible | NA | 39 | 150d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 4.0000000000000001E-2
671 | M7: B3: 05.03 Create & Update Case Plan (r1) (CARESV1-33) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 767SS | 769SS | As Soon As Possible | NA | 39 | 150d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.41999999999999998
672 | M7: B4: 05.07 Provide ILP Services (Early ILP and Transitional Age Youth) (CARESV1-130) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 768SS | 770SS | As Soon As Possible | NA | 39 | 150d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.62
673 | M7: B5: Case Management Assessment Interface (CARESV1-13935) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 769SS | 771SS | As Soon As Possible | NA | 39 | 150d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 4.0000000000000001E-2
674 | M7: B6: Milestone 7 Refinement Stories | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 770SS | 772FF | As Soon As Possible | NA | 39 | 150d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 4.0000000000000001E-2
10448 | Milestone 07: Case Plan (CARESV1-522) Complete | October 3, 2025 5:00 PM | October 3, 2025 5:00 PM | 771FF |  | As Soon As Possible | NA | 0 | 150d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
675 | Milestone 13: Adoption (CARESV1-531) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 38 | 112d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
676 | M13: B1 07.06 Provide Post Adoption Services (CARESV1-34) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 755SS | 775SS | As Soon As Possible | NA | 38 | 112d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
677 | M13: B2 07.01 Conduct Preliminary Adoption Assessment (CARESV1-12) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 774SS | 776SS | As Soon As Possible | NA | 38 | 112d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
679 | M13: B4 07.03 Conduct Activities to Finalize Adoption (CARESV1-8) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 775SS | 777SS | As Soon As Possible | NA | 38 | 112d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
680 | M13: B5 07.04 Voluntary Relinquishment of Parental Rights (CARESV1-13) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 776SS | 778SS | As Soon As Possible | NA | 38 | 112d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
681 | M13: B6 07.05 Conduct Adoption Set Aside Investigation (CARESV1-84) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 777SS | 779FF | As Soon As Possible | NA | 38 | 112d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
10449 | Milestone 13: Adoption (CARESV1-531) Complete | November 28, 2025 5:00 PM | November 28, 2025 5:00 PM | 778FF |  | As Soon As Possible | NA | 0 | 112d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
682 | Milestone 11: Aftercare & Re-Entry (CARESV1-533) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 38 | 5d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
683 | M11: B1: 08.03 Plan Aftercare Services Meeting (CARESV1-2) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 761SS | 782SS,2536SS,2537SS | As Soon As Possible | NA | 38 | 5d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
684 | M11: B2: 08.04 Conduct and Document Aftercare Services Meeting (CARESV1-1) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 781SS | 783SS | As Soon As Possible | NA | 38 | 112d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
685 | M11: B3: 05.10 Conduct Initial or Re-Entry into Extended Foster Care (CARESV1-78) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 782SS | 784FF | As Soon As Possible | NA | 38 | 112d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
10450 | Milestone 11: Aftercare & Re-Entry (CARESV1-533) Complete | November 28, 2025 5:00 PM | November 28, 2025 5:00 PM | 783FF |  | As Soon As Possible | NA | 0 | 112d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
746 | Courts | May 22, 2023 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 596 | 505d | May 22, 2023 8:00 AM | December 30, 2025 5:00 PM | 655 days | No | 5/22/23 | NA | NA | 0.88
4339 | Walkthrough | May 6, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | May 6, 2024 8:00 AM | May 31, 2024 5:00 PM | 19 days | No | 5/6/24 | 5/31/24 | NA | 1
4343 | Milestone 14 | May 6, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | May 6, 2024 8:00 AM | May 31, 2024 5:00 PM | 19 days | No | 5/6/24 | 5/31/24 | NA | 1
4595 | Courts - M14 - Conduct Walkthrough | May 6, 2024 8:00 AM | May 31, 2024 5:00 PM |  | 1475,790SS | Must Start On | 5/6/24 | 19 | 0d | May 6, 2024 8:00 AM | May 31, 2024 5:00 PM | 19 days | No | 5/6/24 | 5/31/24 | NA | 1
4342 | Milestone 15 | May 6, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | May 6, 2024 8:00 AM | May 31, 2024 5:00 PM | 19 days | No | 5/6/24 | 5/31/24 | NA | 1
4596 | Courts - M15 - Conduct Walkthrough | May 6, 2024 8:00 AM | May 31, 2024 5:00 PM | 788SS | 1475,798 | As Soon As Possible | NA | 19 | 0d | May 6, 2024 8:00 AM | May 31, 2024 5:00 PM | 19 days | No | 5/6/24 | 5/31/24 | NA | 1
760 | Courts: Holistic Design Milestones | May 22, 2023 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 596 | 505d | May 22, 2023 8:00 AM | December 30, 2025 5:00 PM | 655 days | No | 5/22/23 | NA | NA | 0.88
4354 | Group 1 Courts Processing (Milestones 16, 17, 18) | April 22, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 236 | 0d | April 22, 2024 8:00 AM | March 28, 2025 5:00 PM | 236 days | No | 4/22/24 | 3/28/25 | NA | 1
4223 | Courts Group 1 - Finalize Requirements Baseline | April 22, 2024 8:00 AM | August 23, 2024 5:00 PM | 835FF | 5453FS-40d,5459FS-40d,5465FS-40d,5471FS-40d | As Soon As Possible | NA | 88 | 0d | April 22, 2024 8:00 AM | August 23, 2024 5:00 PM | 88 days | No | 4/22/24 | 8/23/24 | NA | 1
4210 | Courts: Holistic Design Artifacts | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 173 | 0d | August 15, 2024 8:00 AM | March 28, 2025 5:00 PM | 155 days | No | 7/22/24 | 3/28/25 | NA | 1
4215 | Courts - Design Cycle 1 | July 22, 2024 8:00 AM | January 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 115 | 0d | August 15, 2024 8:00 AM | January 3, 2025 5:00 PM | 97 days | No | 7/22/24 | 1/3/25 | NA | 1
11598 | Courts - Design Cycle 1 - Draft & Review Application Flow | July 22, 2024 8:00 AM | August 14, 2024 5:00 PM |  |  | As Soon As Possible | NA | 18 | 0d | NA | NA | 0 days? | No | 7/22/24 | 8/14/24 | NA | 1
11599 | Courts - Design Cycle 1 - Implementation Artifacts Review | August 5, 2024 8:00 AM | August 9, 2024 5:00 PM |  |  | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 8/5/24 | 8/9/24 | NA | 1
4216 | Courts - Design Cycle 1 - Prepare Blueprint | August 15, 2024 8:00 AM | December 20, 2024 5:00 PM | 790 | 799SS+10d,2282SS,2286SS,2290SS,2294SS,1337SS,1363SS | Must Start On | 8/15/24 | 89 | 0d | August 15, 2024 8:00 AM | December 20, 2024 5:00 PM | 89 days | No | 8/15/24 | 12/20/24 | NA | 1
4217 | Courts - Design Cycle 1 - Review Blueprint | August 29, 2024 8:00 AM | December 27, 2024 5:00 PM | 798SS+10d | 800SS+5d | As Soon As Possible | NA | 83 | 0d | August 29, 2024 8:00 AM | December 27, 2024 5:00 PM | 83 days | No | 8/29/24 | 12/27/24 | NA | 1
4218 | Courts - Design Cycle 1 - Revise and Finalize Blueprint | September 5, 2024 8:00 AM | January 3, 2025 5:00 PM | 799SS+5d | 804FS+14d,802 | As Soon As Possible | NA | 82 | 0d | September 5, 2024 8:00 AM | January 3, 2025 5:00 PM | 82 days | No | 9/5/24 | 1/3/25 | NA | 1
4219 | Design Cycle 2 | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 58 | 0d | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM | 58 days | No | 1/6/25 | 3/28/25 | NA | 1
11484 | Courts - Design Cycle 2 - Perform Pre-Build activities | January 6, 2025 8:00 AM | March 7, 2025 5:00 PM | 800 | 805SS+5d,2283SS,2287SS,2291SS,2295SS,2562SS,2568SS,2574SS,803SS+10d | Start No Earlier Than | 12/6/24 | 43 | 0d | January 6, 2025 8:00 AM | March 7, 2025 5:00 PM | 43 days | No | 1/6/25 | 3/7/25 | NA | 1
11483 | Courts - Design Cycle 2 - Perform Pre-Build QA (with VPOD) and Address Findings | January 21, 2025 8:00 AM | March 7, 2025 5:00 PM | 802SS+10d | 805SS+5d,2283SS,2287SS,2291SS,2295SS,2562SS,2568SS,2574SS | Start No Earlier Than | 12/6/24 | 33 | 0d | January 21, 2025 8:00 AM | March 7, 2025 5:00 PM | 33 days | No | 1/21/25 | 3/7/25 | NA | 1
4220 | Courts - Design Cycle 2 - Prepare for Walkthrough with Core Constituents | January 27, 2025 8:00 AM | March 7, 2025 5:00 PM | 800FS+14d | 805SS+5d,2283SS,2287SS,2291SS,2295SS,2562SS,2568SS,2574SS | Start No Earlier Than | 12/6/24 | 29 | 0d | January 27, 2025 8:00 AM | March 7, 2025 5:00 PM | 29 days | No | 1/27/25 | 3/7/25 | NA | 1
4221 | Courts - Design Cycle 2 - Conduct Design Walkthrough with Core Constituents | February 3, 2025 8:00 AM | March 21, 2025 5:00 PM | 804SS+5d,803SS+5d,802SS+5d | 806SS+5d | As Soon As Possible | NA | 34 | 0d | February 3, 2025 8:00 AM | March 21, 2025 5:00 PM | 34 days | No | 2/3/25 | 3/21/25 | NA | 1
4222 | Courts - Design Cycle 2 - Final Review and Design Baseline | February 10, 2025 8:00 AM | March 28, 2025 5:00 PM | 805SS+5d | 852FF,856FF,861FF | As Soon As Possible | NA | 34 | 0d | February 10, 2025 8:00 AM | March 28, 2025 5:00 PM | 34 days | No | 2/10/25 | 3/28/25 | NA | 1
761 | Courts: Context Setting | May 22, 2023 8:00 AM | May 17, 2024 5:00 PM |  |  | As Soon As Possible | NA | 249 | 0d | May 22, 2023 8:00 AM | May 17, 2024 5:00 PM | 249 days | No | 5/22/23 | 5/17/24 | NA | 1
780 | Milestone 16: Jurisdiction & Disposition Hearing (CARESV1-518) | November 6, 2023 8:00 AM | April 5, 2024 5:00 PM |  |  | As Soon As Possible | NA | 102 | 0d | November 6, 2023 8:00 AM | April 5, 2024 5:00 PM | 102 days | No | 11/6/23 | 4/5/24 | NA | 1
781 | M16: RC: Finalize Value Hypothesis | November 6, 2023 8:00 AM | January 12, 2024 5:00 PM |  | 810SS | Must Start On | 11/6/23 | 45 | 0d | November 6, 2023 8:00 AM | January 12, 2024 5:00 PM | 45 days | No | 11/6/23 | 1/12/24 | NA | 1
782 | M16: RC: Draft Service Maps | November 6, 2023 8:00 AM | December 20, 2023 5:00 PM | 809SS | 811SS | As Soon As Possible | NA | 30 | 0d | November 6, 2023 8:00 AM | December 20, 2023 5:00 PM | 30 days | No | 11/6/23 | 12/20/23 | NA | 1
783 | M16: RC: Complete Legacy Analysis | November 6, 2023 8:00 AM | December 6, 2023 5:00 PM | 810SS | 812SS | As Soon As Possible | NA | 20 | 0d | November 6, 2023 8:00 AM | December 6, 2023 5:00 PM | 20 days | No | 11/6/23 | 12/6/23 | NA | 1
784 | M16: RC: Finalize Epics | November 6, 2023 8:00 AM | November 10, 2023 5:00 PM | 811SS | 813SS | As Soon As Possible | NA | 5 | 0d | November 6, 2023 8:00 AM | November 10, 2023 5:00 PM | 5 days | No | 11/6/23 | 11/10/23 | NA | 1
785 | M16: RC: Complete conceptual and epic-level Domain Model diagrams | November 6, 2023 8:00 AM | January 5, 2024 5:00 PM | 812SS | 814SS | As Soon As Possible | NA | 40 | 0d | November 6, 2023 8:00 AM | January 5, 2024 5:00 PM | 40 days | No | 11/6/23 | 1/5/24 | NA | 1
786 | M16: RC: Define User Story titles | November 6, 2023 8:00 AM | December 20, 2023 5:00 PM | 813SS | 815SS | As Soon As Possible | NA | 30 | 0d | November 6, 2023 8:00 AM | December 20, 2023 5:00 PM | 30 days | No | 11/6/23 | 12/20/23 | NA | 1
787 | M16: RC: Complete External Systems pre-analysis | January 24, 2024 8:00 AM | March 22, 2024 5:00 PM | 814SS | 816SS | As Soon As Possible | NA | 42 | 0d | January 24, 2024 8:00 AM | March 22, 2024 5:00 PM | 42 days | No | 1/24/24 | 3/22/24 | NA | 1
788 | M16: RC: Facilitate Inception | March 8, 2024 8:00 AM | April 5, 2024 5:00 PM | 815SS | 837FS+23d,2561SS | As Soon As Possible | NA | 20 | 0d | March 8, 2024 8:00 AM | April 5, 2024 5:00 PM | 20 days | No | 3/8/24 | 4/5/24 | NA | 1
806 | Milestone 17: Status Reviews (CARESV1-517) | January 2, 2024 8:00 AM | May 17, 2024 5:00 PM |  |  | As Soon As Possible | NA | 96 | 0d | January 2, 2024 8:00 AM | May 17, 2024 5:00 PM | 96 days | No | 1/2/24 | 5/17/24 | NA | 1
807 | M17: RC: Finalize Value Hypothesis | January 2, 2024 8:00 AM | March 6, 2024 5:00 PM |  | 819SS+5d | As Soon As Possible | NA | 45 | 0d | January 2, 2024 8:00 AM | March 6, 2024 5:00 PM | 45 days | No | 1/2/24 | 3/6/24 | NA | 1
808 | M17: RC: Draft Service Maps | January 9, 2024 8:00 AM | February 21, 2024 5:00 PM | 818SS+5d | 820,822SS+5d | As Soon As Possible | NA | 30 | 0d | January 9, 2024 8:00 AM | February 21, 2024 5:00 PM | 30 days | No | 1/9/24 | 2/21/24 | NA | 1
809 | M17: RC: Complete Legacy Analysis | February 22, 2024 8:00 AM | March 20, 2024 5:00 PM | 819 | 821 | As Soon As Possible | NA | 20 | 0d | February 22, 2024 8:00 AM | March 20, 2024 5:00 PM | 20 days | No | 2/22/24 | 3/20/24 | NA | 1
810 | M17: RC: Finalize Epics | March 21, 2024 8:00 AM | March 27, 2024 5:00 PM | 820 | 822 | As Soon As Possible | NA | 5 | 0d | March 21, 2024 8:00 AM | March 27, 2024 5:00 PM | 5 days | No | 3/21/24 | 3/27/24 | NA | 1
811 | M17: RC: Complete conceptual and epic-level Domain Model diagrams | January 17, 2024 8:00 AM | March 13, 2024 5:00 PM | 819SS+5d,821 | 823 | As Soon As Possible | NA | 40 | 0d | January 17, 2024 8:00 AM | March 13, 2024 5:00 PM | 40 days | No | 1/17/24 | 3/13/24 | NA | 1
812 | M17: RC: Define User Story titles | March 14, 2024 8:00 AM | April 25, 2024 5:00 PM | 822 | 824 | As Soon As Possible | NA | 30 | 0d | March 14, 2024 8:00 AM | April 25, 2024 5:00 PM | 30 days | No | 3/14/24 | 4/25/24 | NA | 1
813 | M17: RC: Complete External Systems pre-analysis | April 26, 2024 8:00 AM | May 17, 2024 5:00 PM | 823 | 825SS | As Soon As Possible | NA | 16 | 0d | April 26, 2024 8:00 AM | May 17, 2024 5:00 PM | 16 days | No | 4/26/24 | 5/17/24 | NA | 1
814 | M17: RC: Facilitate Inception | April 26, 2024 8:00 AM | May 17, 2024 5:00 PM | 824SS | 2567SS | As Soon As Possible | NA | 16 | 0d | April 26, 2024 8:00 AM | May 17, 2024 5:00 PM | 16 days | No | 4/26/24 | 5/17/24 | NA | 1
815 | Milestone 18: Other Hearings (CARESV1-516) | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM |  |  | As Soon As Possible | NA | 80 | 0d | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 80 days | No | 5/22/23 | 9/13/23 | NA | 1
816 | M18: RC: Finalize Value Hypothesis | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM |  | 828SS | Must Start On | 5/22/23 | 80 | 0d | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 80 days | No | 5/22/23 | 9/13/23 | NA | 1
817 | M18: RC: Draft Service Maps | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 827SS | 829SS | As Soon As Possible | NA | 80 | 0d | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 80 days | No | 5/22/23 | 9/13/23 | NA | 1
818 | M18: RC: Complete Legacy Analysis | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 828SS | 830SS | As Soon As Possible | NA | 80 | 0d | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 80 days | No | 5/22/23 | 9/13/23 | NA | 1
819 | M18: RC: Finalize Epics | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 829SS | 831SS | As Soon As Possible | NA | 80 | 0d | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 80 days | No | 5/22/23 | 9/13/23 | NA | 1
820 | M18: RC: Complete conceptual and epic-level Domain Model diagrams | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 830SS | 832SS | As Soon As Possible | NA | 80 | 0d | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 80 days | No | 5/22/23 | 9/13/23 | NA | 1
821 | M18: RC: Define User Story titles | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 831SS | 833SS | As Soon As Possible | NA | 80 | 0d | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 80 days | No | 5/22/23 | 9/13/23 | NA | 1
822 | M18: RC: Complete External Systems pre-analysis | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 832SS | 834SS | As Soon As Possible | NA | 80 | 0d | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 80 days | No | 5/22/23 | 9/13/23 | NA | 1
823 | M18: RC: Facilitate Inception | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 833SS | 846FS+12d,2573SS | As Soon As Possible | NA | 80 | 0d | May 22, 2023 8:00 AM | September 13, 2023 5:00 PM | 80 days | No | 5/22/23 | 9/13/23 | NA | 1
789 | Courts: BRC | October 2, 2023 8:00 AM | August 9, 2024 5:00 PM |  | 793FF | As Soon As Possible | NA | 215 | 0d | October 2, 2023 8:00 AM | August 9, 2024 5:00 PM | 215 days | No | 10/2/23 | 8/9/24 | NA | 1
797 | Milestone 16: Jurisdiction & Disposition Hearing (CARESV1-518) | May 9, 2024 8:00 AM | June 21, 2024 5:00 PM |  |  | As Soon As Possible | NA | 31 | 0d | May 9, 2024 8:00 AM | June 21, 2024 5:00 PM | 31 days | No | 5/9/24 | 6/21/24 | NA | 1
798 | M16: B1 09.11 Generate Notices (CARESV1-67) | May 9, 2024 8:00 AM | June 21, 2024 5:00 PM | 816FS+23d | 838SS | As Soon As Possible | NA | 31 | 0d | May 9, 2024 8:00 AM | June 21, 2024 5:00 PM | 31 days | No | 5/9/24 | 6/21/24 | NA | 1
799 | M16: B2 09.02 Prepare for Jurisdiction Hearing (CARESV1-89) | May 9, 2024 8:00 AM | June 21, 2024 5:00 PM | 837SS | 839SS | As Soon As Possible | NA | 31 | 0d | May 9, 2024 8:00 AM | June 21, 2024 5:00 PM | 31 days | No | 5/9/24 | 6/21/24 | NA | 1
800 | M16: B3 09.03 Prepare for Disposition Hearing (CARESV1-71) | May 9, 2024 8:00 AM | June 21, 2024 5:00 PM | 838SS | 841SS-13d | As Soon As Possible | NA | 31 | 0d | May 9, 2024 8:00 AM | June 21, 2024 5:00 PM | 31 days | No | 5/9/24 | 6/21/24 | NA | 1
801 | Milestone 17: Status Reviews (CARESV1-517) | April 22, 2024 8:00 AM | August 9, 2024 5:00 PM |  |  | As Soon As Possible | NA | 78 | 0d | April 22, 2024 8:00 AM | August 9, 2024 5:00 PM | 78 days | No | 4/22/24 | 8/9/24 | NA | 1
836 | M17: B1 09.04 Prepare for Status Review: Family Reunification (CARESV1-23) | April 22, 2024 8:00 AM | August 9, 2024 5:00 PM | 839SS-13d | 842SS | As Soon As Possible | NA | 78 | 0d | April 22, 2024 8:00 AM | August 9, 2024 5:00 PM | 78 days | No | 4/22/24 | 8/9/24 | NA | 1
837 | M17: B2 09.05 Prepare for Status Review: Family Maintenance (CARESV1-27) | April 22, 2024 8:00 AM | August 9, 2024 5:00 PM | 841SS | 843SS | As Soon As Possible | NA | 78 | 0d | April 22, 2024 8:00 AM | August 9, 2024 5:00 PM | 78 days | No | 4/22/24 | 8/9/24 | NA | 1
838 | M17: B3 09.07 Prepare for Status Review: Permanent Plan (CARESV1-31) | April 22, 2024 8:00 AM | August 9, 2024 5:00 PM | 842SS | 844SS | As Soon As Possible | NA | 78 | 0d | April 22, 2024 8:00 AM | August 9, 2024 5:00 PM | 78 days | No | 4/22/24 | 8/9/24 | NA | 1
839 | M17: B4 09.08 Prepare for Non-Minor Dependent Review (CARESV1-38) | April 22, 2024 8:00 AM | August 9, 2024 5:00 PM | 843SS | 849FF | As Soon As Possible | NA | 78 | 0d | April 22, 2024 8:00 AM | August 9, 2024 5:00 PM | 78 days | No | 4/22/24 | 8/9/24 | NA | 1
802 | Milestone 18: Other Hearings (CARESV1-516) | October 2, 2023 8:00 AM | May 10, 2024 5:00 PM |  |  | As Soon As Possible | NA | 152 | 0d | October 2, 2023 8:00 AM | May 10, 2024 5:00 PM | 152 days | No | 10/2/23 | 5/10/24 | NA | 1
840 | M18: B1 09.06 Prepare for 366.26 Selection and Implementation Hearing (CARESV1-25) | October 2, 2023 8:00 AM | May 10, 2024 5:00 PM | 834FS+12d | 847SS | As Soon As Possible | NA | 152 | 0d | October 2, 2023 8:00 AM | May 10, 2024 5:00 PM | 152 days | No | 10/2/23 | 5/10/24 | NA | 1
841 | M18: B2 09.09 Prepare for Special or Interim Hearings CARESV1-36) | October 2, 2023 8:00 AM | May 10, 2024 5:00 PM | 846SS | 848SS | As Soon As Possible | NA | 152 | 0d | October 2, 2023 8:00 AM | May 10, 2024 5:00 PM | 152 days | No | 10/2/23 | 5/10/24 | NA | 1
842 | M18: B3 09.12 Prepare for Ad Hoc Activity (CARESV1-40) | October 2, 2023 8:00 AM | May 10, 2024 5:00 PM | 847SS | 861 | As Soon As Possible | NA | 152 | 0d | October 2, 2023 8:00 AM | May 10, 2024 5:00 PM | 152 days | No | 10/2/23 | 5/10/24 | NA | 1
803 | Courts BRC Milestone Completion | August 9, 2024 5:00 PM | August 9, 2024 5:00 PM | 844FF | 852FS-10d | As Soon As Possible | NA | 0 | 0d | August 9, 2024 5:00 PM | August 9, 2024 5:00 PM | 0 days | Yes | 8/9/24 | 8/9/24 | NA | 1
843 | Courts: Design | July 1, 2024 8:00 AM | June 27, 2025 5:00 PM |  |  | As Soon As Possible | NA | 250 | 0d | July 1, 2024 8:00 AM | March 28, 2025 5:00 PM | 187 days | No | 7/1/24 | 6/27/25 | NA | 1
850 | Milestone 16: Jurisdiction & Disposition Hearing (CARESV1-518) | July 22, 2024 8:00 AM | June 27, 2025 5:00 PM |  |  | As Soon As Possible | NA | 236 | 0d | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM | 173 days | No | 7/22/24 | 6/27/25 | NA | 1
851 | M16: B1 09.11 Generate Notices (CARESV1-67) | July 22, 2024 8:00 AM | June 27, 2025 5:00 PM | 806FF,849FS-10d | 853SS,867,871,876 | Must Start On | 7/22/24 | 234 | 0d | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM | 171 days | No | 7/22/24 | 6/27/25 | NA | 1
852 | M16: B2 09.02 Prepare for Jurisdiction Hearing (CARESV1-89) | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM | 852SS | 854SS | As Soon As Possible | NA | 173 | 0d | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM | 173 days | No | 7/22/24 | 3/28/25 | NA | 1
853 | M16: B3 09.03 Prepare for Disposition Hearing (CARESV1-71) | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM | 853SS |  | As Soon As Possible | NA | 173 | 0d | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM | 173 days | No | 7/22/24 | 3/28/25 | NA | 1
854 | Milestone 17: Status Reviews (CARESV1-517) | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 173 | 0d | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM | 173 days | No | 7/22/24 | 3/28/25 | NA | 1
855 | M17: B1 09.04 Prepare for Status Review: Family Reunification (CARESV1-23) | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM | 806FF | 857SS | As Soon As Possible | NA | 173 | 0d | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM | 173 days | No | 7/22/24 | 3/28/25 | NA | 1
856 | M17: B2 09.05 Prepare for Status Review: Family Maintenance (CARESV1-27) | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM | 856SS | 858SS | As Soon As Possible | NA | 173 | 0d | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM | 173 days | No | 7/22/24 | 3/28/25 | NA | 1
857 | M17: B3 09.07 Prepare for Status Review: Permanent Plan (CARESV1-31) | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM | 857SS | 859SS | As Soon As Possible | NA | 173 | 0d | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM | 173 days | No | 7/22/24 | 3/28/25 | NA | 1
858 | M17: B4 09.08 Prepare for Non-Minor Dependent Review (CARESV1-38) | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM | 858SS |  | As Soon As Possible | NA | 173 | 0d | July 22, 2024 8:00 AM | March 28, 2025 5:00 PM | 173 days | No | 7/22/24 | 3/28/25 | NA | 1
859 | Milestone 18: Other Hearings (CARESV1-516) | July 1, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 187 | 0d | July 1, 2024 8:00 AM | March 28, 2025 5:00 PM | 187 days | No | 7/1/24 | 3/28/25 | NA | 1
860 | M18: B1 09.06 Prepare for 366.26 Selection and Implementation Hearing (CARESV1-25) | July 1, 2024 8:00 AM | March 28, 2025 5:00 PM | 806FF,848 | 862SS | As Soon As Possible | NA | 187 | 0d | July 1, 2024 8:00 AM | March 28, 2025 5:00 PM | 187 days | No | 7/1/24 | 3/28/25 | NA | 1
6376 | M18: B2 09.09 Prepare for Special or Interim Hearings CARESV1-36) | July 1, 2024 8:00 AM | March 28, 2025 5:00 PM | 861SS | 863SS | As Soon As Possible | NA | 187 | 0d | July 1, 2024 8:00 AM | March 28, 2025 5:00 PM | 187 days | No | 7/1/24 | 3/28/25 | NA | 1
6375 | M18: B3 09.12 Prepare for Ad Hoc Activity (CARESV1-40) | July 1, 2024 8:00 AM | March 28, 2025 5:00 PM | 862SS | 864FF | As Soon As Possible | NA | 187 | 0d | July 1, 2024 8:00 AM | March 28, 2025 5:00 PM | 187 days | No | 7/1/24 | 3/28/25 | NA | 1
863 | Courts Design Milestone Completion | March 28, 2025 5:00 PM | March 28, 2025 5:00 PM | 863FF | 4547,4562,4577,4592 | As Soon As Possible | NA | 0 | 0d | March 28, 2025 5:00 PM | March 28, 2025 5:00 PM | 0 days | Yes | 3/28/25 | 3/28/25 | NA | 1
864 | Courts: Build | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 29 | 544d | April 1, 2025 8:00 AM | December 30, 2025 5:00 PM | 190 days | No | 6/30/25 | NA | NA | 0.89000000000000001
871 | Milestone 16: Jurisdiction & Disposition Hearing (CARESV1-518) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 29 | 544d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 6/30/25 | NA | NA | 0.77000000000000002
872 | M16: B1 09.11 Generate Notices (CARESV1-67) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 852 | 868SS,2288SS,2308SS,2563SS,2589SS,4567 | As Soon As Possible | NA | 29 | 0d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 6/30/25 | 8/8/25 | NA | 1
873 | M16: B2 09.02 Prepare for Jurisdiction Hearing (CARESV1-89) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 867SS | 869SS,4567 | Start No Earlier Than | 4/1/25 | 29 | 544d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 6/30/25 | NA | NA | 0.82999999999999996
874 | M16: B3 09.03 Prepare for Disposition Hearing (CARESV1-71) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 868SS | 882SS,4567 | Start No Earlier Than | 4/1/25 | 29 | 544d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 6/30/25 | NA | NA | 0.47999999999999998
875 | Milestone 17: Status Reviews (CARESV1-517) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 29 | 43.74d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 6/30/25 | NA | NA | 0.93999999999999995
876 | M17: B1 09.04 Prepare for Status Review: Family Reunification (CARESV1-23) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 852 | 872SS,2292SS,2569SS,2575SS,4582 | As Soon As Possible | NA | 29 | 0d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 6/30/25 | 8/8/25 | NA | 1
877 | M17: B2 09.05 Prepare for Status Review: Family Maintenance (CARESV1-27) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 871SS | 873SS,4582 | Start No Earlier Than | 4/1/25 | 29 | 43.74d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 6/30/25 | NA | NA | 0.75
878 | M17: B3 09.07 Prepare for Status Review: Permanent Plan (CARESV1-31) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 872SS | 874SS,4582 | Start No Earlier Than | 4/1/25 | 29 | 0d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 6/30/25 | 8/8/25 | NA | 1
879 | M17: B4 09.08 Prepare for Non-Minor Dependent Review (CARESV1-38) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 873SS | 886SS,4582 | Start No Earlier Than | 4/1/25 | 29 | 0d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 6/30/25 | 8/8/25 | NA | 1
880 | Milestone 18: Other Hearings (CARESV1-516) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 29 | 544d | April 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 169 days | No | 6/30/25 | NA | NA | 0.93000000000000005
881 | M18: B1 09.06 Prepare for 366.26 Selection and Implementation Hearing (CARESV1-25) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 852 | 877SS,2296SS,4597 | As Soon As Possible | NA | 29 | 544d | April 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 169 days | No | 6/30/25 | NA | NA | 0.88
882 | M18: B2 09.09 Prepare for Special or Interim Hearings CARESV1-36) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 876SS | 878SS,4597 | As Soon As Possible | NA | 29 | 544d | April 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 169 days | No | 6/30/25 | NA | NA | 0.93999999999999995
883 | M18: B3 09.12 Prepare for Ad Hoc Activity (CARESV1-40) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 877SS | 879FF,1480FF,891SS,4597 | As Soon As Possible | NA | 29 | 544d | April 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 169 days | No | 6/30/25 | NA | NA | 0.96999999999999997
884 | Courts Build Milestone Completion | August 8, 2025 5:00 PM | August 8, 2025 5:00 PM | 878FF | 4597 | As Soon As Possible | NA | 0 | 544d | December 1, 2025 5:00 PM | December 1, 2025 5:00 PM | 0 days | Yes | 8/8/25 | NA | NA | 0.84999999999999998
4915 | Courts: SIT | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 29 | 544d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 6/30/25 | NA | NA | 0.81999999999999995
4920 | Milestone 16: Jurisdiction & Disposition Hearing (CARESV1-518) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 29 | 43.94d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 6/30/25 | NA | NA | 0.66000000000000003
4921 | M16: B1 09.11 Generate Notices (CARESV1-67) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 869SS | 883SS,4567,4571,4572 | As Soon As Possible | NA | 29 | 43.94d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 6/30/25 | NA | NA | 0.80000000000000004
4922 | M16: B2 09.02 Prepare for Jurisdiction Hearing (CARESV1-89) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 882SS | 884SS,4567,4571,4572 | As Soon As Possible | NA | 29 | 43.94d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 6/30/25 | NA | NA | 0.75
4923 | M16: B3 09.03 Prepare for Disposition Hearing (CARESV1-71) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 883SS | 897,4566SS-20d,4567,4571,4572 | As Soon As Possible | NA | 29 | 13.65d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 6/30/25 | NA | NA | 0.42999999999999999
4924 | Milestone 17: Status Reviews (CARESV1-517) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 29 | 43.74d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 6/30/25 | NA | NA | 0.91000000000000003
4925 | M17: B1 09.04 Prepare for Status Review: Family Reunification (CARESV1-23) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 874SS | 887SS,4582,4586,4587 | As Soon As Possible | NA | 29 | 43.74d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 6/30/25 | NA | NA | 0.95999999999999996
4926 | M17: B2 09.05 Prepare for Status Review: Family Maintenance (CARESV1-27) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 886SS | 888SS,4582,4586,4587 | As Soon As Possible | NA | 29 | 43.74d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 6/30/25 | NA | NA | 0.75
4927 | M17: B3 09.07 Prepare for Status Review: Permanent Plan (CARESV1-31) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 887SS | 889SS,4582,4586,4587 | As Soon As Possible | NA | 29 | 0d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 6/30/25 | 8/8/25 | NA | 1
4928 | M17: B4 09.08 Prepare for Non-Minor Dependent Review (CARESV1-38) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 888SS | 901,4581SS-20d,2997,4582,4586,4587 | As Soon As Possible | NA | 29 | 16.38d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 6/30/25 | NA | NA | 0.91000000000000003
4929 | Milestone 18: Other Hearings (CARESV1-516) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 29 | 544d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 6/30/25 | NA | NA | 0.87
4930 | M18: B1 09.06 Prepare for 366.26 Selection and Implementation Hearing (CARESV1-25) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 878SS | 892SS,4597,4601 | As Soon As Possible | NA | 29 | 544d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 6/30/25 | NA | NA | 0.88
4931 | M18: B2 09.09 Prepare for Special or Interim Hearings CARESV1-36) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 891SS | 893SS,4597,4601 | As Soon As Possible | NA | 29 | 544d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 6/30/25 | NA | NA | 0.93999999999999995
4932 | M18: B3 09.12 Prepare for Ad Hoc Activity (CARESV1-40) | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 892SS | 894FF,1480FF,906,4596SS-20d,4597,4601 | As Soon As Possible | NA | 29 | 25.35d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 6/30/25 | NA | NA | 0.80000000000000004
4933 | Courts SIT Milestone Completion | August 8, 2025 5:00 PM | August 8, 2025 5:00 PM | 893FF | 2998,4597 | As Soon As Possible | NA | 0 | 544d | November 28, 2025 5:00 PM | November 28, 2025 5:00 PM | 0 days | Yes | 8/8/25 | NA | NA | 0.84999999999999998
885 | Courts: State QA | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.28999999999999998
892 | Milestone 16: Jurisdiction & Disposition Hearing (CARESV1-518) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.17999999999999999
893 | M16: B1 09.11 Generate Notices (CARESV1-67) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 884 | 898SS,2564SS | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.34999999999999998
894 | M16: B2 09.02 Prepare for Jurisdiction Hearing (CARESV1-89) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 897SS | 899SS | As Soon As Possible | NA | 39 | 7.02d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
895 | M16: B3 09.03 Prepare for Disposition Hearing (CARESV1-71) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 898SS | 911SS,5463 | As Soon As Possible | NA | 39 | 5d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.17999999999999999
896 | Milestone 17: Status Reviews (CARESV1-517) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.20999999999999999
897 | M17: B1 09.04 Prepare for Status Review: Family Reunification (CARESV1-23) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 889 | 902SS,2570SS | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.41999999999999998
898 | M17: B2 09.05 Prepare for Status Review: Family Maintenance (CARESV1-27) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 901SS | 903SS | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.25
899 | M17: B3 09.07 Prepare for Status Review: Permanent Plan (CARESV1-31) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 902SS | 904SS | As Soon As Possible | NA | 39 | 7.02d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
900 | M17: B4 09.08 Prepare for Non-Minor Dependent Review (CARESV1-38) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 903SS | 916SS,5469 | As Soon As Possible | NA | 39 | 5d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.17999999999999999
901 | Milestone 18: Other Hearings (CARESV1-516) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.51000000000000001
902 | M18: B1 09.06 Prepare for 366.26 Selection and Implementation Hearing (CARESV1-25) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 893 | 907SS,2576SS | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.65000000000000002
903 | M18: B2 09.09 Prepare for Special or Interim Hearings CARESV1-36) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 906SS | 908SS | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.5
904 | M18: B3 09.12 Prepare for Ad Hoc Activity (CARESV1-40) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 907SS | 922SS,5475 | As Soon As Possible | NA | 39 | 5d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.37
905 | Courts: Joint Review | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.22
923 | Milestone 16: Jurisdiction & Disposition Hearing (CARESV1-518) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 7.0000000000000007E-2
925 | M16: B1 09.11 Generate Notices (CARESV1-67) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 899SS | 912SS,2565SS | Start No Earlier Than | 4/21/25 | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.20000000000000001
926 | M16: B2 09.02 Prepare for Jurisdiction Hearing (CARESV1-89) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 911SS | 913SS | As Soon As Possible | NA | 39 | 0.78d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
927 | M16: B3 09.03 Prepare for Disposition Hearing (CARESV1-71) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 912SS | 914FF | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.02
10452 | Milestone 16: Jurisdiction & Disposition Hearing (CARESV1-518) Complete | October 3, 2025 5:00 PM | October 3, 2025 5:00 PM | 913FF |  | As Soon As Possible | NA | 0 | 505d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
938 | Milestone 17: Status Reviews (CARESV1-517) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 8.9999999999999997E-2
940 | M17: B1 09.04 Prepare for Status Review: Family Reunification (CARESV1-23) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 904SS | 917SS,2571SS | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.14999999999999999
941 | M17: B2 09.05 Prepare for Status Review: Family Maintenance (CARESV1-27) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 916SS | 918SS | As Soon As Possible | NA | 39 | 8.58d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
942 | M17: B3 09.07 Prepare for Status Review: Permanent Plan (CARESV1-31) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 917SS | 919SS | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.22
943 | M17: B4 09.08 Prepare for Non-Minor Dependent Review (CARESV1-38) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 918SS | 920FF | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
10453 | Milestone 17: Status Reviews (CARESV1-517) Complete | October 3, 2025 5:00 PM | October 3, 2025 5:00 PM | 919FF |  | As Soon As Possible | NA | 0 | 505d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
951 | Milestone 18: Other Hearings (CARESV1-516) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.55000000000000004
953 | M18: B1 09.06 Prepare for 366.26 Selection and Implementation Hearing (CARESV1-25) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 908SS | 923SS,2577SS | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.65000000000000002
954 | M18: B2 09.09 Prepare for Special or Interim Hearings CARESV1-36) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 922SS | 924SS | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.62
955 | M18: B3 09.12 Prepare for Ad Hoc Activity (CARESV1-40) | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 923SS | 925FF | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.37
10454 | Milestone 18: Other Hearings (CARESV1-516) Complete | October 3, 2025 5:00 PM | October 3, 2025 5:00 PM | 924FF |  | As Soon As Possible | NA | 0 | 505d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
966 | Resource Family Approval | June 19, 2023 8:00 AM | January 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 652 | 430d | June 19, 2023 8:00 AM | December 30, 2025 5:00 PM | 700 days | No | 6/19/23 | NA | NA | 0.77000000000000002
967 | Resource Family Approval: Holistic Design Milestones | June 19, 2023 8:00 AM | January 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 652 | 430d | June 19, 2023 8:00 AM | December 30, 2025 5:00 PM | 700 days | No | 6/19/23 | NA | NA | 0.77000000000000002
968 | Group 1 Resource Family Approval (Milestones 26, 27, 28) | June 19, 2023 8:00 AM | January 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 652 | 430d | June 19, 2023 8:00 AM | December 30, 2025 5:00 PM | 700 days | No | 6/19/23 | NA | NA | 0.77000000000000002
969 | Resource Family Approval - Scenario Requirements Validation | October 7, 2024 8:00 AM | October 25, 2024 5:00 PM | 971FF+11d |  | As Soon As Possible | NA | 15 | 0d | July 30, 2024 8:00 AM | October 25, 2024 5:00 PM | 64 days | No | 10/7/24 | 10/25/24 | NA | 1
4195 | Resource Family Approval: Holistic Design Artifacts | July 30, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 167 | 636d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 7/30/24 | NA | NA | 0.98999999999999999
974 | Resource Family Approval - Design Cycle 1 | July 30, 2024 8:00 AM | January 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 109 | 0d | September 30, 2024 8:00 AM | January 3, 2025 5:00 PM | 65 days | No | 7/30/24 | 1/3/25 | NA | 1
11600 | Resource Family Approval - Design Cycle 1 - Draft & Review Application Flow | July 30, 2024 8:00 AM | September 24, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 7/30/24 | 9/24/24 | NA | 1
11601 | Resource Family Approval - Design Cycle 1 - Implementation Artifacts Review | August 29, 2024 8:00 AM | September 20, 2024 5:00 PM |  | 934FS+6d | As Soon As Possible | NA | 17 | 0d | NA | NA | 0 days? | No | 8/29/24 | 9/20/24 | NA | 1
975 | Resource Family Approval - Design Cycle 1 - Prepare Blueprint | September 30, 2024 8:00 AM | December 20, 2024 5:00 PM | 933FS+6d | 935SS+10d,2314SS,2318SS,2322SS,1331SS,1343SS,1369SS | Must Start On | 9/30/24 | 57 | 0d | September 30, 2024 8:00 AM | December 20, 2024 5:00 PM | 57 days | No | 9/30/24 | 12/20/24 | NA | 1
976 | Resource Family Approval - Design Cycle 1 - Review Blueprint | October 14, 2024 8:00 AM | December 27, 2024 5:00 PM | 934SS+10d | 936SS+5d | As Soon As Possible | NA | 51 | 0d | October 14, 2024 8:00 AM | December 27, 2024 5:00 PM | 51 days | No | 10/14/24 | 12/27/24 | NA | 1
977 | Resource Family Approval - Design Cycle 1 - Revise and Finalize Blueprint | October 21, 2024 8:00 AM | January 3, 2025 5:00 PM | 935SS+5d | 940FS+14d,938 | As Soon As Possible | NA | 50 | 0d | October 21, 2024 8:00 AM | January 3, 2025 5:00 PM | 50 days | No | 10/21/24 | 1/3/25 | NA | 1
978 | Resource Family Approval - Design Cycle 2 | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 58 | 636d | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM | 58 days | No | 1/6/25 | NA | NA | 0.98999999999999999
11486 | Resource Family Approval - Design Cycle 2 - Perform Pre-Build activities | January 6, 2025 8:00 AM | March 7, 2025 5:00 PM | 936 | 941SS+5d,2315SS,2319SS,2323SS,2600SS,2606SS,2612SS,939SS+10d | As Soon As Possible | NA | 43 | 0d | January 6, 2025 8:00 AM | March 7, 2025 5:00 PM | 43 days | No | 1/6/25 | 3/7/25 | NA | 1
11485 | Resource Family Approval - Design Cycle 2 - Perform Pre-Build QA (with VPOD) and Address Findings | January 21, 2025 8:00 AM | March 7, 2025 5:00 PM | 938SS+10d | 941SS+5d,2315SS,2319SS,2323SS,2600SS,2606SS,2612SS | As Soon As Possible | NA | 33 | 0d | January 21, 2025 8:00 AM | March 7, 2025 5:00 PM | 33 days | No | 1/21/25 | 3/7/25 | NA | 1
979 | Resource Family Approval - Design Cycle 2 - Prepare for Walkthrough with Core Constituents | January 27, 2025 8:00 AM | March 7, 2025 5:00 PM | 936FS+14d | 941SS+5d,2315SS,2319SS,2323SS,2600SS,2606SS,2612SS | As Soon As Possible | NA | 29 | 0d | January 27, 2025 8:00 AM | March 7, 2025 5:00 PM | 29 days | No | 1/27/25 | 3/7/25 | NA | 1
980 | Resource Family Approval - Design Cycle 2 - Conduct Design Walkthrough with Core Constituents | February 3, 2025 8:00 AM | March 21, 2025 5:00 PM | 940SS+5d,939SS+5d,938SS+5d | 942SS+5d | As Soon As Possible | NA | 34 | 0d | February 3, 2025 8:00 AM | March 21, 2025 5:00 PM | 34 days | No | 2/3/25 | 3/21/25 | NA | 1
981 | Resource Family Approval - Design Cycle 2 - Final Review and Design Baseline | February 10, 2025 8:00 AM | March 28, 2025 5:00 PM | 941SS+5d | 992FF,1000FF | Finish No Earlier Than | 5/9/24 | 34 | 636d | February 10, 2025 8:00 AM | March 28, 2025 5:00 PM | 34 days | No | 2/10/25 | NA | NA | 0.96999999999999997
982 | Resource Family Approval: Context Setting | June 19, 2023 8:00 AM | June 21, 2024 5:00 PM |  |  | As Soon As Possible | NA | 254 | 0d | June 19, 2023 8:00 AM | June 21, 2024 5:00 PM | 254 days | No | 6/19/23 | 6/21/24 | NA | 1
983 | Milestone 26: Maintain Resource Family Approval Home (CARESV1-508) | December 4, 2023 8:00 AM | April 26, 2024 5:00 PM |  |  | As Soon As Possible | NA | 100 | 0d | December 4, 2023 8:00 AM | April 26, 2024 5:00 PM | 100 days | No | 12/4/23 | 4/26/24 | NA | 1
984 | M26: RC: Finalize Value Hypothesis | December 4, 2023 8:00 AM | January 31, 2024 5:00 PM |  | 946SS+15d | As Soon As Possible | NA | 40 | 0d | December 4, 2023 8:00 AM | January 31, 2024 5:00 PM | 40 days | No | 12/4/23 | 1/31/24 | NA | 1
985 | M26: RC: Draft Service Maps | December 26, 2023 8:00 AM | January 24, 2024 5:00 PM | 945SS+15d | 947,949SS+15d | As Soon As Possible | NA | 20 | 0d | December 26, 2023 8:00 AM | January 24, 2024 5:00 PM | 20 days | No | 12/26/23 | 1/24/24 | NA | 1
986 | M26: RC: Complete Legacy Analysis | January 25, 2024 8:00 AM | February 22, 2024 5:00 PM | 946 | 948 | As Soon As Possible | NA | 20 | 0d | January 25, 2024 8:00 AM | February 22, 2024 5:00 PM | 20 days | No | 1/25/24 | 2/22/24 | NA | 1
987 | M26: RC: Finalize Epics | February 23, 2024 8:00 AM | February 29, 2024 5:00 PM | 947 | 949FS-20d | As Soon As Possible | NA | 5 | 0d | February 23, 2024 8:00 AM | February 29, 2024 5:00 PM | 5 days | No | 2/23/24 | 2/29/24 | NA | 1
988 | M26: RC: Complete conceptual and epic-level Domain Model diagrams | January 18, 2024 8:00 AM | February 29, 2024 5:00 PM | 946SS+15d,948FS-20d | 950 | As Soon As Possible | NA | 30 | 0d | January 18, 2024 8:00 AM | February 29, 2024 5:00 PM | 30 days | No | 1/18/24 | 2/29/24 | NA | 1
989 | M26: RC: Define User Story titles | March 1, 2024 8:00 AM | March 28, 2024 5:00 PM | 949 | 951,952 | As Soon As Possible | NA | 20 | 0d | March 1, 2024 8:00 AM | March 28, 2024 5:00 PM | 20 days | No | 3/1/24 | 3/28/24 | NA | 1
990 | M26: RC: Complete External Systems pre-analysis | March 29, 2024 8:00 AM | April 19, 2024 5:00 PM | 950 | 952SS | As Soon As Possible | NA | 15 | 0d | March 29, 2024 8:00 AM | April 19, 2024 5:00 PM | 15 days | No | 3/29/24 | 4/19/24 | NA | 1
991 | M26: RC: Facilitate Inception | March 29, 2024 8:00 AM | April 26, 2024 5:00 PM | 950,951SS | 973SS-4d,2599SS | As Soon As Possible | NA | 20 | 0d | March 29, 2024 8:00 AM | April 26, 2024 5:00 PM | 20 days | No | 3/29/24 | 4/26/24 | NA | 1
992 | Milestone 27: Complaints (CARESV1-505) | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM |  |  | As Soon As Possible | NA | 80 | 0d | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 days | No | 6/19/23 | 10/10/23 | NA | 1
993 | M27: RC: Finalize Value Hypothesis | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM |  | 955SS,2605SS+100d | Must Start On | 6/19/23 | 80 | 0d | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 days | No | 6/19/23 | 10/10/23 | NA | 1
994 | M27: RC: Draft Service Maps | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 954SS | 956SS | As Soon As Possible | NA | 80 | 0d | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 days | No | 6/19/23 | 10/10/23 | NA | 1
995 | M27: RC: Complete Legacy Analysis | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 955SS | 957SS | As Soon As Possible | NA | 80 | 0d | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 days | No | 6/19/23 | 10/10/23 | NA | 1
996 | M27: RC: Finalize Epics | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 956SS | 958SS | As Soon As Possible | NA | 80 | 0d | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 days | No | 6/19/23 | 10/10/23 | NA | 1
997 | M27: RC: Complete conceptual and epic-level Domain Model diagrams | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 957SS | 959SS | As Soon As Possible | NA | 80 | 0d | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 days | No | 6/19/23 | 10/10/23 | NA | 1
998 | M27: RC: Define User Story titles | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 958SS | 960SS | As Soon As Possible | NA | 80 | 0d | June 19, 2023 8:00 AM | October 10, 2023 5:00 PM | 80 days | No | 6/19/23 | 10/10/23 | NA | 1
999 | M27: RC: Complete External Systems pre-analysis | June 19, 2023 8:00 AM | October 6, 2023 5:00 PM | 959SS | 961SS | As Soon As Possible | NA | 78 | 0d | June 19, 2023 8:00 AM | October 6, 2023 5:00 PM | 78 days | No | 6/19/23 | 10/6/23 | NA | 1
1000 | M27: RC: Facilitate Inception | June 19, 2023 8:00 AM | October 6, 2023 5:00 PM | 960SS | 981SS-65d | As Soon As Possible | NA | 78 | 0d | June 19, 2023 8:00 AM | October 6, 2023 5:00 PM | 78 days | No | 6/19/23 | 10/6/23 | NA | 1
1001 | Milestone 28: Legal Action (CARESV1-504) | February 26, 2024 8:00 AM | June 21, 2024 5:00 PM |  |  | As Soon As Possible | NA | 83 | 0d | February 26, 2024 8:00 AM | June 21, 2024 5:00 PM | 83 days | No | 2/26/24 | 6/21/24 | NA | 1
1002 | M28: RC: Finalize Value Hypothesis | February 26, 2024 8:00 AM | April 22, 2024 5:00 PM |  | 964SS+10d | Start No Earlier Than | 2/26/24 | 40 | 0d | February 26, 2024 8:00 AM | April 22, 2024 5:00 PM | 40 days | No | 2/26/24 | 4/22/24 | NA | 1
1003 | M28: RC: Draft Service Maps | March 11, 2024 8:00 AM | April 8, 2024 5:00 PM | 963SS+10d | 965SS+10d | As Soon As Possible | NA | 20 | 0d | March 11, 2024 8:00 AM | April 8, 2024 5:00 PM | 20 days | No | 3/11/24 | 4/8/24 | NA | 1
1004 | M28: RC: Complete Legacy Analysis | March 25, 2024 8:00 AM | April 22, 2024 5:00 PM | 964SS+10d | 966 | As Soon As Possible | NA | 20 | 0d | March 25, 2024 8:00 AM | April 22, 2024 5:00 PM | 20 days | No | 3/25/24 | 4/22/24 | NA | 1
1005 | M28: RC: Finalize Epics | April 23, 2024 8:00 AM | April 29, 2024 5:00 PM | 965 | 967 | As Soon As Possible | NA | 5 | 0d | April 23, 2024 8:00 AM | April 29, 2024 5:00 PM | 5 days | No | 4/23/24 | 4/29/24 | NA | 1
1006 | M28: RC: Complete conceptual and epic-level Domain Model diagrams | April 30, 2024 8:00 AM | May 28, 2024 5:00 PM | 966 | 968SS+10d | As Soon As Possible | NA | 20 | 0d | April 30, 2024 8:00 AM | May 28, 2024 5:00 PM | 20 days | No | 4/30/24 | 5/28/24 | NA | 1
1007 | M28: RC: Define User Story titles | May 14, 2024 8:00 AM | June 4, 2024 5:00 PM | 967SS+10d | 969SS+5d | As Soon As Possible | NA | 15 | 0d | May 14, 2024 8:00 AM | June 4, 2024 5:00 PM | 15 days | No | 5/14/24 | 6/4/24 | NA | 1
1008 | M28: RC: Complete External Systems pre-analysis | May 21, 2024 8:00 AM | June 11, 2024 5:00 PM | 968SS+5d | 970SS+5d | As Soon As Possible | NA | 15 | 0d | May 21, 2024 8:00 AM | June 11, 2024 5:00 PM | 15 days | No | 5/21/24 | 6/11/24 | NA | 1
1010 | M28: RC: Facilitate Inception | May 29, 2024 8:00 AM | June 21, 2024 5:00 PM | 969SS+5d | 2611SS+134d,986 | As Soon As Possible | NA | 18 | 0d | May 29, 2024 8:00 AM | June 21, 2024 5:00 PM | 18 days | No | 5/29/24 | 6/21/24 | NA | 1
1011 | Resource Family Approval: BRC | October 4, 2023 8:00 AM | October 10, 2024 5:00 PM |  | 929FF+11d | As Soon As Possible | NA | 257 | 0d | October 4, 2023 8:00 AM | October 10, 2024 5:00 PM | 396 days | No | 10/4/23 | 10/10/24 | NA | 1
1031 | Milestone 26: Maintain Resource Family Approval Home (CARESV1-508) | March 25, 2024 8:00 AM | July 8, 2024 5:00 PM |  |  | As Soon As Possible | NA | 73 | 0d | March 25, 2024 8:00 AM | July 8, 2024 5:00 PM | 73 days | No | 3/25/24 | 7/8/24 | NA | 1
2601 | M26: B1: GREENFIELD GAP: On-line submission for Resource Family Approval Application (CARESV1-56) | March 25, 2024 8:00 AM | July 8, 2024 5:00 PM | 952SS-4d | 974SS | As Soon As Possible | NA | 73 | 0d | March 25, 2024 8:00 AM | July 8, 2024 5:00 PM | 73 days | No | 3/25/24 | 7/8/24 | NA | 1
2602 | M26: B2: 16.04 Document Resource Family Approval Home Interactions (CARESV1-18) | March 25, 2024 8:00 AM | July 8, 2024 5:00 PM | 973SS | 975SS | As Soon As Possible | NA | 73 | 0d | March 25, 2024 8:00 AM | July 8, 2024 5:00 PM | 73 days | No | 3/25/24 | 7/8/24 | NA | 1
2603 | M26: B3: 16.06 Update Resource Family Approval Home Information (CARESV1-102) | March 25, 2024 8:00 AM | July 8, 2024 5:00 PM | 974SS | 976SS | As Soon As Possible | NA | 73 | 0d | March 25, 2024 8:00 AM | July 8, 2024 5:00 PM | 73 days | No | 3/25/24 | 7/8/24 | NA | 1
2604 | M26: B4: 11.06 Conduct Supervisor Review and Approval (CARESV1-137) | March 25, 2024 8:00 AM | July 8, 2024 5:00 PM | 975SS | 977SS | As Soon As Possible | NA | 73 | 0d | March 25, 2024 8:00 AM | July 8, 2024 5:00 PM | 73 days | No | 3/25/24 | 7/8/24 | NA | 1
2605 | M26: B5: 16.01 Manage Corrective Action Plan (CARESV1-3999) | March 25, 2024 8:00 AM | July 8, 2024 5:00 PM | 976SS | 978SS | As Soon As Possible | NA | 73 | 0d | March 25, 2024 8:00 AM | July 8, 2024 5:00 PM | 73 days | No | 3/25/24 | 7/8/24 | NA | 1
1032 | M26: B6: Licensing Information System (LIS) Interface (CARESV1-13681) | March 25, 2024 8:00 AM | July 8, 2024 5:00 PM | 977SS | 979SS | As Soon As Possible | NA | 73 | 0d | March 25, 2024 8:00 AM | July 8, 2024 5:00 PM | 73 days | No | 3/25/24 | 7/8/24 | NA | 1
1033 | M26: B7: Facility Automation System (FAS) Interface (CARESV1-13683) | March 25, 2024 8:00 AM | July 8, 2024 5:00 PM | 978SS | 1425SS+77d | As Soon As Possible | NA | 73 | 0d | March 25, 2024 8:00 AM | July 8, 2024 5:00 PM | 73 days | No | 3/25/24 | 7/8/24 | NA | 1
1034 | Milestone 27: Complaints (CARESV1-505) | October 4, 2023 8:00 AM | August 16, 2024 5:00 PM |  |  | As Soon As Possible | NA | 218 | 0d | October 4, 2023 8:00 AM | August 16, 2024 5:00 PM | 361 days | No | 10/4/23 | 8/16/24 | NA | 1
1035 | M27: B1: 14.01 RFA Screen Complaint (CARESV1-111) | October 4, 2023 8:00 AM | August 16, 2024 5:00 PM | 961SS-65d | 982SS | Start No Earlier Than | 10/4/23 | 218 | 0d | October 4, 2023 8:00 AM | August 16, 2024 5:00 PM | 361 days | No | 10/4/23 | 8/16/24 | NA | 1
2606 | M27: B2: 14.03 RFA Send a Cross Report of a complaint (CARESV1-132) | October 4, 2023 8:00 AM | August 16, 2024 5:00 PM | 981SS | 983SS | Start No Earlier Than | 10/4/23 | 218 | 0d | October 4, 2023 8:00 AM | August 16, 2024 5:00 PM | 361 days | No | 10/4/23 | 8/16/24 | NA | 1
1036 | M27: B3: 14.02 RFA Investigate Complaint (CARESV1-134) | October 4, 2023 8:00 AM | August 16, 2024 5:00 PM | 982SS | 984SS | Start No Earlier Than | 10/4/23 | 218 | 0d | October 4, 2023 8:00 AM | August 16, 2024 5:00 PM | 361 days | No | 10/4/23 | 8/16/24 | NA | 1
1012 | M27: B4: RSO Address Match Investigations (CARESV1-26915) | October 4, 2023 8:00 AM | August 16, 2024 5:00 PM | 983SS | 1000FS+22d | Start No Earlier Than | 10/4/23 | 218 | 0d | October 4, 2023 8:00 AM | August 16, 2024 5:00 PM | 361 days | No | 10/4/23 | 8/16/24 | NA | 1
1013 | Milestone 28: Legal Action (CARESV1-504) | June 24, 2024 8:00 AM | October 10, 2024 5:00 PM |  |  | As Soon As Possible | NA | 78 | 0d | June 24, 2024 8:00 AM | October 10, 2024 5:00 PM | 78 days | No | 6/24/24 | 10/10/24 | NA | 1
1014 | M28: B1: RFA Legal actions (CARESV1-17) | June 24, 2024 8:00 AM | October 10, 2024 5:00 PM | 970 | 987SS | As Soon As Possible | NA | 78 | 0d | June 24, 2024 8:00 AM | October 10, 2024 5:00 PM | 78 days | No | 6/24/24 | 10/10/24 | NA | 1
1015 | M28: B2: RFA GREENFIELD GAP: Refactor application submission (CARESV1-3936) | June 24, 2024 8:00 AM | October 10, 2024 5:00 PM | 986SS | 988SS | As Soon As Possible | NA | 78 | 0d | June 24, 2024 8:00 AM | October 10, 2024 5:00 PM | 78 days | No | 6/24/24 | 10/10/24 | NA | 1
1037 | M28: B3: Foundational Services (F11) - Unallocated Functionality (CARESV1-5368) | June 24, 2024 8:00 AM | October 10, 2024 5:00 PM | 987SS | 989FF,1005FS+15d | As Soon As Possible | NA | 78 | 0d | June 24, 2024 8:00 AM | October 10, 2024 5:00 PM | 78 days | No | 6/24/24 | 10/10/24 | NA | 1
2848 | Resource Family Approval BRC Milestone Completion | October 10, 2024 5:00 PM | October 10, 2024 5:00 PM | 988FF | 1074 | As Soon As Possible | NA | 0 | 0d | October 10, 2024 5:00 PM | October 10, 2024 5:00 PM | 0 days | Yes | 10/10/24 | 10/10/24 | NA | 1
2656 | Resource Family Approval: Design | September 30, 2024 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 254 | 0d | September 30, 2024 8:00 AM | May 2, 2025 5:00 PM | 147 days | No | 9/30/24 | 10/3/25 | NA | 1
2657 | Milestone 26: Maintain Resource Family Approval Home (CARESV1-508) | September 30, 2024 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 254 | 0d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 9/30/24 | 10/3/25 | NA | 1
2658 | M26: B1: GREENFIELD GAP: On-line submission for Resource Family Approval Application (CARESV1-56) | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 942FF | 993SS | As Soon As Possible | NA | 123 | 0d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 9/30/24 | 3/28/25 | NA | 1
2659 | M26: B2: 16.04 Document Resource Family Approval Home Interactions (CARESV1-18) | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 992SS | 994SS | As Soon As Possible | NA | 123 | 0d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 9/30/24 | 3/28/25 | NA | 1
2660 | M26: B3: 16.06 Update Resource Family Approval Home Information (CARESV1-102) | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 993SS | 995SS | As Soon As Possible | NA | 123 | 0d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 9/30/24 | 3/28/25 | NA | 1
2661 | M26: B4: 11.06 Conduct Supervisor Review and Approval (CARESV1-137) | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 994SS | 996SS | As Soon As Possible | NA | 123 | 0d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 9/30/24 | 3/28/25 | NA | 1
2662 | M26: B5: 16.01 Manage Corrective Action Plan (CARESV1-3999) | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 995SS | 997SS+103d | As Soon As Possible | NA | 123 | 0d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 9/30/24 | 3/28/25 | NA | 1
2663 | M26: B6: Licensing Information System (LIS) Interface (CARESV1-13681) | March 3, 2025 8:00 AM | October 3, 2025 5:00 PM | 996SS+103d | 998SS | As Soon As Possible | NA | 151 | 0d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 3/3/25 | 10/3/25 | NA | 1
2664 | M26: B7: Facility Automation System (FAS) Interface (CARESV1-13683) | March 3, 2025 8:00 AM | October 3, 2025 5:00 PM | 997SS | 1011 | As Soon As Possible | NA | 151 | 0d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 3/3/25 | 10/3/25 | NA | 1
2665 | Milestone 27: Complaints (CARESV1-505) | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 123 | 0d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 9/30/24 | 3/28/25 | NA | 1
2666 | M27: B1: 14.01 RFA Screen Complaint (CARESV1-111) | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 942FF,984FS+22d | 1001SS | As Soon As Possible | NA | 123 | 0d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 9/30/24 | 3/28/25 | NA | 1
2667 | M27: B2: 14.03 RFA Send a Cross Report of a complaint (CARESV1-132) | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 1000SS | 1002SS | As Soon As Possible | NA | 123 | 0d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 9/30/24 | 3/28/25 | NA | 1
2668 | M27: B3: 14.02 RFA Investigate Complaint (CARESV1-134) | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 1001SS | 1003SS | As Soon As Possible | NA | 123 | 0d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 9/30/24 | 3/28/25 | NA | 1
2669 | M27: B4: RSO Address Match Investigations (CARESV1-26915) | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 1002SS |  | As Soon As Possible | NA | 123 | 0d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 9/30/24 | 3/28/25 | NA | 1
2670 | Milestone 28: Legal Action (CARESV1-504) | November 1, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 99 | 0d | November 1, 2024 8:00 AM | May 2, 2025 5:00 PM | 123 days | No | 11/1/24 | 3/28/25 | NA | 1
2671 | M28: B1: RFA Legal actions (CARESV1-17) | November 1, 2024 8:00 AM | March 28, 2025 5:00 PM | 988FS+15d | 1006SS | As Soon As Possible | NA | 99 | 0d | November 1, 2024 8:00 AM | May 2, 2025 5:00 PM | 123 days | No | 11/1/24 | 3/28/25 | NA | 1
2672 | M28: B2: RFA GREENFIELD GAP: Refactor application submission (CARESV1-3936) | November 1, 2024 8:00 AM | March 28, 2025 5:00 PM | 1005SS | 1007SS | As Soon As Possible | NA | 99 | 0d | November 1, 2024 8:00 AM | May 2, 2025 5:00 PM | 123 days | No | 11/1/24 | 3/28/25 | NA | 1
2673 | M28: B3: Foundational Services (F11) - Unallocated Functionality (CARESV1-5368) | November 1, 2024 8:00 AM | March 28, 2025 5:00 PM | 1006SS | 1008FF | As Soon As Possible | NA | 99 | 0d | November 1, 2024 8:00 AM | May 2, 2025 5:00 PM | 123 days | No | 11/1/24 | 3/28/25 | NA | 1
2849 | Resource Family Approval Design Milestone Completion | March 28, 2025 5:00 PM | March 28, 2025 5:00 PM | 1007FF | 4639,4650,4680,4695 | As Soon As Possible | NA | 0 | 0d | May 2, 2025 5:00 PM | May 2, 2025 5:00 PM | 0 days | Yes | 3/28/25 | 3/28/25 | NA | 1
2674 | Resource Family Approval: Build | October 6, 2025 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 57 | -32d | April 1, 2025 8:00 AM | December 30, 2025 5:00 PM | 190 days | No | NA | NA | NA | 0
2675 | Milestone 26: Maintain Resource Family Approval Home (CARESV1-508) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 38 | -32d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2676 | M26: B1: GREENFIELD GAP: On-line submission for Resource Family Approval Application (CARESV1-56) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 998 | 1012SS,2316SS,1370SS,1019SS,1024SS+38d,1029SS,4639FS-19d | As Soon As Possible | NA | 38 | -32d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2677 | M26: B2: 16.04 Document Resource Family Approval Home Interactions (CARESV1-18) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1011SS | 1013SS | As Soon As Possible | NA | 38 | 467d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2678 | M26: B3: 16.06 Update Resource Family Approval Home Information (CARESV1-102) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1012SS | 1014SS | As Soon As Possible | NA | 38 | 467d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2679 | M26: B4: 11.06 Conduct Supervisor Review and Approval (CARESV1-137) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1013SS | 1015SS | As Soon As Possible | NA | 38 | 467d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2680 | M26: B5: 16.01 Manage Corrective Action Plan (CARESV1-3999) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1014SS | 1016SS | As Soon As Possible | NA | 38 | 467d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2681 | M26: B6: Licensing Information System (LIS) Interface (CARESV1-13681) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1015SS | 1017SS | As Soon As Possible | NA | 38 | 467d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2682 | M26: B7: Facility Automation System (FAS) Interface (CARESV1-13683) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1016SS |  | As Soon As Possible | NA | 38 | 467d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2683 | Milestone 27: Complaints (CARESV1-505) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 38 | -13d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2684 | M27: B1: 14.01 RFA Screen Complaint (CARESV1-111) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1011SS | 1020SS,2320SS,2324SS,4650SS+19d | As Soon As Possible | NA | 38 | -13d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2685 | M27: B2: 14.03 RFA Send a Cross Report of a complaint (CARESV1-132) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1019SS | 1021SS,4650SS | As Soon As Possible | NA | 38 | 6d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2686 | M27: B3: 14.02 RFA Investigate Complaint (CARESV1-134) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1020SS | 1022SS | As Soon As Possible | NA | 38 | 467d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2687 | M27: B4: RSO Address Match Investigations (CARESV1-26915) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1021SS |  | As Soon As Possible | NA | 38 | 467d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2688 | Milestone 28: Legal Action (CARESV1-504) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | -32d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2689 | M28: B1: RFA Legal actions (CARESV1-17) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1011SS+38d | 1025SS,4661FS-19d | As Soon As Possible | NA | 19 | -32d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2690 | M28: B2: RFA GREENFIELD GAP: Refactor application submission (CARESV1-3936) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1024SS | 1026SS,4661FS-19d | As Soon As Possible | NA | 19 | -32d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2691 | M28: B3: Foundational Services (F11) - Unallocated Functionality (CARESV1-5368) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1025SS | 4661FS-19d | As Soon As Possible | NA | 19 | -32d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
2701 | Resource Family: SIT | October 6, 2025 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 57 | -13d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2702 | Milestone 26: Maintain Resource Family Home (CARESV1-508) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 38 | -13d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2703 | M26: B1: GREENFIELD GAP: On-line submission for Resource Family Application (CARESV1-56) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1011SS | 1030SS,1037SS,1042SS+38d,4639FS-19d | Start No Earlier Than | 3/3/25 | 38 | -13d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2704 | M26: B2: 16.04 Document Resource Family Home Interactions (CARESV1-18) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1029SS | 1031SS | Start No Earlier Than | 3/3/25 | 38 | 3.42d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2705 | M26: B3: 16.06 Update Resource Family Home Information (CARESV1-102) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1030SS | 1032SS | Start No Earlier Than | 3/3/25 | 38 | 3.42d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2706 | M26: B4: 11.06 Conduct Supervisor Review and Approval (CARESV1-137) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1031SS | 1033SS | Start No Earlier Than | 3/3/25 | 38 | 3.42d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2707 | M26: B5: 16.01 Manage Corrective Action Plan (CARESV1-3999) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1032SS | 1034SS | Start No Earlier Than | 3/3/25 | 38 | 3.42d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2708 | M26: B6: Licensing Information System (LIS) Interface (CARESV1-13681) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1033SS | 1035SS | Start No Earlier Than | 3/3/25 | 38 | 3.42d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2709 | M26: B7: Facility Automation System (FAS) Interface (CARESV1-13683) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1034SS | 1047,4643FF | Start No Earlier Than | 3/3/25 | 38 | 3.42d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2710 | Milestone 27: Complaints (CARESV1-505) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 38 | 59d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2711 | M27: B1: 14.01 RFA Screen Complaint (CARESV1-111) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1029SS | 1038SS | Start No Earlier Than | 2/24/25 | 38 | 59d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2712 | M27: B2: 14.03 RFA Send a Cross Report of a complaint (CARESV1-132) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1037SS | 1039SS | As Soon As Possible | NA | 38 | 59d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2713 | M27: B3: 14.02 RFA Investigate Complaint (CARESV1-134) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1038SS | 1040SS | As Soon As Possible | NA | 38 | 59d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2714 | M27: B4: RSO Address Match Investigations (CARESV1-26915) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1039SS | 4654FF | As Soon As Possible | NA | 38 | 59d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2715 | Milestone 28: Legal Action (CARESV1-504) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 40d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2716 | M28: B1: RFA Legal actions (CARESV1-17) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1029SS+38d | 1043SS,1060 | Start No Earlier Than | 3/3/25 | 19 | 40d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2717 | M28: B2: RFA GREENFIELD GAP: Refactor application submission (CARESV1-3936) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1042SS | 1044SS | Start No Earlier Than | 3/3/25 | 19 | 40d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2718 | M28: B3: Foundational Services (F11) - Unallocated Functionality (CARESV1-5368) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1043SS | 4665FF | Start No Earlier Than | 3/3/25 | 19 | 40d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
2719 | Resource Family Approval: State QA | December 1, 2025 8:00 AM | January 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 37 | 430d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 12/1/25 | NA | NA | 0.17999999999999999
2720 | Milestone 26: Maintain Resource Family Approval Home (CARESV1-508) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 448d | May 30, 2025 8:00 AM | December 26, 2025 5:00 PM | 146 days | No | 12/1/25 | NA | NA | 5.0000000000000003E-2
2721 | M26: B1: GREENFIELD GAP: On-line submission for Resource Family Approval Application (CARESV1-56) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1035 | 1048SS,1333SS,1345SS,1055SS | As Soon As Possible | NA | 19 | 3.42d | May 30, 2025 8:00 AM | December 26, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2722 | M26: B2: 16.04 Document Resource Family Approval Home Interactions (CARESV1-18) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1047SS | 1049SS | As Soon As Possible | NA | 19 | 6.27d | May 30, 2025 8:00 AM | December 26, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2723 | M26: B3: 16.06 Update Resource Family Approval Home Information (CARESV1-102) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1048SS | 1050SS,2430SS-100d | As Soon As Possible | NA | 19 | 6.27d | May 30, 2025 8:00 AM | December 26, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2724 | M26: B4: 11.06 Conduct Supervisor Review and Approval (CARESV1-137) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1049SS | 1051SS | As Soon As Possible | NA | 19 | 6.27d | May 30, 2025 8:00 AM | December 26, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2725 | M26: B5: 16.01 Manage Corrective Action Plan (CARESV1-3999) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1050SS | 1052SS | As Soon As Possible | NA | 19 | 6.27d | May 30, 2025 8:00 AM | December 26, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2726 | M26: B6: Licensing Information System (LIS) Interface (CARESV1-13681) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1051SS | 1053SS | As Soon As Possible | NA | 19 | 448d | May 30, 2025 8:00 AM | December 26, 2025 5:00 PM | 146 days | No | 12/1/25 | NA | NA | 0.33000000000000002
2727 | M26: B7: Facility Automation System (FAS) Interface (CARESV1-13683) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1052SS | 1065SS,5491FS+2d | As Soon As Possible | NA | 19 | 187d | May 30, 2025 8:00 AM | December 26, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2692 | Milestone 27: Complaints (CARESV1-505) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 448d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | 12/1/25 | NA | NA | 0.56000000000000005
2693 | M27: B1: 14.01 RFA Screen Complaint (CARESV1-111) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1047SS | 1056SS | As Soon As Possible | NA | 19 | 448d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | 12/1/25 | NA | NA | 0.88
2694 | M27: B2: 14.03 RFA Send a Cross Report of a complaint (CARESV1-132) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1055SS | 1057SS | As Soon As Possible | NA | 19 | 448d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | 12/1/25 | NA | NA | 0.89000000000000001
2695 | M27: B3: 14.02 RFA Investigate Complaint (CARESV1-134) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1056SS | 1058SS | As Soon As Possible | NA | 19 | 448d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | 12/1/25 | NA | NA | 0.45000000000000001
2696 | M27: B4: RSO Address Match Investigations (CARESV1-26915) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1057SS | 1074SS,5497 | As Soon As Possible | NA | 19 | 189d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2697 | Milestone 28: Legal Action (CARESV1-504) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 18 | 171d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2698 | M28: B1: RFA Legal actions (CARESV1-17) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 1042 | 1061SS,1062SS | As Soon As Possible | NA | 18 | 171d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2699 | M28: B2: RFA GREENFIELD GAP: Refactor application submission (CARESV1-3936) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 1060SS | 1062SS | As Soon As Possible | NA | 18 | 171d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2700 | M28: B3: Foundational Services (F11) - Unallocated Functionality (CARESV1-5368) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 1060SS,1061SS | 1080SS,5503 | As Soon As Possible | NA | 18 | 171d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2767 | Resource Family Approval: Joint Review | December 1, 2025 8:00 AM | January 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 37 | 430d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
2768 | Milestone 26: Maintain Resource Family Approval Home (CARESV1-508) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 448d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
2770 | M26: B1: GREENFIELD GAP: On-line submission for Resource Family Approval Application (CARESV1-56) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1053SS | 1066SS | As Soon As Possible | NA | 19 | 448d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
2771 | M26: B2: 16.04 Document Resource Family Approval Home Interactions (CARESV1-18) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1065SS | 1067SS | As Soon As Possible | NA | 19 | 448d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
2772 | M26: B3: 16.06 Update Resource Family Approval Home Information (CARESV1-102) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1066SS | 1068SS | As Soon As Possible | NA | 19 | 448d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
2773 | M26: B4: 11.06 Conduct Supervisor Review and Approval (CARESV1-137) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1067SS | 1069SS | As Soon As Possible | NA | 19 | 448d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
2774 | M26: B5: 16.01 Manage Corrective Action Plan (CARESV1-3999) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1068SS | 1070SS | As Soon As Possible | NA | 19 | 448d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
2822 | M26: B6: Licensing Information System (LIS) Interface (CARESV1-13681) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1069SS | 1071SS | As Soon As Possible | NA | 19 | 448d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
2775 | M26: B7: Facility Automation System (FAS) Interface (CARESV1-13683) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1070SS | 1072FF | As Soon As Possible | NA | 19 | 448d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
10455 | Milestone 26: Maintain Resource Family Approval Home (CARESV1-508) Complete | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 1071FF |  | As Soon As Possible | NA | 0 | 448d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
2783 | Milestone 27: Complaints (CARESV1-505) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 448d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2785 | M27: B1: 14.01 RFA Screen Complaint (CARESV1-111) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1058SS,989 | 1075SS | As Soon As Possible | NA | 19 | 448d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2786 | M27: B2: 14.03 RFA Send a Cross Report of a complaint (CARESV1-132) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1074SS | 1076SS | As Soon As Possible | NA | 19 | 448d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2787 | M27: B3: 14.02 RFA Investigate Complaint (CARESV1-134) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1075SS | 1077SS | As Soon As Possible | NA | 19 | 448d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2788 | M27: B4: RSO Address Match Investigations (CARESV1-26915) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1076SS | 1078FF | As Soon As Possible | NA | 19 | 448d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
10456 | Milestone 27: Complaints (CARESV1-505) Complete | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 1077FF |  | As Soon As Possible | NA | 0 | 448d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
2798 | Milestone 28: Legal Action (CARESV1-504) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 18 | 430d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2800 | M28: B1: RFA Legal actions (CARESV1-17) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 1062SS | 1081SS | As Soon As Possible | NA | 18 | 430d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2801 | M28: B2: RFA GREENFIELD GAP: Refactor application submission (CARESV1-3936) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 1080SS | 1082SS | As Soon As Possible | NA | 18 | 430d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
2802 | M28: B3: Foundational Services (F11) - Unallocated Functionality (CARESV1-5368) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 1081SS | 1083FF | As Soon As Possible | NA | 18 | 430d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | NA | NA | NA | 0
10457 | Milestone 28: Legal Action (CARESV1-504) Complete | January 23, 2026 5:00 PM | January 23, 2026 5:00 PM | 1082FF |  | As Soon As Possible | NA | 0 | 430d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
1176 | Financial Management | January 2, 2024 8:00 AM | February 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 537 | 411d | January 2, 2024 8:00 AM | December 30, 2025 5:00 PM | 502 days | No | 1/2/24 | NA | NA | 0.80000000000000004
1190 | Financial Management: Holistic Design Milestones | January 2, 2024 8:00 AM | February 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 537 | 411d | January 2, 2024 8:00 AM | December 30, 2025 5:00 PM | 502 days | No | 1/2/24 | NA | NA | 0.80000000000000004
4899 | Group 1 Financial Management (Milestones 23/23.1, 24) | January 2, 2024 8:00 AM | February 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 537 | 411d | January 2, 2024 8:00 AM | December 30, 2025 5:00 PM | 502 days | No | 1/2/24 | NA | NA | 0.80000000000000004
4209 | Financial Management - Scenario Requirements Validation | October 21, 2024 8:00 AM | November 8, 2024 5:00 PM | 1130FF+15d | 1090FS-5d | Finish No Earlier Than | 11/8/24 | 15 | 0d | August 12, 2024 8:00 AM | November 8, 2024 5:00 PM | 65 days | No | 10/21/24 | 11/8/24 | NA | 1
4196 | Financial Management: Holistic Design Artifacts | November 4, 2024 8:00 AM | July 11, 2025 5:00 PM |  |  | As Soon As Possible | NA | 170 | 0d | December 4, 2024 8:00 AM | July 11, 2025 5:00 PM | 151 days | No | 11/4/24 | 7/11/25 | NA | 1
4201 | Financial Management - Design Cycle 1 | November 4, 2024 8:00 AM | April 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 99 | 0d | December 4, 2024 8:00 AM | April 1, 2025 5:00 PM | 80 days | No | 11/4/24 | 4/1/25 | NA | 1
11602 | Financial Management - Design Cycle 1 - Draft & Review Application Flow | November 4, 2024 8:00 AM | December 4, 2024 5:00 PM | 1087FS-5d | 1091SS+2d | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 11/4/24 | 12/4/24 | NA | 1
11603 | Financial Management - Design Cycle 1 - Implementation Artifacts Review | November 6, 2024 8:00 AM | November 20, 2024 5:00 PM | 1090SS+2d | 1092FS+10d | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 11/6/24 | 11/20/24 | NA | 1
4202 | Financial Management - Design Cycle 1 - Prepare Blueprint | December 4, 2024 8:00 AM | March 19, 2025 9:17 AM | 1091FS+10d | 1093SS+10d,2310SS,2312SS,1355SS,1365SS,1133SS,1138SS | Must Start On | 12/4/24 | 71 | 0d | December 4, 2024 8:00 AM | March 18, 2025 5:00 PM | 71 days | No | 12/4/24 | 3/19/25 | NA | 1
4203 | Financial Management - Design Cycle 1 - Review Blueprint | December 18, 2024 8:00 AM | March 25, 2025 5:00 PM | 1092SS+10d | 1094SS+5d | As Soon As Possible | NA | 66 | 0d | December 18, 2024 8:00 AM | March 25, 2025 5:00 PM | 66 days | No | 12/18/24 | 3/25/25 | NA | 1
4204 | Financial Management - Design Cycle 1 - Revise and Finalize Blueprint | December 26, 2024 8:00 AM | April 1, 2025 5:00 PM | 1093SS+5d | 1098FS+28d,1096FS-2d | As Soon As Possible | NA | 65 | 0d | December 26, 2024 8:00 AM | April 1, 2025 5:00 PM | 65 days | No | 12/26/24 | 4/1/25 | NA | 1
4205 | Design Cycle 2 | April 2, 2025 8:00 AM | July 11, 2025 5:00 PM |  |  | As Soon As Possible | NA | 71 | 0d | April 2, 2025 8:00 AM | July 11, 2025 5:00 PM | 71 days | No | 4/2/25 | 7/11/25 | NA | 1
11487 | Financial Management - Design Cycle 2 - Perform Pre-Build activities | April 2, 2025 8:00 AM | June 20, 2025 5:00 PM | 1094FS-2d | 1099SS+5d,2594SS,1097SS+10d | Start No Earlier Than | 4/2/25 | 57 | 0d | April 2, 2025 8:00 AM | June 20, 2025 5:00 PM | 57 days | No | 4/2/25 | 6/20/25 | NA | 1
11488 | Financial Management - Design Cycle 2 - Perform Pre-Build QA (with VPOD) and Address Findings | April 16, 2025 8:00 AM | June 20, 2025 5:00 PM | 1096SS+10d | 1099SS+5d,2594SS | Start No Earlier Than | 4/4/25 | 47 | 0d | April 16, 2025 8:00 AM | June 20, 2025 5:00 PM | 47 days | No | 4/16/25 | 6/20/25 | NA | 1
4206 | Financial Management - Design Cycle 2 - Prepare for Walkthrough with Core Constituents | May 12, 2025 8:00 AM | June 20, 2025 5:00 PM | 1094FS+28d | 1099SS+5d,2594SS | Start No Earlier Than | 4/4/25 | 29 | 0d | May 12, 2025 8:00 AM | June 20, 2025 5:00 PM | 29 days | No | 5/12/25 | 6/20/25 | NA | 1
4207 | Financial Management - Design Cycle 2 - Conduct Design Walkthrough with Core Constituents | May 19, 2025 8:00 AM | June 27, 2025 5:00 PM | 1098SS+5d,1096SS+5d,1097SS+5d | 1100SS+5d | As Soon As Possible | NA | 29 | 0d | May 19, 2025 8:00 AM | June 27, 2025 5:00 PM | 29 days | No | 5/19/25 | 6/27/25 | NA | 1
4208 | Financial Management - Design Cycle 2 - Final Review and Design Baseline | May 27, 2025 8:00 AM | July 11, 2025 5:00 PM | 1099SS+5d |  | As Soon As Possible | NA | 33 | 0d | May 27, 2025 8:00 AM | July 11, 2025 5:00 PM | 33 days | No | 5/27/25 | 7/11/25 | NA | 1
1191 | Financial Management: Context Setting | January 2, 2024 8:00 AM | July 12, 2024 5:00 PM |  |  | As Soon As Possible | NA | 134 | 0d | January 2, 2024 8:00 AM | July 12, 2024 5:00 PM | 134 days | No | 1/2/24 | 7/12/24 | NA | 1
1192 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) | March 25, 2024 8:00 AM | July 12, 2024 5:00 PM |  |  | As Soon As Possible | NA | 77 | 0d | March 25, 2024 8:00 AM | July 12, 2024 5:00 PM | 77 days | No | 3/25/24 | 7/12/24 | NA | 1
1193 | M23: RC: Finalize Value Hypothesis | March 25, 2024 8:00 AM | May 20, 2024 5:00 PM |  | 1104SS+5d | Must Start On | 3/25/24 | 40 | 0d | March 25, 2024 8:00 AM | May 20, 2024 5:00 PM | 40 days | No | 3/25/24 | 5/20/24 | NA | 1
1194 | M23: RC: Draft Service Maps | April 2, 2024 8:00 AM | April 29, 2024 5:00 PM | 1103SS+5d | 1105,1107SS+5d | As Soon As Possible | NA | 20 | 0d | April 2, 2024 8:00 AM | April 29, 2024 5:00 PM | 20 days | No | 4/2/24 | 4/29/24 | NA | 1
1195 | M23: RC: Complete Legacy Analysis | April 30, 2024 8:00 AM | May 28, 2024 5:00 PM | 1104 | 1106 | As Soon As Possible | NA | 20 | 0d | April 30, 2024 8:00 AM | May 28, 2024 5:00 PM | 20 days | No | 4/30/24 | 5/28/24 | NA | 1
1196 | M23: RC: Finalize Epics | May 29, 2024 8:00 AM | June 4, 2024 5:00 PM | 1105 | 1107 | As Soon As Possible | NA | 5 | 0d | May 29, 2024 8:00 AM | June 4, 2024 5:00 PM | 5 days | No | 5/29/24 | 6/4/24 | NA | 1
1197 | M23: RC: Complete conceptual and epic-level Domain Model diagrams | April 9, 2024 8:00 AM | May 20, 2024 5:00 PM | 1104SS+5d,1106 | 1108 | As Soon As Possible | NA | 30 | 0d | April 9, 2024 8:00 AM | May 20, 2024 5:00 PM | 30 days | No | 4/9/24 | 5/20/24 | NA | 1
1198 | M23: RC: Define User Story titles | May 21, 2024 8:00 AM | June 18, 2024 5:00 PM | 1107 | 1109 | As Soon As Possible | NA | 20 | 0d | May 21, 2024 8:00 AM | June 18, 2024 5:00 PM | 20 days | No | 5/21/24 | 6/18/24 | NA | 1
1199 | M23: RC: Complete External Systems pre-analysis | June 19, 2024 8:00 AM | July 12, 2024 5:00 PM | 1108 | 1110SS | As Soon As Possible | NA | 17 | 0d | June 19, 2024 8:00 AM | July 12, 2024 5:00 PM | 17 days | No | 6/19/24 | 7/12/24 | NA | 1
1200 | M23: RC: Facilitate Inception | June 19, 2024 8:00 AM | July 12, 2024 5:00 PM | 1109SS | 1122FS+20d | As Soon As Possible | NA | 17 | 0d | June 19, 2024 8:00 AM | July 12, 2024 5:00 PM | 17 days | No | 6/19/24 | 7/12/24 | NA | 1
1201 | Milestone 24: Track Assistance Costs (CARESV1-506) | January 2, 2024 8:00 AM | May 17, 2024 5:00 PM |  |  | As Soon As Possible | NA | 96 | 0d | January 2, 2024 8:00 AM | May 17, 2024 5:00 PM | 96 days | No | 1/2/24 | 5/17/24 | NA | 1
1202 | M24: RC: Finalize Value Hypothesis | January 2, 2024 8:00 AM | February 28, 2024 5:00 PM |  | 1113SS+15d | Must Start On | 1/2/24 | 40 | 0d | January 2, 2024 8:00 AM | February 28, 2024 5:00 PM | 40 days | No | 1/2/24 | 2/28/24 | NA | 1
1203 | M24: RC: Draft Service Maps | January 24, 2024 8:00 AM | February 21, 2024 5:00 PM | 1112SS+15d | 1114 | As Soon As Possible | NA | 20 | 0d | January 24, 2024 8:00 AM | February 21, 2024 5:00 PM | 20 days | No | 1/24/24 | 2/21/24 | NA | 1
1204 | M24: RC: Complete Legacy Analysis | February 22, 2024 8:00 AM | March 20, 2024 5:00 PM | 1113 | 1115 | As Soon As Possible | NA | 20 | 0d | February 22, 2024 8:00 AM | March 20, 2024 5:00 PM | 20 days | No | 2/22/24 | 3/20/24 | NA | 1
1205 | M24: RC: Finalize Epics | March 21, 2024 8:00 AM | March 27, 2024 5:00 PM | 1114 | 1116SS-25d | As Soon As Possible | NA | 5 | 0d | March 21, 2024 8:00 AM | March 27, 2024 5:00 PM | 5 days | No | 3/21/24 | 3/27/24 | NA | 1
1206 | M24: RC: Complete conceptual and epic-level Domain Model diagrams | February 14, 2024 8:00 AM | March 27, 2024 5:00 PM | 1115SS-25d | 1117 | As Soon As Possible | NA | 30 | 0d | February 14, 2024 8:00 AM | March 27, 2024 5:00 PM | 30 days | No | 2/14/24 | 3/27/24 | NA | 1
1207 | M24: RC: Define User Story titles | March 28, 2024 8:00 AM | April 25, 2024 5:00 PM | 1116 | 1118 | As Soon As Possible | NA | 20 | 0d | March 28, 2024 8:00 AM | April 25, 2024 5:00 PM | 20 days | No | 3/28/24 | 4/25/24 | NA | 1
1208 | M24: RC: Complete External Systems pre-analysis | April 26, 2024 8:00 AM | May 17, 2024 5:00 PM | 1117 | 1119SS | As Soon As Possible | NA | 16 | 0d | April 26, 2024 8:00 AM | May 17, 2024 5:00 PM | 16 days | No | 4/26/24 | 5/17/24 | NA | 1
1209 | M24: RC: Facilitate Inception | April 26, 2024 8:00 AM | May 17, 2024 5:00 PM | 1118SS | 1127FS+58d,2593SS | As Soon As Possible | NA | 16 | 0d | April 26, 2024 8:00 AM | May 17, 2024 5:00 PM | 16 days | No | 4/26/24 | 5/17/24 | NA | 1
1210 | Financial Management: BRC | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM |  |  | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
1211 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM |  |  | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
1212 | M23: B1: 21.04 Track/Update Administrative Costs (CARESV1-32) | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 1110FS+20d | 1123SS,1124SS,1125SS | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
1213 | M23: B2: 21.03 Track Contract Costs (r2) (CARESV1-116) | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 1122SS | 1124SS | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
1224 | M23: B3: Milestone 23 - Other Milestone Refinement Stories (CARESV1-14346) | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 1122SS,1123SS | 1125SS | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
1214 | M23: B1: 21.02 Track Contract Costs (r1) (CARESV1-64) | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 1122SS,1124SS | 1130FF,1431FF | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
1219 | Milestone 24: Track Assistance Costs (CARESV1-506) | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM |  |  | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
1220 | M24: B1: 21.05 Track/Update Assistance Payment (CARESV1-26) | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 1119FS+58d | 1128SS | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
1221 | M24: B2: 18.04 Manage Resource Inventory (CARESV1-118) | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 1127SS | 1129SS | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
1222 | M24: B3: County Expense Claim Reporting Information System (CECRIS) CEC Interface (CARESV1-13931) | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 1128SS | 1130FF | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
2850 | Financial Management BRC Milestone Completion | October 18, 2024 5:00 PM | October 18, 2024 5:00 PM | 1125FF,1129FF | 1133,1087FF+15d | As Soon As Possible | NA | 0 | 0d | October 18, 2024 5:00 PM | October 18, 2024 5:00 PM | 0 days | Yes | 10/18/24 | 10/18/24 | NA | 1
1225 | Financial Management: Design | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 210 | 0d | March 10, 2025 8:00 AM | July 11, 2025 5:00 PM | 87 days | No | 12/4/24 | 10/3/25 | NA | 1
1226 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 210 | 0d | March 10, 2025 8:00 AM | July 11, 2025 5:00 PM | 87 days | No | 12/4/24 | 10/3/25 | NA | 1
1227 | M23: B1: 21.04 Track/Update Administrative Costs (CARESV1-32) | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 1130,1092SS | 1134SS,1135SS,1136SS | As Soon As Possible | NA | 210 | 0d | March 10, 2025 8:00 AM | July 11, 2025 5:00 PM | 87 days | No | 12/4/24 | 10/3/25 | NA | 1
1228 | M23: B2: 21.03 Track Contract Costs (r2) (CARESV1-116) | December 4, 2024 8:00 AM | July 11, 2025 5:00 PM | 1133SS | 1135SS | As Soon As Possible | NA | 151 | 0d | March 10, 2025 8:00 AM | July 11, 2025 5:00 PM | 87 days | No | 12/4/24 | 7/11/25 | NA | 1
1229 | M23: B3: Milestone 23 - Other Milestone Refinement Stories (CARESV1-14346) | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 1133SS,1134SS | 1136SS | As Soon As Possible | NA | 210 | 0d | March 10, 2025 8:00 AM | July 11, 2025 5:00 PM | 87 days | No | 12/4/24 | 10/3/25 | NA | 1
1230 | M23: B1: 21.02 Track Contract Costs (r1) (CARESV1-64) | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 1133SS,1135SS | 1144FS+57d,1432SS | As Soon As Possible | NA | 210 | 0d | March 10, 2025 8:00 AM | July 11, 2025 5:00 PM | 87 days | No | 12/4/24 | 10/3/25 | NA | 1
1231 | Milestone 24: Track Assistance Costs (CARESV1-506) | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 210 | 0d | March 10, 2025 8:00 AM | July 11, 2025 5:00 PM | 87 days | No | 12/4/24 | 10/3/25 | NA | 1
1232 | M24: B1: 21.05 Track/Update Assistance Payment (CARESV1-26) | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 1092SS | 1139SS,1140SS | As Soon As Possible | NA | 210 | 0d | March 10, 2025 8:00 AM | July 11, 2025 5:00 PM | 87 days | No | 12/4/24 | 10/3/25 | NA | 1
1233 | M24: B2: 18.04 Manage Resource Inventory (CARESV1-118) | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 1138SS | 1140SS | As Soon As Possible | NA | 210 | 0d | March 10, 2025 8:00 AM | July 11, 2025 5:00 PM | 87 days | No | 12/4/24 | 10/3/25 | NA | 1
1234 | M24: B3: County Expense Claim Reporting Information System (CECRIS) CEC Interface (CARESV1-13931) | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 1138SS,1139SS | 1141FF,1149 | As Soon As Possible | NA | 210 | 0d | March 10, 2025 8:00 AM | July 11, 2025 5:00 PM | 87 days | No | 12/4/24 | 10/3/25 | NA | 1
2851 | Financial Management Design Milestone Completion | October 3, 2025 5:00 PM | October 3, 2025 5:00 PM | 1140FF | 1144 | As Soon As Possible | NA | 0 | 0d | July 11, 2025 5:00 PM | July 11, 2025 5:00 PM | 0 days | Yes | 10/3/25 | 10/3/25 | NA | 1
1235 | Financial Management: Build | October 6, 2025 8:00 AM | January 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 75 | -50d | August 11, 2025 8:00 AM | December 30, 2025 5:00 PM | 98 days | No | NA | NA | NA | 0
1236 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 18 | -50d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | NA | NA | NA | 0
1237 | M23: B1: 21.04 Track/Update Administrative Costs (CARESV1-32) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 1136FS+57d,1141 | 1145SS,1146SS,1147SS,1366SS | As Soon As Possible | NA | 18 | -50d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | NA | NA | NA | 0
1238 | M23: B2: 21.03 Track Contract Costs (r2) (CARESV1-116) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 1144SS | 1146SS | As Soon As Possible | NA | 18 | -50d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | NA | NA | NA | 0
1239 | M23: B3: Milestone 23 - Other Milestone Refinement Stories (CARESV1-14346) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 1144SS,1145SS | 1147SS,4685FS-19d | As Soon As Possible | NA | 18 | -50d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | NA | NA | NA | 0
1240 | M23: B1: 21.02 Track Contract Costs (r1) (CARESV1-64) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 1144SS,1146SS | 1154SS,4685FS-19d | As Soon As Possible | NA | 18 | -50d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | NA | NA | NA | 0
1241 | Milestone 24: Track Assistance Costs (CARESV1-506) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM |  | 523FF+6d | As Soon As Possible | NA | 38 | -16d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | NA | NA | NA | 0
1242 | M24: B1: 21.05 Track/Update Assistance Payment (CARESV1-26) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1140 | 1150SS,1151SS,4700FS-19d | As Soon As Possible | NA | 38 | -16d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | NA | NA | NA | 0
1243 | M24: B2: 18.04 Manage Resource Inventory (CARESV1-118) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1149SS | 1151SS,4700FS-19d | As Soon As Possible | NA | 38 | -16d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | NA | NA | NA | 0
1244 | M24: B3: County Expense Claim Reporting Information System (CECRIS) CEC Interface (CARESV1-13931) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1149SS,1150SS | 1159SS,4700FS-19d | As Soon As Possible | NA | 38 | -16d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | NA | NA | NA | 0
1245 | Financial Management: SIT | October 6, 2025 8:00 AM | January 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 75 | -16d | September 8, 2025 8:00 AM | November 28, 2025 5:00 PM | 58 days | No | NA | NA | NA | 0
1246 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 18 | -44d | September 8, 2025 8:00 AM | November 28, 2025 5:00 PM | 58 days | No | NA | NA | NA | 0
1247 | M23: B1: 21.04 Track/Update Administrative Costs (CARESV1-32) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 1147SS | 1155SS,1156SS,1157SS,4689 | As Soon As Possible | NA | 18 | -44d | September 8, 2025 8:00 AM | November 28, 2025 5:00 PM | 58 days | No | NA | NA | NA | 0
1248 | M23: B2: 21.03 Track Contract Costs (r2) (CARESV1-116) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 1154SS | 1156SS,4689 | As Soon As Possible | NA | 18 | -44d | September 8, 2025 8:00 AM | November 28, 2025 5:00 PM | 58 days | No | NA | NA | NA | 0
1249 | M23: B3: Milestone 23 - Other Milestone Refinement Stories (CARESV1-14346) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 1154SS,1155SS | 1157SS,4689 | As Soon As Possible | NA | 18 | -44d | September 8, 2025 8:00 AM | November 28, 2025 5:00 PM | 58 days | No | NA | NA | NA | 0
1250 | M23: B1: 21.02 Track Contract Costs (r1) (CARESV1-64) | December 29, 2025 8:00 AM | January 23, 2026 5:00 PM | 1154SS,1156SS | 1164,4684FF | As Soon As Possible | NA | 18 | 0d | September 8, 2025 8:00 AM | November 28, 2025 5:00 PM | 58 days | No | NA | NA | NA | 0
1251 | Milestone 24: Track Assistance Costs (CARESV1-506) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM |  | 3002 | As Soon As Possible | NA | 38 | -16d | September 8, 2025 8:00 AM | November 28, 2025 5:00 PM | 58 days | No | NA | NA | NA | 0
1252 | M24: B1: 21.05 Track/Update Assistance Payment (CARESV1-26) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1151SS | 1160SS,1161SS,4700FS-19d | As Soon As Possible | NA | 38 | -16d | September 8, 2025 8:00 AM | November 28, 2025 5:00 PM | 58 days | No | NA | NA | NA | 0
1253 | M24: B2: 18.04 Manage Resource Inventory (CARESV1-118) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1159SS | 1161SS,4700FS-19d | As Soon As Possible | NA | 38 | -16d | September 8, 2025 8:00 AM | November 28, 2025 5:00 PM | 58 days | No | NA | NA | NA | 0
1254 | M24: B3: County Expense Claim Reporting Information System (CECRIS) CEC Interface (CARESV1-13931) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1159SS,1160SS | 1169,4699FF,4700FS-19d | As Soon As Possible | NA | 38 | -16d | September 8, 2025 8:00 AM | November 28, 2025 5:00 PM | 58 days | No | NA | NA | NA | 0
1255 | Financial Management: State QA | December 1, 2025 8:00 AM | February 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 56 | 411d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | 12/1/25 | NA | NA | 0.14000000000000001
1256 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) | December 1, 2025 8:00 AM | February 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 56 | 411d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | 12/1/25 | NA | NA | 0.25
1257 | M23: B1: 21.04 Track/Update Administrative Costs (CARESV1-32) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 1157 | 1165SS,1166SS,1167SS,1357SS | As Soon As Possible | NA | 19 | 0d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
1258 | M23: B2: 21.03 Track Contract Costs (r2) (CARESV1-116) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 1164SS | 1166SS | As Soon As Possible | NA | 19 | 411d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
1259 | M23: B3: Milestone 23 - Other Milestone Refinement Stories (CARESV1-14346) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1164SS,1165SS | 1167SS | As Soon As Possible | NA | 19 | 0d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | 12/1/25 | 12/26/25 | NA | 1
1260 | M23: B1: 21.02 Track Contract Costs (r1) (CARESV1-64) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 1164SS,1166SS | 1176SS,5511,4690SS-36d | As Soon As Possible | NA | 19 | 0d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
1261 | Milestone 24: Track Assistance Costs (CARESV1-506) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 20d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
1262 | M24: B1: 21.05 Track/Update Assistance Payment (CARESV1-26) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1161 | 1170SS,1171SS | As Soon As Possible | NA | 19 | 20d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
1263 | M24: B2: 18.04 Manage Resource Inventory (CARESV1-118) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1169SS | 1171SS | As Soon As Possible | NA | 19 | 20d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
1264 | M24: B3: County Expense Claim Reporting Information System (CECRIS) CEC Interface (CARESV1-13931) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1169SS,1170SS | 1182SS,5517,4705SS-36d,1173FF | As Soon As Possible | NA | 19 | 20d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
11532 | Financial Management: User Feedback (23/23.1, 24) | December 11, 2025 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 11 | 448d | December 15, 2025 8:00 AM | December 30, 2025 5:00 PM | 11 days | No | NA | NA | NA | 0
11533 | Financial Management - Conduct Hands-on keyboard User Feedback sessions | December 11, 2025 8:00 AM | December 26, 2025 5:00 PM | 1171FF | 1180FF | As Soon As Possible | NA | 11 | 448d | December 15, 2025 8:00 AM | December 30, 2025 5:00 PM | 11 days | No | NA | NA | NA | 0
1265 | Financial Management: Joint Review | December 1, 2025 8:00 AM | February 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 56 | 411d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
1266 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 19 | 411d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
1268 | M23: B1: 21.04 Track/Update Administrative Costs (CARESV1-32) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 1167SS | 1177SS,1178SS,1179SS | As Soon As Possible | NA | 19 | 411d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
1269 | M23: B2: 21.03 Track Contract Costs (r2) (CARESV1-116) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 1176SS | 1178SS | As Soon As Possible | NA | 19 | 411d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
1270 | M23: B3: Milestone 23 - Other Milestone Refinement Stories (CARESV1-14346) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 1176SS,1177SS | 1179SS | As Soon As Possible | NA | 19 | 411d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
1271 | M23: B1: 21.02 Track Contract Costs (r1) (CARESV1-64) | January 26, 2026 8:00 AM | February 20, 2026 5:00 PM | 1176SS,1178SS | 1180FF | As Soon As Possible | NA | 19 | 411d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
10458 | Milestone 23/23.1: Track Administrative Costs (CARESV1-513) Complete | February 20, 2026 5:00 PM | February 20, 2026 5:00 PM | 1179FF,1173FF |  | As Soon As Possible | NA | 0 | 411d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
1283 | Milestone 24: Track Assistance Costs (CARESV1-506) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 448d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
1285 | M24: B1: 21.05 Track/Update Assistance Payment (CARESV1-26) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1171SS | 1183SS | As Soon As Possible | NA | 19 | 448d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
1286 | M24: B2: 18.04 Manage Resource Inventory (CARESV1-118) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1182SS | 1184SS | As Soon As Possible | NA | 19 | 448d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
1287 | M24: B3: County Expense Claim Reporting Information System (CECRIS) CEC Interface (CARESV1-13931) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1183SS | 1185FF | As Soon As Possible | NA | 19 | 448d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
10459 | Milestone 24: Track Assistance Costs (CARESV1-506) Complete | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 1184FF |  | As Soon As Possible | NA | 0 | 448d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
7532 | Eligibility | April 24, 2023 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 692 | 429d | April 24, 2023 8:00 AM | December 30, 2025 5:00 PM | 445 days | No | 4/24/23 | NA | NA | 0.87
7533 | Eligibility: Holistic Design Milestones | April 24, 2023 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 692 | 429d | April 24, 2023 8:00 AM | December 30, 2025 5:00 PM | 445 days | No | 4/24/23 | NA | NA | 0.87
7534 | Group 1 Eligibility (Milestone 21) | April 24, 2023 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 692 | 429d | April 24, 2023 8:00 AM | December 30, 2025 5:00 PM | 445 days | No | 4/24/23 | NA | NA | 0.87
7535 | Eligibility - Scenario Requirements Validation | September 30, 2024 8:00 AM | October 18, 2024 5:00 PM | 1213FF | 5479SS-10d,5507,5513,1194SS+3d | Finish No Earlier Than | 10/18/24 | 15 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 9/30/24 | 10/18/24 | NA | 1
7537 | Eligibility: Holistic Design Artifacts | July 30, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 167 | 0d | August 15, 2024 8:00 AM | March 28, 2025 5:00 PM | 155 days | No | 7/30/24 | 3/28/25 | NA | 1
7538 | Eligibility - Design Cycle 1 | July 30, 2024 8:00 AM | January 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 109 | 0d | August 15, 2024 8:00 AM | January 3, 2025 5:00 PM | 97 days | No | 7/30/24 | 1/3/25 | NA | 1
11604 | Eligibility - Design Cycle 1 - Draft & Review Application Flow | July 30, 2024 8:00 AM | September 13, 2024 5:00 PM |  |  | As Soon As Possible | NA | 34 | 0d | NA | NA | 0 days? | No | 7/30/24 | 9/13/24 | NA | 1
11605 | Eligibility - Design Cycle 1 - Implementation Artifacts Review | August 19, 2024 8:00 AM | September 6, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 0 days? | No | 8/19/24 | 9/6/24 | NA | 1
7539 | Eligibility - Design Cycle 1 - Prepare Interface Specifications | August 15, 2024 8:00 AM | December 20, 2024 5:00 PM | 1189SS+3d | 1195SS+10d,2306SS | Start No Earlier Than | 8/15/24 | 89 | 0d | August 15, 2024 8:00 AM | December 20, 2024 5:00 PM | 89 days | No | 8/15/24 | 12/20/24 | NA | 1
7540 | Eligibility - Design Cycle 1 - Review Interface Specifications | August 29, 2024 8:00 AM | December 27, 2024 5:00 PM | 1194SS+10d | 1196SS+5d | As Soon As Possible | NA | 83 | 0d | August 29, 2024 8:00 AM | December 27, 2024 5:00 PM | 83 days | No | 8/29/24 | 12/27/24 | NA | 1
7541 | Eligibility - Design Cycle 1 - Revise and Finalize Interface Specifications | September 5, 2024 8:00 AM | January 3, 2025 5:00 PM | 1195SS+5d | 1200FS+14d,1198 | As Soon As Possible | NA | 82 | 0d | September 5, 2024 8:00 AM | January 3, 2025 5:00 PM | 82 days | No | 9/5/24 | 1/3/25 | NA | 1
7542 | Eligibilty - Design Cycle 2 | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 58 | 0d | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM | 58 days | No | 1/6/25 | 3/28/25 | NA | 1
11490 | Eligibility - Design Cycle 2 - Perform Pre-Build activities | January 6, 2025 8:00 AM | March 7, 2025 5:00 PM | 1196 | 1201SS+5d,2307SS,2588SS,1199SS+9d | As Soon As Possible | NA | 43 | 0d | January 6, 2025 8:00 AM | March 7, 2025 5:00 PM | 43 days | No | 1/6/25 | 3/7/25 | NA | 1
11489 | Eligibility - Design Cycle 2 - Perform Pre-Build QA (with VPOD) and Address Findings | January 17, 2025 8:00 AM | March 6, 2025 5:00 PM | 1198SS+9d | 1201SS+5d,2307SS,2588SS | As Soon As Possible | NA | 33 | 0d | January 17, 2025 8:00 AM | March 6, 2025 5:00 PM | 33 days | No | 1/17/25 | 3/6/25 | NA | 1
7543 | Eligibility - Design Cycle 2 - Prepare for Walkthrough with Core Constituents | January 27, 2025 8:00 AM | March 7, 2025 5:00 PM | 1196FS+14d | 1201SS+5d,2307SS,2588SS | As Soon As Possible | NA | 29 | 0d | January 27, 2025 8:00 AM | March 7, 2025 5:00 PM | 29 days | No | 1/27/25 | 3/7/25 | NA | 1
7544 | Eligibility - Design Cycle 2 - Conduct Design Walkthrough with Core Constituents | February 3, 2025 8:00 AM | March 14, 2025 5:00 PM | 1200SS+5d,1199SS+5d,1198SS+5d | 1202SS+5d | As Soon As Possible | NA | 29 | 0d | February 3, 2025 8:00 AM | March 14, 2025 5:00 PM | 29 days | No | 2/3/25 | 3/14/25 | NA | 1
7545 | Eligibility - Design Cycle 2 - Final Review and Design Baseline | February 10, 2025 8:00 AM | March 28, 2025 5:00 PM | 1201SS+5d | 1223FF | As Soon As Possible | NA | 34 | 0d | February 10, 2025 8:00 AM | March 28, 2025 5:00 PM | 34 days | No | 2/10/25 | 3/28/25 | NA | 1
7546 | Eligibility: Context Setting | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 80 | 0d | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 77 days | No | 4/24/23 | 8/15/23 | NA | 1
7547 | Milestone 21: Eligibility Programs (CARESV1-511) | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 80 | 0d | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 77 days | No | 4/24/23 | 8/15/23 | NA | 1
7548 | M21: RC: Finalize Value Hypothesis | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM |  | 1206SS | Finish No Earlier Than | 8/15/23 | 80 | 0d | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 40 days | No | 4/24/23 | 8/15/23 | NA | 1
7549 | M21: RC: Draft Service Maps | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 1205SS | 1207SS | Finish No Earlier Than | 8/15/23 | 80 | 0d | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 20 days | No | 4/24/23 | 8/15/23 | NA | 1
7550 | M21: RC: Complete Legacy Analysis | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 1206SS | 1208SS | Finish No Earlier Than | 8/15/23 | 80 | 0d | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 20 days | No | 4/24/23 | 8/15/23 | NA | 1
7551 | M21: RC: Finalize Epics | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 1207SS | 1209SS | Finish No Earlier Than | 8/15/23 | 80 | 0d | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 5 days | No | 4/24/23 | 8/15/23 | NA | 1
7552 | M21: RC: Complete conceptual and epic-level Domain Model diagrams | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 1208SS | 1210SS | Finish No Earlier Than | 8/15/23 | 80 | 0d | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 30 days | No | 4/24/23 | 8/15/23 | NA | 1
7553 | M21: RC: Define User Story titles | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 1209SS | 1211SS | Finish No Earlier Than | 8/15/23 | 80 | 0d | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 20 days | No | 4/24/23 | 8/15/23 | NA | 1
7554 | M21: RC: Complete External Systems pre-analysis | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 1210SS | 1212SS | Finish No Earlier Than | 8/15/23 | 80 | 0d | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 17 days | No | 4/24/23 | 8/15/23 | NA | 1
7555 | M21: RC: Facilitate Inception | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 1211SS | 1215FS+20d,2587FS+210d | Finish No Earlier Than | 8/15/23 | 80 | 0d | April 24, 2023 8:00 AM | August 15, 2023 5:00 PM | 17 days | No | 4/24/23 | 8/15/23 | NA | 1
7565 | Eligibility: BRC | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM |  | 1189FF | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
7566 | Milestone 21: Eligibility Programs (CARESV1-511) | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM |  |  | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
7567 | M21: B1 19.05 Request Kin-GAP eligibility determination (CARESV1-11) | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 1212FS+20d | 1216SS,1217SS,1219SS,1218SS | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
7568 | M21: B2 19.06 Request NRLG eligibility determination (CARESV1-101) | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 1215SS | 150 | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
7569 | M21: B3 19.07 Request AAP eligibility determination (CARESV1-45) | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 1215SS | 1218SS | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
7633 | M21: B4 19.08 Request Extended Foster Care (EFC) determination (CARESV1-117) | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 1215SS,1217SS | 1219SS | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
7570 | M21: B5 FCED (Foster Care Eligibility Determination) Interface - Eligibility Programs (CARESV1-13930) | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 1215SS,1218SS | 1220FF | As Soon As Possible | NA | 50 | 0d | August 12, 2024 8:00 AM | October 18, 2024 5:00 PM | 50 days | No | 8/12/24 | 10/18/24 | NA | 1
7575 | Eligibility BRC Milestone Completion | October 18, 2024 5:00 PM | October 18, 2024 5:00 PM | 1219FF | 1223,1276SS+28d | As Soon As Possible | NA | 0 | 0d | October 18, 2024 5:00 PM | October 18, 2024 5:00 PM | 0 days | Yes | 10/18/24 | 10/18/24 | NA | 1
7576 | Eligibility: Design | December 5, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 78 | 0d | December 5, 2024 8:00 AM | March 28, 2025 5:00 PM | 78 days | No | 12/5/24 | 3/28/25 | NA | 1
7577 | Milestone 21: Eligibility Programs (CARESV1-511) | December 5, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 78 | 0d | December 5, 2024 8:00 AM | March 28, 2025 5:00 PM | 78 days | No | 12/5/24 | 3/28/25 | NA | 1
7578 | M21: B1 19.05 Request Kin-GAP eligibility determination (CARESV1-11) | December 5, 2024 8:00 AM | March 28, 2025 5:00 PM | 1202FF,1220 | 1225SS,1226SS,1227SS,1224SS | Finish No Earlier Than | 3/28/25 | 78 | 0d | December 5, 2024 8:00 AM | March 28, 2025 5:00 PM | 78 days | No | 12/5/24 | 3/28/25 | NA | 1
7634 | M21: B2 19.06 Request NRLG eligibility determination (CARESV1-101) | December 5, 2024 8:00 AM | March 28, 2025 5:00 PM | 1223SS | 1225SS | As Soon As Possible | NA | 78 | 0d | December 5, 2024 8:00 AM | March 28, 2025 5:00 PM | 78 days | No | 12/5/24 | 3/28/25 | NA | 1
7579 | M21: B3 19.07 Request AAP eligibility determination (CARESV1-45) | December 5, 2024 8:00 AM | March 28, 2025 5:00 PM | 1223SS,1224SS | 1226SS | As Soon As Possible | NA | 78 | 0d | December 5, 2024 8:00 AM | March 28, 2025 5:00 PM | 78 days | No | 12/5/24 | 3/28/25 | NA | 1
7580 | M21: B4 19.08 Request Extended Foster Care (EFC) determination (CARESV1-117) | December 5, 2024 8:00 AM | March 28, 2025 5:00 PM | 1223SS,1225SS | 1227SS | As Soon As Possible | NA | 78 | 0d | December 5, 2024 8:00 AM | March 28, 2025 5:00 PM | 78 days | No | 12/5/24 | 3/28/25 | NA | 1
7581 | M21: B5 FCED (Foster Care Eligibility Determination) Interface - Eligibility Programs (CARESV1-13930) | December 5, 2024 8:00 AM | March 28, 2025 5:00 PM | 1223SS,1226SS | 1231,1228FF | As Soon As Possible | NA | 78 | 0d | December 5, 2024 8:00 AM | March 28, 2025 5:00 PM | 78 days | No | 12/5/24 | 3/28/25 | NA | 1
7586 | Eligibility Design Milestone Completion | March 28, 2025 5:00 PM | March 28, 2025 5:00 PM | 1227FF | 1231FS+131d | As Soon As Possible | NA | 0 | 0d | March 28, 2025 5:00 PM | March 28, 2025 5:00 PM | 0 days | Yes | 3/28/25 | 3/28/25 | NA | 1
7587 | Eligibility: Build | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 38 | 467d | April 1, 2025 8:00 AM | December 30, 2025 5:00 PM | 190 days | No | 10/6/25 | NA | NA | 0.38
7588 | Milestone 21: Eligibility Programs (CARESV1-511) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 38 | 467d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 10/6/25 | NA | NA | 0.38
7589 | M21: B1 19.05 Request Kin-GAP eligibility determination (CARESV1-11) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1227,1228FS+131d | 1233SS,1234SS,1235SS,1232SS | As Soon As Possible | NA | 38 | 0d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 10/6/25 | 11/28/25 | NA | 1
7635 | M21: B2 19.06 Request NRLG eligibility determination (CARESV1-101) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1231SS | 1233SS | As Soon As Possible | NA | 38 | 34.2d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
7590 | M21: B3 19.07 Request AAP eligibility determination (CARESV1-45) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1231SS,1232SS | 1234SS | As Soon As Possible | NA | 38 | 34.2d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
7591 | M21: B4 19.08 Request Extended Foster Care (EFC) determination (CARESV1-117) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1231SS,1233SS | 1235SS | As Soon As Possible | NA | 38 | 467d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 10/6/25 | NA | NA | 0.90000000000000002
7592 | M21: B5 FCED (Foster Care Eligibility Determination) Interface - Eligibility Programs (CARESV1-13930) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1231SS,1234SS | 1238SS | As Soon As Possible | NA | 38 | 467d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
7603 | Eligibility: SIT | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 38 | 467d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 10/6/25 | NA | NA | 0.57999999999999996
7604 | Milestone 21: Eligibility Programs (CARESV1-511) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 38 | 467d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 10/6/25 | NA | NA | 0.57999999999999996
7636 | M21: B1 19.05 Request Kin-GAP eligibility determination (CARESV1-11) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1235SS | 1239SS | As Soon As Possible | NA | 38 | 0d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 10/6/25 | 11/28/25 | NA | 1
7605 | M21: B2 19.06 Request NRLG eligibility determination (CARESV1-101) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1238SS | 1241SS,1242SS,1240SS | As Soon As Possible | NA | 38 | 0d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 10/6/25 | 11/28/25 | NA | 1
7606 | M21: B3 19.07 Request AAP eligibility determination (CARESV1-45) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1239SS | 1241SS | As Soon As Possible | NA | 38 | 34.2d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
7607 | M21: B4 19.08 Request Extended Foster Care (EFC) determination (CARESV1-117) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1239SS,1240SS | 128SS | As Soon As Possible | NA | 38 | 467d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 10/6/25 | NA | NA | 0.90000000000000002
7608 | M21: B5 FCED (Foster Care Eligibility Determination) Interface - Eligibility Programs (CARESV1-13930) | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1239SS | 1245,4620FF,4684FF | As Soon As Possible | NA | 38 | 59d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | NA | NA | NA | 0
7613 | Eligibility: State QA | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 448d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 12/1/25 | NA | NA | 0.80000000000000004
7614 | Milestone 21: Eligibility Programs (CARESV1-511) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 448d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 12/1/25 | NA | NA | 0.80000000000000004
7615 | M21: B1 19.05 Request Kin-GAP eligibility determination (CARESV1-11) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1242 | 1247SS,1248SS,1249SS,1246SS | As Soon As Possible | NA | 19 | 0d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 12/1/25 | 12/26/25 | NA | 1
7637 | M21: B2 19.06 Request NRLG eligibility determination (CARESV1-101) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1245SS |  | As Soon As Possible | NA | 19 | 0d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 12/1/25 | 12/26/25 | NA | 1
7616 | M21: B3 19.07 Request AAP eligibility determination (CARESV1-45) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1245SS |  | As Soon As Possible | NA | 19 | 448d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
7617 | M21: B4 19.08 Request Extended Foster Care (EFC) determination (CARESV1-117) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1245SS |  | As Soon As Possible | NA | 19 | 0d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 12/1/25 | 12/26/25 | NA | 1
7618 | M21: B5 FCED (Foster Care Eligibility Determination) Interface - Eligibility Programs (CARESV1-13930) | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1245SS | 1253,1252,5511,4690SS-36d,5483 | As Soon As Possible | NA | 19 | 0d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 12/1/25 | 12/26/25 | NA | 1
7623 | Eligibility: Joint Review | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 19 | 429d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
7624 | Milestone 21: Eligibility Programs (CARESV1-511) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 19 | 429d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
7638 | M21: B1 19.05 Request Kin-GAP eligibility determination (CARESV1-11) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 1249 |  | As Soon As Possible | NA | 19 | 429d | May 30, 2025 8:00 AM | December 29, 2025 5:00 PM | 147 days | No | NA | NA | NA | 0
7625 | M21: B2 19.06 Request NRLG eligibility determination (CARESV1-101) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 1249 | 1254SS,1255SS,1256SS | As Soon As Possible | NA | 19 | 429d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
7626 | M21: B3 19.07 Request AAP eligibility determination (CARESV1-45) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 1253SS | 1255SS | As Soon As Possible | NA | 19 | 429d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
7627 | M21: B4 19.08 Request Extended Foster Care (EFC) determination (CARESV1-117) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 1253SS,1254SS | 1256SS | As Soon As Possible | NA | 19 | 429d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
7628 | M21: B5 FCED (Foster Care Eligibility Determination) Interface - Eligibility Programs (CARESV1-13930) | December 29, 2025 8:00 AM | January 26, 2026 5:00 PM | 1253SS,1255SS | 1257FF | As Soon As Possible | NA | 19 | 429d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
10460 | Milestone 21: Eligibility Programs (CARESV1-511) Complete | January 26, 2026 5:00 PM | January 26, 2026 5:00 PM | 1256FF |  | As Soon As Possible | NA | 0 | 429d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
4665 | Admin Console | May 17, 2024 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 405 | 148d | May 17, 2024 8:00 AM | December 30, 2025 5:00 PM | 407 days | No | 5/17/24 | NA | NA | 0.94999999999999996
4666 | Admin Console: Holistic Design Milestones | May 17, 2024 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 405 | 148d | May 17, 2024 8:00 AM | December 30, 2025 5:00 PM | 407 days | No | 5/17/24 | NA | NA | 0.96999999999999997
4667 | Group 1 Admin Console (Milestone 32) | May 17, 2024 8:00 AM | March 14, 2025 5:00 PM |  |  | As Soon As Possible | NA | 207 | 0d | May 17, 2024 8:00 AM | March 14, 2025 5:00 PM | 207 days | No | 5/17/24 | 3/14/25 | NA | 1
4668 | Admin Console - Finalize Requirements Baseline | May 17, 2024 8:00 AM | March 14, 2025 5:00 PM | 1275FF+15d | 5521FS-45d,1266SS+185d,1293SS,1264FS-40d,1265FS-40d | As Soon As Possible | NA | 192 | 0d | May 17, 2024 8:00 AM | March 14, 2025 5:00 PM | 192 days | No | 5/17/24 | 3/14/25 | NA | 1
4669 | Admin Console: Holistic Design Artifacts | January 16, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 142 | 0d | February 24, 2025 8:00 AM | August 8, 2025 5:00 PM | 117 days | No | 1/16/25 | 8/8/25 | NA | 1
4676 | Admin Console - Design Cycle 1 | January 16, 2025 8:00 AM | May 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 74 | 0d | February 24, 2025 8:00 AM | May 2, 2025 5:00 PM | 49 days | No | 1/16/25 | 5/2/25 | NA | 1
11606 | Admin Console - Design Cycle 1 - Draft & Review Application Flow | January 16, 2025 8:00 AM | April 18, 2025 5:00 PM | 1261FS-40d |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 1/16/25 | 4/18/25 | NA | 1
11607 | Admin Console - Design Cycle 1 - Implementation Artifacts Review | January 16, 2025 8:00 AM | April 18, 2025 5:00 PM | 1261FS-40d | 1278SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 1/16/25 | 4/18/25 | NA | 1
4677 | Admin Console - Design Cycle 1 - Prepare Blueprint | February 24, 2025 8:00 AM | April 18, 2025 5:00 PM | 1261SS+185d | 1267SS+10d | Must Start On | 2/24/25 | 39 | 0d | February 24, 2025 8:00 AM | April 18, 2025 5:00 PM | 39 days | No | 2/24/25 | 4/18/25 | NA | 1
4678 | Admin Console - Design Cycle 1 - Review Blueprint | March 10, 2025 8:00 AM | April 25, 2025 5:00 PM | 1266SS+10d | 1268SS+5d | As Soon As Possible | NA | 34 | 0d | March 10, 2025 8:00 AM | April 25, 2025 5:00 PM | 34 days | No | 3/10/25 | 4/25/25 | NA | 1
4679 | Admin Console - Design Cycle 1 - Revise and Finalize Blueprint | March 17, 2025 8:00 AM | May 2, 2025 5:00 PM | 1267SS+5d | 1272FS+24d,1270 | As Soon As Possible | NA | 34 | 0d | March 17, 2025 8:00 AM | May 2, 2025 5:00 PM | 34 days | No | 3/17/25 | 5/2/25 | NA | 1
4680 | Admin Console - Design Cycle 2 | May 5, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 68 | 0d | May 5, 2025 8:00 AM | August 8, 2025 5:00 PM | 68 days | No | 5/5/25 | 8/8/25 | NA | 1
11492 | Admin Console - Design Cycle 2 - Perform Pre-Build activities | May 5, 2025 8:00 AM | July 18, 2025 5:00 PM | 1268 | 1273SS+5d,1271SS+10d | As Soon As Possible | NA | 53 | 0d | May 5, 2025 8:00 AM | July 18, 2025 5:00 PM | 53 days | No | 5/5/25 | 7/18/25 | NA | 1
11491 | Admin Console - Design Cycle 2 - Perform Pre-Build QA (with VPOD) and Address Findings | May 19, 2025 8:00 AM | July 18, 2025 5:00 PM | 1270SS+10d | 1273SS+5d | As Soon As Possible | NA | 43 | 0d | May 19, 2025 8:00 AM | July 18, 2025 5:00 PM | 43 days | No | 5/19/25 | 7/18/25 | NA | 1
4681 | Admin Console - Design Cycle 2 - Prepare for Walkthrough with Core Constituents | June 9, 2025 8:00 AM | July 18, 2025 5:00 PM | 1268FS+24d | 1273SS+5d | As Soon As Possible | NA | 29 | 0d | June 9, 2025 8:00 AM | July 18, 2025 5:00 PM | 29 days | No | 6/9/25 | 7/18/25 | NA | 1
4684 | Admin Console - Design Cycle 2 - Conduct Design Walkthrough with Core Constituents | June 16, 2025 8:00 AM | July 25, 2025 5:00 PM | 1272SS+5d,1271SS+5d,1270SS+5d | 1274SS+5d | As Soon As Possible | NA | 29 | 0d | June 16, 2025 8:00 AM | July 25, 2025 5:00 PM | 29 days | No | 6/16/25 | 7/25/25 | NA | 1
4687 | Admin Console - Design Cycle 2 - Final Review and Design Baseline | June 23, 2025 8:00 AM | August 8, 2025 5:00 PM | 1273SS+5d |  | As Soon As Possible | NA | 34 | 0d | June 23, 2025 8:00 AM | August 8, 2025 5:00 PM | 34 days | No | 6/23/25 | 8/8/25 | NA | 1
4718 | Admin Console: BRC | December 3, 2024 8:00 AM | February 21, 2025 5:00 PM |  | 1261FF+15d | As Soon As Possible | NA | 55 | 0d | December 2, 2024 8:00 AM | February 21, 2025 5:00 PM | 56 days | No | 12/3/24 | 2/21/25 | NA | 1
4719 | Milestone 32: BRC | December 3, 2024 8:00 AM | February 21, 2025 5:00 PM | 1220SS+28d |  | As Soon As Possible | NA | 55 | 0d | December 2, 2024 8:00 AM | February 21, 2025 5:00 PM | 56 days | No | 12/3/24 | 2/21/25 | NA | 1
4727 | Admin Console: Design | January 16, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 142 | 0d | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 days | No | 1/16/25 | 8/8/25 | NA | 1
4728 | Milestone 32: Design | January 16, 2025 8:00 AM | August 8, 2025 5:00 PM | 1265SS | 1280,4728 | As Soon As Possible | NA | 142 | 0d | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 29 days | No | 1/16/25 | 8/8/25 | NA | 1
4735 | Admin Console: Build | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 77 | 0d | August 11, 2025 8:00 AM | December 30, 2025 5:00 PM | 98 days | No | 8/11/25 | NA | NA | 0.93000000000000005
4736 | Milestone 32: Build | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 1278 | 1282SS,4728FS-19d | As Soon As Possible | NA | 77 | -13d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | 8/11/25 | NA | NA | 0.93000000000000005
4749 | Admin Console: SIT | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 77 | 0d | September 8, 2025 8:00 AM | November 28, 2025 5:00 PM | 58 days | No | 8/11/25 | NA | NA | 0.88
4750 | Milestone 32: SIT | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 1280SS | 1284,4728FS-19d,4732 | As Soon As Possible | NA | 77 | -13d | September 8, 2025 8:00 AM | November 28, 2025 5:00 PM | 58 days | No | 8/11/25 | NA | NA | 0.88
4757 | Admin Console: State QA | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 148d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | 12/1/25 | NA | NA | 0.23999999999999999
4758 | Milestone 32: State QA | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1282 | 1286SS,5525 | As Soon As Possible | NA | 19 | 148d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | 12/1/25 | NA | NA | 0.23999999999999999
4765 | Admin Console: Joint Review | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 16d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
4766 | Milestone 32: Joint Review | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1284SS | 1287FF | As Soon As Possible | NA | 19 | 16d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | NA | NA | NA | 0
10461 | Milestone 32: Admin Console Complete | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 1286FF | 1847 | As Soon As Possible | NA | 0 | 16d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
6335 | Shared Services | November 3, 2022 8:00 AM | March 2, 2026 3:00 PM |  |  | As Soon As Possible | NA | 829.75 | 405.25d | August 14, 2023 8:00 AM | December 30, 2025 5:00 PM | 597 days | No | 11/3/22 | NA | NA | 0.93000000000000005
6336 | Shared Services: Holistic Design Milestones | July 1, 2024 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 279 | 544d | July 15, 2024 8:00 AM | August 8, 2025 5:00 PM | 270 days | No | 7/1/24 | NA | NA | 0.98999999999999999
6337 | Group 1 Shared Services | July 1, 2024 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 279 | 544d | July 15, 2024 8:00 AM | August 8, 2025 5:00 PM | 270 days | No | 7/1/24 | NA | NA | 0.98999999999999999
6339 | Shared Services: Holistic Design Artifacts | July 1, 2024 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 279 | 544d | July 15, 2024 8:00 AM | August 8, 2025 5:00 PM | 270 days | No | 7/1/24 | NA | NA | 0.98999999999999999
6340 | Shared Services - Design Cycle 1 | July 15, 2024 8:00 AM | June 13, 2025 5:00 PM |  |  | As Soon As Possible | NA | 231 | 0d | July 15, 2024 8:00 AM | April 4, 2025 5:00 PM | 182 days | No | 7/15/24 | 6/13/25 | NA | 1
6341 | Shared Services - Design Cycle 1 - Prepare Design | July 15, 2024 8:00 AM | May 30, 2025 5:00 PM | 1261SS | 1294SS+10d | As Soon As Possible | NA | 221 | 0d | July 15, 2024 8:00 AM | March 21, 2025 5:00 PM | 173 days | No | 7/15/24 | 5/30/25 | NA | 1
6342 | Shared Services - Design Cycle 1 - Review Design | July 29, 2024 8:00 AM | June 6, 2025 5:00 PM | 1293SS+10d | 1295SS+5d | As Soon As Possible | NA | 216 | 0d | July 29, 2024 8:00 AM | March 28, 2025 5:00 PM | 168 days | No | 7/29/24 | 6/6/25 | NA | 1
6343 | Shared Services - Design Cycle 1 - Revise and Finalize Design | August 5, 2024 8:00 AM | June 13, 2025 5:00 PM | 1294SS+5d | 1297SS+63d | As Soon As Possible | NA | 216 | 0d | August 5, 2024 8:00 AM | April 4, 2025 5:00 PM | 167 days | No | 8/5/24 | 6/13/25 | NA | 1
6344 | Shared Services - Design Cycle 2 | October 31, 2024 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 192 | 544d | October 31, 2024 8:00 AM | August 8, 2025 5:00 PM | 192 days | No | 10/31/24 | NA | NA | 0.97999999999999998
6345 | Shared Services - Design Cycle 2 - Prepare Walkthrough | October 31, 2024 8:00 AM | July 18, 2025 5:00 PM | 1295SS+63d | 1298SS+5d,1314SS | As Soon As Possible | NA | 177 | 559d | October 31, 2024 8:00 AM | July 18, 2025 5:00 PM | 177 days | No | 10/31/24 | NA | NA | 0.97999999999999998
6346 | Shared Services - Design Cycle 2 - Conduct Design Walkthrough | November 7, 2024 8:00 AM | July 25, 2025 5:00 PM | 1297SS+5d | 1299SS+5d | As Soon As Possible | NA | 177 | 554d | November 7, 2024 8:00 AM | July 25, 2025 5:00 PM | 177 days | No | 11/7/24 | NA | NA | 0.97999999999999998
6347 | Shared Services - Design Cycle 2 - Final Review and Design Baseline | November 15, 2024 8:00 AM | August 8, 2025 5:00 PM | 1298SS+5d | 1314FF | As Soon As Possible | NA | 182 | 544d | November 15, 2024 8:00 AM | August 8, 2025 5:00 PM | 182 days | No | 11/15/24 | NA | NA | 0.97999999999999998
11471 | Global Design Pattern | July 1, 2024 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 279 | 0d | July 15, 2024 8:00 AM | August 8, 2025 5:00 PM | 270 days | No | 7/1/24 | 8/8/25 | NA | 1
11608 | Global Template Identify and Prioritize | July 1, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
11609 | Design Template: Grid | July 1, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
11610 | Design Template: Focus: Case Management Worker | July 1, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
11611 | Design Template: Left Navigation | July 1, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
11612 | Design Template: Console | July 1, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
11613 | Design Template: Utility Bar | July 1, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
11614 | Design Template: Left Navigation - specific | July 1, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
11615 | Design Template: Search Criteria & Search Results | July 1, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
11616 | Design Template: Record View w/Fields | July 1, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
11617 | Design Template: Record View w/Mixed (Fields & Table) | July 1, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
11618 | Design Template: Record View w/Table | July 1, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
11619 | Design Template: Record View w/Edit Fields | July 1, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
11620 | Design Template: Focus: Case, Investigation & Application | July 1, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
11473 | Complete Design of Global Design Pattern | October 31, 2024 8:00 AM | August 8, 2025 5:00 PM | 1297SS,1299FF |  | As Soon As Possible | NA | 192 | 0d | October 31, 2024 8:00 AM | August 8, 2025 5:00 PM | 192 days | No | 10/31/24 | 8/8/25 | NA | 1
11520 | Tech Debt Items | August 12, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 98 | 0d | August 12, 2024 8:00 AM | January 30, 2025 5:00 PM | 118 days | No | 8/12/24 | 12/31/24 | NA | 1
11521 | Identify and Prioritize Tech Debt Items | August 12, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | Finish No Earlier Than | 12/31/24 | 98 | 0d | August 12, 2024 8:00 AM | December 31, 2024 5:00 PM | 98 days | No | 8/12/24 | 12/31/24 | NA | 1
11203 | Shared Services Milestones | August 14, 2023 8:00 AM | March 2, 2026 3:00 PM |  |  | As Soon As Possible | NA | 637.75 | 405.25d | August 14, 2023 8:00 AM | December 30, 2025 5:00 PM | 597 days | No | 8/14/23 | NA | NA | 0.89000000000000001
11104 | Shared Services - Case Planning Framework (M7) | July 15, 2024 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 309 | 505d | July 15, 2024 8:00 AM | December 30, 2025 5:00 PM | 368 days | No | 7/15/24 | NA | NA | 0.96999999999999997
11105 | Shared Services - Case Planning Framework (M7) - Design | July 15, 2024 8:00 AM | March 28, 2025 5:00 PM | 593SS | 1320FS+34d | As Soon As Possible | NA | 178 | 0d | July 15, 2024 8:00 AM | March 28, 2025 5:00 PM | 178 days | No | 7/15/24 | 3/28/25 | NA | 1
11106 | Shared Services - Case Planning Framework (M7) - Build / SIT | May 19, 2025 8:00 AM | August 8, 2025 5:00 PM | 1319FS+34d | 1321 | As Soon As Possible | NA | 58 | 0d | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 days | No | 5/19/25 | 8/8/25 | NA | 1
11204 | Shared Services - Case Planning Framework (M7) - State QA | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 1320 |  | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.77000000000000002
11107 | Shared Services - Content Management (M7) | July 15, 2024 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 309 | 505d | July 15, 2024 8:00 AM | December 30, 2025 5:00 PM | 368 days | No | 7/15/24 | NA | NA | 0.92000000000000004
11108 | Shared Services - Content Management (M7) - Design | July 15, 2024 8:00 AM | March 28, 2025 5:00 PM | 593SS | 1324FS+34d | As Soon As Possible | NA | 178 | 0d | July 15, 2024 8:00 AM | March 28, 2025 5:00 PM | 178 days | No | 7/15/24 | 3/28/25 | NA | 1
11109 | Shared Services - Content Management (M7) - Build / SIT | May 19, 2025 8:00 AM | August 8, 2025 5:00 PM | 1323FS+34d | 1325 | As Soon As Possible | NA | 58 | 0d | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 days | No | 5/19/25 | 8/8/25 | NA | 1
11366 | Shared Services - Content Management (M7) - State QA | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 1324 |  | As Soon As Possible | NA | 39 | 505d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.42999999999999999
11110 | Shared Services - Deletion (M11) | October 21, 2024 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 277 | 467d | October 21, 2024 8:00 AM | December 30, 2025 5:00 PM | 298 days | No | 10/21/24 | NA | NA | 0.81000000000000005
11111 | Shared Services - Deletion (M11) - Design | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 608SS | 1328 | As Soon As Possible | NA | 200 | 0d | October 21, 2024 8:00 AM | May 30, 2025 5:00 PM | 151 days | No | 10/21/24 | 8/8/25 | NA | 1
11112 | Shared Services - Deletion (M11) - Build / SIT | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 1327 | 1329 | As Soon As Possible | NA | 39 | 467d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | NA | NA | 0.62
11367 | Shared Services - Deletion (M11) - State QA | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1328 |  | As Soon As Possible | NA | 38 | 467d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
11113 | Shared Services - Duplicate Management (M26) | September 30, 2024 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 311 | 448d | September 30, 2024 8:00 AM | December 30, 2025 5:00 PM | 313 days | No | 9/30/24 | NA | NA | 0.69999999999999996
11114 | Shared Services - Duplicate Management (M26) - Design | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 934SS | 1332FS+131d | As Soon As Possible | NA | 123 | 0d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 9/30/24 | 3/28/25 | NA | 1
11115 | Shared Services - Duplicate Management (M26) - Build / SIT | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1331FS+131d | 1333FS-60d | As Soon As Possible | NA | 38 | 63.42d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
11368 | Shared Services - Duplicate Management (M26) - State QA | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1047SS,1332FS-60d |  | As Soon As Possible | NA | 19 | 448d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 12/1/25 | NA | NA | 0.17999999999999999
11116 | Shared Services - Group Builder (M7) | July 15, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 178 | 0d | July 15, 2024 8:00 AM | December 30, 2025 5:00 PM | 368 days | No | 7/15/24 | 3/28/25 | NA | 1
11117 | Shared Services - Group Builder (M7) - Design | July 15, 2024 8:00 AM | March 28, 2025 5:00 PM | 593SS |  | As Soon As Possible | NA | 178 | 0d | July 15, 2024 8:00 AM | March 28, 2025 5:00 PM | 178 days | No | 7/15/24 | 3/28/25 | NA | 1
11119 | Shared Services - Location Services (M16) | August 15, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 155 | 0d | August 15, 2024 8:00 AM | December 30, 2025 5:00 PM | 345 days | No | 8/15/24 | 3/28/25 | NA | 1
11120 | Shared Services - Location Services (M16) - Design | August 15, 2024 8:00 AM | March 28, 2025 5:00 PM | 798SS |  | As Soon As Possible | NA | 155 | 0d | August 15, 2024 8:00 AM | March 28, 2025 5:00 PM | 155 days | No | 8/15/24 | 3/28/25 | NA | 1
11122 | Shared Services - Matching (M11) | October 21, 2024 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 277 | 467d | October 21, 2024 8:00 AM | December 30, 2025 5:00 PM | 298 days | No | 10/21/24 | NA | NA | 0.93999999999999995
11123 | Shared Services - Matching (M11) - Design | October 21, 2024 8:00 AM | May 30, 2025 5:00 PM | 608SS | 1340FS+49d | As Soon As Possible | NA | 151 | 0d | October 21, 2024 8:00 AM | May 30, 2025 5:00 PM | 151 days | No | 10/21/24 | 5/30/25 | NA | 1
11124 | Shared Services - Matching (M11) - Build / SIT | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 1339FS+49d | 1341 | As Soon As Possible | NA | 39 | 505d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | NA | NA | 0.62
11371 | Shared Services - Matching (M11) - State QA | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1340 |  | As Soon As Possible | NA | 38 | 0d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | 10/6/25 | 11/28/25 | NA | 1
11125 | Shared Services - MDM (Master Data Management) (M26) | September 30, 2024 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 311 | 448d | September 30, 2024 8:00 AM | December 30, 2025 5:00 PM | 313 days | No | 9/30/24 | NA | NA | 0.81999999999999995
11126 | Shared Services - MDM (Master Data Management) (M26) - Design | September 30, 2024 8:00 AM | October 3, 2025 5:00 PM | 934SS | 1344 | As Soon As Possible | NA | 254 | 0d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 9/30/24 | 10/3/25 | NA | 1
11127 | Shared Services - MDM (Master Data Management) (M26) - Build / SIT | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1343 | 1345FS-106d | As Soon As Possible | NA | 38 | 467d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
11372 | Shared Services - MDM (Master Data Management) (M26) - State QA | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1047SS,1344FS-106d |  | As Soon As Possible | NA | 19 | 448d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
11128 | Shared Services - Notifications (reminders, alerts) (M15) | August 14, 2023 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 538 | 505d | August 14, 2023 8:00 AM | February 28, 2025 5:00 PM | 387 days | No | 8/14/23 | NA | NA | 0.92000000000000004
11129 | Shared Services - Notifications (reminders, alerts) (M15) - Design | August 14, 2023 8:00 AM | July 12, 2024 5:00 PM | 430SS | 1348 | As Soon As Possible | NA | 229 | 0d | August 14, 2023 8:00 AM | July 12, 2024 5:00 PM | 229 days | No | 8/14/23 | 7/12/24 | NA | 1
11130 | Shared Services - Notifications (reminders, alerts) (M15) - Build / SIT | October 7, 2024 8:00 AM | August 8, 2025 5:00 PM | 433SS,1347 | 1349 | As Soon As Possible | NA | 210 | 0d | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM | 76 days | No | 10/7/24 | 8/8/25 | NA | 1
11373 | Shared Services - Notifications (reminders, alerts) (M15) - State QA | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 439SS,1348 |  | As Soon As Possible | NA | 39 | 505d | December 5, 2024 8:00 AM | February 28, 2025 5:00 PM | 58 days | No | NA | NA | NA | 0
11131 | Shared Services - Person Profile (M13) | October 21, 2024 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 277 | 467d | October 21, 2024 8:00 AM | December 30, 2025 5:00 PM | 298 days | No | 10/21/24 | NA | NA | 0.96999999999999997
11132 | Shared Services - Person Profile (M13) - Design | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 608SS | 1352 | As Soon As Possible | NA | 200 | 0d | October 21, 2024 8:00 AM | May 30, 2025 5:00 PM | 151 days | No | 10/21/24 | 8/8/25 | NA | 1
11133 | Shared Services - Person Profile (M13) - Build / SIT | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 709SS,1351 | 1353 | As Soon As Possible | NA | 39 | 32.3d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | NA | NA | 0.92000000000000004
11374 | Shared Services - Person Profile (M13) - State QA | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1352 |  | As Soon As Possible | NA | 38 | 467d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | 10/6/25 | NA | NA | 0.84999999999999998
11134 | Shared Services - Product Metrics (M23) | December 4, 2024 8:00 AM | February 4, 2026 1:48 PM |  |  | As Soon As Possible | NA | 292.6 | 422.4d | December 4, 2024 8:00 AM | December 30, 2025 5:00 PM | 269 days | No | 12/4/24 | NA | NA | 0.82999999999999996
11135 | Shared Services - Product Metrics (M23) - Design | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 1092SS | 1356 | As Soon As Possible | NA | 210 | 0d | December 4, 2024 8:00 AM | July 11, 2025 5:00 PM | 151 days | No | 12/4/24 | 10/3/25 | NA | 1
11136 | Shared Services - Product Metrics (M23) - Build / SIT | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1355 | 1357FS-127d | As Soon As Possible | NA | 38 | 164d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | NA | NA | NA | 0
11375 | Shared Services - Product Metrics (M23) - State QA | December 1, 2025 8:00 AM | February 4, 2026 1:48 PM | 1164SS,1356FS-127d |  | As Soon As Possible | NA | 19 | 422.4d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | 12/1/25 | NA | NA | 0.59999999999999998
11137 | Shared Services - Relationship Diagram (M13) | October 21, 2024 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 277 | 0d | October 21, 2024 8:00 AM | December 30, 2025 5:00 PM | 298 days | No | 10/21/24 | 11/28/25 | NA | 1
11138 | Shared Services - Relationship Diagram (M13) - Design | October 21, 2024 8:00 AM | May 30, 2025 5:00 PM | 608SS | 1360 | As Soon As Possible | NA | 151 | 0d | October 21, 2024 8:00 AM | May 30, 2025 5:00 PM | 151 days | No | 10/21/24 | 5/30/25 | NA | 1
11139 | Shared Services - Relationship Diagram (M13) - Build / SIT | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 709SS,1359 | 1361 | As Soon As Possible | NA | 39 | 0d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | 10/3/25 | NA | 1
11380 | Shared Services - Relationship Diagram (M13) - State QA | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1360 |  | As Soon As Possible | NA | 38 | 0d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | 10/6/25 | 11/28/25 | NA | 1
11140 | Shared Services - Scheduling & Coordination (M17) | August 15, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 155 | 0d | August 15, 2024 8:00 AM | December 30, 2025 5:00 PM | 345 days | No | 8/15/24 | 3/28/25 | NA | 1
11141 | Shared Services - Scheduling & Coordination (M17) - Design | August 15, 2024 8:00 AM | March 28, 2025 5:00 PM | 798SS |  | As Soon As Possible | NA | 155 | 0d | August 15, 2024 8:00 AM | March 28, 2025 5:00 PM | 155 days | No | 8/15/24 | 3/28/25 | NA | 1
11143 | Shared Services - Search (M23) | December 4, 2024 8:00 AM | March 2, 2026 3:00 PM |  |  | As Soon As Possible | NA | 309.75 | 405.25d | December 4, 2024 8:00 AM | December 30, 2025 5:00 PM | 269 days | No | 12/4/24 | NA | NA | 0.83999999999999997
11144 | Shared Services - Search (M23) - Design | December 4, 2024 8:00 AM | October 3, 2025 5:00 PM | 1092SS | 1366 | As Soon As Possible | NA | 210 | 0d | December 4, 2024 8:00 AM | July 11, 2025 5:00 PM | 151 days | No | 12/4/24 | 10/3/25 | NA | 1
11145 | Shared Services - Search (M23) - Build / SIT | December 29, 2025 8:00 AM | February 23, 2026 5:00 PM | 1144SS,1365 | 1367 | As Soon As Possible | NA | 38 | 0d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | NA | NA | NA | 0
11377 | Shared Services - Search (M23) - State QA | December 1, 2025 8:00 AM | March 2, 2026 3:00 PM | 1366 |  | As Soon As Possible | NA | 19 | 405.25d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | 12/1/25 | NA | NA | 0.75
11146 | Shared Services - Worker Mgmt./ Hierarchy (M26) | September 30, 2024 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 311 | 448d | September 30, 2024 8:00 AM | December 30, 2025 5:00 PM | 313 days | No | 9/30/24 | NA | NA | 0.77000000000000002
11147 | Shared Services - Worker Mgmt./ Hierarchy (M26) - Design | September 30, 2024 8:00 AM | October 3, 2025 5:00 PM | 934SS | 1370 | As Soon As Possible | NA | 254 | 448d | September 30, 2024 8:00 AM | March 28, 2025 5:00 PM | 123 days | No | 9/30/24 | NA | NA | 0.93999999999999995
11148 | Shared Services - Worker Mgmt./ Hierarchy (M26) - Build / SIT | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1011SS,1369 | 1371 | As Soon As Possible | NA | 38 | 448d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | NA | NA | NA | 0
11378 | Shared Services - Worker Mgmt./ Hierarchy (M26) - State QA | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1370 |  | As Soon As Possible | NA | 19 | 448d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
11149 | Shared Services - Workload View (M13) | October 21, 2024 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 277 | 467d | October 21, 2024 8:00 AM | December 30, 2025 5:00 PM | 298 days | No | 10/21/24 | NA | NA | 0.81000000000000005
11150 | Shared Services - Workload View (M13) - Design | October 21, 2024 8:00 AM | August 8, 2025 5:00 PM | 608SS | 1374 | As Soon As Possible | NA | 200 | 0d | October 21, 2024 8:00 AM | May 30, 2025 5:00 PM | 151 days | No | 10/21/24 | 8/8/25 | NA | 1
11151 | Shared Services - Workload View (M13) - Build / SIT | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 709SS,1373 | 1375 | As Soon As Possible | NA | 39 | 467d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 8/11/25 | NA | NA | 0.62
11379 | Shared Services - Workload View (M13) - State QA | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1374 |  | As Soon As Possible | NA | 38 | 467d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | NA | NA | NA | 0
12681 | Shared Services Admin Services | November 3, 2022 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 768 | 467d | NA | NA | 0 days? | No | 11/3/22 | NA | NA | 0.94999999999999996
12685 | RBAC Framework (SalesForce) | November 3, 2022 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 768 | 467d | NA | NA | 0 days? | No | 11/3/22 | NA | NA | 0.93000000000000005
12682 | Shared Services - RBAC Framework (SalesForce) - BRC | November 3, 2022 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 579 | 0d | NA | NA | 0 days? | No | 11/3/22 | 2/28/25 | NA | 1
12683 | Shared Services - RBAC Framework (SalesForce) - Design | May 5, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 1380 | Start No Earlier Than | 5/5/25 | 68 | 0d | NA | NA | 0 days? | No | 5/5/25 | 8/8/25 | NA | 1
12684 | Shared Services - RBAC Framework (SalesForce) - Build | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 1379 |  | As Soon As Possible | NA | 77 | 467d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.31
12679 | RBAC Framework (Tableau) | June 25, 2024 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 342 | 0d | NA | NA | 0 days? | No | 6/25/24 | NA | NA | 0.97999999999999998
12680 | Shared Services - RBAC Framework (Tableau) - BRC | June 25, 2024 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 277 | 0d | NA | NA | 0 days? | No | 6/25/24 | 7/31/25 | NA | 1
12678 | Shared Services - RBAC Framework (Tableau) - Design | November 1, 2024 8:00 AM | August 29, 2025 5:00 PM |  |  | As Soon As Possible | NA | 206 | 0d | NA | NA | 0 days? | No | 11/1/24 | 8/29/25 | NA | 1
12677 | Shared Services - RBAC Framework (Tableau) - Build | April 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 151 | 485d | NA | NA | 0 days? | No | 4/1/25 | NA | NA | 0.90000000000000002
7455 | Walkthrough Findings (M6, 8, 9, 14, 15) | July 15, 2024 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 452 | 80d | July 15, 2024 8:00 AM | May 1, 2026 5:00 PM | 452 days | No | 7/15/24 | NA | NA | 0.78000000000000003
7457 | Complete Build/SIT/QA of Walkthrough Findings - EUST 2 | July 15, 2024 8:00 AM | May 2, 2025 5:00 PM | 577SS-31d | 1387SS | Must Start On | 7/15/24 | 202 | 0d | July 15, 2024 8:00 AM | May 2, 2025 5:00 PM | 202 days | No | 7/15/24 | 5/2/25 | NA | 1
7456 | Complete Build/SIT/QA of Walkthrough Findings - EUST 3 | July 15, 2024 8:00 AM | May 1, 2026 5:00 PM | 1386SS | 1855 | Start No Earlier Than | 7/15/24 | 452 | 80d | July 15, 2024 8:00 AM | May 1, 2026 5:00 PM | 452 days | No | 7/15/24 | NA | NA | 0.68000000000000005
43871 | EUST 3 Build Drop Demos | May 30, 2025 8:00 AM | January 9, 2026 5:00 PM |  |  | As Soon As Possible | NA | 155 | 439d | NA | NA | 0 days? | No | 5/30/25 | NA | NA | 0.53000000000000003
43872 | BD 1 Demo | May 30, 2025 8:00 AM | June 19, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 0 days? | No | 5/30/25 | 6/19/25 | NA | 1
43873 | Conduct and Gather User Feedback | May 30, 2025 8:00 AM | June 5, 2025 5:00 PM | 616FS-1d |  | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 5/30/25 | 6/5/25 | NA | 1
43874 | Capture and Document in JIRA | May 30, 2025 8:00 AM | June 19, 2025 5:00 PM | 616FS-1d | 1393FS+14d | As Soon As Possible | NA | 15 | 0d | NA | NA | 0 days? | No | 5/30/25 | 6/19/25 | NA | 1
43875 | BD 2 Demo | July 11, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 0 days? | No | 7/11/25 | 7/31/25 | NA | 1
43876 | Conduct and Gather User Feedback | July 11, 2025 8:00 AM | July 17, 2025 5:00 PM | 1391FS+14d | 1394SS | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 7/11/25 | 7/17/25 | NA | 1
43877 | Capture and Document in JIRA | July 11, 2025 8:00 AM | July 31, 2025 5:00 PM | 1393SS | 1396FS+14d | As Soon As Possible | NA | 15 | 0d | NA | NA | 0 days? | No | 7/11/25 | 7/31/25 | NA | 1
43878 | BD 3 Demo | August 21, 2025 8:00 AM | September 19, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 8/21/25 | 9/19/25 | NA | 1
43867 | Conduct and Gather User Feedback | August 21, 2025 8:00 AM | September 3, 2025 5:00 PM | 1394FS+14d | 1397SS | As Soon As Possible | NA | 9 | 0d | NA | NA | 0 days? | No | 8/21/25 | 9/3/25 | NA | 1
43879 | Capture and Document in JIRA | August 21, 2025 8:00 AM | September 19, 2025 5:00 PM | 1396SS | 1399FS+20d | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 8/21/25 | 9/19/25 | NA | 1
43880 | BD 4 Demo | October 20, 2025 8:00 AM | November 14, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 439d | NA | NA | 0 days? | No | NA | NA | NA | 0
43881 | Conduct and Gather User Feedback | October 20, 2025 8:00 AM | October 31, 2025 5:00 PM | 1397FS+20d | 1400SS | As Soon As Possible | NA | 10 | 439d | NA | NA | 0 days? | No | NA | NA | NA | 0
43868 | Capture and Document in JIRA | October 20, 2025 8:00 AM | November 14, 2025 5:00 PM | 1399SS | 1402FS+14d | As Soon As Possible | NA | 19 | 439d | NA | NA | 0 days? | No | NA | NA | NA | 0
43869 | BD 5 Demo | December 8, 2025 8:00 AM | January 9, 2026 5:00 PM |  |  | As Soon As Possible | NA | 23 | 439d | NA | NA | 0 days? | No | NA | NA | NA | 0
43870 | Conduct and Gather User Feedback | December 8, 2025 8:00 AM | December 19, 2025 5:00 PM | 1400FS+14d | 1403SS | As Soon As Possible | NA | 10 | 439d | NA | NA | 0 days? | No | NA | NA | NA | 0
43865 | Capture and Document in JIRA | December 8, 2025 8:00 AM | January 9, 2026 5:00 PM | 1402SS |  | As Soon As Possible | NA | 23 | 439d | NA | NA | 0 days? | No | NA | NA | NA | 0
4273 | Interfaces | January 30, 2023 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 731 | 448d | January 30, 2023 8:00 AM | December 26, 2025 5:00 PM | 731 days | No | 1/30/23 | NA | NA | 0.95999999999999996
4274 | Milestone FCED 20.1 (M19/20/21/13) (CARESV1-45363) | January 30, 2023 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 731 | 448d | January 30, 2023 8:00 AM | December 26, 2025 5:00 PM | 731 days | No | 1/30/23 | NA | NA | 0.98999999999999999
4275 | Milestone FCED 20.1 - BRC | January 30, 2023 8:00 AM | October 4, 2024 5:00 PM | 674SS-500d | 1407 | Finish No Earlier Than | 10/4/24 | 425 | 0d | January 30, 2023 8:00 AM | October 4, 2024 5:00 PM | 425 days | No | 1/30/23 | 10/4/24 | NA | 1
4276 | Milestone FCED 20.1 - Design | August 14, 2023 8:00 AM | May 30, 2025 5:00 PM | 694SS-417d,1406 | 1408SS+19d | As Soon As Possible | NA | 196 | 0d | August 14, 2023 8:00 AM | May 30, 2025 5:00 PM | 196 days | No | 8/14/23 | 5/30/25 | NA | 1
4277 | Milestone FCED 20.1 - Build / SIT | September 11, 2023 8:00 AM | November 28, 2025 5:00 PM | 1407SS+19d | 1410 | As Soon As Possible | NA | 557 | 0d | September 11, 2023 8:00 AM | November 28, 2025 5:00 PM | 557 days | No | 9/11/23 | 11/28/25 | NA | 1
12833 | Milestone FCED 20.1 - QA Environment Build | November 11, 2024 8:00 AM | December 13, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 11/11/24 | 12/13/24 | NA | 1
4278 | Milestone FCED 20.1 - QA and End-to-End Testing | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1408 | 1411FF | As Soon As Possible | NA | 19 | 0d | October 7, 2024 8:00 AM | December 26, 2025 5:00 PM | 306 days | No | 12/1/25 | 12/26/25 | NA | 1
11587 | Milestone FCED 20.1 (M19/20/21/13) (CARESV1-45363) Complete | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 1410FF |  | As Soon As Possible | NA | 0 | 448d | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
4279 | Milestone JNET 15.1 (CARESV1-45367) | May 30, 2023 8:00 AM | December 6, 2024 5:00 PM |  |  | As Soon As Possible | NA | 384 | 0d | May 30, 2023 8:00 AM | December 6, 2024 5:00 PM | 384 days | No | 5/30/23 | 12/6/24 | NA | 1
4280 | Milestone JNET 15.1 - BRC | May 30, 2023 8:00 AM | July 31, 2024 5:00 PM | 426SS-2d | 1414 | Finish No Earlier Than | 1/26/24 | 295 | 0d | May 30, 2023 8:00 AM | July 31, 2024 5:00 PM | 295 days | No | 5/30/23 | 7/31/24 | NA | 1
4281 | Milestone JNET 15.1 - Design | January 29, 2024 8:00 AM | August 30, 2024 8:58 AM | 1413,431SS+113d | 1415SS+39d | Finish No Earlier Than | 3/22/24 | 57 | 0d | January 29, 2024 8:00 AM | August 30, 2024 8:58 AM | 57 days | No | 1/29/24 | 8/30/24 | NA | 1
4282 | Milestone JNET 15.1 - Build / SIT | March 25, 2024 8:00 AM | November 1, 2024 5:00 PM | 1414SS+39d | 1416SS+58d | As Soon As Possible | NA | 157 | 0d | March 25, 2024 8:00 AM | November 1, 2024 5:00 PM | 157 days | No | 3/25/24 | 11/1/24 | NA | 1
4283 | Milestone JNET 15.1 - QA and End-to-End Testing | June 17, 2024 8:00 AM | December 6, 2024 5:00 PM | 1415SS+58d | 1417FF | Finish No Earlier Than | 12/6/24 | 121 | 0d | June 17, 2024 8:00 AM | December 6, 2024 5:00 PM | 121 days | No | 6/17/24 | 12/6/24 | NA | 1
11588 | Milestone JNET 15.1 (CARESV1-45367) Complete | December 6, 2024 8:00 AM | December 6, 2024 5:00 PM | 1416FF |  | Finish No Earlier Than | 12/6/24 | 1 | 0d | December 6, 2024 5:00 PM | December 6, 2024 5:00 PM | 0 s | No | 12/6/24 | 12/6/24 | NA | 1
4284 | Milestone CMA 7.1 (CARESV1-45369) | May 24, 2024 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 343 | 505d | May 24, 2024 8:00 AM | December 26, 2025 5:00 PM | 400 days | No | 5/24/24 | NA | NA | 0.87
4285 | Milestone CMA 7.1 - BRC | May 24, 2024 8:00 AM | October 31, 2024 5:00 PM | 668SS+63d | 1420FS-25d | As Soon As Possible | NA | 113 | 0d | May 24, 2024 8:00 AM | October 31, 2024 5:00 PM | 113 days | No | 5/24/24 | 10/31/24 | NA | 1
4286 | Milestone CMA 7.1 - Design | October 7, 2024 8:00 AM | March 21, 2025 5:00 PM | 687SS+58d,1419FS-25d | 1421FS+68d | As Soon As Possible | NA | 113 | 0d | October 7, 2024 8:00 AM | March 21, 2025 5:00 PM | 113 days | No | 10/7/24 | 3/21/25 | NA | 1
4287 | Milestone CMA 7.1 - Build / SIT | June 30, 2025 8:00 AM | August 8, 2025 5:00 PM | 1420FS+68d | 1422 | As Soon As Possible | NA | 29 | 1.56d | March 24, 2025 8:00 AM | November 28, 2025 5:00 PM | 174 days | No | 6/30/25 | NA | NA | 0.97999999999999998
4288 | Milestone CMA 7.1 - QA and End-to-End Testing | August 11, 2025 8:00 AM | October 3, 2025 5:00 PM | 1421 | 1423 | As Soon As Possible | NA | 39 | 505d | May 19, 2025 8:00 AM | December 26, 2025 5:00 PM | 154 days | No | 8/11/25 | NA | NA | 4.0000000000000001E-2
11589 | Milestone CMA 7.1 (CARESV1-45369) Complete | October 3, 2025 5:00 PM | October 3, 2025 5:00 PM | 1422 |  | As Soon As Possible | NA | 0 | 505d | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
4289 | Milestone (LIS/FAS data) 26.1 (CARESV1-45375) | July 15, 2024 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 366 | 448d | July 15, 2024 8:00 AM | November 28, 2025 5:00 PM | 347 days | No | 7/15/24 | NA | NA | 0.72999999999999998
4290 | Milestone (LIS/FAS data) 26.1 - BRC | July 15, 2024 8:00 AM | October 25, 2024 5:00 PM | 979SS+77d |  | Finish No Earlier Than | 7/8/24 | 75 | 0d | July 15, 2024 8:00 AM | October 25, 2024 5:00 PM | 75 days | No | 7/15/24 | 10/25/24 | NA | 1
4291 | Milestone (LIS/FAS data) 26.1 - Design | March 3, 2025 8:00 AM | October 3, 2025 5:00 PM |  | 1427 | Start No Earlier Than | 3/3/25 | 151 | -7d | October 28, 2024 8:00 AM | March 7, 2025 5:00 PM | 88 days | No | 3/3/25 | NA | NA | 0.85999999999999999
4292 | Milestone (LIS/FAS data) 26.1 - Build / SIT | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1426 | 1428,4644 | Finish No Earlier Than | 11/3/25 | 38 | -7d | April 21, 2025 8:00 AM | November 7, 2025 5:00 PM | 142 days | No | NA | NA | NA | 0
4293 | Milestone (LIS/FAS data) 26.1 - QA and End-to-End Testing | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1427 | 1429FF | Start No Earlier Than | 2/24/25 | 19 | 448d | April 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 149 days | No | 12/1/25 | NA | NA | 8.0000000000000002E-2
11590 | Milestone (LIS/FAS data) 26.1 (CARESV1-45375) Complete | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 1428FF |  | Start No Earlier Than | 2/24/25 | 0 | 448d | November 28, 2025 5:00 PM | November 28, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
4294 | Milestone CECRIS 23.2 (CARESV1-45376) | July 15, 2024 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 366 | 448d | July 15, 2024 8:00 AM | October 31, 2025 5:00 PM | 329 days | No | 7/15/24 | NA | NA | 0.79000000000000004
4295 | Milestone CECRIS 23.2 - BRC | July 15, 2024 8:00 AM | October 18, 2024 5:00 PM | 1125FF | 1432 | As Soon As Possible | NA | 70 | 0d | July 15, 2024 8:00 AM | October 18, 2024 5:00 PM | 70 days | No | 7/15/24 | 10/18/24 | NA | 1
4296 | Milestone CECRIS 23.2 - Design | March 10, 2025 8:00 AM | October 3, 2025 5:00 PM | 1136SS,1431 | 1433 | Finish No Earlier Than | 6/27/25 | 146 | 0d | March 10, 2025 8:00 AM | June 27, 2025 5:00 PM | 78 days | No | 3/10/25 | 10/3/25 | NA | 1
4297 | Milestone CECRIS 23.2 - Build / SIT | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1432 | 1434,523FF+21d | Finish No Earlier Than | 10/31/25 | 38 | 446d | May 19, 2025 8:00 AM | October 31, 2025 5:00 PM | 117 days | No | NA | NA | NA | 0
4298 | Milestone CECRIS 23.2 - QA and End-to-End Testing | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 1433 | 1435 | Finish No Earlier Than | 10/31/25 | 19 | 448d | June 16, 2025 8:00 AM | October 31, 2025 5:00 PM | 98 days | No | NA | NA | NA | 0
11591 | Milestone CECRIS 23.2 (CARESV1-45376) Complete | December 26, 2025 5:00 PM | December 26, 2025 5:00 PM | 1434 |  | As Soon As Possible | NA | 0 | 448d | June 16, 2025 8:00 AM | October 31, 2025 5:00 PM | 98 days | Yes | NA | NA | NA | 0
6814 | Milestone 10.1: Structured Decision Making (SDM) (CARESV1-27260) | April 24, 2023 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 616 | 505d | April 24, 2023 8:00 AM | July 11, 2025 5:00 PM | 557 days | No | 4/24/23 | NA | NA | 0.96999999999999997
6815 | M10.1: Research & Context Setting | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 134 | 0d | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 134 days | No | 4/24/23 | 10/31/23 | NA | 1
6816 | M10.1: RC: Finalize Value Hypothesis | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM |  | 1439SS | Must Start On | 4/24/23 | 134 | 0d | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 134 days | No | 4/24/23 | 10/31/23 | NA | 1
6817 | M10.1: RC: Draft Service Maps | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 1438SS | 1440SS | As Soon As Possible | NA | 134 | 0d | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 134 days | No | 4/24/23 | 10/31/23 | NA | 1
6818 | M10.1: RC: Complete Legacy Analysis | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 1439SS | 1441SS | As Soon As Possible | NA | 134 | 0d | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 134 days | No | 4/24/23 | 10/31/23 | NA | 1
6819 | M10.1: RC: Finalize Epics | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 1440SS | 1442SS | As Soon As Possible | NA | 134 | 0d | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 134 days | No | 4/24/23 | 10/31/23 | NA | 1
6820 | M10.1: RC: Complete conceptual and epic-level Domain Model diagrams | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 1441SS | 1443SS | As Soon As Possible | NA | 134 | 0d | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 134 days | No | 4/24/23 | 10/31/23 | NA | 1
6821 | M10.1: RC: Define User Story titles | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 1442SS | 1444SS | As Soon As Possible | NA | 134 | 0d | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 134 days | No | 4/24/23 | 10/31/23 | NA | 1
6822 | M10.1: RC: Complete External Systems pre-analysis | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 1443SS | 1445SS | As Soon As Possible | NA | 134 | 0d | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 134 days | No | 4/24/23 | 10/31/23 | NA | 1
6823 | M10.1: RC: Facilitate Inception | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 1444SS | 1447FS-17d | As Soon As Possible | NA | 134 | 0d | April 24, 2023 8:00 AM | October 31, 2023 5:00 PM | 134 days | No | 4/24/23 | 10/31/23 | NA | 1
6786 | M10.1: BRC | October 9, 2023 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 203 | 0d | October 9, 2023 8:00 AM | July 31, 2024 5:00 PM | 203 days | No | 10/9/23 | 7/31/24 | NA | 1
6787 | M10.1: B1 Structured Decision Making (SDM) Interface - Hotline Assessment (CARESV1-4194) | October 9, 2023 8:00 AM | July 31, 2024 5:00 PM | 1445FS-17d | 1448SS,2266SS | As Soon As Possible | NA | 203 | 0d | October 9, 2023 8:00 AM | July 31, 2024 5:00 PM | 203 days | No | 10/9/23 | 7/31/24 | NA | 1
6788 | M10.1: B2 Structured Decision Making (SDM) Interface - Risk (1) and Safety (3) Assessments (CARESV1-13933) | October 9, 2023 8:00 AM | July 31, 2024 5:00 PM | 1447SS | 1449SS | As Soon As Possible | NA | 203 | 0d | October 9, 2023 8:00 AM | July 31, 2024 5:00 PM | 203 days | No | 10/9/23 | 7/31/24 | NA | 1
6789 | M10.1: B3 Structured Decision Making (SDM) Interface - Reunification Assessment and Risk Reassessment (CARESV1-13934) | October 9, 2023 8:00 AM | July 31, 2024 5:00 PM | 1448SS | 1451FS+5d | As Soon As Possible | NA | 203 | 0d | October 9, 2023 8:00 AM | July 31, 2024 5:00 PM | 203 days | No | 10/9/23 | 7/31/24 | NA | 1
6790 | M10.1: Design | May 24, 2024 8:00 AM | April 11, 2025 5:00 PM |  |  | As Soon As Possible | NA | 221 | 0d | May 24, 2024 8:00 AM | April 11, 2025 5:00 PM | 221 days | No | 5/24/24 | 4/11/25 | NA | 1
6791 | M10.1: B1 Structured Decision Making (SDM) Interface - Hotline Assessment (CARESV1-4194) | May 24, 2024 8:00 AM | April 11, 2025 10:29 AM | 1449FS+5d | 1452SS,2267SS | As Soon As Possible | NA | 220 | 0d | May 24, 2024 8:00 AM | April 11, 2025 10:29 AM | 220 days | No | 5/24/24 | 4/11/25 | NA | 1
6792 | M10.1: B2 Structured Decision Making (SDM) Interface - Risk (1) and Safety (3) Assessments (CARESV1-13933) | May 24, 2024 8:00 AM | April 11, 2025 5:00 PM | 1451SS | 1453SS | As Soon As Possible | NA | 221 | 0d | May 24, 2024 8:00 AM | April 11, 2025 5:00 PM | 221 days | No | 5/24/24 | 4/11/25 | NA | 1
6793 | M10.1: B3 Structured Decision Making (SDM) Interface - Reunification Assessment and Risk Reassessment (CARESV1-13934) | May 24, 2024 8:00 AM | April 11, 2025 5:00 PM | 1452SS | 1455FS-64d | As Soon As Possible | NA | 221 | 0d | May 24, 2024 8:00 AM | April 11, 2025 5:00 PM | 221 days | No | 5/24/24 | 4/11/25 | NA | 1
6456 | M10.1: Build | January 6, 2025 8:00 AM | June 27, 2025 5:00 PM |  |  | As Soon As Possible | NA | 121 | 0d | January 6, 2025 8:00 AM | June 13, 2025 5:00 PM | 111 days | No | 1/6/25 | 6/27/25 | NA | 1
6457 | M10.1: B1 Structured Decision Making (SDM) Interface - Hotline Assessment (CARESV1-4194) | January 6, 2025 8:00 AM | June 27, 2025 5:00 PM | 1453FS-64d | 1456SS,2268SS | Must Start On | 1/6/25 | 121 | 0d | January 6, 2025 8:00 AM | June 13, 2025 5:00 PM | 111 days | No | 1/6/25 | 6/27/25 | NA | 1
6458 | M10.1: B2 Structured Decision Making (SDM) Interface - Risk (1) and Safety (3) Assessments (CARESV1-13933) | January 6, 2025 8:00 AM | June 27, 2025 5:00 PM | 1455SS | 1457SS | As Soon As Possible | NA | 121 | 0d | January 6, 2025 8:00 AM | June 13, 2025 5:00 PM | 111 days | No | 1/6/25 | 6/27/25 | NA | 1
6459 | M10.1: B3 Structured Decision Making (SDM) Interface - Reunification Assessment and Risk Reassessment (CARESV1-13934) | January 6, 2025 8:00 AM | June 27, 2025 5:00 PM | 1456SS | 1459SS | As Soon As Possible | NA | 121 | 0d | January 6, 2025 8:00 AM | June 13, 2025 5:00 PM | 111 days | No | 1/6/25 | 6/27/25 | NA | 1
6463 | M10.1: SIT | January 6, 2025 8:00 AM | June 27, 2025 5:00 PM |  |  | As Soon As Possible | NA | 121 | 0d | January 6, 2025 8:00 AM | June 13, 2025 5:00 PM | 111 days | No | 1/6/25 | 6/27/25 | NA | 1
6464 | M10.1: B1 Structured Decision Making (SDM) Interface - Hotline Assessment (CARESV1-4194) | January 6, 2025 8:00 AM | June 27, 2025 5:00 PM | 1457SS | 1460SS | As Soon As Possible | NA | 121 | 0d | January 6, 2025 8:00 AM | June 13, 2025 5:00 PM | 111 days | No | 1/6/25 | 6/27/25 | NA | 1
6465 | M10.1: B2 Structured Decision Making (SDM) Interface - Risk (1) and Safety (3) Assessments (CARESV1-13933) | January 6, 2025 8:00 AM | June 27, 2025 5:00 PM | 1459SS | 1461SS | As Soon As Possible | NA | 121 | 0d | January 6, 2025 8:00 AM | June 13, 2025 5:00 PM | 111 days | No | 1/6/25 | 6/27/25 | NA | 1
6466 | M10.1: B3 Structured Decision Making (SDM) Interface - Reunification Assessment and Risk Reassessment (CARESV1-13934) | January 6, 2025 8:00 AM | June 27, 2025 5:00 PM | 1460SS | 1463SS | As Soon As Possible | NA | 121 | 0d | January 6, 2025 8:00 AM | June 13, 2025 5:00 PM | 111 days | No | 1/6/25 | 6/27/25 | NA | 1
6470 | M10.1: State QA | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 189 | 505d | January 6, 2025 8:00 AM | July 11, 2025 5:00 PM | 130 days | No | 1/6/25 | NA | NA | 0.95999999999999996
6471 | M10.1: B1 Structured Decision Making (SDM) Interface - Hotline Assessment (CARESV1-4194) | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 1461SS | 1464SS,1467SS | As Soon As Possible | NA | 189 | 0d | January 6, 2025 8:00 AM | July 11, 2025 5:00 PM | 130 days | No | 1/6/25 | 10/3/25 | NA | 1
6472 | M10.1: B2 Structured Decision Making (SDM) Interface - Risk (1) and Safety (3) Assessments (CARESV1-13933) | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 1463SS | 1465SS | As Soon As Possible | NA | 189 | 505d | January 6, 2025 8:00 AM | July 11, 2025 5:00 PM | 130 days | No | 1/6/25 | NA | NA | 0.95999999999999996
6473 | M10.1: B3 Structured Decision Making (SDM) Interface - Reunification Assessment and Risk Reassessment (CARESV1-13934) | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 1464SS | 1469FF | As Soon As Possible | NA | 189 | 505d | January 6, 2025 8:00 AM | July 11, 2025 5:00 PM | 130 days | No | 1/6/25 | NA | NA | 0.92000000000000004
6477 | M10.1: Joint Review | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 189 | 505d | January 6, 2025 8:00 AM | July 11, 2025 5:00 PM | 130 days | No | 1/6/25 | NA | NA | 0.83999999999999997
6478 | M10.1: B1 Structured Decision Making (SDM) Interface - Hotline Assessment (CARESV1-4194) | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 1463SS | 1468SS | As Soon As Possible | NA | 189 | 0d | January 6, 2025 8:00 AM | July 11, 2025 5:00 PM | 130 days | No | 1/6/25 | 10/3/25 | NA | 1
6479 | M10.1: B2 Structured Decision Making (SDM) Interface - Risk (1) and Safety (3) Assessments (CARESV1-13933) | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 1467SS | 1469SS | As Soon As Possible | NA | 189 | 505d | January 6, 2025 8:00 AM | July 11, 2025 5:00 PM | 130 days | No | 1/6/25 | NA | NA | 0.92000000000000004
6480 | M10.1: B3 Structured Decision Making (SDM) Interface - Reunification Assessment and Risk Reassessment (CARESV1-13934) | January 6, 2025 8:00 AM | October 3, 2025 5:00 PM | 1468SS,1465FF | 1470 | As Soon As Possible | NA | 189 | 505d | January 6, 2025 8:00 AM | July 11, 2025 5:00 PM | 130 days | No | 1/6/25 | NA | NA | 0.58999999999999997
11592 | Milestone 10.1: Structured Decision Making (SDM) (CARESV1-27260) Complete | October 3, 2025 5:00 PM | October 3, 2025 5:00 PM | 1469 |  | As Soon As Possible | NA | 0 | 505d | July 11, 2025 5:00 PM | July 11, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
4299 | Hardening | September 4, 2023 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 562 | 466d | September 4, 2023 8:00 AM | December 1, 2025 5:00 PM | 562 days | No | 9/4/23 | NA | NA | 0.75
4300 | H1 (Hardening - 3, 4, 5) | September 4, 2023 8:00 AM | September 29, 2023 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | September 4, 2023 8:00 AM | September 29, 2023 5:00 PM | 19 days | No | 9/4/23 | 9/29/23 | NA | 1
4301 | H1 - Conduct Hardening | September 4, 2023 8:00 AM | September 29, 2023 5:00 PM |  | 1484 | As Soon As Possible | NA | 20 | 0d | September 4, 2023 8:00 AM | September 29, 2023 5:00 PM | 20 days | No | 9/4/23 | 9/29/23 | NA | 1
4305 | H2 (Hardening - 1, 2, 6, 8, 15, 15.1, 19, 20) | June 17, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 137 | 0d | June 17, 2024 8:00 AM | December 31, 2024 5:00 PM | 137 days | No | 6/17/24 | 12/31/24 | NA | 1
4306 | H2 Re-work (Conduct Hardening) | June 17, 2024 8:00 AM | December 31, 2024 5:00 PM | 20,45,234,279,788,790 | 2987,2990,3000 | Start No Earlier Than | 6/17/24 | 137 | 0d | June 17, 2024 8:00 AM | December 31, 2024 5:00 PM | 137 days | No | 6/17/24 | 12/31/24 | NA | 1
5413 | H2 EUST Backlog (Resolve Prior EUST Findings) | June 17, 2024 8:00 AM | December 31, 2024 5:00 PM | 568,571FS-19d | 1477SS+38d | As Soon As Possible | NA | 137 | 0d | June 17, 2024 8:00 AM | December 31, 2024 5:00 PM | 137 days | No | 6/17/24 | 12/31/24 | NA | 1
11625 | H2 Re-skin of EUST-2 Milestones (1, 2, 3, 4, 5, 6, 8, 15, 19, 20) | August 12, 2024 8:00 AM | October 30, 2024 5:00 PM | 1476SS+38d | 5296FS+2d | As Soon As Possible | NA | 58 | 0d | NA | NA | 0 days? | No | 8/12/24 | 10/30/24 | NA | 1
4311 | H3 (Hardening - 6.1, 7, 7.1, 9, 10, 10.1, 11, 13, 14, 16, 17, 18, 20.1, 21, 23, 23.1, 23.2, 24, 26, 26.1, 27, 28) | July 14, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 98 | 466d | July 14, 2025 8:00 AM | December 1, 2025 5:00 PM | 98 days | No | 7/14/25 | NA | NA | 0.45000000000000001
4312 | H3 Re-work (Conduct Hardening) | July 14, 2025 8:00 AM | December 1, 2025 5:00 PM | 345 | 2988,2991,2992,3001,3003,3004,3005 | Start No Earlier Than | 7/14/25 | 98 | -17d | July 14, 2025 8:00 AM | December 1, 2025 5:00 PM | 98 days | No | 7/14/25 | NA | NA | 0.45000000000000001
5478 | H3 EUST Backlog (Resolve Prior EUST Findings) | July 14, 2025 8:00 AM | December 1, 2025 5:00 PM | 707FF,735FF,717FF,745FF,713FF,741FF,878FF,893FF | 1481SS | Start No Earlier Than | 7/14/25 | 98 | 466d | July 14, 2025 8:00 AM | December 1, 2025 5:00 PM | 98 days | No | 7/14/25 | NA | NA | 0.45000000000000001
11626 | H3 Re-skin of EUST-3 Milestones (1, 9, 10, 14, 21) | July 14, 2025 8:00 AM | December 1, 2025 5:00 PM | 1480SS |  | As Soon As Possible | NA | 98 | 466d | NA | NA | 0 days? | No | 7/14/25 | NA | NA | 0.45000000000000001
2858 | EUST (Extended User Scenario Testing) / Validation Sprints in CARES V1 | February 1, 2024 8:00 AM | July 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 613 | 314d? | February 1, 2024 8:00 AM | July 10, 2026 5:00 PM | 519 days | No | 2/1/24 | NA | NA | 0.45000000000000001
2859 | EUST - 1 | February 1, 2024 8:00 AM | April 11, 2024 5:00 PM |  |  | As Soon As Possible | NA | 49 | 0d | February 1, 2024 8:00 AM | April 11, 2024 5:00 PM | 39 days | No | 2/1/24 | 4/11/24 | NA | 1
2860 | EUST for Milestones 3, 4, and 5 | February 1, 2024 8:00 AM | April 11, 2024 5:00 PM | 87FF,133FF,189FF,98,144,204,1473,2483,2490 | 1485SS+30d | Finish No Earlier Than | 4/11/24 | 49 | 0d | February 1, 2024 8:00 AM | April 11, 2024 5:00 PM | 39 days | No | 2/1/24 | 4/11/24 | NA | 1
6926 | EUST 1 - Triage/Prioritize Findings | March 15, 2024 8:00 AM | April 11, 2024 5:00 PM | 1484SS+30d | 1486SS | As Soon As Possible | NA | 19 | 0d | March 15, 2024 8:00 AM | April 11, 2024 5:00 PM | 39 days | No | 3/15/24 | 4/11/24 | NA | 1
6927 | EUST 1 - Build/SIT Findings | March 15, 2024 8:00 AM | April 11, 2024 5:00 PM | 1485SS | 1487SS | As Soon As Possible | NA | 19 | 0d | March 15, 2024 8:00 AM | April 11, 2024 5:00 PM | 19 days | No | 3/15/24 | 4/11/24 | NA | 1
6928 | EUST 1 - QA Findings | March 15, 2024 8:00 AM | April 11, 2024 5:00 PM | 1486SS |  | As Soon As Possible | NA | 19 | 0d | March 15, 2024 8:00 AM | April 11, 2024 5:00 PM | 10 days | No | 3/15/24 | 4/11/24 | NA | 1
2861 | EUST - 2 | October 4, 2024 8:00 AM | June 10, 2025 5:00 PM |  |  | As Soon As Possible | NA | 169 | 0d | November 4, 2024 8:00 AM | May 5, 2025 5:00 PM | 123 days | No | 10/4/24 | 6/10/25 | NA | 1
12689 | EUST 2 - Admin | October 4, 2024 8:00 AM | November 8, 2024 5:00 PM |  |  | As Soon As Possible | NA | 26 | 0d | NA | NA | 0 days? | No | 10/4/24 | 11/8/24 | NA | 1
12690 | Develop EUST 2 timeline and assign roles with team | October 24, 2024 8:00 AM | November 8, 2024 5:00 PM |  |  | As Soon As Possible | NA | 12 | 0d | NA | NA | 0 days? | No | 10/24/24 | 11/8/24 | NA | 1
12688 | Create MS Teams space for EUST | October 21, 2024 8:00 AM | October 25, 2024 5:00 PM |  |  | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 10/21/24 | 10/25/24 | NA | 1
12687 | Update Confluence space for EUST 2 | October 4, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 10/4/24 | 10/31/24 | NA | 1
4841 | EUST 2 - Preparation | October 22, 2024 8:00 AM | March 21, 2025 5:00 PM |  |  | As Soon As Possible | NA | 102 | 0d | November 4, 2024 8:00 AM | March 18, 2025 5:00 PM | 90 days | No | 10/22/24 | 3/21/25 | NA | 1
4842 | EUST 2 - Identification and validation of scenarios | October 22, 2024 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 87 | 0d | November 4, 2024 8:00 AM | December 30, 2024 5:00 PM | 37 days | No | 10/22/24 | 2/28/25 | NA | 1
12695 | Validation of all EUST 2 stories marked as BRC and tagged EUST 2 Scope | November 1, 2024 8:00 AM | November 1, 2024 5:00 PM | 499SS-1d | 1496 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 11/1/24 | 11/1/24 | NA | 1
12696 | Identify scenarios that must be excluded from EUST 2 | November 4, 2024 8:00 AM | November 7, 2024 5:00 PM | 1495 | 1501 | As Soon As Possible | NA | 4 | 0d | NA | NA | 0 days? | No | 11/4/24 | 11/7/24 | NA | 1
12699 | Send communication to Service Managers, SMEs and interface partners around scenario writing workshops | October 22, 2024 8:00 AM | October 22, 2024 5:00 PM |  |  | Start No Earlier Than | 10/22/24 | 1 | 0d | NA | NA | 0 s? | No | 10/22/24 | 10/22/24 | NA | 1
12700 | Schedule EUST 2 scenario writing workgroups based on Milestone | October 30, 2024 8:00 AM | November 1, 2024 5:00 PM |  | 1500 | Start No Earlier Than | 10/30/24 | 3 | 0d | NA | NA | 0 days? | No | 10/30/24 | 11/1/24 | NA | 1
12701 | Prepare template for scenarios, includes mapping to specific functionality | November 1, 2024 8:00 AM | November 7, 2024 5:00 PM |  |  | Start No Earlier Than | 11/1/24 | 5 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/7/24 | NA | 1
12702 | Validate and document all personas for EUST 2 | November 4, 2024 8:00 AM | November 4, 2024 5:00 PM | 1498 |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 11/4/24 | 11/4/24 | NA | 1
12703 | Begin scenario writing process | November 8, 2024 8:00 AM | November 8, 2024 5:00 PM | 1496 | 1502,1503 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 11/8/24 | 11/8/24 | NA | 1
12704 | Conduct scenario writing workgroups | November 12, 2024 8:00 AM | December 5, 2024 5:00 PM | 1501 |  | As Soon As Possible | NA | 16 | 0d | NA | NA | 0 days? | No | 11/12/24 | 12/5/24 | NA | 1
12697 | Perform PDL validation of scenarios | November 12, 2024 8:00 AM | December 5, 2024 5:00 PM | 1501 | 1504 | As Soon As Possible | NA | 16 | 0d | NA | NA | 0 days? | No | 11/12/24 | 12/5/24 | NA | 1
12698 | Distribute drafts to Leadership for review | December 6, 2024 8:00 AM | December 12, 2024 5:00 PM | 1503 | 1505 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 12/6/24 | 12/12/24 | NA | 1
12693 | Incorporate feedback from leadership | December 13, 2024 8:00 AM | December 19, 2024 5:00 PM | 1504 | 1506 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 12/13/24 | 12/19/24 | NA | 1
12694 | Finalize scenarios and validate with SM | December 20, 2024 8:00 AM | December 27, 2024 5:00 PM | 1505 | 1507FS+17d | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 12/20/24 | 12/27/24 | NA | 1
12692 | Execute scenarios for EUST (trial run) | January 24, 2025 8:00 AM | February 28, 2025 5:00 PM | 1506FS+17d |  | As Soon As Possible | NA | 25 | 0d | NA | NA | 0 days? | No | 1/24/25 | 2/28/25 | NA | 1
4844 | EUST 2 - User setup and access validation | November 7, 2024 8:00 AM | March 10, 2025 5:00 PM |  |  | As Soon As Possible | NA | 81 | 0d | January 24, 2025 8:00 AM | March 18, 2025 5:00 PM | 37 days | No | 11/7/24 | 3/10/25 | NA | 1
12709 | Establish date the communications should be sent to CC SPOC to identify users | November 7, 2024 8:00 AM | November 14, 2024 5:00 PM |  | 1510SS | Start No Earlier Than | 11/7/24 | 5 | 0d | NA | NA | 0 days? | No | 11/7/24 | 11/14/24 | NA | 1
12710 | Confirm w/SPOC the users who participated in UF are still available to perform validation | November 7, 2024 8:00 AM | November 7, 2024 5:00 PM | 1509SS |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 11/7/24 | 11/7/24 | NA | 1
12711 | Draft communication to send to all counties requesting EUST participation | November 8, 2024 8:00 AM | November 15, 2024 5:00 PM |  | 1512 | Start No Earlier Than | 11/8/24 | 5 | 0d | NA | NA | 0 days? | No | 11/8/24 | 11/15/24 | NA | 1
12712 | Send communication to ELT for approval | November 18, 2024 8:00 AM | November 22, 2024 5:00 PM | 1511 | 1513 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 11/18/24 | 11/22/24 | NA | 1
12713 | Send communication to all counties for participation in EUST 2 | November 25, 2024 8:00 AM | November 25, 2024 5:00 PM | 1512 | 1514SS,1517FS+8d,1518FS+8d,1519FS+8d | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 11/25/24 | 11/25/24 | NA | 1
12714 | Schedule EUTS overview/Q&A meeting for counties | November 25, 2024 8:00 AM | November 25, 2024 5:00 PM | 1513SS |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 11/25/24 | 11/25/24 | NA | 1
12715 | Hold EUST 2 overview meeting option 1 | December 6, 2024 8:00 AM | December 6, 2024 5:00 PM |  | 1516 | Start No Earlier Than | 12/6/24 | 1 | 0d | NA | NA | 0 s? | No | 12/6/24 | 12/6/24 | NA | 1
12716 | Hold EUST 2 overview meeting option 2 | December 9, 2024 8:00 AM | December 9, 2024 5:00 PM | 1515 |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 12/9/24 | 12/9/24 | NA | 1
12707 | Document county participants in EUST 2 | December 10, 2024 8:00 AM | January 7, 2025 5:00 PM | 1513FS+8d | 1521FS-1d | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 12/10/24 | 1/7/25 | NA | 1
12708 | Add new users to spreadsheet: Users by County | December 10, 2024 8:00 AM | January 7, 2025 5:00 PM | 1513FS+8d |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 12/10/24 | 1/7/25 | NA | 1
12705 | Add county participants to Microsoft Teams Space for EUST 2 Feedback | December 10, 2024 8:00 AM | March 10, 2025 5:00 PM | 1513FS+8d |  | As Soon As Possible | NA | 61 | 0d | NA | NA | 0 days? | No | 12/10/24 | 3/10/25 | NA | 1
12706 | User Provisioning | January 7, 2025 8:00 AM | March 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 38 | 0d | NA | NA | 0 days? | No | 1/7/25 | 3/3/25 | NA | 1
12719 | Provision users to EUST environment | January 7, 2025 8:00 AM | January 28, 2025 5:00 PM | 1517FS-1d | 1522FS-1d | As Soon As Possible | NA | 15 | 0d | NA | NA | 0 days? | No | 1/7/25 | 1/28/25 | NA | 1
12720 | Coordinate with OKTA to complete IP whitelisting for counties in EUST | January 28, 2025 8:00 AM | February 18, 2025 5:00 PM | 1521FS-1d | 1523SS | As Soon As Possible | NA | 15 | 0d | NA | NA | 0 days? | No | 1/28/25 | 2/18/25 | NA | 1
12721 | Confirm User Set up w/OKTA team | January 28, 2025 8:00 AM | February 3, 2025 5:00 PM | 1522SS | 1524FS-1d | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 1/28/25 | 2/3/25 | NA | 1
12722 | Assign Profile, Permissions and complete user set up/complete spreadsheet | February 3, 2025 8:00 AM | February 14, 2025 5:00 PM | 1523FS-1d | 1525FS-1d | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/14/25 | NA | 1
12718 | Receive communication from OKTA team that user set up is complete and active | February 14, 2025 8:00 AM | February 28, 2025 5:00 PM | 1524FS-1d | 1526 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 2/14/25 | 2/28/25 | NA | 1
12723 | Communicate to end users and confirm access (CC SPOC) or if they need a PW reset | March 3, 2025 8:00 AM | March 3, 2025 5:00 PM | 1525 |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 3/3/25 | 3/3/25 | NA | 1
12717 | EUST 2 Infrastructure / Environment Setup | October 28, 2024 8:00 AM | March 14, 2025 5:00 PM |  |  | As Soon As Possible | NA | 93 | 0d | NA | NA | 0 days? | No | 10/28/24 | 3/14/25 | NA | 1
12732 | Set up Salesforce EUST environment | October 28, 2024 8:00 AM | October 28, 2024 5:00 PM |  | 1529SS | Start No Earlier Than | 10/28/24 | 1 | 0d | NA | NA | 0 s? | No | 10/28/24 | 10/28/24 | NA | 1
12733 | Setup Okta Integration | October 28, 2024 8:00 AM | October 28, 2024 5:00 PM | 1528SS | 1541SS | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 10/28/24 | 10/28/24 | NA | 1
12734 | Mule Integration Setup | November 12, 2024 8:00 AM | November 15, 2024 5:00 PM |  | 1539,1531,1532,1533,1535,1537 | Start No Earlier Than | 11/12/24 | 4 | 0d | NA | NA | 0 days? | No | 11/12/24 | 11/15/24 | NA | 1
12735 | Mule API Deployment | November 18, 2024 8:00 AM | November 22, 2024 5:00 PM | 1530 |  | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 11/18/24 | 11/22/24 | NA | 1
12736 | DocuEdge Deployment | November 18, 2024 8:00 AM | November 22, 2024 5:00 PM | 1530 |  | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 11/18/24 | 11/22/24 | NA | 1
12737 | DocuEdge Mule Endpoint | November 18, 2024 8:00 AM | November 19, 2024 5:00 PM | 1530 | 1534 | As Soon As Possible | NA | 2 | 0d | NA | NA | 0 days? | No | 11/18/24 | 11/19/24 | NA | 1
12738 | DocuEdge Configuration | November 20, 2024 8:00 AM | November 22, 2024 5:00 PM | 1533 | 1539 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 11/20/24 | 11/22/24 | NA | 1
12739 | AEM Environment Setup | November 18, 2024 8:00 AM | November 20, 2024 5:00 PM | 1530 | 1539,1536 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 11/18/24 | 11/20/24 | NA | 1
12728 | AEM Deployment | November 21, 2024 8:00 AM | November 22, 2024 5:00 PM | 1535 |  | As Soon As Possible | NA | 2 | 0d | NA | NA | 0 days? | No | 11/21/24 | 11/22/24 | NA | 1
12729 | SOLR Setup | November 18, 2024 8:00 AM | November 20, 2024 5:00 PM | 1530 | 1539,1538 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 11/18/24 | 11/20/24 | NA | 1
12730 | SOLR API Deployment | November 21, 2024 8:00 AM | November 22, 2024 5:00 PM | 1537 |  | As Soon As Possible | NA | 2 | 0d | NA | NA | 0 days? | No | 11/21/24 | 11/22/24 | NA | 1
12731 | Salesforce Integration | November 25, 2024 8:00 AM | December 3, 2024 5:00 PM | 1530,1534,1535,1537 | 1540 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 11/25/24 | 12/3/24 | NA | 1
12726 | Deploy code build (Initial) | December 4, 2024 8:00 AM | December 10, 2024 5:00 PM | 1539 | 1542 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 12/4/24 | 12/10/24 | NA | 1
12741 | Snowflake Setup | October 28, 2024 8:00 AM | October 28, 2024 5:00 PM | 1529SS |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 10/28/24 | 10/28/24 | NA | 1
12742 | Syncing users in Okta | December 11, 2024 8:00 AM | December 17, 2024 5:00 PM | 1540 | 1543 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 12/11/24 | 12/17/24 | NA | 1
12727 | Validate Access for Testing Team | December 18, 2024 8:00 AM | December 19, 2024 5:00 PM | 1542 | 1544 | As Soon As Possible | NA | 2 | 0d | NA | NA | 0 days? | No | 12/18/24 | 12/19/24 | NA | 1
12725 | Smoke Test Initial Environment Build | December 20, 2024 8:00 AM | December 24, 2024 5:00 PM | 1543 | 1549 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 12/20/24 | 12/24/24 | NA | 1
12724 | EUST County Setup | October 28, 2024 8:00 AM | March 14, 2025 5:00 PM |  |  | As Soon As Possible | NA | 93 | 0d | NA | NA | 0 days? | No | 10/28/24 | 3/14/25 | NA | 1
12745 | Identify counties participating in EUST 2 | November 12, 2024 8:00 AM | November 18, 2024 5:00 PM |  | 1547FS+73d,1548FS+73d | Start No Earlier Than | 11/12/24 | 5 | 0d | NA | NA | 0 days? | No | 11/12/24 | 11/18/24 | NA | 1
12746 | Communicate with County teams to test access to EUST 2 | March 10, 2025 8:00 AM | March 14, 2025 5:00 PM | 1546FS+73d |  | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 3/10/25 | 3/14/25 | NA | 1
12744 | Confirm EUST 2 environment connectivity for all counties | March 10, 2025 8:00 AM | March 14, 2025 5:00 PM | 1546FS+73d | 1549FS-5d | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 3/10/25 | 3/14/25 | NA | 1
12743 | Confirm EUST 2 county user access to the environment | March 10, 2025 8:00 AM | March 14, 2025 5:00 PM | 1544,1548FS-5d |  | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 3/10/25 | 3/14/25 | NA | 1
12747 | Deployment to EUST 2 Environment | December 23, 2024 8:00 AM | March 14, 2025 5:00 PM |  |  | As Soon As Possible | NA | 56 | 0d | NA | NA | 0 days? | No | 12/23/24 | 3/14/25 | NA | 1
12750 | Final Code Deployment for User Feedback | December 23, 2024 8:00 AM | December 30, 2024 5:00 PM |  | 1552 | Start No Earlier Than | 12/23/24 | 5 | 0d | NA | NA | 0 days? | No | 12/23/24 | 12/30/24 | NA | 1
12751 | Smoke Test Deployment for User Feedback | December 31, 2024 8:00 AM | January 7, 2025 5:00 PM | 1551 | 1553FS-2d | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 12/31/24 | 1/7/25 | NA | 1
12748 | EUST 2 - User Feedback Start | January 6, 2025 8:00 AM | January 6, 2025 5:00 PM | 1552FS-2d |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 1/6/25 | 1/6/25 | NA | 1
12752 | Final Code Deployment for EUST2 | February 24, 2025 8:00 AM | February 28, 2025 5:00 PM |  | 1555 | Start No Earlier Than | 2/24/25 | 5 | 0d | NA | NA | 0 days? | No | 2/24/25 | 2/28/25 | NA | 1
12749 | Smoke Test Environment | March 3, 2025 8:00 AM | March 14, 2025 5:00 PM | 1554 |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/14/25 | NA | 1
12754 | EUST 2 Data Readiness | October 28, 2024 8:00 AM | March 10, 2025 5:00 PM |  |  | As Soon As Possible | NA | 89 | 0d | NA | NA | 0 days? | No | 10/28/24 | 3/10/25 | NA | 1
12758 | Identify Transactional Data Needs for EUST 2 (including volume) | November 18, 2024 8:00 AM | January 2, 2025 5:00 PM |  | 1559 | Start No Earlier Than | 11/18/24 | 30 | 0d | NA | NA | 0 days? | No | 11/18/24 | 1/2/25 | NA | 1
12762 | Identify Office / Unit Structure Needs for EUST 2 | October 28, 2024 8:00 AM | November 1, 2024 5:00 PM |  | 1559 | Start No Earlier Than | 10/28/24 | 5 | 0d | NA | NA | 0 days? | No | 10/28/24 | 11/1/24 | NA | 1
12763 | Confirm Data needs for EUST 2 Office / Unit and Transactional Data | January 3, 2025 8:00 AM | January 9, 2025 5:00 PM | 1557,1558 | 1560FS-1d,1563,1564 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 1/3/25 | 1/9/25 | NA | 1
12764 | Produce Template for Office / Unit Structure | January 9, 2025 8:00 AM | January 9, 2025 5:00 PM | 1559FS-1d | 1561 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 1/9/25 | 1/9/25 | NA | 1
12765 | Distribute the Template to Counties | January 10, 2025 8:00 AM | January 10, 2025 5:00 PM | 1560 | 1562 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 1/10/25 | 1/10/25 | NA | 1
12766 | Counties to fill out Office / Unit Structure and Return | January 13, 2025 8:00 AM | January 24, 2025 5:00 PM | 1561 |  | As Soon As Possible | NA | 9 | 0d | NA | NA | 0 days? | No | 1/13/25 | 1/24/25 | NA | 1
12767 | Provide User (Tester) details for EUST 2 | January 10, 2025 8:00 AM | January 24, 2025 5:00 PM | 1559 | 1565FS+15d | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 1/10/25 | 1/24/25 | NA | 1
12768 | Develop steps to manually create Transactional Data | January 10, 2025 8:00 AM | February 7, 2025 5:00 PM | 1559 |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 1/10/25 | 2/7/25 | NA | 1
12759 | Deploy EUST 2 Package and Day 0 Data | February 18, 2025 8:00 AM | March 3, 2025 5:00 PM | 1563FS+15d | 1566 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 2/18/25 | 3/3/25 | NA | 1
12760 | Upload Office / Unit Structure from templates | March 4, 2025 8:00 AM | March 10, 2025 5:00 PM | 1565 | 1567SS-1d | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 3/4/25 | 3/10/25 | NA | 1
12761 | Provision Users for EUST 2 (Okta Team) | March 3, 2025 8:00 AM | March 7, 2025 5:00 PM | 1566SS-1d |  | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/7/25 | NA | 1
4843 | EUST 2 - Deployment to Staging | October 23, 2024 8:00 AM | March 7, 2025 5:00 PM |  |  | As Soon As Possible | NA | 91 | 0d | January 24, 2025 8:00 AM | March 18, 2025 5:00 PM | 37 days | No | 10/23/24 | 3/7/25 | NA | 1
12757 | Confirm readiness of staging environment | October 23, 2024 8:00 AM | October 29, 2024 5:00 PM |  | 1571,1572 | Start No Earlier Than | 10/23/24 | 5 | 0d | NA | NA | 0 days? | No | 10/23/24 | 10/29/24 | NA | 1
12769 | Confirm interface integration connection | December 2, 2024 8:00 AM | December 6, 2024 5:00 PM |  | 1571FS+56d,1572FS+56d | Start No Earlier Than | 12/2/24 | 5 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/6/24 | NA | 1
12753 | Test interface integration with EUST environment - FCED/CalSAWS | March 3, 2025 8:00 AM | March 7, 2025 5:00 PM | 1569,1570FS+56d |  | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/7/25 | NA | 1
12755 | Test interface integration with EUST environment - JNET/San Bern. | March 3, 2025 8:00 AM | March 7, 2025 5:00 PM | 1569,1570FS+56d | 1581FS-1d | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/7/25 | NA | 1
12774 | EUST 2 - Conduct User Training | October 28, 2024 8:00 AM | March 21, 2025 5:00 PM |  |  | As Soon As Possible | NA | 98 | 0d | NA | NA | 0 days? | No | 10/28/24 | 3/21/25 | NA | 1
12777 | Draft User Guide with updated screenshots | January 6, 2025 8:00 AM | February 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 1/6/25 | 2/18/25 | NA | 1
12772 | Develop the Training Materials for EUST 2 | October 28, 2024 8:00 AM | February 14, 2025 5:00 PM |  | 1577FS+4d | Start No Earlier Than | 10/28/24 | 74 | 0d | NA | NA | 0 days? | No | 10/28/24 | 2/14/25 | NA | 1
12773 | Develop EUST Overview training/Kickoff | January 6, 2025 8:00 AM | February 14, 2025 5:00 PM |  |  | As Soon As Possible | NA | 29 | 0d | NA | NA | 0 days? | No | 1/6/25 | 2/14/25 | NA | 1
12779 | Schedule Option 1 and 2 of overview trainings/kickoff | February 24, 2025 8:00 AM | February 25, 2025 5:00 PM | 1575FS+4d |  | As Soon As Possible | NA | 2 | 0d | NA | NA | 0 days? | No | 2/24/25 | 2/25/25 | NA | 1
13069 | Setup EUST Testers in Salesforce Enablement | January 6, 2025 8:00 AM | February 19, 2025 5:00 PM |  |  | Start No Earlier Than | 1/6/25 | 31 | 0d | NA | NA | 0 days? | No | 1/6/25 | 2/19/25 | NA | 1
12771 | EUST Testers complete online training | March 17, 2025 8:00 AM | March 21, 2025 5:00 PM |  |  | Start No Earlier Than | 3/17/25 | 5 | 0d | NA | NA | 0 days? | No | 3/17/25 | 3/21/25 | NA | 1
12770 | EUST 2 Go-No-Go | December 17, 2024 8:00 AM | March 7, 2025 5:00 PM |  |  | As Soon As Possible | NA | 55 | 0d | NA | NA | 0 days? | No | 12/17/24 | 3/7/25 | NA | 1
12782 | EUST 2 - Confirm EUST Readiness | March 7, 2025 8:00 AM | March 7, 2025 5:00 PM | 1572FS-1d | 1582 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 3/7/25 | 3/7/25 | NA | 1
12783 | Validation for all scenarios | December 17, 2024 8:00 AM | December 17, 2024 5:00 PM | 1581 |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 12/17/24 | 12/17/24 | NA | 1
12785 | Conduct ELT presentation of EUST 2 | March 3, 2025 8:00 AM | March 3, 2025 5:00 PM |  |  | Start No Earlier Than | 3/3/25 | 1 | 0d | NA | NA | 0 s? | No | 3/3/25 | 3/3/25 | NA | 1
12781 | Formal Go-No-Go Decision | March 3, 2025 8:00 AM | March 3, 2025 5:00 PM |  | 1593,1594,1595,1596,1597,1586FS+4d | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 3/3/25 | 3/3/25 | NA | 1
12780 | EUST 2 - Execution | March 4, 2025 8:00 AM | April 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 33 | 0d | NA | NA | 0 days? | No | 3/4/25 | 4/18/25 | NA | 1
13064 | Facilitate EUST 2 Kickoff | March 10, 2025 8:00 AM | March 10, 2025 5:00 PM | 1584FS+4d |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 3/10/25 | 3/10/25 | NA | 1
12786 | EUST 2 Testing Start | March 24, 2025 8:00 AM | March 24, 2025 5:00 PM |  | 1589SS,1590SS,1591SS,1598SS,1599SS,1600SS,1601SS | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 3/24/25 | 3/24/25 | NA | 1
12795 | EUST 2 Validation | March 24, 2025 8:00 AM | April 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 3/24/25 | 4/18/25 | NA | 1
12797 | EUST for Milestones 1, 2, 6, 8, 15, 19, 20 | March 24, 2025 8:00 AM | April 18, 2025 5:00 PM | 1587SS |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 3/24/25 | 4/18/25 | NA | 1
12798 | EUST for Interface Milestones 15.1 (San Bernardino Only) | March 24, 2025 8:00 AM | April 18, 2025 5:00 PM | 1587SS |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 3/24/25 | 4/18/25 | NA | 1
12799 | EUST 2 Interface for Milestone 20.1 | March 24, 2025 8:00 AM | April 18, 2025 5:00 PM | 1587SS |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 3/24/25 | 4/18/25 | NA | 1
12800 | EUST 2 Feedback | March 4, 2025 8:00 AM | April 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 33 | 0d | NA | NA | 0 days? | No | 3/4/25 | 4/18/25 | NA | 1
12801 | Schedule EUST Office Hours | March 4, 2025 8:00 AM | March 4, 2025 5:00 PM | 1584 |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 3/4/25 | 3/4/25 | NA | 1
12803 | Create EUST Milestone in JIRA | March 4, 2025 8:00 AM | March 17, 2025 5:00 PM | 1584 |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 3/4/25 | 3/17/25 | NA | 1
12804 | Create the Building Blocks and Epics accordingly | March 4, 2025 8:00 AM | March 17, 2025 5:00 PM | 1584 |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 3/4/25 | 3/17/25 | NA | 1
12805 | Prepare MS Teams feedback template for feedback in alignment with JIRA fields | March 4, 2025 8:00 AM | March 21, 2025 5:00 PM | 1584 |  | As Soon As Possible | NA | 14 | 0d | NA | NA | 0 days? | No | 3/4/25 | 3/21/25 | NA | 1
12806 | Schedule prioritization sessions to prioritize feedback | March 4, 2025 8:00 AM | March 10, 2025 5:00 PM | 1584 |  | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 3/4/25 | 3/10/25 | NA | 1
12807 | Conduct Office Hours | March 24, 2025 8:00 AM | April 18, 2025 5:00 PM | 1587SS | 1608SS,1609SS+10d | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 3/24/25 | 4/18/25 | NA | 1
12808 | Prepare communications after each office hours and send to CCs | March 24, 2025 8:00 AM | April 18, 2025 5:00 PM | 1587SS |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 3/24/25 | 4/18/25 | NA | 1
12809 | Upload the spreadsheet w/user feedback to JIRA | March 24, 2025 8:00 AM | April 18, 2025 5:00 PM | 1587SS |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 3/24/25 | 4/18/25 | NA | 1
12810 | Manage MS teams feedback | March 24, 2025 8:00 AM | April 18, 2025 5:00 PM | 1587SS |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 3/24/25 | 4/18/25 | NA | 1
12811 | EUST 2 - Triage/Prioritize Findings | March 24, 2025 8:00 AM | May 7, 2025 5:00 PM |  |  | As Soon As Possible | NA | 32 | 0d | NA | NA | 0 days? | No | 3/24/25 | 5/7/25 | NA | 1
12788 | Sentiment Survey | March 24, 2025 8:00 AM | May 7, 2025 5:00 PM |  |  | As Soon As Possible | NA | 32 | 0d | NA | NA | 0 days? | No | 3/24/25 | 5/7/25 | NA | 1
12816 | Send link to Sentiment Survey to CCs | April 22, 2025 8:00 AM | April 22, 2025 5:00 PM | 1609 | 1605 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 4/22/25 | 4/22/25 | NA | 1
12817 | Upload Sentiment Survey results to JIRA UF Project | April 23, 2025 8:00 AM | April 29, 2025 5:00 PM | 1604 | 1606,1611FS+3d | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 4/23/25 | 4/29/25 | NA | 1
12818 | Coordinate with Communications team to prepare the Sentiment Survey for EUST | April 30, 2025 8:00 AM | May 6, 2025 5:00 PM | 1605 | 1607 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 4/30/25 | 5/6/25 | NA | 1
12820 | Conduct report out to CCs for EUST Feedback | May 7, 2025 8:00 AM | May 7, 2025 5:00 PM | 1606 |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 5/7/25 | 5/7/25 | NA | 1
12821 | EUST 2 - Build/SIT Findings | March 24, 2025 8:00 AM | April 21, 2025 5:00 PM | 1598SS |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 3/24/25 | 4/21/25 | NA | 1
12822 | EUST 2 - QA Findings | April 8, 2025 8:00 AM | April 21, 2025 5:00 PM | 1598SS+10d | 1604 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 4/8/25 | 4/21/25 | NA | 1
12823 | EUST 2 - Closeout | May 5, 2025 8:00 AM | June 10, 2025 5:00 PM |  |  | As Soon As Possible | NA | 26 | 0d | NA | NA | 0 days? | No | 5/5/25 | 6/10/25 | NA | 1
12824 | Confirm exit criteria for EUST is met | May 5, 2025 8:00 AM | May 5, 2025 5:00 PM | 1605FS+3d | 1612 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 5/5/25 | 5/5/25 | NA | 1
12819 | Prepare presentations to ELT | May 6, 2025 8:00 AM | May 12, 2025 5:00 PM | 1611 | 1613,1614FS+15d,1615FS+15d,1616FS+15d,1617FS+15d | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 5/6/25 | 5/12/25 | NA | 1
12814 | Send EUST wrap-up email confirmation | May 13, 2025 8:00 AM | May 13, 2025 5:00 PM | 1612 |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 5/13/25 | 5/13/25 | NA | 1
12825 | Present to ELT (DOF, BOD tentatively as well) | June 4, 2025 8:00 AM | June 4, 2025 5:00 PM | 1612FS+15d |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/4/25 | 6/4/25 | NA | 1
12826 | Schedule Presentation to the counties | June 4, 2025 8:00 AM | June 4, 2025 5:00 PM | 1612FS+15d |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/4/25 | 6/4/25 | NA | 1
12813 | Create Presentation for the counties | June 4, 2025 8:00 AM | June 10, 2025 5:00 PM | 1612FS+15d |  | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 6/4/25 | 6/10/25 | NA | 1
12812 | Present to the counties | June 4, 2025 8:00 AM | June 4, 2025 5:00 PM | 1612FS+15d |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/4/25 | 6/4/25 | NA | 1
2864 | EUST - 3 | October 28, 2024 8:00 AM | May 19, 2026 5:00 PM |  |  | As Soon As Possible | NA | 389 | 350d? | August 11, 2025 8:00 AM | May 8, 2026 5:00 PM | 187 days | No | 10/28/24 | NA | NA | 0.17000000000000001
43567 | EUST 3 - Preparation | October 28, 2024 8:00 AM | February 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 332 | 407d? | November 4, 2024 8:00 AM | March 18, 2025 5:00 PM | 90 days | No | 10/28/24 | NA | NA | 0.28999999999999998
43568 | EUST 3 - Scenario Writing | May 19, 2025 8:00 AM | December 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 154 | 448d? | November 4, 2024 8:00 AM | December 30, 2024 5:00 PM | 37 days | No | 5/19/25 | NA | NA | 0.59999999999999998
43569 | Build Drop 1 Scenario Writing | June 2, 2025 8:00 AM | July 11, 2025 5:00 PM |  |  | As Soon As Possible | NA | 29 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/11/25 | NA | 1
43570 | Conduct Funcational Analysis | June 2, 2025 8:00 AM | June 6, 2025 5:00 PM |  | 1623 | Start No Earlier Than | 6/2/25 | 5 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/6/25 | NA | 1
43571 | Develop Scenario Narratives | June 9, 2025 8:00 AM | June 20, 2025 5:00 PM | 1622 | 1624SS | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 6/9/25 | 6/20/25 | NA | 1
43572 | Review Draft Scenario Narratives with Service Areas | June 9, 2025 8:00 AM | June 13, 2025 5:00 PM | 1623SS | 1625 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 6/9/25 | 6/13/25 | NA | 1
43573 | Submit Scenario Narratives to Technical Testing Team | June 16, 2025 8:00 AM | June 16, 2025 5:00 PM | 1624 | 1626 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/16/25 | 6/16/25 | NA | 1
43574 | Conduct Testing and Add Key Actions | June 17, 2025 8:00 AM | July 7, 2025 5:00 PM | 1625 | 1627FF | As Soon As Possible | NA | 14 | 0d | NA | NA | 0 days? | No | 6/17/25 | 7/7/25 | NA | 1
43575 | Submit completed testing and key Actions and sed to User Feedback Team | July 7, 2025 8:00 AM | July 7, 2025 5:00 PM | 1626FF | 1628SS | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 7/7/25 | 7/7/25 | NA | 1
43576 | Review and Validate Key Actions/Steps | July 7, 2025 8:00 AM | July 11, 2025 5:00 PM | 1627SS | 1629FF | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 7/7/25 | 7/11/25 | NA | 1
43577 | Submit Final Scenarios to Training Team | July 11, 2025 8:00 AM | July 11, 2025 5:00 PM | 1628FF | 1766 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 7/11/25 | 7/11/25 | NA | 1
43578 | Build Drop 2 Scenario Writing | June 13, 2025 8:00 AM | August 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 45 | 539d | NA | NA | 0 days? | No | 6/13/25 | NA | NA | 0.98999999999999999
43579 | Conduct Initial Analysis of Planned Build Drop 2 | June 13, 2025 8:00 AM | July 11, 2025 5:00 PM |  |  | Start No Earlier Than | 6/13/25 | 20 | 0d | NA | NA | 0 days? | No | 6/13/25 | 7/11/25 | NA | 1
43580 | Delivery of Build Drop Completed | July 7, 2025 8:00 AM | July 7, 2025 5:00 PM |  | 1634SS | Start No Earlier Than | 7/7/25 | 1 | 0d | NA | NA | 0 s? | No | 7/7/25 | 7/7/25 | NA | 1
43581 | PaaS application demo and walkthrough of developed funcationality | July 11, 2025 8:00 AM | July 11, 2025 5:00 PM |  |  | Start No Earlier Than | 7/11/25 | 1 | 0d | NA | NA | 0 s? | No | 7/11/25 | 7/11/25 | NA | 1
43582 | Conduct Funcational Analysis | July 7, 2025 8:00 AM | July 11, 2025 5:00 PM | 1632SS | 1635 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 7/7/25 | 7/11/25 | NA | 1
43583 | Develop Scenario Narratives | July 14, 2025 8:00 AM | July 30, 2025 5:00 PM | 1634 |  | As Soon As Possible | NA | 13 | 0d | NA | NA | 0 days? | No | 7/14/25 | 7/30/25 | NA | 1
43584 | Review Draft Scenario Narratives with Service Areas | July 21, 2025 8:00 AM | July 30, 2025 5:00 PM |  | 1637FF | Start No Earlier Than | 7/21/25 | 8 | 0d | NA | NA | 0 days? | No | 7/21/25 | 7/30/25 | NA | 1
43585 | Submit Scenario Narratives to Technical Testing Team | July 30, 2025 8:00 AM | July 30, 2025 5:00 PM | 1636FF | 1638 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 7/30/25 | 7/30/25 | NA | 1
43586 | Conduct Testing and Add Key Actions | July 31, 2025 8:00 AM | August 15, 2025 5:00 PM | 1637 | 1639FF | As Soon As Possible | NA | 12 | 0d | NA | NA | 0 days? | No | 7/31/25 | 8/15/25 | NA | 1
43587 | Submit completed testing and key Actions and sed to User Feedback Team | August 15, 2025 8:00 AM | August 15, 2025 5:00 PM | 1638FF |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 8/15/25 | 8/15/25 | NA | 1
43588 | Review and Validate Key Actions/Steps | August 11, 2025 8:00 AM | August 15, 2025 5:00 PM |  | 1641FF | Start No Earlier Than | 8/11/25 | 5 | 539d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.90000000000000002
43589 | Submit Final Scenarios to Training Team | August 15, 2025 8:00 AM | August 15, 2025 5:00 PM | 1640FF | 1767 | As Soon As Possible | NA | 1 | 539d | NA | NA | 0 s? | No | 8/15/25 | NA | NA | 0.90000000000000002
43590 | Build Drop 3 Scenario Writing | July 7, 2025 8:00 AM | September 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 50 | 519d | NA | NA | 0 days? | No | 7/7/25 | NA | NA | 0.78000000000000003
43591 | Conduct Initial Analysis of Planned Build Drop 3 | July 7, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | Start No Earlier Than | 7/7/25 | 25 | 0d | NA | NA | 0 days? | No | 7/7/25 | 8/8/25 | NA | 1
43592 | Delivery of Build Drop Completed | August 8, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 1645,1646 | Start No Earlier Than | 8/8/25 | 1 | 0d | NA | NA | 0 s? | No | 8/8/25 | 8/8/25 | NA | 1
43593 | PaaS application demo and walkthrough of developed funcationality | August 11, 2025 8:00 AM | August 11, 2025 5:00 PM | 1644 |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 8/11/25 | 8/11/25 | NA | 1
43594 | Conduct Funcational Analysis | August 11, 2025 8:00 AM | August 15, 2025 5:00 PM | 1644 | 1647SS,1648 | Finish No Earlier Than | 7/11/25 | 5 | 0d | NA | NA | 0 days? | No | 8/11/25 | 8/15/25 | NA | 1
43595 | Develop Scenario Narratives | August 11, 2025 8:00 AM | August 27, 2025 5:00 PM | 1646SS |  | Finish No Earlier Than | 7/30/25 | 13 | 0d | NA | NA | 0 days? | No | 8/11/25 | 8/27/25 | NA | 1
43596 | Review Draft Scenario Narratives with Service Areas | August 18, 2025 8:00 AM | August 22, 2025 5:00 PM | 1646 | 1649FF | Finish No Earlier Than | 7/30/25 | 5 | 0d | NA | NA | 0 days? | No | 8/18/25 | 8/22/25 | NA | 1
43597 | Submit Scenario Narratives to Technical Testing Team | August 22, 2025 8:00 AM | August 22, 2025 5:00 PM | 1648FF | 1650 | Start No Earlier Than | 7/30/25 | 1 | 1.2d | NA | NA | 0 s? | No | 8/22/25 | NA | NA | 0.80000000000000004
43598 | Conduct Testing and Add Key Actions | August 25, 2025 8:00 AM | September 10, 2025 5:00 PM | 1649 | 1651,1652 | Finish No Earlier Than | 8/15/25 | 12 | 0.1d | NA | NA | 0 days? | No | 8/25/25 | NA | NA | 0.10000000000000001
43599 | Submit completed testing and key Actions and sed to User Feedback Team | September 11, 2025 8:00 AM | September 11, 2025 5:00 PM | 1650 |  | Start No Earlier Than | 8/15/25 | 1 | 521d | NA | NA | 0 s? | No | 9/11/25 | NA | NA | 0.10000000000000001
43600 | Review and Validate Key Actions/Steps | September 11, 2025 8:00 AM | September 12, 2025 5:00 PM | 1650 | 1653 | Finish No Earlier Than | 8/15/25 | 2 | 0.05d | NA | NA | 0 days? | No | 9/11/25 | NA | NA | 5.0000000000000003E-2
43601 | Submit Final Scenarios to Training Team | September 15, 2025 8:00 AM | September 15, 2025 5:00 PM | 1652 | 1768 | Start No Earlier Than | 8/15/25 | 1 | 519d | NA | NA | 0 s? | No | 9/15/25 | NA | NA | 5.0000000000000003E-2
43602 | Build Drop 4 Scenario Writing | August 18, 2025 8:00 AM | November 14, 2025 5:00 PM |  |  | As Soon As Possible | NA | 63 | 476d | NA | NA | 0 days? | No | 8/18/25 | NA | NA | 0.44
43603 | Conduct Initial Analysis of Planned Build Drop 4 | August 18, 2025 8:00 AM | September 22, 2025 5:00 PM |  |  | Start No Earlier Than | 8/18/25 | 25 | 0d | NA | NA | 0 days? | No | 8/18/25 | 9/22/25 | NA | 1
43604 | Delivery of Build Drop Completed | October 3, 2025 8:00 AM | October 3, 2025 5:00 PM |  | 1658,1659SS | Start No Earlier Than | 10/3/25 | 1 | 0.99d | NA | NA | 0 s? | No | NA | NA | NA | 0
43605 | PaaS application demo and walkthrough of developed funcationality | October 6, 2025 8:00 AM | October 6, 2025 5:00 PM |  |  | Start No Earlier Than | 10/6/25 | 1 | 504d | NA | NA | 0 s? | No | NA | NA | NA | 0
43606 | Conduct Funcational Analysis | October 6, 2025 8:00 AM | October 10, 2025 5:00 PM | 1656 | 1660 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 10/6/25 | 10/10/25 | NA | 1
43607 | Develop Scenario Narratives | October 3, 2025 8:00 AM | October 17, 2025 5:00 PM | 1656SS |  | Finish No Earlier Than | 8/27/25 | 11 | 495d | NA | NA | 0 days? | No | 10/3/25 | NA | NA | 8.9999999999999997E-2
43608 | Review Draft Scenario Narratives with Service Areas | October 13, 2025 8:00 AM | October 17, 2025 5:00 PM | 1658 | 1661FF | As Soon As Possible | NA | 5 | 480d | NA | NA | 0 days? | No | NA | NA | NA | 0
43609 | Submit Scenario Narratives to Technical Testing Team | October 17, 2025 8:00 AM | October 17, 2025 5:00 PM | 1660FF | 1662 | Start No Earlier Than | 8/22/25 | 1 | 480d | NA | NA | 0 s? | No | NA | NA | NA | 0
43610 | Conduct Testing and Add Key Actions | October 20, 2025 8:00 AM | November 7, 2025 5:00 PM | 1661 |  | As Soon As Possible | NA | 15 | 480d | NA | NA | 0 days? | No | NA | NA | NA | 0
43611 | Submit completed testing and key Actions and sed to User Feedback Team | November 7, 2025 8:00 AM | November 7, 2025 5:00 PM |  | 1664 | Start No Earlier Than | 11/7/25 | 1 | 476d | NA | NA | 0 s? | No | NA | NA | NA | 0
43612 | Review and Validate Key Actions/Steps | November 10, 2025 8:00 AM | November 14, 2025 5:00 PM | 1663 |  | As Soon As Possible | NA | 4 | 476d | NA | NA | 0 days? | No | NA | NA | NA | 0
43613 | Submit Final Scenarios to Training Team | November 14, 2025 8:00 AM | November 14, 2025 5:00 PM |  | 1769 | Start No Earlier Than | 11/14/25 | 1 | 439d | NA | NA | 0 s? | No | NA | NA | NA | 0
43614 | Build Drop 5 Scenario Writing | September 17, 2025 8:00 AM | January 14, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 436d | NA | NA | 0 days? | No | 9/17/25 | NA | NA | 0.13
43615 | Conduct Initial Analysis of Planned Build Drop 5 | September 17, 2025 8:00 AM | November 28, 2025 5:00 PM |  | 1669 | Start No Earlier Than | 9/17/25 | 51 | 466d | NA | NA | 0 days? | No | 9/17/25 | NA | NA | 0.25
43616 | Delivery of Build Drop Completed | November 28, 2025 8:00 AM | November 28, 2025 5:00 PM |  | 1670 | Start No Earlier Than | 11/28/25 | 1 | 426d | NA | NA | 0 s? | No | NA | NA | NA | 0
43617 | PaaS application demo and walkthrough of developed funcationality | December 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 1667 |  | As Soon As Possible | NA | 1 | 466d | NA | NA | 0 s? | No | NA | NA | NA | 0
43618 | Conduct Funcational Analysis | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 1668 | 1672 | As Soon As Possible | NA | 5 | 426d | NA | NA | 0 days? | No | NA | NA | NA | 0
43619 | Develop Scenario Narratives | December 1, 2025 8:00 AM | December 12, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 10 | 457d | NA | NA | 0 days? | No | NA | NA | NA | 0
43620 | Review Draft Scenario Narratives with Service Areas | December 8, 2025 8:00 AM | December 12, 2025 5:00 PM | 1670 | 1673FF | As Soon As Possible | NA | 5 | 426d | NA | NA | 0 days? | No | NA | NA | NA | 0
43621 | Submit Scenario Narratives to Technical Testing Team | December 12, 2025 8:00 AM | December 12, 2025 5:00 PM | 1672FF | 1674 | Start No Earlier Than | 8/22/25 | 1 | 426d | NA | NA | 0 s? | No | NA | NA | NA | 0
43622 | Conduct Testing and Add Key Actions | December 15, 2025 8:00 AM | January 6, 2026 5:00 PM | 1673 | 1675 | As Soon As Possible | NA | 15 | 426d | NA | NA | 0 days? | No | NA | NA | NA | 0
43623 | Submit completed testing and key Actions and sed to User Feedback Team | January 7, 2026 8:00 AM | January 7, 2026 5:00 PM | 1674 | 1676 | As Soon As Possible | NA | 1 | 426d | NA | NA | 0 s? | No | NA | NA | NA | 0
43624 | Review and Validate Key Actions/Steps | January 8, 2026 8:00 AM | January 13, 2026 5:00 PM | 1675 | 1677 | Start No Earlier Than | 1/7/26 | 4 | 426d | NA | NA | 0 days? | No | NA | NA | NA | 0
43625 | Submit Final Scenarios to Training Team | January 14, 2026 8:00 AM | January 14, 2026 5:00 PM | 1676 | 1770 | As Soon As Possible | NA | 1 | 426d | NA | NA | 0 s? | No | NA | NA | NA | 0
43828 | Usability Testing Feedback (Previously Milestone User Feedback) | July 11, 2025 8:00 AM | January 13, 2026 5:00 PM |  |  | As Soon As Possible | NA | 128 | 437d | NA | NA | 0 days? | No | 7/11/25 | NA | NA | 0.19
43829 | Create new MS Teams/SharePoint space for User Feedback (EUST 3 ) | July 14, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | Start No Earlier Than | 7/14/25 | 5 | 0d | NA | NA | 0 days? | No | 7/14/25 | 7/18/25 | NA | 1
43830 | Identify CC to participate in UF Testing (Must have completed EUST 2) | July 11, 2025 8:00 AM | July 11, 2025 5:00 PM |  |  | Start No Earlier Than | 7/11/25 | 1 | 0d | NA | NA | 0 s? | No | 7/11/25 | 7/11/25 | NA | 1
43831 | Usability Testing (BD 1-3) | September 8, 2025 8:00 AM | December 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 61 | 464d | NA | NA | 0 days? | No | 9/8/25 | NA | NA | 0.26000000000000001
43832 | Draft communication User Feedback Effort | September 8, 2025 8:00 AM | September 10, 2025 5:00 PM |  | 1683 | Start No Earlier Than | 9/8/25 | 3 | 0d | NA | NA | 0 days? | No | 9/8/25 | 9/10/25 | NA | 1
43833 | Send communication to ELT for approval | September 11, 2025 8:00 AM | September 12, 2025 5:00 PM | 1682 | 1684,1686,1687 | As Soon As Possible | NA | 2 | 0d | NA | NA | 0 days? | No | 9/11/25 | 9/12/25 | NA | 1
43834 | Send communication to CC and CARES team members for participation | September 15, 2025 8:00 AM | September 26, 2025 5:00 PM | 1683 |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/15/25 | 9/26/25 | NA | 1
43835 | Load users to SharePoint feedback site as needed | October 7, 2025 8:00 AM | November 3, 2025 5:00 PM |  |  | Start No Earlier Than | 10/7/25 | 20 | 484d | NA | NA | 0 days? | No | NA | NA | NA | 0
43836 | Validate environment access for CC | September 15, 2025 8:00 AM | September 19, 2025 5:00 PM | 1683 |  | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 9/15/25 | 9/19/25 | NA | 1
43837 | Validate environment access for CARES team | September 15, 2025 8:00 AM | September 19, 2025 5:00 PM | 1683 |  | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 9/15/25 | 9/19/25 | NA | 1
43838 | Confirm Staging Environment Readiness | October 6, 2025 8:00 AM | October 6, 2025 5:00 PM |  | 1689SS | Start No Earlier Than | 10/6/25 | 1 | 494d | NA | NA | 0 s? | No | NA | NA | NA | 0
43839 | Complete Build / SIT and data load in Staging | October 6, 2025 8:00 AM | October 10, 2025 5:00 PM | 1688SS | 1690SS | As Soon As Possible | NA | 5 | 494d | NA | NA | 0 days? | No | NA | NA | NA | 0
43840 | Data loaded in staging (Day 0 data) | October 6, 2025 8:00 AM | October 10, 2025 5:00 PM | 1689SS | 1692,1694 | As Soon As Possible | NA | 5 | 494d | NA | NA | 0 days? | No | NA | NA | NA | 0
43841 | PaaS User Access Testing to Staging | October 20, 2025 8:00 AM | October 24, 2025 5:00 PM |  |  | Start No Earlier Than | 10/20/25 | 5 | 490d | NA | NA | 0 days? | No | NA | NA | NA | 0
43842 | Complete State QA of code in Staging | October 20, 2025 8:00 AM | October 24, 2025 5:00 PM | 1690 | 1693 | Start No Earlier Than | 10/20/25 | 5 | 489d | NA | NA | 0 days? | No | NA | NA | NA | 0
43843 | Hold User Feedback Kickoff Meeting | October 27, 2025 8:00 AM | October 27, 2025 5:00 PM | 1692 |  | As Soon As Possible | NA | 1 | 489d | NA | NA | 0 s? | No | NA | NA | NA | 0
43844 | Schedule M-Th office hours for 2 weeks of testing | October 27, 2025 8:00 AM | October 27, 2025 5:00 PM | 1690 |  | Start No Earlier Than | 10/27/25 | 1 | 489d | NA | NA | 0 s? | No | NA | NA | NA | 0
43845 | Conduct User Feedback Testing | October 27, 2025 8:00 AM | November 7, 2025 5:00 PM |  | 1696SS | Start No Earlier Than | 10/27/25 | 10 | 465d | NA | NA | 0 days? | No | NA | NA | NA | 0
43846 | Capture feedback in MS Teams and Document in JIRA | October 27, 2025 8:00 AM | November 7, 2025 5:00 PM | 1695SS | 1697 | Start No Earlier Than | 10/27/25 | 10 | 465d | NA | NA | 0 days? | No | NA | NA | NA | 0
43847 | Report out on User Feedback | November 10, 2025 8:00 AM | November 20, 2025 5:00 PM | 1696 | 1698 | Finish No Earlier Than | 10/9/25 | 8 | 465d | NA | NA | 0 days? | No | NA | NA | NA | 0
43848 | Present findings to ELT | November 24, 2025 8:00 AM | November 24, 2025 5:00 PM | 1697 | 1699FS+5d | Start No Earlier Than | 11/24/25 | 1 | 464d | NA | NA | 0 s? | No | NA | NA | NA | 0
43849 | Present findings to User Feedback participants | December 3, 2025 8:00 AM | December 3, 2025 5:00 PM | 1698FS+5d |  | Start No Earlier Than | 12/1/25 | 1 | 464d | NA | NA | 0 s? | No | NA | NA | NA | 0
43850 | Usability Testing (BD 4) | November 24, 2025 8:00 AM | January 13, 2026 5:00 PM |  |  | As Soon As Possible | NA | 34 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
43851 | Confrim User Permission Sets Validated | November 24, 2025 8:00 AM | November 26, 2025 5:00 PM |  |  | Start No Earlier Than | 11/24/25 | 3 | 468d | NA | NA | 0 days? | No | NA | NA | NA | 0
43852 | Confirm Staging Environment Readiness | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 5 | 462d | NA | NA | 0 days? | No | NA | NA | NA | 0
43853 | Complete Build / SIT and data load in Staging | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 5 | 462d | NA | NA | 0 days? | No | NA | NA | NA | 0
43854 | Data loaded in staging (Day 0 data) | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 5 | 462d | NA | NA | 0 days? | No | NA | NA | NA | 0
43855 | Complete State QA of code in Staging | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 5 | 462d | NA | NA | 0 days? | No | NA | NA | NA | 0
43856 | Hold User Feedback Kickoff Meeting | December 8, 2025 8:00 AM | December 8, 2025 5:00 PM |  |  | Start No Earlier Than | 12/8/25 | 1 | 461d | NA | NA | 0 s? | No | NA | NA | NA | 0
43857 | Schedule M-Th office hours for 2 weeks of testing | December 8, 2025 8:00 AM | December 8, 2025 5:00 PM |  |  | Start No Earlier Than | 12/8/25 | 1 | 461d | NA | NA | 0 s? | No | NA | NA | NA | 0
43858 | Conduct User Feedback Testing | December 8, 2025 8:00 AM | December 19, 2025 5:00 PM |  |  | Start No Earlier Than | 12/8/25 | 10 | 452d | NA | NA | 0 days? | No | NA | NA | NA | 0
43859 | Capture feedback in MS Teams and Document in JIRA | December 8, 2025 8:00 AM | December 19, 2025 5:00 PM |  | 1710 | Start No Earlier Than | 12/8/25 | 10 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
43860 | Report out on User Feedback | December 22, 2025 8:00 AM | January 2, 2026 5:00 PM | 1709 | 1711 | Finish No Earlier Than | 10/9/25 | 8 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
43861 | Present findings to ELT | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM | 1710 | 1712FS+5d | Start No Earlier Than | 10/13/25 | 1 | 437d | NA | NA | 0 s? | No | NA | NA | NA | 0
43862 | Present findings to User Feedback participants | January 13, 2026 8:00 AM | January 13, 2026 5:00 PM | 1711FS+5d |  | Start No Earlier Than | 1/5/26 | 1 | 437d | NA | NA | 0 s? | No | NA | NA | NA | 0
43647 | EUST 3 - User setup and access validation | November 7, 2024 8:00 AM | March 10, 2025 5:00 PM |  |  | As Soon As Possible | NA |  | 650d? | January 24, 2025 8:00 AM | March 18, 2025 5:00 PM | 37 days | No | 11/7/24 | NA | NA | 8.9999999999999997E-2
43648 | Establish date the communications should be sent to CC SPOC to identify users | September 8, 2025 8:00 AM | September 12, 2025 5:00 PM |  | 1715 | Start No Earlier Than | 9/8/25 | 5 | 0d | NA | NA | 0 days? | No | 9/8/25 | 9/12/25 | NA | 1
43649 | Draft communication to send to all counties requesting EUST participation | September 15, 2025 8:00 AM | September 19, 2025 5:00 PM | 1714 | 1716 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 9/15/25 | 9/19/25 | NA | 1
43650 | Send communication to ELT for approval | September 22, 2025 8:00 AM | October 3, 2025 5:00 PM | 1715 | 1717 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/22/25 | 10/3/25 | NA | 1
43651 | Send communication to all counties for participation in EUST 3 | October 6, 2025 8:00 AM | October 6, 2025 5:00 PM | 1716 | 1718SS,1721SS,1722SS,1723SS | As Soon As Possible | NA | 1 | 504d | NA | NA | 0 s? | No | 10/6/25 | NA | NA | 0.5
43652 | Schedule EUST overview/Q&A meeting for counties | October 6, 2025 8:00 AM | October 6, 2025 5:00 PM | 1717SS |  | As Soon As Possible | NA | 1 | 504d | NA | NA | 0 s? | No | 10/6/25 | NA | NA | 0.5
43653 | Hold EUST 3 overview meeting option 1 | November 6, 2025 8:00 AM | November 6, 2025 5:00 PM |  | 1720 | Finish No Earlier Than | 11/6/25 | 1 | 480d | NA | NA | 0 s? | No | NA | NA | NA | 0
43654 | Hold EUST 3 overview meeting option 2 | November 7, 2025 8:00 AM | November 7, 2025 5:00 PM | 1719 |  | As Soon As Possible | NA | 1 | 480d | NA | NA | 0 s? | No | NA | NA | NA | 0
43655 | Document county participants in EUST 3 | October 6, 2025 8:00 AM | November 26, 2025 5:00 PM | 1717SS | 1729FS-1d | Start No Earlier Than | 10/6/25 | 37 | 454d | NA | NA | 0 days? | No | NA | NA | NA | 0
43656 | Add new users to spreadsheet: Users by County | October 6, 2025 8:00 AM | November 26, 2025 5:00 PM | 1717SS |  | Start No Earlier Than | 10/6/25 | 37 | 468d | NA | NA | 0 days? | No | NA | NA | NA | 0
43657 | Add county participants to Microsoft Teams Space for EUST 3 Feedback | October 6, 2025 8:00 AM | November 26, 2025 5:00 PM | 1717SS |  | Start No Earlier Than | 10/6/25 | 37 | 468d | NA | NA | 0 days? | No | NA | NA | NA | 0
43658 | Communicate with County teams to test access to EUST 3 | January 26, 2026 8:00 AM | January 30, 2026 5:00 PM |  | 1725SS | Start No Earlier Than | 1/26/26 | 5 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
43659 | Confirm EUST 3 environment connectivity for all counties | January 26, 2026 8:00 AM | January 30, 2026 5:00 PM | 1724SS | 1726FS-5d | As Soon As Possible | NA | 5 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
43660 | Confirm EUST 3 county user access to the environment | February 10, 2026 8:00 AM | February 17, 2026 5:00 PM | 1725FS-5d,1754 |  | As Soon As Possible | NA | 5 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
43661 | User Provisioning | October 13, 2025 8:00 AM | January 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 66 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
43662 | Identify Office / Unit Structure Needs for EUST 3 | October 13, 2025 8:00 AM | October 17, 2025 5:00 PM |  | 1761 | Start No Earlier Than | 10/13/25 | 5 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
43663 | Provision users to EUST environment | November 26, 2025 8:00 AM | December 17, 2025 5:00 PM | 1721FS-1d |  | As Soon As Possible | NA | 15 | 454d | NA | NA | 0 days? | No | NA | NA | NA | 0
43664 | Produce Template for Office / Unit Structure | November 26, 2025 8:00 AM | November 26, 2025 5:00 PM |  | 1731 | Start No Earlier Than | 11/26/25 | 1 | 434d | NA | NA | 0 s? | No | NA | NA | NA | 0
43665 | Distribute the Template to Counties | November 28, 2025 8:00 AM | November 28, 2025 5:00 PM | 1730 | 1732 | Start No Earlier Than | 11/26/25 | 1 | 434d | NA | NA | 0 s? | No | NA | NA | NA | 0
43666 | Counties to fill out Office / Unit Structure and Return | December 1, 2025 8:00 AM | December 12, 2025 5:00 PM | 1731 | 1733 | As Soon As Possible | NA | 10 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
43667 | Coordinate with OKTA to complete IP whitelisting for counties in EUST | December 15, 2025 8:00 AM | January 6, 2026 5:00 PM | 1732 | 1734SS | As Soon As Possible | NA | 15 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
43668 | Confirm User Set up w/OKTA team | December 15, 2025 8:00 AM | December 19, 2025 5:00 PM | 1733SS | 1735FS-1d | As Soon As Possible | NA | 5 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
43669 | Assign Profile, Permissions and complete user set up/complete spreadsheet | December 19, 2025 8:00 AM | January 5, 2026 5:00 PM | 1734FS-1d | 1736FS-1d | As Soon As Possible | NA | 10 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
43670 | Receive communication from OKTA team that user set up is complete and active | January 5, 2026 8:00 AM | January 9, 2026 5:00 PM | 1735FS-1d | 1739,1737 | As Soon As Possible | NA | 5 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
43671 | Upload Office / Unit Structure from templates | January 12, 2026 8:00 AM | January 16, 2026 5:00 PM | 1736 | 1738SS-1d | As Soon As Possible | NA | 5 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
43672 | Provision Users for EUST 3 (Okta Team) | January 9, 2026 8:00 AM | January 15, 2026 5:00 PM | 1737SS-1d |  | As Soon As Possible | NA | 5 | 435d | NA | NA | 0 days? | No | NA | NA | NA | 0
43673 | Communicate to end users and confirm access (CC SPOC) or if they need a PW reset | January 16, 2026 8:00 AM | January 16, 2026 5:00 PM | 1736 |  | Start No Earlier Than | 1/16/26 | 1 | 434d | NA | NA | 0 s? | No | NA | NA | NA | 0
43674 | EUST 3 Infrastructure / Environment Setup | October 28, 2024 8:00 AM | February 9, 2026 5:00 PM |  |  | As Soon As Possible | NA | 320 | 419d | NA | NA | 0 days? | No | 10/28/24 | NA | NA | 0.02
43675 | Set up Salesforce EUST environment | October 28, 2024 8:00 AM | October 28, 2024 5:00 PM |  |  | Start No Earlier Than | 10/28/24 | 1 | 0d | NA | NA | 0 s? | No | 10/28/24 | 10/28/24 | NA | 1
43676 | Setup Okta Integration | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM | 1743SS | 1751SS | As Soon As Possible | NA | 1 | 443d | NA | NA | 0 s? | No | NA | NA | NA | 0
43677 | Mule API Updated Deployment | January 5, 2026 8:00 AM | January 9, 2026 5:00 PM |  | 1742SS | Start No Earlier Than | 1/5/26 | 5 | 439d | NA | NA | 0 days? | No | NA | NA | NA | 0
43678 | DocuEdge Deployment | January 5, 2026 8:00 AM | January 9, 2026 5:00 PM |  |  | Start No Earlier Than | 1/5/26 | 5 | 439d | NA | NA | 0 days? | No | NA | NA | NA | 0
43679 | DocuEdge Mule Endpoint Updated Deployment | January 5, 2026 8:00 AM | January 6, 2026 5:00 PM |  | 1746 | Start No Earlier Than | 1/5/26 | 2 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
43680 | DocuEdge Configuration | January 7, 2026 8:00 AM | January 9, 2026 5:00 PM | 1745 | 1749 | As Soon As Possible | NA | 3 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
43681 | AEM Updated Deployment | January 5, 2026 8:00 AM | January 6, 2026 5:00 PM |  |  | Start No Earlier Than | 1/5/26 | 2 | 442d | NA | NA | 0 days? | No | NA | NA | NA | 0
43682 | SOLR API Updated Deployment | January 5, 2026 8:00 AM | January 6, 2026 5:00 PM |  |  | Start No Earlier Than | 1/5/26 | 2 | 442d | NA | NA | 0 days? | No | NA | NA | NA | 0
43683 | Salesforce Integration | January 12, 2026 8:00 AM | January 16, 2026 5:00 PM | 1746 | 1750 | As Soon As Possible | NA | 5 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
43684 | Deploy code build (Initial) | January 20, 2026 8:00 AM | January 26, 2026 5:00 PM | 1749 | 1752 | As Soon As Possible | NA | 5 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
43685 | Snowflake Updated Deployment | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM | 1742SS |  | Start No Earlier Than | 1/5/26 | 1 | 443d | NA | NA | 0 s? | No | NA | NA | NA | 0
43686 | Syncing users in Okta | January 27, 2026 8:00 AM | February 2, 2026 5:00 PM | 1750 | 1753 | As Soon As Possible | NA | 5 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
43687 | Validate Access for Testing Team | February 3, 2026 8:00 AM | February 4, 2026 5:00 PM | 1752 | 1754 | As Soon As Possible | NA | 2 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
43688 | Smoke Test Initial Environment Build | February 5, 2026 8:00 AM | February 9, 2026 5:00 PM | 1753 | 1726 | As Soon As Possible | NA | 3 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
43689 | Deployment to EUST 3 Environment | November 17, 2025 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 47 | 429d | NA | NA | 0 days? | No | NA | NA | NA | 0
43690 | Final Code Deployment for EUST 3 Admin | January 6, 2026 8:00 AM | January 6, 2026 5:00 PM |  | 1758 | Start No Earlier Than | 1/6/26 | 1 | 437d | NA | NA | 0 s? | No | NA | NA | NA | 0
43691 | Final Code Depoloyment for EUST 3 | January 20, 2026 8:00 AM | January 26, 2026 5:00 PM | 1759 |  | As Soon As Possible | NA | 5 | 429d | NA | NA | 0 days? | No | NA | NA | NA | 0
43692 | Smoke Test Environment | January 7, 2026 8:00 AM | January 13, 2026 5:00 PM | 1756 |  | As Soon As Possible | NA | 5 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
43693 | EUST 3 Data Readiness | November 17, 2025 8:00 AM | January 16, 2026 5:00 PM |  | 1757 | As Soon As Possible | NA | 42 | 429d | NA | NA | 0 days? | No | NA | NA | NA | 0
43694 | Identify Transactional Data Needs for EUST 3 (including volume) | November 17, 2025 8:00 AM | December 30, 2025 5:00 PM |  | 1761 | Start No Earlier Than | 11/17/25 | 30 | 436d | NA | NA | 0 days? | No | NA | NA | NA | 0
43695 | Confirm Data needs for EUST 3 Office / Unit and Transactional Data | December 31, 2025 8:00 AM | January 7, 2026 5:00 PM | 1728,1760 |  | As Soon As Possible | NA | 5 | 436d | NA | NA | 0 days? | No | NA | NA | NA | 0
43696 | Develop steps to manually create Transactional Data | December 8, 2025 8:00 AM | January 6, 2026 5:00 PM |  |  | Start No Earlier Than | 12/8/25 | 20 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
43697 | Deploy EUST 3 Package and Day 0 Data | January 5, 2026 8:00 AM | January 16, 2026 5:00 PM |  |  | Start No Earlier Than | 1/5/26 | 10 | 429d | NA | NA | 0 days? | No | NA | NA | NA | 0
43698 | EUST 3 - Conduct User Training | July 14, 2025 8:00 AM | February 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 157 | 407d | NA | NA | 0 days? | No | 7/14/25 | NA | NA | 0.40999999999999998
43699 | Virtual Instructor-Led Training (1/12/26 - 2/20/26) | July 14, 2025 8:00 AM | January 29, 2026 5:00 PM |  |  | As Soon As Possible | NA | 138 | 426d | NA | NA | 0 days? | No | 7/14/25 | NA | NA | 0.55000000000000004
43700 | Develop Training Curriculum and Materials (Drop 1) | July 14, 2025 8:00 AM | August 1, 2025 5:00 PM | 1629 |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 0 days? | No | 7/14/25 | 8/1/25 | NA | 1
43701 | Develop Training Curriculum and Materials (Drop 2) | August 18, 2025 8:00 AM | September 8, 2025 5:00 PM | 1641 |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 0 days? | No | 8/18/25 | 9/8/25 | NA | 1
43702 | Develop Training Curriculum and Materials (Drop 3) | September 16, 2025 8:00 AM | October 6, 2025 5:00 PM | 1653 |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 0 days? | No | 9/16/25 | 10/6/25 | NA | 1
43703 | Develop Training Curriculum and Materials (Drop 4) | November 17, 2025 8:00 AM | December 8, 2025 5:00 PM | 1665 | 1771FF+7d | As Soon As Possible | NA | 15 | 439d | NA | NA | 0 days? | No | NA | NA | NA | 0
43704 | Develop Training Curriculum and Materials (Drop 5) | January 15, 2026 8:00 AM | January 29, 2026 5:00 PM | 1677 |  | As Soon As Possible | NA | 10 | 426d | NA | NA | 0 days? | No | NA | NA | NA | 0
43705 | Confirm Number of Admin Console Training Attendees (by Course) | December 17, 2025 8:00 AM | December 17, 2025 5:00 PM | 1769FF+7d | 1773FS+10d | Finish No Earlier Than | 12/17/25 | 1 | 439d | NA | NA | 0 s? | No | NA | NA | NA | 0
43706 | Schedule Training Sessions | December 22, 2025 8:00 AM | December 22, 2025 5:00 PM |  |  | Start No Earlier Than | 12/22/25 | 1 | 451d | NA | NA | 0 s? | No | NA | NA | NA | 0
43707 | Finalize Training Materials | January 5, 2026 8:00 AM | January 9, 2026 5:00 PM | 1771FS+10d |  | As Soon As Possible | NA | 5 | 439d | NA | NA | 0 days? | No | NA | NA | NA | 0
43708 | Load Quick Reference Guides and Knowledge Base Articles for Admin | January 12, 2026 8:00 AM | January 16, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 5 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
43709 | Deliver training for EUST 3 Admin Console | January 12, 2026 8:00 AM | January 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 5 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
43710 | Support Office Hours / Delivery Make-Up Sessions (As needed) | January 12, 2026 8:00 AM | January 16, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 5 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
43711 | Load Quick Reference Guides and Knowledge Base Articles for EUST3 | January 12, 2026 8:00 AM | January 16, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 5 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
43712 | Deliver training for EUST 3 | January 12, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 14 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
43713 | Support Office Hours / Delivery Make-Up Sessions (As needed) | January 12, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 14 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
43714 | Load Quick Reference Guides and Knowledge Base Articles for Reporting Training | January 30, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/30/26 | 1 | 425d | NA | NA | 0 s? | No | NA | NA | NA | 0
43715 | Deliver training for EUST 3 Reporting Training | February 23, 2026 8:00 AM | February 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 4 | 407d | NA | NA | 0 days? | No | NA | NA | NA | 0
43716 | Support Office Hours / Delivery Make-Up Sessions (As needed) | February 23, 2026 8:00 AM | February 26, 2026 5:00 PM |  |  | Start No Earlier Than | 2/23/26 | 4 | 407d | NA | NA | 0 days? | No | NA | NA | NA | 0
43717 | EUST 3 - Deployment to CARES EUST V1 | January 6, 2026 8:00 AM | January 27, 2026 5:00 PM |  |  | As Soon As Possible | NA | 15 | 428d | January 24, 2025 8:00 AM | March 18, 2025 5:00 PM | 37 days | No | NA | NA | NA | 0
43718 | Confirm readiness of environment | January 6, 2026 8:00 AM | January 12, 2026 5:00 PM |  | 1786,1787,1785,1788,1789,1790,1791 | Start No Earlier Than | 1/6/26 | 5 | 428d | NA | NA | 0 days? | No | NA | NA | NA | 0
43719 | Confirm interface integration connection | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 1784 |  | Start No Earlier Than | 12/2/24 | 10 | 428d | NA | NA | 0 days? | No | NA | NA | NA | 0
43720 | Test interface integration with EUST environment - FCED/CalSAWS | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 1784 |  | As Soon As Possible | NA | 10 | 428d | NA | NA | 0 days? | No | NA | NA | NA | 0
43721 | Test interface integration with EUST environment - JNET/San Bern. | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 1784 |  | As Soon As Possible | NA | 10 | 428d | NA | NA | 0 days? | No | NA | NA | NA | 0
43722 | Test interface integration with EUST environment - SDM/Evident Change | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 1784 |  | As Soon As Possible | NA | 10 | 428d | NA | NA | 0 days? | No | NA | NA | NA | 0
43723 | Test interface integration with EUST environment - P-CIS/Opeeka | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 1784 |  | As Soon As Possible | NA | 10 | 428d | NA | NA | 0 days? | No | NA | NA | NA | 0
43724 | Test interface integration with EUST environment - LIS/FAS/CDSS | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 1784 |  | As Soon As Possible | NA | 10 | 428d | NA | NA | 0 days? | No | NA | NA | NA | 0
43725 | Test interface integration with EUST environment - CECRIS/CDSS | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 1784 |  | As Soon As Possible | NA | 10 | 428d | NA | NA | 0 days? | No | NA | NA | NA | 0
43726 | EUST 3 Go-No-Go | January 5, 2026 8:00 AM | February 9, 2026 5:00 PM |  |  | As Soon As Possible | NA | 25 | 419d | NA | NA | 0 days? | No | NA | NA | NA | 0
43727 | EUST 3 Admin Go-No-Go | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM |  |  | Start No Earlier Than | 1/5/26 | 1 | 443d | NA | NA | 0 s? | No | NA | NA | NA | 0
43728 | EUST 3 Go-No-Go (session 1) | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM |  |  | Start No Earlier Than | 1/5/26 | 1 | 443d | NA | NA | 0 s? | No | NA | NA | NA | 0
43729 | EUST 3 Final Go-No-Go | January 26, 2026 8:00 AM | January 26, 2026 5:00 PM |  |  | Start No Earlier Than | 1/26/26 | 1 | 429d | NA | NA | 0 s? | No | NA | NA | NA | 0
43730 | EUST 3 Reporting - Confirm EUST Readiness | February 9, 2026 8:00 AM | February 9, 2026 5:00 PM |  |  | Start No Earlier Than | 2/9/26 | 1 | 419d | NA | NA | 0 s? | No | NA | NA | NA | 0
43731 | Validation for all scenarios | January 30, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/30/26 | 1 | 425d | NA | NA | 0 s? | No | NA | NA | NA | 0
43732 | EUST 3 - Execution | January 13, 2026 8:00 AM | April 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 56 | 3d | NA | NA | 0 days? | No | NA | NA | NA | 0
43733 | Facilitate EUST 3 Admin Kickoff | January 20, 2026 8:00 AM | January 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 1 | 433d | NA | NA | 0 s? | No | NA | NA | NA | 0
43734 | EUST 3 Admin Testing Start | January 20, 2026 8:00 AM | January 20, 2026 5:00 PM |  |  | Start No Earlier Than | 1/20/26 | 1 | 433d | NA | NA | 0 s? | No | NA | NA | NA | 0
43735 | Facilitate EUST 3 Kickoff | February 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 1 | 424d | NA | NA | 0 s? | No | NA | NA | NA | 0
43736 | EUST 3 Testing Start | February 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 1 | 424d | NA | NA | 0 s? | No | NA | NA | NA | 0
43737 | Facilitate EUST 3 Reporting Kickoff | February 23, 2026 8:00 AM | February 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 1 | 410d | NA | NA | 0 s? | No | NA | NA | NA | 0
43738 | EUST 3 Reporting Testing Start | February 23, 2026 8:00 AM | February 23, 2026 5:00 PM |  | 1815SS | As Soon As Possible | NA | 1 | 410d | NA | NA | 0 s? | No | NA | NA | NA | 0
43739 | EUST 3 Validation | January 16, 2026 8:00 AM | April 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 53 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43740 | EUST 3 Admin Console (Partial M32) | January 20, 2026 8:00 AM | January 30, 2026 5:00 PM |  | 1807 | Start No Earlier Than | 1/20/26 | 9 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43741 | Validation for Milestone 1, 2, 3 ,4, 5, 6, 8, 15, 15.1, 19, 20, 20.1 | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 1806 | 1808SS,1809SS,1810SS,1811SS,1812SS,1813SS,1814SS | As Soon As Possible | NA | 43 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43742 | Test interface integration with EUST environment - FCED/CalSAWS | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 1807SS |  | As Soon As Possible | NA | 43 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43743 | Test interface integration with EUST environment - JNET/San Bern. | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 1807SS |  | As Soon As Possible | NA | 43 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43744 | Test interface integration with EUST environment - SDM/Evident Change | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 1807SS |  | As Soon As Possible | NA | 43 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43745 | Test interface integration with EUST environment - P-CIS/Opeeka | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 1807SS |  | As Soon As Possible | NA | 43 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43746 | Test interface integration with EUST environment - LIS/FAS/CDSS | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 1807SS |  | As Soon As Possible | NA | 43 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43747 | Test interface integration with EUST environment - CECRIS/CDSS | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 1807SS |  | As Soon As Possible | NA | 43 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43748 | EUST for Milestones 6.1, 7, 7.1, 9, 10, 10.1, 11, 13, 14, 16, 17, 18, 20.1, 21, 23, 23.1, 23.2, 24, 26, 26.1, 27, 28, 29, 30, 32 | February 2, 2026 8:00 AM | April 3, 2026 5:00 PM | 1807SS |  | As Soon As Possible | NA | 43 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43749 | EUST 3 Reporting | February 23, 2026 8:00 AM | April 3, 2026 5:00 PM | 1804SS |  | Start No Earlier Than | 2/23/26 | 29 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43750 | EUST 3 Feedback | January 13, 2026 8:00 AM | April 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 56 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43751 | Prepare MS Teams feedback template for feedback in alignment with JIRA fields | January 13, 2026 8:00 AM | January 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 4 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
43752 | Schedule EUST Office Hours | January 13, 2026 8:00 AM | January 13, 2026 5:00 PM |  |  | As Soon As Possible | NA | 1 | 437d | NA | NA | 0 s? | No | NA | NA | NA | 0
43753 | Conduct Office Hours | January 16, 2026 8:00 AM | April 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/16/26 | 53 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43754 | Schedule prioritization sessions to prioritize feedback | January 13, 2026 8:00 AM | January 13, 2026 5:00 PM |  |  | Start No Earlier Than | 1/13/26 | 1 | 437d | NA | NA | 0 s? | No | NA | NA | NA | 0
43755 | Upload the spreadsheet w/user feedback to JIRA | January 20, 2026 8:00 AM | April 3, 2026 5:00 PM |  | 1822SS,1823SS,1824SS | Start No Earlier Than | 1/20/26 | 52 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43756 | Manage MS teams feedback | January 20, 2026 8:00 AM | April 3, 2026 5:00 PM | 1821SS |  | As Soon As Possible | NA | 52 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43757 | EUST 3 - Build/SIT Findings | January 20, 2026 8:00 AM | April 3, 2026 5:00 PM | 1821SS |  | As Soon As Possible | NA | 52 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43758 | EUST 3 - QA Findings | January 20, 2026 8:00 AM | April 3, 2026 5:00 PM | 1821SS |  | Start No Earlier Than | 1/16/26 | 52 | 382d | NA | NA | 0 days? | No | NA | NA | NA | 0
43759 | EUST 3 - Triage/Prioritize Findings | February 23, 2026 8:00 AM | April 14, 2026 5:00 PM |  |  | As Soon As Possible | NA | 36 | 375d | NA | NA | 0 days? | No | NA | NA | NA | 0
43760 | Sentiment Survey | February 23, 2026 8:00 AM | April 14, 2026 5:00 PM |  |  | As Soon As Possible | NA | 36 | 375d | NA | NA | 0 days? | No | NA | NA | NA | 0
43761 | Coordinate with comms team to prepare mid-point sentiment survey | February 23, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/23/26 | 5 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
43762 | Send link to mid-point survey | March 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  | 1829SS | Start No Earlier Than | 3/2/26 | 1 | 396d | NA | NA | 0 s? | No | NA | NA | NA | 0
43763 | Consoladate mid-point sentiment survey | March 2, 2026 8:00 AM | March 13, 2026 5:00 PM | 1828SS |  | As Soon As Possible | NA | 10 | 396d | NA | NA | 0 days? | No | NA | NA | NA | 0
43764 | Coordinate with Communications team to prepare the Sentiment Survey for EUST | March 30, 2026 8:00 AM | April 6, 2026 5:00 PM |  | 1831SS | Start No Earlier Than | 3/30/26 | 5 | 376d | NA | NA | 0 days? | No | NA | NA | NA | 0
43765 | Send link to Sentiment Survey to EUST Participants | April 1, 2026 8:00 AM | April 1, 2026 5:00 PM | 1830SS | 1832SS | Start No Earlier Than | 4/1/26 | 1 | 375d | NA | NA | 0 s? | No | NA | NA | NA | 0
43766 | Consoladate sentiment survey results for close out presentation | April 1, 2026 8:00 AM | April 14, 2026 5:00 PM | 1831SS |  | As Soon As Possible | NA | 10 | 375d | NA | NA | 0 days? | No | NA | NA | NA | 0
43767 | EUST 3 - Closeout | April 13, 2026 8:00 AM | May 19, 2026 5:00 PM |  |  | As Soon As Possible | NA | 27 | 350d | NA | NA | 0 days? | No | NA | NA | NA | 0
43768 | Confirm exit criteria for EUST is met | April 13, 2026 8:00 AM | April 13, 2026 5:00 PM |  | 1835 | Start No Earlier Than | 4/13/26 | 1 | 350d | NA | NA | 0 s? | No | NA | NA | NA | 0
43769 | Prepare presentations to ELT | April 14, 2026 8:00 AM | April 24, 2026 5:00 PM | 1834 | 1838FS+15d,1836 | As Soon As Possible | NA | 9 | 350d | NA | NA | 0 days? | No | NA | NA | NA | 0
43770 | Present to ELT (DOF, BOD tentatively as well) | April 27, 2026 8:00 AM | April 27, 2026 5:00 PM | 1835 | 1837 | As Soon As Possible | NA | 1 | 365d | NA | NA | 0 s? | No | NA | NA | NA | 0
43771 | Schedule Presentation to the counties | April 28, 2026 8:00 AM | April 28, 2026 5:00 PM | 1836 |  | As Soon As Possible | NA | 1 | 365d | NA | NA | 0 s? | No | NA | NA | NA | 0
43772 | Present to the counties | May 18, 2026 8:00 AM | May 18, 2026 5:00 PM | 1835FS+15d | 1839 | As Soon As Possible | NA | 1 | 350d | NA | NA | 0 s? | No | NA | NA | NA | 0
43773 | Send EUST wrap-up email confirmation | May 19, 2026 8:00 AM | May 19, 2026 5:00 PM | 1838 |  | As Soon As Possible | NA | 1 | 350d | NA | NA | 0 s? | No | NA | NA | NA | 0
11209 | EUST - 3R (Reports) | December 26, 2025 8:00 AM | June 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 108 | -17d | December 26, 2025 8:00 AM | June 2, 2026 5:00 PM | 108 days | No | NA | NA | NA | 0
11210 | EUST - 3R Preparation | December 26, 2025 8:00 AM | February 24, 2026 5:00 PM |  |  | As Soon As Possible | NA | 40 | -17d | December 26, 2025 8:00 AM | February 24, 2026 5:00 PM | 40 days | No | NA | NA | NA | 0
11211 | EUST 3R - Identification and validation of scenarios | December 26, 2025 8:00 AM | January 26, 2026 5:00 PM | 525FS-3d,548FS-3d | 1843,1848 | As Soon As Possible | NA | 20 | -13d | December 26, 2025 8:00 AM | January 26, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
11212 | EUST 3R - Deployment to Staging | February 2, 2026 8:00 AM | February 13, 2026 5:00 PM | 525,548,1842,2985,2986,2987,2988,2989,2990,2991,2992,2993,2994,2995,2996,2997,2998,2999,3000,3001,3002,3003,3004,3005,3007,3008,3009,3010,3011,3012,3013,3014 | 1844,1845,1846,1847,1848 | As Soon As Possible | NA | 10 | -17d | February 2, 2026 8:00 AM | February 13, 2026 5:00 PM | 10 days | No | NA | NA | NA | 0
11213 | EUST 3R - User setup and access validation | February 17, 2026 8:00 AM | February 23, 2026 5:00 PM | 1843 | 1848 | As Soon As Possible | NA | 5 | -17d | February 17, 2026 8:00 AM | February 23, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
11214 | EUST 3R - Pdl validation of scenarios in the environment | February 17, 2026 8:00 AM | February 23, 2026 5:00 PM | 1843 | 1848 | As Soon As Possible | NA | 5 | -17d | February 17, 2026 8:00 AM | February 23, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
11215 | EUST 3R - Conduct EUST Training | February 17, 2026 8:00 AM | February 23, 2026 5:00 PM | 1843 | 1848 | As Soon As Possible | NA | 5 | -17d | February 17, 2026 8:00 AM | February 23, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
11216 | EUST 3R - Confirm EUST Readiness | February 17, 2026 8:00 AM | February 23, 2026 5:00 PM | 1843,1287 | 1848 | As Soon As Possible | NA | 5 | -17d | February 17, 2026 8:00 AM | February 23, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
11217 | EUST 3R Go-No-Go | February 24, 2026 8:00 AM | February 24, 2026 5:00 PM | 1847,1843,1844,1845,1846,1842,2976,2977,2978,2979,2980,2981,2982 | 1850FS-1d | As Soon As Possible | NA | 1 | -17d | February 24, 2026 8:00 AM | February 24, 2026 5:00 PM | 1 | No | NA | NA | NA | 0
11218 | EUST - 3R Execution | February 24, 2026 8:00 AM | June 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 69 | -17d | February 24, 2026 8:00 AM | June 2, 2026 5:00 PM | 69 days | No | NA | NA | NA | 0
11220 | EUST for Milestones 29, 30 | February 24, 2026 8:00 AM | April 6, 2026 5:00 PM | 528FS-1d,550FS-1d,1848FS-1d | 1851,4779 | As Soon As Possible | NA | 29 | -17d | February 24, 2026 8:00 AM | April 6, 2026 5:00 PM | 29 days | No | NA | NA | NA | 0
11221 | EUST 3R - Triage/Prioritize Findings | April 7, 2026 8:00 AM | April 20, 2026 5:00 PM | 1850 | 1852 | As Soon As Possible | NA | 10 | -17d | April 7, 2026 8:00 AM | April 20, 2026 5:00 PM | 10 days | No | NA | NA | NA | 0
11222 | EUST 3R - Build/SIT Findings | April 21, 2026 8:00 AM | May 18, 2026 5:00 PM | 1851 | 1853 | As Soon As Possible | NA | 20 | -17d | April 21, 2026 8:00 AM | May 18, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
11223 | EUST 3R - QA Findings | May 19, 2026 8:00 AM | June 2, 2026 5:00 PM | 1852 | 1856FS-16d | As Soon As Possible | NA | 10 | -17d | May 19, 2026 8:00 AM | June 2, 2026 5:00 PM | 10 days | No | NA | NA | NA | 0
2872 | EUST - 4 | May 1, 2026 5:00 PM | July 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 48 | -12d | May 8, 2026 5:00 PM | July 10, 2026 5:00 PM | 43 days | No | NA | NA | NA | 0
11541 | EUST 4 Go-No-Go | May 1, 2026 5:00 PM | May 1, 2026 5:00 PM | 1387,2817,2818,2819,2820,2822,2823,2824,2825,2827,2828,2829,2830,2831,2832,2836,2837,2838,2839,2840,2841,2842,2843,2844,2845,2846,2847,2848,2849,2850,2851,2852,2853,2854,2855,2856,2857,2858,2859,2860,2861,2862,2863,2864,2865,2866,2867,2868,2869,2876 | 5630,5623FS-73d | As Soon As Possible | NA | 0 | 80d | May 8, 2026 5:00 PM | May 8, 2026 5:00 PM | 0 days | Yes | NA | NA | NA | 0
2873 | Validation for All Milestones | May 11, 2026 8:00 AM | June 5, 2026 5:00 PM | 1853FS-16d | 1857SS,5611FF-5d,5612FF+8d,5613FF+10d | As Soon As Possible | NA | 19 | -17d | May 11, 2026 8:00 AM | June 5, 2026 5:00 PM | 19 days | No | NA | NA | NA | 0
6698 | EUST 4 - Triage/Prioritize Findings | May 11, 2026 8:00 AM | June 5, 2026 5:00 PM | 1856SS | 1858SS+10d | As Soon As Possible | NA | 19 | 48d | May 11, 2026 8:00 AM | June 5, 2026 5:00 PM | 19 days | No | NA | NA | NA | 0
6699 | EUST 4 - Build/SIT Findings | May 26, 2026 8:00 AM | July 10, 2026 5:00 PM | 1857SS+10d | 1859FS-10d | As Soon As Possible | NA | 33 | 48d | May 26, 2026 8:00 AM | July 10, 2026 5:00 PM | 33 days | No | NA | NA | NA | 0
6700 | EUST 4 - QA Findings | June 26, 2026 8:00 AM | July 10, 2026 5:00 PM | 1858FS-10d | 5628 | As Soon As Possible | NA | 10 | 48d | June 26, 2026 8:00 AM | July 10, 2026 5:00 PM | 10 days | No | NA | NA | NA | 0
10290 | Schedule Mitigation Checkpoints | September 20, 2024 8:00 AM | November 14, 2024 5:00 PM |  |  | As Soon As Possible | NA | 39 | 0d | September 20, 2024 8:00 AM | November 14, 2025 5:00 PM | 289 days | No | 9/20/24 | 11/14/24 | NA | 1
10295 | Schedule Mitigation Checkpoint # 1 | September 20, 2024 8:00 AM | September 20, 2024 5:00 PM |  | 1862FS+37d | Must Start On | 9/20/24 | 1 | 0d | September 20, 2024 8:00 AM | September 20, 2024 5:00 PM | 1 | No | 9/20/24 | 9/20/24 | NA | 1
10291 | Schedule Mitigation Checkpoint # 2 | November 14, 2024 8:00 AM | November 14, 2024 5:00 PM | 1861FS+37d |  | As Soon As Possible | NA | 1 | 0d | November 14, 2025 8:00 AM | November 14, 2025 5:00 PM | 1 | No | 11/14/24 | 11/14/24 | NA | 1
13137 | Deliverables from PMO Schedule | October 1, 2024 8:00 AM | October 11, 2027 5:00 PM |  |  | As Soon As Possible | NA | 758 | 0d | NA | NA | 0 days? | No | 10/1/24 | NA | NA | 0.78000000000000003
13100 | System Technical Recovery Plan (STRP) CARES V1 2024 - 2025 | October 1, 2024 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 165 | 0d | NA | NA | 0 days? | No | 10/1/24 | 5/30/25 | NA | 1
13101 | STRP: Draft new Plan | October 1, 2024 8:00 AM | November 26, 2024 5:00 PM |  | 1866FS-20d | Start No Earlier Than | 10/1/24 | 40 | 0d | NA | NA | 0 days? | No | 10/1/24 | 11/26/24 | NA | 1
13102 | STRP: Collect input from Internal Teams (including all as indicated on the RACI) | October 29, 2024 8:00 AM | December 27, 2024 5:00 PM | 1865FS-20d | 1867FS-19d | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 10/29/24 | 12/27/24 | NA | 1
13108 | STRP: Update based on Reviews | December 2, 2024 8:00 AM | January 10, 2025 5:00 PM | 1866FS-19d | 1868 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 12/2/24 | 1/10/25 | NA | 1
13109 | STRP: Collect Feedback from Management and IPO/IV&V Reviews (based on RACI) | January 13, 2025 8:00 AM | April 2, 2025 5:00 PM | 1867 | 1869 | As Soon As Possible | NA | 55 | 0d | NA | NA | 0 days? | No | 1/13/25 | 4/2/25 | NA | 1
13110 | STRP: Update based on Management Team and IPO/IV&V Reviews | April 3, 2025 8:00 AM | April 9, 2025 5:00 PM | 1868 | 1870 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 4/3/25 | 4/9/25 | NA | 1
13111 | STRP: ELT Review and Approval | April 10, 2025 8:00 AM | April 23, 2025 5:00 PM | 1869 | 1871 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 4/10/25 | 4/23/25 | NA | 1
13103 | STRP: Update based on ELT Review | April 24, 2025 8:00 AM | April 29, 2025 5:00 PM | 1870 | 1872 | As Soon As Possible | NA | 4 | 0d | NA | NA | 0 days? | No | 4/24/25 | 4/29/25 | NA | 1
13104 | STRP: Finalize Plan and submit to PMO | April 30, 2025 8:00 AM | April 30, 2025 5:00 PM | 1871 | 1873 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 4/30/25 | 4/30/25 | NA | 1
13105 | STRP: ADA Remediation | May 1, 2025 8:00 AM | May 29, 2025 5:00 PM | 1872 | 1874 | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/29/25 | NA | 1
13106 | STRP: Update PMO Tracking and Publish to Project Management SP Folder | May 30, 2025 8:00 AM | May 30, 2025 5:00 PM | 1873 | 1875 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 5/30/25 | 5/30/25 | NA | 1
13107 | SPR 6: CWS-CARES System Technical Recovery Plan (CARES V1) | May 30, 2025 5:00 PM | May 30, 2025 5:00 PM | 1874 |  | As Soon As Possible | NA | 0 | 0d | NA | NA | 0 days? | Yes | 5/30/25 | 5/30/25 | NA | 1
13112 | CARES V1 Final Cutover Plan (V1CP) 2025 | December 31, 2024 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 125 | 0d | NA | NA | 0 days? | No | 12/31/24 | 6/30/25 | NA | 1
13113 | V1CP: Determine CARES V1 Final Cutover Plan | December 31, 2024 8:00 AM | February 18, 2025 5:00 PM |  | 1878 | Start No Earlier Than | 12/31/24 | 33 | 0d | NA | NA | 0 days? | No | 12/31/24 | 2/18/25 | NA | 1
13114 | V1CP: Update Final Cutover plan | February 19, 2025 8:00 AM | April 8, 2025 5:00 PM | 1877 | 1879 | As Soon As Possible | NA | 34 | 0d | NA | NA | 0 days? | No | 2/19/25 | 4/8/25 | NA | 1
13115 | V1CP: Draft pilot, contingency, rollback approach for board review for Final Cutover Plan | April 9, 2025 8:00 AM | May 1, 2025 5:00 PM | 1878 | 1880 | As Soon As Possible | NA | 17 | 0d | NA | NA | 0 days? | No | 4/9/25 | 5/1/25 | NA | 1
13116 | V1CP: Board review and confirmation of cutover approach for Final Cutover Plan | May 2, 2025 8:00 AM | May 8, 2025 5:00 PM | 1879 | 1881 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 5/2/25 | 5/8/25 | NA | 1
13117 | V1CP: Collect input from Internal Teams for Final Cutover Plan (including all as indicated on the RACI) | May 9, 2025 8:00 AM | May 15, 2025 5:00 PM | 1880 | 1882 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 5/9/25 | 5/15/25 | NA | 1
13120 | V1CP: Update based on Reviews for Final Cutover Plan | May 16, 2025 8:00 AM | May 21, 2025 5:00 PM | 1881 | 1883 | As Soon As Possible | NA | 4 | 0d | NA | NA | 0 days? | No | 5/16/25 | 5/21/25 | NA | 1
13121 | V1CP: Collect Feedback from Management and IPO/IV&V Reviews for Final Cutover Plan (based on RACI) | May 22, 2025 8:00 AM | May 28, 2025 5:00 PM | 1882 | 1884 | As Soon As Possible | NA | 4 | 0d | NA | NA | 0 days? | No | 5/22/25 | 5/28/25 | NA | 1
13122 | V1CP: Update based on Management Team and IPO/IV&V Reviews for Final Cutover Plan | May 29, 2025 8:00 AM | June 4, 2025 5:00 PM | 1883 | 1885 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 5/29/25 | 6/4/25 | NA | 1
13123 | V1CP: ELT Review and Approval for Final Cutover Plan | June 5, 2025 8:00 AM | June 12, 2025 5:00 PM | 1884 | 1886 | As Soon As Possible | NA | 6 | 0d | NA | NA | 0 days? | No | 6/5/25 | 6/12/25 | NA | 1
13124 | V1CP: Update based on ELT Review for Final Cutover Plan | June 13, 2025 8:00 AM | June 17, 2025 5:00 PM | 1885 | 1887 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 6/13/25 | 6/17/25 | NA | 1
13125 | V1CP: Finalize Plan and submit Final Cutover Plan to PMO | June 18, 2025 8:00 AM | June 18, 2025 5:00 PM | 1886 | 1888 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/18/25 | 6/18/25 | NA | 1
13126 | V1CP: ADA Remediation for Final Cutover Plan | June 19, 2025 8:00 AM | June 27, 2025 5:00 PM | 1887 | 1889 | As Soon As Possible | NA | 7 | 0d | NA | NA | 0 days? | No | 6/19/25 | 6/27/25 | NA | 1
13127 | V1CP: Update PMO Tracking and Publish to Project Management SP Folder | June 30, 2025 8:00 AM | June 30, 2025 5:00 PM | 1888 | 1890 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/30/25 | 6/30/25 | NA | 1
13128 | SPR 6: Final V1 Cutover Plan Complete | June 30, 2025 5:00 PM | June 30, 2025 5:00 PM | 1889 |  | As Soon As Possible | NA | 0 | 0d | NA | NA | 0 days? | Yes | 6/30/25 | 6/30/25 | NA | 1
13118 | CARES V2 Cutover Plan (V2CP) 2027 | June 1, 2027 8:00 AM | October 11, 2027 5:00 PM |  |  | As Soon As Possible | NA | 93 | 0d | NA | NA | 0 days? | No | NA | NA | NA | 0
13119 | V2CP: Draft new plan or update existing V1 Cutover Plan | June 1, 2027 8:00 AM | July 27, 2027 5:00 PM |  | 1893 | Start No Earlier Than | 6/1/27 | 40 | 0d | NA | NA | 0 days? | No | NA | NA | NA | 0
13129 | V2CP: Collect input from Internal Teams (including all as indicated on the RACI) | July 28, 2027 8:00 AM | August 31, 2027 5:00 PM | 1892 | 1894 | As Soon As Possible | NA | 25 | 0d | NA | NA | 0 days? | No | NA | NA | NA | 0
13130 | V2CP: Update based on Reviews | September 1, 2027 8:00 AM | September 3, 2027 5:00 PM | 1893 | 1895 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | NA | NA | NA | 0
13131 | V2CP: Collect Feedback from Management and IPO/IV&V Reviews (based on RACI) | September 7, 2027 8:00 AM | September 13, 2027 5:00 PM | 1894 | 1896 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | NA | NA | NA | 0
13132 | V2CP: Update based on Management Team and IPO/IV&V Reviews | September 14, 2027 8:00 AM | September 20, 2027 5:00 PM | 1895 | 1897 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | NA | NA | NA | 0
13133 | V2CP: ELT Review and Approval | September 21, 2027 8:00 AM | September 27, 2027 5:00 PM | 1896 | 1898 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | NA | NA | NA | 0
13134 | V2CP: Update based on ELT Review | September 28, 2027 8:00 AM | September 30, 2027 5:00 PM | 1897 | 1899 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | NA | NA | NA | 0
13135 | V2CP: Finalize Plan and submit to PMO | October 1, 2027 8:00 AM | October 1, 2027 5:00 PM | 1898 | 1900 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | NA | NA | NA | 0
13136 | V2CP: ADA Remediation | October 4, 2027 8:00 AM | October 8, 2027 5:00 PM | 1899 | 1901 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | NA | NA | NA | 0
13096 | V2CP: Update PMO Tracking and Publish to Project Management SP Folder | October 11, 2027 8:00 AM | October 11, 2027 5:00 PM | 1900 | 1902 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | NA | NA | NA | 0
13097 | V2CP: Final V2 Cutover Plan Complete | October 11, 2027 5:00 PM | October 11, 2027 5:00 PM | 1901 |  | As Soon As Possible | NA | 0 | 0d | NA | NA | 0 days? | Yes | NA | NA | NA | 0
11049 | Training Checkpoints | December 5, 2025 8:00 AM | March 13, 2026 5:00 PM |  |  | As Soon As Possible | NA | 67 | 0d | December 5, 2025 8:00 AM | March 13, 2026 5:00 PM | 67 days | No | NA | NA | NA | 0
11050 | Training Checkpoint # 1 | December 5, 2025 8:00 AM | December 5, 2025 5:00 PM |  | 5618,1905FS+65d | Must Start On | 12/5/25 | 1 | 0d | December 5, 2025 8:00 AM | December 5, 2025 5:00 PM | 1 | No | NA | NA | NA | 0
11051 | Training Checkpoint # 2 | March 13, 2026 8:00 AM | March 13, 2026 5:00 PM | 1904FS+65d | 5618 | As Soon As Possible | NA | 1 | 98d | March 13, 2026 8:00 AM | March 13, 2026 5:00 PM | 1 | No | NA | NA | NA | 0
2875 | LOE Activities | April 1, 2021 8:00 AM | December 9, 2026 3:24 PM |  |  | As Soon As Possible | NA | 1427.8 | 210.2d | April 1, 2021 8:00 AM | December 31, 2026 5:00 PM | 1443 days | No | 4/1/21 | NA | NA | 0.81999999999999995
2876 | Forms - DocuEdge (CARESV1-4220) | June 1, 2022 8:00 AM | December 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 883 | 461d | June 1, 2022 8:00 AM | December 8, 2025 5:00 PM | 883 days | No | 6/1/22 | NA | NA | 0.93999999999999995
2877 | Research & Proof of Concept | June 1, 2022 8:00 AM | November 14, 2025 5:00 PM | 12SS+25d | 1909 | As Soon As Possible | NA | 868 | 476d | June 1, 2022 8:00 AM | November 14, 2025 5:00 PM | 868 days | No | 6/1/22 | NA | NA | 0.96999999999999997
2878 | DocuEdge Infrastructure Setup & Configuration | June 1, 2022 8:00 AM | April 11, 2024 5:00 PM | 1908 | 1912 | Start No Earlier Than | 6/1/22 | 466 | 0d | June 1, 2022 8:00 AM | April 11, 2024 5:00 PM | 466 days | No | 6/1/22 | 4/11/24 | NA | 1
2879 | DocuEdge - Product Development & Support | August 15, 2022 8:00 AM | December 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 831 | 461d | August 15, 2022 8:00 AM | December 8, 2025 5:00 PM | 831 days | No | 8/15/22 | NA | NA | 0.93999999999999995
2880 | DocuEdge - Milestone 1 | August 15, 2022 8:00 AM | September 1, 2022 5:00 PM |  |  | As Soon As Possible | NA | 14 | 0d | August 15, 2022 8:00 AM | September 1, 2022 5:00 PM | 14 days | No | 8/15/22 | 9/1/22 | NA | 1
2881 | DocuEdge - Milestone 1 - CARESV1-313 ADM - CM - File Management and Metadata | August 15, 2022 8:00 AM | August 26, 2022 5:00 PM | 1909 | 1913,1914,1915,1916,1917,1918 | As Soon As Possible | NA | 10 | 0d | August 15, 2022 8:00 AM | August 26, 2022 5:00 PM | 10 days | No | 8/15/22 | 8/26/22 | NA | 1
2882 | DocuEdge - Milestone 1 - CARESV1-315 ADM - CM - Redaction | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 1912 | 1914 | As Soon As Possible | NA | 4 | 0d | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 4 days | No | 8/29/22 | 9/1/22 | NA | 1
2883 | DocuEdge - Milestone 1 - CARESV1-317 ADM - CM - Versioning | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 1912,1913 | 1915 | As Soon As Possible | NA | 4 | 0d | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 4 days | No | 8/29/22 | 9/1/22 | NA | 1
2884 | DocuEdge - Milestone 1 - CARESV1-319 ADM - CM - Retrieval | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 1912,1914 | 1916 | As Soon As Possible | NA | 4 | 0d | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 4 days | No | 8/29/22 | 9/1/22 | NA | 1
2885 | DocuEdge - Milestone 1 - CARESV1-320 ADM - CM - Upload | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 1912,1915 | 1917 | As Soon As Possible | NA | 4 | 0d | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 4 days | No | 8/29/22 | 9/1/22 | NA | 1
2886 | DocuEdge - Milestone 1 - CARESV1-322 ADM - CM - Storage | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 1912,1916 | 1918 | As Soon As Possible | NA | 4 | 0d | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 4 days | No | 8/29/22 | 9/1/22 | NA | 1
2887 | DocuEdge - Milestone 1 - CARESV1-323 ADM - CM - Search | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 1912,1917 | 1920 | As Soon As Possible | NA | 4 | 0d | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 4 days | No | 8/29/22 | 9/1/22 | NA | 1
2888 | DocuEdge - Milestone 2 | August 15, 2022 8:00 AM | September 1, 2022 5:00 PM |  |  | As Soon As Possible | NA | 14 | 0d | August 15, 2022 8:00 AM | September 1, 2022 5:00 PM | 14 days | No | 8/15/22 | 9/1/22 | NA | 1
2889 | DocuEdge - Milestone 2 - CARESV1-313 ADM - CM - File Management and Metadata | August 15, 2022 8:00 AM | August 26, 2022 5:00 PM | 1918 | 1921,1922,1923,1924,1925,1926 | As Soon As Possible | NA | 10 | 0d | August 15, 2022 8:00 AM | August 26, 2022 5:00 PM | 10 days | No | 8/15/22 | 8/26/22 | NA | 1
2890 | DocuEdge - Milestone 2 - CARESV1-315 ADM - CM - Redaction | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 1920 | 1922 | As Soon As Possible | NA | 4 | 0d | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 4 days | No | 8/29/22 | 9/1/22 | NA | 1
2891 | DocuEdge - Milestone 2 - CARESV1-317 ADM - CM - Versioning | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 1920,1921 | 1923 | As Soon As Possible | NA | 4 | 0d | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 4 days | No | 8/29/22 | 9/1/22 | NA | 1
2892 | DocuEdge - Milestone 2 - CARESV1-319 ADM - CM - Retrieval | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 1920,622,634,628,1922 | 1924 | As Soon As Possible | NA | 4 | 0d | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 4 days | No | 8/29/22 | 9/1/22 | NA | 1
2893 | DocuEdge - Milestone 2 - CARESV1-320 ADM - CM - Upload | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 1920,1923 | 1925 | As Soon As Possible | NA | 4 | 0d | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 4 days | No | 8/29/22 | 9/1/22 | NA | 1
2894 | DocuEdge - Milestone 2 - CARESV1-322 ADM - CM - Storage | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 1920,1924 | 1926 | As Soon As Possible | NA | 4 | 0d | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 4 days | No | 8/29/22 | 9/1/22 | NA | 1
2895 | DocuEdge - Milestone 2 - CARESV1-323 ADM - CM - Search | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 1920,1925 | 1928 | As Soon As Possible | NA | 4 | 0d | August 29, 2022 8:00 AM | September 1, 2022 5:00 PM | 4 days | No | 8/29/22 | 9/1/22 | NA | 1
2896 | DocuEdge - Milestone 3 | August 15, 2022 8:00 AM | October 11, 2022 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | August 15, 2022 8:00 AM | October 11, 2022 5:00 PM | 41 days | No | 8/15/22 | 10/11/22 | NA | 1
2897 | DocuEdge - Milestone 3 - CARESV1-313 ADM - CM - File Management and Metadata | August 15, 2022 8:00 AM | September 23, 2022 5:00 PM | 1926 | 1929,1930,1931,1932,1933,1934 | As Soon As Possible | NA | 30 | 0d | August 15, 2022 8:00 AM | September 23, 2022 5:00 PM | 30 days | No | 8/15/22 | 9/23/22 | NA | 1
2898 | DocuEdge - Milestone 3 - CARESV1-315 ADM - CM - Redaction | September 26, 2022 8:00 AM | October 11, 2022 5:00 PM | 1928 | 1930 | As Soon As Possible | NA | 12 | 0d | September 26, 2022 8:00 AM | October 11, 2022 5:00 PM | 12 days | No | 9/26/22 | 10/11/22 | NA | 1
2899 | DocuEdge - Milestone 3 - CARESV1-317 ADM - CM - Versioning | September 26, 2022 8:00 AM | October 11, 2022 5:00 PM | 1928,1929 | 1931 | As Soon As Possible | NA | 12 | 0d | September 26, 2022 8:00 AM | October 11, 2022 5:00 PM | 12 days | No | 9/26/22 | 10/11/22 | NA | 1
2900 | DocuEdge - Milestone 3 - CARESV1-319 ADM - CM - Retrieval | September 26, 2022 8:00 AM | October 11, 2022 5:00 PM | 1928,1930 | 1932 | As Soon As Possible | NA | 12 | 0d | September 26, 2022 8:00 AM | October 11, 2022 5:00 PM | 12 days | No | 9/26/22 | 10/11/22 | NA | 1
2901 | DocuEdge - Milestone 3 - CARESV1-320 ADM - CM - Upload | September 26, 2022 8:00 AM | October 11, 2022 5:00 PM | 1928,1931 | 1933 | As Soon As Possible | NA | 12 | 0d | September 26, 2022 8:00 AM | October 11, 2022 5:00 PM | 12 days | No | 9/26/22 | 10/11/22 | NA | 1
2902 | DocuEdge - Milestone 3 - CARESV1-322 ADM - CM - Storage | September 26, 2022 8:00 AM | October 11, 2022 5:00 PM | 1928,1932 | 1934 | As Soon As Possible | NA | 12 | 0d | September 26, 2022 8:00 AM | October 11, 2022 5:00 PM | 12 days | No | 9/26/22 | 10/11/22 | NA | 1
2903 | DocuEdge - Milestone 3 - CARESV1-323 ADM - CM - Search | September 26, 2022 8:00 AM | October 11, 2022 5:00 PM | 1928,1933 | 1936 | As Soon As Possible | NA | 12 | 0d | September 26, 2022 8:00 AM | October 11, 2022 5:00 PM | 12 days | No | 9/26/22 | 10/11/22 | NA | 1
2904 | DocuEdge - Milestone 4 | November 7, 2022 8:00 AM | January 3, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | November 7, 2022 8:00 AM | January 3, 2023 5:00 PM | 37 days | No | 11/7/22 | 1/3/23 | NA | 1
2905 | DocuEdge - Milestone 4 - CARESV1-313 ADM - CM - File Management and Metadata | November 7, 2022 8:00 AM | December 16, 2022 5:00 PM | 1934 | 1937,1938,1939,1940,1941,1942 | As Soon As Possible | NA | 30 | 0d | November 7, 2022 8:00 AM | December 16, 2022 5:00 PM | 30 days | No | 11/7/22 | 12/16/22 | NA | 1
2906 | DocuEdge - Milestone 4 - CARESV1-315 ADM - CM - Redaction | December 19, 2022 8:00 AM | January 3, 2023 5:00 PM | 1936 | 1938 | As Soon As Possible | NA | 12 | 0d | December 19, 2022 8:00 AM | January 3, 2023 5:00 PM | 12 days | No | 12/19/22 | 1/3/23 | NA | 1
2907 | DocuEdge - Milestone 4 - CARESV1-317 ADM - CM - Versioning | December 19, 2022 8:00 AM | January 3, 2023 5:00 PM | 1936,1937 | 1939 | As Soon As Possible | NA | 12 | 0d | December 19, 2022 8:00 AM | January 3, 2023 5:00 PM | 12 days | No | 12/19/22 | 1/3/23 | NA | 1
2908 | DocuEdge - Milestone 4 - CARESV1-319 ADM - CM - Retrieval | December 19, 2022 8:00 AM | January 3, 2023 5:00 PM | 1936,1938 | 1940 | As Soon As Possible | NA | 12 | 0d | December 19, 2022 8:00 AM | January 3, 2023 5:00 PM | 12 days | No | 12/19/22 | 1/3/23 | NA | 1
2909 | DocuEdge - Milestone 4 - CARESV1-320 ADM - CM - Upload | December 19, 2022 8:00 AM | January 3, 2023 5:00 PM | 1936,1939 | 1941 | As Soon As Possible | NA | 12 | 0d | December 19, 2022 8:00 AM | January 3, 2023 5:00 PM | 12 days | No | 12/19/22 | 1/3/23 | NA | 1
2910 | DocuEdge - Milestone 4 - CARESV1-322 ADM - CM - Storage | December 19, 2022 8:00 AM | January 3, 2023 5:00 PM | 1936,1940 | 1942 | As Soon As Possible | NA | 12 | 0d | December 19, 2022 8:00 AM | January 3, 2023 5:00 PM | 12 days | No | 12/19/22 | 1/3/23 | NA | 1
2911 | DocuEdge - Milestone 4 - CARESV1-323 ADM - CM - Search | December 19, 2022 8:00 AM | January 3, 2023 5:00 PM | 1936,1941 | 1944 | As Soon As Possible | NA | 12 | 0d | December 19, 2022 8:00 AM | January 3, 2023 5:00 PM | 12 days | No | 12/19/22 | 1/3/23 | NA | 1
2912 | DocuEdge - Milestone 5 | January 2, 2023 8:00 AM | February 8, 2023 5:00 PM |  |  | As Soon As Possible | NA | 26 | 0d | January 2, 2023 8:00 AM | February 8, 2023 5:00 PM | 26 days | No | 1/2/23 | 2/8/23 | NA | 1
2913 | DocuEdge - Milestone 5 - CARESV1-313 ADM - CM - File Management and Metadata | January 2, 2023 8:00 AM | January 27, 2023 5:00 PM | 1942 | 1945,1946,1947,1948,1949,1950 | As Soon As Possible | NA | 20 | 0d | January 2, 2023 8:00 AM | January 27, 2023 5:00 PM | 20 days | No | 1/2/23 | 1/27/23 | NA | 1
2914 | DocuEdge - Milestone 5 - CARESV1-315 ADM - CM - Redaction | January 30, 2023 8:00 AM | February 8, 2023 5:00 PM | 1944 | 1946 | As Soon As Possible | NA | 8 | 0d | January 30, 2023 8:00 AM | February 8, 2023 5:00 PM | 8 days | No | 1/30/23 | 2/8/23 | NA | 1
2915 | DocuEdge - Milestone 5 - CARESV1-317 ADM - CM - Versioning | January 30, 2023 8:00 AM | February 8, 2023 5:00 PM | 1944,1945 | 1947 | As Soon As Possible | NA | 8 | 0d | January 30, 2023 8:00 AM | February 8, 2023 5:00 PM | 8 days | No | 1/30/23 | 2/8/23 | NA | 1
2916 | DocuEdge - Milestone 5 - CARESV1-319 ADM - CM - Retrieval | January 30, 2023 8:00 AM | February 8, 2023 5:00 PM | 1944,1946 | 1948 | As Soon As Possible | NA | 8 | 0d | January 30, 2023 8:00 AM | February 8, 2023 5:00 PM | 8 days | No | 1/30/23 | 2/8/23 | NA | 1
2917 | DocuEdge - Milestone 5 - CARESV1-320 ADM - CM - Upload | January 30, 2023 8:00 AM | February 8, 2023 5:00 PM | 1944,1947 | 1949 | As Soon As Possible | NA | 8 | 0d | January 30, 2023 8:00 AM | February 8, 2023 5:00 PM | 8 days | No | 1/30/23 | 2/8/23 | NA | 1
2918 | DocuEdge - Milestone 5 - CARESV1-322 ADM - CM - Storage | January 30, 2023 8:00 AM | February 8, 2023 5:00 PM | 1944,1948 | 1950 | As Soon As Possible | NA | 8 | 0d | January 30, 2023 8:00 AM | February 8, 2023 5:00 PM | 8 days | No | 1/30/23 | 2/8/23 | NA | 1
2919 | DocuEdge - Milestone 5 - CARESV1-323 ADM - CM - Search | January 30, 2023 8:00 AM | February 8, 2023 5:00 PM | 1944,1949 | 1952 | As Soon As Possible | NA | 8 | 0d | January 30, 2023 8:00 AM | February 8, 2023 5:00 PM | 8 days | No | 1/30/23 | 2/8/23 | NA | 1
2920 | DocuEdge - Milestone 6 | March 27, 2023 8:00 AM | May 3, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | March 27, 2023 8:00 AM | May 3, 2023 5:00 PM | 27 days | No | 3/27/23 | 5/3/23 | NA | 1
2921 | DocuEdge - Milestone 6 - CARESV1-313 ADM - CM - File Management and Metadata | March 27, 2023 8:00 AM | April 21, 2023 5:00 PM | 1950 | 1953,1954,1955,1956,1957,1958 | As Soon As Possible | NA | 20 | 0d | March 27, 2023 8:00 AM | April 21, 2023 5:00 PM | 20 days | No | 3/27/23 | 4/21/23 | NA | 1
2922 | DocuEdge - Milestone 6 - CARESV1-315 ADM - CM - Redaction | April 24, 2023 8:00 AM | May 3, 2023 5:00 PM | 1952 | 1954 | As Soon As Possible | NA | 8 | 0d | April 24, 2023 8:00 AM | May 3, 2023 5:00 PM | 8 days | No | 4/24/23 | 5/3/23 | NA | 1
2923 | DocuEdge - Milestone 6 - CARESV1-317 ADM - CM - Versioning | April 24, 2023 8:00 AM | May 3, 2023 5:00 PM | 1952,1953 | 1955 | As Soon As Possible | NA | 8 | 0d | April 24, 2023 8:00 AM | May 3, 2023 5:00 PM | 8 days | No | 4/24/23 | 5/3/23 | NA | 1
2924 | DocuEdge - Milestone 6 - CARESV1-319 ADM - CM - Retrieval | April 24, 2023 8:00 AM | May 3, 2023 5:00 PM | 1952,1954 | 1956 | As Soon As Possible | NA | 8 | 0d | April 24, 2023 8:00 AM | May 3, 2023 5:00 PM | 8 days | No | 4/24/23 | 5/3/23 | NA | 1
2925 | DocuEdge - Milestone 6 - CARESV1-320 ADM - CM - Upload | April 24, 2023 8:00 AM | May 3, 2023 5:00 PM | 1952,1955 | 1957 | As Soon As Possible | NA | 8 | 0d | April 24, 2023 8:00 AM | May 3, 2023 5:00 PM | 8 days | No | 4/24/23 | 5/3/23 | NA | 1
2926 | DocuEdge - Milestone 6 - CARESV1-322 ADM - CM - Storage | April 24, 2023 8:00 AM | May 3, 2023 5:00 PM | 1952,1956 | 1958 | As Soon As Possible | NA | 8 | 0d | April 24, 2023 8:00 AM | May 3, 2023 5:00 PM | 8 days | No | 4/24/23 | 5/3/23 | NA | 1
2927 | DocuEdge - Milestone 6 - CARESV1-323 ADM - CM - Search | April 24, 2023 8:00 AM | May 3, 2023 5:00 PM | 1952,1957 | 1960 | As Soon As Possible | NA | 8 | 0d | April 24, 2023 8:00 AM | May 3, 2023 5:00 PM | 8 days | No | 4/24/23 | 5/3/23 | NA | 1
2928 | DocuEdge - Milestone 6.1 | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 168 | 467d | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 days | No | 4/2/25 | NA | NA | 0.81000000000000005
2929 | DocuEdge - Milestone 6.1 - CARESV1-313 ADM - CM - File Management and Metadata | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 308FS+102d,1958 | 1961SS | As Soon As Possible | NA | 168 | 467d | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 days | No | 4/2/25 | NA | NA | 0.80000000000000004
2930 | DocuEdge - Milestone 6.1 - CARESV1-315 ADM - CM - Redaction | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 308SS,1960SS | 1962SS | As Soon As Possible | NA | 168 | 467d | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 days | No | 4/2/25 | NA | NA | 0.80000000000000004
2931 | DocuEdge - Milestone 6.1 - CARESV1-317 ADM - CM - Versioning | April 2, 2025 8:00 AM | November 28, 2025 12:00 PM | 308SS,1961SS | 1963SS | As Soon As Possible | NA | 125 | 467.5d | April 2, 2025 8:00 AM | November 28, 2025 12:00 PM | 125 days | No | 4/2/25 | NA | NA | 0.81000000000000005
2932 | DocuEdge - Milestone 6.1 - CARESV1-319 ADM - CM - Retrieval | April 2, 2025 8:00 AM | November 28, 2025 12:00 PM | 308SS,1962SS | 1964SS | As Soon As Possible | NA | 125 | 467.5d | April 2, 2025 8:00 AM | November 28, 2025 12:00 PM | 125 days | No | 4/2/25 | NA | NA | 0.81000000000000005
2933 | DocuEdge - Milestone 6.1 - CARESV1-320 ADM - CM - Upload | April 2, 2025 8:00 AM | November 28, 2025 12:00 PM | 308SS,1963SS | 1965SS | As Soon As Possible | NA | 125 | 467.5d | April 2, 2025 8:00 AM | November 28, 2025 12:00 PM | 125 days | No | 4/2/25 | NA | NA | 0.81000000000000005
2934 | DocuEdge - Milestone 6.1 - CARESV1-322 ADM - CM - Storage | April 2, 2025 8:00 AM | November 28, 2025 12:00 PM | 308SS,1964SS | 1966SS | As Soon As Possible | NA | 125 | 467.5d | April 2, 2025 8:00 AM | November 28, 2025 12:00 PM | 125 days | No | 4/2/25 | NA | NA | 0.81000000000000005
2935 | DocuEdge - Milestone 6.1 - CARESV1-323 ADM - CM - Search | April 2, 2025 8:00 AM | November 28, 2025 12:00 PM | 308SS,1965SS | 1968FS-335d | As Soon As Possible | NA | 125 | 467.5d | April 2, 2025 8:00 AM | November 28, 2025 12:00 PM | 125 days | No | 4/2/25 | NA | NA | 0.81000000000000005
2936 | DocuEdge - Milestone 7 | July 30, 2024 8:00 AM | September 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 284 | 0d | July 30, 2024 8:00 AM | September 15, 2025 5:00 PM | 284 days | No | 7/30/24 | 9/15/25 | NA | 1
2937 | DocuEdge - Milestone 7 - CARESV1-313 ADM - CM - File Management and Metadata | July 30, 2024 1:00 PM | January 27, 2025 12:00 PM | 1966FS-335d | 1969SS,1970SS-1d,2008SS-10d | As Soon As Possible | NA | 123 | 0d | July 30, 2024 1:00 PM | January 27, 2025 12:00 PM | 123 days | No | 7/30/24 | 1/27/25 | NA | 1
2938 | DocuEdge - Milestone 7 - CARESV1-315 ADM - CM - Redaction | August 30, 2024 8:00 AM | September 15, 2025 5:00 PM | 1968SS | 1970FS-285d | Finish No Earlier Than | 9/15/25 | 261 | 0d | August 30, 2024 8:00 AM | September 15, 2025 5:00 PM | 261 days | No | 8/30/24 | 9/15/25 | NA | 1
2939 | DocuEdge - Milestone 7 - CARESV1-317 ADM - CM - Versioning | July 30, 2024 8:00 AM | August 29, 2024 5:00 PM | 1968SS-1d,1969FS-285d | 1971SS | Finish No Earlier Than | 8/29/24 | 23 | 0d | July 30, 2024 8:00 AM | August 29, 2024 5:00 PM | 23 days | No | 7/30/24 | 8/29/24 | NA | 1
2940 | DocuEdge - Milestone 7 - CARESV1-319 ADM - CM - Retrieval | August 12, 2024 8:00 AM | August 22, 2024 5:00 PM | 1970SS | 1972SS | Finish No Earlier Than | 8/22/24 | 9 | 0d | August 12, 2024 8:00 AM | August 22, 2024 5:00 PM | 9 days | No | 8/12/24 | 8/22/24 | NA | 1
2941 | DocuEdge - Milestone 7 - CARESV1-320 ADM - CM - Upload | August 12, 2024 8:00 AM | August 29, 2024 5:00 PM | 1971SS | 1973 | Finish No Earlier Than | 8/29/24 | 14 | 0d | August 12, 2024 8:00 AM | August 29, 2024 5:00 PM | 14 days | No | 8/12/24 | 8/29/24 | NA | 1
2942 | DocuEdge - Milestone 7 - CARESV1-322 ADM - CM - Storage | September 3, 2024 8:00 AM | September 24, 2024 5:00 PM | 1972 | 1974 | Finish No Earlier Than | 9/24/24 | 16 | 0d | September 3, 2024 8:00 AM | September 24, 2024 5:00 PM | 16 days | No | 9/3/24 | 9/24/24 | NA | 1
2943 | DocuEdge - Milestone 7 - CARESV1-323 ADM - CM - Search | October 15, 2024 8:00 AM | January 27, 2025 5:00 PM | 1973 | 1976,2088FS+29d | Finish No Earlier Than | 1/27/25 | 69 | 0d | October 15, 2024 8:00 AM | January 27, 2025 5:00 PM | 69 days | No | 10/15/24 | 1/27/25 | NA | 1
2944 | DocuEdge - Milestone 8 | June 19, 2023 8:00 AM | July 6, 2023 5:00 PM |  |  | As Soon As Possible | NA | 13 | 0d | June 19, 2023 8:00 AM | July 6, 2023 5:00 PM | 13 days | No | 6/19/23 | 7/6/23 | NA | 1
2945 | DocuEdge - Milestone 8 - CARESV1-313 ADM - CM - File Management and Metadata | June 19, 2023 8:00 AM | June 30, 2023 5:00 PM | 1974 | 1977,1978,1979,1980,1981,1982 | As Soon As Possible | NA | 10 | 0d | June 19, 2023 8:00 AM | June 30, 2023 5:00 PM | 10 days | No | 6/19/23 | 6/30/23 | NA | 1
2946 | DocuEdge - Milestone 8 - CARESV1-315 ADM - CM - Redaction | July 3, 2023 8:00 AM | July 6, 2023 5:00 PM | 1976 | 1978 | As Soon As Possible | NA | 4 | 0d | July 3, 2023 8:00 AM | July 6, 2023 5:00 PM | 4 days | No | 7/3/23 | 7/6/23 | NA | 1
2947 | DocuEdge - Milestone 8 - CARESV1-317 ADM - CM - Versioning | July 3, 2023 8:00 AM | July 6, 2023 5:00 PM | 1976,1977 | 1979 | As Soon As Possible | NA | 4 | 0d | July 3, 2023 8:00 AM | July 6, 2023 5:00 PM | 4 days | No | 7/3/23 | 7/6/23 | NA | 1
2948 | DocuEdge - Milestone 8 - CARESV1-319 ADM - CM - Retrieval | July 3, 2023 8:00 AM | July 6, 2023 5:00 PM | 1976,1978 | 1980 | As Soon As Possible | NA | 4 | 0d | July 3, 2023 8:00 AM | July 6, 2023 5:00 PM | 4 days | No | 7/3/23 | 7/6/23 | NA | 1
2949 | DocuEdge - Milestone 8 - CARESV1-320 ADM - CM - Upload | July 3, 2023 8:00 AM | July 6, 2023 5:00 PM | 1976,1979 | 1981 | As Soon As Possible | NA | 4 | 0d | July 3, 2023 8:00 AM | July 6, 2023 5:00 PM | 4 days | No | 7/3/23 | 7/6/23 | NA | 1
2950 | DocuEdge - Milestone 8 - CARESV1-322 ADM - CM - Storage | July 3, 2023 8:00 AM | July 6, 2023 5:00 PM | 1976,1980 | 1982 | As Soon As Possible | NA | 4 | 0d | July 3, 2023 8:00 AM | July 6, 2023 5:00 PM | 4 days | No | 7/3/23 | 7/6/23 | NA | 1
2951 | DocuEdge - Milestone 8 - CARESV1-323 ADM - CM - Search | July 3, 2023 8:00 AM | July 6, 2023 5:00 PM | 1976,1981 | 1984 | As Soon As Possible | NA | 4 | 0d | July 3, 2023 8:00 AM | July 6, 2023 5:00 PM | 4 days | No | 7/3/23 | 7/6/23 | NA | 1
2952 | DocuEdge - Milestone 9 | August 14, 2023 8:00 AM | August 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 14 | 0d | August 14, 2023 8:00 AM | August 31, 2023 5:00 PM | 14 days | No | 8/14/23 | 8/31/23 | NA | 1
2953 | DocuEdge - Milestone 9 - CARESV1-313 ADM - CM - File Management and Metadata | August 14, 2023 8:00 AM | August 25, 2023 5:00 PM | 1982 | 1985,1986,1987,1988,1989,1990,2024SS+20d | As Soon As Possible | NA | 10 | 0d | August 14, 2023 8:00 AM | August 25, 2023 5:00 PM | 10 days | No | 8/14/23 | 8/25/23 | NA | 1
2954 | DocuEdge - Milestone 9 - CARESV1-315 ADM - CM - Redaction | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 1984 | 1986 | As Soon As Possible | NA | 4 | 0d | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 4 days | No | 8/28/23 | 8/31/23 | NA | 1
2955 | DocuEdge - Milestone 9 - CARESV1-317 ADM - CM - Versioning | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 1984,1985 | 1987 | As Soon As Possible | NA | 4 | 0d | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 4 days | No | 8/28/23 | 8/31/23 | NA | 1
2956 | DocuEdge - Milestone 9 - CARESV1-319 ADM - CM - Retrieval | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 1984,1986 | 1988 | As Soon As Possible | NA | 4 | 0d | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 4 days | No | 8/28/23 | 8/31/23 | NA | 1
2957 | DocuEdge - Milestone 9 - CARESV1-320 ADM - CM - Upload | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 1984,1987 | 1989 | As Soon As Possible | NA | 4 | 0d | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 4 days | No | 8/28/23 | 8/31/23 | NA | 1
2958 | DocuEdge - Milestone 9 - CARESV1-322 ADM - CM - Storage | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 1984,1988 | 1990 | As Soon As Possible | NA | 4 | 0d | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 4 days | No | 8/28/23 | 8/31/23 | NA | 1
2959 | DocuEdge - Milestone 9 - CARESV1-323 ADM - CM - Search | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 1984,1989 | 1992 | As Soon As Possible | NA | 4 | 0d | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 4 days | No | 8/28/23 | 8/31/23 | NA | 1
2960 | DocuEdge - Milestone 10 | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM | 150 days | No | 1/6/25 | 8/8/25 | NA | 1
2961 | DocuEdge - Milestone 10 - CARESV1-313 ADM - CM - File Management and Metadata | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM | 2302,1990 | 1993SS+7d,2000SS | Finish No Earlier Than | 8/8/25 | 150 | 0d | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM | 150 days | No | 1/6/25 | 8/8/25 | NA | 1
2962 | DocuEdge - Milestone 10 - CARESV1-315 ADM - CM - Redaction | January 15, 2025 8:00 AM | January 31, 2025 5:00 PM | 1992SS+7d | 1994 | As Soon As Possible | NA | 12 | 0d | January 15, 2025 8:00 AM | January 31, 2025 5:00 PM | 12 days | No | 1/15/25 | 1/31/25 | NA | 1
2963 | DocuEdge - Milestone 10 - CARESV1-317 ADM - CM - Versioning | February 3, 2025 8:00 AM | March 7, 2025 5:00 PM | 1993 | 1995 | As Soon As Possible | NA | 24 | 0d | February 3, 2025 8:00 AM | March 7, 2025 5:00 PM | 24 days | No | 2/3/25 | 3/7/25 | NA | 1
2964 | DocuEdge - Milestone 10 - CARESV1-319 ADM - CM - Retrieval | March 10, 2025 8:00 AM | March 21, 2025 5:00 PM | 1994 | 1996 | As Soon As Possible | NA | 10 | 0d | March 10, 2025 8:00 AM | March 21, 2025 5:00 PM | 10 days | No | 3/10/25 | 3/21/25 | NA | 1
2965 | DocuEdge - Milestone 10 - CARESV1-320 ADM - CM - Upload | March 24, 2025 8:00 AM | April 21, 2025 5:00 PM | 1995 | 1997FS+20d | As Soon As Possible | NA | 20 | 0d | March 24, 2025 8:00 AM | April 21, 2025 5:00 PM | 20 days | No | 3/24/25 | 4/21/25 | NA | 1
2966 | DocuEdge - Milestone 10 - CARESV1-322 ADM - CM - Storage | May 20, 2025 8:00 AM | June 30, 2025 5:00 PM | 1996FS+20d | 1998FS+15d | As Soon As Possible | NA | 29 | 0d | May 20, 2025 8:00 AM | June 30, 2025 5:00 PM | 29 days | No | 5/20/25 | 6/30/25 | NA | 1
2967 | DocuEdge - Milestone 10 - CARESV1-323 ADM - CM - Search | July 23, 2025 8:00 AM | August 1, 2025 5:00 PM | 1997FS+15d |  | As Soon As Possible | NA | 8 | 0d | July 23, 2025 8:00 AM | August 1, 2025 5:00 PM | 8 days | No | 7/23/25 | 8/1/25 | NA | 1
2968 | DocuEdge - Milestone 10.1 | January 6, 2025 8:00 AM | September 11, 2025 5:00 PM |  |  | As Soon As Possible | NA | 173 | 0d | January 6, 2025 8:00 AM | September 11, 2025 5:00 PM | 173 days | No | 1/6/25 | 9/11/25 | NA | 1
2969 | DocuEdge - Milestone 10.1 - CARESV1-313 ADM - CM - File Management and Metadata | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM | 1992SS | 2001FS-146d,2032SS-5d | Finish No Earlier Than | 8/8/25 | 150 | 0d | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM | 150 days | No | 1/6/25 | 8/8/25 | NA | 1
2970 | DocuEdge - Milestone 10.1 - CARESV1-315 ADM - CM - Redaction | January 10, 2025 8:00 AM | February 11, 2025 5:00 PM | 2000FS-146d | 2002FS-2d | Finish No Earlier Than | 2/11/25 | 22 | 0d | January 10, 2025 8:00 AM | February 11, 2025 5:00 PM | 22 days | No | 1/10/25 | 2/11/25 | NA | 1
2971 | DocuEdge - Milestone 10.1 - CARESV1-317 ADM - CM - Versioning | February 10, 2025 8:00 AM | March 11, 2025 5:00 PM | 2001FS-2d | 2003FS-2d | Finish No Earlier Than | 3/11/25 | 21 | 0d | February 10, 2025 8:00 AM | March 11, 2025 5:00 PM | 21 days | No | 2/10/25 | 3/11/25 | NA | 1
2972 | DocuEdge - Milestone 10.1 - CARESV1-319 ADM - CM - Retrieval | March 10, 2025 8:00 AM | April 11, 2025 5:00 PM | 2002FS-2d | 2004FS-2d | Finish No Earlier Than | 4/11/25 | 24 | 0d | March 10, 2025 8:00 AM | April 11, 2025 5:00 PM | 24 days | No | 3/10/25 | 4/11/25 | NA | 1
2973 | DocuEdge - Milestone 10.1 - CARESV1-320 ADM - CM - Upload | April 10, 2025 8:00 AM | May 9, 2025 5:00 PM | 2003FS-2d | 2005 | Finish No Earlier Than | 5/9/25 | 22 | 0d | April 10, 2025 8:00 AM | May 11, 2025 5:00 PM | 22 days | No | 4/10/25 | 5/9/25 | NA | 1
2974 | DocuEdge - Milestone 10.1 - CARESV1-322 ADM - CM - Storage | June 10, 2025 8:00 AM | July 11, 2025 5:00 PM | 2004 | 2006 | Finish No Earlier Than | 7/11/25 | 23 | 0d | June 10, 2025 8:00 AM | July 11, 2025 5:00 PM | 23 days | No | 6/10/25 | 7/11/25 | NA | 1
2975 | DocuEdge - Milestone 10.1 - CARESV1-323 ADM - CM - Search | August 11, 2025 8:00 AM | September 11, 2025 5:00 PM | 2005 |  | Finish No Earlier Than | 9/11/25 | 23 | 0d | August 11, 2025 8:00 AM | September 11, 2025 5:00 PM | 23 days | No | 8/11/25 | 9/11/25 | NA | 1
2976 | DocuEdge - Milestone 11 | July 10, 2024 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 273 | 0d | July 10, 2024 8:00 AM | August 8, 2025 5:00 PM | 273 days | No | 7/10/24 | 8/8/25 | NA | 1
2977 | DocuEdge - Milestone 11 - CARESV1-313 ADM - CM - File Management and Metadata | July 10, 2024 8:00 AM | August 8, 2025 5:00 PM | 1968SS-10d | 2009FS-249d,2016SS-3d | Finish No Earlier Than | 8/8/25 | 273 | 0d | July 10, 2024 8:00 AM | August 8, 2025 5:00 PM | 273 days | No | 7/10/24 | 8/8/25 | NA | 1
2978 | DocuEdge - Milestone 11 - CARESV1-315 ADM - CM - Redaction | August 13, 2024 8:00 AM | September 11, 2024 5:00 PM | 2008FS-249d | 2010FS-1d | As Soon As Possible | NA | 22 | 0d | August 13, 2024 8:00 AM | September 11, 2024 5:00 PM | 22 days | No | 8/13/24 | 9/11/24 | NA | 1
2979 | DocuEdge - Milestone 11 - CARESV1-317 ADM - CM - Versioning | September 11, 2024 8:00 AM | October 10, 2024 5:00 PM | 2009FS-1d | 2011FS-1d | As Soon As Possible | NA | 22 | 0d | September 11, 2024 8:00 AM | October 10, 2024 5:00 PM | 22 days | No | 9/11/24 | 10/10/24 | NA | 1
2980 | DocuEdge - Milestone 11 - CARESV1-319 ADM - CM - Retrieval | October 10, 2024 8:00 AM | November 8, 2024 5:00 PM | 2010FS-1d | 2012FS+18d | As Soon As Possible | NA | 22 | 0d | October 10, 2024 8:00 AM | November 8, 2024 5:00 PM | 22 days | No | 10/10/24 | 11/8/24 | NA | 1
2981 | DocuEdge - Milestone 11 - CARESV1-320 ADM - CM - Upload | December 10, 2024 8:00 AM | January 3, 2025 5:00 PM | 2011FS+18d | 2013FS+11d | As Soon As Possible | NA | 17 | 0d | December 10, 2024 8:00 AM | January 3, 2025 5:00 PM | 17 days | No | 12/10/24 | 1/3/25 | NA | 1
2982 | DocuEdge - Milestone 11 - CARESV1-322 ADM - CM - Storage | January 22, 2025 8:00 AM | April 11, 2025 5:00 PM | 2012FS+11d | 2014FS+21d | As Soon As Possible | NA | 56 | 0d | January 22, 2025 8:00 AM | April 11, 2025 5:00 PM | 56 days | No | 1/22/25 | 4/11/25 | NA | 1
2983 | DocuEdge - Milestone 11 - CARESV1-323 ADM - CM - Search | May 13, 2025 8:00 AM | July 11, 2025 5:00 PM | 2013FS+21d |  | As Soon As Possible | NA | 42 | 0d | May 13, 2025 8:00 AM | July 11, 2025 5:00 PM | 42 days | No | 5/13/25 | 7/11/25 | NA | 1
2984 | DocuEdge - Milestone 13 | July 5, 2024 8:00 AM | September 11, 2025 5:00 PM |  |  | As Soon As Possible | NA | 299 | 0d | July 5, 2024 8:00 AM | September 11, 2025 5:00 PM | 299 days | No | 7/5/24 | 9/11/25 | NA | 1
2985 | DocuEdge - Milestone 13 - CARESV1-313 ADM - CM - File Management and Metadata | July 5, 2024 8:00 AM | August 28, 2024 5:00 PM | 2008SS-3d | 2017FS-12d | Finish No Earlier Than | 8/28/24 | 39 | 0d | July 5, 2024 8:00 AM | August 28, 2024 5:00 PM | 39 days | No | 7/5/24 | 8/28/24 | NA | 1
2986 | DocuEdge - Milestone 13 - CARESV1-315 ADM - CM - Redaction | August 13, 2024 8:00 AM | September 11, 2024 5:00 PM | 2016FS-12d | 2018FS-1d | As Soon As Possible | NA | 22 | 0d | August 13, 2024 8:00 AM | September 11, 2024 5:00 PM | 22 days | No | 8/13/24 | 9/11/24 | NA | 1
2987 | DocuEdge - Milestone 13 - CARESV1-317 ADM - CM - Versioning | September 11, 2024 8:00 AM | October 11, 2024 5:00 PM | 2017FS-1d | 2019FS-2d | As Soon As Possible | NA | 23 | 0d | September 11, 2024 8:00 AM | October 11, 2024 5:00 PM | 23 days | No | 9/11/24 | 10/11/24 | NA | 1
2988 | DocuEdge - Milestone 13 - CARESV1-319 ADM - CM - Retrieval | October 10, 2024 8:00 AM | November 8, 2024 5:00 PM | 2018FS-2d | 2020FS+18d | As Soon As Possible | NA | 22 | 0d | October 10, 2024 8:00 AM | November 8, 2024 5:00 PM | 22 days | No | 10/10/24 | 11/8/24 | NA | 1
2989 | DocuEdge - Milestone 13 - CARESV1-320 ADM - CM - Upload | December 10, 2024 8:00 AM | January 3, 2025 5:00 PM | 2019FS+18d | 2021FS+11d | As Soon As Possible | NA | 17 | 0d | December 10, 2024 8:00 AM | January 3, 2025 5:00 PM | 17 days | No | 12/10/24 | 1/3/25 | NA | 1
2990 | DocuEdge - Milestone 13 - CARESV1-322 ADM - CM - Storage | January 22, 2025 8:00 AM | April 11, 2025 5:00 PM | 2020FS+11d | 2022FS+11d | As Soon As Possible | NA | 56 | 0d | January 22, 2025 8:00 AM | April 11, 2025 5:00 PM | 56 days | No | 1/22/25 | 4/11/25 | NA | 1
2991 | DocuEdge - Milestone 13 - CARESV1-323 ADM - CM - Search | April 29, 2025 8:00 AM | September 11, 2025 5:00 PM | 2021FS+11d |  | As Soon As Possible | NA | 95 | 0d | April 29, 2025 8:00 AM | September 11, 2025 5:00 PM | 95 days | No | 4/29/25 | 9/11/25 | NA | 1
2992 | DocuEdge - Milestone 14 | September 11, 2023 8:00 AM | October 9, 2023 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | September 11, 2023 8:00 AM | October 9, 2023 5:00 PM | 21 days | No | 9/11/23 | 10/9/23 | NA | 1
2993 | DocuEdge - Milestone 14 - CARESV1-313 ADM - CM - File Management and Metadata | September 11, 2023 8:00 AM | September 29, 2023 5:00 PM | 1984SS+20d | 2025,2064SS-20d | As Soon As Possible | NA | 15 | 0d | September 11, 2023 8:00 AM | September 29, 2023 5:00 PM | 15 days | No | 9/11/23 | 9/29/23 | NA | 1
2994 | DocuEdge - Milestone 14 - CARESV1-315 ADM - CM - Redaction | October 2, 2023 8:00 AM | October 9, 2023 5:00 PM | 2024 | 2026 | As Soon As Possible | NA | 6 | 0d | October 2, 2023 8:00 AM | October 9, 2023 5:00 PM | 6 days | No | 10/2/23 | 10/9/23 | NA | 1
2995 | DocuEdge - Milestone 14 - CARESV1-317 ADM - CM - Versioning | October 2, 2023 8:00 AM | October 9, 2023 5:00 PM | 2025 | 2027 | As Soon As Possible | NA | 6 | 0d | October 2, 2023 8:00 AM | October 9, 2023 5:00 PM | 6 days | No | 10/2/23 | 10/9/23 | NA | 1
2996 | DocuEdge - Milestone 14 - CARESV1-319 ADM - CM - Retrieval | October 2, 2023 8:00 AM | October 9, 2023 5:00 PM | 2026 | 2028 | As Soon As Possible | NA | 6 | 0d | October 2, 2023 8:00 AM | October 9, 2023 5:00 PM | 6 days | No | 10/2/23 | 10/9/23 | NA | 1
2997 | DocuEdge - Milestone 14 - CARESV1-320 ADM - CM - Upload | October 2, 2023 8:00 AM | October 9, 2023 5:00 PM | 2027 | 2029 | As Soon As Possible | NA | 6 | 0d | October 2, 2023 8:00 AM | October 9, 2023 5:00 PM | 6 days | No | 10/2/23 | 10/9/23 | NA | 1
2998 | DocuEdge - Milestone 14 - CARESV1-322 ADM - CM - Storage | October 2, 2023 8:00 AM | October 9, 2023 5:00 PM | 2028 | 2030 | As Soon As Possible | NA | 6 | 0d | October 2, 2023 8:00 AM | October 9, 2023 5:00 PM | 6 days | No | 10/2/23 | 10/9/23 | NA | 1
2999 | DocuEdge - Milestone 14 - CARESV1-323 ADM - CM - Search | October 2, 2023 8:00 AM | October 9, 2023 5:00 PM | 2029 |  | As Soon As Possible | NA | 6 | 0d | October 2, 2023 8:00 AM | October 9, 2023 5:00 PM | 6 days | No | 10/2/23 | 10/9/23 | NA | 1
3000 | DocuEdge - Milestone 15 | January 1, 2024 8:00 AM | August 7, 2025 5:00 PM |  |  | As Soon As Possible | NA | 403 | 0d | January 1, 2024 8:00 AM | August 7, 2025 5:00 PM | 403 days | No | 1/1/24 | 8/7/25 | NA | 1
3001 | DocuEdge - Milestone 15 - CARESV1-313 ADM - CM - File Management and Metadata | January 1, 2024 8:00 AM | August 7, 2025 5:00 PM | 2000SS-5d | 2033,2040SS+105d,2072SS+23d | Finish No Earlier Than | 8/7/25 | 404 | 0d | January 1, 2024 8:00 AM | August 7, 2025 5:00 PM | 404 days | No | 1/1/24 | 8/7/25 | NA | 1
3002 | DocuEdge - Milestone 15 - CARESV1-315 ADM - CM - Redaction | February 6, 2024 8:00 AM | April 5, 2024 5:00 PM | 2032 | 2034 | As Soon As Possible | NA | 42 | 0d | February 6, 2024 8:00 AM | April 5, 2024 5:00 PM | 42 days | No | 2/6/24 | 4/5/24 | NA | 1
3003 | DocuEdge - Milestone 15 - CARESV1-317 ADM - CM - Versioning | May 1, 2024 8:00 AM | June 28, 2024 5:00 PM | 2033 | 2035 | As Soon As Possible | NA | 42 | 0d | May 1, 2024 8:00 AM | June 28, 2024 5:00 PM | 42 days | No | 5/1/24 | 6/28/24 | NA | 1
3004 | DocuEdge - Milestone 15 - CARESV1-319 ADM - CM - Retrieval | July 1, 2024 8:00 AM | July 8, 2024 5:00 PM | 2034 | 2036FS+21d | As Soon As Possible | NA | 5 | 0d | July 1, 2024 8:00 AM | July 8, 2024 5:00 PM | 5 days | No | 7/1/24 | 7/8/24 | NA | 1
3005 | DocuEdge - Milestone 15 - CARESV1-320 ADM - CM - Upload | August 7, 2024 8:00 AM | October 10, 2024 5:00 PM | 2035FS+21d | 2037FS+15d | As Soon As Possible | NA | 47 | 0d | August 7, 2024 8:00 AM | October 10, 2024 5:00 PM | 47 days | No | 8/7/24 | 10/10/24 | NA | 1
3006 | DocuEdge - Milestone 15 - CARESV1-322 ADM - CM - Storage | November 1, 2024 8:00 AM | March 7, 2025 5:00 PM | 2036FS+15d | 2038FS+22d | As Soon As Possible | NA | 84 | 0d | November 1, 2024 8:00 AM | March 7, 2025 5:00 PM | 84 days | No | 11/1/24 | 3/7/25 | NA | 1
3007 | DocuEdge - Milestone 15 - CARESV1-323 ADM - CM - Search | April 10, 2025 8:00 AM | August 7, 2025 5:00 PM | 2037FS+22d |  | As Soon As Possible | NA | 84 | 0d | April 10, 2025 8:00 AM | August 7, 2025 5:00 PM | 84 days | No | 4/10/25 | 8/7/25 | NA | 1
3008 | DocuEdge - Milestone 16 | June 11, 2024 8:00 AM | May 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 234 | 0d | June 11, 2024 8:00 AM | May 15, 2025 5:00 PM | 234 days | No | 6/11/24 | 5/15/25 | NA | 1
3009 | DocuEdge - Milestone 16 - CARESV1-313 ADM - CM - File Management and Metadata | June 11, 2024 8:00 AM | May 15, 2025 5:00 PM | 2032SS+105d | 2041SS+14d,2048SS | Finish No Earlier Than | 5/15/25 | 234 | 0d | June 11, 2024 8:00 AM | May 15, 2025 5:00 PM | 234 days | No | 6/11/24 | 5/15/25 | NA | 1
3010 | DocuEdge - Milestone 16 - CARESV1-315 ADM - CM - Redaction | July 1, 2024 8:00 AM | July 8, 2024 5:00 PM | 2040SS+14d | 2042FS+21d | As Soon As Possible | NA | 5 | 0d | July 1, 2024 8:00 AM | July 8, 2024 5:00 PM | 5 days | No | 7/1/24 | 7/8/24 | NA | 1
3011 | DocuEdge - Milestone 16 - CARESV1-317 ADM - CM - Versioning | August 7, 2024 8:00 AM | October 10, 2024 5:00 PM | 2041FS+21d | 2043FS+15d | As Soon As Possible | NA | 47 | 0d | August 7, 2024 8:00 AM | October 10, 2024 5:00 PM | 47 days | No | 8/7/24 | 10/10/24 | NA | 1
3012 | DocuEdge - Milestone 16 - CARESV1-319 ADM - CM - Retrieval | November 1, 2024 8:00 AM | March 7, 2025 5:00 PM | 2042FS+15d | 2044SS+1d | As Soon As Possible | NA | 84 | 0d | November 1, 2024 8:00 AM | March 7, 2025 5:00 PM | 84 days | No | 11/1/24 | 3/7/25 | NA | 1
3013 | DocuEdge - Milestone 16 - CARESV1-320 ADM - CM - Upload | November 4, 2024 8:00 AM | March 28, 2025 5:00 PM | 2043SS+1d | 2045SS+19d | As Soon As Possible | NA | 98 | 0d | November 4, 2024 8:00 AM | March 28, 2025 5:00 PM | 98 days | No | 11/4/24 | 3/28/25 | NA | 1
3014 | DocuEdge - Milestone 16 - CARESV1-322 ADM - CM - Storage | December 4, 2024 8:00 AM | April 4, 2025 5:00 PM | 2044SS+19d | 2046FS-1d | As Soon As Possible | NA | 83 | 0d | December 4, 2024 8:00 AM | April 4, 2025 5:00 PM | 83 days | No | 12/4/24 | 4/4/25 | NA | 1
3015 | DocuEdge - Milestone 16 - CARESV1-323 ADM - CM - Search | April 4, 2025 8:00 AM | May 15, 2025 5:00 PM | 2045FS-1d |  | As Soon As Possible | NA | 30 | 0d | April 4, 2025 8:00 AM | May 15, 2025 5:00 PM | 30 days | No | 4/4/25 | 5/15/25 | NA | 1
3016 | DocuEdge - Milestone 17 | June 11, 2024 8:00 AM | May 14, 2025 5:00 PM |  |  | As Soon As Possible | NA | 233 | 0d | June 11, 2024 8:00 AM | May 14, 2025 5:00 PM | 233 days | No | 6/11/24 | 5/14/25 | NA | 1
3017 | DocuEdge - Milestone 17 - CARESV1-313 ADM - CM - File Management and Metadata | June 11, 2024 8:00 AM | May 14, 2025 5:00 PM | 2040SS | 2049SS+20d,2056SS-1d,2104SS-20d | Finish No Earlier Than | 5/14/25 | 233 | 0d | June 11, 2024 8:00 AM | May 14, 2025 5:00 PM | 233 days | No | 6/11/24 | 5/14/25 | NA | 1
3018 | DocuEdge - Milestone 17 - CARESV1-315 ADM - CM - Redaction | July 10, 2024 8:00 AM | September 13, 2024 5:00 PM | 2048SS+20d | 2050FS-24d | As Soon As Possible | NA | 48 | 0d | July 10, 2024 8:00 AM | September 13, 2024 5:00 PM | 48 days | No | 7/10/24 | 9/13/24 | NA | 1
3019 | DocuEdge - Milestone 17 - CARESV1-317 ADM - CM - Versioning | August 13, 2024 8:00 AM | October 16, 2024 5:00 PM | 2049FS-24d | 2051FS-26d | As Soon As Possible | NA | 47 | 0d | August 13, 2024 8:00 AM | October 16, 2024 5:00 PM | 47 days | No | 8/13/24 | 10/16/24 | NA | 1
3020 | DocuEdge - Milestone 17 - CARESV1-319 ADM - CM - Retrieval | September 11, 2024 8:00 AM | December 17, 2024 5:00 PM | 2050FS-26d | 2052FS-44d | As Soon As Possible | NA | 67 | 0d | September 11, 2024 8:00 AM | December 17, 2024 5:00 PM | 67 days | No | 9/11/24 | 12/17/24 | NA | 1
3021 | DocuEdge - Milestone 17 - CARESV1-320 ADM - CM - Upload | October 14, 2024 8:00 AM | February 18, 2025 5:00 PM | 2051FS-44d | 2053FS-64d | As Soon As Possible | NA | 85 | 0d | October 14, 2024 8:00 AM | February 18, 2025 5:00 PM | 85 days | No | 10/14/24 | 2/18/25 | NA | 1
3022 | DocuEdge - Milestone 17 - CARESV1-322 ADM - CM - Storage | November 13, 2024 8:00 AM | March 19, 2025 5:00 PM | 2052FS-64d | 2054FS-64d | As Soon As Possible | NA | 85 | 0d | November 13, 2024 8:00 AM | March 19, 2025 5:00 PM | 85 days | No | 11/13/24 | 3/19/25 | NA | 1
3023 | DocuEdge - Milestone 17 - CARESV1-323 ADM - CM - Search | December 16, 2024 8:00 AM | May 14, 2025 5:00 PM | 2053FS-64d |  | As Soon As Possible | NA | 103 | 0d | December 16, 2024 8:00 AM | May 14, 2025 5:00 PM | 103 days | No | 12/16/24 | 5/14/25 | NA | 1
3024 | DocuEdge - Milestone 18 | June 10, 2024 8:00 AM | July 11, 2025 5:00 PM |  |  | As Soon As Possible | NA | 274 | 0d | June 10, 2024 8:00 AM | July 11, 2025 5:00 PM | 274 days | No | 6/10/24 | 7/11/25 | NA | 1
3025 | DocuEdge - Milestone 18 - CARESV1-313 ADM - CM - File Management and Metadata | June 10, 2024 8:00 AM | August 14, 2024 5:00 PM | 2048SS-1d | 2057FS+1d | Finish No Earlier Than | 8/14/24 | 47 | 0d | June 10, 2024 8:00 AM | August 14, 2024 5:00 PM | 47 days | No | 6/10/24 | 8/14/24 | NA | 1
3026 | DocuEdge - Milestone 18 - CARESV1-315 ADM - CM - Redaction | August 16, 2024 8:00 AM | October 18, 2024 5:00 PM | 2056FS+1d | 2058 | As Soon As Possible | NA | 46 | 0d | August 16, 2024 8:00 AM | October 18, 2024 5:00 PM | 46 days | No | 8/16/24 | 10/18/24 | NA | 1
3027 | DocuEdge - Milestone 18 - CARESV1-317 ADM - CM - Versioning | October 21, 2024 8:00 AM | December 26, 2024 5:00 PM | 2057 | 2059 | As Soon As Possible | NA | 45 | 0d | October 21, 2024 8:00 AM | December 26, 2024 5:00 PM | 45 days | No | 10/21/24 | 12/26/24 | NA | 1
3028 | DocuEdge - Milestone 18 - CARESV1-319 ADM - CM - Retrieval | December 27, 2024 8:00 AM | February 28, 2025 5:00 PM | 2058 | 2060 | As Soon As Possible | NA | 43 | 0d | December 27, 2024 8:00 AM | February 28, 2025 5:00 PM | 43 days | No | 12/27/24 | 2/28/25 | NA | 1
3029 | DocuEdge - Milestone 18 - CARESV1-320 ADM - CM - Upload | March 3, 2025 8:00 AM | May 7, 2025 5:00 PM | 2059 | 2061 | As Soon As Possible | NA | 47 | 0d | March 3, 2025 8:00 AM | May 7, 2025 5:00 PM | 47 days | No | 3/3/25 | 5/7/25 | NA | 1
3030 | DocuEdge - Milestone 18 - CARESV1-322 ADM - CM - Storage | May 8, 2025 8:00 AM | July 11, 2025 5:00 PM | 2060 | 2062FS-25d | As Soon As Possible | NA | 45 | 0d | May 8, 2025 8:00 AM | July 11, 2025 5:00 PM | 45 days | No | 5/8/25 | 7/11/25 | NA | 1
3031 | DocuEdge - Milestone 18 - CARESV1-323 ADM - CM - Search | June 6, 2025 8:00 AM | June 13, 2025 5:00 PM | 2061FS-25d |  | As Soon As Possible | NA | 6 | 0d | June 6, 2025 8:00 AM | June 13, 2025 5:00 PM | 6 days | No | 6/6/25 | 6/13/25 | NA | 1
3032 | DocuEdge - Milestone 19 | August 14, 2023 8:00 AM | August 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 14 | 0d | August 14, 2023 8:00 AM | August 31, 2023 5:00 PM | 14 days | No | 8/14/23 | 8/31/23 | NA | 1
3033 | DocuEdge - Milestone 19 - CARESV1-313 ADM - CM - File Management and Metadata | August 14, 2023 8:00 AM | August 25, 2023 5:00 PM | 2024SS-20d | 2065,2066,2067,2068,2069,2070 | As Soon As Possible | NA | 10 | 0d | August 14, 2023 8:00 AM | August 25, 2023 5:00 PM | 10 days | No | 8/14/23 | 8/25/23 | NA | 1
3034 | DocuEdge - Milestone 19 - CARESV1-315 ADM - CM - Redaction | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 2064 | 2066 | As Soon As Possible | NA | 4 | 0d | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 4 days | No | 8/28/23 | 8/31/23 | NA | 1
3035 | DocuEdge - Milestone 19 - CARESV1-317 ADM - CM - Versioning | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 2064,2065 | 2067 | As Soon As Possible | NA | 4 | 0d | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 4 days | No | 8/28/23 | 8/31/23 | NA | 1
3036 | DocuEdge - Milestone 19 - CARESV1-319 ADM - CM - Retrieval | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 2064,2066 | 2068 | As Soon As Possible | NA | 4 | 0d | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 4 days | No | 8/28/23 | 8/31/23 | NA | 1
3037 | DocuEdge - Milestone 19 - CARESV1-320 ADM - CM - Upload | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 2064,2067 | 2069 | As Soon As Possible | NA | 4 | 0d | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 4 days | No | 8/28/23 | 8/31/23 | NA | 1
3038 | DocuEdge - Milestone 19 - CARESV1-322 ADM - CM - Storage | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 2064,2068 | 2070 | As Soon As Possible | NA | 4 | 0d | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 4 days | No | 8/28/23 | 8/31/23 | NA | 1
3039 | DocuEdge - Milestone 19 - CARESV1-323 ADM - CM - Search | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 2064,2069 | 2080FS+72d | As Soon As Possible | NA | 4 | 0d | August 28, 2023 8:00 AM | August 31, 2023 5:00 PM | 4 days | No | 8/28/23 | 8/31/23 | NA | 1
3040 | DocuEdge - Milestone 20 | February 5, 2024 8:00 AM | February 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 267 | 0d | February 5, 2024 8:00 AM | February 26, 2025 5:00 PM | 267 days | No | 2/5/24 | 2/26/25 | NA | 1
3041 | DocuEdge - Milestone 20 - CARESV1-313 ADM - CM - File Management and Metadata | February 5, 2024 8:00 AM | September 6, 2024 5:00 PM | 2032SS+23d | 2073,2112 | Finish No Earlier Than | 9/6/24 | 150 | 0d | February 5, 2024 8:00 AM | September 6, 2024 5:00 PM | 150 days | No | 2/5/24 | 9/6/24 | NA | 1
3042 | DocuEdge - Milestone 20 - CARESV1-315 ADM - CM - Redaction | March 6, 2024 8:00 AM | April 9, 2024 5:00 PM | 2072 | 2074 | Finish No Earlier Than | 4/9/24 | 24 | 0d | March 6, 2024 8:00 AM | April 9, 2024 5:00 PM | 24 days | No | 3/6/24 | 4/9/24 | NA | 1
3043 | DocuEdge - Milestone 20 - CARESV1-317 ADM - CM - Versioning | April 8, 2024 8:00 AM | May 9, 2024 5:00 PM | 2073 | 2075 | Finish No Earlier Than | 5/9/24 | 24 | 0d | April 8, 2024 8:00 AM | May 9, 2024 5:00 PM | 24 days | No | 4/8/24 | 5/9/24 | NA | 1
3044 | DocuEdge - Milestone 20 - CARESV1-319 ADM - CM - Retrieval | March 6, 2024 8:00 AM | May 9, 2024 5:00 PM | 2074 | 2076 | Finish No Earlier Than | 5/9/24 | 46 | 0d | March 6, 2024 8:00 AM | May 9, 2024 5:00 PM | 46 days | No | 3/6/24 | 5/9/24 | NA | 1
3045 | DocuEdge - Milestone 20 - CARESV1-320 ADM - CM - Upload | March 6, 2024 8:00 AM | December 20, 2024 5:00 PM | 2075 | 2077 | Start No Earlier Than | 3/6/24 | 202 | 0d | March 6, 2024 8:00 AM | December 20, 2024 5:00 PM | 202 days | No | 3/6/24 | 12/20/24 | NA | 1
3046 | DocuEdge - Milestone 20 - CARESV1-322 ADM - CM - Storage | December 23, 2024 8:00 AM | January 27, 2025 5:00 PM | 2076 | 2078FS-23d | Finish No Earlier Than | 7/9/24 | 23 | 0d | December 23, 2024 8:00 AM | January 27, 2025 5:00 PM | 23 days | No | 12/23/24 | 1/27/25 | NA | 1
3047 | DocuEdge - Milestone 20 - CARESV1-323 ADM - CM - Search | December 23, 2024 8:00 AM | February 26, 2025 5:00 PM | 2077FS-23d |  | Finish No Earlier Than | 2/26/25 | 44 | 0d | December 23, 2024 8:00 AM | February 26, 2025 5:00 PM | 44 days | No | 12/23/24 | 2/26/25 | NA | 1
3048 | DocuEdge - Milestone 21 | December 15, 2023 8:00 AM | September 6, 2024 5:00 PM |  |  | As Soon As Possible | NA | 184 | 0d | December 15, 2023 8:00 AM | September 6, 2024 5:00 PM | 184 days | No | 12/15/23 | 9/6/24 | NA | 1
3049 | DocuEdge - Milestone 21 - CARESV1-313 ADM - CM - File Management and Metadata | December 15, 2023 8:00 AM | September 6, 2024 5:00 PM | 2070FS+72d | 2081FS-170d | Finish No Earlier Than | 9/6/24 | 183 | 0d | December 15, 2023 8:00 AM | September 6, 2024 5:00 PM | 183 days | No | 12/15/23 | 9/6/24 | NA | 1
3050 | DocuEdge - Milestone 21 - CARESV1-315 ADM - CM - Redaction | January 8, 2024 8:00 AM | August 6, 2024 5:00 PM | 2080FS-170d | 2082 | Finish No Earlier Than | 8/6/24 | 147 | 0d | January 8, 2024 8:00 AM | August 6, 2024 5:00 PM | 147 days | No | 1/8/24 | 8/6/24 | NA | 1
3051 | DocuEdge - Milestone 21 - CARESV1-317 ADM - CM - Versioning | February 22, 2024 8:00 AM | March 29, 2024 5:00 PM | 2081 | 2083 | Finish No Earlier Than | 4/1/24 | 27 | 0d | February 22, 2024 8:00 AM | March 29, 2024 5:00 PM | 27 days | No | 2/22/24 | 3/29/24 | NA | 1
3052 | DocuEdge - Milestone 21 - CARESV1-319 ADM - CM - Retrieval | April 22, 2024 8:00 AM | June 25, 2024 5:00 PM | 2082 | 2084FS-2d | Finish No Earlier Than | 6/25/24 | 46 | 0d | April 22, 2024 8:00 AM | June 25, 2024 5:00 PM | 46 days | No | 4/22/24 | 6/25/24 | NA | 1
3053 | DocuEdge - Milestone 21 - CARESV1-320 ADM - CM - Upload | June 24, 2024 8:00 AM | August 23, 2024 5:00 PM | 2083FS-2d | 2085FS-25d | Finish No Earlier Than | 8/23/24 | 44 | 0d | June 24, 2024 8:00 AM | August 25, 2024 5:00 PM | 44 days | No | 6/24/24 | 8/23/24 | NA | 1
3054 | DocuEdge - Milestone 21 - CARESV1-322 ADM - CM - Storage | July 22, 2024 8:00 AM | August 23, 2024 5:00 PM | 2084FS-25d | 2086FS-1d | Finish No Earlier Than | 8/23/24 | 25 | 0d | July 22, 2024 8:00 AM | August 25, 2024 5:00 PM | 25 days | No | 7/22/24 | 8/23/24 | NA | 1
3055 | DocuEdge - Milestone 21 - CARESV1-323 ADM - CM - Search | August 23, 2024 8:00 AM | September 6, 2024 5:00 PM | 2085FS-1d |  | Finish No Earlier Than | 9/6/24 | 11 | 0d | August 23, 2024 8:00 AM | September 6, 2024 5:00 PM | 11 days | No | 8/23/24 | 9/6/24 | NA | 1
3056 | DocuEdge - Milestone 23 | March 11, 2025 8:00 AM | December 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 189 | 461d | March 11, 2025 8:00 AM | December 8, 2025 5:00 PM | 189 days | No | 3/11/25 | NA | NA | 0.79000000000000004
3057 | DocuEdge - Milestone 23 - CARESV1-313 ADM - CM - File Management and Metadata | March 11, 2025 8:00 AM | December 2, 2025 5:00 PM | 1974FS+29d | 2089FS-162d,2096SS-1d | Finish No Earlier Than | 12/2/25 | 185 | 127.14d | March 11, 2025 8:00 AM | December 2, 2025 5:00 PM | 185 days | No | 3/11/25 | NA | NA | 0.81000000000000005
3058 | DocuEdge - Milestone 23 - CARESV1-315 ADM - CM - Redaction | April 14, 2025 8:00 AM | December 3, 2025 5:00 PM | 2088FS-162d | 2090FS-142d | Finish No Earlier Than | 12/3/25 | 163 | 105.82d | April 14, 2025 8:00 AM | December 3, 2025 5:00 PM | 163 days | No | 4/14/25 | NA | NA | 0.78000000000000003
3059 | DocuEdge - Milestone 23 - CARESV1-317 ADM - CM - Versioning | May 13, 2025 8:00 AM | December 4, 2025 5:00 PM | 2089FS-142d | 2091FS-1834d | Finish No Earlier Than | 12/4/25 | 143 | 463d | May 13, 2025 8:00 AM | December 4, 2025 5:00 PM | 143 days | No | 5/13/25 | NA | NA | 0.73999999999999999
3060 | DocuEdge - Milestone 23 - CARESV1-319 ADM - CM - Retrieval | March 14, 2025 8:00 AM | December 5, 2025 5:00 PM | 2090FS-1834d | 2092FS-184d | Finish No Earlier Than | 12/5/25 | 185 | 145.36d | March 14, 2025 8:00 AM | December 5, 2025 5:00 PM | 185 days | No | 3/14/25 | NA | NA | 0.79000000000000004
3061 | DocuEdge - Milestone 23 - CARESV1-320 ADM - CM - Upload | March 17, 2025 8:00 AM | December 5, 2025 5:00 PM | 2091FS-184d | 2093FS-183d | As Soon As Possible | NA | 184 | 144.57d | March 17, 2025 8:00 AM | December 6, 2025 5:00 PM | 184 days | No | 3/17/25 | NA | NA | 0.79000000000000004
3062 | DocuEdge - Milestone 23 - CARESV1-322 ADM - CM - Storage | March 18, 2025 8:00 AM | December 5, 2025 5:00 PM | 2092FS-183d | 2094FS-183d | As Soon As Possible | NA | 183 | 145.36d | March 18, 2025 8:00 AM | December 7, 2025 5:00 PM | 183 days | No | 3/18/25 | NA | NA | 0.79000000000000004
3063 | DocuEdge - Milestone 23 - CARESV1-323 ADM - CM - Search | March 18, 2025 8:00 AM | December 8, 2025 5:00 PM | 2093FS-183d |  | Finish No Earlier Than | 12/8/25 | 184 | 461d | March 18, 2025 8:00 AM | December 8, 2025 5:00 PM | 184 days | No | 3/18/25 | NA | NA | 0.79000000000000004
3064 | DocuEdge - Milestone 24 | March 10, 2025 8:00 AM | December 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 186 | 465d | March 10, 2025 8:00 AM | December 2, 2025 5:00 PM | 186 days | No | 3/10/25 | NA | NA | 0.81999999999999995
3065 | DocuEdge - Milestone 24 - CARESV1-313 ADM - CM - File Management and Metadata | March 10, 2025 8:00 AM | April 16, 2025 5:00 PM | 2088SS-1d | 2097 | Finish No Earlier Than | 4/16/25 | 27 | 0d | March 10, 2025 8:00 AM | April 16, 2025 5:00 PM | 27 days | No | 3/10/25 | 4/16/25 | NA | 1
3066 | DocuEdge - Milestone 24 - CARESV1-315 ADM - CM - Redaction | April 17, 2025 8:00 AM | May 23, 2025 5:00 PM | 2096 | 2098 | As Soon As Possible | NA | 27 | 0d | April 17, 2025 8:00 AM | May 24, 2025 5:00 PM | 27 days | No | 4/17/25 | 5/23/25 | NA | 1
3067 | DocuEdge - Milestone 24 - CARESV1-317 ADM - CM - Versioning | May 27, 2025 8:00 AM | July 1, 2025 5:00 PM | 2097 | 2099 | Finish No Earlier Than | 7/1/25 | 26 | 0d | May 27, 2025 8:00 AM | July 1, 2025 5:00 PM | 26 days | No | 5/27/25 | 7/1/25 | NA | 1
3068 | DocuEdge - Milestone 24 - CARESV1-319 ADM - CM - Retrieval | July 2, 2025 8:00 AM | August 8, 2025 5:00 PM | 2098 | 2100 | Finish No Earlier Than | 8/8/25 | 27 | 0d | July 2, 2025 8:00 AM | August 8, 2025 5:00 PM | 27 days | No | 7/2/25 | 8/8/25 | NA | 1
3069 | DocuEdge - Milestone 24 - CARESV1-320 ADM - CM - Upload | August 11, 2025 8:00 AM | September 15, 2025 5:00 PM | 2099 | 2101 | Finish No Earlier Than | 9/15/25 | 25 | 0d | August 11, 2025 8:00 AM | September 15, 2025 5:00 PM | 25 days | No | 8/11/25 | 9/15/25 | NA | 1
3070 | DocuEdge - Milestone 24 - CARESV1-322 ADM - CM - Storage | September 16, 2025 8:00 AM | October 23, 2025 5:00 PM | 2100 | 2102 | Finish No Earlier Than | 10/23/25 | 28 | 466d | September 16, 2025 8:00 AM | October 23, 2025 5:00 PM | 28 days | No | 9/16/25 | NA | NA | 0.68000000000000005
3071 | DocuEdge - Milestone 24 - CARESV1-323 ADM - CM - Search | October 27, 2025 8:00 AM | December 2, 2025 5:00 PM | 2101 |  | Finish No Earlier Than | 12/2/25 | 25 | 465d | October 27, 2025 8:00 AM | December 2, 2025 5:00 PM | 25 days | No | NA | NA | NA | 0
3072 | DocuEdge - Milestone 26 | May 8, 2024 8:00 AM | December 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 395 | 465d | May 8, 2024 8:00 AM | December 2, 2025 5:00 PM | 395 days | No | 5/8/24 | NA | NA | 0.87
3073 | DocuEdge - Milestone 26 - CARESV1-313 ADM - CM - File Management and Metadata | May 8, 2024 8:00 AM | December 2, 2025 5:00 PM | 2048SS-20d | 2105SS | Finish No Earlier Than | 12/2/25 | 395 | 465d | May 8, 2024 8:00 AM | December 2, 2025 5:00 PM | 395 days | No | 5/8/24 | NA | NA | 0.91000000000000003
3074 | DocuEdge - Milestone 26 - CARESV1-315 ADM - CM - Redaction | June 7, 2024 8:00 AM | September 2, 2025 5:00 PM | 2104SS | 2106SS | Finish No Earlier Than | 9/2/25 | 311 | 0d | June 7, 2024 8:00 AM | September 2, 2025 5:00 PM | 311 days | No | 6/7/24 | 9/2/25 | NA | 1
3075 | DocuEdge - Milestone 26 - CARESV1-317 ADM - CM - Versioning | January 6, 2025 8:00 AM | May 2, 2025 5:00 PM | 2105SS | 2107 | Finish No Earlier Than | 5/2/25 | 82 | 0d | January 6, 2025 8:00 AM | May 2, 2025 5:00 PM | 82 days | No | 1/6/25 | 5/2/25 | NA | 1
3076 | DocuEdge - Milestone 26 - CARESV1-319 ADM - CM - Retrieval | June 9, 2025 8:00 AM | September 12, 2025 5:00 PM | 2106 | 2108 | Finish No Earlier Than | 9/12/25 | 68 | 0d | June 9, 2025 8:00 AM | September 12, 2025 5:00 PM | 68 days | No | 6/9/25 | 9/12/25 | NA | 1
3077 | DocuEdge - Milestone 26 - CARESV1-320 ADM - CM - Upload | October 8, 2025 8:00 AM | November 12, 2025 5:00 PM | 2107 | 163,2109SS-45d | Finish No Earlier Than | 11/12/25 | 25 | 478d | October 8, 2025 8:00 AM | November 12, 2025 5:00 PM | 25 days | No | 10/8/25 | NA | NA | 0.12
3078 | DocuEdge - Milestone 26 - CARESV1-322 ADM - CM - Storage | September 10, 2025 8:00 AM | December 2, 2025 5:00 PM | 2108SS-45d | 2110FF | Finish No Earlier Than | 12/2/25 | 58 | 465d | September 10, 2025 8:00 AM | December 2, 2025 5:00 PM | 58 days | No | 9/10/25 | NA | NA | 0.40000000000000002
3079 | DocuEdge - Milestone 26 - CARESV1-323 ADM - CM - Search | August 12, 2025 8:00 AM | December 2, 2025 5:00 PM | 2109FF |  | Finish No Earlier Than | 12/2/25 | 78 | 465d | August 12, 2025 8:00 AM | December 2, 2025 5:00 PM | 78 days | No | 8/12/25 | NA | NA | 0.55000000000000004
3080 | DocuEdge - Milestone 27 | September 9, 2024 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 0d | September 9, 2024 8:00 AM | August 9, 2025 5:00 PM | 230 days | No | 9/9/24 | 8/8/25 | NA | 1
3081 | DocuEdge - Milestone 27 - CARESV1-313 ADM - CM - File Management and Metadata | September 9, 2024 8:00 AM | November 1, 2024 5:00 PM | 2072 | 2113,2120SS | As Soon As Possible | NA | 40 | 0d | September 9, 2024 8:00 AM | November 3, 2024 5:00 PM | 40 days | No | 9/9/24 | 11/1/24 | NA | 1
3082 | DocuEdge - Milestone 27 - CARESV1-315 ADM - CM - Redaction | November 4, 2024 8:00 AM | December 27, 2024 5:00 PM | 2112 | 2114 | As Soon As Possible | NA | 36 | 0d | November 4, 2024 8:00 AM | December 29, 2024 5:00 PM | 36 days | No | 11/4/24 | 12/27/24 | NA | 1
3083 | DocuEdge - Milestone 27 - CARESV1-317 ADM - CM - Versioning | December 30, 2024 8:00 AM | February 21, 2025 5:00 PM | 2113 | 2115 | As Soon As Possible | NA | 37 | 0d | December 30, 2024 8:00 AM | February 22, 2025 5:00 PM | 37 days | No | 12/30/24 | 2/21/25 | NA | 1
3084 | DocuEdge - Milestone 27 - CARESV1-319 ADM - CM - Retrieval | February 24, 2025 8:00 AM | April 18, 2025 5:00 PM | 2114 | 2116 | Finish No Earlier Than | 4/18/25 | 39 | 0d | February 24, 2025 8:00 AM | April 19, 2025 5:00 PM | 39 days | No | 2/24/25 | 4/18/25 | NA | 1
3085 | DocuEdge - Milestone 27 - CARESV1-320 ADM - CM - Upload | April 21, 2025 8:00 AM | June 13, 2025 5:00 PM | 2115 | 2117 | Finish No Earlier Than | 6/13/25 | 39 | 0d | April 21, 2025 8:00 AM | June 14, 2025 5:00 PM | 39 days | No | 4/21/25 | 6/13/25 | NA | 1
3086 | DocuEdge - Milestone 27 - CARESV1-322 ADM - CM - Storage | June 16, 2025 8:00 AM | August 8, 2025 5:00 PM | 2116 | 2118SS-15d | Finish No Earlier Than | 8/8/25 | 39 | 0d | June 16, 2025 8:00 AM | August 9, 2025 5:00 PM | 39 days | No | 6/16/25 | 8/8/25 | NA | 1
3087 | DocuEdge - Milestone 27 - CARESV1-323 ADM - CM - Search | July 21, 2025 8:00 AM | August 7, 2025 5:00 PM | 2117SS-15d |  | Finish No Earlier Than | 8/7/25 | 14 | 0d | July 21, 2025 8:00 AM | August 7, 2025 5:00 PM | 14 days | No | 7/21/25 | 8/7/25 | NA | 1
3088 | DocuEdge - Milestone 28 | September 9, 2024 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 224 | 0d | September 9, 2024 8:00 AM | July 31, 2025 5:00 PM | 224 days | No | 9/9/24 | 7/31/25 | NA | 1
3089 | DocuEdge - Milestone 28 - CARESV1-313 ADM - CM - File Management and Metadata | September 9, 2024 8:00 AM | November 1, 2024 5:00 PM | 2112SS | 2121,2129SS-145d | Finish No Earlier Than | 11/1/24 | 40 | 0d | September 9, 2024 8:00 AM | November 1, 2024 5:00 PM | 40 days | No | 9/9/24 | 11/1/24 | NA | 1
3090 | DocuEdge - Milestone 28 - CARESV1-315 ADM - CM - Redaction | November 4, 2024 8:00 AM | December 25, 2024 5:00 PM | 2120 | 2122 | Finish No Earlier Than | 12/25/24 | 34 | 0d | November 4, 2024 8:00 AM | December 25, 2024 5:00 PM | 34 days | No | 11/4/24 | 12/25/24 | NA | 1
3091 | DocuEdge - Milestone 28 - CARESV1-317 ADM - CM - Versioning | December 26, 2024 8:00 AM | February 17, 2025 5:00 PM | 2121 | 2123 | Finish No Earlier Than | 2/17/25 | 35 | 0d | December 26, 2024 8:00 AM | February 17, 2025 5:00 PM | 35 days | No | 12/26/24 | 2/17/25 | NA | 1
3092 | DocuEdge - Milestone 28 - CARESV1-319 ADM - CM - Retrieval | February 18, 2025 8:00 AM | April 11, 2025 5:00 PM | 2122 | 2124 | Finish No Earlier Than | 4/11/25 | 38 | 0d | February 18, 2025 8:00 AM | April 12, 2025 5:00 PM | 38 days | No | 2/18/25 | 4/11/25 | NA | 1
3093 | DocuEdge - Milestone 28 - CARESV1-320 ADM - CM - Upload | April 14, 2025 8:00 AM | June 6, 2025 5:00 PM | 2123 | 2125 | Finish No Earlier Than | 6/6/25 | 39 | 0d | April 14, 2025 8:00 AM | June 6, 2025 5:00 PM | 39 days | No | 4/14/25 | 6/6/25 | NA | 1
3094 | DocuEdge - Milestone 28 - CARESV1-322 ADM - CM - Storage | June 9, 2025 8:00 AM | July 31, 2025 5:00 PM | 2124 | 2126SS-18d | Finish No Earlier Than | 7/31/25 | 38 | 0d | June 9, 2025 8:00 AM | July 31, 2025 5:00 PM | 38 days | No | 6/9/25 | 7/31/25 | NA | 1
3095 | DocuEdge - Milestone 28 - CARESV1-323 ADM - CM - Search | July 8, 2025 8:00 AM | July 11, 2025 5:00 PM | 2125SS-18d |  | Finish No Earlier Than | 7/11/25 | 4 | 0d | July 8, 2025 8:00 AM | July 11, 2025 5:00 PM | 4 days | No | 7/8/25 | 7/11/25 | NA | 1
3120 | Document Migration | January 30, 2024 8:00 AM | June 25, 2025 5:00 PM |  |  | As Soon As Possible | NA | 354 | 0d | January 30, 2024 8:00 AM | December 5, 2024 5:00 PM | 216 days | No | 1/30/24 | 6/25/25 | NA | 1
3121 | Document Ingestion | January 30, 2024 8:00 AM | September 27, 2024 5:00 PM |  |  | As Soon As Possible | NA | 170 | 0d | January 30, 2024 8:00 AM | September 6, 2024 5:00 PM | 155 days | No | 1/30/24 | 9/27/24 | NA | 1
3122 | Document Ingestion - DC Baseline | January 30, 2024 8:00 AM | May 22, 2024 5:00 PM | 2120SS-145d | 2130 | Finish No Earlier Than | 5/22/24 | 80 | 0d | January 30, 2024 8:00 AM | May 22, 2024 5:00 PM | 80 days | No | 1/30/24 | 5/22/24 | NA | 1
3123 | Document Ingestion - DC Dev | May 20, 2024 8:00 AM | June 13, 2024 5:00 PM | 2129 | 2131 | As Soon As Possible | NA | 18 | 0d | May 20, 2024 8:00 AM | June 13, 2024 5:00 PM | 18 days | No | 5/20/24 | 6/13/24 | NA | 1
3124 | Document Ingestion - DC QA | August 26, 2024 8:00 AM | September 27, 2024 5:00 PM | 2130 | 2132 | As Soon As Possible | NA | 25 | 0d | June 14, 2024 8:00 AM | July 26, 2024 5:00 PM | 30 days | No | 8/26/24 | 9/27/24 | NA | 1
3125 | Document Ingestion - DC VAL | July 29, 2024 8:00 AM | September 6, 2024 5:00 PM | 2131 | 2134 | As Soon As Possible | NA | 30 | 0d | July 29, 2024 8:00 AM | September 6, 2024 5:00 PM | 30 days | No | 7/29/24 | 9/6/24 | NA | 1
3126 | Document Linking | September 10, 2024 8:00 AM | December 5, 2024 5:00 PM |  |  | As Soon As Possible | NA | 60 | 0d | September 10, 2024 8:00 AM | December 5, 2024 5:00 PM | 60 days | No | 9/10/24 | 12/5/24 | NA | 1
3127 | Document Linking - DC Dev | September 10, 2024 8:00 AM | October 21, 2024 5:00 PM | 2132 | 2135 | Finish No Earlier Than | 10/21/24 | 30 | 0d | September 10, 2024 8:00 AM | October 21, 2024 5:00 PM | 30 days | No | 9/10/24 | 10/21/24 | NA | 1
3128 | Document Linking - DC QA | October 22, 2024 8:00 AM | November 12, 2024 5:00 PM | 2134 | 2136 | Finish No Earlier Than | 11/12/24 | 15 | 0d | October 22, 2024 8:00 AM | November 12, 2024 5:00 PM | 15 days | No | 10/22/24 | 11/12/24 | NA | 1
3129 | Document Linking - DC VAL | November 13, 2024 8:00 AM | December 5, 2024 5:00 PM | 2135 |  | Finish No Earlier Than | 12/5/24 | 15 | 0d | November 13, 2024 8:00 AM | December 5, 2024 5:00 PM | 15 days | No | 11/13/24 | 12/5/24 | NA | 1
11773 | Document Taxonomy | December 19, 2024 8:00 AM | June 25, 2025 5:00 PM |  |  | As Soon As Possible | NA | 129 | 0d | NA | NA | 0 days? | No | 12/19/24 | 6/25/25 | NA | 1
13046 | Taxonomy Design Update | December 19, 2024 8:00 AM | January 10, 2025 5:00 PM |  | 2139 | Start No Earlier Than | 12/19/24 | 15 | 0d | NA | NA | 0 days? | No | 12/19/24 | 1/10/25 | NA | 1
13047 | Taxonomy Internal Review | January 13, 2025 8:00 AM | January 17, 2025 5:00 PM | 2138 | 2140 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 1/13/25 | 1/17/25 | NA | 1
13048 | Taxonomy Review w/SMs and PDLs | January 21, 2025 8:00 AM | January 31, 2025 5:00 PM | 2139 | 2141 | As Soon As Possible | NA | 9 | 0d | NA | NA | 0 days? | No | 1/21/25 | 1/31/25 | NA | 1
13045 | Gap Analysis and prep for Implementation | February 3, 2025 8:00 AM | April 1, 2025 5:00 PM | 2140 | 2142 | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 2/3/25 | 4/1/25 | NA | 1
11774 | Implement Approved Taxonomy | April 2, 2025 8:00 AM | June 25, 2025 5:00 PM | 2141 | 2167 | As Soon As Possible | NA | 60 | 0d | NA | NA | 0 days? | No | 4/2/25 | 6/25/25 | NA | 1
3131 | Data Conversion LOE (CARESV1-13763) | June 20, 2022 8:00 AM | December 9, 2026 3:24 PM |  |  | As Soon As Possible | NA | 1120.8 | 210.2d | June 20, 2022 8:00 AM | August 27, 2026 5:00 PM | 1051 days | No | 6/20/22 | NA | NA | 0.90000000000000002
3132 | Non-Structured Data Conversion Activities (CARESV1-11551) | February 1, 2023 8:00 AM | June 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 854 | 272d | February 1, 2023 8:00 AM | June 26, 2026 5:00 PM | 854 days | No | 2/1/23 | NA | NA | 0.93000000000000005
3133 | Non-Structured Data Conversion - File extracts from CWS-CMS Host to CDI | February 1, 2023 8:00 AM | February 28, 2023 5:00 PM |  | 2147 | Start No Earlier Than | 2/1/23 | 20 | 0d | February 1, 2023 8:00 AM | February 28, 2023 5:00 PM | 20 days | No | 2/1/23 | 2/28/23 | NA | 1
3134 | CWS-CMS host documents Phase1 and 2 | April 3, 2023 8:00 AM | December 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 184 | 0d | April 3, 2023 8:00 AM | December 22, 2023 5:00 PM | 184 days | No | 4/3/23 | 12/22/23 | NA | 1
3135 | Non-Structured Data Conversion - Extract CWS-CMS host documents from PullDOCS vdi to CDI (Phase 1 and 2) | June 1, 2023 8:00 AM | August 30, 2023 5:00 PM | 2145 | 2148,2154SS | Finish No Earlier Than | 8/30/23 | 64 | 0d | June 1, 2023 8:00 AM | August 30, 2023 5:00 PM | 64 days | No | 6/1/23 | 8/30/23 | NA | 1
3136 | Non-Structured Data Conversion - Build Metadata generation | April 3, 2023 8:00 AM | May 31, 2023 5:00 PM | 2147 | 2149 | Finish No Earlier Than | 5/31/23 | 42 | 0d | April 3, 2023 8:00 AM | May 31, 2023 5:00 PM | 42 days | No | 4/3/23 | 5/31/23 | NA | 1
3137 | Non-Structured Data Conversion - Generate document metadata ingestion | November 1, 2023 8:00 AM | December 22, 2023 5:00 PM | 2148 | 2151 | As Soon As Possible | NA | 35 | 0d | November 1, 2023 8:00 AM | December 22, 2023 5:00 PM | 35 days | No | 11/1/23 | 12/22/23 | NA | 1
3138 | CWS-CMS host documents Phase3 | December 26, 2023 8:00 AM | June 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 629 | 57d | December 26, 2023 8:00 AM | June 26, 2026 5:00 PM | 629 days | No | 12/26/23 | NA | NA | 0.71999999999999997
3139 | Non-Structured Data Conversion - Extract from Pulldoc VDI into CDI S3 | December 26, 2023 8:00 AM | May 29, 2026 5:00 PM | 2149 | 2152 | As Soon As Possible | NA | 609 | 57d | December 26, 2023 8:00 AM | May 29, 2026 5:00 PM | 609 days | No | 12/26/23 | NA | NA | 0.73999999999999999
3140 | Non-Structured Data Conversion - Generate document ingestion metadata | June 1, 2026 8:00 AM | June 26, 2026 5:00 PM | 2151 | 5628 | Finish No Earlier Than | 6/26/26 | 20 | 57d | June 1, 2026 8:00 AM | June 26, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
3141 | Generating document linking metadata Foundation framework | June 1, 2023 8:00 AM | August 30, 2023 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | June 1, 2023 8:00 AM | August 30, 2023 5:00 PM | 64 days | No | 6/1/23 | 8/30/23 | NA | 1
3142 | Generating document linking metadata Foundation framework - Build | June 1, 2023 8:00 AM | August 30, 2023 5:00 PM | 2147SS | 2156 | Finish No Earlier Than | 8/30/23 | 64 | 0d | June 1, 2023 8:00 AM | August 30, 2023 5:00 PM | 64 days | No | 6/1/23 | 8/30/23 | NA | 1
3143 | Documents and metadata copy from Baseline DocuEdge to DC env | March 4, 2024 8:00 AM | June 21, 2024 5:00 PM |  |  | As Soon As Possible | NA | 78 | 0d | March 4, 2024 8:00 AM | June 21, 2024 5:00 PM | 78 days | No | 3/4/24 | 6/21/24 | NA | 1
3144 | Documents and metadata copy from Baseline DocuEdge to DC env - Analysis | March 4, 2024 8:00 AM | March 8, 2024 5:00 PM | 2154 | 2157 | Finish No Earlier Than | 3/8/24 | 5 | 0d | March 4, 2024 8:00 AM | March 8, 2024 5:00 PM | 5 days | No | 3/4/24 | 3/8/24 | NA | 1
3145 | Documents and metadata copy from Baseline DocuEdge to DC env - Design | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 2156 | 2158 | Finish No Earlier Than | 3/15/24 | 5 | 0d | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 5 days | No | 3/11/24 | 3/15/24 | NA | 1
3146 | Documents and metadata copy from Baseline DocuEdge to DC env - Build | April 2, 2024 8:00 AM | April 12, 2024 5:00 PM | 2157 | 2159 | Finish No Earlier Than | 4/12/24 | 9 | 0d | April 2, 2024 8:00 AM | April 12, 2024 5:00 PM | 9 days | No | 4/2/24 | 4/12/24 | NA | 1
3147 | Documents and metadata copy from Baseline DocuEdge to DC env - Execution in DCDEV | April 16, 2024 8:00 AM | May 17, 2024 5:00 PM | 2158 | 2160 | Finish No Earlier Than | 5/17/24 | 24 | 0d | April 16, 2024 8:00 AM | May 17, 2024 5:00 PM | 24 days | No | 4/16/24 | 5/17/24 | NA | 1
3148 | Documents and metadata copy from Baseline DocuEdge to DC env - Execution in DCVAL | May 20, 2024 8:00 AM | June 21, 2024 5:00 PM | 2159 | 2162 | Finish No Earlier Than | 6/21/24 | 24 | 0d | May 20, 2024 8:00 AM | June 21, 2024 5:00 PM | 24 days | No | 5/20/24 | 6/21/24 | NA | 1
3149 | Generating document linking metadata | April 1, 2024 8:00 AM | October 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 380 | 0d | April 1, 2024 8:00 AM | October 2, 2025 5:00 PM | 380 days | No | 4/1/24 | 10/2/25 | NA | 1
5568 | Generating document linking metadata - Build Interim doc linking logic | April 1, 2024 8:00 AM | May 6, 2024 5:00 PM | 2160 | 2163,2169 | As Soon As Possible | NA | 25 | 0d | April 1, 2024 8:00 AM | May 6, 2024 5:00 PM | 25 days | No | 4/1/24 | 5/6/24 | NA | 1
3150 | Generating document linking metadata - Build doc linking logic DC Cycle1,2,3 service areas | June 17, 2024 8:00 AM | June 28, 2024 5:00 PM | 2162 | 2164 | Finish No Earlier Than | 6/28/24 | 10 | 0d | June 17, 2024 8:00 AM | June 28, 2024 5:00 PM | 10 days | No | 6/17/24 | 6/28/24 | NA | 1
3151 | Generating document linking metadata - Build doc linking logic DC Cycle4 service areas | September 23, 2024 8:00 AM | October 4, 2024 5:00 PM | 2163 | 2165 | Start No Earlier Than | 9/23/24 | 10 | 0d | September 23, 2024 8:00 AM | October 4, 2024 5:00 PM | 10 days | No | 9/23/24 | 10/4/24 | NA | 1
3152 | Generating document linking metadata - Build doc linking logic DC Cycle5 Service areas | March 24, 2025 8:00 AM | April 4, 2025 5:00 PM | 2164 | 2166 | Start No Earlier Than | 3/24/25 | 9 | 0d | March 24, 2025 8:00 AM | April 4, 2025 5:00 PM | 9 days | No | 3/24/25 | 4/4/25 | NA | 1
3153 | Generating document linking metadata - Build doc linking logic DC Cycle6 Service areas | September 22, 2025 8:00 AM | October 2, 2025 5:00 PM | 2165 |  | Start No Earlier Than | 9/22/25 | 9 | 0d | September 22, 2025 8:00 AM | October 2, 2025 5:00 PM | 9 days | No | 9/22/25 | 10/2/25 | NA | 1
3155 | Generating document linking metadata - Build Document Ingestion and Linking Reports | June 26, 2025 8:00 AM | July 2, 2025 5:00 PM | 2142 | 2198FS-24d | Start No Earlier Than | 8/26/24 | 5 | 0d | August 26, 2024 8:00 AM | September 19, 2024 5:00 PM | 19 days | No | 6/26/25 | 7/2/25 | NA | 1
3156 | Load person search master data entity to Solr | March 1, 2023 8:00 AM | December 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 206 | 0d | March 1, 2023 8:00 AM | December 22, 2023 5:00 PM | 206 days | No | 3/1/23 | 12/22/23 | NA | 1
3157 | Load person search master data entity to Solr - Build | March 1, 2023 8:00 AM | April 28, 2023 5:00 PM | 2162 | 2170 | Finish No Earlier Than | 4/28/23 | 43 | 0d | March 1, 2023 8:00 AM | April 28, 2023 5:00 PM | 43 days | No | 3/1/23 | 4/28/23 | NA | 1
3158 | Load person search master data entity to Solr - Execution - DC Cycle 1 | June 1, 2023 8:00 AM | June 30, 2023 5:00 PM | 2169 | 2171 | Finish No Earlier Than | 6/30/23 | 22 | 0d | June 1, 2023 8:00 AM | June 30, 2023 5:00 PM | 22 days | No | 6/1/23 | 6/30/23 | NA | 1
3159 | Load person search master data entity to Solr - Execution - DC Cycle 2 | December 4, 2023 8:00 AM | December 22, 2023 5:00 PM | 2170 | 2173 | Finish No Earlier Than | 12/22/23 | 15 | 0d | December 4, 2023 8:00 AM | December 22, 2023 5:00 PM | 15 days | No | 12/4/23 | 12/22/23 | NA | 1
3160 | Provider Search Solr Master data entities foundation | March 4, 2024 8:00 AM | April 19, 2024 5:00 PM |  |  | As Soon As Possible | NA | 34 | 0d | March 4, 2024 8:00 AM | April 19, 2024 5:00 PM | 34 days | No | 3/4/24 | 4/19/24 | NA | 1
3161 | Provider Search Solr Master data entities foundation - Analysis | March 4, 2024 8:00 AM | March 8, 2024 5:00 PM | 2171 | 2174 | Finish No Earlier Than | 3/8/24 | 5 | 0d | March 4, 2024 8:00 AM | March 8, 2024 5:00 PM | 5 days | No | 3/4/24 | 3/8/24 | NA | 1
3162 | Provider Search Solr Master data entities foundation - Mapping | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 2173 | 2175 | Finish No Earlier Than | 3/15/24 | 5 | 0d | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 5 days | No | 3/11/24 | 3/15/24 | NA | 1
3163 | Provider Search Solr Master data entities foundation - Build | March 18, 2024 8:00 AM | March 22, 2024 5:00 PM | 2174 | 2176 | Finish No Earlier Than | 3/22/24 | 5 | 0d | March 18, 2024 8:00 AM | March 22, 2024 5:00 PM | 5 days | No | 3/18/24 | 3/22/24 | NA | 1
3164 | Provider Search Solr Master data entities foundation - Execution in DCDEV | April 8, 2024 8:00 AM | April 19, 2024 5:00 PM | 2175 | 2178 | Finish No Earlier Than | 4/19/24 | 10 | 0d | April 8, 2024 8:00 AM | April 19, 2024 5:00 PM | 10 days | No | 4/8/24 | 4/19/24 | NA | 1
3165 | Micro Conversion foundation framework | May 1, 2023 8:00 AM | December 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 164 | 0d | May 1, 2023 8:00 AM | December 22, 2023 5:00 PM | 164 days | No | 5/1/23 | 12/22/23 | NA | 1
3166 | Micro Conversion foundation framework - Build | May 1, 2023 8:00 AM | September 29, 2023 5:00 PM | 2176 | 2179,2214SS+1d | Finish No Earlier Than | 9/29/23 | 110 | 0d | May 1, 2023 8:00 AM | September 29, 2023 5:00 PM | 110 days | No | 5/1/23 | 9/29/23 | NA | 1
3167 | Micro Conversion foundation framework - Unit Test | July 10, 2023 8:00 AM | October 27, 2023 5:00 PM | 2178 | 2180,2210SS | Finish No Earlier Than | 10/27/23 | 80 | 0d | July 10, 2023 8:00 AM | October 27, 2023 5:00 PM | 80 days | No | 7/10/23 | 10/27/23 | NA | 1
3168 | Micro Conversion foundation framework - Execution - DC Cycle2 | December 4, 2023 8:00 AM | December 22, 2023 5:00 PM | 2179 | 2182 | Finish No Earlier Than | 12/22/23 | 15 | 0d | December 4, 2023 8:00 AM | December 22, 2023 5:00 PM | 15 days | No | 12/4/23 | 12/22/23 | NA | 1
3169 | Micro Conversion scripts | December 4, 2023 8:00 AM | October 17, 2025 5:00 PM |  |  | As Soon As Possible | NA | 472 | 444d | December 4, 2023 8:00 AM | October 17, 2025 5:00 PM | 472 days | No | 12/4/23 | NA | NA | 0.93999999999999995
3170 | Micro Conversion scripts - Build scripts for DC Cycle1,2 Scope objects | December 4, 2023 8:00 AM | December 29, 2023 5:00 PM | 2180 | 2333,2183FS+85d | Finish No Earlier Than | 12/29/23 | 19 | 0d | December 4, 2023 8:00 AM | December 29, 2023 5:00 PM | 19 days | No | 12/4/23 | 12/29/23 | NA | 1
3171 | Micro Conversion scripts - Build scripts for DC Cycle3 Scope objects | May 6, 2024 8:00 AM | May 24, 2024 5:00 PM | 2182FS+85d | 2343,2184FS+85d | Finish No Earlier Than | 5/24/24 | 15 | 0d | May 6, 2024 8:00 AM | May 24, 2024 5:00 PM | 15 days | No | 5/6/24 | 5/24/24 | NA | 1
3172 | Micro Conversion scripts - Build scripts for DC Cycle4 Scope objects | September 30, 2024 8:00 AM | October 18, 2024 5:00 PM | 2183FS+85d | 2353,2185FS+85d | Finish No Earlier Than | 10/18/24 | 15 | 0d | September 30, 2024 8:00 AM | October 18, 2024 5:00 PM | 15 days | No | 9/30/24 | 10/18/24 | NA | 1
3173 | Micro Conversion scripts - Build scripts for DC Cycle5 Scope objects | April 7, 2025 8:00 AM | April 25, 2025 5:00 PM | 2184FS+85d | 2363,2186FS+85d,2192SS+10d | Finish No Earlier Than | 4/25/25 | 15 | 0d | April 7, 2025 8:00 AM | April 25, 2025 5:00 PM | 15 days | No | 4/7/25 | 4/25/25 | NA | 1
3174 | Micro Conversion scripts - Build scripts for DC Cycle6 Scope objects | September 29, 2025 8:00 AM | October 17, 2025 5:00 PM | 2185FS+85d | 2373FS-5d,2193SS+5d | Finish No Earlier Than | 10/17/25 | 15 | 444d | September 29, 2025 8:00 AM | October 17, 2025 5:00 PM | 15 days | No | 9/29/25 | NA | NA | 0.67000000000000004
3176 | Converted Data Load to Snowflake | December 4, 2023 8:00 AM | October 17, 2025 5:00 PM |  |  | As Soon As Possible | NA | 472 | 444d | December 4, 2023 8:00 AM | October 17, 2025 5:00 PM | 472 days | No | 12/4/23 | NA | NA | 0.93999999999999995
3177 | Converted Data Load to Snowflake - Build foundation framework | December 4, 2023 8:00 AM | January 26, 2024 5:00 PM | 3348SS | 2189,2201FS-18d | Finish No Earlier Than | 1/26/24 | 37 | 0d | December 4, 2023 8:00 AM | January 26, 2024 5:00 PM | 37 days | No | 12/4/23 | 1/26/24 | NA | 1
3178 | Converted Data Load to Snowflake - Build views for DC Cycle1,2 scope objects | January 29, 2024 8:00 AM | February 2, 2024 5:00 PM | 2188 | 2333,2190FS+70d,2195FS+60d | Finish No Earlier Than | 2/2/24 | 5 | 0d | January 29, 2024 8:00 AM | February 2, 2024 5:00 PM | 5 days | No | 1/29/24 | 2/2/24 | NA | 1
3179 | Converted Data Load to Snowflake - Build views for DC Cycle3 scope objects | May 20, 2024 8:00 AM | June 3, 2024 5:00 PM | 2189FS+70d | 2343,2191FS+90d | Start No Earlier Than | 5/20/24 | 10 | 0d | May 20, 2024 8:00 AM | June 3, 2024 5:00 PM | 10 days | No | 5/20/24 | 6/3/24 | NA | 1
3180 | Converted Data Load to Snowflake - Build views for DC Cycle4 scope objects | October 21, 2024 8:00 AM | November 1, 2024 5:00 PM | 2190FS+90d | 2353 | Start No Earlier Than | 10/21/24 | 10 | 0d | October 21, 2024 8:00 AM | November 1, 2024 5:00 PM | 10 days | No | 10/21/24 | 11/1/24 | NA | 1
3181 | Converted Data Load to Snowflake - Build views for DC Cycle5 scope objects | April 21, 2025 8:00 AM | May 2, 2025 5:00 PM | 2185SS+10d | 2363 | Start No Earlier Than | 4/21/25 | 10 | 0d | April 21, 2025 8:00 AM | May 2, 2025 5:00 PM | 10 days | No | 4/21/25 | 5/2/25 | NA | 1
3182 | Converted Data Load to Snowflake - Build views for DC Cycle6 scope objects | October 6, 2025 8:00 AM | October 17, 2025 5:00 PM | 2186SS+5d | 2373FS-5d,2199SS | Finish No Earlier Than | 10/17/25 | 10 | 444d | October 6, 2025 8:00 AM | October 17, 2025 5:00 PM | 10 days | No | 10/6/25 | NA | NA | 0.5
5569 | Trigger analysis for data conversion | May 6, 2024 8:00 AM | October 17, 2025 5:00 PM |  |  | As Soon As Possible | NA | 367 | 444d | May 6, 2024 8:00 AM | October 17, 2025 5:00 PM | 367 days | No | 5/6/24 | NA | NA | 0.96999999999999997
5570 | Trigger analysis for data conversion - Analysis for DC Cycle1,2 scope objects | May 6, 2024 8:00 AM | June 28, 2024 5:00 PM | 2189FS+60d | 2333,2196 | Start No Later Than | 5/6/24 | 39 | 0d | May 6, 2024 8:00 AM | June 28, 2024 5:00 PM | 39 days | No | 5/6/24 | 6/28/24 | NA | 1
5571 | Trigger analysis for data conversion - Analysis for DC Cycle3 scope objects | July 1, 2024 8:00 AM | August 23, 2024 5:00 PM | 2195 | 2343FS-44d,2197 | Start No Earlier Than | 7/1/24 | 39 | 0d | July 1, 2024 8:00 AM | August 23, 2024 5:00 PM | 39 days | No | 7/1/24 | 8/23/24 | NA | 1
5572 | Trigger analysis for data conversion - Analysis for DC Cycle4 scope objects | August 26, 2024 8:00 AM | October 17, 2024 5:00 PM | 2196 | 2353 | Start No Earlier Than | 8/26/24 | 39 | 0d | August 26, 2024 8:00 AM | October 17, 2024 5:00 PM | 39 days | No | 8/26/24 | 10/17/24 | NA | 1
5573 | Trigger analysis for data conversion - Analysis for DC Cycle5 scope objects | January 6, 2025 8:00 AM | July 10, 2025 9:07 AM | 2167FS-24d | 2363 | Start No Earlier Than | 1/6/25 | 42 | 0d | January 6, 2025 8:00 AM | March 6, 2025 5:00 PM | 42 days | No | 1/6/25 | 7/10/25 | NA | 1
5574 | Trigger analysis for data conversion - Analysis for DC Cycle6 scope objects | October 6, 2025 8:00 AM | October 17, 2025 5:00 PM | 2193SS | 2373FS-5d | Start No Earlier Than | 10/6/25 | 10 | 444d | October 6, 2025 8:00 AM | October 17, 2025 5:00 PM | 10 days | No | 10/6/25 | NA | NA | 0.5
5575 | Legacy User loads | January 1, 2024 8:00 AM | September 5, 2025 5:00 PM |  |  | As Soon As Possible | NA | 423 | 0d | January 1, 2024 8:00 AM | February 28, 2025 5:00 PM | 292 days | No | 1/1/24 | 9/5/25 | NA | 1
5576 | Legacy User loads - Build Legacy user load foundation framework | January 1, 2024 8:00 AM | April 2, 2024 5:00 PM | 2188FS-18d | 2202FS-1d,2207SS+18d | As Soon As Possible | NA | 63 | 0d | January 1, 2024 8:00 AM | April 2, 2024 5:00 PM | 63 days | No | 1/1/24 | 4/2/24 | NA | 1
5577 | Legacy User loads - Legacy user Initial Load to DCDEV | April 1, 2024 8:00 AM | May 10, 2024 5:00 PM | 2201FS-1d | 2203SS | Start No Earlier Than | 4/1/24 | 29 | 0d | April 1, 2024 8:00 AM | May 10, 2024 5:00 PM | 29 days | No | 4/1/24 | 5/10/24 | NA | 1
5578 | Legacy User loads - Address Legacy User data quality | April 1, 2024 8:00 AM | December 26, 2024 5:00 PM | 2202SS | 2204FS+135d | Finish No Earlier Than | 12/26/24 | 187 | 0d | April 1, 2024 8:00 AM | December 26, 2024 5:00 PM | 187 days | No | 4/1/24 | 12/26/24 | NA | 1
5579 | Legacy User loads - Build revision with the Legacy vs CARES Persona finalized mapping | July 14, 2025 8:00 AM | September 5, 2025 5:00 PM | 2203FS+135d | 2205SS-150d,2212SS+8d | Start No Earlier Than | 1/6/25 | 39 | 0d | January 6, 2025 8:00 AM | February 28, 2025 5:00 PM | 38 days | No | 7/14/25 | 9/5/25 | NA | 1
5580 | Legacy User loads - Link Legacy converted data created by, updated by to the legacy users | May 20, 2024 8:00 AM | July 19, 2024 5:00 PM | 2204SS-150d |  | Start No Earlier Than | 5/20/24 | 43 | 0d | May 20, 2024 8:00 AM | July 19, 2024 5:00 PM | 43 days | No | 5/20/24 | 7/19/24 | NA | 1
5581 | Legacy data Owner Id mapping | January 22, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 156 | 0d | January 22, 2024 8:00 AM | August 30, 2024 5:00 PM | 156 days | No | 1/22/24 | 8/30/24 | NA | 1
5582 | Legacy data Owner Id mapping - Categorize and identify Options | January 22, 2024 8:00 AM | March 29, 2024 5:00 PM | 2201SS+18d | 2208 | As Soon As Possible | NA | 49 | 0d | January 22, 2024 8:00 AM | March 29, 2024 5:00 PM | 49 days | No | 1/22/24 | 3/29/24 | NA | 1
5583 | Legacy data Owner Id mapping - Mapping for each category | April 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 2207 |  | Finish No Earlier Than | 8/30/24 | 107 | 0d | April 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 107 days | No | 4/1/24 | 8/30/24 | NA | 1
3184 | Infected, Unsupported file extensions Report | July 10, 2023 8:00 AM | April 19, 2024 5:00 PM |  |  | As Soon As Possible | NA | 196 | 0d | July 10, 2023 8:00 AM | April 19, 2024 5:00 PM | 196 days | No | 7/10/23 | 4/19/24 | NA | 1
3185 | Infected, Unsupported file extensions Report - Iteration 1 | July 10, 2023 8:00 AM | October 6, 2023 5:00 PM | 2179SS | 2211 | Finish No Earlier Than | 10/6/23 | 65 | 0d | July 10, 2023 8:00 AM | October 6, 2023 5:00 PM | 65 days | No | 7/10/23 | 10/6/23 | NA | 1
3186 | Infected, Unsupported file extensions Report - Iteration 2 | January 29, 2024 8:00 AM | April 19, 2024 5:00 PM | 2210 |  | Start No Earlier Than | 1/29/24 | 60 | 0d | January 29, 2024 8:00 AM | April 19, 2024 5:00 PM | 60 days | No | 1/29/24 | 4/19/24 | NA | 1
3187 | Micro Conversion Delta Merge to Stage daily schedule job | January 15, 2024 8:00 AM | February 2, 2024 5:00 PM | 2204SS+8d | 2373FS-5d | Start No Earlier Than | 1/15/24 | 15 | 0d | January 15, 2024 8:00 AM | February 2, 2024 5:00 PM | 15 days | No | 1/15/24 | 2/2/24 | NA | 1
3188 | Conversion Cycle 5 - Micro Conversion Execution | May 2, 2023 8:00 AM | June 26, 2023 5:00 PM |  |  | As Soon As Possible | NA | 39 | 0d | May 2, 2023 8:00 AM | June 26, 2023 5:00 PM | 39 days | No | 5/2/23 | 6/26/23 | NA | 1
3189 | Address Standardization using Smarty foundation framework - Build | May 2, 2023 8:00 AM | June 26, 2023 5:00 PM | 2178SS+1d | 2373FS-5d | Start No Earlier Than | 5/2/23 | 40 | 0d | May 2, 2023 8:00 AM | June 26, 2023 5:00 PM | 40 days | No | 5/2/23 | 6/26/23 | NA | 1
11579 | CWS/CMS to CARES Core Data Model Mapping | January 16, 2024 8:00 AM | October 18, 2024 5:00 PM |  |  | As Soon As Possible | NA | 195 | 0d | January 16, 2024 8:00 AM | October 18, 2024 5:00 PM | 195 days | No | 1/16/24 | 10/18/24 | NA | 1
11578 | CWS/CMS to CARES Core Data Model Mapping -Entity level gap analysis | January 16, 2024 8:00 AM | May 31, 2024 5:00 PM | 2256FS+103d | 2217FS-19d | As Soon As Possible | NA | 96 | 0d | January 16, 2024 8:00 AM | May 31, 2024 5:00 PM | 96 days | No | 1/16/24 | 5/31/24 | NA | 1
11577 | CWS/CMS to CARES Core Data Model Mapping - Attribute level gap analysis | May 6, 2024 8:00 AM | October 18, 2024 5:00 PM | 2216FS-19d | 2218FS-118d | As Soon As Possible | NA | 118 | 0d | May 6, 2024 8:00 AM | October 18, 2024 5:00 PM | 118 days | No | 5/6/24 | 10/18/24 | NA | 1
11576 | CWS/CMS to CARES Core Data Model Mapping - LoV gap analysis | May 6, 2024 8:00 AM | October 18, 2024 5:00 PM | 2217FS-118d | 2219FS-79d | As Soon As Possible | NA | 118 | 0d | May 6, 2024 8:00 AM | October 18, 2024 5:00 PM | 118 days | No | 5/6/24 | 10/18/24 | NA | 1
11575 | CWS/CMS to CARES Core Data Model Mapping - Incorporate the gaps in CARES domain and object models | July 1, 2024 8:00 AM | October 18, 2024 5:00 PM | 2218FS-79d | 2389 | As Soon As Possible | NA | 79 | 0d | July 1, 2024 8:00 AM | October 18, 2024 5:00 PM | 79 days | No | 7/1/24 | 10/18/24 | NA | 1
3190 | Structured Data Conversion Activities | June 20, 2022 8:00 AM | May 8, 2026 3:24 PM |  |  | As Soon As Possible | NA | 973.8 | 13.2d | June 20, 2022 8:00 AM | December 30, 2025 5:00 PM | 885 days | No | 6/20/22 | NA | NA | 0.92000000000000004
3191 | Data Conversion - Milestone 01 | June 20, 2022 8:00 AM | November 4, 2022 5:00 PM |  |  | As Soon As Possible | NA | 98 | 0d | June 20, 2022 8:00 AM | November 4, 2022 5:00 PM | 98 days | No | 6/20/22 | 11/4/22 | NA | 1
3192 | Data Conversion - Milestone 01 - Pre-Analysis | June 20, 2022 8:00 AM | August 15, 2022 5:00 PM | 16 | 2223 | Start No Earlier Than | 6/20/22 | 40 | 0d | June 20, 2022 8:00 AM | August 15, 2022 5:00 PM | 40 days | No | 6/20/22 | 8/15/22 | NA | 1
3193 | Data Conversion - Milestone 01 - Analysis and Mapping | August 15, 2022 8:00 AM | October 10, 2022 5:00 PM | 2222 | 2224SS+20d | As Soon As Possible | NA | 40 | 0d | August 15, 2022 8:00 AM | October 10, 2022 5:00 PM | 40 days | No | 8/15/22 | 10/10/22 | NA | 1
3194 | Data Conversion - Milestone 01 - Build and SIT | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 2223SS+20d | 2344 | As Soon As Possible | NA | 40 | 0d | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 40 days | No | 9/12/22 | 11/4/22 | NA | 1
3195 | Data Conversion - Milestone 02 | June 20, 2022 8:00 AM | November 4, 2022 5:00 PM |  |  | As Soon As Possible | NA | 98 | 0d | June 20, 2022 8:00 AM | November 4, 2022 5:00 PM | 98 days | No | 6/20/22 | 11/4/22 | NA | 1
3196 | Data Conversion - Milestone 02 - Pre-Analysis | June 20, 2022 8:00 AM | August 15, 2022 5:00 PM | 41 | 2227 | As Soon As Possible | NA | 40 | 0d | June 20, 2022 8:00 AM | August 15, 2022 5:00 PM | 40 days | No | 6/20/22 | 8/15/22 | NA | 1
3197 | Data Conversion - Milestone 02 - Analysis and Mapping | August 15, 2022 8:00 AM | October 10, 2022 5:00 PM | 2226 | 2228SS+20d | As Soon As Possible | NA | 40 | 0d | August 15, 2022 8:00 AM | October 10, 2022 5:00 PM | 40 days | No | 8/15/22 | 10/10/22 | NA | 1
3198 | Data Conversion - Milestone 02 - Build and SIT | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 2227SS+20d | 2344 | As Soon As Possible | NA | 40 | 0d | September 12, 2022 8:00 AM | November 4, 2022 5:00 PM | 40 days | No | 9/12/22 | 11/4/22 | NA | 1
3199 | Data Conversion - Milestone 03 | September 12, 2022 8:00 AM | July 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 205 | 0d | September 12, 2022 8:00 AM | July 7, 2023 5:00 PM | 205 days | No | 9/12/22 | 7/7/23 | NA | 1
3200 | Data Conversion - Milestone 03 - Pre-Analysis | September 12, 2022 8:00 AM | January 30, 2023 5:00 PM | 72 | 2231FS-20d | Start No Earlier Than | 5/2/22 | 95 | 0d | September 12, 2022 8:00 AM | January 30, 2023 5:00 PM | 95 days | No | 9/12/22 | 1/30/23 | NA | 1
3201 | Data Conversion - Milestone 03 - Analysis and Mapping | December 26, 2022 8:00 AM | June 19, 2023 5:00 PM | 2230FS-20d | 2232SS+20d | As Soon As Possible | NA | 120 | 0d | December 26, 2022 8:00 AM | June 19, 2023 5:00 PM | 120 days | No | 12/26/22 | 6/19/23 | NA | 1
3202 | Data Conversion - Milestone 03 - Build and SIT | January 23, 2023 8:00 AM | July 7, 2023 5:00 PM | 2231SS+20d | 2334 | As Soon As Possible | NA | 120 | 0d | January 23, 2023 8:00 AM | July 7, 2023 5:00 PM | 120 days | No | 1/23/23 | 7/7/23 | NA | 1
3203 | Data Conversion - Milestone 04 | August 15, 2022 8:00 AM | May 19, 2023 5:00 PM |  |  | As Soon As Possible | NA | 191 | 0d | August 15, 2022 8:00 AM | May 19, 2023 5:00 PM | 191 days | No | 8/15/22 | 5/19/23 | NA | 1
3204 | Data Conversion - Milestone 04 - Pre-Analysis | August 15, 2022 8:00 AM | December 8, 2022 5:00 PM | 118 | 2235FS-20d | Start No Earlier Than | 8/15/22 | 80 | 0d | August 15, 2022 8:00 AM | December 8, 2022 5:00 PM | 80 days | No | 8/15/22 | 12/8/22 | NA | 1
3205 | Data Conversion - Milestone 04 - Analysis and Mapping | November 7, 2022 8:00 AM | May 3, 2023 5:00 PM | 2234FS-20d | 2236SS+20d | As Soon As Possible | NA | 120 | 0d | November 7, 2022 8:00 AM | May 3, 2023 5:00 PM | 120 days | No | 11/7/22 | 5/3/23 | NA | 1
3206 | Data Conversion - Milestone 04 - Build and SIT | December 5, 2022 8:00 AM | May 19, 2023 5:00 PM | 2235SS+20d | 2334 | As Soon As Possible | NA | 120 | 0d | December 5, 2022 8:00 AM | May 19, 2023 5:00 PM | 120 days | No | 12/5/22 | 5/19/23 | NA | 1
3207 | Data Conversion - Milestone 05 | October 10, 2022 8:00 AM | May 19, 2023 5:00 PM |  |  | As Soon As Possible | NA | 152 | 0d | October 10, 2022 8:00 AM | May 19, 2023 5:00 PM | 152 days | No | 10/10/22 | 5/19/23 | NA | 1
3208 | Data Conversion - Milestone 05 - Pre-Analysis | October 10, 2022 8:00 AM | February 6, 2023 5:00 PM | 168 | 2239FS-20d | As Soon As Possible | NA | 80 | 0d | October 10, 2022 8:00 AM | February 6, 2023 5:00 PM | 80 days | No | 10/10/22 | 2/6/23 | NA | 1
3209 | Data Conversion - Milestone 05 - Analysis and Mapping | January 2, 2023 8:00 AM | April 27, 2023 5:00 PM | 2238FS-20d | 2240SS+20d | As Soon As Possible | NA | 80 | 0d | January 2, 2023 8:00 AM | April 27, 2023 5:00 PM | 80 days | No | 1/2/23 | 4/27/23 | NA | 1
3210 | Data Conversion - Milestone 05 - Build and SIT | January 30, 2023 8:00 AM | May 19, 2023 5:00 PM | 2239SS+20d | 2334 | As Soon As Possible | NA | 80 | 0d | January 30, 2023 8:00 AM | May 19, 2023 5:00 PM | 80 days | No | 1/30/23 | 5/19/23 | NA | 1
3211 | Data Conversion - Milestone 06 | December 5, 2022 8:00 AM | August 11, 2023 5:00 PM |  |  | As Soon As Possible | NA | 173 | 0d | December 5, 2022 8:00 AM | August 11, 2023 5:00 PM | 173 days | No | 12/5/22 | 8/11/23 | NA | 1
3212 | Data Conversion - Milestone 06 - Pre-Analysis | December 5, 2022 8:00 AM | May 26, 2023 5:00 PM | 224 | 2243FS-40d | Start No Earlier Than | 12/5/22 | 120 | 0d | December 5, 2022 8:00 AM | May 26, 2023 5:00 PM | 120 days | No | 12/5/22 | 5/26/23 | NA | 1
3213 | Data Conversion - Milestone 06 - Analysis and Mapping | March 27, 2023 8:00 AM | July 19, 2023 5:00 PM | 2242FS-40d | 2244SS+20d | As Soon As Possible | NA | 80 | 0d | March 27, 2023 8:00 AM | July 19, 2023 5:00 PM | 80 days | No | 3/27/23 | 7/19/23 | NA | 1
3214 | Data Conversion - Milestone 06 - Build and SIT | April 24, 2023 8:00 AM | August 11, 2023 5:00 PM | 2243SS+20d | 2334 | As Soon As Possible | NA | 80 | 0d | April 24, 2023 8:00 AM | August 11, 2023 5:00 PM | 80 days | No | 4/24/23 | 8/11/23 | NA | 1
3215 | Data Conversion - Milestone 6.1 | July 15, 2024 8:00 AM | December 29, 2025 5:00 PM |  |  | As Soon As Possible | NA | 367 | 103d | July 15, 2024 8:00 AM | December 29, 2025 5:00 PM | 367 days | No | 7/15/24 | NA | NA | 0.83999999999999997
3216 | Data Conversion - Milestone 6.1 - Pre-Analysis | July 15, 2024 8:00 AM | October 28, 2024 5:00 PM | 593SS | 2247 | Finish No Earlier Than | 5/30/24 | 76 | 0d | July 15, 2024 8:00 AM | October 28, 2024 5:00 PM | 76 days | No | 7/15/24 | 10/28/24 | NA | 1
3217 | Data Conversion - Milestone 6.1 - Analysis and Mapping | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM | 599SS,597SS,598SS,2246 | 2248 | Finish No Earlier Than | 6/14/24 | 58 | 0d | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM | 58 days | No | 1/6/25 | 3/28/25 | NA | 1
3218 | Data Conversion - Milestone 6.1 - Build | April 2, 2025 8:00 AM | December 29, 2025 5:00 PM | 702SS,2247 | 2379 | Finish No Earlier Than | 7/12/24 | 188 | 103d | April 2, 2025 8:00 AM | December 29, 2025 5:00 PM | 188 days | No | 4/2/25 | NA | NA | 0.71999999999999997
3219 | Data Conversion - Milestone 07 (CARESV1-13737) | July 15, 2024 8:00 AM | December 29, 2025 5:00 PM |  |  | As Soon As Possible | NA | 367 | 103d | July 15, 2024 8:00 AM | December 29, 2025 5:00 PM | 367 days | No | 7/15/24 | NA | NA | 0.83999999999999997
3220 | Data Conversion - Milestone 07 - Pre-Analysis | July 15, 2024 8:00 AM | October 28, 2024 5:00 PM | 593SS | 2251 | As Soon As Possible | NA | 76 | 0d | July 15, 2024 8:00 AM | October 28, 2024 5:00 PM | 76 days | No | 7/15/24 | 10/28/24 | NA | 1
3221 | Data Conversion - Milestone 07 - Analysis and Mapping | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM | 599SS,597SS,598SS,2250 | 2252 | As Soon As Possible | NA | 58 | 0d | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM | 58 days | No | 1/6/25 | 3/28/25 | NA | 1
3222 | Data Conversion - Milestone 07 - Build | April 2, 2025 8:00 AM | December 29, 2025 5:00 PM | 702SS,2251 | 2379 | Finish No Earlier Than | 8/11/25 | 188 | 103d | April 2, 2025 8:00 AM | December 29, 2025 5:00 PM | 188 days | No | 4/2/25 | NA | NA | 0.71999999999999997
3223 | Data Conversion - Milestone 08 (CARESV1-13738) | April 7, 2023 8:00 AM | October 5, 2023 5:00 PM |  |  | As Soon As Possible | NA | 127 | 0d | April 7, 2023 8:00 AM | October 5, 2023 5:00 PM | 127 days | No | 4/7/23 | 10/5/23 | NA | 1
3224 | Data Conversion - Milestone 08 - Pre-Analysis | April 7, 2023 8:00 AM | July 14, 2023 5:00 PM | 267SS | 2255SS+40d,2327SS+4d,2399SS+15d | Finish No Earlier Than | 7/18/23 | 69 | 0d | April 7, 2023 8:00 AM | July 14, 2023 5:00 PM | 69 days | No | 4/7/23 | 7/14/23 | NA | 1
3225 | Data Conversion - Milestone 08 - Analysis and Mapping | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM | 2254SS+40d | 2256SS+20d | Finish No Earlier Than | 10/9/23 | 77 | 0d | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM | 77 days | No | 6/19/23 | 10/5/23 | NA | 1
3226 | Data Conversion - Milestone 08 - Build and SIT | July 19, 2023 8:00 AM | August 14, 2023 5:00 PM | 2255SS+20d | 2216FS+103d | Finish No Earlier Than | 12/8/23 | 19 | 0d | July 19, 2023 8:00 AM | August 14, 2023 5:00 PM | 19 days | No | 7/19/23 | 8/14/23 | NA | 1
3227 | Data Conversion - Milestone 09 (CARESV1-13739) | August 14, 2023 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 407 | 0d | August 14, 2023 8:00 AM | March 28, 2025 5:00 PM | 407 days | No | 8/14/23 | 3/28/25 | NA | 1
3228 | Data Conversion - Milestone 09 - Pre-Analysis | July 15, 2024 8:00 AM | October 28, 2024 5:00 PM | 593SS | 2259 | Finish No Earlier Than | 1/26/24 | 76 | 0d | July 15, 2024 8:00 AM | October 28, 2024 5:00 PM | 76 days | No | 7/15/24 | 10/28/24 | NA | 1
3229 | Data Conversion - Milestone 09 - Analysis and Mapping | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM | 599SS,597SS,598SS,2258 | 2260 | Finish No Earlier Than | 3/22/24 | 58 | 0d | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM | 58 days | No | 1/6/25 | 3/28/25 | NA | 1
3230 | Data Conversion - Milestone 09 - Build and SIT | August 14, 2023 8:00 AM | May 15, 2024 5:00 PM | 339SS,2259 | 2344 | Finish No Earlier Than | 4/22/24 | 189 | 0d | August 14, 2023 8:00 AM | May 15, 2024 5:00 PM | 189 days | No | 8/14/23 | 5/15/24 | NA | 1
3231 | Data Conversion - Milestone 10 (CARESV1-13740) | October 21, 2024 8:00 AM | December 29, 2025 1:58 PM |  |  | As Soon As Possible | NA | 296.62 | 103.38d | October 21, 2024 8:00 AM | December 29, 2025 5:00 PM | 297 days | No | 10/21/24 | NA | NA | 0.84999999999999998
3232 | Data Conversion - Milestone 10 - Pre-Analysis | October 21, 2024 8:00 AM | February 28, 2025 5:00 PM | 608SS | 2263 | As Soon As Possible | NA | 88 | 0d | October 21, 2024 8:00 AM | February 28, 2025 5:00 PM | 88 days | No | 10/21/24 | 2/28/25 | NA | 1
3233 | Data Conversion - Milestone 10 - Analysis and Mapping | April 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 614SS,613SS,612SS,2262 | 2264 | As Soon As Possible | NA | 43 | 0d | April 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 43 days | No | 4/1/25 | 5/30/25 | NA | 1
3234 | Data Conversion - Milestone 10 - Build and SIT | August 11, 2025 8:00 AM | December 29, 2025 1:58 PM | 380SS,2263 | 2379 | Start No Earlier Than | 2/6/25 | 52 | 103.38d | June 2, 2025 8:00 AM | December 29, 2025 5:00 PM | 146 days | No | 8/11/25 | NA | NA | 0.46000000000000002
3235 | Data Conversion - Milestone 10.1 | October 9, 2023 8:00 AM | July 14, 2025 5:00 PM |  |  | As Soon As Possible | NA | 441 | 0d | October 9, 2023 8:00 AM | July 14, 2025 5:00 PM | 441 days | No | 10/9/23 | 7/14/25 | NA | 1
3236 | Data Conversion - Milestone 10.1 - Pre-Analysis | October 9, 2023 8:00 AM | May 17, 2024 5:00 PM | 1447SS | 2267 | As Soon As Possible | NA | 152 | 0d | October 9, 2023 8:00 AM | May 17, 2024 5:00 PM | 152 days | No | 10/9/23 | 5/17/24 | NA | 1
3237 | Data Conversion - Milestone 10.1 - Analysis and Mapping | May 24, 2024 8:00 AM | April 11, 2025 5:00 PM | 1451SS,2266 | 2268FF | As Soon As Possible | NA | 221 | 0d | May 24, 2024 8:00 AM | April 11, 2025 5:00 PM | 221 days | No | 5/24/24 | 4/11/25 | NA | 1
3238 | Data Conversion - Milestone 10.1 - Build and SIT | January 6, 2025 8:00 AM | July 14, 2025 5:00 PM | 1455SS,2267FF | 2379 | As Soon As Possible | NA | 131 | 0d | January 6, 2025 8:00 AM | July 14, 2025 5:00 PM | 131 days | No | 1/6/25 | 7/14/25 | NA | 1
3239 | Data Conversion - Milestone 11 (CARESV1-13741) | October 21, 2024 8:00 AM | December 29, 2025 1:58 PM |  |  | As Soon As Possible | NA | 296.62 | 103.38d | October 21, 2024 8:00 AM | December 29, 2025 5:00 PM | 297 days | No | 10/21/24 | NA | NA | 0.83999999999999997
3240 | Data Conversion - Milestone 11 - Pre-Analysis | October 21, 2024 8:00 AM | February 28, 2025 5:00 PM | 608SS | 2271 | As Soon As Possible | NA | 88 | 0d | October 21, 2024 8:00 AM | February 28, 2025 5:00 PM | 88 days | No | 10/21/24 | 2/28/25 | NA | 1
3241 | Data Conversion - Milestone 11 - Analysis and Mapping | April 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 614SS,613SS,612SS,2270 | 2272 | As Soon As Possible | NA | 43 | 0d | April 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 43 days | No | 4/1/25 | 5/30/25 | NA | 1
3242 | Data Conversion - Milestone 11 - Build and SIT | June 2, 2025 8:00 AM | December 29, 2025 1:58 PM | 715SS,2271 | 2379 | Finish No Earlier Than | 8/11/25 | 101 | 103.38d | June 2, 2025 8:00 AM | December 29, 2025 5:00 PM | 146 days | No | 6/2/25 | NA | NA | 0.64000000000000001
3243 | Data Conversion - Milestone 13 (CARESV1-13743) | October 21, 2024 8:00 AM | December 29, 2025 1:58 PM |  |  | As Soon As Possible | NA | 296.62 | 103.38d | October 21, 2024 8:00 AM | December 29, 2025 5:00 PM | 297 days | No | 10/21/24 | NA | NA | 0.83999999999999997
3244 | Data Conversion - Milestone 13 - Pre-Analysis | October 21, 2024 8:00 AM | February 28, 2025 5:00 PM | 608SS | 2275 | As Soon As Possible | NA | 88 | 0d | October 21, 2024 8:00 AM | February 28, 2025 5:00 PM | 88 days | No | 10/21/24 | 2/28/25 | NA | 1
3245 | Data Conversion - Milestone 13 - Analysis and Mapping | April 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 614SS,613SS,612SS,2274 | 2276 | As Soon As Possible | NA | 43 | 0d | April 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 43 days | No | 4/1/25 | 5/30/25 | NA | 1
3246 | Data Conversion - Milestone 13 - Build and SIT | June 2, 2025 8:00 AM | December 29, 2025 1:58 PM | 709SS,2275 | 2379 | Finish No Earlier Than | 9/8/25 | 101 | 103.38d | June 2, 2025 8:00 AM | December 29, 2025 5:00 PM | 146 days | No | 6/2/25 | NA | NA | 0.64000000000000001
3247 | Data Conversion - Milestone 14 (CARESV1-13744) | May 22, 2023 8:00 AM | August 8, 2024 5:00 PM |  |  | As Soon As Possible | NA | 306 | 0d | May 22, 2023 8:00 AM | August 8, 2024 5:00 PM | 306 days | No | 5/22/23 | 8/8/24 | NA | 1
3248 | Data Conversion - Milestone 14 - Pre-Analysis | May 22, 2023 8:00 AM | September 8, 2023 5:00 PM | 403SS | 2279 | As Soon As Possible | NA | 77 | 0d | May 22, 2023 8:00 AM | September 8, 2023 5:00 PM | 77 days | No | 5/22/23 | 9/8/23 | NA | 1
3249 | Data Conversion - Milestone 14 - Analysis and Mapping | October 9, 2023 8:00 AM | February 23, 2024 5:00 PM | 405SS,2278 | 2280 | As Soon As Possible | NA | 93 | 0d | October 9, 2023 8:00 AM | February 23, 2024 5:00 PM | 93 days | No | 10/9/23 | 2/23/24 | NA | 1
3250 | Data Conversion - Milestone 14 - Build and SIT | November 6, 2023 8:00 AM | August 8, 2024 5:00 PM | 407SS,2279 | 2379 | As Soon As Possible | NA | 189 | 0d | November 6, 2023 8:00 AM | August 8, 2024 5:00 PM | 189 days | No | 11/6/23 | 8/8/24 | NA | 1
3251 | Data Conversion - Milestone 15 (CARESV1-13745) | August 15, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 155 | 0d | August 15, 2024 8:00 AM | March 28, 2025 5:00 PM | 155 days | No | 8/15/24 | 3/28/25 | NA | 1
3252 | Data Conversion - Milestone 15 - Pre-Analysis | August 15, 2024 8:00 AM | January 3, 2025 5:00 PM | 798SS | 2283 | As Soon As Possible | NA | 97 | 0d | August 15, 2024 8:00 AM | January 3, 2025 5:00 PM | 97 days | No | 8/15/24 | 1/3/25 | NA | 1
3253 | Data Conversion - Milestone 15 - Analysis and Mapping | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 804SS,803SS,802SS,2282 | 2284FS-118d | As Soon As Possible | NA | 44 | 0d | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 days | No | 1/27/25 | 3/28/25 | NA | 1
3254 | Data Conversion - Milestone 15 - Build and SIT | October 7, 2024 8:00 AM | February 26, 2025 5:00 PM | 433SS,2283FS-118d | 2379 | As Soon As Possible | NA | 96 | 0d | October 7, 2024 8:00 AM | February 26, 2025 5:00 PM | 96 days | No | 10/7/24 | 2/26/25 | NA | 1
3255 | Data Conversion - Milestone 16 (CARESV1-13746) | August 15, 2024 8:00 AM | December 29, 2025 3:00 PM |  |  | As Soon As Possible | NA | 343.75 | 103.25d | August 15, 2024 8:00 AM | December 29, 2025 5:00 PM | 344 days | No | 8/15/24 | NA | NA | 0.84999999999999998
3256 | Data Conversion - Milestone 16 - Pre-Analysis | August 15, 2024 8:00 AM | January 3, 2025 5:00 PM | 798SS | 2287 | As Soon As Possible | NA | 97 | 0d | August 15, 2024 8:00 AM | January 3, 2025 5:00 PM | 97 days | No | 8/15/24 | 1/3/25 | NA | 1
3257 | Data Conversion - Milestone 16 - Analysis and Mapping | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 804SS,803SS,802SS,2286 | 2288 | As Soon As Possible | NA | 44 | 0d | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 days | No | 1/27/25 | 3/28/25 | NA | 1
3258 | Data Conversion - Milestone 16 - Build and SIT | April 1, 2025 8:00 AM | December 29, 2025 3:00 PM | 867SS,2287 | 2379 | Finish No Earlier Than | 4/21/25 | 173 | 103.25d | April 1, 2025 8:00 AM | December 29, 2025 5:00 PM | 189 days | No | 4/1/25 | NA | NA | 0.71999999999999997
3259 | Data Conversion - Milestone 17 (CARESV1-13747) | October 15, 2024 8:00 AM | December 29, 2025 3:00 PM |  |  | As Soon As Possible | NA | 300.75 | 103.25d | October 15, 2024 8:00 AM | December 29, 2025 5:00 PM | 301 days | No | 10/15/24 | NA | NA | 0.84999999999999998
3260 | Data Conversion - Milestone 17 - Pre-Analysis | October 15, 2024 8:00 AM | March 7, 2025 5:00 PM | 798SS | 2291FS-29d | Finish No Earlier Than | 3/7/25 | 97 | 0d | October 15, 2024 8:00 AM | March 7, 2025 5:00 PM | 97 days | No | 10/15/24 | 3/7/25 | NA | 1
3261 | Data Conversion - Milestone 17 - Analysis and Mapping | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 804SS,803SS,802SS,2290FS-29d | 2292FS-29d | Start No Earlier Than | 1/2/25 | 44 | 0d | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 days | No | 1/27/25 | 3/28/25 | NA | 1
3262 | Data Conversion - Milestone 17 - Build and SIT | April 1, 2025 8:00 AM | December 29, 2025 3:00 PM | 871SS,2291FS-29d | 2379 | Finish No Earlier Than | 4/21/25 | 173 | 103.25d | April 1, 2025 8:00 AM | December 29, 2025 5:00 PM | 189 days | No | 4/1/25 | NA | NA | 0.71999999999999997
3263 | Data Conversion - Milestone 18 (CARESV1-13748) | October 15, 2024 8:00 AM | January 22, 2026 3:00 PM |  |  | As Soon As Possible | NA | 316.75 | 87.25d | October 15, 2024 8:00 AM | December 30, 2025 5:00 PM | 302 days | No | 10/15/24 | NA | NA | 0.81000000000000005
3264 | Data Conversion - Milestone 18 - Pre-Analysis | October 15, 2024 8:00 AM | March 7, 2025 5:00 PM | 798SS | 2295FS-30d | Finish No Earlier Than | 3/7/25 | 97 | 0d | October 15, 2024 8:00 AM | March 7, 2025 5:00 PM | 97 days | No | 10/15/24 | 3/7/25 | NA | 1
3265 | Data Conversion - Milestone 18 - Analysis and Mapping | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 804SS,803SS,802SS,2294FS-30d | 2296FS-29d | As Soon As Possible | NA | 44 | 0d | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 days | No | 1/27/25 | 3/28/25 | NA | 1
3266 | Data Conversion - Milestone 18 - Build and SIT | April 2, 2025 8:00 AM | January 22, 2026 3:00 PM | 876SS,2295FS-29d | 2379 | Finish No Earlier Than | 5/16/25 | 189 | 87.25d | April 2, 2025 8:00 AM | December 30, 2025 5:00 PM | 189 days | No | 4/2/25 | NA | NA | 0.66000000000000003
3267 | Data Conversion - Milestone 19 (CARESV1-13749) | January 30, 2023 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 523 | 0d | January 30, 2023 8:00 AM | February 28, 2025 5:00 PM | 523 days | No | 1/30/23 | 2/28/25 | NA | 1
3268 | Data Conversion - Milestone 19 - Pre-Analysis | January 30, 2023 8:00 AM | February 2, 2024 5:00 PM | 456SS | 2299 | As Soon As Possible | NA | 254 | 0d | January 30, 2023 8:00 AM | February 2, 2024 5:00 PM | 254 days | No | 1/30/23 | 2/2/24 | NA | 1
3269 | Data Conversion - Milestone 19 - Analysis and Mapping | July 17, 2023 8:00 AM | February 23, 2024 5:00 PM | 459SS,2298 | 2300 | As Soon As Possible | NA | 152 | 0d | July 17, 2023 8:00 AM | February 23, 2024 5:00 PM | 152 days | No | 7/17/23 | 2/23/24 | NA | 1
3270 | Data Conversion - Milestone 19 - Build and SIT | October 7, 2024 8:00 AM | February 28, 2025 5:00 PM | 462SS,2299 | 2379 | As Soon As Possible | NA | 98 | 0d | October 7, 2024 8:00 AM | February 28, 2025 5:00 PM | 98 days | No | 10/7/24 | 2/28/25 | NA | 1
3271 | Data Conversion - Milestone 20 (CARESV1-13750) | October 3, 2023 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 352 | 0d | October 3, 2023 8:00 AM | February 28, 2025 5:00 PM | 352 days | No | 10/3/23 | 2/28/25 | NA | 1
3272 | Data Conversion - Milestone 20 - Pre-Analysis | October 3, 2023 8:00 AM | April 26, 2024 5:00 PM | 485SS | 1992 | As Soon As Possible | NA | 141 | 0d | October 3, 2023 8:00 AM | April 26, 2024 5:00 PM | 141 days | No | 10/3/23 | 4/26/24 | NA | 1
3273 | Data Conversion - Milestone 20 - Analysis and Mapping | February 5, 2024 8:00 AM | May 21, 2024 5:00 PM | 489SS | 2304 | As Soon As Possible | NA | 75 | 0d | February 5, 2024 8:00 AM | May 21, 2024 5:00 PM | 75 days | No | 2/5/24 | 5/21/24 | NA | 1
3274 | Data Conversion - Milestone 20 - Build and SIT | October 7, 2024 8:00 AM | February 28, 2025 5:00 PM | 493SS,2303 | 2379 | As Soon As Possible | NA | 98 | 0d | October 7, 2024 8:00 AM | February 28, 2025 5:00 PM | 98 days | No | 10/7/24 | 2/28/25 | NA | 1
3275 | Data Conversion - Milestone 21 (CARESV1-13751) | August 15, 2024 8:00 AM | December 29, 2025 3:00 PM |  |  | As Soon As Possible | NA | 343.75 | 103.25d | August 15, 2024 8:00 AM | December 29, 2025 5:00 PM | 344 days | No | 8/15/24 | NA | NA | 0.84999999999999998
3276 | Data Conversion - Milestone 21 - Pre-Analysis | August 15, 2024 8:00 AM | January 3, 2025 5:00 PM | 1194SS | 2307 | Finish No Earlier Than | 4/19/24 | 97 | 0d | August 15, 2024 8:00 AM | January 3, 2025 5:00 PM | 97 days | No | 8/15/24 | 1/3/25 | NA | 1
3277 | Data Conversion - Milestone 21 - Analysis and Mapping | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 1200SS,1199SS,1198SS,2306 | 2308 | Finish No Earlier Than | 6/17/24 | 44 | 0d | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 days | No | 1/27/25 | 3/28/25 | NA | 1
3278 | Data Conversion - Milestone 21 - Build and SIT | April 1, 2025 8:00 AM | December 29, 2025 3:00 PM | 867SS,2307 | 2379 | Finish No Earlier Than | 7/17/24 | 173 | 103.25d | April 1, 2025 8:00 AM | December 29, 2025 5:00 PM | 189 days | No | 4/1/25 | NA | NA | 0.71999999999999997
3279 | Data Conversion - Milestone 23 (CARESV1-13754) | December 4, 2024 8:00 AM | April 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 80 | 0d | December 4, 2024 8:00 AM | December 29, 2025 5:00 PM | 268 days | No | 12/4/24 | 4/1/25 | NA | 1
3280 | Data Conversion - Milestone 23 - Pre-Analysis | December 4, 2024 8:00 AM | April 1, 2025 5:00 PM | 1092SS |  | As Soon As Possible | NA | 80 | 0d | December 4, 2024 8:00 AM | April 1, 2025 5:00 PM | 80 days | No | 12/4/24 | 4/1/25 | NA | 1
3283 | Data Conversion - Milestone 24 (CARESV1-13755) | December 4, 2024 8:00 AM | April 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 80 | 0d | December 4, 2024 8:00 AM | December 29, 2025 5:00 PM | 268 days | No | 12/4/24 | 4/1/25 | NA | 1
3284 | Data Conversion - Milestone 24 - Pre-Analysis | December 4, 2024 8:00 AM | April 1, 2025 5:00 PM | 1092SS |  | As Soon As Possible | NA | 80 | 0d | December 4, 2024 8:00 AM | April 1, 2025 5:00 PM | 80 days | No | 12/4/24 | 4/1/25 | NA | 1
3287 | Data Conversion - Milestone 26 (CARESV1-13757) | September 30, 2024 8:00 AM | May 8, 2026 3:24 PM |  |  | As Soon As Possible | NA | 401.8 | 13.2d | September 30, 2024 8:00 AM | December 29, 2025 5:00 PM | 312 days | No | 9/30/24 | NA | NA | 0.75
3288 | Data Conversion - Milestone 26 - Pre-Analysis | September 30, 2024 8:00 AM | January 3, 2025 5:00 PM | 934SS | 2315 | As Soon As Possible | NA | 65 | 0d | September 30, 2024 8:00 AM | January 3, 2025 5:00 PM | 65 days | No | 9/30/24 | 1/3/25 | NA | 1
3289 | Data Conversion - Milestone 26 - Analysis and Mapping | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 940SS,939SS,938SS,2314 | 2316 | As Soon As Possible | NA | 44 | 0d | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 days | No | 1/27/25 | 3/28/25 | NA | 1
3290 | Data Conversion - Milestone 26 - Build and SIT | April 1, 2025 8:00 AM | May 8, 2026 3:24 PM | 1011SS,2315 | 2379 | As Soon As Possible | NA | 105 | 13.2d | April 1, 2025 8:00 AM | December 29, 2025 5:00 PM | 189 days | No | 4/1/25 | NA | NA | 0.48999999999999999
3291 | Data Conversion - Milestone 27 (CARESV1-13758) | September 30, 2024 8:00 AM | May 8, 2026 3:24 PM |  |  | As Soon As Possible | NA | 401.8 | 13.2d | September 30, 2024 8:00 AM | December 29, 2025 5:00 PM | 312 days | No | 9/30/24 | NA | NA | 0.75
3292 | Data Conversion - Milestone 27 - Pre-Analysis | September 30, 2024 8:00 AM | January 3, 2025 5:00 PM | 934SS | 2319 | As Soon As Possible | NA | 65 | 0d | September 30, 2024 8:00 AM | January 3, 2025 5:00 PM | 65 days | No | 9/30/24 | 1/3/25 | NA | 1
3293 | Data Conversion - Milestone 27 - Analysis and Mapping | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 940SS,939SS,938SS,2318 | 2320 | As Soon As Possible | NA | 44 | 0d | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 days | No | 1/27/25 | 3/28/25 | NA | 1
3294 | Data Conversion - Milestone 27 - Build and SIT | April 1, 2025 8:00 AM | May 8, 2026 3:24 PM | 1019SS,2319 | 2379 | As Soon As Possible | NA | 105 | 13.2d | April 1, 2025 8:00 AM | December 29, 2025 5:00 PM | 189 days | No | 4/1/25 | NA | NA | 0.48999999999999999
3295 | Data Conversion - Milestone 28 (CARESV1-13759) | September 30, 2024 8:00 AM | May 8, 2026 3:24 PM |  |  | As Soon As Possible | NA | 401.8 | 13.2d | September 30, 2024 8:00 AM | December 29, 2025 5:00 PM | 312 days | No | 9/30/24 | NA | NA | 0.75
3296 | Data Conversion - Milestone 28 - Pre-Analysis | September 30, 2024 8:00 AM | January 3, 2025 5:00 PM | 934SS | 2323 | As Soon As Possible | NA | 65 | 0d | September 30, 2024 8:00 AM | January 3, 2025 5:00 PM | 65 days | No | 9/30/24 | 1/3/25 | NA | 1
3297 | Data Conversion - Milestone 28 - Analysis and Mapping | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 940SS,939SS,938SS,2322 | 2324 | As Soon As Possible | NA | 44 | 0d | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 days | No | 1/27/25 | 3/28/25 | NA | 1
3298 | Data Conversion - Milestone 28 - Build and SIT | April 1, 2025 8:00 AM | May 8, 2026 3:24 PM | 1019SS,2323 | 2379 | As Soon As Possible | NA | 105 | 13.2d | April 1, 2025 8:00 AM | December 29, 2025 5:00 PM | 189 days | No | 4/1/25 | NA | NA | 0.48999999999999999
3311 | Conversion Cycles | April 3, 2023 8:00 AM | December 9, 2026 3:24 PM |  |  | As Soon As Possible | NA | 925.8 | 210.2d | April 3, 2023 8:00 AM | August 27, 2026 5:00 PM | 856 days | No | 4/3/23 | NA | NA | 0.67000000000000004
3312 | Cycle 1 (Intake I) | April 3, 2023 8:00 AM | July 14, 2023 5:00 PM |  |  | As Soon As Possible | NA | 73 | 0d | April 3, 2023 8:00 AM | July 14, 2023 5:00 PM | 73 days | No | 4/3/23 | 7/14/23 | NA | 1
3313 | Conversion Cycle 1 - ETL | April 3, 2023 8:00 AM | April 28, 2023 5:00 PM | 2254SS+4d | 2328SS | Start No Earlier Than | 4/3/23 | 20 | 0d | April 3, 2023 8:00 AM | April 28, 2023 5:00 PM | 20 days | No | 4/3/23 | 4/28/23 | NA | 1
3314 | Conversion Cycle 1 - SIT | April 3, 2023 8:00 AM | April 28, 2023 5:00 PM | 2327SS | 2329 | As Soon As Possible | NA | 20 | 0d | April 3, 2023 8:00 AM | April 28, 2023 5:00 PM | 20 days | No | 4/3/23 | 4/28/23 | NA | 1
3315 | Conversion Cycle 1 - QA | May 1, 2023 8:00 AM | May 26, 2023 5:00 PM | 2328 | 2330 | As Soon As Possible | NA | 20 | 0d | May 1, 2023 8:00 AM | May 26, 2023 5:00 PM | 20 days | No | 5/1/23 | 5/26/23 | NA | 1
3316 | Conversion Cycle 1 - County Validation | May 29, 2023 8:00 AM | June 30, 2023 5:00 PM | 2329 | 2331 | As Soon As Possible | NA | 25 | 0d | May 29, 2023 8:00 AM | June 30, 2023 5:00 PM | 25 days | No | 5/29/23 | 6/30/23 | NA | 1
3317 | Conversion Cycle 1 - Review & Closure | July 3, 2023 8:00 AM | July 14, 2023 5:00 PM | 2330 | 2333FS+42d | As Soon As Possible | NA | 10 | 0d | July 3, 2023 8:00 AM | July 14, 2023 5:00 PM | 10 days | No | 7/3/23 | 7/14/23 | NA | 1
3318 | Cycle 2 (Intake II & Case Management Part I) | September 11, 2023 8:00 AM | February 13, 2024 5:00 PM |  |  | As Soon As Possible | NA | 106 | 0d | September 11, 2023 8:00 AM | February 13, 2024 5:00 PM | 106 days | No | 9/11/23 | 2/13/24 | NA | 1
3319 | Conversion Cycle 2 - ETL | September 11, 2023 8:00 AM | October 6, 2023 5:00 PM | 2331FS+42d,2182,2189,2195 | 2334 | Start No Earlier Than | 9/11/23 | 20 | 0d | September 11, 2023 8:00 AM | October 6, 2023 5:00 PM | 20 days | No | 9/11/23 | 10/6/23 | NA | 1
3320 | Conversion Cycle 2 - SIT | October 9, 2023 8:00 AM | November 3, 2023 5:00 PM | 2333,2232,2236,2240,2244 | 2335 | As Soon As Possible | NA | 20 | 0d | October 9, 2023 8:00 AM | November 3, 2023 5:00 PM | 20 days | No | 10/9/23 | 11/3/23 | NA | 1
3321 | Conversion Cycle 2 - QA | November 6, 2023 8:00 AM | December 6, 2023 5:00 PM | 2334 | 2336FS+32d | As Soon As Possible | NA | 20 | 0d | November 6, 2023 8:00 AM | December 6, 2023 5:00 PM | 20 days | No | 11/6/23 | 12/6/23 | NA | 1
3322 | Conversion Cycle 2 - County Validation | January 17, 2024 8:00 AM | January 30, 2024 5:00 PM | 2335FS+32d | 2337 | As Soon As Possible | NA | 10 | 0d | January 17, 2024 8:00 AM | January 30, 2024 5:00 PM | 10 days | No | 1/17/24 | 1/30/24 | NA | 1
3323 | Conversion Cycle 2 - Review & Closure | January 31, 2024 8:00 AM | February 13, 2024 5:00 PM | 2336 | 2339 | As Soon As Possible | NA | 10 | 0d | January 31, 2024 8:00 AM | February 13, 2024 5:00 PM | 10 days | No | 1/31/24 | 2/13/24 | NA | 1
3324 | Cycle 3 (RM, Placement) | April 22, 2024 8:00 AM | August 16, 2024 5:00 PM |  |  | As Soon As Possible | NA | 83 | 0d | April 22, 2024 8:00 AM | August 16, 2024 5:00 PM | 83 days | No | 4/22/24 | 8/16/24 | NA | 1
3325 | Conversion Cycle 3 - ETL | April 22, 2024 8:00 AM | June 3, 2024 5:00 PM | 2337 | 2340 | Finish No Earlier Than | 6/3/24 | 30 | 0d | April 22, 2024 8:00 AM | June 3, 2024 5:00 PM | 30 days | No | 4/22/24 | 6/3/24 | NA | 1
5602 | Conversion Cycle 3 - Link Documents | May 27, 2024 8:00 AM | July 12, 2024 5:00 PM | 2339 | 2341 | As Soon As Possible | NA | 33 | 0d | May 27, 2024 8:00 AM | July 12, 2024 5:00 PM | 33 days | No | 5/27/24 | 7/12/24 | NA | 1
5603 | Conversion Cycle 3 - Solr Load | May 27, 2024 8:00 AM | June 7, 2024 5:00 PM | 2340 | 2342 | As Soon As Possible | NA | 9 | 0d | May 27, 2024 8:00 AM | June 7, 2024 5:00 PM | 9 days | No | 5/27/24 | 6/7/24 | NA | 1
5604 | Conversion Cycle 3 - Snowflake Load | May 20, 2024 8:00 AM | July 12, 2024 5:00 PM | 2341 | 2343FS-14d | As Soon As Possible | NA | 38 | 0d | May 20, 2024 8:00 AM | July 12, 2024 5:00 PM | 38 days | No | 5/20/24 | 7/12/24 | NA | 1
5605 | Conversion Cycle 3 - Micro Conversion Execution | June 24, 2024 8:00 AM | July 26, 2024 5:00 PM | 2342FS-14d,2183,2190,2196FS-44d | 2344FS-43d | As Soon As Possible | NA | 24 | 0d | June 24, 2024 8:00 AM | July 26, 2024 5:00 PM | 24 days | No | 6/24/24 | 7/26/24 | NA | 1
3326 | Conversion Cycle 3 - SIT | May 28, 2024 8:00 AM | June 21, 2024 5:00 PM | 2343FS-43d,2224,2228,2260 | 2345 | As Soon As Possible | NA | 19 | 0d | May 28, 2024 8:00 AM | June 21, 2024 5:00 PM | 19 days | No | 5/28/24 | 6/21/24 | NA | 1
3327 | Conversion Cycle 3 - QA | June 24, 2024 8:00 AM | July 22, 2024 5:00 PM | 2344 | 2346FS-10d | As Soon As Possible | NA | 20 | 0d | June 24, 2024 8:00 AM | July 22, 2024 5:00 PM | 20 days | No | 6/24/24 | 7/22/24 | NA | 1
3328 | Conversion Cycle 3 - County Validation | July 9, 2024 8:00 AM | August 2, 2024 5:00 PM | 2345FS-10d | 2347 | As Soon As Possible | NA | 19 | 0d | July 9, 2024 8:00 AM | August 2, 2024 5:00 PM | 19 days | No | 7/9/24 | 8/2/24 | NA | 1
3329 | Conversion Cycle 3 - Review & Closure | August 5, 2024 8:00 AM | August 16, 2024 5:00 PM | 2346 | 2349 | As Soon As Possible | NA | 10 | 0d | August 5, 2024 8:00 AM | August 16, 2024 5:00 PM | 10 days | No | 8/5/24 | 8/16/24 | NA | 1
5606 | Cycle 4 (RM, Courts I) | September 23, 2024 8:00 AM | February 14, 2025 5:00 PM |  |  | As Soon As Possible | NA | 99 | 0d | September 23, 2024 8:00 AM | February 14, 2025 5:00 PM | 99 days | No | 9/23/24 | 2/14/25 | NA | 1
5607 | Conversion Cycle 4 - ETL | September 23, 2024 8:00 AM | November 1, 2024 5:00 PM | 2347 | 2350 | Start No Earlier Than | 9/23/24 | 30 | 0d | September 23, 2024 8:00 AM | November 1, 2024 5:00 PM | 30 days | No | 9/23/24 | 11/1/24 | NA | 1
5608 | Conversion Cycle 4 - Link Documents | November 4, 2024 8:00 AM | November 25, 2024 5:00 PM | 2349 | 2351FS-20d | As Soon As Possible | NA | 15 | 0d | November 4, 2024 8:00 AM | November 25, 2024 5:00 PM | 15 days | No | 11/4/24 | 11/25/24 | NA | 1
5609 | Conversion Cycle 4 - Solr Load | October 28, 2024 8:00 AM | November 8, 2024 5:00 PM | 2350FS-20d | 2352FS-15d | As Soon As Possible | NA | 10 | 0d | October 28, 2024 8:00 AM | November 8, 2024 5:00 PM | 10 days | No | 10/28/24 | 11/8/24 | NA | 1
5610 | Conversion Cycle 4 - Snowflake Load | October 21, 2024 8:00 AM | November 8, 2024 5:00 PM | 2351FS-15d | 2353FS+4d | As Soon As Possible | NA | 15 | 0d | October 21, 2024 8:00 AM | November 8, 2024 5:00 PM | 15 days | No | 10/21/24 | 11/8/24 | NA | 1
5611 | Conversion Cycle 4 - Micro Conversion Execution | November 18, 2024 8:00 AM | January 24, 2025 5:00 PM | 2352FS+4d,2184,2191,2197 | 2354FS-54d | As Soon As Possible | NA | 45 | 0d | November 18, 2024 8:00 AM | January 24, 2025 5:00 PM | 45 days | No | 11/18/24 | 1/24/25 | NA | 1
5612 | Conversion Cycle 4 - SIT | November 4, 2024 8:00 AM | November 27, 2024 5:00 PM | 2353FS-54d | 2355 | As Soon As Possible | NA | 17 | 0d | November 4, 2024 8:00 AM | November 27, 2024 5:00 PM | 17 days | No | 11/4/24 | 11/27/24 | NA | 1
5613 | Conversion Cycle 4 - QA | December 2, 2024 8:00 AM | January 3, 2025 5:00 PM | 2354 | 2356 | As Soon As Possible | NA | 23 | 0d | December 2, 2024 8:00 AM | January 3, 2025 5:00 PM | 23 days | No | 12/2/24 | 1/3/25 | NA | 1
5614 | Conversion Cycle 4 - County Validation | January 6, 2025 8:00 AM | January 31, 2025 5:00 PM | 2355 | 2357 | As Soon As Possible | NA | 19 | 0d | January 6, 2025 8:00 AM | January 31, 2025 5:00 PM | 19 days | No | 1/6/25 | 1/31/25 | NA | 1
5615 | Conversion Cycle 4 - Review & Closure | February 3, 2025 8:00 AM | February 14, 2025 5:00 PM | 2356 | 2359 | As Soon As Possible | NA | 10 | 0d | February 3, 2025 8:00 AM | February 14, 2025 5:00 PM | 10 days | No | 2/3/25 | 2/14/25 | NA | 1
5620 | Cycle 5 (Court II, Case Management II) | March 24, 2025 8:00 AM | September 12, 2025 9:07 AM |  |  | As Soon As Possible | NA | 120.14 | 0d | March 24, 2025 8:00 AM | August 8, 2025 5:00 PM | 97 days | No | 3/24/25 | 9/12/25 | NA | 1
5621 | Conversion Cycle 5 - ETL | March 24, 2025 8:00 AM | May 2, 2025 5:00 PM | 2357 | 2360 | Start No Earlier Than | 3/24/25 | 29 | 0d | March 24, 2025 8:00 AM | May 2, 2025 5:00 PM | 29 days | No | 3/24/25 | 5/2/25 | NA | 1
5622 | Conversion Cycle 5 - Link Documents | May 5, 2025 8:00 AM | May 23, 2025 5:00 PM | 2359 | 2361FS-50d | Start No Earlier Than | 5/5/25 | 15 | 0d | May 5, 2025 8:00 AM | May 23, 2025 5:00 PM | 15 days | No | 5/5/25 | 5/23/25 | NA | 1
5623 | Conversion Cycle 5 - Solr Load | April 21, 2025 8:00 AM | May 2, 2025 5:00 PM | 2360FS-50d | 2362FS-10d | Start No Earlier Than | 4/21/25 | 10 | 0d | April 21, 2025 8:00 AM | May 2, 2025 5:00 PM | 10 days | No | 4/21/25 | 5/2/25 | NA | 1
5624 | Conversion Cycle 5 - Snowflake Load | April 21, 2025 8:00 AM | May 9, 2025 5:00 PM | 2361FS-10d | 2363 | Start No Earlier Than | 4/21/25 | 15 | 0d | April 21, 2025 8:00 AM | May 9, 2025 5:00 PM | 15 days | No | 4/21/25 | 5/9/25 | NA | 1
5625 | Conversion Cycle 5 - Micro Conversion Execution | July 10, 2025 9:07 AM | September 12, 2025 9:07 AM | 2185,2192,2198,2362 | 2364FS-55d | Start No Earlier Than | 5/19/25 | 45 | 0d | May 19, 2025 8:00 AM | July 22, 2025 5:00 PM | 45 days | No | 7/10/25 | 9/12/25 | NA | 1
5626 | Conversion Cycle 5 - SIT | June 25, 2025 9:07 AM | July 9, 2025 9:07 AM | 2363FS-55d | 2365 | Start No Earlier Than | 5/5/25 | 9 | 0d | May 5, 2025 8:00 AM | May 30, 2025 5:00 PM | 19 days | No | 6/25/25 | 7/9/25 | NA | 1
5627 | Conversion Cycle 5 - QA | July 9, 2025 9:07 AM | July 22, 2025 9:07 AM | 2364 | 2366 | Start No Earlier Than | 6/2/25 | 9 | 0d | June 2, 2025 8:00 AM | June 27, 2025 5:00 PM | 20 days | No | 7/9/25 | 7/22/25 | NA | 1
5628 | Conversion Cycle 5 - County Validation | July 22, 2025 9:07 AM | August 5, 2025 9:07 AM | 2365 | 2367 | Start No Earlier Than | 6/30/25 | 10 | 0d | June 30, 2025 8:00 AM | July 25, 2025 5:00 PM | 19 days | No | 7/22/25 | 8/5/25 | NA | 1
5629 | Conversion Cycle 5 - Review & Closure | August 5, 2025 9:07 AM | August 19, 2025 9:07 AM | 2366 | 2369 | Start No Earlier Than | 7/28/25 | 10 | 0d | July 28, 2025 8:00 AM | August 8, 2025 5:00 PM | 10 days | No | 8/5/25 | 8/19/25 | NA | 1
5630 | Cycle 6 ( Eligibility, Financial, RFA) | September 8, 2025 8:00 AM | January 9, 2026 5:00 PM |  |  | As Soon As Possible | NA | 86 | 439d | September 8, 2025 8:00 AM | January 9, 2026 5:00 PM | 86 days | No | 9/8/25 | NA | NA | 0.14000000000000001
5631 | Conversion Cycle 6 - ETL | September 8, 2025 8:00 AM | October 17, 2025 5:00 PM | 2367 | 2370 | Start No Earlier Than | 9/8/25 | 30 | 439d | September 8, 2025 8:00 AM | October 17, 2025 5:00 PM | 30 days | No | 9/8/25 | NA | NA | 0.82999999999999996
5632 | Conversion Cycle 6 - Link Documents | October 20, 2025 8:00 AM | November 7, 2025 5:00 PM | 2369 | 2371FS-25d | Start No Earlier Than | 10/20/25 | 15 | 439d | October 20, 2025 8:00 AM | November 7, 2025 5:00 PM | 15 days | No | NA | NA | NA | 0
5633 | Conversion Cycle 6 - Solr Load | October 6, 2025 8:00 AM | October 17, 2025 5:00 PM | 2370FS-25d | 2372FS-10d | Start No Earlier Than | 10/6/25 | 10 | 439d | October 6, 2025 8:00 AM | October 17, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
5634 | Conversion Cycle 6 - Snowflake Load | October 6, 2025 8:00 AM | October 24, 2025 5:00 PM | 2371FS-10d | 2373FS-5d | Start No Earlier Than | 10/6/25 | 15 | 439d | October 6, 2025 8:00 AM | October 24, 2025 5:00 PM | 15 days | No | NA | NA | NA | 0
5635 | Conversion Cycle 6 - Micro Conversion Execution | October 20, 2025 8:00 AM | December 23, 2025 5:00 PM | 2186FS-5d,2193FS-5d,2199FS-5d,2212FS-5d,2214FS-5d,2372FS-5d | 2374FS-55d | Start No Earlier Than | 10/20/25 | 45 | 439d | October 20, 2025 8:00 AM | December 23, 2025 5:00 PM | 45 days | No | NA | NA | NA | 0
5636 | Conversion Cycle 6 - SIT | October 6, 2025 8:00 AM | October 31, 2025 5:00 PM | 2373FS-55d | 2375 | Start No Earlier Than | 10/6/25 | 20 | 439d | October 6, 2025 8:00 AM | October 31, 2025 5:00 PM | 20 days | No | NA | NA | NA | 0
5637 | Conversion Cycle 6 - QA | November 3, 2025 8:00 AM | December 2, 2025 5:00 PM | 2374 | 2376FS-2d | Start No Earlier Than | 10/20/25 | 20 | 439d | November 3, 2025 8:00 AM | December 2, 2025 5:00 PM | 20 days | No | NA | NA | NA | 0
5638 | Conversion Cycle 6 - County Validation | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 2375FS-2d | 2377 | Start No Earlier Than | 12/1/25 | 19 | 439d | December 1, 2025 8:00 AM | December 26, 2025 5:00 PM | 19 days | No | NA | NA | NA | 0
5639 | Conversion Cycle 6 - Review & Closure | December 29, 2025 8:00 AM | January 9, 2026 5:00 PM | 2376 |  | Start No Earlier Than | 12/29/25 | 9 | 439d | December 29, 2025 8:00 AM | January 9, 2026 5:00 PM | 9 days | No | NA | NA | NA | 0
5640 | Full Mock Cycle 1 | May 8, 2026 3:24 PM | June 29, 2026 3:24 PM |  |  | As Soon As Possible | NA | 35 | 13.2d | January 12, 2026 8:00 AM | March 3, 2026 5:00 PM | 35 days | No | NA | NA | NA | 0
5641 | Conversion Full Mock Cycle 1 - ETL & SIT | May 8, 2026 3:24 PM | June 8, 2026 3:24 PM | 2264,2268,2272,2276,2280,2284,2288,2292,2296,2300,2304,2308,2316,2320,2324,2248,2252 | 2380 | Start No Earlier Than | 1/12/26 | 20 | 13.2d | January 12, 2026 8:00 AM | February 9, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
5642 | Conversion Full Mock Cycle 1 - QA | June 8, 2026 3:24 PM | June 15, 2026 3:24 PM | 2379 | 2381 | Start No Earlier Than | 2/10/26 | 5 | 13.2d | February 10, 2026 8:00 AM | February 17, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
5643 | Conversion Full Mock Cycle 1 - County Testing | June 15, 2026 3:24 PM | June 22, 2026 3:24 PM | 2380 | 2382 | Start No Earlier Than | 2/18/26 | 5 | 13.2d | February 18, 2026 8:00 AM | February 24, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
5644 | Conversion Full Mock Cycle 1 - Review & Closure | June 22, 2026 3:24 PM | June 29, 2026 3:24 PM | 2381 | 2384 | Start No Earlier Than | 2/25/26 | 5 | 13.2d | February 25, 2026 8:00 AM | March 3, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
5645 | Full Mock Cycle 2 | June 29, 2026 3:24 PM | August 18, 2026 3:24 PM |  |  | As Soon As Possible | NA | 35 | 13.2d | March 16, 2026 8:00 AM | May 4, 2026 5:00 PM | 35 days | No | NA | NA | NA | 0
5646 | Conversion Full Mock Cycle 2 - ETL & SIT | June 29, 2026 3:24 PM | July 28, 2026 3:24 PM | 2382 | 2385 | Start No Earlier Than | 3/16/26 | 20 | 13.2d | March 16, 2026 8:00 AM | April 13, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
5647 | Conversion Full Mock Cycle 2 - QA | July 28, 2026 3:24 PM | August 4, 2026 3:24 PM | 2384 | 2386 | Start No Earlier Than | 4/14/26 | 5 | 13.2d | April 14, 2026 8:00 AM | April 20, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
5648 | Conversion Full Mock Cycle 2 - County Testing | August 4, 2026 3:24 PM | August 11, 2026 3:24 PM | 2385 | 2387 | Start No Earlier Than | 4/21/26 | 5 | 13.2d | April 21, 2026 8:00 AM | April 27, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
5649 | Conversion Full Mock Cycle 2 - Review & Closure | August 11, 2026 3:24 PM | August 18, 2026 3:24 PM | 2386 | 2389 | Start No Earlier Than | 4/28/26 | 5 | 13.2d | April 28, 2026 8:00 AM | May 4, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
5650 | Full Mock Cycle 3 | August 18, 2026 3:24 PM | October 7, 2026 3:24 PM |  |  | As Soon As Possible | NA | 35 | 13.2d | May 11, 2026 8:00 AM | June 29, 2026 5:00 PM | 35 days | No | NA | NA | NA | 0
5651 | Conversion Full Mock Cycle 3 - ETL & SIT | August 18, 2026 3:24 PM | September 16, 2026 3:24 PM | 2219,2387 | 2390 | Start No Earlier Than | 5/11/26 | 20 | 13.2d | May 11, 2026 8:00 AM | June 8, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
5652 | Conversion Full Mock Cycle 3 - QA | September 16, 2026 3:24 PM | September 23, 2026 3:24 PM | 2389 | 2391 | Start No Earlier Than | 6/9/26 | 5 | 13.2d | June 9, 2026 8:00 AM | June 15, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
5653 | Conversion Full Mock Cycle 3 - County Testing | September 23, 2026 3:24 PM | September 30, 2026 3:24 PM | 2390 | 2392 | Start No Earlier Than | 6/16/26 | 5 | 13.2d | June 16, 2026 8:00 AM | June 22, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
5654 | Conversion Full Mock Cycle 3 - Review & Closure | September 30, 2026 3:24 PM | October 7, 2026 3:24 PM | 2391 | 5630,2394FS-1d | Start No Earlier Than | 6/23/26 | 5 | 13.2d | June 23, 2026 8:00 AM | June 29, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
11580 | Final Conversion | October 6, 2026 3:24 PM | December 9, 2026 3:24 PM |  |  | As Soon As Possible | NA | 43 | 210.2d | June 29, 2026 8:00 AM | August 27, 2026 5:00 PM | 43 days | No | NA | NA | NA | 0
11581 | Final Structured Data Conversion | October 6, 2026 3:24 PM | November 3, 2026 3:24 PM | 2392FS-1d | 2395FS-13d | As Soon As Possible | NA | 20 | 210.2d | June 29, 2026 8:00 AM | July 27, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
11582 | Final Conversion - Link Documents to Structured Data | October 15, 2026 3:24 PM | December 9, 2026 3:24 PM | 2394FS-13d | 2396FS-43d | As Soon As Possible | NA | 36 | 210.2d | July 9, 2026 8:00 AM | August 27, 2026 5:00 PM | 36 days | No | NA | NA | NA | 0
11583 | Final Conversion - Run Micro Conversion (Structured Data and Documents) | October 6, 2026 3:24 PM | December 9, 2026 3:24 PM | 2395FS-43d |  | As Soon As Possible | NA | 43 | 210.2d | June 29, 2026 8:00 AM | August 27, 2026 5:00 PM | 43 days | No | NA | NA | NA | 0
6972 | Data Extracts LOE (CARESV1-34760) | May 1, 2023 8:00 AM | August 7, 2026 5:00 PM |  |  | As Soon As Possible | NA | 822 | 0d | May 1, 2023 8:00 AM | August 7, 2026 5:00 PM | 822 days | No | 5/1/23 | NA | NA | 0.82999999999999996
6973 | Requirements | May 1, 2023 8:00 AM | January 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 440 | 0d | May 1, 2023 8:00 AM | January 30, 2025 5:00 PM | 440 days | No | 5/1/23 | 1/30/25 | NA | 1
6974 | CWS/CMS - Research and Document Current Functionality | May 1, 2023 8:00 AM | October 30, 2024 5:00 PM | 2254SS+15d | 2400SS,2401SS,2402SS,2416SS | Must Start On | 5/1/23 | 380 | 0d | May 1, 2023 8:00 AM | October 30, 2024 5:00 PM | 380 days | No | 5/1/23 | 10/30/24 | NA | 1
6975 | Security Requirements-High Level Controls | May 2, 2023 8:00 AM | January 2, 2024 5:00 PM | 2399SS | 2404SS,2405SS,2407SS | As Soon As Possible | NA | 168 | 0d | May 2, 2023 8:00 AM | January 2, 2024 5:00 PM | 168 days | No | 5/2/23 | 1/2/24 | NA | 1
6976 | Security Requirements-Requirements Identification | May 1, 2024 8:00 AM | January 30, 2025 5:00 PM | 2399SS | 2409 | As Soon As Possible | NA | 189 | 0d | May 1, 2024 8:00 AM | January 30, 2025 5:00 PM | 189 days | No | 5/1/24 | 1/30/25 | NA | 1
6977 | Future State Requirements - Requirement Elaboration | May 2, 2024 8:00 AM | December 30, 2024 5:00 PM | 2399SS | 2404 | Start No Earlier Than | 5/2/24 | 167 | 0d | May 2, 2024 8:00 AM | December 30, 2024 5:00 PM | 167 days | No | 5/2/24 | 12/30/24 | NA | 1
6978 | Design - Extracts | May 2, 2023 8:00 AM | October 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 629 | 0d | May 2, 2023 8:00 AM | October 30, 2025 5:00 PM | 629 days | No | 5/2/23 | NA | NA | 0.96999999999999997
6979 | Design Extracts - Perform Initial Design | May 2, 2023 8:00 AM | January 2, 2024 5:00 PM | 2400SS,2402 | 2411 | Must Start On | 5/2/23 | 168 | 0d | May 2, 2023 8:00 AM | January 2, 2024 5:00 PM | 168 days | No | 5/2/23 | 1/2/24 | NA | 1
6980 | Design Extracts - Conduct Detailed Design of Extracts | May 1, 2024 8:00 AM | October 30, 2025 5:00 PM | 2400SS | 2415 | Must Start On | 5/1/24 | 379 | 0d | May 1, 2024 8:00 AM | October 30, 2025 5:00 PM | 379 days | No | 5/1/24 | NA | NA | 0.95999999999999996
6981 | Security Controls and Capacity Management | May 2, 2023 8:00 AM | December 29, 2025 5:00 PM |  |  | As Soon As Possible | NA | 668 | 142d | May 2, 2023 8:00 AM | December 29, 2025 5:00 PM | 668 days | No | 5/2/23 | NA | NA | 0.91000000000000003
6982 | Security Controls and Capacity Management - Perform Initial Design | May 2, 2023 8:00 AM | January 2, 2024 5:00 PM | 2400SS | 2408,2411 | Must Start On | 5/2/23 | 168 | 0d | May 2, 2023 8:00 AM | January 2, 2024 5:00 PM | 168 days | No | 5/2/23 | 1/2/24 | NA | 1
6983 | Security Controls and Capacity Management - Conduct Detailed Design | May 1, 2024 8:00 AM | October 30, 2025 5:00 PM | 2407 | 2414SS,2415FS+19d | As Soon As Possible | NA | 379 | -10d | May 1, 2024 8:00 AM | October 30, 2025 5:00 PM | 379 days | No | 5/1/24 | NA | NA | 0.95999999999999996
6984 | Security Controls and Capacity Management - Obtain Security Approvals | January 31, 2025 8:00 AM | December 29, 2025 5:00 PM | 2401 | 2415FF | As Soon As Possible | NA | 229 | 142d | January 31, 2025 8:00 AM | December 29, 2025 5:00 PM | 229 days | No | 1/31/25 | NA | NA | 0.77000000000000002
6985 | Perform Validation | June 3, 2024 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 168 | 0d | June 1, 2024 8:00 AM | January 31, 2025 5:00 PM | 168 days | No | 6/3/24 | 1/31/25 | NA | 1
6986 | Perform Validation - POC 1 | June 3, 2024 8:00 AM | September 27, 2024 5:00 PM | 2407,2404 | 2412FS+1d | Must Start On | 6/1/24 | 84 | 0d | June 1, 2024 8:00 AM | September 27, 2024 5:00 PM | 84 days | No | 6/3/24 | 9/27/24 | NA | 1
6987 | Perform Validation - POC 2 | October 1, 2024 8:00 AM | January 31, 2025 5:00 PM | 2411FS+1d | 2417SS | As Soon As Possible | NA | 83 | 0d | October 1, 2024 8:00 AM | January 31, 2025 5:00 PM | 83 days | No | 10/1/24 | 1/31/25 | NA | 1
6988 | Implementation - Extract Generation | May 1, 2023 8:00 AM | August 7, 2026 5:00 PM |  |  | As Soon As Possible | NA | 822 | 0d | May 1, 2023 8:00 AM | August 7, 2026 5:00 PM | 822 days | No | 5/1/23 | NA | NA | 0.66000000000000003
6929 | Build Core Extract Capabilities | June 3, 2024 8:00 AM | November 28, 2025 5:00 PM | 2408SS | 2415 | Must Start On | 6/1/24 | 376 | 0d | June 1, 2024 8:00 AM | November 28, 2025 5:00 PM | 376 days | No | 6/3/24 | NA | NA | 0.91000000000000003
6930 | Perform Feature Expansion | December 1, 2025 8:00 AM | August 6, 2026 5:00 PM | 2414,2409FF,2408FS+19d,2405 | 5625 | As Soon As Possible | NA | 172 | -10d | December 1, 2025 8:00 AM | August 6, 2026 5:00 PM | 172 days | No | NA | NA | NA | 0
6931 | Semantic Layer Data Model Development | May 1, 2023 8:00 AM | August 5, 2026 5:00 PM | 2399SS | 5625,2435SS | As Soon As Possible | NA | 820 | -9d | May 1, 2023 8:00 AM | August 5, 2026 5:00 PM | 820 days | No | 5/1/23 | NA | NA | 0.75
6932 | Org Enablement - Knowledge Transfer | October 1, 2024 8:00 AM | August 7, 2026 5:00 PM | 2412SS | 5625FS+5d | As Soon As Possible | NA | 464 | -16d | October 1, 2024 8:00 AM | August 7, 2026 5:00 PM | 464 days | No | 10/1/24 | NA | NA | 0.56000000000000005
6943 | County Transition | May 1, 2023 8:00 AM | November 24, 2026 5:00 PM |  |  | As Soon As Possible | NA | 897 | 219d | May 1, 2023 8:00 AM | May 26, 2026 5:00 PM | 770 days | Yes | 5/1/23 | NA | NA | 0.46000000000000002
11547 | County - Forms | May 2, 2024 8:00 AM | May 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 518 | 346d | May 2, 2024 8:00 AM | May 26, 2026 5:00 PM | 518 days | No | 5/2/24 | NA | NA | 0.27000000000000002
6989 | Forms Training | May 2, 2024 8:00 AM | March 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 459 | 405d | May 2, 2024 8:00 AM | March 2, 2026 5:00 PM | 459 days | No | 5/2/24 | NA | NA | 0.20000000000000001
6990 | Forms Training - Organize AEM Training Pilot Cohort | May 2, 2024 8:00 AM | August 8, 2025 5:00 PM | 557FF | 2422FS-29d | Must Start On | 5/2/24 | 320 | 0d | May 2, 2024 8:00 AM | August 8, 2025 5:00 PM | 320 days | No | 5/2/24 | NA | NA | 0.47999999999999998
6991 | Forms Training - Instructor Led Trainings | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 557SS,2421FS-29d | 2423SS | As Soon As Possible | NA | 106 | 467d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | NA | NA | NA | 0
6992 | Forms Training - Conduct Workshops | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 557SS,2422SS | 2424SS | As Soon As Possible | NA | 106 | 467d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | NA | NA | NA | 0
6993 | Forms Training - Perform On Demand Trainings | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 557SS,2423SS | 2425SS-76d | As Soon As Possible | NA | 106 | 467d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | NA | NA | NA | 0
6994 | Forms Training - Planned KT Session | August 11, 2025 8:00 AM | March 2, 2026 5:00 PM | 559SS,2424SS-76d | 2426FS-289d | As Soon As Possible | NA | 139 | 405d | August 11, 2025 8:00 AM | March 2, 2026 5:00 PM | 139 days | No | NA | NA | NA | 0
11546 | Forms Training - Identify | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM | 2425FS-289d | 2427 | As Soon As Possible | NA | 150 | 0d | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM | 150 days | No | 1/6/25 | 8/8/25 | NA | 1
11545 | Forms Training - Prioritize | August 11, 2025 8:00 AM | April 15, 2026 5:00 PM | 2426 | 2428SS | As Soon As Possible | NA | 170 | 374d | August 11, 2025 8:00 AM | April 15, 2026 5:00 PM | 170 days | No | 8/11/25 | NA | NA | 0.14000000000000001
11558 | Monitor Progress for Prioritized Forms | August 11, 2025 8:00 AM | May 26, 2026 5:00 PM | 2427SS |  | As Soon As Possible | NA | 198 | 346d | August 11, 2025 8:00 AM | May 26, 2026 5:00 PM | 198 days | No | 8/11/25 | NA | NA | 0.12
11548 | County - External Systems | July 9, 2025 8:00 AM | November 24, 2026 5:00 PM |  |  | As Soon As Possible | NA | 348 | 219d | January 6, 2025 8:00 AM | May 26, 2026 5:00 PM | 348 days | No | NA | NA | NA | 0
11549 | County - External Systems - Identify | July 9, 2025 8:00 AM | February 11, 2026 5:00 PM | 1049SS-100d | 2431 | As Soon As Possible | NA | 150 | 219d | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM | 150 days | No | NA | NA | NA | 0
11550 | County - External Systems - Prioritize | February 12, 2026 8:00 AM | October 14, 2026 5:00 PM | 2430 | 2432FS-170d | As Soon As Possible | NA | 170 | 219d | August 11, 2025 8:00 AM | April 15, 2026 5:00 PM | 170 days | No | NA | NA | NA | 0
11559 | Monitor Progress for Prioritized External Systems | February 12, 2026 8:00 AM | November 24, 2026 5:00 PM | 2431FS-170d |  | As Soon As Possible | NA | 198 | 219d | August 11, 2025 8:00 AM | May 26, 2026 5:00 PM | 198 days | No | NA | NA | NA | 0
11553 | County Analytics Transition | May 1, 2023 8:00 AM | May 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 770 | 346d | May 1, 2023 8:00 AM | May 26, 2026 5:00 PM | 770 days | No | 5/1/23 | NA | NA | 0.69999999999999996
6934 | Tableau Training (CARESV1-21329) | May 1, 2023 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 649 | 162d | May 1, 2023 8:00 AM | November 28, 2025 5:00 PM | 649 days | Yes | 5/1/23 | NA | NA | 0.95999999999999996
6935 | Training Cohort - Cycle 1 | May 1, 2023 8:00 AM | June 7, 2024 5:00 PM | 2416SS | 2436,2443FS+144d,2441SS,2983 | Must Start On | 6/7/24 | 278 | 0d | May 1, 2023 8:00 AM | June 7, 2024 5:00 PM | 278 days | No | 5/1/23 | 6/7/24 | NA | 1
6936 | Training Cohort - Cycle 2 | December 12, 2023 8:00 AM | July 24, 2024 5:00 PM | 2435,2441 | 2437FS-15d | As Soon As Possible | NA | 155 | 0d | December 12, 2023 8:00 AM | July 24, 2024 5:00 PM | 155 days | No | 12/12/23 | 7/24/24 | NA | 1
6937 | Training Cohort - Cycle 3 | July 3, 2024 8:00 AM | March 7, 2025 5:00 PM | 2436FS-15d | 2438FS+29d | As Soon As Possible | NA | 170 | 0d | July 3, 2024 8:00 AM | March 7, 2025 5:00 PM | 170 days | No | 7/3/24 | 3/7/25 | NA | 1
6938 | Training Cohort - Cycle 4 | April 21, 2025 8:00 AM | November 28, 2025 5:00 PM | 2437FS+29d | 5625 | As Soon As Possible | NA | 155 | 162d | April 21, 2025 8:00 AM | November 28, 2025 5:00 PM | 155 days | No | 4/21/25 | NA | NA | 0.79000000000000004
6939 | Tableau - Knowledge Transfer | May 2, 2023 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 648 | 162d | May 2, 2023 8:00 AM | November 28, 2025 5:00 PM | 648 days | Yes | 5/2/23 | NA | NA | 0.91000000000000003
6940 | Periodic Data Model Reviews CARESV1-48917 | January 2, 2024 8:00 AM | November 26, 2025 5:00 PM | 559FF-1d | 5625 | As Soon As Possible | NA | 480 | 163d | January 2, 2024 8:00 AM | November 26, 2025 5:00 PM | 480 days | No | 1/2/24 | NA | NA | 0.93000000000000005
6941 | Tableau KT Initial Release | May 2, 2023 8:00 AM | January 3, 2024 5:00 PM | 2435SS | 2436 | As Soon As Possible | NA | 169 | 0d | May 2, 2023 8:00 AM | January 3, 2024 5:00 PM | 169 days | No | 5/2/23 | 1/3/24 | NA | 1
6942 | Tableau KT Play Book Enhancements (CARESV1-15699) | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 557SS | 5625 | As Soon As Possible | NA | 106 | 162d | June 30, 2025 8:00 AM | November 28, 2025 5:00 PM | 106 days | No | 6/30/25 | NA | NA | 0.68999999999999995
11554 | County Analytics Transition - Identify | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM | 2435FS+144d | 2444 | As Soon As Possible | NA | 150 | 346d | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM | 150 days | No | NA | NA | NA | 0
11555 | County Analytics Transition - Prioritize | August 11, 2025 8:00 AM | April 15, 2026 5:00 PM | 2443 | 2445FS-170d | As Soon As Possible | NA | 170 | 346d | August 11, 2025 8:00 AM | April 15, 2026 5:00 PM | 170 days | No | NA | NA | NA | 0
11560 | County Analytics Transition - Monitor Progress for Prioritized Reports | August 11, 2025 8:00 AM | May 26, 2026 5:00 PM | 2444FS-170d |  | As Soon As Possible | NA | 198 | 346d | August 11, 2025 8:00 AM | May 26, 2026 5:00 PM | 198 days | No | NA | NA | NA | 0
3369 | Forms - DocGen | May 23, 2022 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 905 | 445d | May 23, 2022 8:00 AM | December 31, 2025 5:00 PM | 905 days | No | 5/23/22 | NA | NA | 0.87
3370 | Research & Proof of Concept | July 13, 2023 8:00 AM | June 26, 2024 5:00 PM |  |  | As Soon As Possible | NA | 240 | 0d | July 13, 2023 8:00 AM | June 26, 2024 5:00 PM | 240 days | No | 7/13/23 | 6/26/24 | NA | 1
3371 | DocGen Research and Proof of Concept - County Specific - Forms | July 13, 2023 8:00 AM | June 26, 2024 5:00 PM |  | 2450SS,2461SS-18d | Must Start On | 7/13/23 | 250 | 0d | July 13, 2023 8:00 AM | June 26, 2024 5:00 PM | 250 days | No | 7/13/23 | 6/26/24 | NA | 1
3372 | AEM Infrastructure Setup & Configuration | November 6, 2023 8:00 AM | January 19, 2024 5:00 PM |  |  | As Soon As Possible | NA | 49 | 0d | November 6, 2023 8:00 AM | January 19, 2024 5:00 PM | 49 days | No | 11/6/23 | 1/19/24 | NA | 1
3373 | DocGen AEM QA Environment - CDI Controls and MuleSoft Mapping | November 6, 2023 8:00 AM | November 27, 2023 5:00 PM | 2448SS | 2451 | As Soon As Possible | NA | 16 | 0d | November 6, 2023 8:00 AM | November 27, 2023 5:00 PM | 16 days | No | 11/6/23 | 11/27/23 | NA | 1
3374 | DocGen AEM ProdDataReplica Environment - CDI Controls and MuleSoft Mapping | November 8, 2023 8:00 AM | January 11, 2024 5:00 PM | 2450 | 2452 | As Soon As Possible | NA | 47 | 0d | November 8, 2023 8:00 AM | January 11, 2024 5:00 PM | 47 days | No | 11/8/23 | 1/11/24 | NA | 1
3375 | AEM Staging Whitelisting with Global Protect VPN | November 13, 2023 8:00 AM | December 8, 2023 5:00 PM | 2451 | 2453 | As Soon As Possible | NA | 20 | 0d | November 13, 2023 8:00 AM | December 8, 2023 5:00 PM | 20 days | No | 11/13/23 | 12/8/23 | NA | 1
3376 | AEM Integration with Mule Endpoint - Requesting for Okta API client Id / secret for integration between AEM and MuleSoft | November 13, 2023 8:00 AM | December 15, 2023 5:00 PM | 2452 | 2454 | As Soon As Possible | NA | 25 | 0d | November 13, 2023 8:00 AM | December 15, 2023 5:00 PM | 25 days | No | 11/13/23 | 12/15/23 | NA | 1
3377 | Requesting for API client Id / secret for integration between AEM and MuleSoft - QA Environment | November 13, 2023 8:00 AM | November 14, 2023 5:00 PM | 2453 | 2455 | As Soon As Possible | NA | 2 | 0d | November 13, 2023 8:00 AM | November 14, 2023 5:00 PM | 2 days | No | 11/13/23 | 11/14/23 | NA | 1
3378 | AEM Access Request for PaaS team in Okta 3 | November 6, 2023 8:00 AM | November 29, 2023 5:00 PM | 2454 | 2456 | As Soon As Possible | NA | 18 | 0d | November 6, 2023 8:00 AM | November 29, 2023 5:00 PM | 18 days | No | 11/6/23 | 11/29/23 | NA | 1
3379 | - DocGen AEM Stage New Environment - CDI Controls and MuleSoft Mapping | December 14, 2023 8:00 AM | January 11, 2024 5:00 PM | 2455 | 2457 | As Soon As Possible | NA | 21 | 0d | December 14, 2023 8:00 AM | January 11, 2024 5:00 PM | 21 days | No | 12/14/23 | 1/11/24 | NA | 1
3380 | MuleSoft- AEM Stage Endpoints for DocGen Deployment | December 12, 2023 8:00 AM | January 19, 2024 5:00 PM | 2456 | 2458 | As Soon As Possible | NA | 29 | 0d | December 12, 2023 8:00 AM | January 19, 2024 5:00 PM | 29 days | No | 12/12/23 | 1/19/24 | NA | 1
3381 | DocGen AEM Readiness1 Environment (Staging) - MuleSoft Mapping | January 8, 2024 8:00 AM | January 12, 2024 5:00 PM | 2457 | 2499 | As Soon As Possible | NA | 5 | 0d | January 8, 2024 8:00 AM | January 12, 2024 5:00 PM | 5 days | No | 1/8/24 | 1/12/24 | NA | 1
3382 | DocGen Framework | September 22, 2022 8:00 AM | November 6, 2023 5:00 PM |  |  | As Soon As Possible | NA | 282 | 0d | September 22, 2022 8:00 AM | November 6, 2023 5:00 PM | 282 days | No | 9/22/22 | 11/6/23 | NA | 1
3383 | DocGen In-line Editing (MuleSoft API Integration for In-line editing ) | September 22, 2022 8:00 AM | November 6, 2023 5:00 PM |  |  | As Soon As Possible | NA | 282 | 0d | September 22, 2022 8:00 AM | November 6, 2023 5:00 PM | 282 days | No | 9/22/22 | 11/6/23 | NA | 1
3384 | SF Integration for In-line editing | June 15, 2023 8:00 AM | August 16, 2023 5:00 PM | 2448SS-18d | 2462 | As Soon As Possible | NA | 45 | 0d | June 15, 2023 8:00 AM | August 16, 2023 5:00 PM | 45 days | No | 6/15/23 | 8/16/23 | NA | 1
3385 | Aurora DB Integration for In-line editing | September 22, 2022 8:00 AM | February 2, 2023 5:00 PM | 2461 | 2463 | As Soon As Possible | NA | 96 | 0d | September 22, 2022 8:00 AM | February 2, 2023 5:00 PM | 96 days | No | 9/22/22 | 2/2/23 | NA | 1
3386 | HTML and IC forms dynamic rendering for In-line | February 23, 2023 8:00 AM | March 24, 2023 5:00 PM | 2462 | 2464 | As Soon As Possible | NA | 22 | 0d | February 23, 2023 8:00 AM | March 24, 2023 5:00 PM | 22 days | No | 2/23/23 | 3/24/23 | NA | 1
3387 | DocuEdge Integration for In-line editing | February 23, 2023 8:00 AM | March 24, 2023 5:00 PM | 2463 | 2465 | As Soon As Possible | NA | 22 | 0d | February 23, 2023 8:00 AM | March 24, 2023 5:00 PM | 22 days | No | 2/23/23 | 3/24/23 | NA | 1
3388 | Save-as-Draft for In-line editing | February 23, 2023 8:00 AM | March 24, 2023 5:00 PM | 2464 | 2466 | As Soon As Possible | NA | 22 | 0d | February 23, 2023 8:00 AM | March 24, 2023 5:00 PM | 22 days | No | 2/23/23 | 3/24/23 | NA | 1
3389 | OKTA Integration | March 8, 2023 8:00 AM | November 6, 2023 5:00 PM | 2465 | 2468 | As Soon As Possible | NA | 174 | 0d | March 8, 2023 8:00 AM | November 6, 2023 5:00 PM | 174 days | No | 3/8/23 | 11/6/23 | NA | 1
3390 | DocGen e-Signature | February 16, 2023 8:00 AM | August 16, 2023 5:00 PM |  |  | As Soon As Possible | NA | 126 | 0d | February 16, 2023 8:00 AM | August 16, 2023 5:00 PM | 126 days | No | 2/16/23 | 8/16/23 | NA | 1
3391 | DocGen e-Signature - Oauth Integration with Adobe Sign account | May 15, 2023 8:00 AM | August 16, 2023 5:00 PM | 2466 | 2469 | As Soon As Possible | NA | 68 | 0d | May 15, 2023 8:00 AM | August 16, 2023 5:00 PM | 68 days | No | 5/15/23 | 8/16/23 | NA | 1
3392 | DocGen e-Signature - Solution Design | February 16, 2023 8:00 AM | March 24, 2023 5:00 PM | 2468 | 2470 | As Soon As Possible | NA | 27 | 0d | February 16, 2023 8:00 AM | March 24, 2023 5:00 PM | 27 days | No | 2/16/23 | 3/24/23 | NA | 1
3393 | DocGen e-Signature - OSI Risk assessment | April 10, 2023 8:00 AM | May 10, 2023 5:00 PM | 2469 | 2471 | As Soon As Possible | NA | 23 | 0d | April 10, 2023 8:00 AM | May 10, 2023 5:00 PM | 23 days | No | 4/10/23 | 5/10/23 | NA | 1
3394 | DocGen e-Signature - MuleSoft Integration | May 15, 2023 8:00 AM | August 16, 2023 5:00 PM | 2470 | 2472 | As Soon As Possible | NA | 68 | 0d | May 15, 2023 8:00 AM | August 16, 2023 5:00 PM | 68 days | No | 5/15/23 | 8/16/23 | NA | 1
3395 | DocGen e-Signature - Salesforce Integration | May 15, 2023 8:00 AM | August 16, 2023 5:00 PM | 2471 | 2473 | As Soon As Possible | NA | 68 | 0d | May 15, 2023 8:00 AM | August 16, 2023 5:00 PM | 68 days | No | 5/15/23 | 8/16/23 | NA | 1
3396 | DocGen e-Signature - MuleSoft API development for eSign | May 15, 2023 8:00 AM | August 16, 2023 5:00 PM | 2472 | 2474 | As Soon As Possible | NA | 68 | 0d | May 15, 2023 8:00 AM | August 16, 2023 5:00 PM | 68 days | No | 5/15/23 | 8/16/23 | NA | 1
3397 | DocGen e-Signature - Adobe Sign Configuration | May 15, 2023 8:00 AM | August 16, 2023 5:00 PM | 2473 | 2475 | As Soon As Possible | NA | 68 | 0d | May 15, 2023 8:00 AM | August 16, 2023 5:00 PM | 68 days | No | 5/15/23 | 8/16/23 | NA | 1
3398 | DocGen e-Signature - Whitelisting MuleSoft IP with OSI network | June 6, 2023 8:00 AM | August 1, 2023 5:00 PM | 2474 | 2507 | As Soon As Possible | NA | 41 | 0d | June 6, 2023 8:00 AM | August 1, 2023 5:00 PM | 41 days | No | 6/6/23 | 8/1/23 | NA | 1
3399 | DocGen - Product Development & Support | May 23, 2022 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 905 | 445d | May 23, 2022 8:00 AM | December 31, 2025 5:00 PM | 905 days | No | 5/23/22 | NA | NA | 0.84999999999999998
3400 | DocGen - Milestone 3 | May 23, 2022 8:00 AM | September 30, 2022 5:00 PM |  |  | As Soon As Possible | NA | 92 | 0d | May 23, 2022 8:00 AM | September 30, 2022 5:00 PM | 92 days | No | 5/23/22 | 9/30/22 | NA | 1
3401 | DocGen - Milestone 3 - Form Identification | May 23, 2022 8:00 AM | June 10, 2022 5:00 PM | 62SS | 2479 | As Soon As Possible | NA | 15 | 0d | May 23, 2022 8:00 AM | June 10, 2022 5:00 PM | 15 days | No | 5/23/22 | 6/10/22 | NA | 1
3402 | DocGen - Milestone 3 - Analysis and Template Design | June 13, 2022 8:00 AM | June 24, 2022 5:00 PM | 2478 | 2480 | As Soon As Possible | NA | 10 | 0d | June 13, 2022 8:00 AM | June 24, 2022 5:00 PM | 10 days | No | 6/13/22 | 6/24/22 | NA | 1
3403 | DocGen - Milestone 3 - Template Design Review and Approval | June 27, 2022 8:00 AM | July 22, 2022 5:00 PM | 2479 | 2481 | As Soon As Possible | NA | 20 | 0d | June 27, 2022 8:00 AM | July 22, 2022 5:00 PM | 20 days | No | 6/27/22 | 7/22/22 | NA | 1
3404 | DocGen - Milestone 3 - AEM Design, Review & Approval | July 25, 2022 8:00 AM | September 2, 2022 5:00 PM | 2480 | 2482 | As Soon As Possible | NA | 30 | 0d | July 25, 2022 8:00 AM | September 2, 2022 5:00 PM | 30 days | No | 7/25/22 | 9/2/22 | NA | 1
3405 | DocGen - Milestone 3 - AEM Integration (Build/SIT) | September 5, 2022 8:00 AM | September 16, 2022 5:00 PM | 2481 | 2483 | As Soon As Possible | NA | 10 | 0d | September 5, 2022 8:00 AM | September 16, 2022 5:00 PM | 10 days | No | 9/5/22 | 9/16/22 | NA | 1
3406 | DocGen - Milestone 3 - QA/Joint Review | September 19, 2022 8:00 AM | September 30, 2022 5:00 PM | 2482 | 1484 | As Soon As Possible | NA | 10 | 0d | September 19, 2022 8:00 AM | September 30, 2022 5:00 PM | 10 days | No | 9/19/22 | 9/30/22 | NA | 1
3407 | DocGen - Milestone 5 | August 29, 2022 8:00 AM | January 6, 2023 5:00 PM |  |  | As Soon As Possible | NA | 89 | 0d | August 29, 2022 8:00 AM | January 6, 2023 5:00 PM | 89 days | No | 8/29/22 | 1/6/23 | NA | 1
3408 | DocGen - Milestone 5 - Form Identification | August 29, 2022 8:00 AM | September 16, 2022 5:00 PM | 154SS+15d | 2486 | As Soon As Possible | NA | 15 | 0d | August 29, 2022 8:00 AM | September 16, 2022 5:00 PM | 15 days | No | 8/29/22 | 9/16/22 | NA | 1
3409 | DocGen - Milestone 5 - Analysis and Template Design | September 19, 2022 8:00 AM | September 30, 2022 5:00 PM | 2485 | 2487 | As Soon As Possible | NA | 10 | 0d | September 19, 2022 8:00 AM | September 30, 2022 5:00 PM | 10 days | No | 9/19/22 | 9/30/22 | NA | 1
3410 | DocGen - Milestone 5 - Template Design Review and Approval | October 3, 2022 8:00 AM | October 28, 2022 5:00 PM | 2486 | 2488 | As Soon As Possible | NA | 20 | 0d | October 3, 2022 8:00 AM | October 28, 2022 5:00 PM | 20 days | No | 10/3/22 | 10/28/22 | NA | 1
3411 | DocGen - Milestone 5 - AEM Design, Review & Approval | October 31, 2022 8:00 AM | December 9, 2022 5:00 PM | 2487 | 2489 | As Soon As Possible | NA | 30 | 0d | October 31, 2022 8:00 AM | December 9, 2022 5:00 PM | 30 days | No | 10/31/22 | 12/9/22 | NA | 1
3412 | DocGen - Milestone 5 - AEM Integration (Build/SIT) | December 12, 2022 8:00 AM | December 23, 2022 5:00 PM | 2488 | 2490 | As Soon As Possible | NA | 10 | 0d | December 12, 2022 8:00 AM | December 23, 2022 5:00 PM | 10 days | No | 12/12/22 | 12/23/22 | NA | 1
3413 | DocGen - Milestone 5 - QA/Joint Review | December 26, 2022 8:00 AM | January 6, 2023 5:00 PM | 2489 | 1484 | As Soon As Possible | NA | 10 | 0d | December 26, 2022 8:00 AM | January 6, 2023 5:00 PM | 10 days | No | 12/26/22 | 1/6/23 | NA | 1
3414 | DocGen - Milestone 6 | October 31, 2022 8:00 AM | March 10, 2023 5:00 PM |  |  | As Soon As Possible | NA | 88 | 0d | October 31, 2022 8:00 AM | March 10, 2023 5:00 PM | 88 days | No | 10/31/22 | 3/10/23 | NA | 1
3415 | DocGen - Milestone 6 - Form Identification | October 31, 2022 8:00 AM | November 18, 2022 5:00 PM | 214SS+55d | 2493 | As Soon As Possible | NA | 15 | 0d | October 31, 2022 8:00 AM | November 18, 2022 5:00 PM | 15 days | No | 10/31/22 | 11/18/22 | NA | 1
3416 | DocGen - Milestone 6 - Analysis and Template Design | November 21, 2022 8:00 AM | December 2, 2022 5:00 PM | 2492 | 2494 | As Soon As Possible | NA | 10 | 0d | November 21, 2022 8:00 AM | December 2, 2022 5:00 PM | 10 days | No | 11/21/22 | 12/2/22 | NA | 1
3417 | DocGen - Milestone 6 - Template Design Review and Approval | December 5, 2022 8:00 AM | December 30, 2022 5:00 PM | 2493 | 2495 | As Soon As Possible | NA | 20 | 0d | December 5, 2022 8:00 AM | December 30, 2022 5:00 PM | 20 days | No | 12/5/22 | 12/30/22 | NA | 1
3418 | DocGen - Milestone 6 - AEM Design, Review & Approval | January 2, 2023 8:00 AM | February 10, 2023 5:00 PM | 2494 | 2496 | As Soon As Possible | NA | 30 | 0d | January 2, 2023 8:00 AM | February 10, 2023 5:00 PM | 30 days | No | 1/2/23 | 2/10/23 | NA | 1
3419 | DocGen - Milestone 6 - AEM Integration (Build/SIT) | February 13, 2023 8:00 AM | February 24, 2023 5:00 PM | 2495 | 2497 | As Soon As Possible | NA | 10 | 0d | February 13, 2023 8:00 AM | February 24, 2023 5:00 PM | 10 days | No | 2/13/23 | 2/24/23 | NA | 1
3420 | DocGen - Milestone 6 - QA/Joint Review | February 27, 2023 8:00 AM | March 10, 2023 5:00 PM | 2496 |  | As Soon As Possible | NA | 10 | 0d | February 27, 2023 8:00 AM | March 10, 2023 5:00 PM | 10 days | No | 2/27/23 | 3/10/23 | NA | 1
3421 | DocGen - Milestone 6.1 | January 2, 2024 8:00 AM | August 16, 2024 5:00 PM |  |  | As Soon As Possible | NA | 159 | 0d | January 2, 2024 8:00 AM | August 16, 2024 5:00 PM | 159 days | No | 1/2/24 | 8/16/24 | NA | 1
3422 | DocGen - Milestone 6.1 - Form Identification | January 2, 2024 8:00 AM | January 23, 2024 5:00 PM | 2458 | 2500,2617SS+1d | Start No Earlier Than | 1/2/24 | 15 | 0d | January 2, 2024 8:00 AM | January 23, 2024 5:00 PM | 15 days | No | 1/2/24 | 1/23/24 | NA | 1
3423 | DocGen - Milestone 6.1 - Analysis and Template Design | January 24, 2024 8:00 AM | February 6, 2024 5:00 PM | 2499 | 2501 | As Soon As Possible | NA | 10 | 0d | January 24, 2024 8:00 AM | February 6, 2024 5:00 PM | 10 days | No | 1/24/24 | 2/6/24 | NA | 1
3424 | DocGen - Milestone 6.1 - Template Design Review and Approval | February 7, 2024 8:00 AM | March 6, 2024 5:00 PM | 2500 | 2502SS-1d | As Soon As Possible | NA | 20 | 0d | February 7, 2024 8:00 AM | March 6, 2024 5:00 PM | 20 days | No | 2/7/24 | 3/6/24 | NA | 1
3425 | DocGen - Milestone 6.1 - AEM Design, Review & Approval | February 6, 2024 8:00 AM | May 30, 2024 5:00 PM | 2501SS-1d | 2503SS+31d | As Soon As Possible | NA | 80 | 0d | February 6, 2024 8:00 AM | May 30, 2024 5:00 PM | 80 days | No | 2/6/24 | 5/30/24 | NA | 1
3426 | DocGen - Milestone 6.1 - AEM Integration (Build/SIT) | March 21, 2024 8:00 AM | June 14, 2024 5:00 PM | 2502SS+31d | 2504FS+18d | As Soon As Possible | NA | 60 | 0d | March 21, 2024 8:00 AM | June 14, 2024 5:00 PM | 60 days | No | 3/21/24 | 6/14/24 | NA | 1
7428 | DocGen - Milestone 6.1 - QA | July 12, 2024 8:00 AM | August 2, 2024 5:00 PM | 2503FS+18d | 2505,5414 | As Soon As Possible | NA | 16 | 0d | July 12, 2024 8:00 AM | August 2, 2024 5:00 PM | 16 days | No | 7/12/24 | 8/2/24 | NA | 1
3427 | DocGen - Milestone 6.1 - Joint Review | August 5, 2024 8:00 AM | August 16, 2024 5:00 PM | 2504 |  | As Soon As Possible | NA | 10 | 0d | August 5, 2024 8:00 AM | August 16, 2024 5:00 PM | 10 days | No | 8/5/24 | 8/16/24 | NA | 1
3428 | DocGen - Milestone 7 | September 11, 2023 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 579 | 445d | September 11, 2023 8:00 AM | December 31, 2025 5:00 PM | 579 days | No | 9/11/23 | NA | NA | 0.82999999999999996
3429 | DocGen - Milestone 7 - Form Identification | September 11, 2023 8:00 AM | October 28, 2024 5:00 PM | 644,2475 |  | As Soon As Possible | NA | 286 | 0d | September 11, 2023 8:00 AM | October 28, 2024 5:00 PM | 286 days | No | 9/11/23 | 10/28/24 | NA | 1
3432 | DocGen - Milestone 7 - AEM Design, Review & Approval | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM | 599SS,597SS,598SS | 2509 | As Soon As Possible | NA | 58 | 0d | January 6, 2025 8:00 AM | March 28, 2025 5:00 PM | 58 days | No | 1/6/25 | 3/28/25 | NA | 1
3433 | DocGen - Milestone 7 - AEM Integration (Build/SIT) | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 702SS,2508 | 2510FS-127d | As Soon As Possible | NA | 168 | 93.87d | April 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 168 days | No | 4/2/25 | NA | NA | 0.80000000000000004
7429 | DocGen - Milestone 7 - QA | May 30, 2025 8:00 AM | December 31, 2025 5:00 PM | 2509FS-127d | 2511FS-148d | As Soon As Possible | NA | 149 | 109.45d | May 30, 2025 8:00 AM | December 31, 2025 5:00 PM | 149 days | No | 5/30/25 | NA | NA | 0.63
3434 | DocGen - Milestone 7 - Joint Review | June 2, 2025 8:00 AM | December 31, 2025 1:29 PM | 766SS,2510FS-148d |  | As Soon As Possible | NA | 103 | 445.44d | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 148 days | No | 6/2/25 | NA | NA | 0.63
3435 | DocGen - Milestone 8 | October 3, 2022 8:00 AM | February 28, 2024 5:00 PM |  |  | As Soon As Possible | NA | 350 | 0d | October 3, 2022 8:00 AM | February 28, 2024 5:00 PM | 350 days | No | 10/3/22 | 2/28/24 | NA | 1
3436 | DocGen - Milestone 8 - Form Identification | October 3, 2022 8:00 AM | October 20, 2022 5:00 PM | 255SS | 2514 | As Soon As Possible | NA | 14 | 0d | October 3, 2022 8:00 AM | October 20, 2022 5:00 PM | 14 days | No | 10/3/22 | 10/20/22 | NA | 1
3437 | DocGen - Milestone 8 - Analysis and Template Design | October 24, 2022 8:00 AM | November 30, 2022 5:00 PM | 577SS,2513 | 2515 | As Soon As Possible | NA | 25 | 0d | October 24, 2022 8:00 AM | November 30, 2022 5:00 PM | 25 days | No | 10/24/22 | 11/30/22 | NA | 1
3438 | DocGen - Milestone 8 - Template Design Review and Approval | December 1, 2022 8:00 AM | December 29, 2022 5:00 PM | 577SS,2514 | 2516 | As Soon As Possible | NA | 20 | 0d | December 1, 2022 8:00 AM | December 29, 2022 5:00 PM | 20 days | No | 12/1/22 | 12/29/22 | NA | 1
3439 | DocGen - Milestone 8 - AEM Design, Review & Approval | April 7, 2023 8:00 AM | July 18, 2023 5:00 PM | 577SS,2515 | 2517 | As Soon As Possible | NA | 71 | 0d | April 7, 2023 8:00 AM | July 18, 2023 5:00 PM | 71 days | No | 4/7/23 | 7/18/23 | NA | 1
3440 | DocGen - Milestone 8 - AEM Integration (Build/SIT) | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM | 273SS,2516 | 2518 | As Soon As Possible | NA | 77 | 0d | June 19, 2023 8:00 AM | October 5, 2023 5:00 PM | 77 days | No | 6/19/23 | 10/5/23 | NA | 1
3441 | DocGen - Milestone 8 - QA/Joint Review | June 9, 2023 8:00 AM | February 28, 2024 5:00 PM | 284SS,2517 |  | As Soon As Possible | NA | 180 | 0d | June 9, 2023 8:00 AM | February 28, 2024 5:00 PM | 180 days | No | 6/9/23 | 2/28/24 | NA | 1
3442 | DocGen - Milestone 9 | June 20, 2023 8:00 AM | April 22, 2024 5:00 PM |  |  | As Soon As Possible | NA | 210 | 0d | June 20, 2023 8:00 AM | April 22, 2024 5:00 PM | 210 days | No | 6/20/23 | 4/22/24 | NA | 1
3443 | DocGen - Milestone 9 - Form Identification | June 20, 2023 8:00 AM | July 11, 2023 5:00 PM | 318SS | 2521 | Start No Earlier Than | 6/20/23 | 15 | 0d | June 20, 2023 8:00 AM | July 11, 2023 5:00 PM | 15 days | No | 6/20/23 | 7/11/23 | NA | 1
3444 | DocGen - Milestone 9 - Analysis and Template Design | July 12, 2023 8:00 AM | July 25, 2023 5:00 PM | 593SS,2520 | 2522 | Start No Earlier Than | 7/12/23 | 10 | 0d | July 12, 2023 8:00 AM | July 25, 2023 5:00 PM | 10 days | No | 7/12/23 | 7/25/23 | NA | 1
3445 | DocGen - Milestone 9 - Template Design Review and Approval | July 26, 2023 8:00 AM | August 22, 2023 5:00 PM | 593SS,2521 | 2523 | Start No Earlier Than | 7/26/23 | 20 | 0d | July 26, 2023 8:00 AM | August 22, 2023 5:00 PM | 20 days | No | 7/26/23 | 8/22/23 | NA | 1
3446 | DocGen - Milestone 9 - AEM Design, Review & Approval | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 599SS,597SS,598SS,2522 | 2524 | Start No Earlier Than | 1/26/24 | 94 | 0d | September 11, 2023 8:00 AM | January 26, 2024 5:00 PM | 94 days | No | 9/11/23 | 1/26/24 | NA | 1
3447 | DocGen - Milestone 9 - AEM Integration (Build/SIT) | October 9, 2023 8:00 AM | February 23, 2024 5:00 PM | 343SS,2523 | 2525 | Start No Earlier Than | 2/23/24 | 93 | 0d | October 9, 2023 8:00 AM | February 23, 2024 5:00 PM | 93 days | No | 10/9/23 | 2/23/24 | NA | 1
3448 | DocGen - Milestone 9 - QA/Joint Review | March 22, 2024 8:00 AM | April 22, 2024 5:00 PM | 351SS,2524 |  | Start No Earlier Than | 4/22/24 | 21 | 0d | March 22, 2024 8:00 AM | April 22, 2024 5:00 PM | 21 days | No | 3/22/24 | 4/22/24 | NA | 1
3449 | DocGen - Milestone 10 | February 27, 2023 8:00 AM | December 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 714 | 446d | February 27, 2023 8:00 AM | December 30, 2025 5:00 PM | 714 days | No | 2/27/23 | NA | NA | 0.59999999999999998
3450 | DocGen - Milestone 10 - Form Identification | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 372SS |  | As Soon As Possible | NA | 80 | 0d | February 27, 2023 8:00 AM | June 20, 2023 5:00 PM | 80 days | No | 2/27/23 | 6/20/23 | NA | 1
3453 | DocGen - Milestone 10 - AEM Design, Review & Approval | April 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 614SS,613SS,612SS | 2529 | As Soon As Possible | NA | 43 | 0d | April 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 43 days | No | 4/1/25 | 5/30/25 | NA | 1
3454 | DocGen - Milestone 10 - AEM Integration (Build/SIT) | June 2, 2025 8:00 AM | November 28, 2025 4:41 PM | 380SS,2528 | 2530FS-84d | As Soon As Possible | NA | 82 | 50.76d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 6/2/25 | NA | NA | 0.73999999999999999
7430 | DocGen - Milestone 10 - QA | October 6, 2025 8:00 AM | December 30, 2025 5:00 PM | 386SS,2529FS-84d | 2531FS-105d | As Soon As Possible | NA | 59 | 50.72d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | 10/6/25 | NA | NA | 8.0000000000000002E-2
3455 | DocGen - Milestone 10 - Joint Review | October 6, 2025 8:00 AM | December 30, 2025 5:00 PM | 389SS,2530FS-105d |  | As Soon As Possible | NA | 59 | 446d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | 10/6/25 | NA | NA | 8.0000000000000002E-2
3463 | DocGen - Milestone 11 | March 29, 2024 8:00 AM | December 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 441 | 446d | March 29, 2024 8:00 AM | December 30, 2025 5:00 PM | 441 days | No | 3/29/24 | NA | NA | 0.72999999999999998
3464 | DocGen - Milestone 11 - Form Identification | March 29, 2024 8:00 AM | February 28, 2025 5:00 PM | 660 |  | As Soon As Possible | NA | 231 | 0d | March 29, 2024 8:00 AM | February 28, 2025 5:00 PM | 231 days | No | 3/29/24 | 2/28/25 | NA | 1
3467 | DocGen - Milestone 11 - AEM Design, Review & Approval | April 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 614SS,613SS,612SS | 2535 | As Soon As Possible | NA | 43 | 0d | April 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 43 days | No | 4/1/25 | 5/30/25 | NA | 1
3468 | DocGen - Milestone 11 - AEM Integration (Build/SIT) | June 2, 2025 8:00 AM | November 28, 2025 4:41 PM | 715SS,2534 | 2536FS-84d | As Soon As Possible | NA | 82 | 51.04d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 6/2/25 | NA | NA | 0.73999999999999999
7431 | DocGen - Milestone 11 - QA | October 6, 2025 8:00 AM | December 30, 2025 5:00 PM | 781SS,2535FS-84d | 2537FS-105d | As Soon As Possible | NA | 59 | 51d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | 10/6/25 | NA | NA | 8.0000000000000002E-2
3469 | DocGen - Milestone 11 - Joint Review | October 6, 2025 8:00 AM | December 30, 2025 5:00 PM | 781SS,2536FS-105d |  | As Soon As Possible | NA | 59 | 446d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | 10/6/25 | NA | NA | 8.0000000000000002E-2
3470 | DocGen - Milestone 13 | February 12, 2024 8:00 AM | December 30, 2025 4:22 PM |  |  | As Soon As Possible | NA | 473.92 | 446.08d | February 12, 2024 8:00 AM | December 30, 2025 5:00 PM | 474 days | No | 2/12/24 | NA | NA | 0.78000000000000003
3471 | DocGen - Milestone 13 - Form Identification | February 12, 2024 8:00 AM | February 28, 2025 5:00 PM | 651SS-151d |  | As Soon As Possible | NA | 264 | 0d | February 12, 2024 8:00 AM | February 28, 2025 5:00 PM | 264 days | No | 2/12/24 | 2/28/25 | NA | 1
3474 | DocGen - Milestone 13 - AEM Design, Review & Approval | April 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 614SS,613SS,612SS | 2541 | As Soon As Possible | NA | 43 | 0d | April 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 43 days | No | 4/1/25 | 5/30/25 | NA | 1
3475 | DocGen - Milestone 13 - AEM Integration (Build/SIT) | June 2, 2025 8:00 AM | December 1, 2025 4:22 PM | 709SS,2540 | 2542FS-85d | As Soon As Possible | NA | 83 | 51.08d | June 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 127 days | No | 6/2/25 | NA | NA | 0.72999999999999998
7432 | DocGen - Milestone 13 - QA | July 30, 2025 4:22 PM | December 30, 2025 4:22 PM | 2541FS-85d | 2543FS-105d | As Soon As Possible | NA | 105 | 51.08d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | 7/30/25 | NA | NA | 0.48999999999999999
3476 | DocGen - Milestone 13 - Joint Review | July 30, 2025 4:22 PM | December 30, 2025 4:22 PM | 2542FS-105d |  | As Soon As Possible | NA | 105 | 446.08d | July 31, 2025 8:00 AM | December 30, 2025 5:00 PM | 105 days | No | 7/30/25 | NA | NA | 0.48999999999999999
3477 | DocGen - Milestone 14 | January 3, 2023 8:00 AM | July 15, 2024 5:00 PM |  |  | As Soon As Possible | NA | 384 | 0d | January 3, 2023 8:00 AM | July 15, 2024 5:00 PM | 384 days | No | 1/3/23 | 7/15/24 | NA | 1
3478 | DocGen - Milestone 14 - Form Identification | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 401SS | 2546 | As Soon As Possible | NA | 119 | 0d | January 3, 2023 8:00 AM | June 22, 2023 5:00 PM | 119 days | No | 1/3/23 | 6/22/23 | NA | 1
3479 | DocGen - Milestone 14 - Analysis and Template Design | October 9, 2023 8:00 AM | February 23, 2024 5:00 PM | 405SS,2545 | 2547 | As Soon As Possible | NA | 93 | 0d | October 9, 2023 8:00 AM | February 23, 2024 5:00 PM | 93 days | No | 10/9/23 | 2/23/24 | NA | 1
3480 | DocGen - Milestone 14 - Template Design Review and Approval | October 9, 2023 8:00 AM | February 23, 2024 5:00 PM | 405SS,2546 | 2548 | As Soon As Possible | NA | 93 | 0d | October 9, 2023 8:00 AM | February 23, 2024 5:00 PM | 93 days | No | 10/9/23 | 2/23/24 | NA | 1
3481 | DocGen - Milestone 14 - AEM Design, Review & Approval | October 9, 2023 8:00 AM | February 23, 2024 5:00 PM | 405SS,2547 | 2549 | As Soon As Possible | NA | 93 | 0d | October 9, 2023 8:00 AM | February 23, 2024 5:00 PM | 93 days | No | 10/9/23 | 2/23/24 | NA | 1
3482 | DocGen - Milestone 14 - AEM Integration (Build/SIT) | November 6, 2023 8:00 AM | July 11, 2024 5:00 PM | 407SS,2548 | 2550FS-147d | As Soon As Possible | NA | 169 | 0d | November 6, 2023 8:00 AM | July 11, 2024 5:00 PM | 169 days | No | 11/6/23 | 7/11/24 | NA | 1
7433 | DocGen - Milestone 14 - QA | December 11, 2023 8:00 AM | July 15, 2024 5:00 PM | 411SS,2549FS-147d | 2551FS-149d | As Soon As Possible | NA | 149 | 0d | December 11, 2023 8:00 AM | July 15, 2024 5:00 PM | 149 days | No | 12/11/23 | 7/15/24 | NA | 1
3483 | DocGen - Milestone 14 - Joint Review | December 11, 2023 8:00 AM | July 15, 2024 5:00 PM | 413SS,2550FS-149d |  | As Soon As Possible | NA | 149 | 0d | December 11, 2023 8:00 AM | July 15, 2024 5:00 PM | 149 days | No | 12/11/23 | 7/15/24 | NA | 1
3484 | DocGen - Milestone 15 | January 30, 2023 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 523 | 0d | January 30, 2023 8:00 AM | February 28, 2025 5:00 PM | 523 days | No | 1/30/23 | 2/28/25 | NA | 1
3485 | DocGen - Milestone 15 - Form Identification | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 424SS | 2554 | As Soon As Possible | NA | 85 | 0d | January 30, 2023 8:00 AM | May 31, 2023 5:00 PM | 85 days | No | 1/30/23 | 5/31/23 | NA | 1
3486 | DocGen - Milestone 15 - Analysis and Template Design | September 2, 2024 8:00 AM | September 27, 2024 5:00 PM | 577SS,2553 | 2555FS-20d | As Soon As Possible | NA | 20 | 0d | September 2, 2024 8:00 AM | September 27, 2024 5:00 PM | 20 days | No | 9/2/24 | 9/27/24 | NA | 1
3487 | DocGen - Milestone 15 - Template Design Review and Approval | September 2, 2024 8:00 AM | September 27, 2024 5:00 PM | 577SS,2554FS-20d | 2556FS-20d | As Soon As Possible | NA | 20 | 0d | September 2, 2024 8:00 AM | September 27, 2024 5:00 PM | 20 days | No | 9/2/24 | 9/27/24 | NA | 1
3488 | DocGen - Milestone 15 - AEM Design, Review & Approval | September 2, 2024 8:00 AM | September 27, 2024 5:00 PM | 577SS,2555FS-20d | 2557 | As Soon As Possible | NA | 20 | 0d | September 2, 2024 8:00 AM | September 27, 2024 5:00 PM | 20 days | No | 9/2/24 | 9/27/24 | NA | 1
3489 | DocGen - Milestone 15 - AEM Integration (Build/SIT) | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM | 433SS,2556 | 2558FS-36d | As Soon As Possible | NA | 76 | 0d | October 7, 2024 8:00 AM | January 28, 2025 5:00 PM | 76 days | No | 10/7/24 | 1/28/25 | NA | 1
7434 | DocGen - Milestone 15 - QA | December 5, 2024 8:00 AM | February 28, 2025 5:00 PM | 439SS,2557FS-36d | 2559FS-58d | As Soon As Possible | NA | 58 | 0d | December 5, 2024 8:00 AM | February 28, 2025 5:00 PM | 58 days | No | 12/5/24 | 2/28/25 | NA | 1
3490 | DocGen - Milestone 15 - Joint Review | December 5, 2024 8:00 AM | February 28, 2025 5:00 PM | 442SS,2558FS-58d |  | As Soon As Possible | NA | 58 | 0d | December 5, 2024 8:00 AM | February 28, 2025 5:00 PM | 58 days | No | 12/5/24 | 2/28/25 | NA | 1
3491 | DocGen - Milestone 16 | March 8, 2024 8:00 AM | December 30, 2025 8:38 AM |  |  | As Soon As Possible | NA | 455.08 | 446.92d | March 8, 2024 8:00 AM | December 30, 2025 5:00 PM | 456 days | No | 3/8/24 | NA | NA | 0.82999999999999996
3492 | DocGen - Milestone 16 - Form Identification | March 8, 2024 8:00 AM | January 3, 2025 5:00 PM | 816SS |  | Finish No Earlier Than | 1/3/25 | 208 | 0d | March 8, 2024 8:00 AM | January 3, 2025 5:00 PM | 208 days | No | 3/8/24 | 1/3/25 | NA | 1
3495 | DocGen - Milestone 16 - AEM Design, Review & Approval | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 804SS,803SS,802SS | 2563 | As Soon As Possible | NA | 44 | 0d | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 days | No | 1/27/25 | 3/28/25 | NA | 1
3496 | DocGen - Milestone 16 - AEM Integration (Build/SIT) | April 1, 2025 8:00 AM | November 28, 2025 2:26 PM | 867SS,2562 | 2564FS-127d | As Soon As Possible | NA | 153 | 110.32d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 4/1/25 | NA | NA | 0.81000000000000005
7435 | DocGen - Milestone 16 - QA | May 30, 2025 8:00 AM | December 30, 2025 8:38 AM | 897SS,2563FS-127d | 2565FS-148d | As Soon As Possible | NA | 103 | 110.92d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 5/30/25 | NA | NA | 0.64000000000000001
3497 | DocGen - Milestone 16 - Joint Review | May 30, 2025 8:00 AM | December 30, 2025 8:38 AM | 911SS,2564FS-148d |  | As Soon As Possible | NA | 103 | 446.92d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 5/30/25 | NA | NA | 0.64000000000000001
3498 | DocGen - Milestone 17 | April 26, 2024 8:00 AM | December 30, 2025 8:38 AM |  |  | As Soon As Possible | NA | 421.08 | 446.92d | April 26, 2024 8:00 AM | December 30, 2025 5:00 PM | 422 days | No | 4/26/24 | NA | NA | 0.81999999999999995
3499 | DocGen - Milestone 17 - Form Identification | April 26, 2024 8:00 AM | January 3, 2025 5:00 PM | 825SS |  | As Soon As Possible | NA | 174 | 0d | April 26, 2024 8:00 AM | January 3, 2025 5:00 PM | 174 days | No | 4/26/24 | 1/3/25 | NA | 1
3502 | DocGen - Milestone 17 - AEM Design, Review & Approval | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 804SS,803SS,802SS | 2569 | As Soon As Possible | NA | 44 | 0d | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 days | No | 1/27/25 | 3/28/25 | NA | 1
3503 | DocGen - Milestone 17 - AEM Integration (Build/SIT) | April 1, 2025 8:00 AM | November 28, 2025 2:26 PM | 871SS,2568 | 2570FS-127d | As Soon As Possible | NA | 153 | 110.32d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 4/1/25 | NA | NA | 0.81000000000000005
7436 | DocGen - Milestone 17 - QA | May 30, 2025 8:00 AM | December 30, 2025 8:38 AM | 901SS,2569FS-127d | 2571FS-148d | As Soon As Possible | NA | 103 | 110.92d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 5/30/25 | NA | NA | 0.64000000000000001
3504 | DocGen - Milestone 17 - Joint Review | May 30, 2025 8:00 AM | December 30, 2025 8:38 AM | 916SS,2570FS-148d |  | As Soon As Possible | NA | 103 | 446.92d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 5/30/25 | NA | NA | 0.64000000000000001
3505 | DocGen - Milestone 18 | May 22, 2023 8:00 AM | December 30, 2025 8:38 AM |  |  | As Soon As Possible | NA | 654.08 | 446.92d | May 22, 2023 8:00 AM | December 30, 2025 5:00 PM | 655 days | No | 5/22/23 | NA | NA | 0.87
3506 | DocGen - Milestone 18 - Form Identification | May 22, 2023 8:00 AM | January 3, 2025 5:00 PM | 834SS |  | Finish No Earlier Than | 1/3/25 | 407 | 0d | May 22, 2023 8:00 AM | January 3, 2025 5:00 PM | 407 days | No | 5/22/23 | 1/3/25 | NA | 1
3509 | DocGen - Milestone 18 - AEM Design, Review & Approval | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 804SS,803SS,802SS | 2575 | As Soon As Possible | NA | 44 | 0d | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 days | No | 1/27/25 | 3/28/25 | NA | 1
3510 | DocGen - Milestone 18 - AEM Integration (Build/SIT) | April 1, 2025 8:00 AM | November 28, 2025 2:26 PM | 871SS,2574 | 2576FS-127d | As Soon As Possible | NA | 153 | 110.32d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 4/1/25 | NA | NA | 0.81000000000000005
7437 | DocGen - Milestone 18 - QA | May 30, 2025 8:00 AM | December 30, 2025 8:38 AM | 906SS,2575FS-127d | 2577FS-148d | As Soon As Possible | NA | 103 | 110.92d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 5/30/25 | NA | NA | 0.64000000000000001
3511 | DocGen - Milestone 18 - Joint Review | May 30, 2025 8:00 AM | December 30, 2025 8:38 AM | 922SS,2576FS-148d |  | As Soon As Possible | NA | 103 | 446.92d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 5/30/25 | NA | NA | 0.64000000000000001
3512 | DocGen - Milestone 19 | November 7, 2022 8:00 AM | August 16, 2024 5:00 PM |  |  | As Soon As Possible | NA | 444 | 0d | November 7, 2022 8:00 AM | August 16, 2024 5:00 PM | 444 days | No | 11/7/22 | 8/16/24 | NA | 1
3513 | DocGen - Milestone 19 - Form Identification | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 447SS | 2580 | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
3514 | DocGen - Milestone 19 - Analysis and Template Design | July 17, 2023 8:00 AM | February 23, 2024 5:00 PM | 459SS,2579 | 2581 | As Soon As Possible | NA | 152 | 0d | July 17, 2023 8:00 AM | February 23, 2024 5:00 PM | 152 days | No | 7/17/23 | 2/23/24 | NA | 1
3515 | DocGen - Milestone 19 - Template Design Review and Approval | July 17, 2023 8:00 AM | February 23, 2024 5:00 PM | 459SS,2580 | 2582 | As Soon As Possible | NA | 152 | 0d | July 17, 2023 8:00 AM | February 23, 2024 5:00 PM | 152 days | No | 7/17/23 | 2/23/24 | NA | 1
3516 | DocGen - Milestone 19 - AEM Design, Review & Approval | July 17, 2023 8:00 AM | February 23, 2024 5:00 PM | 459SS,2581 | 2583 | As Soon As Possible | NA | 152 | 0d | July 17, 2023 8:00 AM | February 23, 2024 5:00 PM | 152 days | No | 7/17/23 | 2/23/24 | NA | 1
3517 | DocGen - Milestone 19 - AEM Integration (Build/SIT) | February 26, 2024 8:00 AM | April 22, 2024 5:00 PM | 2582 | 2584 | As Soon As Possible | NA | 40 | 0d | February 26, 2024 8:00 AM | April 22, 2024 5:00 PM | 40 days | No | 2/26/24 | 4/22/24 | NA | 1
7438 | DocGen - Milestone 19 - QA | April 23, 2024 8:00 AM | June 18, 2024 5:00 PM | 2583 | 2585FS+2d | As Soon As Possible | NA | 40 | 0d | April 23, 2024 8:00 AM | June 18, 2024 5:00 PM | 40 days | No | 4/23/24 | 6/18/24 | NA | 1
3518 | DocGen - Milestone 19 - Joint Review | June 21, 2024 8:00 AM | August 16, 2024 5:00 PM | 2584FS+2d |  | As Soon As Possible | NA | 40 | 0d | June 21, 2024 8:00 AM | August 16, 2024 5:00 PM | 40 days | No | 6/21/24 | 8/16/24 | NA | 1
3526 | DocGen - Milestone 21 | June 19, 2024 8:00 AM | December 30, 2025 2:26 PM |  |  | As Soon As Possible | NA | 384.68 | 446.32d | June 19, 2024 8:00 AM | December 29, 2025 5:00 PM | 384 days | No | 6/19/24 | NA | NA | 0.72999999999999998
3527 | DocGen - Milestone 21 - Form Identification | June 19, 2024 8:00 AM | July 12, 2024 5:00 PM | 1212FS+210d |  | As Soon As Possible | NA | 17 | 0d | June 19, 2024 8:00 AM | July 12, 2024 5:00 PM | 17 days | No | 6/19/24 | 7/12/24 | NA | 1
3530 | DocGen - Milestone 21 - AEM Design, Review & Approval | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 1200SS,1199SS,1198SS | 2589 | As Soon As Possible | NA | 44 | 0d | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 days | No | 1/27/25 | 3/28/25 | NA | 1
3531 | DocGen - Milestone 21 - AEM Integration (Build/SIT) | April 1, 2025 8:00 AM | November 28, 2025 2:26 PM | 867SS,2588 | 2590FS-126d | As Soon As Possible | NA | 153 | 93.32d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 4/1/25 | NA | NA | 0.81000000000000005
7439 | DocGen - Milestone 21 - QA | May 30, 2025 2:26 PM | December 30, 2025 2:26 PM | 2589FS-126d | 2591FS-147d | As Soon As Possible | NA | 147 | 93.32d | May 30, 2025 8:00 AM | December 29, 2025 5:00 PM | 147 days | No | 5/30/25 | NA | NA | 0.63
3532 | DocGen - Milestone 21 - Joint Review | May 30, 2025 2:26 PM | December 30, 2025 2:26 PM | 2590FS-147d |  | As Soon As Possible | NA | 147 | 446.32d | May 30, 2025 8:00 AM | December 29, 2025 5:00 PM | 147 days | No | 5/30/25 | NA | NA | 0.63
3533 | DocGen - Milestone 23 | April 26, 2024 8:00 AM | December 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 422 | 446d | April 26, 2024 8:00 AM | December 30, 2025 5:00 PM | 422 days | No | 4/26/24 | NA | NA | 0.69999999999999996
3534 | DocGen - Milestone 23 - Form Identification | April 26, 2024 8:00 AM | April 1, 2025 5:00 PM | 1119SS |  | Finish No Earlier Than | 4/1/25 | 233 | 0d | April 26, 2024 8:00 AM | April 1, 2025 5:00 PM | 233 days | No | 4/26/24 | 4/1/25 | NA | 1
3537 | DocGen - Milestone 23 - AEM Design, Review & Approval | May 12, 2025 8:00 AM | July 11, 2025 5:00 PM | 1098SS,1096SS,1097SS | 2595FS+20d | Finish No Earlier Than | 6/27/25 | 43 | 0d | May 12, 2025 8:00 AM | July 11, 2025 5:00 PM | 43 days | No | 5/12/25 | 7/11/25 | NA | 1
3538 | DocGen - Milestone 23 - AEM Integration (Build/SIT) | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 2594FS+20d | 2596FS-36d | Finish No Earlier Than | 10/3/25 | 77 | 3d | August 11, 2025 8:00 AM | November 28, 2025 5:00 PM | 77 days | No | 8/11/25 | NA | NA | 0.56999999999999995
7440 | DocGen - Milestone 23 - QA | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 2595FS-36d | 2597FS-57d | As Soon As Possible | NA | 57 | 3d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | 10/8/25 | NA | NA | 5.0000000000000003E-2
3539 | DocGen - Milestone 23 - Joint Review | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 2596FS-57d |  | As Soon As Possible | NA | 57 | 446d | October 8, 2025 8:00 AM | December 30, 2025 5:00 PM | 57 days | No | 10/8/25 | NA | NA | 5.0000000000000003E-2
3547 | DocGen - Milestone 26 | March 29, 2024 8:00 AM | December 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 441 | 446d | March 29, 2024 8:00 AM | December 30, 2025 5:00 PM | 441 days | No | 3/29/24 | NA | NA | 0.80000000000000004
3548 | DocGen - Milestone 26 - Form Identification | March 29, 2024 8:00 AM | January 3, 2025 5:00 PM | 952SS |  | Finish No Earlier Than | 1/3/25 | 193 | 0d | March 29, 2024 8:00 AM | January 3, 2025 5:00 PM | 193 days | No | 3/29/24 | 1/3/25 | NA | 1
3551 | DocGen - Milestone 26 - AEM Design, Review & Approval | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 940SS,939SS,938SS | 2601 | As Soon As Possible | NA | 44 | 0d | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 days | No | 1/27/25 | 3/28/25 | NA | 1
3552 | DocGen - Milestone 26 - AEM Integration (Build/SIT) | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 2600 | 2602FS-127d | As Soon As Possible | NA | 169 | 94d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 4/1/25 | NA | NA | 0.80000000000000004
7441 | DocGen - Milestone 26 - QA | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 2601FS-127d | 2603FS-148d | As Soon As Possible | NA | 148 | 94d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 5/30/25 | NA | NA | 0.64000000000000001
3553 | DocGen - Milestone 26 - Joint Review | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 2602FS-148d |  | As Soon As Possible | NA | 148 | 446d | May 30, 2025 8:00 AM | December 30, 2025 5:00 PM | 148 days | No | 5/30/25 | NA | NA | 0.64000000000000001
3554 | DocGen - Milestone 27 | January 25, 2024 8:00 AM | December 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 486 | 446d | January 25, 2024 8:00 AM | December 30, 2025 5:00 PM | 486 days | No | 1/25/24 | NA | NA | 0.81000000000000005
3555 | DocGen - Milestone 27 - Form Identification | January 25, 2024 8:00 AM | January 3, 2025 5:00 PM | 954SS+100d |  | As Soon As Possible | NA | 238 | 0d | January 25, 2024 8:00 AM | January 3, 2025 5:00 PM | 238 days | No | 1/25/24 | 1/3/25 | NA | 1
3558 | DocGen - Milestone 27 - AEM Design, Review & Approval | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 940SS,939SS,938SS | 2607 | As Soon As Possible | NA | 44 | 0d | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 days | No | 1/27/25 | 3/28/25 | NA | 1
3559 | DocGen - Milestone 27 - AEM Integration (Build/SIT) | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 2606 | 2608FS-125d | As Soon As Possible | NA | 169 | 92d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 4/1/25 | NA | NA | 0.80000000000000004
7442 | DocGen - Milestone 27 - QA | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 2607FS-125d | 2609FS-146d | As Soon As Possible | NA | 146 | 92d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | 6/3/25 | NA | NA | 0.63
3560 | DocGen - Milestone 27 - Joint Review | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 2608FS-146d |  | As Soon As Possible | NA | 146 | 446d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | 6/3/25 | NA | NA | 0.63
3561 | DocGen - Milestone 28 | December 9, 2024 8:00 AM | December 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 266 | 446d | September 30, 2024 8:00 AM | December 30, 2025 5:00 PM | 313 days | No | 12/9/24 | NA | NA | 0.72999999999999998
3562 | DocGen - Milestone 28 - Form Identification | December 9, 2024 8:00 AM | January 3, 2025 5:00 PM | 970SS+134d |  | As Soon As Possible | NA | 18 | 0d | December 9, 2024 8:00 AM | January 3, 2025 5:00 PM | 18 days | No | 12/9/24 | 1/3/25 | NA | 1
3565 | DocGen - Milestone 28 - AEM Design, Review & Approval | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 940SS,939SS,938SS | 2613 | As Soon As Possible | NA | 44 | 0d | January 27, 2025 8:00 AM | March 28, 2025 5:00 PM | 44 days | No | 1/27/25 | 3/28/25 | NA | 1
3566 | DocGen - Milestone 28 - AEM Integration (Build/SIT) | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 2612 | 2614FS-125d | As Soon As Possible | NA | 169 | 92d | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM | 169 days | No | 4/1/25 | NA | NA | 0.80000000000000004
3567 | DocGen - Milestone 28 - Joint Review | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 2613FS-125d | 2615FS-146d | As Soon As Possible | NA | 146 | 92d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | 6/3/25 | NA | NA | 0.63
7443 | DocGen - Milestone 28 - QA | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 2614FS-146d |  | As Soon As Possible | NA | 146 | 446d | June 3, 2025 8:00 AM | December 30, 2025 5:00 PM | 146 days | No | 6/3/25 | NA | NA | 0.63
3568 | Knowledge Management | January 3, 2024 8:00 AM | September 29, 2025 5:00 PM |  |  | As Soon As Possible | NA | 438 | 0d | January 3, 2024 8:00 AM | September 29, 2025 5:00 PM | 438 days | No | 1/3/24 | 9/29/25 | NA | 1
3569 | Recommended Training Content Development | January 3, 2024 8:00 AM | April 25, 2024 5:00 PM | 2499SS+1d | 2619 | As Soon As Possible | NA | 79 | 0d | January 3, 2024 8:00 AM | April 25, 2024 5:00 PM | 79 days | No | 1/3/24 | 4/25/24 | NA | 1
3570 | KX Material Development | January 6, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | January 6, 2025 8:00 AM | April 1, 2025 5:00 PM | 59 days | No | 1/6/25 | 4/1/25 | NA | 1
7526 | Design, Deploy, and Manage Form Templates | January 6, 2025 8:00 AM | January 31, 2025 5:00 PM | 2617 | 2620 | Finish No Earlier Than | 1/31/25 | 19 | 0d | January 6, 2025 8:00 AM | January 31, 2025 5:00 PM | 19 days | No | 1/6/25 | 1/31/25 | NA | 1
7527 | CARES Doc Gen Features, Data model | February 3, 2025 8:00 AM | March 3, 2025 5:00 PM | 2619 | 2621 | Start No Earlier Than | 2/3/25 | 20 | 0d | February 3, 2025 8:00 AM | March 3, 2025 5:00 PM | 20 days | No | 2/3/25 | 3/3/25 | NA | 1
7528 | Customizing State Templates to County-Specific Needs | March 4, 2025 8:00 AM | April 1, 2025 5:00 PM | 2620 | 2623 | Start No Earlier Than | 3/4/25 | 20 | 0d | March 4, 2025 8:00 AM | April 1, 2025 5:00 PM | 20 days | No | 3/4/25 | 4/1/25 | NA | 1
3571 | KX sessions | May 5, 2025 8:00 AM | September 29, 2025 5:00 PM |  |  | As Soon As Possible | NA | 103 | 0d | May 5, 2025 8:00 AM | September 29, 2025 5:00 PM | 103 days | No | 5/5/25 | 9/29/25 | NA | 1
7529 | KX Sessions - Session 1 | May 5, 2025 8:00 AM | June 23, 2025 5:00 PM | 2621 | 2624 | Start No Earlier Than | 5/5/25 | 35 | 0d | May 5, 2025 8:00 AM | June 23, 2025 5:00 PM | 35 days | No | 5/5/25 | 6/23/25 | NA | 1
7530 | KX Sessions - Session 2 | June 24, 2025 8:00 AM | August 12, 2025 5:00 PM | 2623 | 2625 | Start No Earlier Than | 6/24/25 | 35 | 0d | June 24, 2025 8:00 AM | August 12, 2025 5:00 PM | 35 days | No | 6/24/25 | 8/12/25 | NA | 1
7531 | KX Sessions - Session 3 | August 13, 2025 8:00 AM | September 29, 2025 5:00 PM | 2624 |  | Start No Earlier Than | 8/13/25 | 33 | 0d | August 13, 2025 8:00 AM | September 29, 2025 5:00 PM | 33 days | No | 8/13/25 | 9/29/25 | NA | 1
3619 | Testing - ADA (CARESV1-5420) | April 4, 2022 8:00 AM | January 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 960 | 425d | April 4, 2022 8:00 AM | January 5, 2026 5:00 PM | 942 days | No | 4/4/22 | NA | NA | 0.34000000000000002
3620 | Setup ADA Validation Infra/ Tools (CARESV1-5420) | April 4, 2022 8:00 AM | May 13, 2022 5:00 PM |  | 2629FS+420d | Start No Earlier Than | 4/4/22 | 30 | 0d | April 4, 2022 8:00 AM | May 13, 2022 5:00 PM | 30 days | No | 4/4/22 | 5/13/22 | NA | 1
3621 | Perform ADA Validation (CARESV1-5421) | January 6, 2025 8:00 AM | January 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 269 | 425d | May 2, 2022 8:00 AM | January 5, 2026 5:00 PM | 922 days | No | 1/6/25 | NA | NA | 0.33000000000000002
3622 | M1: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 2627FS+420d | 2630SS,2631SS,2632SS,2633SS,2634SS,2638SS,2645SS,2649SS,2651SS | Finish No Earlier Than | 3/21/25 | 53 | 0d | May 2, 2022 8:00 AM | May 31, 2022 5:00 PM | 22 days | No | 1/6/25 | 3/21/25 | NA | 1
3623 | M2: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 2629SS |  | Finish No Earlier Than | 3/21/25 | 53 | 0d | June 20, 2022 8:00 AM | July 15, 2022 5:00 PM | 20 days | No | 1/6/25 | 3/21/25 | NA | 1
3624 | M3: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 2629SS |  | Finish No Earlier Than | 3/21/25 | 53 | 0d | July 18, 2022 8:00 AM | August 12, 2022 5:00 PM | 20 days | No | 1/6/25 | 3/21/25 | NA | 1
3625 | M4: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 2629SS |  | Finish No Earlier Than | 3/21/25 | 53 | 0d | August 15, 2022 8:00 AM | September 9, 2022 5:00 PM | 20 days | No | 1/6/25 | 3/21/25 | NA | 1
3626 | M5: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 2629SS |  | Finish No Earlier Than | 3/21/25 | 53 | 0d | September 12, 2022 8:00 AM | October 7, 2022 5:00 PM | 20 days | No | 1/6/25 | 3/21/25 | NA | 1
3627 | M6: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 2629SS | 2635FS-40d,2636FS-40d,2637FS-40d,2639FS-40d,2640FS-40d,2641FS-40d,2642FS-40d,2643FS-40d,2644FS-40d,2646FS-40d,2647FS-40d,2648FS-40d,2650FS-40d,2652FS-40d,2653FS-40d,2654FS-40d,2655FS-40d,2656FS-40d,2657FS-40d,2658FS-40d,2659FS-40d,2660FS-40d,2661FS-40d... | Finish No Earlier Than | 3/21/25 | 53 | 0d | October 10, 2022 8:00 AM | November 4, 2022 5:00 PM | 20 days | No | 1/6/25 | 3/21/25 | NA | 1
3628 | M6.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | November 7, 2022 8:00 AM | December 2, 2022 5:00 PM | 20 days | No | NA | NA | NA | 0
3629 | M7: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | December 5, 2022 8:00 AM | December 30, 2022 5:00 PM | 20 days | No | NA | NA | NA | 0
3630 | M7.1 ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | January 2, 2023 8:00 AM | January 27, 2023 5:00 PM | 20 days | No | NA | NA | NA | 0
3631 | M8: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 2629SS |  | Finish No Earlier Than | 3/21/25 | 53 | 0d | January 30, 2023 8:00 AM | February 24, 2023 5:00 PM | 20 days | No | 1/6/25 | 3/21/25 | NA | 1
3632 | M9: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | February 27, 2023 8:00 AM | March 24, 2023 5:00 PM | 20 days | No | NA | NA | NA | 0
3633 | M10: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | March 27, 2023 8:00 AM | April 21, 2023 5:00 PM | 20 days | No | NA | NA | NA | 0
3634 | M10.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | April 24, 2023 8:00 AM | May 19, 2023 5:00 PM | 20 days | No | NA | NA | NA | 0
3635 | M11: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | May 22, 2023 8:00 AM | June 16, 2023 5:00 PM | 20 days | No | NA | NA | NA | 0
3636 | M13: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | June 19, 2023 8:00 AM | July 14, 2023 5:00 PM | 20 days | No | NA | NA | NA | 0
3637 | M14: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | July 17, 2023 8:00 AM | August 11, 2023 5:00 PM | 20 days | No | NA | NA | NA | 0
3638 | M15: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 2629SS |  | Finish No Earlier Than | 3/21/25 | 53 | 0d | August 14, 2023 8:00 AM | September 8, 2023 5:00 PM | 20 days | No | 1/6/25 | 3/21/25 | NA | 1
3640 | M16: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | October 9, 2023 8:00 AM | November 3, 2023 5:00 PM | 20 days | No | NA | NA | NA | 0
3641 | M17: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | November 6, 2023 8:00 AM | December 1, 2023 5:00 PM | 20 days | No | NA | NA | NA | 0
3642 | M18: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | December 4, 2023 8:00 AM | December 29, 2023 5:00 PM | 20 days | No | NA | NA | NA | 0
3643 | M19: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 2629SS |  | Finish No Earlier Than | 3/21/25 | 53 | 0d | January 1, 2024 8:00 AM | January 26, 2024 5:00 PM | 20 days | No | 1/6/25 | 3/21/25 | NA | 1
3644 | M21: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | January 29, 2024 8:00 AM | February 26, 2024 5:00 PM | 20 days | No | NA | NA | NA | 0
3645 | M20: ADA Accessibility Testing | January 6, 2025 8:00 AM | March 21, 2025 5:00 PM | 2629SS |  | Finish No Earlier Than | 3/21/25 | 53 | 0d | February 27, 2024 8:00 AM | March 25, 2024 5:00 PM | 20 days | No | 1/6/25 | 3/21/25 | NA | 1
3646 | M20.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | March 26, 2024 8:00 AM | April 23, 2024 5:00 PM | 20 days | No | NA | NA | NA | 0
3647 | M23: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | April 24, 2024 8:00 AM | May 21, 2024 5:00 PM | 20 days | No | NA | NA | NA | 0
3648 | M23.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | May 22, 2024 8:00 AM | June 19, 2024 5:00 PM | 20 days | No | NA | NA | NA | 0
3649 | M23.2: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | June 20, 2024 8:00 AM | July 18, 2024 5:00 PM | 20 days | No | NA | NA | NA | 0
3650 | M24: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | July 19, 2024 8:00 AM | August 15, 2024 5:00 PM | 20 days | No | NA | NA | NA | 0
3651 | M26: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | August 16, 2024 8:00 AM | September 12, 2024 5:00 PM | 20 days | No | NA | NA | NA | 0
3652 | M26.1: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | September 13, 2024 8:00 AM | October 10, 2024 5:00 PM | 20 days | No | NA | NA | NA | 0
3653 | M27: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | October 11, 2024 8:00 AM | November 7, 2024 5:00 PM | 20 days | No | NA | NA | NA | 0
3654 | M28: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | November 8, 2024 8:00 AM | December 10, 2024 5:00 PM | 20 days | No | NA | NA | NA | 0
3655 | M29: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | December 11, 2024 8:00 AM | January 9, 2025 5:00 PM | 20 days | No | NA | NA | NA | 0
5536 | M30: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | December 31, 2024 8:00 AM | January 28, 2025 5:00 PM | 19 days | No | NA | NA | NA | 0
5537 | M31: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | January 28, 2025 8:00 AM | February 24, 2025 5:00 PM | 19 days | No | NA | NA | NA | 0
5538 | M32: ADA Accessibility Testing | December 1, 2025 8:00 AM | January 30, 2026 5:00 PM | 2634FS-40d |  | Finish No Earlier Than | 1/30/26 | 42 | 425d | February 25, 2025 8:00 AM | March 21, 2025 5:00 PM | 19 days | No | NA | NA | NA | 0
3656 | Testing - Automation (CARESV1-21622) | December 2, 2024 8:00 AM | January 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 292 | 425d | May 2, 2022 8:00 AM | May 8, 2026 5:00 PM | 1008 days | No | 12/2/24 | NA | NA | 0.46999999999999997
3657 | Create Automation Scripts | December 2, 2024 8:00 AM | December 23, 2025 5:00 PM |  |  | As Soon As Possible | NA | 267 | 450d | May 2, 2022 8:00 AM | February 9, 2026 5:00 PM | 946 days | No | 12/2/24 | NA | NA | 0.51000000000000001
3658 | M1: Create Automation scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM |  | 2668SS,2676SS,2704FS+4d,2744SS,2745SS,2746SS,2747SS,2748SS,2752SS,2780FS+4d,2743SS | Start No Earlier Than | 12/2/24 | 37 | 0d | May 2, 2022 8:00 AM | May 31, 2022 5:00 PM | 22 days | No | 12/2/24 | 1/24/25 | NA | 1
3659 | M2: Create Automation scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 2667SS | 2674SS+8d,2678SS+4d,2685SS+4d,2686SS+4d,2750SS+8d,2754SS+4d,2760SS+4d,2761SS+4d,2762SS+4d,2669SS | Finish No Earlier Than | 12/9/24 | 37 | 0d | June 20, 2022 8:00 AM | July 15, 2022 5:00 PM | 20 days | No | 12/2/24 | 1/24/25 | NA | 1
3660 | M3: Create Automation scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 2668SS | 2670SS | Finish No Earlier Than | 12/2/24 | 37 | 0d | July 18, 2022 8:00 AM | August 12, 2022 5:00 PM | 20 days | No | 12/2/24 | 1/24/25 | NA | 1
3661 | M4: Create Automation scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 2669SS | 2671SS | Finish No Earlier Than | 12/2/24 | 37 | 0d | August 15, 2022 8:00 AM | September 9, 2022 5:00 PM | 20 days | No | 12/2/24 | 1/24/25 | NA | 1
3662 | M5: Create Automation scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 2670SS | 2672SS | Finish No Earlier Than | 12/2/24 | 37 | 0d | September 12, 2022 8:00 AM | October 7, 2022 5:00 PM | 20 days | No | 12/2/24 | 1/24/25 | NA | 1
3663 | M6: Create Automation scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 2671SS | 2673,2749 | Finish No Earlier Than | 12/2/24 | 42 | 0d | October 10, 2022 8:00 AM | November 4, 2022 5:00 PM | 20 days | No | 12/2/24 | 1/31/25 | NA | 1
3664 | M6.1: Create Automation scripts | October 21, 2025 8:00 AM | December 23, 2025 5:00 PM | 2672 | 2688SS-10d,2710FS+6d,2711FS+6d,2712FS+6d,2714FS+6d,2715FS+6d,2716FS+6d,2717FS+6d,2718FS+6d,2719FS+6d,2721FS+6d,2722FS+6d,2723FS+6d,2725FS+6d,2727FS+6d,2728FS+6d,2729FS+6d,2730FS+6d,2731FS+6d,2732FS+6d,2733FS+6d,2734FS+6d,2735FS+6d,2736FS+6d,2737FS+6d,2... | Finish No Earlier Than | 12/23/25 | 44 | 425d | November 7, 2022 8:00 AM | December 2, 2022 5:00 PM | 20 days | No | NA | NA | NA | 0
3665 | M7: Create Automation scripts | September 26, 2025 8:00 AM | December 19, 2025 5:00 PM | 2668SS+8d | 2675SS-92d,2751SS-92d | Finish No Earlier Than | 12/19/25 | 59 | 452d | December 5, 2022 8:00 AM | December 30, 2022 5:00 PM | 20 days | No | 9/26/25 | NA | NA | 0.10000000000000001
3666 | M7.1 Create Automation scripts | May 16, 2025 8:00 AM | October 31, 2025 5:00 PM | 2674SS-92d | 2677SS-20d,2679SS-20d,2682SS-20d,2753SS-20d,2755SS-20d,2758SS-20d | Finish No Earlier Than | 10/31/25 | 118 | 485d | January 2, 2023 8:00 AM | January 27, 2023 5:00 PM | 20 days | No | 5/16/25 | NA | NA | 0.82999999999999996
3667 | M8: Create Automation scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 2667SS | 2683SS,2687SS,2689SS,2759SS,2763SS,2765SS | Finish No Earlier Than | 12/20/24 | 42 | 0d | January 30, 2023 8:00 AM | February 24, 2023 5:00 PM | 20 days | No | 12/2/24 | 1/31/25 | NA | 1
3668 | M9: Create Automation scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 2675SS-20d |  | Finish No Earlier Than | 12/23/25 | 173 | 450d | February 27, 2023 8:00 AM | March 24, 2023 5:00 PM | 20 days | No | 4/18/25 | NA | NA | 0.68000000000000005
3669 | M10: Create Automation scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 2668SS+4d | 2680SS-23d,2681SS-23d,2756SS-23d,2757SS-23d | Finish No Earlier Than | 12/23/25 | 71 | 450d | March 27, 2023 8:00 AM | April 21, 2023 5:00 PM | 20 days | No | 9/12/25 | NA | NA | 0.23000000000000001
3670 | M10.1: Create Automation scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 2675SS-20d |  | Finish No Earlier Than | 12/23/25 | 173 | 450d | April 24, 2023 8:00 AM | May 19, 2023 5:00 PM | 20 days | No | 4/18/25 | NA | NA | 0.68000000000000005
3671 | M11: Create Automation scripts | August 11, 2025 8:00 AM | December 23, 2025 5:00 PM | 2678SS-23d |  | Finish No Earlier Than | 12/23/25 | 94 | 450d | May 22, 2023 8:00 AM | June 16, 2023 5:00 PM | 20 days | No | 8/11/25 | NA | NA | 0.40999999999999998
3672 | M13: Create Automation scripts | August 11, 2025 8:00 AM | December 23, 2025 5:00 PM | 2678SS-23d |  | Finish No Earlier Than | 12/23/25 | 94 | 450d | June 19, 2023 8:00 AM | July 14, 2023 5:00 PM | 20 days | No | 8/11/25 | NA | NA | 0.40999999999999998
3673 | M14: Create Automation scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 2675SS-20d |  | Finish No Earlier Than | 12/23/25 | 173 | 450d | July 17, 2023 8:00 AM | August 11, 2023 5:00 PM | 20 days | No | 4/18/25 | NA | NA | 0.68000000000000005
3674 | M15: Create Automation scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 2676SS | 2684FS+154d | Finish No Earlier Than | 12/27/24 | 42 | 0d | August 14, 2023 8:00 AM | September 8, 2023 5:00 PM | 20 days | No | 12/2/24 | 1/31/25 | NA | 1
3676 | M16: Create Automation scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 2683FS+154d | 2690SS+3d,2766SS+3d | As Soon As Possible | NA | 71 | 450d | October 9, 2023 8:00 AM | November 3, 2023 5:00 PM | 20 days | No | 9/12/25 | NA | NA | 0.23000000000000001
3677 | M17: Create Automation scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 2668SS+4d |  | Finish No Earlier Than | 12/23/25 | 71 | 450d | November 6, 2023 8:00 AM | December 1, 2023 5:00 PM | 20 days | No | 9/12/25 | NA | NA | 0.23000000000000001
3678 | M18: Create Automation scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 2668SS+4d |  | Finish No Earlier Than | 12/23/25 | 71 | 450d | December 4, 2023 8:00 AM | December 29, 2023 5:00 PM | 20 days | No | 9/12/25 | NA | NA | 0.23000000000000001
3679 | M19: Create Automation scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 2676SS |  | Finish No Earlier Than | 1/3/25 | 42 | 0d | November 27, 2023 8:00 AM | January 18, 2024 5:00 PM | 36 days | No | 12/2/24 | 1/31/25 | NA | 1
3680 | M21: Create Automation scripts | October 14, 2025 8:00 AM | December 23, 2025 5:00 PM | 2673SS-10d |  | Finish No Earlier Than | 12/23/25 | 49 | 450d | February 18, 2025 8:00 AM | April 14, 2025 5:00 PM | 39 days | No | NA | NA | NA | 0
3681 | M20: Create Automation scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 2676SS |  | Finish No Earlier Than | 1/3/25 | 42 | 0d | May 14, 2025 8:00 AM | February 6, 2026 5:00 PM | 185 days | No | 12/2/24 | 1/31/25 | NA | 1
3682 | M20.1: Create Automation scripts | September 17, 2025 8:00 AM | December 23, 2025 5:00 PM | 2684SS+3d | 2691SS-7d,2692SS-7d,2693SS-7d,2699SS-7d,2700SS-7d,2701SS-7d,2767SS-7d,2768SS-7d,2769SS-7d,2775SS-7d,2776SS-7d,2777SS-7d | Finish No Earlier Than | 12/23/25 | 68 | 450d | March 7, 2024 8:00 AM | June 28, 2024 5:00 PM | 80 days | No | 9/17/25 | NA | NA | 0.19
3683 | M23: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 2690SS-7d |  | Finish No Earlier Than | 12/23/25 | 75 | 450d | March 21, 2024 8:00 AM | December 13, 2024 5:00 PM | 186 days | No | 9/8/25 | NA | NA | 0.27000000000000002
3684 | M23.1: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 2690SS-7d |  | Finish No Earlier Than | 12/23/25 | 75 | 450d | July 14, 2025 8:00 AM | February 6, 2026 5:00 PM | 144 days | No | 9/8/25 | NA | NA | 0.27000000000000002
3685 | M23.2: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 2690SS-7d | 2694SS-33d,2695SS-33d,2696SS-33d,2697SS-33d,2698SS-33d,2770SS-33d,2771SS-33d,2772SS-33d,2773SS-33d,2774SS-33d | Finish No Earlier Than | 12/23/25 | 75 | 450d | February 14, 2025 8:00 AM | August 22, 2025 5:00 PM | 132 days | No | 9/8/25 | NA | NA | 0.27000000000000002
3686 | M24: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 2693SS-33d |  | Finish No Earlier Than | 12/23/25 | 108 | 450d | July 14, 2025 8:00 AM | February 6, 2026 5:00 PM | 144 days | No | 7/22/25 | NA | NA | 0.48999999999999999
3687 | M26: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 2693SS-33d |  | Finish No Earlier Than | 12/23/25 | 108 | 450d | July 14, 2025 8:00 AM | February 6, 2026 5:00 PM | 144 days | No | 7/22/25 | NA | NA | 0.48999999999999999
3688 | M26.1: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 2693SS-33d |  | Finish No Earlier Than | 12/23/25 | 108 | 450d | December 21, 2023 8:00 AM | September 16, 2024 5:00 PM | 186 days | No | 7/22/25 | NA | NA | 0.48999999999999999
3689 | M27: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 2693SS-33d |  | Finish No Earlier Than | 12/23/25 | 108 | 450d | November 18, 2024 8:00 AM | April 8, 2025 5:00 PM | 95 days | No | 7/22/25 | NA | NA | 0.48999999999999999
3690 | M28: Create Automation scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 2693SS-33d |  | Finish No Earlier Than | 12/23/25 | 108 | 450d | May 13, 2025 8:00 AM | February 6, 2026 5:00 PM | 186 days | No | 7/22/25 | NA | NA | 0.48999999999999999
3691 | M29: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 2690SS-7d |  | Finish No Earlier Than | 12/23/25 | 75 | 450d | May 13, 2025 8:00 AM | February 6, 2026 5:00 PM | 186 days | No | 9/8/25 | NA | NA | 0.27000000000000002
3692 | M30: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 2690SS-7d |  | Finish No Earlier Than | 12/23/25 | 75 | 450d | May 14, 2025 8:00 AM | February 9, 2026 5:00 PM | 186 days | No | 9/8/25 | NA | NA | 0.27000000000000002
3693 | M31: Create Automation scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 2690SS-7d | 2702SS-1d,2778SS-1d | Finish No Earlier Than | 12/23/25 | 75 | 450d | November 18, 2024 8:00 AM | April 8, 2025 5:00 PM | 95 days | No | 9/8/25 | NA | NA | 0.27000000000000002
3694 | M32: Create Automation scripts | September 5, 2025 8:00 AM | November 28, 2025 5:00 PM | 2701SS-1d |  | Finish No Earlier Than | 11/28/25 | 59 | 467d | November 18, 2024 8:00 AM | April 8, 2025 5:00 PM | 95 days | No | 9/5/25 | NA | NA | 0.35999999999999999
3704 | Execute Automation Scripts | January 31, 2025 8:00 AM | January 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 251 | 425d | May 2, 2022 8:00 AM | May 8, 2026 5:00 PM | 1008 days | No | 1/31/25 | NA | NA | 0.31
3705 | M1: Execute Automation scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 2667FS+4d | 2705SS,2706SS,2707SS,2708SS,2709SS+5d | Finish No Earlier Than | 1/6/25 | 20 | 0d | May 2, 2022 8:00 AM | May 31, 2022 5:00 PM | 21 days | No | 1/31/25 | 2/28/25 | NA | 1
3706 | M2: Execute Automation scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 2704SS | 2713SS+5d,2789SS+5d | Start No Earlier Than | 12/16/24 | 20 | 0d | June 20, 2022 8:00 AM | July 15, 2022 5:00 PM | 19 days | No | 1/31/25 | 2/28/25 | NA | 1
3707 | M3: Execute Automation scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 2704SS |  | Finish No Earlier Than | 1/6/25 | 20 | 0d | July 18, 2022 8:00 AM | August 12, 2022 5:00 PM | 20 days | No | 1/31/25 | 2/28/25 | NA | 1
3708 | M4: Execute Automation scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 2704SS |  | Start No Earlier Than | 12/9/24 | 20 | 0d | August 15, 2022 8:00 AM | September 9, 2022 5:00 PM | 19 days | No | 1/31/25 | 2/28/25 | NA | 1
3709 | M5: Execute Automation scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 2704SS |  | Finish No Earlier Than | 1/6/25 | 20 | 0d | September 12, 2022 8:00 AM | October 7, 2022 5:00 PM | 20 days | No | 1/31/25 | 2/28/25 | NA | 1
3710 | M6: Execute Automation scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 2704SS+5d | 2720SS | Finish No Earlier Than | 1/6/25 | 25 | 0d | October 10, 2022 8:00 AM | November 4, 2022 5:00 PM | 20 days | No | 2/7/25 | 3/14/25 | NA | 1
3711 | M6.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | November 7, 2022 8:00 AM | December 2, 2022 5:00 PM | 17 days | No | NA | NA | NA | 0
3712 | M7: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | December 5, 2022 8:00 AM | December 30, 2022 5:00 PM | 19 days | No | NA | NA | NA | 0
3713 | M7.1 Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | January 3, 2023 8:00 AM | January 27, 2023 5:00 PM | 18 days | No | NA | NA | NA | 0
3714 | M8: Execute Automation scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 2705SS+5d |  | Start No Earlier Than | 12/27/24 | 25 | 0d | January 30, 2023 8:00 AM | February 24, 2023 5:00 PM | 19 days | No | 2/7/25 | 3/14/25 | NA | 1
3715 | M9: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | February 27, 2023 8:00 AM | March 24, 2023 5:00 PM | 20 days | No | NA | NA | NA | 0
3716 | M10: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | March 27, 2023 8:00 AM | April 21, 2023 5:00 PM | 19 days | No | NA | NA | NA | 0
3717 | M10.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | April 24, 2023 8:00 AM | May 19, 2023 5:00 PM | 20 days | No | NA | NA | NA | 0
3718 | M11: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | May 22, 2023 8:00 AM | June 16, 2023 5:00 PM | 19 days | No | NA | NA | NA | 0
3719 | M13: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | June 19, 2023 8:00 AM | July 14, 2023 5:00 PM | 19 days | No | NA | NA | NA | 0
3720 | M14: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | July 17, 2023 8:00 AM | August 11, 2023 5:00 PM | 20 days | No | NA | NA | NA | 0
3721 | M15: Execute Automation scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 2709SS | 2724SS,2726SS | Finish No Earlier Than | 1/31/25 | 25 | 0d | August 14, 2023 8:00 AM | September 8, 2023 5:00 PM | 19 days | No | 2/7/25 | 3/14/25 | NA | 1
3723 | M16: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | October 9, 2023 8:00 AM | November 3, 2023 5:00 PM | 20 days | No | NA | NA | NA | 0
3724 | M17: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | November 6, 2023 8:00 AM | December 1, 2023 5:00 PM | 17 days | No | NA | NA | NA | 0
3725 | M18: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | December 4, 2023 8:00 AM | December 29, 2023 5:00 PM | 19 days | No | NA | NA | NA | 0
3726 | M19: Execute Automation scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 2720SS |  | Start No Earlier Than | 1/10/25 | 25 | 0d | January 26, 2024 8:00 AM | February 23, 2024 5:00 PM | 20 days | No | 2/7/25 | 3/14/25 | NA | 1
3727 | M21: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | April 21, 2025 8:00 AM | May 19, 2025 5:00 PM | 21 days | No | NA | NA | NA | 0
3728 | M20: Execute Automation scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 2720SS |  | Finish No Earlier Than | 2/7/25 | 25 | 0d | February 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 59 days | No | 2/7/25 | 3/14/25 | NA | 1
3729 | M20.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | September 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 83 days | No | NA | NA | NA | 0
3730 | M23: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | December 20, 2024 8:00 AM | March 18, 2025 5:00 PM | 59 days | No | NA | NA | NA | 0
3731 | M23.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | February 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 59 days | No | NA | NA | NA | 0
3732 | M23.2: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | August 29, 2025 8:00 AM | December 31, 2025 5:00 PM | 85 days | No | NA | NA | NA | 0
3733 | M24: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | February 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 59 days | No | NA | NA | NA | 0
3734 | M26: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | February 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 59 days | No | NA | NA | NA | 0
3735 | M26.1: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | September 23, 2024 8:00 AM | December 17, 2024 5:00 PM | 59 days | No | NA | NA | NA | 0
3736 | M27: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | April 16, 2025 8:00 AM | June 30, 2025 5:00 PM | 53 days | No | NA | NA | NA | 0
3737 | M28: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | February 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 59 days | No | NA | NA | NA | 0
3738 | M29: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | February 13, 2026 8:00 AM | May 8, 2026 5:00 PM | 59 days | No | NA | NA | NA | 0
3739 | M30: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | February 17, 2026 8:00 AM | May 1, 2026 5:00 PM | 53 days | No | NA | NA | NA | 0
3740 | M31: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | April 15, 2025 8:00 AM | May 1, 2026 5:00 PM | 264 days | No | NA | NA | NA | 0
3741 | M32: Execute Automation scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | April 15, 2025 8:00 AM | May 1, 2026 5:00 PM | 264 days | No | NA | NA | NA | 0
3777 | Testing - Performance (CARESV1-22880) | September 1, 2022 8:00 AM | January 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 854 | 425d | September 1, 2022 8:00 AM | June 2, 2026 5:00 PM | 938 days | No | 9/1/22 | NA | NA | 0.48999999999999999
3778 | Performance Test Plan | September 1, 2022 8:00 AM | March 1, 2023 5:00 PM |  |  | Finish No Earlier Than | 2/28/23 | 130 | 0d | September 1, 2022 8:00 AM | March 1, 2023 5:00 PM | 130 days | No | 9/1/22 | 3/1/23 | NA | 1
3779 | Create Performance Testing Scripts | December 2, 2024 8:00 AM | December 23, 2025 5:00 PM |  |  | As Soon As Possible | NA | 267 | 450d | March 2, 2023 8:00 AM | January 2, 2026 5:00 PM | 713 days | No | 12/2/24 | NA | NA | 0.51000000000000001
5480 | M1: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 2667SS |  | Finish No Earlier Than | 12/2/24 | 37 | 0d | March 2, 2023 8:00 AM | April 13, 2023 5:00 PM | 30 days | No | 12/2/24 | 1/24/25 | NA | 1
5481 | M2: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 2667SS |  | Finish No Earlier Than | 12/9/24 | 37 | 0d | April 27, 2023 8:00 AM | June 8, 2023 5:00 PM | 30 days | No | 12/2/24 | 1/24/25 | NA | 1
5482 | M3: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 2667SS |  | Finish No Earlier Than | 12/2/24 | 37 | 0d | June 22, 2023 8:00 AM | August 3, 2023 5:00 PM | 30 days | No | 12/2/24 | 1/24/25 | NA | 1
5483 | M4: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 2667SS |  | Finish No Earlier Than | 12/2/24 | 37 | 0d | November 30, 2023 8:00 AM | January 25, 2024 5:00 PM | 38 days | No | 12/2/24 | 1/24/25 | NA | 1
5484 | M5: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 24, 2025 5:00 PM | 2667SS |  | Finish No Earlier Than | 12/2/24 | 37 | 0d | February 8, 2024 8:00 AM | April 4, 2024 5:00 PM | 39 days | No | 12/2/24 | 1/24/25 | NA | 1
5485 | M6: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 2667SS |  | Finish No Earlier Than | 12/2/24 | 42 | 0d | May 1, 2024 8:00 AM | June 28, 2024 5:00 PM | 42 days | No | 12/2/24 | 1/31/25 | NA | 1
5655 | M6.1: Create Performance Testing scripts | October 21, 2025 8:00 AM | December 23, 2025 5:00 PM | 2672 |  | Finish No Earlier Than | 12/23/25 | 44 | 450d | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 days | No | NA | NA | NA | 0
5656 | M7: Create Performance Testing scripts | September 26, 2025 8:00 AM | December 19, 2025 5:00 PM | 2668SS+8d |  | Finish No Earlier Than | 12/19/25 | 59 | 452d | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 148 days | No | 9/26/25 | NA | NA | 0.10000000000000001
5486 | M7.1 Create Performance Testing scripts | May 16, 2025 8:00 AM | October 31, 2025 5:00 PM | 2674SS-92d |  | Finish No Earlier Than | 10/31/25 | 118 | 485d | May 1, 2024 8:00 AM | June 28, 2024 5:00 PM | 42 days | No | 5/16/25 | NA | NA | 0.82999999999999996
5487 | M8: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 2667SS |  | Finish No Earlier Than | 12/20/24 | 42 | 0d | October 13, 2023 8:00 AM | May 17, 2024 5:00 PM | 148 days | No | 12/2/24 | 1/31/25 | NA | 1
5488 | M9: Create Performance Testing scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 2675SS-20d |  | Finish No Earlier Than | 12/23/25 | 173 | 450d | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 148 days | No | 4/18/25 | NA | NA | 0.68000000000000005
5489 | M10: Create Performance Testing scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 2668SS+4d |  | Finish No Earlier Than | 12/23/25 | 71 | 450d | December 2, 2024 8:00 AM | March 28, 2025 5:00 PM | 81 days | No | 9/12/25 | NA | NA | 0.23000000000000001
5490 | M10.1: Create Performance Testing scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 2675SS-20d |  | Finish No Earlier Than | 12/23/25 | 173 | 450d | September 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 84 days | No | 4/18/25 | NA | NA | 0.68000000000000005
5491 | M11: Create Performance Testing scripts | August 11, 2025 8:00 AM | December 23, 2025 5:00 PM | 2678SS-23d |  | Finish No Earlier Than | 12/23/25 | 94 | 450d | December 2, 2024 8:00 AM | March 28, 2025 5:00 PM | 81 days | No | 8/11/25 | NA | NA | 0.40999999999999998
5492 | M13: Create Performance Testing scripts | August 11, 2025 8:00 AM | December 23, 2025 5:00 PM | 2678SS-23d |  | Finish No Earlier Than | 12/23/25 | 94 | 450d | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 148 days | No | 8/11/25 | NA | NA | 0.40999999999999998
5493 | M14: Create Performance Testing scripts | April 18, 2025 8:00 AM | December 23, 2025 5:00 PM | 2675SS-20d |  | Finish No Earlier Than | 12/23/25 | 173 | 450d | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 148 days | No | 4/18/25 | NA | NA | 0.68000000000000005
5494 | M15: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 2676SS |  | Finish No Earlier Than | 12/27/24 | 42 | 0d | June 3, 2025 8:00 AM | January 2, 2026 5:00 PM | 148 days | No | 12/2/24 | 1/31/25 | NA | 1
5496 | M16: Create Performance Testing scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 2668SS+4d |  | Finish No Earlier Than | 12/23/25 | 71 | 450d | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 148 days | No | 9/12/25 | NA | NA | 0.23000000000000001
5497 | M17: Create Performance Testing scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 2668SS+4d |  | Finish No Earlier Than | 12/23/25 | 71 | 450d | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 64 days | No | 9/12/25 | NA | NA | 0.23000000000000001
5498 | M18: Create Performance Testing scripts | September 12, 2025 8:00 AM | December 23, 2025 5:00 PM | 2668SS+4d |  | Finish No Earlier Than | 12/23/25 | 71 | 450d | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 42 days | No | 9/12/25 | NA | NA | 0.23000000000000001
5499 | M19: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 2676SS |  | Finish No Earlier Than | 1/3/25 | 42 | 0d | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 148 days | No | 12/2/24 | 1/31/25 | NA | 1
5500 | M21: Create Performance Testing scripts | October 14, 2025 8:00 AM | December 23, 2025 5:00 PM | 2673SS-10d |  | Finish No Earlier Than | 12/23/25 | 49 | 450d | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 148 days | No | NA | NA | NA | 0
5501 | M20: Create Performance Testing scripts | December 2, 2024 8:00 AM | January 31, 2025 5:00 PM | 2676SS |  | Finish No Earlier Than | 1/3/25 | 42 | 0d | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 148 days | No | 12/2/24 | 1/31/25 | NA | 1
5502 | M20.1: Create Performance Testing scripts | September 17, 2025 8:00 AM | December 23, 2025 5:00 PM | 2684SS+3d |  | Finish No Earlier Than | 12/23/25 | 68 | 450d | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 148 days | No | 9/17/25 | NA | NA | 0.19
5503 | M23: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 2690SS-7d |  | Finish No Earlier Than | 12/23/25 | 75 | 450d | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 148 days | No | 9/8/25 | NA | NA | 0.27000000000000002
5504 | M23.1: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 2690SS-7d |  | Finish No Earlier Than | 12/23/25 | 75 | 450d | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 148 days | No | 9/8/25 | NA | NA | 0.27000000000000002
3791 | M23.2: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 2690SS-7d |  | Start No Earlier Than | 9/8/25 | 75 | 450d | August 10, 2023 8:00 AM | June 2, 2026 5:00 PM | 704 days | No | 9/8/25 | NA | NA | 0.27000000000000002
5509 | M24: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 2693SS-33d |  | Finish No Earlier Than | 12/23/25 | 108 | 450d | August 10, 2023 8:00 AM | September 7, 2023 5:00 PM | 20 days | No | 7/22/25 | NA | NA | 0.48999999999999999
5510 | M26: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 2693SS-33d |  | Finish No Earlier Than | 12/23/25 | 108 | 450d | September 14, 2023 8:00 AM | October 11, 2023 5:00 PM | 20 days | No | 7/22/25 | NA | NA | 0.48999999999999999
5511 | M26.1: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 2693SS-33d |  | Finish No Earlier Than | 12/23/25 | 108 | 450d | October 19, 2023 8:00 AM | November 16, 2023 5:00 PM | 20 days | No | 7/22/25 | NA | NA | 0.48999999999999999
5512 | M27: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 2693SS-33d |  | Finish No Earlier Than | 12/23/25 | 108 | 450d | April 11, 2024 8:00 AM | May 9, 2024 5:00 PM | 21 days | No | 7/22/25 | NA | NA | 0.48999999999999999
5513 | M28: Create Performance Testing scripts | July 22, 2025 8:00 AM | December 23, 2025 5:00 PM | 2693SS-33d |  | Finish No Earlier Than | 12/23/25 | 108 | 450d | May 16, 2024 8:00 AM | July 1, 2024 5:00 PM | 32 days | No | 7/22/25 | NA | NA | 0.48999999999999999
5514 | M29: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 2690SS-7d |  | Finish No Earlier Than | 12/23/25 | 75 | 450d | July 29, 2024 8:00 AM | November 21, 2024 5:00 PM | 83 days | No | 9/8/25 | NA | NA | 0.27000000000000002
5657 | M30: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 2690SS-7d |  | Finish No Earlier Than | 12/23/25 | 75 | 450d | March 3, 2025 8:00 AM | June 30, 2025 5:00 PM | 84 days | No | 9/8/25 | NA | NA | 0.27000000000000002
5658 | M31: Create Performance Testing scripts | September 8, 2025 8:00 AM | December 23, 2025 5:00 PM | 2690SS-7d |  | Finish No Earlier Than | 12/23/25 | 75 | 450d | February 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 83 days | No | 9/8/25 | NA | NA | 0.27000000000000002
5515 | M32: Create Performance Testing scripts | September 5, 2025 8:00 AM | November 28, 2025 5:00 PM | 2701SS-1d |  | Finish No Earlier Than | 11/28/25 | 59 | 467d | September 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 83 days | No | 9/5/25 | NA | NA | 0.35999999999999999
11631 | Execute Performance Testing Scripts | January 31, 2025 8:00 AM | January 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 251 | 425d | NA | NA | 0 days? | No | 1/31/25 | NA | NA | 0.31
5516 | M1: Execute Performance Testing scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 2667FS+4d | 2781SS,2782SS,2783SS,2784SS,2785SS+5d | Finish No Earlier Than | 1/6/25 | 20 | 0d | June 18, 2024 8:00 AM | October 11, 2024 5:00 PM | 83 days | No | 1/31/25 | 2/28/25 | NA | 1
5517 | M2: Execute Performance Testing scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 2780SS |  | Finish No Earlier Than | 1/13/25 | 20 | 0d | February 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 83 days | No | 1/31/25 | 2/28/25 | NA | 1
5518 | M3: Execute Performance Testing scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 2780SS |  | Finish No Earlier Than | 1/6/25 | 20 | 0d | February 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 83 days | No | 1/31/25 | 2/28/25 | NA | 1
5519 | M4: Execute Performance Testing scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 2780SS |  | Finish No Earlier Than | 1/6/25 | 20 | 0d | February 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 83 days | No | 1/31/25 | 2/28/25 | NA | 1
5520 | M5: Execute Performance Testing scripts | January 31, 2025 8:00 AM | February 28, 2025 5:00 PM | 2780SS |  | Finish No Earlier Than | 1/6/25 | 20 | 0d | February 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 83 days | No | 1/31/25 | 2/28/25 | NA | 1
5521 | M6: Execute Performance Testing scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 2780SS+5d |  | Finish No Earlier Than | 1/6/25 | 25 | 0d | February 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 83 days | No | 2/7/25 | 3/14/25 | NA | 1
5522 | M6.1: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | February 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 83 days | No | NA | NA | NA | 0
5523 | M7: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | February 3, 2026 8:00 AM | June 2, 2026 5:00 PM | 83 days | No | NA | NA | NA | 0
5524 | M7.1 Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | February 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 83 days | No | NA | NA | NA | 0
5525 | M8: Execute Performance Testing scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 2705SS+5d | 2796SS | Finish No Earlier Than | 1/24/25 | 25 | 0d | February 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 83 days | No | 2/7/25 | 3/14/25 | NA | 1
5526 | M9: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | September 2, 2025 8:00 AM | December 31, 2025 5:00 PM | 84 days | No | NA | NA | NA | 0
5527 | M10: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | March 3, 2025 8:00 AM | June 30, 2025 5:00 PM | 84 days | No | NA | NA | NA | 0
5528 | M10.1: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | February 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 83 days | No | NA | NA | NA | 0
5529 | M11: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | February 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 83 days | No | NA | NA | NA | 0
5530 | M13: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | February 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 83 days | No | NA | NA | NA | 0
5531 | M14: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | Finish No Earlier Than | 1/30/26 | 19 | 425d | February 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 83 days | No | NA | NA | NA | 0
5532 | M15: Execute Performance Testing scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 2789SS | 2800SS | Finish No Earlier Than | 1/31/25 | 25 | 0d | February 2, 2026 8:00 AM | June 1, 2026 5:00 PM | 83 days | No | 2/7/25 | 3/14/25 | NA | 1
11632 | M16: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
11633 | M17: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
11634 | M18: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
11635 | M19: Execute Performance Testing scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM | 2796SS |  | As Soon As Possible | NA | 25 | 0d | NA | NA | 0 days? | No | 2/7/25 | 3/14/25 | NA | 1
11636 | M21: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
11637 | M20: Execute Performance Testing scripts | February 7, 2025 8:00 AM | March 14, 2025 5:00 PM |  |  | As Soon As Possible | NA | 25 | 0d | NA | NA | 0 days? | No | 2/7/25 | 3/14/25 | NA | 1
11638 | M20.1: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
11639 | M23: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
11640 | M23.1: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
11641 | M23.2: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
11642 | M24: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
11643 | M26: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
11644 | M26.1: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
11645 | M27: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
11646 | M28: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
11647 | M29: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
11648 | M30: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
11649 | M31: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
11650 | M32: Execute Performance Testing scripts | January 5, 2026 8:00 AM | January 30, 2026 5:00 PM | 2673FS+6d |  | As Soon As Possible | NA | 19 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
3804 | Systems Integration | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM |  |  | As Soon As Possible | NA | 1252 | 104d | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1252 days | No | 4/1/21 | NA | NA | 0.93999999999999995
3805 | Schedule Management (CARESV1-14443) | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 12SS-240d | 1855,2818SS | As Soon As Possible | NA | 1261 | 104d | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1261 days | No | 4/1/21 | NA | NA | 0.91000000000000003
3806 | Quality Management (CARESV1-14448) | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 2817SS | 1855,2819SS | Finish No Earlier Than | 3/27/26 | 1261 | 104d | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1261 days | No | 4/1/21 | NA | NA | 0.91000000000000003
3807 | Product Strategy (CARESV1-14458) | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 2818SS | 1855,2820SS | Finish No Earlier Than | 3/27/26 | 1261 | 104d | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1261 days | No | 4/1/21 | NA | NA | 0.91000000000000003
3808 | SDLC Advisory (CARESV1-14459) | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 2819SS | 1855,2822SS | Finish No Earlier Than | 3/27/26 | 1261 | 104d | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1261 days | No | 4/1/21 | NA | NA | 0.91000000000000003
3809 | Risk Management | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM |  |  | As Soon As Possible | NA | 1252 | 104d | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1252 days | No | 4/1/21 | NA | NA | 0.91000000000000003
3810 | Risk identification and tracking (CARESV1-14439) | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 2820SS | 1855,2823SS | Finish No Earlier Than | 3/27/26 | 1261 | 104d | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1261 days | No | 4/1/21 | NA | NA | 0.91000000000000003
3811 | Risk analysis (CARESV1-14440) | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 2822SS | 1855,2824SS | Finish No Earlier Than | 3/27/26 | 1261 | 104d | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1261 days | No | 4/1/21 | NA | NA | 0.91000000000000003
3812 | Risk mitigation (CARESV1-14441) | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 2823SS | 1855,2825SS | Finish No Earlier Than | 3/27/26 | 1261 | 104d | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1261 days | No | 4/1/21 | NA | NA | 0.91000000000000003
3813 | Risk reporting (CARESV1-14442) | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 2824SS | 1855,2827SS | Finish No Earlier Than | 3/27/26 | 1261 | 104d | April 1, 2021 8:00 AM | March 27, 2026 5:00 PM | 1261 days | No | 4/1/21 | NA | NA | 0.91000000000000003
3814 | CCWIS | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 1153 | 203d | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1153 days | No | 4/1/21 | NA | NA | 0.98999999999999999
3815 | CCWIS Self-Assessments (Checklist) (CARESV1-14449) | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 2825SS | 1855,2828SS | Finish No Earlier Than | 10/31/25 | 1163 | 203d | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 days | No | 4/1/21 | NA | NA | 0.98999999999999999
3816 | CARESV1-19070 CCWIS Self-Assessments (Checklist) - Implementation | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 2827SS | 1855,2829SS | Finish No Earlier Than | 10/31/25 | 1163 | 203d | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 days | No | 4/1/21 | NA | NA | 0.98999999999999999
3817 | California CCWIS Monitoring Review (CARESV1-14450) | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 2828SS | 1855,2830SS | Finish No Earlier Than | 10/31/25 | 1163 | 203d | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 days | No | 4/1/21 | NA | NA | 0.98999999999999999
3818 | Governance (CARESV1-14456) | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 2829SS | 1855,2831SS | Finish No Earlier Than | 10/31/25 | 1163 | 203d | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 days | No | 4/1/21 | NA | NA | 0.98999999999999999
3819 | Expectation Management (CARESV1-14446) | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 2830SS | 1855,2832SS | Finish No Earlier Than | 10/31/25 | 1163 | 203d | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 days | No | 4/1/21 | NA | NA | 0.98999999999999999
3820 | Conflict Management (CARESV1-14447) | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 2831SS | 1855,2976SS | Finish No Earlier Than | 10/31/25 | 1163 | 203d | April 1, 2021 8:00 AM | October 31, 2025 5:00 PM | 1163 days | No | 4/1/21 | NA | NA | 0.98999999999999999
3821 | Security | June 1, 2022 8:00 AM | February 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 921 | 423d | June 1, 2022 8:00 AM | April 1, 2025 4:12 PM | 708.9 days | No | 6/1/22 | NA | NA | 0.97999999999999998
3822 | Information Security (CARESV1-12620) | June 1, 2022 8:00 AM | February 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 921 | 0d | June 1, 2022 8:00 AM | December 31, 2024 5:00 PM | 648 days | No | 6/1/22 | 2/3/26 | NA | 1
3823 | County IAM Integration | June 1, 2022 8:00 AM | February 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 921 | 0d | June 1, 2022 8:00 AM | October 7, 2024 5:00 PM | 591 days | No | 6/1/22 | 2/3/26 | NA | 1
5660 | County IAM Integration - Alameda | December 5, 2022 8:00 AM | April 14, 2023 5:00 PM |  | 1855,2837FS-35d,2838SS-5d,2839SS-120d,2843SS-41d,2852SS | Finish No Earlier Than | 4/14/23 | 90 | 0d | December 5, 2022 8:00 AM | April 14, 2023 5:00 PM | 90 days | No | 12/5/22 | 4/14/23 | NA | 1
5661 | County IAM Integration - Calaveras | February 27, 2023 8:00 AM | August 10, 2023 5:00 PM | 2836FS-35d | 1855,2840SS-22d,2849SS+13d | As Soon As Possible | NA | 116 | 0d | February 26, 2023 8:00 AM | August 10, 2023 5:00 PM | 116 days | No | 2/27/23 | 8/10/23 | NA | 1
5662 | County IAM Integration - El Dorado | November 29, 2022 8:00 AM | February 22, 2023 5:00 PM | 2836SS-5d | 1855,2846SS-20d | As Soon As Possible | NA | 58 | 0d | November 29, 2022 8:00 AM | February 22, 2023 5:00 PM | 58 days | No | 11/29/22 | 2/22/23 | NA | 1
5663 | County IAM Integration - Fresno | June 1, 2022 8:00 AM | November 1, 2022 5:00 PM | 2836SS-120d | 1855,2853SS+19d,2858SS+20d | As Soon As Possible | NA | 108 | 0d | June 1, 2022 8:00 AM | November 1, 2022 5:00 PM | 108 days | No | 6/1/22 | 11/1/22 | NA | 1
5664 | County IAM Integration - Glenn (Dedicated) | January 27, 2023 8:00 AM | July 10, 2023 5:00 PM | 2837SS-22d | 1855,2841SS-5d,2854SS-12d | As Soon As Possible | NA | 113 | 0d | January 27, 2023 8:00 AM | July 10, 2023 5:00 PM | 113 days | No | 1/27/23 | 7/10/23 | NA | 1
5665 | County IAM Integration - Humboldt | January 20, 2023 8:00 AM | May 5, 2023 5:00 PM | 2840SS-5d | 1855,2842FS-20d,2855SS+15d | As Soon As Possible | NA | 74 | 0d | January 20, 2023 8:00 AM | May 5, 2023 5:00 PM | 74 days | No | 1/20/23 | 5/5/23 | NA | 1
5666 | County IAM Integration - Kern | April 5, 2023 8:00 AM | June 14, 2023 5:00 PM | 2841FS-20d | 1855,2844SS+15d,2845SS+48d,2848SS+15d,2851SS-12d | As Soon As Possible | NA | 50 | 0d | April 5, 2023 8:00 AM | June 14, 2023 5:00 PM | 50 days | No | 4/5/23 | 6/14/23 | NA | 1
5667 | County IAM Integration - Los Angeles | October 3, 2022 8:00 AM | February 2, 2023 5:00 PM | 2836SS-41d | 1855 | As Soon As Possible | NA | 83 | 0d | October 1, 2022 8:00 AM | February 2, 2023 5:00 PM | 83 days | No | 10/3/22 | 2/2/23 | NA | 1
5668 | County IAM Integration - Lake | April 22, 2024 8:00 AM | August 2, 2024 5:00 PM | 2842SS+15d | 1855,2847SS-40d | As Soon As Possible | NA | 73 | 0d | April 22, 2024 8:00 AM | August 2, 2024 5:00 PM | 73 days | No | 4/22/24 | 8/2/24 | NA | 1
5669 | County IAM Integration - Mendocino | June 28, 2023 8:00 AM | September 28, 2023 5:00 PM | 2842SS+48d | 1855,2867SS+40d | As Soon As Possible | NA | 65 | 0d | June 28, 2023 8:00 AM | September 28, 2023 5:00 PM | 65 days | No | 6/28/23 | 9/28/23 | NA | 1
5670 | County IAM Integration - Monterey | October 27, 2022 8:00 AM | February 23, 2023 5:00 PM | 2838SS-20d | 1855,2850SS-8d | As Soon As Possible | NA | 79 | 0d | October 27, 2022 8:00 AM | February 23, 2023 5:00 PM | 79 days | No | 10/27/22 | 2/23/23 | NA | 1
5671 | County IAM Integration - Marin | February 26, 2024 8:00 AM | October 7, 2024 5:00 PM | 2844SS-40d | 1855,2866SS-5d | As Soon As Possible | NA | 158 | 0d | February 24, 2024 8:00 AM | October 7, 2024 5:00 PM | 158 days | No | 2/26/24 | 10/7/24 | NA | 1
5672 | County IAM Integration - Napa | April 20, 2023 8:00 AM | May 11, 2023 5:00 PM | 2842SS+15d | 1855 | As Soon As Possible | NA | 16 | 0d | April 20, 2023 8:00 AM | May 11, 2023 5:00 PM | 16 days | No | 4/20/23 | 5/11/23 | NA | 1
5673 | County IAM Integration - Nevada | March 15, 2023 8:00 AM | April 6, 2023 5:00 PM | 2837SS+13d | 1855 | As Soon As Possible | NA | 16 | 0d | March 15, 2023 8:00 AM | April 6, 2023 5:00 PM | 16 days | No | 3/15/23 | 4/6/23 | NA | 1
5674 | County IAM Integration - Orange | October 17, 2022 8:00 AM | February 9, 2023 5:00 PM | 2846SS-8d | 1855 | As Soon As Possible | NA | 78 | 0d | October 17, 2022 8:00 AM | February 9, 2023 5:00 PM | 78 days | No | 10/17/22 | 2/9/23 | NA | 1
5675 | County IAM Integration - Placer | March 20, 2023 8:00 AM | June 19, 2023 5:00 PM | 2842SS-12d | 1855,2863SS+6d,2865SS+15d | As Soon As Possible | NA | 64 | 0d | March 20, 2023 8:00 AM | June 19, 2023 5:00 PM | 64 days | No | 3/20/23 | 6/19/23 | NA | 1
5676 | County IAM Integration - Riverside | December 5, 2022 8:00 AM | March 2, 2023 5:00 PM | 2836SS | 1855 | As Soon As Possible | NA | 60 | 0d | December 5, 2022 8:00 AM | March 2, 2023 5:00 PM | 60 days | No | 12/5/22 | 3/2/23 | NA | 1
5677 | County IAM Integration - Sacramento | June 29, 2022 8:00 AM | October 4, 2022 5:00 PM | 2839SS+19d | 1855,2856SS+5d,2859SS-19d | As Soon As Possible | NA | 68 | 0d | June 29, 2022 8:00 AM | October 4, 2022 5:00 PM | 68 days | No | 6/29/22 | 10/4/22 | NA | 1
5678 | County IAM Integration - San Bernardino | January 6, 2023 8:00 AM | June 6, 2023 5:00 PM | 2840SS-12d | 1855,2860SS+18d | As Soon As Possible | NA | 104 | 0d | January 6, 2023 8:00 AM | June 6, 2023 5:00 PM | 104 days | No | 1/6/23 | 6/6/23 | NA | 1
5679 | County IAM Integration - San Francisco | February 10, 2023 8:00 AM | March 30, 2023 5:00 PM | 2841SS+15d | 1855,2861SS+1d | As Soon As Possible | NA | 34 | 0d | February 10, 2023 8:00 AM | March 30, 2023 5:00 PM | 34 days | No | 2/10/23 | 3/30/23 | NA | 1
5680 | County IAM Integration - San Joaquin | January 13, 2023 8:00 AM | June 17, 2024 5:00 PM | 2853SS+5d | 1855,2857SS,2862SS+1d | As Soon As Possible | NA | 357 | 0d | January 13, 2023 8:00 AM | June 17, 2024 5:00 PM | 357 days | No | 1/13/23 | 6/17/24 | NA | 1
5681 | County IAM Integration - San Luis Obispo | January 13, 2023 8:00 AM | June 26, 2023 5:00 PM | 2856SS | 1855 | As Soon As Possible | NA | 113 | 0d | January 13, 2023 8:00 AM | June 26, 2023 5:00 PM | 113 days | No | 1/13/23 | 6/26/23 | NA | 1
5682 | County IAM Integration - San Mateo | July 13, 2022 8:00 AM | January 19, 2024 5:00 PM | 2839SS+20d | 1855,2869SS+5d | As Soon As Possible | NA | 380 | 0d | July 13, 2022 8:00 AM | January 19, 2024 5:00 PM | 380 days | No | 7/13/22 | 1/19/24 | NA | 1
5683 | County IAM Integration - Santa Clara | June 1, 2022 8:00 AM | November 1, 2022 5:00 PM | 2853SS-19d | 1855 | As Soon As Possible | NA | 108 | 0d | June 1, 2022 8:00 AM | November 1, 2022 5:00 PM | 108 days | No | 6/1/22 | 11/1/22 | NA | 1
5684 | County IAM Integration - Santa Cruz | January 26, 2023 8:00 AM | March 8, 2023 5:00 PM | 2854SS+18d | 1855 | As Soon As Possible | NA | 29 | 0d | January 26, 2023 8:00 AM | March 8, 2023 5:00 PM | 29 days | No | 1/26/23 | 3/8/23 | NA | 1
5685 | County IAM Integration - Siskiyou (Dedicated) | February 13, 2023 8:00 AM | April 12, 2023 5:00 PM | 2855SS+1d | 1855 | As Soon As Possible | NA | 41 | 0d | February 13, 2023 8:00 AM | April 12, 2023 5:00 PM | 41 days | No | 2/13/23 | 4/12/23 | NA | 1
5686 | County IAM Integration - Solano | January 17, 2023 8:00 AM | March 13, 2023 5:00 PM | 2856SS+1d | 1855 | As Soon As Possible | NA | 39 | 0d | January 17, 2023 8:00 AM | March 13, 2023 5:00 PM | 39 days | No | 1/17/23 | 3/13/23 | NA | 1
5687 | County IAM Integration - Sonoma | March 28, 2023 8:00 AM | June 2, 2023 5:00 PM | 2851SS+6d | 1855,2864SS-1d | As Soon As Possible | NA | 47 | 0d | March 28, 2023 8:00 AM | June 2, 2023 5:00 PM | 47 days | No | 3/28/23 | 6/2/23 | NA | 1
5688 | County IAM Integration - Stanislaus | March 27, 2023 8:00 AM | May 4, 2023 5:00 PM | 2863SS-1d | 1855 | As Soon As Possible | NA | 28 | 0d | March 27, 2023 8:00 AM | May 4, 2023 5:00 PM | 28 days | No | 3/27/23 | 5/4/23 | NA | 1
5689 | County IAM Integration - Tulare (Dedicated) | April 11, 2023 8:00 AM | June 5, 2023 5:00 PM | 2851SS+15d | 1855 | As Soon As Possible | NA | 39 | 0d | April 11, 2023 8:00 AM | June 5, 2023 5:00 PM | 39 days | No | 4/11/23 | 6/5/23 | NA | 1
5690 | County IAM Integration - Tuolumne | February 16, 2024 8:00 AM | June 17, 2024 5:00 PM | 2847SS-5d | 1855 | As Soon As Possible | NA | 84 | 0d | February 16, 2024 8:00 AM | June 17, 2024 5:00 PM | 84 days | No | 2/16/24 | 6/17/24 | NA | 1
5691 | County IAM Integration - Yolo | August 24, 2023 8:00 AM | September 22, 2023 5:00 PM | 2845SS+40d | 1855,2868SS+6d | As Soon As Possible | NA | 21 | 0d | August 24, 2023 8:00 AM | September 22, 2023 5:00 PM | 21 days | No | 8/24/23 | 9/22/23 | NA | 1
5692 | County IAM Integration - Yuba | September 1, 2023 8:00 AM | September 27, 2023 5:00 PM | 2867SS+6d | 1855 | As Soon As Possible | NA | 18 | 0d | September 1, 2023 8:00 AM | September 27, 2023 5:00 PM | 18 days | No | 9/1/23 | 9/27/23 | NA | 1
5693 | County IAM Integration - King | July 19, 2023 8:00 AM | June 10, 2024 5:00 PM | 2858SS+5d | 1855,2876FS-4d,2870FS+18d | As Soon As Possible | NA | 224 | 0d | July 19, 2023 8:00 AM | June 10, 2024 5:00 PM | 224 days | No | 7/19/23 | 6/10/24 | NA | 1
11628 | County IAM Integration - Santa Barbara | July 10, 2024 8:00 AM | August 30, 2024 5:00 PM | 2869FS+18d | 2871FS-5d | As Soon As Possible | NA | 38 | 0d | NA | NA | 0 days? | No | 7/10/24 | 8/30/24 | NA | 1
12258 | County IAM Integration - Merced | August 26, 2024 8:00 AM | January 31, 2025 5:00 PM | 2870FS-5d | 2872SS+35d | As Soon As Possible | NA | 109 | 0d | NA | NA | 0 days? | No | 8/26/24 | 1/31/25 | NA | 1
12259 | County IAM Integration - Ventura | October 10, 2024 8:00 AM | March 28, 2025 5:00 PM | 2871SS+35d | 2873SS+21d | As Soon As Possible | NA | 115 | 0d | NA | NA | 0 days? | No | 10/10/24 | 3/28/25 | NA | 1
12260 | County IAM Integration - Contra Costa | November 8, 2024 8:00 AM | May 30, 2025 5:00 PM | 2872SS+21d | 2874FS-79d | As Soon As Possible | NA | 137 | 0d | NA | NA | 0 days? | No | 11/8/24 | 5/30/25 | NA | 1
12261 | County IAM Integration - San Diego | February 6, 2025 8:00 AM | May 7, 2025 5:00 PM | 2873FS-79d | 2875FS+124d | As Soon As Possible | NA | 63 | 0d | NA | NA | 0 days? | No | 2/6/25 | 5/7/25 | NA | 1
12262 | County IAM Integration - Madera | November 3, 2025 8:00 AM | February 3, 2026 5:00 PM | 2874FS+124d |  | As Soon As Possible | NA | 62 | 0d | NA | NA | 0 days? | No | 11/3/25 | 2/3/26 | NA | 1
3824 | Security - Privileged Access Management (PAM) | November 4, 2024 8:00 AM | April 18, 2025 5:00 PM | 2869FS-4d | 1855,2880SS-37d | Start No Earlier Than | 11/4/24 | 112 | 0d | June 4, 2024 8:00 AM | December 31, 2024 5:00 PM | 146 days | No | 11/4/24 | 4/18/25 | NA | 1
3828 | DevSecOps (CARESV1-14453) | April 8, 2024 8:00 AM | December 19, 2025 5:00 PM |  |  | As Soon As Possible | NA | 430 | 452d | April 8, 2024 8:00 AM | April 1, 2025 4:12 PM | 246.9 days | No | 4/8/24 | NA | NA | 0.84999999999999998
3829 | Vulnerability Assessments/ Management | April 8, 2024 8:00 AM | February 14, 2025 5:00 PM |  |  | As Soon As Possible | NA | 217 | 0d | April 8, 2024 8:00 AM | February 14, 2025 5:00 PM | 217 days | No | 4/8/24 | 2/14/25 | NA | 1
3830 | Conduct SAST Testing | April 8, 2024 8:00 AM | October 25, 2024 5:00 PM |  |  | As Soon As Possible | NA | 143 | 0d | April 8, 2024 8:00 AM | October 27, 2024 5:00 PM | 143 days | No | 4/8/24 | 10/25/24 | NA | 1
5877 | SAST-4/22/2024 | April 8, 2024 8:00 AM | April 11, 2024 5:00 PM | 2876SS-37d | 2881 | Start No Earlier Than | 4/8/24 | 4 | 0d | April 8, 2024 8:00 AM | April 11, 2024 5:00 PM | 4 days | No | 4/8/24 | 4/11/24 | NA | 1
5878 | SAST-4/22/2024 | April 22, 2024 8:00 AM | April 29, 2024 5:00 PM | 2880 | 2882 | Start No Earlier Than | 4/22/24 | 6 | 0d | April 22, 2024 8:00 AM | April 29, 2024 5:00 PM | 6 days | No | 4/22/24 | 4/29/24 | NA | 1
5879 | SAST-4/22/2024 | May 6, 2024 8:00 AM | May 13, 2024 5:00 PM | 2881 | 2883 | Start No Earlier Than | 5/6/24 | 6 | 0d | May 6, 2024 8:00 AM | May 13, 2024 5:00 PM | 6 days | No | 5/6/24 | 5/13/24 | NA | 1
5880 | SAST-4/22/2024 | May 20, 2024 8:00 AM | May 27, 2024 5:00 PM | 2882 | 2884 | Start No Earlier Than | 5/20/24 | 5 | 0d | May 20, 2024 8:00 AM | May 27, 2024 5:00 PM | 5 days | No | 5/20/24 | 5/27/24 | NA | 1
5881 | SAST-4/22/2024 | June 3, 2024 8:00 AM | June 10, 2024 5:00 PM | 2883 | 2885 | Start No Earlier Than | 6/3/24 | 6 | 0d | June 3, 2024 8:00 AM | June 10, 2024 5:00 PM | 6 days | No | 6/3/24 | 6/10/24 | NA | 1
5882 | SAST-4/22/2024 | June 17, 2024 8:00 AM | June 24, 2024 5:00 PM | 2884 | 2886 | Start No Earlier Than | 6/17/24 | 6 | 0d | June 17, 2024 8:00 AM | June 24, 2024 5:00 PM | 6 days | No | 6/17/24 | 6/24/24 | NA | 1
5883 | SAST-4/22/2024 | July 1, 2024 8:00 AM | July 9, 2024 5:00 PM | 2885 | 2887 | Start No Earlier Than | 7/1/24 | 6 | 0d | July 1, 2024 8:00 AM | July 9, 2024 5:00 PM | 6 days | No | 7/1/24 | 7/9/24 | NA | 1
5884 | SAST-4/22/2024 | July 15, 2024 8:00 AM | July 22, 2024 5:00 PM | 2886 | 2888 | Start No Earlier Than | 7/15/24 | 6 | 0d | July 15, 2024 8:00 AM | July 22, 2024 5:00 PM | 6 days | No | 7/15/24 | 7/22/24 | NA | 1
5885 | SAST-4/22/2024 | July 29, 2024 8:00 AM | August 5, 2024 5:00 PM | 2887 | 2889 | Start No Earlier Than | 7/29/24 | 6 | 0d | July 29, 2024 8:00 AM | August 5, 2024 5:00 PM | 6 days | No | 7/29/24 | 8/5/24 | NA | 1
5886 | SAST-4/22/2024 | August 12, 2024 8:00 AM | August 19, 2024 5:00 PM | 2888 | 2890 | Start No Earlier Than | 8/12/24 | 6 | 0d | August 12, 2024 8:00 AM | August 19, 2024 5:00 PM | 6 days | No | 8/12/24 | 8/19/24 | NA | 1
5887 | SAST-4/22/2024 | August 26, 2024 8:00 AM | September 3, 2024 5:00 PM | 2889 | 2891 | Start No Earlier Than | 8/26/24 | 7 | 0d | August 26, 2024 8:00 AM | September 3, 2024 5:00 PM | 7 days | No | 8/26/24 | 9/3/24 | NA | 1
5888 | SAST-4/22/2024 | September 9, 2024 8:00 AM | September 16, 2024 5:00 PM | 2890 | 2892 | Start No Earlier Than | 9/9/24 | 6 | 0d | September 9, 2024 8:00 AM | September 16, 2024 5:00 PM | 6 days | No | 9/9/24 | 9/16/24 | NA | 1
5889 | SAST-4/22/2024 | September 23, 2024 8:00 AM | September 23, 2024 5:00 PM | 2891 | 2893 | Start No Earlier Than | 9/23/24 | 1 | 0d | September 23, 2024 8:00 AM | September 23, 2024 5:00 PM | 1 | No | 9/23/24 | 9/23/24 | NA | 1
5890 | SAST-4/22/2024 | October 7, 2024 8:00 AM | October 14, 2024 5:00 PM | 2892 | 2894 | Start No Earlier Than | 10/7/24 | 6 | 0d | October 7, 2024 8:00 AM | October 14, 2024 5:00 PM | 6 days | No | 10/7/24 | 10/14/24 | NA | 1
5891 | DevSecOps Security - Conduct SAST-4/22/2024 | October 21, 2024 8:00 AM | October 25, 2024 5:00 PM | 2893 | 2896FS-85d | Finish No Earlier Than | 10/25/24 | 5 | 0d | October 21, 2024 8:00 AM | October 27, 2024 5:00 PM | 5 days | No | 10/21/24 | 10/25/24 | NA | 1
3831 | Conduct DAST Testing | June 28, 2024 8:00 AM | February 14, 2025 5:00 PM |  |  | As Soon As Possible | NA | 159 | 0d | June 28, 2024 8:00 AM | February 14, 2025 5:00 PM | 159 days | No | 6/28/24 | 2/14/25 | NA | 1
5893 | DAST-6/28/2024 | June 28, 2024 8:00 AM | July 15, 2024 5:00 PM | 2894FS-85d | 2897FS+23d | As Soon As Possible | NA | 11 | 0d | June 28, 2024 8:00 AM | July 15, 2024 5:00 PM | 11 days | No | 6/28/24 | 7/15/24 | NA | 1
5894 | DAST-8/16/2024 | August 16, 2024 8:00 AM | August 30, 2024 5:00 PM | 2896FS+23d | 2898FS+24d | As Soon As Possible | NA | 11 | 0d | August 16, 2024 8:00 AM | August 30, 2024 5:00 PM | 11 days | No | 8/16/24 | 8/30/24 | NA | 1
5895 | DAST-10/4/2024 | October 4, 2024 8:00 AM | November 1, 2024 5:00 PM | 2897FS+24d | 2899FS+17d | As Soon As Possible | NA | 21 | 0d | October 4, 2024 8:00 AM | November 1, 2024 5:00 PM | 21 days | No | 10/4/24 | 11/1/24 | NA | 1
5896 | DAST-11/30/2024 | December 2, 2024 8:00 AM | December 10, 2024 5:00 PM | 2898FS+17d | 2900FS+3d | As Soon As Possible | NA | 7 | 0d | December 2, 2024 8:00 AM | December 10, 2024 5:00 PM | 7 days | No | 12/2/24 | 12/10/24 | NA | 1
5897 | DAST-12/16/2024 | December 16, 2024 8:00 AM | January 3, 2025 5:00 PM | 2899FS+3d | 2901FS+19d | As Soon As Possible | NA | 13 | 0d | December 16, 2024 8:00 AM | January 3, 2025 5:00 PM | 13 days | No | 12/16/24 | 1/3/25 | NA | 1
5898 | DAST-2/2/2025 | February 3, 2025 8:00 AM | February 14, 2025 5:00 PM | 2900FS+19d | 2902FS-31d | As Soon As Possible | NA | 10 | 0d | February 3, 2025 8:00 AM | February 14, 2025 5:00 PM | 10 days | No | 2/3/25 | 2/14/25 | NA | 1
3832 | System Security Plan (SSP) | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 2901FS-31d | 2903 | As Soon As Possible | NA | 21 | 0d | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 21 days | No | 1/2/25 | 1/31/25 | NA | 1
3833 | Okta FedRAMP Transition | February 3, 2025 8:00 AM | September 22, 2025 5:00 PM | 2902 |  | Finish No Earlier Than | 6/27/25 | 161 | 0d | June 4, 2024 8:00 AM | April 1, 2025 4:12 PM | 42 days | No | 2/3/25 | 9/22/25 | NA | 1
13697 | Okta Migration | June 23, 2025 8:00 AM | December 19, 2025 5:00 PM |  |  | As Soon As Possible | NA | 126 | 452d | NA | NA | 0 days? | No | 6/23/25 | NA | NA | 0.66000000000000003
13698 | Okta Dev Migration | June 23, 2025 8:00 AM | August 4, 2025 5:00 PM |  | 2906SS,2907FS+3d | Start No Earlier Than | 6/23/25 | 30 | 0d | NA | NA | 0 days? | No | 6/23/25 | 8/4/25 | NA | 1
13699 | Okta API Security Migration | June 23, 2025 8:00 AM | August 8, 2025 5:00 PM | 2905SS |  | As Soon As Possible | NA | 34 | 0d | NA | NA | 0 days? | No | 6/23/25 | 8/8/25 | NA | 1
13700 | Okta SIT Migration | August 8, 2025 8:00 AM | August 29, 2025 5:00 PM | 2905FS+3d | 2908SS,2909 | As Soon As Possible | NA | 16 | 0d | NA | NA | 0 days? | No | 8/8/25 | 8/29/25 | NA | 1
13695 | Okta API Security Migration | August 8, 2025 8:00 AM | September 5, 2025 5:00 PM | 2907SS |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 8/8/25 | 9/5/25 | NA | 1
13701 | Okta QA Migration | September 2, 2025 8:00 AM | September 26, 2025 5:00 PM | 2907 | 2910SS,2911FS-10d | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/26/25 | NA | 1
13702 | Okta API Security Migration | September 2, 2025 8:00 AM | October 2, 2025 5:00 PM | 2909SS |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/2/25 | NA | 1
13703 | Okta Pre-prod Migration | September 15, 2025 8:00 AM | December 15, 2025 5:00 PM | 2909FS-10d | 2912SS | As Soon As Possible | NA | 64 | 456d | NA | NA | 0 days? | No | 9/15/25 | NA | NA | 0.31
13696 | Okta API Security Migration | September 15, 2025 8:00 AM | December 19, 2025 5:00 PM | 2911SS |  | As Soon As Possible | NA | 68 | 452d | NA | NA | 0 days? | No | 9/15/25 | NA | NA | 0.28999999999999998
3836 | External Systems (CARESV1-14108) | November 15, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 491 | 235d | October 10, 2022 8:00 AM | December 31, 2026 5:00 PM | 1058 days | No | 11/15/24 | NA | NA | 0.29999999999999999
13177 | Template development | November 15, 2024 8:00 AM | June 27, 2025 5:00 PM |  |  | As Soon As Possible | NA | 153 | 573d | NA | NA | 0 days? | No | 11/15/24 | NA | NA | 0.93999999999999995
13178 | Develop Data templates for Drop 1 | November 15, 2024 8:00 AM | March 10, 2025 5:00 PM |  | 2916FS-1d | Start No Earlier Than | 11/15/24 | 76 | 0d | NA | NA | 0 days? | No | 11/15/24 | 3/10/25 | NA | 1
13179 | Data Template Drop 1 | March 10, 2025 8:00 AM | March 21, 2025 5:00 PM | 2915FS-1d | 2917,2919 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 3/10/25 | 3/21/25 | NA | 1
13180 | Data Template Walkthrough 1 | March 24, 2025 8:00 AM | March 28, 2025 5:00 PM | 2916 | 2918 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 3/24/25 | 3/28/25 | NA | 1
13181 | Data Template County feedback for Drop 1 | April 1, 2025 8:00 AM | April 25, 2025 5:00 PM | 2917 |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/25/25 | NA | 1
13182 | Develop Data templates for Drop 2 | March 24, 2025 8:00 AM | April 11, 2025 5:00 PM | 2916 | 2920 | As Soon As Possible | NA | 14 | 0d | NA | NA | 0 days? | No | 3/24/25 | 4/11/25 | NA | 1
13183 | Data Template Drop 2 | April 14, 2025 8:00 AM | April 25, 2025 5:00 PM | 2919 | 2921,2923 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 4/14/25 | 4/25/25 | NA | 1
13184 | Data Template Walkthrough 2 | April 28, 2025 8:00 AM | May 2, 2025 5:00 PM | 2920 | 2922 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 4/28/25 | 5/2/25 | NA | 1
13185 | County review and Feedback for Drop 2 | May 5, 2025 8:00 AM | May 30, 2025 5:00 PM | 2921 |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 5/5/25 | 5/30/25 | NA | 1
13186 | Develop Data templates for Drop 3 | April 28, 2025 8:00 AM | May 16, 2025 5:00 PM | 2920 | 2924,2927FS+5d | As Soon As Possible | NA | 15 | 0d | NA | NA | 0 days? | No | 4/28/25 | 5/16/25 | NA | 1
13187 | Data Template Drop 3 | May 19, 2025 8:00 AM | June 6, 2025 5:00 PM | 2923 | 2925 | As Soon As Possible | NA | 14 | 0d | NA | NA | 0 days? | No | 5/19/25 | 6/6/25 | NA | 1
13188 | Data Template Walkthrough 3 | June 9, 2025 8:00 AM | June 13, 2025 5:00 PM | 2924 | 2926FS-1d | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 6/9/25 | 6/13/25 | NA | 1
13189 | Data Template County feedback | June 13, 2025 8:00 AM | June 20, 2025 5:00 PM | 2925FS-1d |  | As Soon As Possible | NA | 6 | 578d | NA | NA | 0 days? | No | 6/13/25 | NA | NA | 0.94999999999999996
13190 | Develop Data templates for Revision 1 | May 27, 2025 8:00 AM | June 6, 2025 5:00 PM | 2923FS+5d | 2928 | As Soon As Possible | NA | 9 | 2.5d | NA | NA | 0 days? | No | 5/27/25 | NA | NA | 0.5
13191 | Data Template Revision 1 | June 9, 2025 8:00 AM | June 13, 2025 5:00 PM | 2927 | 2929 | As Soon As Possible | NA | 5 | 2.5d | NA | NA | 0 days? | No | 6/9/25 | NA | NA | 0.5
13192 | Develop Data templates for Revision 2 | June 16, 2025 8:00 AM | June 20, 2025 5:00 PM | 2928 | 2930 | As Soon As Possible | NA | 5 | 2.5d | NA | NA | 0 days? | No | 6/16/25 | NA | NA | 0.5
13193 | Data Template Revision 2 | June 23, 2025 8:00 AM | June 27, 2025 5:00 PM | 2929 |  | As Soon As Possible | NA | 5 | 573d | NA | NA | 0 days? | No | 6/23/25 | NA | NA | 0.5
13194 | Infrastructure and tooling | February 3, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 83 | 0d | NA | NA | 0 days? | No | 2/3/25 | 6/2/25 | NA | 1
13195 | SFTP Server Set up | February 3, 2025 8:00 AM | March 18, 2025 5:00 PM |  | 2933FS-1d | Start No Earlier Than | 2/3/25 | 31 | 0d | NA | NA | 0 days? | No | 2/3/25 | 3/18/25 | NA | 1
13196 | County Account Provisioning for Drop 1 | March 18, 2025 8:00 AM | March 28, 2025 5:00 PM | 2932FS-1d | 2934 | As Soon As Possible | NA | 9 | 0d | NA | NA | 0 days? | No | 3/18/25 | 3/28/25 | NA | 1
13197 | County Account Provisioning for Drop 2 | April 1, 2025 8:00 AM | April 28, 2025 5:00 PM | 2933 | 2935FS+14d | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/28/25 | NA | 1
13198 | County Account Provisioning for Drop 3 | May 19, 2025 8:00 AM | June 2, 2025 5:00 PM | 2934FS+14d |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 5/19/25 | 6/2/25 | NA | 1
13199 | Environment Set up - V1DCDEV2, Mulesoft | February 24, 2025 8:00 AM | April 11, 2025 5:00 PM |  |  | Start No Earlier Than | 2/24/25 | 34 | 0d | NA | NA | 0 days? | No | 2/24/25 | 4/11/25 | NA | 1
13200 | Workspace Seup and access provisioning | February 24, 2025 8:00 AM | April 25, 2025 5:00 PM |  |  | Start No Earlier Than | 2/24/25 | 44 | 0d | NA | NA | 0 days? | No | 2/24/25 | 4/25/25 | NA | 1
13201 | Conversion ETL Development and Test | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 148 | 445d | NA | NA | 0 days? | No | 6/2/25 | NA | NA | 0.19
13202 | ETL code development and unit testing for Drop 1 | June 2, 2025 8:00 AM | October 17, 2025 5:00 PM |  |  | Start No Earlier Than | 6/2/25 | 98 | 495d | NA | NA | 0 days? | No | 6/2/25 | NA | NA | 0.23999999999999999
13203 | ETL code development and unit testing for Drop 2 | June 2, 2025 8:00 AM | November 21, 2025 5:00 PM |  |  | Start No Earlier Than | 6/2/25 | 122 | 471d | NA | NA | 0 days? | No | 6/2/25 | NA | NA | 0.20000000000000001
13204 | ETL code development and unit testing for Drop 3 | June 2, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 6/2/25 | 148 | 445d | NA | NA | 0 days? | No | 6/2/25 | NA | NA | 0.16
13205 | Receive Data template for Dry Run 1 | June 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 6/2/25 | 108 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
13206 | Dry run1 | November 3, 2025 8:00 AM | January 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 51 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
13207 | Data Conversion & Issue remediation | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  | 2945 | Start No Earlier Than | 11/3/25 | 18 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
13208 | Generate Conversion Report | December 1, 2025 8:00 AM | December 12, 2025 5:00 PM | 2944 | 2946 | As Soon As Possible | NA | 10 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
13161 | Data Validation Support | December 15, 2025 8:00 AM | December 26, 2025 5:00 PM | 2945 | 2947 | As Soon As Possible | NA | 9 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
13162 | System Testing | December 29, 2025 8:00 AM | January 16, 2026 5:00 PM | 2946 |  | As Soon As Possible | NA | 14 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
13163 | Receive Data template for Dry Run 2 | December 22, 2025 8:00 AM | January 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/22/25 | 18 | 434d | NA | NA | 0 days? | No | NA | NA | NA | 0
13164 | Dry run2 | January 20, 2026 8:00 AM | March 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 43 | 391d | NA | NA | 0 days? | No | NA | NA | NA | 0
13165 | Data Conversion & Issue remediation | January 20, 2026 8:00 AM | February 6, 2026 5:00 PM |  | 2951 | Start No Earlier Than | 1/20/26 | 14 | 391d | NA | NA | 0 days? | No | NA | NA | NA | 0
13166 | Generate Conversion Report | February 9, 2026 8:00 AM | February 20, 2026 5:00 PM | 2950 | 2952,2954 | As Soon As Possible | NA | 9 | 391d | NA | NA | 0 days? | No | NA | NA | NA | 0
13167 | Data Validation Support | February 23, 2026 8:00 AM | March 6, 2026 5:00 PM | 2951 | 2953 | As Soon As Possible | NA | 10 | 391d | NA | NA | 0 days? | No | NA | NA | NA | 0
13168 | System Testing | March 9, 2026 8:00 AM | March 20, 2026 5:00 PM | 2952 |  | As Soon As Possible | NA | 10 | 391d | NA | NA | 0 days? | No | NA | NA | NA | 0
13169 | Receive Data template for Dry Run 3 | February 23, 2026 8:00 AM | March 20, 2026 5:00 PM | 2951 |  | As Soon As Possible | NA | 20 | 391d | NA | NA | 0 days? | No | NA | NA | NA | 0
13170 | Dry run3 | March 23, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | As Soon As Possible | NA | 48 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
13171 | Data Conversion & Issue remediation | March 23, 2026 8:00 AM | April 17, 2026 5:00 PM |  | 2957,2960 | Start No Earlier Than | 3/23/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
13172 | Generate Conversion Report | April 20, 2026 8:00 AM | May 1, 2026 5:00 PM | 2956 | 2958 | As Soon As Possible | NA | 10 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
13173 | Data Validation Support | May 4, 2026 8:00 AM | May 15, 2026 5:00 PM | 2957 | 2959 | As Soon As Possible | NA | 10 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
13174 | System Testing | May 18, 2026 8:00 AM | May 29, 2026 5:00 PM | 2958 |  | As Soon As Possible | NA | 9 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
13175 | Receive Data template for Dry Run 4 | April 20, 2026 8:00 AM | May 29, 2026 5:00 PM | 2956 |  | As Soon As Possible | NA | 29 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
13176 | Dry run4 | June 1, 2026 8:00 AM | August 6, 2026 5:00 PM |  |  | As Soon As Possible | NA | 48 | 295d | NA | NA | 0 days? | No | NA | NA | NA | 0
13153 | Data Conversion & Issue remediation | June 1, 2026 8:00 AM | June 19, 2026 5:00 PM |  | 2963 | Start No Earlier Than | 6/1/26 | 15 | 295d | NA | NA | 0 days? | No | NA | NA | NA | 0
13154 | Generate Conversion Report | June 22, 2026 8:00 AM | July 2, 2026 5:00 PM | 2962 | 2964 | As Soon As Possible | NA | 9 | 295d | NA | NA | 0 days? | No | NA | NA | NA | 0
13155 | Data Validation Support | July 6, 2026 8:00 AM | July 24, 2026 5:00 PM | 2963 | 2965 | As Soon As Possible | NA | 15 | 295d | NA | NA | 0 days? | No | NA | NA | NA | 0
13156 | System Testing | July 27, 2026 8:00 AM | August 6, 2026 5:00 PM | 2964 |  | As Soon As Possible | NA | 9 | 295d | NA | NA | 0 days? | No | NA | NA | NA | 0
13157 | Integrated Testing | February 6, 2026 8:00 AM | August 6, 2026 5:00 PM |  |  | As Soon As Possible | NA | 126 | 295d | NA | NA | 0 days? | No | NA | NA | NA | 0
13158 | Data load support | February 6, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 2968SS+5d | Start No Earlier Than | 2/6/26 | 122 | 295d | NA | NA | 0 days? | No | NA | NA | NA | 0
13159 | Testing Support | February 13, 2026 8:00 AM | August 6, 2026 5:00 PM | 2967SS+5d |  | As Soon As Possible | NA | 121 | 295d | NA | NA | 0 days? | No | NA | NA | NA | 0
13160 | Production data load | August 3, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 64 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
13149 | Pre-Production activities and CutOver Support, Receive Data Templates for Prod load | August 3, 2026 8:00 AM | August 14, 2026 5:00 PM |  | 2971 | Start No Earlier Than | 8/3/26 | 10 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
13150 | Production data load | August 17, 2026 8:00 AM | August 28, 2026 5:00 PM | 2970 | 2972 | As Soon As Possible | NA | 10 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
13151 | Pilot - Go live | August 31, 2026 8:00 AM | August 31, 2026 5:00 PM | 2971 | 2973 | As Soon As Possible | NA | 1 | 235d | NA | NA | 0 s? | No | NA | NA | NA | 0
13152 | Hyper Care | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 2972 |  | As Soon As Possible | NA | 43 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
3973 | CDI | April 1, 2021 8:00 AM | October 9, 2026 5:00 PM |  |  | As Soon As Possible | NA | 1388 | 0d | April 1, 2021 8:00 AM | October 9, 2026 5:00 PM | 1388 days | No | 4/1/21 | NA | NA | 0.90000000000000002
3974 | Technical Roadmap | April 1, 2021 8:00 AM | October 9, 2026 5:00 PM |  |  | As Soon As Possible | NA | 1388 | 0d | April 1, 2021 8:00 AM | October 9, 2026 5:00 PM | 1388 days | No | 4/1/21 | NA | NA | 0.93999999999999995
3975 | CDI: Centralized Business Rules (CARESV1-5231) | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 2832SS | 1848,2977SS | Start No Earlier Than | 10/30/26 | 561 | 0d | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 561 days | No | 4/1/21 | 6/23/23 | NA | 1
3976 | CDI: Event Framework (CARESV1-5238) | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 2976SS | 1848,2978SS | Start No Earlier Than | 10/30/26 | 561 | 0d | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 561 days | No | 4/1/21 | 6/23/23 | NA | 1
3977 | CDI: Query Composer and Graph Builder Controls (CARESV1-5197) | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 2977SS | 1848,2979SS | Start No Earlier Than | 10/30/26 | 561 | 0d | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 561 days | No | 4/1/21 | 6/23/23 | NA | 1
3978 | CDI: Curated Metric Feed/View (CARESV1-5198) | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 2978SS | 1848,2980SS | Start No Earlier Than | 10/30/26 | 561 | 0d | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 561 days | No | 4/1/21 | 6/23/23 | NA | 1
3979 | CDI: Notifications (CARESV1-5199) | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 2979SS | 1848,2981SS | Start No Earlier Than | 10/30/26 | 561 | 0d | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 561 days | No | 4/1/21 | 6/23/23 | NA | 1
3980 | CDI: Timers (CARESV1-5191) | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 2980SS | 1848,2982SS | Start No Earlier Than | 10/30/26 | 561 | 0d | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 561 days | No | 4/1/21 | 6/23/23 | NA | 1
3981 | CDI: Validations (CARESV1-5192) | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 2981SS | 1848 | Start No Earlier Than | 10/30/26 | 561 | 0d | April 1, 2021 8:00 AM | June 23, 2023 5:00 PM | 561 days | No | 4/1/21 | 6/23/23 | NA | 1
3982 | County Specific - Reports (CARESV1-14107) | June 10, 2024 8:00 AM | October 9, 2026 5:00 PM | 2435 | 5628 | As Soon As Possible | NA | 588 | -16d | June 10, 2024 8:00 AM | October 9, 2026 5:00 PM | 588 days | No | 6/10/24 | NA | NA | 0.56999999999999995
3983 | Reporting & Analytics - Functional Reports (Operational) (CARESV1-14112) | June 30, 2023 8:00 AM | January 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 648 | -1d | June 30, 2023 8:00 AM | January 30, 2026 5:00 PM | 648 days | No | 6/30/23 | NA | NA | 0.75
3984 | CARESV1-21981 Reporting & Analytics: M4 (LOE) | June 30, 2023 8:00 AM | June 26, 2024 5:00 PM | 119 | 1843,3007FS-80d | As Soon As Possible | NA | 248 | 0d | June 30, 2023 8:00 AM | June 26, 2024 5:00 PM | 248 days | No | 6/30/23 | 6/26/24 | NA | 1
3985 | CARESV1-18894 Reporting & Analytics: M5 (LOE) | July 24, 2023 8:00 AM | December 27, 2024 5:00 PM | 169 | 1843 | Start No Earlier Than | 7/24/23 | 360 | 0d | July 24, 2023 8:00 AM | December 27, 2024 5:00 PM | 360 days | No | 7/24/23 | 12/27/24 | NA | 1
3986 | CARESV1-18895 Reporting & Analytics: M6 (LOE) | January 2, 2025 8:00 AM | January 29, 2026 5:00 PM | 1475 | 1843 | As Soon As Possible | NA | 270 | -16d | January 2, 2025 8:00 AM | January 29, 2026 5:00 PM | 270 days | No | 1/2/25 | NA | NA | 0.72999999999999998
3987 | CARESV1-21984 Reporting & Analytics: M6.1 (LOE) | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 1479 | 1843 | As Soon As Possible | NA | 41 | -17d | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 41 days | No | NA | NA | NA | 0
3988 | CARESV1-21990 Reporting & Analytics: M7 (LOE) | August 11, 2025 8:00 AM | October 7, 2025 5:00 PM | 731 | 1843 | As Soon As Possible | NA | 41 | 0d | December 1, 2025 8:00 AM | January 29, 2026 5:00 PM | 41 days | No | 8/11/25 | 10/7/25 | NA | 1
3989 | CARESV1-18896 Reporting & Analytics: M8 (LOE) | January 2, 2025 8:00 AM | January 28, 2026 5:00 PM | 1475 | 1843 | As Soon As Possible | NA | 269 | -15d | January 2, 2025 8:00 AM | January 28, 2026 5:00 PM | 269 days | No | 1/2/25 | NA | NA | 0.72999999999999998
3990 | CARESV1-18897 Reporting & Analytics: M9 (LOE) | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 1479 | 1843 | As Soon As Possible | NA | 41 | -17d | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 41 days | No | NA | NA | NA | 0
3991 | CARESV1-20274 Reporting & Analytics: M10 (LOE) | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 1479 | 1843 | As Soon As Possible | NA | 41 | -17d | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 41 days | No | NA | NA | NA | 0
3992 | CARESV1-30592 Reporting & Analytics: M11 (LOE) | October 6, 2025 8:00 AM | December 3, 2025 5:00 PM | 744 | 1843 | As Soon As Possible | NA | 41 | 22d | December 1, 2025 8:00 AM | January 29, 2026 5:00 PM | 41 days | No | 10/6/25 | NA | NA | 0.12
3993 | CARESV1-21989 Reporting & Analytics: M13 (LOE) | October 6, 2025 8:00 AM | December 3, 2025 5:00 PM | 738 | 1843 | As Soon As Possible | NA | 41 | 22d | December 1, 2025 8:00 AM | January 29, 2026 5:00 PM | 41 days | No | 10/6/25 | NA | NA | 0.12
3994 | CARESV1-20273 Reporting & Analytics: M14 (LOE) | January 29, 2025 8:00 AM | January 27, 2026 5:00 PM | 496 | 1843 | As Soon As Possible | NA | 250 | -14d | January 29, 2025 8:00 AM | January 27, 2026 5:00 PM | 250 days | No | 1/29/25 | NA | NA | 0.70999999999999996
3995 | CARESV1-21983 Reporting & Analytics: M15 (LOE) | November 19, 2024 8:00 AM | September 8, 2025 5:00 PM | 463 | 1843 | As Soon As Possible | NA | 200 | 0d | January 29, 2025 8:00 AM | November 12, 2025 5:00 PM | 200 days | No | 11/19/24 | 9/8/25 | NA | 1
3996 | CARESV1-31448 Reporting & Analytics: M17 (LOE) | August 11, 2025 8:00 AM | October 7, 2025 5:00 PM | 889 | 1843 | As Soon As Possible | NA | 41 | 0d | December 1, 2025 8:00 AM | January 29, 2026 5:00 PM | 41 days | No | 8/11/25 | 10/7/25 | NA | 1
3997 | CARESV1-21987 Reporting & Analytics: M18 (LOE) | August 11, 2025 8:00 AM | October 7, 2025 5:00 PM | 894 | 1843 | As Soon As Possible | NA | 41 | 0d | December 1, 2025 8:00 AM | January 29, 2026 5:00 PM | 41 days | No | 8/11/25 | 10/7/25 | NA | 1
3998 | CARESV1-18898 Reporting & Analytics: M19 (LOE) | January 29, 2025 8:00 AM | November 12, 2025 5:00 PM | 496 | 1843 | As Soon As Possible | NA | 200 | 36d | January 29, 2025 8:00 AM | November 12, 2025 5:00 PM | 200 days | No | 1/29/25 | NA | NA | 0.89000000000000001
3999 | CARESV1-21988 Reporting & Analytics: M20 (LOE) | January 2, 2025 8:00 AM | October 16, 2025 5:00 PM | 1475 | 1843 | As Soon As Possible | NA | 200 | 54d | January 2, 2025 8:00 AM | October 16, 2025 5:00 PM | 200 days | No | 1/2/25 | NA | NA | 0.97999999999999998
4000 | CARESV1-21985 Reporting & Analytics: M21 (LOE) | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 1479 | 1843 | As Soon As Possible | NA | 41 | -17d | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 41 days | No | NA | NA | NA | 0
4001 | CARESV1-31449 Reporting & Analytics: M23 (LOE) | December 1, 2025 8:00 AM | January 29, 2026 5:00 PM | 1158 | 1843 | As Soon As Possible | NA | 41 | -16d | December 1, 2025 8:00 AM | January 29, 2026 5:00 PM | 41 days | No | NA | NA | NA | 0
4002 | CARESV1-27765 Reporting & Analytics: M24 (LOE) | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 1479 | 1843 | As Soon As Possible | NA | 41 | -17d | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 41 days | No | NA | NA | NA | 0
4003 | CARESV1-30207 Reporting & Analytics: M26 (LOE) | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 1479 | 1843 | As Soon As Possible | NA | 41 | -17d | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 41 days | No | NA | NA | NA | 0
4004 | CARESV1-21986 Reporting & Analytics: M27 (LOE) | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 1479 | 1843 | As Soon As Possible | NA | 41 | -17d | December 2, 2025 8:00 AM | January 30, 2026 5:00 PM | 41 days | No | NA | NA | NA | 0
4005 | Reporting & Analytics Support (CDI/ KPI) | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 423 | 44d | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 days | No | 2/28/24 | NA | NA | 0.96999999999999997
4006 | CARESV1-34755 Data Pipeline (LOE) | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 2985FS-80d | 1843,3008SS,3009SS,3010SS,3011SS,3012SS,3013SS,3014SS | Start No Earlier Than | 10/30/25 | 423 | 44d | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 days | No | 2/28/24 | NA | NA | 0.96999999999999997
4007 | CARESV1-34757 State & Federal Report Mapping (LOE) | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 3007SS | 1843 | Finish No Earlier Than | 10/30/25 | 423 | 44d | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 days | No | 2/28/24 | NA | NA | 0.96999999999999997
4008 | CARESV1-34759 Data Architecture Layer (LOE) | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 3007SS | 1843 | Finish No Earlier Than | 10/30/25 | 423 | 44d | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 days | No | 2/28/24 | NA | NA | 0.96999999999999997
4009 | CARESV1-34760 Data Extract (LOE) | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 3007SS | 1843 | Finish No Earlier Than | 10/30/25 | 423 | 44d | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 days | No | 2/28/24 | NA | NA | 0.96999999999999997
4010 | CARESV1-34762 Analytical Authorization Layer (LOE) | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 3007SS | 1843 | Finish No Earlier Than | 10/30/25 | 423 | 44d | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 days | No | 2/28/24 | NA | NA | 0.96999999999999997
4011 | CARESV1-34763 Product Metrics (LOE) | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 3007SS | 1843 | Finish No Earlier Than | 10/30/25 | 423 | 44d | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 days | No | 2/28/24 | NA | NA | 0.96999999999999997
4012 | CARESV1-34764 Functional Training Material Support (LOE) | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 3007SS | 1843 | Finish No Earlier Than | 10/30/25 | 423 | 44d | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 days | No | 2/28/24 | NA | NA | 0.96999999999999997
4013 | CARESV1-34765 Data Generation | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 3007SS | 1843 | Finish No Earlier Than | 10/30/25 | 423 | 44d | February 28, 2024 8:00 AM | October 30, 2025 5:00 PM | 423 days | No | 2/28/24 | NA | NA | 0.96999999999999997
6132 | Strategic Communications | January 5, 2023 8:00 AM | February 12, 2027 5:00 PM |  |  | As Soon As Possible | NA | 1029 | 0d | January 5, 2023 8:00 AM | February 12, 2027 5:00 PM | 1029 days | No | 1/5/23 | 2/12/27 | NA | 1
6133 | Collaborative Team Culture | April 1, 2024 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 314 | 0d | April 1, 2024 8:00 AM | June 30, 2025 5:00 PM | 314 days | No | 4/1/24 | 6/30/25 | NA | 1
6134 | CWDS Staff Newsletter, Volume 1 Issue 1 | June 17, 2024 8:00 AM | August 30, 2024 5:00 PM |  | 3018FS+10d | Must Start On | 6/17/24 | 54 | 0d | April 15, 2024 8:00 AM | June 30, 2024 5:00 PM | 54 days | No | 6/17/24 | 8/30/24 | NA | 1
6135 | CWDS Staff Newsletter, Volume 1 Issue 2 | September 16, 2024 8:00 AM | November 27, 2024 5:00 PM | 3017FS+10d | 3019FS+10d | As Soon As Possible | NA | 52 | 0d | July 15, 2024 8:00 AM | September 27, 2024 5:00 PM | 55 days | No | 9/16/24 | 11/27/24 | NA | 1
6136 | CWDS Staff Newsletter, Volume 1 Issue 3 | December 16, 2024 8:00 AM | March 14, 2025 5:00 PM | 3018FS+10d | 3020 | As Soon As Possible | NA | 61 | 0d | October 15, 2024 8:00 AM | December 31, 2024 5:00 PM | 52 days | No | 12/16/24 | 3/14/25 | NA | 1
6137 | CWDS Staff Newsletter, Volume 1 Issue 4 | March 17, 2025 8:00 AM | June 30, 2025 5:00 PM | 3019 | 3021FS-1d | As Soon As Possible | NA | 74 | 0d | January 15, 2025 8:00 AM | March 28, 2025 5:00 PM | 51 days | No | 3/17/25 | 6/30/25 | NA | 1
6138 | Develop Strategic Communications Use Disclaimer & Guidelines | April 1, 2024 8:00 AM | May 31, 2024 5:00 PM | 3020FS-1d | 3022 | As Soon As Possible | NA | 43 | 0d | April 1, 2024 8:00 AM | May 31, 2024 5:00 PM | 43 days | No | 4/1/24 | 5/31/24 | NA | 1
6139 | Strategic Communications Accessibility Guidebook | April 15, 2024 8:00 AM | May 31, 2024 5:00 PM | 3021 | 3023FS+24d | As Soon As Possible | NA | 34 | 0d | April 15, 2024 8:00 AM | May 31, 2024 5:00 PM | 34 days | No | 4/15/24 | 5/31/24 | NA | 1
6140 | CWDS All-staff meeting | July 8, 2024 8:00 AM | October 30, 2024 5:00 PM | 3022FS+24d | 3024FS+16d | As Soon As Possible | NA | 83 | 0d | July 8, 2024 8:00 AM | October 30, 2024 5:00 PM | 83 days | No | 7/8/24 | 10/30/24 | NA | 1
6141 | CWDS Core Values Refresh | November 25, 2024 8:00 AM | June 30, 2025 5:00 PM | 3023FS+16d | 3037 | As Soon As Possible | NA | 148 | 0d | November 25, 2024 8:00 AM | June 30, 2025 5:00 PM | 148 days | No | 11/25/24 | 6/30/25 | NA | 1
6142 | Deliver Messages in Multiple Channels | January 5, 2023 8:00 AM | January 22, 2025 5:00 PM |  |  | As Soon As Possible | NA | 513 | 0d | January 5, 2023 8:00 AM | January 22, 2025 5:00 PM | 513 days | No | 1/5/23 | 1/22/25 | NA | 1
6143 | CARES Compass, Volume 1 Issue 1 | January 5, 2023 8:00 AM | April 2, 2024 5:00 PM |  | 3027 | Must Start On | 1/5/23 | 310 | 0d | January 5, 2023 8:00 AM | April 2, 2024 5:00 PM | 310 days | No | 1/5/23 | 4/2/24 | NA | 1
6144 | CARES Compass, Volume 1 Issue 2 | April 5, 2024 8:00 AM | May 10, 2024 5:00 PM | 3026 | 3028 | As Soon As Possible | NA | 26 | 0d | April 5, 2024 8:00 AM | May 10, 2024 5:00 PM | 26 days | No | 4/5/24 | 5/10/24 | NA | 1
6145 | CARES Compass, Volume 1 Issue 3 | May 23, 2024 8:00 AM | July 17, 2024 5:00 PM | 3027 | 3029FS+4d | As Soon As Possible | NA | 38 | 0d | May 23, 2024 8:00 AM | July 17, 2024 5:00 PM | 38 days | No | 5/23/24 | 7/17/24 | NA | 1
6146 | CARES Compass, Volume 1 Issue 4 | July 24, 2024 8:00 AM | September 20, 2024 5:00 PM | 3028FS+4d | 3030 | As Soon As Possible | NA | 43 | 0d | July 24, 2024 8:00 AM | September 20, 2024 5:00 PM | 43 days | No | 7/24/24 | 9/20/24 | NA | 1
6147 | CARES Explorer, Volume 1 - Issue 1 | January 15, 2024 8:00 AM | April 3, 2024 5:00 PM | 3029 | 3031 | As Soon As Possible | NA | 55 | 0d | January 15, 2024 8:00 AM | April 3, 2024 5:00 PM | 55 days | No | 1/15/24 | 4/3/24 | NA | 1
6148 | CARES Explorer, Volume 1 - Issue 2 | April 5, 2024 8:00 AM | June 28, 2024 5:00 PM | 3030 | 3032FS+9d | As Soon As Possible | NA | 60 | 0d | April 5, 2024 8:00 AM | June 30, 2024 5:00 PM | 60 days | No | 4/5/24 | 6/28/24 | NA | 1
6149 | CARES Explorer, Volume 1 - Issue 3 | July 15, 2024 8:00 AM | September 27, 2024 5:00 PM | 3031FS+9d | 3033FS+5d | As Soon As Possible | NA | 55 | 0d | July 15, 2024 8:00 AM | September 27, 2024 5:00 PM | 55 days | No | 7/15/24 | 9/27/24 | NA | 1
6150 | CARES Explorer, Volume 1 - Issue 4 | October 7, 2024 8:00 AM | December 31, 2024 5:00 PM | 3032FS+5d | 3034FS-221d | As Soon As Possible | NA | 58 | 0d | October 7, 2024 8:00 AM | December 31, 2024 5:00 PM | 58 days | No | 10/7/24 | 12/31/24 | NA | 1
6151 | CWS-CARES Stakeholder Briefing #1 | February 15, 2024 8:00 AM | June 28, 2024 5:00 PM | 3033FS-221d | 3035FS+116d | As Soon As Possible | NA | 94 | 0d | February 15, 2024 8:00 AM | June 28, 2024 5:00 PM | 94 days | No | 2/15/24 | 6/28/24 | NA | 1
6152 | CWS-CARES Stakeholder Briefing #2 | December 16, 2024 8:00 AM | January 22, 2025 5:00 PM | 3034FS+116d | 3041FS-76d | As Soon As Possible | NA | 25 | 0d | December 16, 2024 8:00 AM | January 22, 2025 5:00 PM | 25 days | No | 12/16/24 | 1/22/25 | NA | 1
6153 | Diverse Stakeholder Materials | November 27, 2023 8:00 AM | February 12, 2027 5:00 PM |  |  | As Soon As Possible | NA | 806 | 0d | November 26, 2023 8:00 AM | February 12, 2027 5:00 PM | 806 days | No | 11/27/23 | 2/12/27 | NA | 1
6154 | Updated CWS-CARES Strategic Plan for Stakeholder Management, Communications and Adoption | November 27, 2023 8:00 AM | April 3, 2024 5:00 PM | 3024 | 3038 | As Soon As Possible | NA | 88 | 0d | November 26, 2023 8:00 AM | April 3, 2024 5:00 PM | 88 days | No | 11/27/23 | 4/3/24 | NA | 1
6155 | CWS-CARES Public Library for existing project materials accessible by CWDS website | February 3, 2025 8:00 AM | February 12, 2027 5:00 PM | 3037 | 3040 | Finish No Earlier Than | 2/12/27 | 509 | 0d | February 3, 2025 8:00 AM | February 12, 2027 5:00 PM | 509 days | No | 2/3/25 | 2/12/27 | NA | 1
6156 | Establish A Unified CARES Brand | October 2, 2023 8:00 AM | January 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 333 | 0d | October 1, 2023 8:00 AM | January 30, 2025 5:00 PM | 333 days | No | 10/2/23 | 1/30/25 | NA | 1
6157 | Develop CWS-CARES Style Guide | October 2, 2023 8:00 AM | May 1, 2024 5:00 PM | 3038 | 3041 | As Soon As Possible | NA | 145 | 0d | October 1, 2023 8:00 AM | May 1, 2024 5:00 PM | 145 days | No | 10/2/23 | 5/1/24 | NA | 1
6158 | Establish a CWS-CARES Branded Merchandise Store | October 1, 2024 8:00 AM | January 30, 2025 5:00 PM | 3040,3035FS-76d | 3043 | Start No Earlier Than | 10/1/24 | 82 | 0d | October 1, 2024 8:00 AM | January 30, 2025 5:00 PM | 82 days | No | 10/1/24 | 1/30/25 | NA | 1
6159 | Measure Effectiveness | December 15, 2023 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 302 | 0d | December 15, 2023 8:00 AM | February 28, 2025 5:00 PM | 302 days | No | 12/15/23 | 2/28/25 | NA | 1
6160 | External Baseline Communication Survey | December 15, 2023 8:00 AM | February 29, 2024 5:00 PM | 3041 | 3044 | Start No Earlier Than | 12/15/23 | 51 | 0d | December 15, 2023 8:00 AM | February 29, 2024 5:00 PM | 51 days | No | 12/15/23 | 2/29/24 | NA | 1
6161 | Create Strategic Communications Effectiveness and User Engagement Dashboard | March 1, 2024 8:00 AM | October 30, 2024 5:00 PM | 3043 | 3045FS-98d | As Soon As Possible | NA | 171 | 0d | March 1, 2024 8:00 AM | October 30, 2024 5:00 PM | 171 days | No | 3/1/24 | 10/30/24 | NA | 1
6162 | Annual Report on Communication Effectiveness | June 14, 2024 8:00 AM | August 29, 2024 5:00 PM | 3044FS-98d | 3046FS-84d | As Soon As Possible | NA | 54 | 0d | June 14, 2024 8:00 AM | August 29, 2024 5:00 PM | 54 days | No | 6/14/24 | 8/29/24 | NA | 1
6163 | CWDS staff survey on Newsletter and Internal Communications | May 2, 2024 8:00 AM | June 28, 2024 5:00 PM | 3045FS-84d | 3047FS-42d | As Soon As Possible | NA | 41 | 0d | May 2, 2024 8:00 AM | June 28, 2024 5:00 PM | 41 days | No | 5/2/24 | 6/28/24 | NA | 1
6164 | ACF Metrics to address the Administration for Children and Families (ACF) report to measure user engagement and adoption | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM | 3046FS-42d | 3048FS-22d | As Soon As Possible | NA | 22 | 0d | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM | 22 days | No | 5/1/24 | 5/31/24 | NA | 1
6165 | User Sentiment Surveys | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM | 3047FS-22d | 3049FS+136d | As Soon As Possible | NA | 22 | 0d | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM | 22 days | No | 5/1/24 | 5/31/24 | NA | 1
6166 | Annual Communication Survey for External Audiences | December 16, 2024 8:00 AM | February 28, 2025 5:00 PM | 3048FS+136d | 5628 | As Soon As Possible | NA | 51 | 0d | December 16, 2024 8:00 AM | February 28, 2025 5:00 PM | 51 days | No | 12/16/24 | 2/28/25 | NA | 1
13228 | Consolidated Self Assessments (C-SA) | January 2, 2025 8:00 AM | December 15, 2026 5:00 PM |  |  | As Soon As Possible | NA | 490 | 206d | NA | NA | 0 days? | No | 1/2/25 | NA | NA | 0.34999999999999998
13229 | C-SA ACF Reporting 2025 | January 2, 2025 8:00 AM | December 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 240 | 456d | NA | NA | 0 days? | No | 1/2/25 | NA | NA | 0.75
13244 | Q1 C-SA ACF Reporting 2025 | January 2, 2025 8:00 AM | April 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 74 | 0d | NA | NA | 0 days? | No | 1/2/25 | 4/18/25 | NA | 1
13245 | Initiate Q1 ACF reporting of C-SA to all Stakeholders | January 2, 2025 8:00 AM | January 2, 2025 5:00 PM |  | 3054 | Start No Earlier Than | 1/2/25 | 1 | 0d | NA | NA | 0 s? | No | 1/2/25 | 1/2/25 | NA | 1
13246 | Create Initial Draft of Q1 C-SA | January 3, 2025 8:00 AM | January 21, 2025 5:00 PM | 3053 | 3055 | As Soon As Possible | NA | 12 | 0d | NA | NA | 0 days? | No | 1/3/25 | 1/21/25 | NA | 1
13247 | Request Review / Approval from Service Managers (SMs) for Q1 C-SA | January 22, 2025 8:00 AM | February 6, 2025 5:00 PM | 3054 | 3056 | As Soon As Possible | NA | 12 | 0d | NA | NA | 0 days? | No | 1/22/25 | 2/6/25 | NA | 1
13266 | Update Draft Q1 C-SA w/ SM Feedback | February 7, 2025 8:00 AM | February 25, 2025 5:00 PM | 3055 | 3057 | As Soon As Possible | NA | 12 | 0d | NA | NA | 0 days? | No | 2/7/25 | 2/25/25 | NA | 1
13267 | Request Collaborated Responses from project teams: PaaS, PVS, CDI,& Product for Q1 C-SA | February 26, 2025 8:00 AM | March 7, 2025 5:00 PM | 3056 | 3058 | As Soon As Possible | NA | 8 | 0d | NA | NA | 0 days? | No | 2/26/25 | 3/7/25 | NA | 1
13295 | Conduct Status Checkpoint – Create Second Draft of Q1 C-SA | March 10, 2025 8:00 AM | March 10, 2025 5:00 PM | 3057 | 3059,3060FS+11d | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 3/10/25 | 3/10/25 | NA | 1
13296 | Request Pre-liminary Review& Feedback from Product & Technology Leadership of Q1 C-SA | March 11, 2025 8:00 AM | March 24, 2025 5:00 PM | 3058 | 3061,3063 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 3/11/25 | 3/24/25 | NA | 1
13297 | Request Final Review& Approval from Service Managers (SMs) of Q1 C-SA | March 26, 2025 8:00 AM | April 4, 2025 5:00 PM | 3058FS+11d | 3061 | As Soon As Possible | NA | 7 | 0d | NA | NA | 0 days? | No | 3/26/25 | 4/4/25 | NA | 1
13298 | Proofread Final Draft of Q1 C-SA w/ Pre-liminary Feedback | April 7, 2025 8:00 AM | April 11, 2025 5:00 PM | 3059,3060 | 3062SS+1d | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 4/7/25 | 4/11/25 | NA | 1
13299 | Meet with Product& Technology Leadership prior to requesting ELT Approval | April 8, 2025 8:00 AM | April 8, 2025 5:00 PM | 3061SS+1d |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 4/8/25 | 4/8/25 | NA | 1
13300 | Request Final Review/Approval from Product& Technology Leadership of Q1 C-SA | March 25, 2025 8:00 AM | April 8, 2025 5:00 PM | 3059 | 3064 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 3/25/25 | 4/8/25 | NA | 1
13301 | Finalize All Documents to Request ELT Approval of Q1 C-SA – target noon | April 9, 2025 8:00 AM | April 9, 2025 5:00 PM | 3063 | 3065 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 4/9/25 | 4/9/25 | NA | 1
13302 | Request Final Review/Approval from ELT of Q1 C-SA | April 10, 2025 8:00 AM | April 17, 2025 5:00 PM | 3064 | 3066FS-1d | As Soon As Possible | NA | 6 | 0d | NA | NA | 0 days? | No | 4/10/25 | 4/17/25 | NA | 1
13303 | Submit ELT Approved Q1 C-SA to ACF | April 17, 2025 8:00 AM | April 18, 2025 5:00 PM | 3065FS-1d | 3067FS-1d | As Soon As Possible | NA | 2 | 0d | NA | NA | 0 days? | No | 4/17/25 | 4/18/25 | NA | 1
13304 | Closeout Q1 C-SA process | April 18, 2025 8:00 AM | April 18, 2025 5:00 PM | 3066FS-1d | 3068 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 4/18/25 | 4/18/25 | NA | 1
13305 | Q2 C-SA ACF Reporting 2025 (Not Required) | April 21, 2025 8:00 AM | April 21, 2025 5:00 PM | 3067 |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 4/21/25 | 4/21/25 | NA | 1
13306 | Q3 C-SA ACF Reporting 2025 | July 16, 2025 8:00 AM | September 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/16/25 | 9/15/25 | NA | 1
13307 | Initiate Q3 ACF reporting of C-SA with all resources | July 16, 2025 8:00 AM | July 16, 2025 5:00 PM |  | 3071 | Start No Earlier Than | 7/16/25 | 1 | 0d | NA | NA | 0 s? | No | 7/16/25 | 7/16/25 | NA | 1
13308 | Create Q3 C-SA draft & share SharePoint location with all resources | July 17, 2025 8:00 AM | July 17, 2025 5:00 PM | 3070 | 3072 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 7/17/25 | 7/17/25 | NA | 1
13309 | 1st review of Q3 C-SA by PaaS, PVS, & CDI teams to provide collaborated responses | July 18, 2025 8:00 AM | July 23, 2025 5:00 PM | 3071 | 3073 | As Soon As Possible | NA | 4 | 0d | NA | NA | 0 days? | No | 7/18/25 | 7/23/25 | NA | 1
13310 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q3 C-SA status | July 24, 2025 8:00 AM | July 24, 2025 5:00 PM | 3072 | 3074 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 7/24/25 | 7/24/25 | NA | 1
13311 | 1st review of Q3 C-SA by Service Managers (SMs) to review, edit & comment | July 25, 2025 8:00 AM | July 30, 2025 5:00 PM | 3073 | 3075 | As Soon As Possible | NA | 4 | 0d | NA | NA | 0 days? | No | 7/25/25 | 7/30/25 | NA | 1
13312 | Conduct Checkpoint w/ SMs for Q3 C-SA status | July 31, 2025 8:00 AM | July 31, 2025 5:00 PM | 3074 | 3076 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 7/31/25 | 7/31/25 | NA | 1
13313 | 2nd review of Q3 C-SA by PaaS, PVS, & CDI teams to proofread collaborated responses | August 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 3075 | 3077 | As Soon As Possible | NA | 4 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/6/25 | NA | 1
13314 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q3 C-SA status | August 7, 2025 8:00 AM | August 7, 2025 5:00 PM | 3076 | 3078FS+1d | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 8/7/25 | 8/7/25 | NA | 1
13315 | 1st pre-liminary review & feedback of Q3 C-SA by Product & Technology Leadership | August 11, 2025 8:00 AM | August 14, 2025 5:00 PM | 3077FS+1d | 3079 | As Soon As Possible | NA | 4 | 0d | NA | NA | 0 days? | No | 8/11/25 | 8/14/25 | NA | 1
13316 | 2nd & final review & approval of Q3 C-SA by Service Managers (SMs) | August 14, 2025 8:00 AM | August 19, 2025 5:00 PM | 3078 | 3080 | As Soon As Possible | NA | 4 | 0d | NA | NA | 0 days? | No | 8/14/25 | 8/19/25 | NA | 1
13317 | Conduct Checkpoint w/ Product & Technology Leadership | August 20, 2025 8:00 AM | August 20, 2025 5:00 PM | 3079 | 3081 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 8/20/25 | 8/20/25 | NA | 1
13318 | 3rd & final review & approval of Q3 C-SA by PaaS, PVS, & CDI teams | August 21, 2025 8:00 AM | August 25, 2025 5:00 PM | 3080 | 3082 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 8/21/25 | 8/25/25 | NA | 1
13268 | Conduct status checkpoint w/ Leads from PaaS, PVS, & CDI for Q3 C-SA status | August 26, 2025 8:00 AM | August 26, 2025 5:00 PM | 3081 | 3083 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 8/26/25 | 8/26/25 | NA | 1
13269 | 2nd & final review & approval of Q3 C-SA by Product & Technology Leadership | August 27, 2025 8:00 AM | August 29, 2025 5:00 PM | 3082 | 3084 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 8/27/25 | 8/29/25 | NA | 1
13270 | Conduct final status checkpoint w/ Product & Technology Leadership for Q3 C-SA | September 2, 2025 8:00 AM | September 2, 2025 5:00 PM | 3083 | 3085 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 9/2/25 | 9/2/25 | NA | 1
13271 | Conduct final readiness check of Q3 C-SA to request ELT Approval | September 3, 2025 8:00 AM | September 4, 2025 5:00 PM | 3084 | 3086 | As Soon As Possible | NA | 2 | 0d | NA | NA | 0 days? | No | 9/3/25 | 9/4/25 | NA | 1
13272 | Request review & approval from ELT of Q3 C-SA | September 5, 2025 8:00 AM | September 11, 2025 5:00 PM | 3085 | 3087 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 9/5/25 | 9/11/25 | NA | 1
13273 | Submit ELT approved Q3 C-SA to PMO for Filing | September 12, 2025 8:00 AM | September 12, 2025 5:00 PM | 3086 | 3088 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 9/12/25 | 9/12/25 | NA | 1
13274 | Closeout Q3 C-SA process | September 15, 2025 8:00 AM | September 15, 2025 5:00 PM | 3087 |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 9/15/25 | 9/15/25 | NA | 1
13275 | Q4 C-SA ACF Reporting 2025 | October 14, 2025 8:00 AM | December 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 456d | NA | NA | 0 days? | No | NA | NA | NA | 0
13276 | Initiate Q4 ACF reporting of C-SA with all resources | October 14, 2025 8:00 AM | October 14, 2025 5:00 PM |  | 3091 | Start No Earlier Than | 10/14/25 | 1 | 456d | NA | NA | 0 s? | No | NA | NA | NA | 0
13277 | Create Q4 C-SA draft & share SharePoint location with all resources | October 15, 2025 8:00 AM | October 15, 2025 5:00 PM | 3090 | 3092 | As Soon As Possible | NA | 1 | 456d | NA | NA | 0 s? | No | NA | NA | NA | 0
13278 | 1st review of Q4 C-SA by PaaS, PVS, & CDI teams to provide collaborated responses | October 16, 2025 8:00 AM | October 21, 2025 5:00 PM | 3091 | 3093 | As Soon As Possible | NA | 4 | 456d | NA | NA | 0 days? | No | NA | NA | NA | 0
13279 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q4 C-SA status | October 22, 2025 8:00 AM | October 22, 2025 5:00 PM | 3092 | 3094 | As Soon As Possible | NA | 1 | 456d | NA | NA | 0 s? | No | NA | NA | NA | 0
13280 | 1st review of Q4 C-SA by Service Managers (SMs) to review, edit & comment | October 23, 2025 8:00 AM | October 28, 2025 5:00 PM | 3093 | 3095 | As Soon As Possible | NA | 4 | 456d | NA | NA | 0 days? | No | NA | NA | NA | 0
13281 | Conduct Checkpoint w/ SMs for Q4 C-SA status | October 29, 2025 8:00 AM | October 29, 2025 5:00 PM | 3094 | 3096 | As Soon As Possible | NA | 1 | 456d | NA | NA | 0 s? | No | NA | NA | NA | 0
13282 | 2nd review of Q4 C-SA by PaaS, PVS, & CDI teams to proofread collaborated responses | October 30, 2025 8:00 AM | November 4, 2025 5:00 PM | 3095 | 3097 | As Soon As Possible | NA | 4 | 456d | NA | NA | 0 days? | No | NA | NA | NA | 0
13283 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q4 C-SA status | November 5, 2025 8:00 AM | November 5, 2025 5:00 PM | 3096 | 3098 | As Soon As Possible | NA | 1 | 456d | NA | NA | 0 s? | No | NA | NA | NA | 0
13284 | 1st pre-liminary review & feedback of Q4 C-SA by Product & Technology Leadership | November 6, 2025 8:00 AM | November 12, 2025 5:00 PM | 3097 | 3099 | As Soon As Possible | NA | 4 | 456d | NA | NA | 0 days? | No | NA | NA | NA | 0
13285 | 2nd & final review & approval of Q4 C-SA by Service Managers (SMs) | November 13, 2025 8:00 AM | November 18, 2025 5:00 PM | 3098 | 3100 | As Soon As Possible | NA | 4 | 456d | NA | NA | 0 days? | No | NA | NA | NA | 0
13286 | Conduct Checkpoint w/ Product & Technology Leadership | November 19, 2025 8:00 AM | November 19, 2025 5:00 PM | 3099 | 3101 | As Soon As Possible | NA | 1 | 456d | NA | NA | 0 s? | No | NA | NA | NA | 0
13287 | 3rd & final review & approval of Q4 C-SA by PaaS, PVS, & CDI teams | November 20, 2025 8:00 AM | November 25, 2025 5:00 PM | 3100 | 3102 | As Soon As Possible | NA | 4 | 456d | NA | NA | 0 days? | No | NA | NA | NA | 0
13288 | Conduct status checkpoint w/ Leads from PaaS, PVS, & CDI for Q4 C-SA status | November 26, 2025 8:00 AM | November 26, 2025 5:00 PM | 3101 | 3103 | As Soon As Possible | NA | 1 | 456d | NA | NA | 0 s? | No | NA | NA | NA | 0
13289 | 2nd & final review & approval of Q4 C-SA by Product & Technology Leadership | November 28, 2025 8:00 AM | December 3, 2025 5:00 PM | 3102 | 3104 | As Soon As Possible | NA | 4 | 456d | NA | NA | 0 days? | No | NA | NA | NA | 0
13290 | Conduct final status checkpoint w/ Product & Technology Leadership for Q4 C-SA | December 4, 2025 8:00 AM | December 4, 2025 5:00 PM | 3103 | 3105 | As Soon As Possible | NA | 1 | 456d | NA | NA | 0 s? | No | NA | NA | NA | 0
13291 | Conduct final readiness check of Q4 C-SA to request ELT Approval | December 5, 2025 8:00 AM | December 8, 2025 5:00 PM | 3104 | 3106 | As Soon As Possible | NA | 2 | 456d | NA | NA | 0 days? | No | NA | NA | NA | 0
13292 | Request review & approval from ELT of Q4 C-SA | December 9, 2025 8:00 AM | December 12, 2025 5:00 PM | 3105 | 3107FS-1d | As Soon As Possible | NA | 4 | 456d | NA | NA | 0 days? | No | NA | NA | NA | 0
13293 | Submit ELT approved Q4 C-SA to PMO Filing | December 12, 2025 8:00 AM | December 12, 2025 5:00 PM | 3106FS-1d | 3108 | As Soon As Possible | NA | 1 | 456d | NA | NA | 0 s? | No | NA | NA | NA | 0
13294 | Closeout Q4 C-SA process | December 15, 2025 8:00 AM | December 15, 2025 5:00 PM | 3107 |  | As Soon As Possible | NA | 1 | 456d | NA | NA | 0 s? | No | NA | NA | NA | 0
13248 | C-SA ACF Reporting 2026 | January 5, 2026 8:00 AM | December 15, 2026 5:00 PM |  |  | As Soon As Possible | NA | 238 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13249 | Q1 C-SA ACF Reporting 2026 | January 5, 2026 8:00 AM | April 17, 2026 5:00 PM |  |  | As Soon As Possible | NA | 72 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13250 | Initiate Q1 ACF reporting of C-SA with all resources | January 5, 2026 8:00 AM | January 5, 2026 5:00 PM |  | 3112 | Start No Earlier Than | 1/5/26 | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13251 | Create Q1 C-SA draft & share SharePoint location with all resources | January 6, 2026 8:00 AM | January 20, 2026 5:00 PM | 3111 | 3113 | As Soon As Possible | NA | 10 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13252 | 1st review of Q1 C-SA by PaaS, PVS, & CDI teams to provide collaborated responses | January 21, 2026 8:00 AM | January 29, 2026 5:00 PM | 3112 | 3114 | As Soon As Possible | NA | 7 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13253 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q1 C-SA status | January 30, 2026 8:00 AM | February 10, 2026 5:00 PM | 3113 | 3115 | As Soon As Possible | NA | 8 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13254 | 1st review of Q1 C-SA by Service Managers (SMs) to review, edit & comment | February 11, 2026 8:00 AM | February 18, 2026 5:00 PM | 3114 | 3116 | As Soon As Possible | NA | 5 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13255 | Conduct Checkpoint w/ SMs for Q1 C-SA status | February 19, 2026 8:00 AM | February 19, 2026 5:00 PM | 3115 | 3117 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13256 | 2nd review of Q1 C-SA by PaaS, PVS, & CDI teams to proofread collaborated responses | February 20, 2026 8:00 AM | February 26, 2026 5:00 PM | 3116 | 3118 | As Soon As Possible | NA | 5 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13257 | Conduct checkpoint w/ Leads from PaaS, PVS,& CDI for Q1 C-SA status | February 27, 2026 8:00 AM | March 5, 2026 5:00 PM | 3117 | 3119 | As Soon As Possible | NA | 5 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13258 | 1st pre-liminary review & feedback of Q1 C-SA by Product & Technology Leadership | March 6, 2026 8:00 AM | March 6, 2026 5:00 PM | 3118 | 3120 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13259 | 2nd& final review & approval of Q1 C-SA by Service Managers (SMs) | March 9, 2026 8:00 AM | March 13, 2026 5:00 PM | 3119 | 3121 | As Soon As Possible | NA | 5 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13260 | Conduct Checkpoint w/ Product& Technology Leadership | March 16, 2026 8:00 AM | March 16, 2026 5:00 PM | 3120 | 3122 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13261 | 3rd & final review & approval of Q1 C-SA by PaaS, PVS, & CDI teams | March 17, 2026 8:00 AM | March 25, 2026 5:00 PM | 3121 | 3123 | As Soon As Possible | NA | 7 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13262 | Conduct status checkpoint w/ Leads from PaaS, PVS, & CDI for Q1 C-SA status | March 26, 2026 8:00 AM | March 26, 2026 5:00 PM | 3122 | 3124 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13263 | 2nd& final review & approval of Q1 C-SA by Product & Technology Leadership | March 27, 2026 8:00 AM | April 3, 2026 5:00 PM | 3123 | 3125 | As Soon As Possible | NA | 5 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13264 | Conduct final status checkpoint w/ Product & Technology Leadership for Q1 C-SA | April 6, 2026 8:00 AM | April 7, 2026 5:00 PM | 3124 | 3126 | As Soon As Possible | NA | 2 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13265 | Conduct final readiness check of Q1 C-SA to request ELT Approval | April 8, 2026 8:00 AM | April 8, 2026 5:00 PM | 3125 | 3127 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13230 | Request review & approval from ELT of Q1 C-SA | April 9, 2026 8:00 AM | April 15, 2026 5:00 PM | 3126 | 3128 | As Soon As Possible | NA | 5 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13231 | Submit ELT approved Q1 C-SA to ACF | April 16, 2026 8:00 AM | April 16, 2026 5:00 PM | 3127 | 3129 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13232 | Closeout Q1 C-SA process | April 17, 2026 8:00 AM | April 17, 2026 5:00 PM | 3128 | 3131 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13233 | Q2 C-SA ACF Reporting 2026 | April 20, 2026 8:00 AM | June 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 41 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13562 | Initiate Q2 ACF reporting of C-SA with all resources | April 20, 2026 8:00 AM | April 20, 2026 5:00 PM | 3129 | 3132 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13563 | Create Q2 C-SA draft & share SharePoint location with all resources | April 21, 2026 8:00 AM | April 23, 2026 5:00 PM | 3131 | 3133 | As Soon As Possible | NA | 3 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13564 | 1st review of Q2 C-SA by PaaS, PVS, & CDI teams to provide collaborated responses | April 24, 2026 8:00 AM | April 29, 2026 5:00 PM | 3132 | 3134 | As Soon As Possible | NA | 4 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13565 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q2 C-SA status | April 30, 2026 8:00 AM | May 1, 2026 5:00 PM | 3133 | 3135 | As Soon As Possible | NA | 2 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13566 | 1st review of Q2 C-SA by Service Managers (SMs) to review, edit & comment | May 4, 2026 8:00 AM | May 6, 2026 5:00 PM | 3134 | 3136 | As Soon As Possible | NA | 3 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13567 | Conduct Checkpoint w/ SMs for Q2 C-SA status | May 7, 2026 8:00 AM | May 7, 2026 5:00 PM | 3135 | 3137 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13568 | 2nd review of Q2 C-SA by PaaS, PVS, & CDI teams to proofread collaborated responses | May 8, 2026 8:00 AM | May 12, 2026 5:00 PM | 3136 | 3138 | As Soon As Possible | NA | 3 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13569 | Conduct checkpoint w/ Leads from PaaS, PVS,& CDI for Q2 C-SA status | May 13, 2026 8:00 AM | May 18, 2026 5:00 PM | 3137 | 3139 | As Soon As Possible | NA | 4 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13585 | 1st pre-liminary review & feedback of Q2 C-SA by Product & Technology Leadership | May 19, 2026 8:00 AM | May 19, 2026 5:00 PM | 3138 | 3140 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13586 | 2nd& final review & approval of Q2 C-SA by Service Managers (SMs) | May 20, 2026 8:00 AM | May 22, 2026 5:00 PM | 3139 | 3141 | As Soon As Possible | NA | 3 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13587 | Conduct Checkpoint w/ Product& Technology Leadership | May 26, 2026 8:00 AM | May 26, 2026 5:00 PM | 3140 | 3142 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13588 | 3rd & final review & approval of Q2 C-SA by PaaS, PVS, & CDI teams | May 27, 2026 8:00 AM | May 29, 2026 5:00 PM | 3141 | 3143 | As Soon As Possible | NA | 3 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13589 | Conduct status checkpoint w/ Leads from PaaS, PVS, & CDI for Q2 C-SA status | June 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 3142 | 3144 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13590 | 2nd& final review & approval of Q2 C-SA by Product & Technology Leadership | June 2, 2026 8:00 AM | June 5, 2026 5:00 PM | 3143 | 3145 | As Soon As Possible | NA | 4 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13591 | Conduct final status checkpoint w/ Product & Technology Leadership for Q2 C-SA | June 8, 2026 8:00 AM | June 8, 2026 5:00 PM | 3144 | 3146 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13592 | Conduct final readiness check of Q2 C-SA to request ELT Approval | June 9, 2026 8:00 AM | June 9, 2026 5:00 PM | 3145 | 3147 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13593 | Request review & approval from ELT of Q2 C-SA | June 10, 2026 8:00 AM | June 15, 2026 5:00 PM | 3146 | 3148FS-1d | As Soon As Possible | NA | 4 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13594 | Submit ELT approved Q2 C-SA to PMO Filing | June 15, 2026 8:00 AM | June 15, 2026 5:00 PM | 3147FS-1d | 3149 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13595 | Closeout Q2 C-SA process | June 16, 2026 8:00 AM | June 16, 2026 5:00 PM | 3148 | 3151FS+18d | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13596 | Q3 C-SA ACF Reporting 2026 | July 14, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | As Soon As Possible | NA | 45 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13597 | Initiate Q3 ACF reporting of C-SA with all resources | July 14, 2026 8:00 AM | July 14, 2026 5:00 PM | 3149FS+18d | 3152 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13598 | Create Q3 C-SA draft & share SharePoint location with all resources | July 15, 2026 8:00 AM | July 17, 2026 5:00 PM | 3151 | 3153 | As Soon As Possible | NA | 3 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13599 | 1st review of Q3 C-SA by PaaS, PVS, & CDI teams to provide collaborated responses | July 20, 2026 8:00 AM | July 23, 2026 5:00 PM | 3152 | 3154 | As Soon As Possible | NA | 4 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13600 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q3 C-SA status | July 24, 2026 8:00 AM | July 27, 2026 5:00 PM | 3153 | 3155 | As Soon As Possible | NA | 2 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13601 | 1st review of Q3 C-SA by Service Managers (SMs) to review, edit & comment | July 28, 2026 8:00 AM | July 31, 2026 5:00 PM | 3154 | 3156 | As Soon As Possible | NA | 4 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13602 | Conduct Checkpoint w/ SMs for Q3 C-SA status | August 3, 2026 8:00 AM | August 3, 2026 5:00 PM | 3155 | 3157 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13603 | 2nd review of Q3 C-SA by PaaS, PVS, & CDI teams to proofread collaborated responses | August 4, 2026 8:00 AM | August 7, 2026 5:00 PM | 3156 | 3158 | As Soon As Possible | NA | 4 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13570 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q3 C-SA status | August 10, 2026 8:00 AM | August 13, 2026 5:00 PM | 3157 | 3159 | As Soon As Possible | NA | 4 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13571 | 1st pre-liminary review & feedback of Q3 C-SA by Product & Technology Leadership | August 14, 2026 8:00 AM | August 14, 2026 5:00 PM | 3158 | 3160 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13572 | 2nd & final review & approval of Q3 C-SA by Service Managers (SMs) | August 17, 2026 8:00 AM | August 19, 2026 5:00 PM | 3159 | 3161 | As Soon As Possible | NA | 3 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13573 | Conduct Checkpoint w/ Product & Technology Leadership | August 20, 2026 8:00 AM | August 20, 2026 5:00 PM | 3160 | 3162 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13574 | 3rd & final review & approval of Q3 C-SA by PaaS, PVS, & CDI teams | August 21, 2026 8:00 AM | August 26, 2026 5:00 PM | 3161 | 3163 | As Soon As Possible | NA | 4 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13575 | Conduct status checkpoint w/ Leads from PaaS, PVS, & CDI for Q3 C-SA status | August 27, 2026 8:00 AM | August 27, 2026 5:00 PM | 3162 | 3164 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13576 | 2nd & final review & approval of Q3 C-SA by Product & Technology Leadership | August 28, 2026 8:00 AM | September 2, 2026 5:00 PM | 3163 | 3165 | As Soon As Possible | NA | 4 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13577 | Conduct final status checkpoint w/ Product & Technology Leadership for Q3 C-SA | September 3, 2026 8:00 AM | September 3, 2026 5:00 PM | 3164 | 3166 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13578 | Conduct final readiness check of Q3 C-SA to request ELT Approval | September 4, 2026 8:00 AM | September 4, 2026 5:00 PM | 3165 | 3167 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13579 | Request review & approval from ELT of Q3 C-SA | September 8, 2026 8:00 AM | September 14, 2026 5:00 PM | 3166 | 3168FS-1d | As Soon As Possible | NA | 5 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13580 | Submit ELT approved Q3 C-SA to PMO Filing | September 14, 2026 8:00 AM | September 14, 2026 5:00 PM | 3167FS-1d | 3169 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13581 | Closeout Q3 C-SA process | September 15, 2026 8:00 AM | September 15, 2026 5:00 PM | 3168 | 3171FS+20d | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13582 | Q4 C-SA ACF Reporting 2026 | October 14, 2026 8:00 AM | December 15, 2026 5:00 PM |  |  | As Soon As Possible | NA | 42 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13583 | Initiate Q4 ACF reporting of C-SA with all resources | October 14, 2026 8:00 AM | October 14, 2026 5:00 PM | 3169FS+20d | 3172 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13584 | Create Q4 C-SA draft & share SharePoint location with all resources | October 15, 2026 8:00 AM | October 19, 2026 5:00 PM | 3171 | 3173 | As Soon As Possible | NA | 3 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13234 | 1st review of Q4 C-SA by PaaS, PVS, & CDI teams to provide collaborated responses | October 20, 2026 8:00 AM | October 23, 2026 5:00 PM | 3172 | 3174 | As Soon As Possible | NA | 4 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13235 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q4 C-SA status | October 26, 2026 8:00 AM | October 27, 2026 5:00 PM | 3173 | 3175 | As Soon As Possible | NA | 2 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13236 | 1st review of Q4 C-SA by Service Managers (SMs) to review, edit & comment | October 28, 2026 8:00 AM | November 2, 2026 5:00 PM | 3174 | 3176 | As Soon As Possible | NA | 4 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13237 | Conduct Checkpoint w/ SMs for Q4 C-SA status | November 3, 2026 8:00 AM | November 3, 2026 5:00 PM | 3175 | 3177 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13238 | 2nd review of Q4 C-SA by PaaS, PVS, & CDI teams to proofread collaborated responses | November 4, 2026 8:00 AM | November 6, 2026 5:00 PM | 3176 | 3178 | As Soon As Possible | NA | 3 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13239 | Conduct checkpoint w/ Leads from PaaS, PVS, & CDI for Q4 C-SA status | November 9, 2026 8:00 AM | November 12, 2026 5:00 PM | 3177 | 3179 | As Soon As Possible | NA | 3 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13240 | 1st pre-liminary review & feedback of Q4 C-SA by Product & Technology Leadership | November 13, 2026 8:00 AM | November 13, 2026 5:00 PM | 3178 | 3180 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13241 | 2nd & final review & approval of Q4 C-SA by Service Managers (SMs) | November 16, 2026 8:00 AM | November 18, 2026 5:00 PM | 3179 | 3181 | As Soon As Possible | NA | 3 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13242 | Conduct Checkpoint w/ Product & Technology Leadership | November 19, 2026 8:00 AM | November 19, 2026 5:00 PM | 3180 | 3182 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13243 | 3rd & final review & approval of Q4 C-SA by PaaS, PVS, & CDI teams | November 20, 2026 8:00 AM | November 25, 2026 5:00 PM | 3181 | 3183 | As Soon As Possible | NA | 4 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13220 | Conduct status checkpoint w/ Leads from PaaS, PVS, & CDI for Q4 C-SA status | November 30, 2026 8:00 AM | November 30, 2026 5:00 PM | 3182 | 3184 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13221 | 2nd & final review & approval of Q4 C-SA by Product & Technology Leadership | December 1, 2026 8:00 AM | December 4, 2026 5:00 PM | 3183 | 3185 | As Soon As Possible | NA | 4 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13222 | Conduct final status checkpoint w/ Product & Technology Leadership for Q4 C-SA | December 7, 2026 8:00 AM | December 7, 2026 5:00 PM | 3184 | 3186 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13223 | Conduct final readiness check of Q4 C-SA to request ELT Approval | December 8, 2026 8:00 AM | December 8, 2026 5:00 PM | 3185 | 3187 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13224 | Request review & approval from ELT of Q4 C-SA | December 9, 2026 8:00 AM | December 14, 2026 5:00 PM | 3186 | 3188FS-1d | As Soon As Possible | NA | 4 | 206d | NA | NA | 0 days? | No | NA | NA | NA | 0
13225 | Submit ELT approved Q4 C-SA to PMO Filing | December 14, 2026 8:00 AM | December 14, 2026 5:00 PM | 3187FS-1d | 3189 | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
13226 | Closeout Q4 C-SA process | December 15, 2026 8:00 AM | December 15, 2026 5:00 PM | 3188 |  | As Soon As Possible | NA | 1 | 206d | NA | NA | 0 s? | No | NA | NA | NA | 0
6486 | CARES V1 - Implementation | June 1, 2022 8:00 AM | June 7, 2027 5:00 PM |  |  | As Soon As Possible | NA | 1256 | 88d | June 1, 2022 8:00 AM | April 19, 2027 5:00 PM | 1222 days | No | 6/1/22 | NA | NA | 0.80000000000000004
7639 | Implementation | June 1, 2022 8:00 AM | June 7, 2027 5:00 PM |  |  | As Soon As Possible | NA | 1256 | 88d | June 1, 2022 8:00 AM | April 19, 2027 5:00 PM | 1222 days | No | 6/1/22 | NA | NA | 0.91000000000000003
7640 | Start | June 1, 2022 8:00 AM | June 1, 2022 8:00 AM |  | 4966FS+52d,3235,4027FS+47d,4153SS+60d,4189SS+35d,4300SS+194d,4957SS+87d,5028FS+55d,5059FS+75d,5064FS+65d,5073SS+108d,5099SS+120d,5158SS+130d,5363SS+184d,3195,3227,3229,3322,3431,3451,3466,3472,3514,3527,3537,4031,4287,4302,4320,4344,4360,4445,4740,4819... | As Soon As Possible | NA | 0 | 0d | June 1, 2022 8:00 AM | June 1, 2022 8:00 AM | 0 days | Yes | 6/1/22 | 6/1/22 | NA | 1
7641 | Onboard Vendor Resources | November 7, 2022 8:00 AM | May 28, 2024 5:00 PM |  |  | As Soon As Possible | NA | 387 | 0d | November 7, 2022 8:00 AM | May 28, 2024 5:00 PM | 387 days | No | 11/7/22 | 5/28/24 | NA | 1
7642 | Resources Approved Prior to WOA 12 | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM |  |  | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
7643 | Create IL Onboarding Toolkit/Playbook | November 7, 2022 8:00 AM | February 14, 2023 5:00 PM | 3192 | 3196SS,3228SS,3197SS,3198SS,3199SS,3200SS | Start No Earlier Than | 11/7/22 | 66 | 0d | November 7, 2022 8:00 AM | February 14, 2023 5:00 PM | 66 days | No | 11/7/22 | 2/14/23 | NA | 1
7644 | Onboard additional Implementation team members per approved staffing plan | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 3195SS | 3325SS,3402SS,3203FS+49d,3204FS+39d,3205FS+24d,3207FS+24d,3208FS+24d | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
7645 | Complete State provided laptop setup and gain access to environments | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 3195SS | 3198SS | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
7646 | Complete required new employee and Implementation reading and training videos | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 3195SS,3197SS | 3199SS | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
7647 | Complete CWS Program Overview Training (Court Module) | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 3195SS,3198SS | 3200SS | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
7648 | Maintain Onboarding Playbook and continue to create and deliver targeted child welfare bootcamp materials | November 7, 2022 8:00 AM | January 17, 2023 5:00 PM | 3195SS,3199SS | 3203 | As Soon As Possible | NA | 46 | 0d | November 7, 2022 8:00 AM | January 17, 2023 5:00 PM | 46 days | No | 11/7/22 | 1/17/23 | NA | 1
7649 | Resources Approved During WOA 12 | April 3, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 83 | 0d | April 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 83 days | No | 4/3/23 | 7/28/23 | NA | 1
7650 | Approved Resources (16 Resources) | April 3, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 83 | 0d | April 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 83 days | No | 4/3/23 | 7/28/23 | NA | 1
7651 | Onboard 05 Implementation team members per approved staffing plan (On boarded 05 resources) | May 8, 2023 8:00 AM | July 28, 2023 5:00 PM | 3196FS+49d,3200 | 3214FS+49d | As Soon As Possible | NA | 58 | 0d | May 8, 2023 8:00 AM | July 28, 2023 5:00 PM | 58 days | No | 5/8/23 | 7/28/23 | NA | 1
7652 | Onboard 10 Training team members per approved staffing plan (On boarded 10 resources) | April 24, 2023 8:00 AM | July 17, 2023 5:00 PM | 3196FS+39d | 3215FS+19d | As Soon As Possible | NA | 59 | 0d | April 24, 2023 8:00 AM | July 17, 2023 5:00 PM | 59 days | No | 4/24/23 | 7/17/23 | NA | 1
7653 | Onboard 1 OCM team members per approved staffing plan (On Boarded 01 resources) | April 3, 2023 8:00 AM | July 14, 2023 5:00 PM | 3196FS+24d | 3216FS+21d | As Soon As Possible | NA | 73 | 0d | April 3, 2023 8:00 AM | July 14, 2023 5:00 PM | 73 days | No | 4/3/23 | 7/14/23 | NA | 1
7654 | Onboarding Activities (16 Resources) | April 3, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 83 | 0d | April 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 83 days | No | 4/3/23 | 7/28/23 | NA | 1
7655 | Complete State provided laptop setup and gain access to environments (Completed for 16 resources) | April 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 3196FS+24d | 3208SS | As Soon As Possible | NA | 83 | 0d | April 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 83 days | No | 4/3/23 | 7/28/23 | NA | 1
7656 | Complete required new employee and Implementation reading and training videos (Completed for 16 resources) | April 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 3196FS+24d,3207SS | 3210SS+5d | As Soon As Possible | NA | 83 | 0d | April 3, 2023 8:00 AM | July 28, 2023 5:00 PM | 83 days | No | 4/3/23 | 7/28/23 | NA | 1
7658 | Conduct IL Workshops (aka bootcamp) training (Completed for 08 resources) | April 10, 2023 8:00 AM | July 14, 2023 5:00 PM |  |  | As Soon As Possible | NA | 68 | 0d | April 10, 2023 8:00 AM | July 14, 2023 5:00 PM | 68 days | No | 4/10/23 | 7/14/23 | NA | 1
7659 | Conduct IL Workshops for IL Joined Prior to WOA 12 (Completed for 08 resources) | April 10, 2023 8:00 AM | May 8, 2023 5:00 PM | 3208SS+5d | 3211FS+38d | As Soon As Possible | NA | 21 | 0d | April 10, 2023 8:00 AM | May 8, 2023 5:00 PM | 21 days | No | 4/10/23 | 5/8/23 | NA | 1
7660 | Conduct IL Workshops for ILs within 3 months of Onboarding (Completed for 00 resources) | July 3, 2023 8:00 AM | July 14, 2023 5:00 PM | 3210FS+38d | 3214 | As Soon As Possible | NA | 9 | 0d | July 3, 2023 8:00 AM | July 14, 2023 5:00 PM | 9 days | No | 7/3/23 | 7/14/23 | NA | 1
7661 | Resources Approved During WOA 13 | August 14, 2023 8:00 AM | December 8, 2023 5:00 PM |  |  | As Soon As Possible | NA | 81 | 0d | August 14, 2023 8:00 AM | December 8, 2023 5:00 PM | 81 days | No | 8/14/23 | 12/8/23 | NA | 1
7662 | Approved Resources (06 Resources) | August 14, 2023 8:00 AM | November 6, 2023 5:00 PM |  |  | As Soon As Possible | NA | 60 | 0d | August 14, 2023 8:00 AM | November 6, 2023 5:00 PM | 60 days | No | 8/14/23 | 11/6/23 | NA | 1
7663 | Onboard 02 Implementation team members per approved staffing plan (On boarded 02 resources) | October 9, 2023 8:00 AM | November 6, 2023 5:00 PM | 3203FS+49d,3211 | 3224 | As Soon As Possible | NA | 21 | 0d | October 9, 2023 8:00 AM | November 6, 2023 5:00 PM | 21 days | No | 10/9/23 | 11/6/23 | NA | 1
7664 | Onboard 03 Training team members per approved staffing plan (On boarded 03 resources) | August 14, 2023 8:00 AM | September 7, 2023 5:00 PM | 3204FS+19d | 3218SS | As Soon As Possible | NA | 18 | 0d | August 14, 2023 8:00 AM | September 7, 2023 5:00 PM | 18 days | No | 8/14/23 | 9/7/23 | NA | 1
7665 | Onboard 01 OCM team members per approved staffing plan (On boarded nn resources) | August 15, 2023 8:00 AM | August 15, 2023 5:00 PM | 3205FS+21d | 3219 | As Soon As Possible | NA | 1 | 0d | August 15, 2023 8:00 AM | August 15, 2023 5:00 PM | 1 | No | 8/15/23 | 8/15/23 | NA | 1
7666 | Onboarding Activities (08 Resources) | August 14, 2023 8:00 AM | December 8, 2023 5:00 PM |  |  | As Soon As Possible | NA | 81 | 0d | August 14, 2023 8:00 AM | December 8, 2023 5:00 PM | 81 days | No | 8/14/23 | 12/8/23 | NA | 1
7667 | Complete State provided laptop setup and gain access to environments (Completed for 08 resources) | August 14, 2023 8:00 AM | November 9, 2023 5:00 PM | 3215SS | 3219SS+10d,3221SS | As Soon As Possible | NA | 63 | 0d | August 14, 2023 8:00 AM | November 9, 2023 5:00 PM | 63 days | No | 8/14/23 | 11/9/23 | NA | 1
7668 | Complete required new employee and Implementation reading and training videos (Completed for 08 resources) | August 28, 2023 8:00 AM | December 8, 2023 5:00 PM | 3218SS+10d,3216 | 3224FS+88d | As Soon As Possible | NA | 71 | 0d | August 28, 2023 8:00 AM | December 8, 2023 5:00 PM | 71 days | No | 8/28/23 | 12/8/23 | NA | 1
7669 | Conduct IL Workshops (aka bootcamp) training (Completed for nn resources) | August 14, 2023 8:00 AM | September 11, 2023 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | August 14, 2023 8:00 AM | September 11, 2023 5:00 PM | 20 days | No | 8/14/23 | 9/11/23 | NA | 1
7670 | Conduct IL Workshops for ILs within 3 months of Onboarding (Completed for 00 resources) | August 14, 2023 8:00 AM | September 11, 2023 5:00 PM | 3218SS | 3224 | As Soon As Possible | NA | 20 | 0d | August 14, 2023 8:00 AM | September 11, 2023 5:00 PM | 20 days | No | 8/14/23 | 9/11/23 | NA | 1
7671 | Resources Approved During WOA 14 | April 18, 2024 8:00 AM | May 28, 2024 5:00 PM |  |  | As Soon As Possible | NA | 28 | 0d | April 18, 2024 8:00 AM | May 28, 2024 5:00 PM | 28 days | No | 4/18/24 | 5/28/24 | NA | 1
7672 | Onboarding Activities (01 Resources) | April 18, 2024 8:00 AM | May 28, 2024 5:00 PM |  |  | As Soon As Possible | NA | 28 | 0d | April 18, 2024 8:00 AM | May 28, 2024 5:00 PM | 28 days | No | 4/18/24 | 5/28/24 | NA | 1
7673 | Complete State provided laptop setup and gain access to environments (Completed for 01 resources) | April 18, 2024 8:00 AM | May 7, 2024 5:00 PM | 3219FS+88d,3214,3221 | 3225 | As Soon As Possible | NA | 14 | 0d | April 18, 2024 8:00 AM | May 7, 2024 5:00 PM | 14 days | No | 4/18/24 | 5/7/24 | NA | 1
7674 | Complete required new employee and Implementation reading and training videos (Completed for 00 resources) | May 8, 2024 8:00 AM | May 28, 2024 5:00 PM | 3224 | 3872 | As Soon As Possible | NA | 14 | 0d | May 8, 2024 8:00 AM | May 28, 2024 5:00 PM | 14 days | No | 5/8/24 | 5/28/24 | NA | 1
7675 | Finalize Current Iteration of Implementation Plan | October 12, 2022 8:00 AM | January 27, 2023 5:00 PM |  |  | As Soon As Possible | NA | 72 | 0d | October 12, 2022 8:00 AM | January 27, 2023 5:00 PM | 72 days | No | 10/12/22 | 1/27/23 | NA | 1
7676 | Update plan to align with pilot/statewide rollout approach | October 12, 2022 8:00 AM | January 17, 2023 5:00 PM | 3192 | 3228SS+15d | As Soon As Possible | NA | 64 | 0d | October 12, 2022 8:00 AM | January 17, 2023 5:00 PM | 64 days | No | 10/12/22 | 1/17/23 | NA | 1
7677 | Complete V1 Implementation Plan, facilitate review with impacted teams, and update accordingly | November 7, 2022 8:00 AM | January 12, 2023 5:00 PM | 3195SS,3227SS+15d | 3230FS-20d | As Soon As Possible | NA | 44 | 0d | November 7, 2022 8:00 AM | January 12, 2023 5:00 PM | 44 days | No | 11/7/22 | 1/12/23 | NA | 1
7678 | Update plan and review with State implementation team | October 12, 2022 8:00 AM | December 5, 2022 5:00 PM | 3192 | 3230 | As Soon As Possible | NA | 36 | 0d | October 12, 2022 8:00 AM | December 5, 2022 5:00 PM | 36 days | No | 10/12/22 | 12/5/22 | NA | 1
7679 | Update plan and review with RACI-required reviewers | December 14, 2022 8:00 AM | January 12, 2023 5:00 PM | 3228FS-20d,3229 | 3231FS+1d | As Soon As Possible | NA | 20 | 0d | December 14, 2022 8:00 AM | January 12, 2023 5:00 PM | 20 days | No | 12/14/22 | 1/12/23 | NA | 1
7680 | Present to ELT | January 17, 2023 8:00 AM | January 17, 2023 5:00 PM | 3230FS+1d | 3232 | As Soon As Possible | NA | 1 | 0d | January 17, 2023 8:00 AM | January 17, 2023 5:00 PM | 1 | No | 1/17/23 | 1/17/23 | NA | 1
7681 | Incorporate ELT feedback and finalize Master Implementation Plan | January 23, 2023 8:00 AM | January 27, 2023 5:00 PM | 3231 | 3264FS+43d | As Soon As Possible | NA | 5 | 0d | January 23, 2023 8:00 AM | January 27, 2023 5:00 PM | 5 days | No | 1/23/23 | 1/27/23 | NA | 1
7682 | Leverage Artifacts and Develop Implementation Strategies and Plans - SOW Task 2.1 | June 1, 2022 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 708 | 0d | June 1, 2022 8:00 AM | March 28, 2025 5:00 PM | 708 days | No | 6/1/22 | 3/28/25 | NA | 1
7683 | Deliver CARES MIP Version 7 | June 1, 2022 8:00 AM | August 1, 2022 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | June 1, 2022 8:00 AM | August 1, 2022 5:00 PM | 43 days | No | 6/1/22 | 8/1/22 | NA | 1
7684 | Review CARES-Live Statewide Implementation Plan and existing CARES MIP | June 1, 2022 8:00 AM | June 2, 2022 5:00 PM | 3192 | 3236 | As Soon As Possible | NA | 2 | 0d | June 1, 2022 8:00 AM | June 2, 2022 5:00 PM | 2 days | No | 6/1/22 | 6/2/22 | NA | 1
7685 | Determine and draft updates for MIP V7 | June 3, 2022 8:00 AM | June 16, 2022 5:00 PM | 3235 | 3237 | As Soon As Possible | NA | 10 | 0d | June 3, 2022 8:00 AM | June 16, 2022 5:00 PM | 10 days | No | 6/3/22 | 6/16/22 | NA | 1
7686 | Review draft with vendor implementation team | June 17, 2022 8:00 AM | June 23, 2022 5:00 PM | 3236 | 3238 | As Soon As Possible | NA | 5 | 0d | June 17, 2022 8:00 AM | June 23, 2022 5:00 PM | 5 days | No | 6/17/22 | 6/23/22 | NA | 1
7687 | Update plan and review with State implementation team | June 24, 2022 8:00 AM | July 8, 2022 5:00 PM | 3237 | 3239 | As Soon As Possible | NA | 10 | 0d | June 24, 2022 8:00 AM | July 8, 2022 5:00 PM | 10 days | No | 6/24/22 | 7/8/22 | NA | 1
7688 | Update plan and review with RACI-required reviewers | July 8, 2022 8:00 AM | July 21, 2022 5:00 PM | 3238 | 3240 | As Soon As Possible | NA | 10 | 0d | July 8, 2022 8:00 AM | July 21, 2022 5:00 PM | 10 days | No | 7/8/22 | 7/21/22 | NA | 1
7689 | Make final updates to MIP | July 22, 2022 8:00 AM | July 28, 2022 5:00 PM | 3239 | 3241 | As Soon As Possible | NA | 5 | 0d | July 22, 2022 8:00 AM | July 28, 2022 5:00 PM | 5 days | No | 7/22/22 | 7/28/22 | NA | 1
7690 | Prepare PPT for ELT | July 29, 2022 8:00 AM | August 1, 2022 5:00 PM | 3240 | 3242,3244,3460 | As Soon As Possible | NA | 2 | 0d | July 29, 2022 8:00 AM | August 1, 2022 5:00 PM | 2 days | No | 7/29/22 | 8/1/22 | NA | 1
7691 | Gain approval for MIP V7 | August 1, 2022 5:00 PM | August 1, 2022 5:00 PM | 3241 | 3251 | As Soon As Possible | NA | 0 | 0d | August 1, 2022 5:00 PM | August 1, 2022 5:00 PM | 0 days | Yes | 8/1/22 | 8/1/22 | NA | 1
7692 | Deliver Org Engagement Overview (OEO) Document | August 2, 2022 8:00 AM | November 2, 2022 5:00 PM |  |  | As Soon As Possible | NA | 66 | 0d | August 2, 2022 8:00 AM | November 2, 2022 5:00 PM | 66 days | No | 8/2/22 | 11/2/22 | NA | 1
7693 | Update draft OEO to align with implementation strategy | August 2, 2022 8:00 AM | September 13, 2022 5:00 PM | 3241 | 3245 | As Soon As Possible | NA | 30 | 0d | August 2, 2022 8:00 AM | September 13, 2022 5:00 PM | 30 days | No | 8/2/22 | 9/13/22 | NA | 1
7694 | Review OEO with vendor implementation team | September 14, 2022 8:00 AM | September 27, 2022 5:00 PM | 3244 | 3246 | As Soon As Possible | NA | 10 | 0d | September 14, 2022 8:00 AM | September 27, 2022 5:00 PM | 10 days | No | 9/14/22 | 9/27/22 | NA | 1
7695 | Update and review with State implementation team | September 28, 2022 8:00 AM | October 25, 2022 5:00 PM | 3245 | 3247 | As Soon As Possible | NA | 20 | 0d | September 28, 2022 8:00 AM | October 25, 2022 5:00 PM | 20 days | No | 9/28/22 | 10/25/22 | NA | 1
7696 | Finalize OEO | October 26, 2022 8:00 AM | November 1, 2022 5:00 PM | 3246 | 3248 | As Soon As Possible | NA | 5 | 0d | October 26, 2022 8:00 AM | November 1, 2022 5:00 PM | 5 days | No | 10/26/22 | 11/1/22 | NA | 1
7697 | Present to ELT | November 2, 2022 8:00 AM | November 2, 2022 5:00 PM | 3247 | 3249 | As Soon As Possible | NA | 1 | 0d | November 2, 2022 8:00 AM | November 2, 2022 5:00 PM | 1 | No | 11/2/22 | 11/2/22 | NA | 1
7698 | Complete OEO | November 2, 2022 5:00 PM | November 2, 2022 5:00 PM | 3248 | 3256 | As Soon As Possible | NA | 0 | 0d | November 2, 2022 5:00 PM | November 2, 2022 5:00 PM | 0 days | Yes | 11/2/22 | 11/2/22 | NA | 1
7699 | Deliver CARES MIP Version 8 | August 2, 2022 8:00 AM | January 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 124 | 0d | August 2, 2022 8:00 AM | January 31, 2023 5:00 PM | 124 days | No | 8/2/22 | 1/31/23 | NA | 1
7700 | Determine and draft updates for MIP V8 | August 2, 2022 8:00 AM | August 15, 2022 5:00 PM | 3242 | 3252 | As Soon As Possible | NA | 10 | 0d | August 2, 2022 8:00 AM | August 15, 2022 5:00 PM | 10 days | No | 8/2/22 | 8/15/22 | NA | 1
7701 | Restructure MIP content to align with implementation strategy | August 17, 2022 8:00 AM | September 14, 2022 5:00 PM | 3251 | 3253 | As Soon As Possible | NA | 20 | 0d | August 17, 2022 8:00 AM | September 14, 2022 5:00 PM | 20 days | No | 8/17/22 | 9/14/22 | NA | 1
7702 | Review draft with vendor implementation team | September 14, 2022 8:00 AM | September 27, 2022 5:00 PM | 3252 | 3254 | As Soon As Possible | NA | 10 | 0d | September 14, 2022 8:00 AM | September 27, 2022 5:00 PM | 10 days | No | 9/14/22 | 9/27/22 | NA | 1
7703 | Update plan and review with State implementation team | September 28, 2022 8:00 AM | October 12, 2022 5:00 PM | 3253 | 3255 | As Soon As Possible | NA | 11 | 0d | September 28, 2022 8:00 AM | October 12, 2022 5:00 PM | 11 days | No | 9/28/22 | 10/12/22 | NA | 1
7704 | Update plan to align with pilot/statewide rollout approach | October 12, 2022 8:00 AM | December 5, 2022 5:00 PM | 3254 | 3256 | As Soon As Possible | NA | 36 | 0d | October 12, 2022 8:00 AM | December 5, 2022 5:00 PM | 36 days | No | 10/12/22 | 12/5/22 | NA | 1
7705 | Review draft with vendor implementation team | November 18, 2022 8:00 AM | November 28, 2022 5:00 PM | 3255,3249 | 3257 | As Soon As Possible | NA | 5 | 0d | November 18, 2022 8:00 AM | November 28, 2022 5:00 PM | 5 days | No | 11/18/22 | 11/28/22 | NA | 1
7706 | Update plan and review with State implementation team | November 29, 2022 8:00 AM | December 13, 2022 5:00 PM | 3256 | 3258 | As Soon As Possible | NA | 11 | 0d | November 29, 2022 8:00 AM | December 13, 2022 5:00 PM | 11 days | No | 11/29/22 | 12/13/22 | NA | 1
7707 | Update plan and review with RACI-required reviewers | December 14, 2022 8:00 AM | January 9, 2023 5:00 PM | 3257 | 3259 | As Soon As Possible | NA | 17 | 0d | December 14, 2022 8:00 AM | January 9, 2023 5:00 PM | 17 days | No | 12/14/22 | 1/9/23 | NA | 1
7708 | Make final updates to MIP | January 10, 2023 8:00 AM | January 24, 2023 5:00 PM | 3258 | 3260 | As Soon As Possible | NA | 10 | 0d | January 10, 2023 8:00 AM | January 24, 2023 5:00 PM | 10 days | No | 1/10/23 | 1/24/23 | NA | 1
7709 | Prepare PPT for ELT | January 9, 2023 8:00 AM | January 12, 2023 5:00 PM | 3259 | 3261FS+12d | As Soon As Possible | NA | 4 | 0d | January 9, 2023 8:00 AM | January 12, 2023 5:00 PM | 4 days | No | 1/9/23 | 1/12/23 | NA | 1
7710 | Gain approval for MIP V8 | January 31, 2023 5:00 PM | January 31, 2023 5:00 PM | 3260FS+12d | 3262,3275FS+134d | As Soon As Possible | NA | 0 | 0d | January 31, 2023 5:00 PM | January 31, 2023 5:00 PM | 0 days | Yes | 1/31/23 | 1/31/23 | NA | 1
7711 | SPR 6 - Master Plan for Implementation Update (CWS-CARES V1) | January 31, 2023 5:00 PM | January 31, 2023 5:00 PM | 3261 | 3264 | As Soon As Possible | NA | 0 | 0d | January 31, 2023 5:00 PM | January 31, 2023 5:00 PM | 0 days | Yes | 1/31/23 | 1/31/23 | 1/31/23 | 1
7712 | Mid-Cycle Updates to Master Implementation Plan (MIP) Version 9 | April 3, 2023 8:00 AM | June 30, 2023 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | April 3, 2023 8:00 AM | June 30, 2023 5:00 PM | 64 days | No | 4/3/23 | 6/30/23 | NA | 1
7713 | Review MIP Version 8 and identify gaps | April 3, 2023 8:00 AM | April 10, 2023 5:00 PM | 3232FS+43d,3262 | 3265 | As Soon As Possible | NA | 6 | 0d | April 3, 2023 8:00 AM | April 10, 2023 5:00 PM | 6 days | No | 4/3/23 | 4/10/23 | NA | 1
7714 | Create outline with updated content based on gaps | April 11, 2023 8:00 AM | April 21, 2023 5:00 PM | 3264 | 3266 | As Soon As Possible | NA | 9 | 0d | April 11, 2023 8:00 AM | April 21, 2023 5:00 PM | 9 days | No | 4/11/23 | 4/21/23 | NA | 1
7715 | Draft updated content based on outline | April 24, 2023 8:00 AM | May 5, 2023 5:00 PM | 3265 | 3267FS-1d | As Soon As Possible | NA | 10 | 0d | April 24, 2023 8:00 AM | May 5, 2023 5:00 PM | 10 days | No | 4/24/23 | 5/5/23 | NA | 1
7716 | Update document control section of MIP to describe changes | May 5, 2023 8:00 AM | May 5, 2023 5:00 PM | 3266FS-1d | 3268FS-1d | As Soon As Possible | NA | 1 | 0d | May 5, 2023 8:00 AM | May 5, 2023 5:00 PM | 1 | No | 5/5/23 | 5/5/23 | NA | 1
7717 | Review updated MIP with State Implementation Lead and incorporate feedback | May 5, 2023 8:00 AM | May 11, 2023 5:00 PM | 3267FS-1d | 3269FS+1d | As Soon As Possible | NA | 5 | 0d | May 5, 2023 8:00 AM | May 11, 2023 5:00 PM | 5 days | No | 5/5/23 | 5/11/23 | NA | 1
7718 | Review updated MIP with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager and incorporate feedback | May 15, 2023 8:00 AM | May 26, 2023 5:00 PM | 3268FS+1d | 3270 | As Soon As Possible | NA | 10 | 0d | May 15, 2023 8:00 AM | May 26, 2023 5:00 PM | 10 days | No | 5/15/23 | 5/26/23 | NA | 1
7719 | Review updated MIP with RACI required reviewers and incorporate feedback | May 30, 2023 8:00 AM | June 9, 2023 5:00 PM | 3269 | 3271 | As Soon As Possible | NA | 9 | 0d | May 30, 2023 8:00 AM | June 9, 2023 5:00 PM | 9 days | No | 5/30/23 | 6/9/23 | NA | 1
7720 | Prepare PPT for ELT | June 12, 2023 8:00 AM | June 15, 2023 5:00 PM | 3270 | 3272FS+1d | As Soon As Possible | NA | 4 | 0d | June 12, 2023 8:00 AM | June 15, 2023 5:00 PM | 4 days | No | 6/12/23 | 6/15/23 | NA | 1
7721 | Present to ELT and Ask for Feedback | June 19, 2023 8:00 AM | June 19, 2023 5:00 PM | 3271FS+1d | 3273FS+4d | As Soon As Possible | NA | 1 | 0d | June 19, 2023 8:00 AM | June 19, 2023 5:00 PM | 1 | No | 6/19/23 | 6/19/23 | NA | 1
7722 | Incorporate ELT feedback and finalize | June 26, 2023 8:00 AM | June 30, 2023 5:00 PM | 3272FS+4d | 3275 | As Soon As Possible | NA | 5 | 0d | June 26, 2023 8:00 AM | June 30, 2023 5:00 PM | 5 days | No | 6/26/23 | 6/30/23 | NA | 1
7723 | Deliver CARES MIP Version 10 | August 14, 2023 8:00 AM | January 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 96 | 0d | August 14, 2023 8:00 AM | January 2, 2024 5:00 PM | 96 days | No | 8/14/23 | 1/2/24 | NA | 1
7724 | Review latest version of MIP (mid-cycle updated version) and identify gaps | August 14, 2023 8:00 AM | August 25, 2023 5:00 PM | 3261FS+134d,3273 | 3276 | As Soon As Possible | NA | 10 | 0d | August 14, 2023 8:00 AM | August 25, 2023 5:00 PM | 10 days | No | 8/14/23 | 8/25/23 | NA | 1
7725 | Create outline with updated content based on gaps | August 28, 2023 8:00 AM | September 15, 2023 5:00 PM | 3275 | 3277 | As Soon As Possible | NA | 14 | 0d | August 28, 2023 8:00 AM | September 15, 2023 5:00 PM | 14 days | No | 8/28/23 | 9/15/23 | NA | 1
7726 | Draft updated content based on outline | September 18, 2023 8:00 AM | October 26, 2023 5:00 PM | 3276 | 3278,3279FS-8d | As Soon As Possible | NA | 29 | 0d | September 18, 2023 8:00 AM | October 26, 2023 5:00 PM | 29 days | No | 9/18/23 | 10/26/23 | NA | 1
7727 | Update document control section of MIP to describe changes | October 27, 2023 8:00 AM | November 2, 2023 5:00 PM | 3277 | 3281 | As Soon As Possible | NA | 5 | 0d | October 27, 2023 8:00 AM | November 2, 2023 5:00 PM | 5 days | No | 10/27/23 | 11/2/23 | NA | 1
7728 | Review updated MIP with State Implementation Lead and incorporate feedback | October 17, 2023 8:00 AM | October 23, 2023 5:00 PM | 3277FS-8d | 3280 | As Soon As Possible | NA | 5 | 0d | October 17, 2023 8:00 AM | October 23, 2023 5:00 PM | 5 days | No | 10/17/23 | 10/23/23 | NA | 1
7729 | Review updated MIP with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager and incorporate feedback | October 24, 2023 8:00 AM | November 6, 2023 5:00 PM | 3279 | 3281FS+2d | As Soon As Possible | NA | 10 | 0d | October 24, 2023 8:00 AM | November 6, 2023 5:00 PM | 10 days | No | 10/24/23 | 11/6/23 | NA | 1
7730 | Review updated MIP with RACI required reviewers and incorporate feedback | November 9, 2023 8:00 AM | November 29, 2023 5:00 PM | 3280FS+2d,3278 | 3282 | As Soon As Possible | NA | 12 | 0d | November 9, 2023 8:00 AM | November 29, 2023 5:00 PM | 12 days | No | 11/9/23 | 11/29/23 | NA | 1
7731 | Prepare PPT for ELT | November 30, 2023 8:00 AM | December 8, 2023 5:00 PM | 3281 | 3283 | As Soon As Possible | NA | 7 | 0d | November 30, 2023 8:00 AM | December 8, 2023 5:00 PM | 7 days | No | 11/30/23 | 12/8/23 | NA | 1
7732 | Present to ELT | December 11, 2023 8:00 AM | December 11, 2023 5:00 PM | 3282 | 3284FS+4d | As Soon As Possible | NA | 1 | 0d | December 11, 2023 8:00 AM | December 11, 2023 5:00 PM | 1 | No | 12/11/23 | 12/11/23 | NA | 1
7733 | Incorporate ELT feedback and finalize | December 18, 2023 8:00 AM | January 2, 2024 5:00 PM | 3283FS+4d | 3286FS+70d | As Soon As Possible | NA | 10 | 0d | December 18, 2023 8:00 AM | January 2, 2024 5:00 PM | 10 days | No | 12/18/23 | 1/2/24 | NA | 1
7734 | Deliver CARES MIP Version 11 | April 15, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 98 | 0d | April 15, 2024 8:00 AM | August 30, 2024 5:00 PM | 98 days | No | 4/15/24 | 8/30/24 | NA | 1
7735 | Review outline of recommended updates on content with State Implementation Leadership Team | April 15, 2024 8:00 AM | April 19, 2024 5:00 PM | 3284FS+70d | 3287 | As Soon As Possible | NA | 5 | 0d | April 15, 2024 8:00 AM | April 19, 2024 5:00 PM | 5 days | No | 4/15/24 | 4/19/24 | NA | 1
7736 | Draft Updated Content Based on Outline | April 22, 2024 8:00 AM | April 26, 2024 5:00 PM | 3286 | 3288 | As Soon As Possible | NA | 5 | 0d | April 22, 2024 8:00 AM | April 26, 2024 5:00 PM | 5 days | No | 4/22/24 | 4/26/24 | NA | 1
7737 | Edit / Validate all Updates IL | April 29, 2024 8:00 AM | May 10, 2024 5:00 PM | 3287 | 3289 | As Soon As Possible | NA | 10 | 0d | April 29, 2024 8:00 AM | May 10, 2024 5:00 PM | 10 days | No | 4/29/24 | 5/10/24 | NA | 1
7738 | Review Updated MIP with IDO and Michelle | May 13, 2024 8:00 AM | May 24, 2024 5:00 PM | 3288 | 3290FF | As Soon As Possible | NA | 10 | 0d | May 13, 2024 8:00 AM | May 24, 2024 5:00 PM | 10 days | No | 5/13/24 | 5/24/24 | NA | 1
7739 | Review updated MIP with State Implementation Lead | May 14, 2024 8:00 AM | May 24, 2024 5:00 PM | 3289FF | 3291FF | As Soon As Possible | NA | 9 | 0d | May 14, 2024 8:00 AM | May 24, 2024 5:00 PM | 9 days | No | 5/14/24 | 5/24/24 | NA | 1
7740 | Incorporate feedback/comments from State Imp Lead | May 20, 2024 8:00 AM | May 24, 2024 5:00 PM | 3290FF | 3292 | As Soon As Possible | NA | 5 | 0d | May 20, 2024 8:00 AM | May 24, 2024 5:00 PM | 5 days | No | 5/20/24 | 5/24/24 | NA | 1
7741 | Review updated MIP with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | May 28, 2024 8:00 AM | June 5, 2024 5:00 PM | 3291 | 3293 | As Soon As Possible | NA | 7 | 0d | May 28, 2024 8:00 AM | June 5, 2024 5:00 PM | 7 days | No | 5/28/24 | 6/5/24 | NA | 1
7742 | Incorporate feedback/comments from State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | June 6, 2024 8:00 AM | June 14, 2024 5:00 PM | 3292 | 3294 | As Soon As Possible | NA | 7 | 0d | June 6, 2024 8:00 AM | June 14, 2024 5:00 PM | 7 days | No | 6/6/24 | 6/14/24 | NA | 1
7743 | Review updated MIP with RACI required reviewers | June 17, 2024 8:00 AM | July 15, 2024 5:00 PM | 3293 | 3295 | As Soon As Possible | NA | 20 | 0d | June 17, 2024 8:00 AM | July 15, 2024 5:00 PM | 20 days | No | 6/17/24 | 7/15/24 | NA | 1
7744 | Incorporate feedback/comments from RACI team | July 16, 2024 8:00 AM | July 29, 2024 5:00 PM | 3294 | 3296SS-1d | As Soon As Possible | NA | 10 | 0d | July 16, 2024 8:00 AM | July 29, 2024 5:00 PM | 10 days | No | 7/16/24 | 7/29/24 | NA | 1
7745 | Prepare PPT for ELT | July 15, 2024 8:00 AM | August 2, 2024 5:00 PM | 3295SS-1d | 3297 | As Soon As Possible | NA | 15 | 0d | July 30, 2024 8:00 AM | August 12, 2024 5:00 PM | 10 days | No | 7/15/24 | 8/2/24 | NA | 1
7746 | Send MIP to ELT | August 5, 2024 8:00 AM | August 5, 2024 5:00 PM | 3296 | 3298SS,3299FS+4d | As Soon As Possible | NA | 1 | 0d | August 13, 2024 8:00 AM | August 21, 2024 5:00 PM | 7 s | No | 8/5/24 | 8/5/24 | NA | 1
7747 | Present MIP Version 11 to ELT | August 5, 2024 8:00 AM | August 5, 2024 5:00 PM | 3297SS | 3299 | As Soon As Possible | NA | 1 | 0d | August 19, 2024 8:00 AM | August 19, 2024 5:00 PM | 1 | No | 8/5/24 | 8/5/24 | NA | 1
7748 | Incorporate ELT feedback and finalize | August 12, 2024 8:00 AM | August 26, 2024 5:00 PM | 3297FS+4d,3298 | 3300 | As Soon As Possible | NA | 11 | 0d | August 26, 2024 8:00 AM | August 29, 2024 5:00 PM | 4 days | No | 8/12/24 | 8/26/24 | NA | 1
7749 | Complete ADA on MIP | August 27, 2024 8:00 AM | August 29, 2024 5:00 PM | 3299 | 3301 | As Soon As Possible | NA | 3 | 0d | August 29, 2024 8:00 AM | August 29, 2024 5:00 PM | 1 day | No | 8/27/24 | 8/29/24 | NA | 1
7750 | Send PMO the ADA version of the MIP Version 11 | August 30, 2024 8:00 AM | August 30, 2024 5:00 PM | 3300 | 3303FS+25d | As Soon As Possible | NA | 1 | 0d | August 30, 2024 8:00 AM | August 30, 2024 5:00 PM | 1 | No | 8/30/24 | 8/30/24 | NA | 1
11001 | Deliver CARES MIP Version 12 | October 7, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 118 | 0d | September 26, 2024 8:00 AM | March 28, 2025 5:00 PM | 125 days | No | 10/7/24 | 3/28/25 | NA | 1
11019 | Review Latest Version of MIP and Identify Gaps | October 7, 2024 8:00 AM | November 6, 2024 5:00 PM | 3301FS+25d | 3304 | As Soon As Possible | NA | 23 | 0d | September 26, 2024 8:00 AM | October 25, 2024 5:00 PM | 22 days | No | 10/7/24 | 11/6/24 | NA | 1
11018 | Create Outline with Updated Content Based on Gaps | November 7, 2024 8:00 AM | December 6, 2024 5:00 PM | 3303 | 3305 | As Soon As Possible | NA | 19 | 0d | October 28, 2024 8:00 AM | November 1, 2024 5:00 PM | 5 days | No | 11/7/24 | 12/6/24 | NA | 1
11002 | Review outline of recommended updates on content with State Implementation Leadership Team | December 9, 2024 8:00 AM | December 13, 2024 5:00 PM | 3304 | 3306 | As Soon As Possible | NA | 5 | 0d | November 4, 2024 8:00 AM | November 8, 2024 5:00 PM | 5 days | No | 12/9/24 | 12/13/24 | NA | 1
11003 | Draft Updated Content Based on Outline | December 16, 2024 8:00 AM | December 27, 2024 5:00 PM | 3305 | 3307 | As Soon As Possible | NA | 9 | 0d | November 12, 2024 8:00 AM | November 18, 2024 5:00 PM | 5 days | No | 12/16/24 | 12/27/24 | NA | 1
11004 | Edit / Validate all Updates IL | December 30, 2024 8:00 AM | January 8, 2025 5:00 PM | 3306 | 3308 | As Soon As Possible | NA | 7 | 0d | November 19, 2024 8:00 AM | December 4, 2024 5:00 PM | 10 days | No | 12/30/24 | 1/8/25 | NA | 1
11005 | Review Updated MIP with IDO and Michelle | January 9, 2025 8:00 AM | January 16, 2025 5:00 PM | 3307 | 3309 | As Soon As Possible | NA | 6 | 0d | December 5, 2024 8:00 AM | December 18, 2024 5:00 PM | 10 days | No | 1/9/25 | 1/16/25 | NA | 1
11006 | Review updated MIP with State Implementation Lead | January 17, 2025 8:00 AM | January 22, 2025 5:00 PM | 3308 | 3310 | As Soon As Possible | NA | 3 | 0d | December 5, 2024 8:00 AM | December 18, 2024 5:00 PM | 10 days | No | 1/17/25 | 1/22/25 | NA | 1
11007 | Incorporate feedback/comments from State Imp Lead | January 23, 2025 8:00 AM | January 27, 2025 5:00 PM | 3309 | 3311 | As Soon As Possible | NA | 3 | 0d | December 12, 2024 8:00 AM | December 18, 2024 5:00 PM | 5 days | No | 1/23/25 | 1/27/25 | NA | 1
11008 | Review updated MIP with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | January 28, 2025 8:00 AM | February 4, 2025 5:00 PM | 3310 | 3312 | As Soon As Possible | NA | 6 | 0d | January 6, 2025 8:00 AM | January 14, 2025 5:00 PM | 7 days | No | 1/28/25 | 2/4/25 | NA | 1
11009 | Incorporate feedback/comments from State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | February 5, 2025 8:00 AM | February 10, 2025 5:00 PM | 3311 | 3313 | As Soon As Possible | NA | 4 | 0d | January 15, 2025 8:00 AM | January 24, 2025 5:00 PM | 7 days | No | 2/5/25 | 2/10/25 | NA | 1
11010 | Review updated MIP with RACI required reviewers | February 11, 2025 8:00 AM | February 20, 2025 5:00 PM | 3312 | 3314 | As Soon As Possible | NA | 7 | 0d | January 27, 2025 8:00 AM | February 7, 2025 5:00 PM | 10 days | No | 2/11/25 | 2/20/25 | NA | 1
11011 | Incorporate feedback/comments from RACI team | February 21, 2025 8:00 AM | February 27, 2025 5:00 PM | 3313 | 3315 | As Soon As Possible | NA | 5 | 0d | February 10, 2025 8:00 AM | February 24, 2025 5:00 PM | 10 days | No | 2/21/25 | 2/27/25 | NA | 1
11012 | Prepare PPT for ELT | February 28, 2025 8:00 AM | March 5, 2025 5:00 PM | 3314 | 3316 | As Soon As Possible | NA | 4 | 0d | February 25, 2025 8:00 AM | March 10, 2025 5:00 PM | 10 days | No | 2/28/25 | 3/5/25 | NA | 1
11013 | Send MIP to ELT | March 6, 2025 8:00 AM | March 14, 2025 5:00 PM | 3315 | 3317SS+2d,3318 | As Soon As Possible | NA | 7 | 0d | March 11, 2025 8:00 AM | March 19, 2025 5:00 PM | 7 days | No | 3/6/25 | 3/14/25 | NA | 1
11014 | Present MIP Version to ELT | March 10, 2025 8:00 AM | March 10, 2025 5:00 PM | 3316SS+2d | 3318 | As Soon As Possible | NA | 1 | 0d | March 17, 2025 8:00 AM | March 17, 2025 5:00 PM | 1 | No | 3/10/25 | 3/10/25 | NA | 1
11015 | Incorporate ELT feedback and finalize | March 17, 2025 8:00 AM | March 21, 2025 5:00 PM | 3316,3317 | 3319 | As Soon As Possible | NA | 5 | 0d | March 24, 2025 8:00 AM | March 27, 2025 5:00 PM | 4 days | No | 3/17/25 | 3/21/25 | NA | 1
11016 | Complete ADA on MIP | March 24, 2025 8:00 AM | March 28, 2025 5:00 PM | 3318 | 3320FF | As Soon As Possible | NA | 5 | 0d | March 27, 2025 8:00 AM | March 27, 2025 5:00 PM | 1 day | No | 3/24/25 | 3/28/25 | NA | 1
11017 | Send PMO the ADA version of the MIP Version 12 | March 28, 2025 8:00 AM | March 28, 2025 5:00 PM | 3319FF | 3872 | As Soon As Possible | NA | 1 | 0d | March 28, 2025 8:00 AM | March 28, 2025 5:00 PM | 1 | No | 3/28/25 | 3/28/25 | NA | 1
7751 | DMF | August 1, 2023 8:00 AM | October 2, 2023 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | August 1, 2023 8:00 AM | October 2, 2023 5:00 PM | 44 days | No | 8/1/23 | 10/2/23 | NA | 1
7752 | Conduct Environment Analysis for CARES V1 and Create a Summary Report (DMF) | August 1, 2023 8:00 AM | October 2, 2023 5:00 PM | 3192 | 5260FS+33d,5265 | Start No Earlier Than | 8/1/23 | 44 | 0d | August 1, 2023 8:00 AM | October 2, 2023 5:00 PM | 44 days | No | 8/1/23 | 10/2/23 | NA | 1
7753 | Develop Rollout Contingency Plan | November 7, 2022 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 661 | 0d | November 7, 2022 8:00 AM | June 27, 2025 5:00 PM | 660 days | No | 11/7/22 | 6/30/25 | NA | 1
7754 | Initial Draft Contingency Plan / Risk Scenarios | November 7, 2022 8:00 AM | February 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 75 | 0d | November 7, 2022 8:00 AM | February 28, 2023 5:00 PM | 75 days | No | 11/7/22 | 2/28/23 | NA | 1
7755 | Initiate and facilitate working group discussions related to rollout contingency planning, in support of Contingency Plan being completed by May 31, 2023 | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 3196SS | 3326FS-19d | Must Start On | 11/7/22 | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
7756 | Create Initial Draft Contingency Plan DED | January 3, 2023 8:00 AM | February 1, 2023 5:00 PM | 3325FS-19d | 3327,3333FS+2d | As Soon As Possible | NA | 21 | 0d | January 3, 2023 8:00 AM | February 1, 2023 5:00 PM | 21 days | No | 1/3/23 | 2/1/23 | NA | 1
7757 | Review Contingency Plan DED with State Implementation Team | February 2, 2023 8:00 AM | February 8, 2023 5:00 PM | 3326 | 3328FS-1d | As Soon As Possible | NA | 5 | 0d | February 2, 2023 8:00 AM | February 8, 2023 5:00 PM | 5 days | No | 2/2/23 | 2/8/23 | NA | 1
7758 | Incorporate feedback from State Imp Team | February 8, 2023 8:00 AM | February 10, 2023 5:00 PM | 3327FS-1d | 3329 | As Soon As Possible | NA | 3 | 0d | February 8, 2023 8:00 AM | February 10, 2023 5:00 PM | 3 days | No | 2/8/23 | 2/10/23 | NA | 1
7759 | Review Contingency Plan DED with RACI required reviewers | February 14, 2023 8:00 AM | February 22, 2023 5:00 PM | 3328 | 3330 | As Soon As Possible | NA | 6 | 0d | February 14, 2023 8:00 AM | February 22, 2023 5:00 PM | 6 days | No | 2/14/23 | 2/22/23 | NA | 1
7760 | Update and Finalize Contingency Plan DED | February 23, 2023 8:00 AM | February 28, 2023 5:00 PM | 3329 | 3336 | As Soon As Possible | NA | 4 | 0d | February 23, 2023 8:00 AM | February 28, 2023 5:00 PM | 4 days | No | 2/23/23 | 2/28/23 | NA | 1
7769 | Draft Contingency Plan | February 6, 2023 8:00 AM | December 19, 2024 5:00 PM |  |  | As Soon As Possible | NA | 471 | 0d | February 6, 2023 8:00 AM | December 19, 2024 5:00 PM | 471 days | No | 2/6/23 | 12/19/24 | NA | 1
7770 | Contingency Plan Sections 1-8 | February 6, 2023 8:00 AM | May 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 69 | 0d | February 6, 2023 8:00 AM | May 15, 2023 5:00 PM | 69 days | No | 2/6/23 | 5/15/23 | NA | 1
7771 | Create outline of Contingency Plan Sections 1-8 | February 6, 2023 8:00 AM | February 24, 2023 5:00 PM | 3326FS+2d | 3334 | As Soon As Possible | NA | 14 | 0d | February 6, 2023 8:00 AM | February 24, 2023 5:00 PM | 14 days | No | 2/6/23 | 2/24/23 | NA | 1
7772 | Review outline with Contingency Plan Working Group | February 27, 2023 8:00 AM | March 24, 2023 5:00 PM | 3333 | 3335FF | As Soon As Possible | NA | 20 | 0d | February 27, 2023 8:00 AM | March 24, 2023 5:00 PM | 20 days | No | 2/27/23 | 3/24/23 | NA | 1
7773 | Create First Draft of Contingency Plan Sections 1-8 | February 28, 2023 8:00 AM | March 24, 2023 5:00 PM | 3334FF | 3336 | As Soon As Possible | NA | 19 | 0d | February 28, 2023 8:00 AM | March 24, 2023 5:00 PM | 19 days | No | 2/28/23 | 3/24/23 | NA | 1
7774 | Review First Draft with Contingency Plan working group | March 28, 2023 8:00 AM | March 28, 2023 5:00 PM | 3335,3330 | 3337FS+3d | As Soon As Possible | NA | 1 | 0d | March 28, 2023 8:00 AM | March 28, 2023 5:00 PM | 1 | No | 3/28/23 | 3/28/23 | NA | 1
7775 | Create final draft of Contingency Plan Sections 1-8 | April 4, 2023 8:00 AM | April 21, 2023 5:00 PM | 3336FS+3d | 3338FF | As Soon As Possible | NA | 14 | 0d | April 4, 2023 8:00 AM | April 21, 2023 5:00 PM | 14 days | No | 4/4/23 | 4/21/23 | NA | 1
7776 | Review final draft with Contingency Plan Working Group | April 17, 2023 8:00 AM | April 21, 2023 5:00 PM | 3337FF | 3339 | As Soon As Possible | NA | 5 | 0d | April 17, 2023 8:00 AM | April 21, 2023 5:00 PM | 5 days | No | 4/17/23 | 4/21/23 | NA | 1
7777 | Review final draft with State Imp Team | April 13, 2023 8:00 AM | April 19, 2023 5:00 PM | 3338 | 3340 | As Soon As Possible | NA | 5 | 0d | April 13, 2023 8:00 AM | April 19, 2023 5:00 PM | 5 days | No | 4/13/23 | 4/19/23 | NA | 1
7778 | Incorporate feedback from State Imp Team | April 19, 2023 8:00 AM | April 25, 2023 5:00 PM | 3339 | 3341FS+8d | As Soon As Possible | NA | 5 | 0d | April 19, 2023 8:00 AM | April 25, 2023 5:00 PM | 5 days | No | 4/19/23 | 4/25/23 | NA | 1
7779 | Review final draft with RACI required reviewers | May 8, 2023 8:00 AM | May 15, 2023 5:00 PM | 3340FS+8d | 3342 | As Soon As Possible | NA | 6 | 0d | May 8, 2023 8:00 AM | May 15, 2023 5:00 PM | 6 days | No | 5/8/23 | 5/15/23 | NA | 1
7780 | Update and Finalize Contingency Plan Sections 1-8 | May 15, 2023 5:00 PM | May 15, 2023 5:00 PM | 3341 | 3343 | As Soon As Possible | NA | 0 | 0d | May 15, 2023 5:00 PM | May 15, 2023 5:00 PM | 0 days | Yes | 5/15/23 | 5/15/23 | NA | 1
7781 | Prepare PPT for ELT | May 15, 2023 5:00 PM | May 15, 2023 5:00 PM | 3342 | 3344 | As Soon As Possible | NA | 0 | 0d | May 15, 2023 5:00 PM | May 15, 2023 5:00 PM | 0 days | Yes | 5/15/23 | 5/15/23 | NA | 1
7782 | Present to ELT | May 15, 2023 5:00 PM | May 15, 2023 5:00 PM | 3343 | 3345 | As Soon As Possible | NA | 0 | 0d | May 15, 2023 5:00 PM | May 15, 2023 5:00 PM | 0 days | Yes | 5/15/23 | 5/15/23 | NA | 1
7783 | Incorporate ELT feedback and finalize | May 15, 2023 5:00 PM | May 15, 2023 5:00 PM | 3344 | 3348FS+18d,3346 | As Soon As Possible | NA | 0 | 0d | May 15, 2023 5:00 PM | May 15, 2023 5:00 PM | 0 days | Yes | 5/15/23 | 5/15/23 | NA | 1
7784 | SPR 6 - Complete Initial Draft CWS-CARES V1 Contingency Plan Risk Scenario Framework | May 15, 2023 5:00 PM | May 15, 2023 5:00 PM | 3345 | 3348 | As Soon As Possible | NA | 0 | 0d | May 15, 2023 5:00 PM | May 15, 2023 5:00 PM | 0 days | Yes | 5/15/23 | 5/15/23 | 5/31/23 | 1
7785 | Contingency Plan Sections 9-13 | June 12, 2023 8:00 AM | December 19, 2024 5:00 PM |  |  | As Soon As Possible | NA | 384 | 0d | June 12, 2023 8:00 AM | December 19, 2024 5:00 PM | 384 days | No | 6/12/23 | 12/19/24 | NA | 1
7786 | Create outline of Contingency Plan Sections 9-13 | June 12, 2023 8:00 AM | June 16, 2023 5:00 PM | 3345FS+18d,3346 | 3350FS+73d,3367,3368,3369,3370,2188SS | As Soon As Possible | NA | 5 | 0d | June 12, 2023 8:00 AM | June 16, 2023 5:00 PM | 5 days | No | 6/12/23 | 6/16/23 | NA | 1
7799 | Conduct Workgroup Session - Walkthrough Section 9 Rollout Risks | September 29, 2023 8:00 AM | November 2, 2023 5:00 PM |  |  | As Soon As Possible | NA | 25 | 0d | September 29, 2023 8:00 AM | November 2, 2023 5:00 PM | 25 days | No | 9/29/23 | 11/2/23 | NA | 1
7800 | Set up Bi-weekly Meeting (Oct - December 2024) | September 29, 2023 8:00 AM | September 29, 2023 5:00 PM | 3348FS+73d | 3351FS+12d | As Soon As Possible | NA | 1 | 0d | September 29, 2023 8:00 AM | September 29, 2023 5:00 PM | 1 | No | 9/29/23 | 9/29/23 | NA | 1
7801 | Contingency Plan Workgroup Meeting Prep | October 18, 2023 8:00 AM | October 18, 2023 5:00 PM | 3350FS+12d | 3352,3353,3358FS+10d | As Soon As Possible | NA | 1 | 0d | October 18, 2023 8:00 AM | October 18, 2023 5:00 PM | 1 | No | 10/18/23 | 10/18/23 | NA | 1
7802 | Conduct Contingency Plan Workgroup Reconnect Meeting #1 | October 19, 2023 8:00 AM | October 19, 2023 5:00 PM | 3351 | 3354FF,3355 | As Soon As Possible | NA | 1 | 0d | October 19, 2023 8:00 AM | October 19, 2023 5:00 PM | 1 | No | 10/19/23 | 10/19/23 | NA | 1
7803 | Validate Contingency Plan Sections 9-13 Topics | October 19, 2023 8:00 AM | October 19, 2023 5:00 PM | 3351 | 3354SS | As Soon As Possible | NA | 1 | 0d | October 19, 2023 8:00 AM | October 19, 2023 5:00 PM | 1 | No | 10/19/23 | 10/19/23 | NA | 1
7804 | Validate Workgroup Members | October 19, 2023 8:00 AM | October 19, 2023 5:00 PM | 3352FF,3353SS | 3356 | As Soon As Possible | NA | 1 | 0d | October 19, 2023 8:00 AM | October 19, 2023 5:00 PM | 1 | No | 10/19/23 | 10/19/23 | NA | 1
7805 | Contingency Plan Workgroup Meeting Debrief | October 20, 2023 8:00 AM | October 20, 2023 5:00 PM | 3352 | 3356SS | As Soon As Possible | NA | 1 | 0d | October 20, 2023 8:00 AM | October 20, 2023 5:00 PM | 1 | No | 10/20/23 | 10/20/23 | NA | 1
7806 | Send Draft Rollout Risk Tracker for Review | October 20, 2023 8:00 AM | November 2, 2023 5:00 PM | 3354,3355SS | 3361 | As Soon As Possible | NA | 10 | 0d | October 20, 2023 8:00 AM | November 2, 2023 5:00 PM | 10 days | No | 10/20/23 | 11/2/23 | NA | 1
7808 | Conduct Workgroup Session - Walkthrough Section 9 Rollout Risks | November 1, 2023 5:00 PM | November 6, 2023 5:00 PM |  |  | As Soon As Possible | NA | 3 | 0d | November 1, 2023 5:00 PM | November 6, 2023 5:00 PM | 3 days | No | 11/1/23 | 11/6/23 | NA | 1
7809 | Contingency Plan Workgroup Meeting Prep | November 1, 2023 5:00 PM | November 1, 2023 5:00 PM | 3351FS+10d | 3359 | As Soon As Possible | NA | 0 | 0d | November 1, 2023 5:00 PM | November 1, 2023 5:00 PM | 0 days | Yes | 11/1/23 | 11/1/23 | NA | 1
7810 | Categorize, Score, and Assign Category Leads Meeting | November 2, 2023 8:00 AM | November 2, 2023 5:00 PM | 3358 | 3360 | As Soon As Possible | NA | 1 | 0d | November 2, 2023 8:00 AM | November 2, 2023 5:00 PM | 1 | No | 11/2/23 | 11/2/23 | NA | 1
7811 | Update Rollout Risk Tracker | November 3, 2023 8:00 AM | November 6, 2023 5:00 PM | 3359 | 3361FF | As Soon As Possible | NA | 2 | 0d | November 3, 2023 8:00 AM | November 6, 2023 5:00 PM | 2 days | No | 11/3/23 | 11/6/23 | NA | 1
7812 | Contingency Plan Workgroup Meeting Debrief | November 6, 2023 8:00 AM | November 6, 2023 5:00 PM | 3360FF,3356 | 3363FS+5d | As Soon As Possible | NA | 1 | 0d | November 6, 2023 8:00 AM | November 6, 2023 5:00 PM | 1 | No | 11/6/23 | 11/6/23 | NA | 1
7813 | Conduct Workgroup Session - Walkthrough Section 10 Rollout Risks | November 15, 2023 8:00 AM | January 12, 2024 5:00 PM |  |  | As Soon As Possible | NA | 39 | 0d | November 15, 2023 8:00 AM | January 12, 2024 5:00 PM | 39 days | No | 11/15/23 | 1/12/24 | NA | 1
7814 | Contingency Plan Workgroup Meeting Prep | November 15, 2023 8:00 AM | November 15, 2023 5:00 PM | 3361FS+5d | 3364 | As Soon As Possible | NA | 1 | 0d | November 15, 2023 8:00 AM | November 15, 2023 5:00 PM | 1 | No | 11/15/23 | 11/15/23 | NA | 1
7815 | Continue to Categorize, Score and Assign Category Leads Meeting | November 16, 2023 8:00 AM | November 16, 2023 5:00 PM | 3363 | 3365 | As Soon As Possible | NA | 1 | 0d | November 16, 2023 8:00 AM | November 16, 2023 5:00 PM | 1 | No | 11/16/23 | 11/16/23 | NA | 1
7816 | Workgroup Session - Gain Consensus Section 10 Rollout Risks | November 17, 2023 8:00 AM | November 30, 2023 5:00 PM | 3364 | 3366 | As Soon As Possible | NA | 8 | 0d | November 17, 2023 8:00 AM | November 30, 2023 5:00 PM | 8 days | No | 11/17/23 | 11/30/23 | NA | 1
7817 | Draft Contingency Plan Section 10-Monitoring & Management | December 1, 2023 8:00 AM | January 12, 2024 5:00 PM | 3365 | 3367FS+38d,3368FS+38d,3369FS+41d,3370FS+38d | As Soon As Possible | NA | 29 | 0d | December 1, 2023 8:00 AM | January 12, 2024 5:00 PM | 29 days | No | 12/1/23 | 1/12/24 | NA | 1
8032 | Conduct Knowledge Transfer Session with Debra and Christina to transition Rollout Contingency Plan | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 3348,3366FS+38d | 3368SS | As Soon As Possible | NA | 5 | 0d | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 5 days | No | 3/11/24 | 3/15/24 | NA | 1
8033 | Schedule new recurring bi-monthly Rollout Contingency Workgroup Meetings | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 3348,3366FS+38d,3367SS | 3369SS+3d | As Soon As Possible | NA | 5 | 0d | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 5 days | No | 3/11/24 | 3/15/24 | NA | 1
8034 | Rollout Contingency Meeting (Review Meeting Calendar) and discuss new approach | March 14, 2024 8:00 AM | March 14, 2024 5:00 PM | 3348,3366FS+41d,3368SS+3d | 3371 | As Soon As Possible | NA | 1 | 0d | March 14, 2024 8:00 AM | March 14, 2024 5:00 PM | 1 | No | 3/14/24 | 3/14/24 | NA | 1
8035 | Draft Section 9. risks, triggers, and mitigations (collect State Imp Leads + Imp Mgt. Team feedback prior to work group) | March 11, 2024 8:00 AM | March 29, 2024 5:00 PM | 3348,3366FS+38d | 3371SS+13d | As Soon As Possible | NA | 15 | 0d | March 11, 2024 8:00 AM | March 29, 2024 5:00 PM | 15 days | No | 3/11/24 | 3/29/24 | NA | 1
8036 | Review Section 9 content (risks, triggers, and mitigations) and collect inputs during bi-weekly workgroup meetings – Prioritize high risk exposure ratings | March 28, 2024 8:00 AM | June 20, 2024 5:00 PM | 3370SS+13d,3369 | 3372FS+10d,3373SS+45d | As Soon As Possible | NA | 59 | 0d | March 28, 2024 8:00 AM | July 31, 2024 5:00 PM | 87 days | No | 3/28/24 | 6/20/24 | NA | 1
8037 | Incorporate validated risks, triggers, and mitigations into Section 9 of Rollout Contingency Plan | July 8, 2024 8:00 AM | July 12, 2024 5:00 PM | 3371FS+10d | 3376SS | As Soon As Possible | NA | 5 | 0d | August 1, 2024 8:00 AM | August 7, 2024 5:00 PM | 5 days | No | 7/8/24 | 7/12/24 | NA | 1
8038 | Draft Section 10. Rollout Risk Contingency Monitoring & Management | June 3, 2024 8:00 AM | July 31, 2024 5:00 PM | 3371SS+45d | 3376,3377,3374FS+5d | As Soon As Possible | NA | 42 | 0d | June 3, 2024 8:00 AM | July 31, 2024 5:00 PM | 42 days | No | 6/3/24 | 7/31/24 | NA | 1
11775 | Review Section 9 with RACI Reviewers and Incorporate Feedback | August 8, 2024 8:00 AM | August 13, 2024 5:00 PM | 3373FS+5d | 3375FS+3d | As Soon As Possible | NA | 4 | 0d | NA | NA | 0 days? | No | 8/8/24 | 8/13/24 | NA | 1
11776 | Review Draft section 9 with ELT | August 19, 2024 8:00 AM | August 26, 2024 5:00 PM | 3374FS+3d | 3381 | As Soon As Possible | NA | 6 | 0d | NA | NA | 0 days? | No | 8/19/24 | 8/26/24 | NA | 1
8039 | Review Section 10 (Rollout Risk Contingency Monitoring & Management) and collect inputs during bi-weekly workgroup meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 3373,3372SS | 3377SS | As Soon As Possible | NA | 22 | 0d | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 22 days | No | 8/1/24 | 8/30/24 | NA | 1
8040 | Draft Section 11. Connection Points to the Risk and Issue Management Plan | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 3373,3376SS | 3378FS-2d,3379 | As Soon As Possible | NA | 22 | 0d | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 22 days | No | 8/1/24 | 8/30/24 | NA | 1
8041 | Review Section 11 (Connection Points to the Risk and Issue Management Plan) and collect inputs during bi-weekly workgroup meetings | August 29, 2024 8:00 AM | September 26, 2024 5:00 PM | 3377FS-2d | 3379SS | As Soon As Possible | NA | 21 | 0d | September 2, 2024 8:00 AM | September 26, 2024 5:00 PM | 19 days | No | 8/29/24 | 9/26/24 | NA | 1
8042 | Draft Sections 12 & 13 Communication Strategy & Timeline and Roles & Responsibilities | September 2, 2024 8:00 AM | September 26, 2024 5:00 PM | 3377,3378SS | 3382FS+1d,3380FS-4d | As Soon As Possible | NA | 19 | 0d | September 2, 2024 8:00 AM | September 26, 2024 5:00 PM | 19 days | No | 9/2/24 | 9/26/24 | NA | 1
11778 | Review Sections 10-11 with RACI Reviewers and Incorporate Feedback | September 23, 2024 8:00 AM | October 2, 2024 5:00 PM | 3379FS-4d | 3381 | As Soon As Possible | NA | 8 | 0d | NA | NA | 0 days? | No | 9/23/24 | 10/2/24 | NA | 1
11777 | Review Draft section 10-11 with ELT | October 3, 2024 8:00 AM | October 11, 2024 5:00 PM | 3375,3380 | 3886 | As Soon As Possible | NA | 7 | 0d | NA | NA | 0 days? | No | 10/3/24 | 10/11/24 | NA | 1
8043 | Review Sections 12 & 13 (Communication Strategy & Timeline and Roles & Responsibilities) and collect inputs during bi-weekly workgroup meetings | September 30, 2024 8:00 AM | October 30, 2024 5:00 PM | 3379FS+1d | 3383FS+1d,3386FS+2d | As Soon As Possible | NA | 23 | 0d | September 30, 2024 8:00 AM | October 30, 2024 5:00 PM | 23 days | No | 9/30/24 | 10/30/24 | NA | 1
8044 | Finalize draft of Rollout Contingency Plan (Sections 9-13) | November 1, 2024 8:00 AM | November 7, 2024 5:00 PM | 3382FS+1d | 3384 | As Soon As Possible | NA | 5 | 0d | November 1, 2024 8:00 AM | November 7, 2024 5:00 PM | 5 days | No | 11/1/24 | 11/7/24 | NA | 1
8045 | Review Rollout Contingency Plan (Sections 9-13) with Christina and incorporate feedback | November 8, 2024 8:00 AM | November 14, 2024 5:00 PM | 3383 | 3385 | As Soon As Possible | NA | 4 | 0d | November 8, 2024 8:00 AM | November 14, 2024 5:00 PM | 4 days | No | 11/8/24 | 11/14/24 | NA | 1
8046 | Review Rollout Contingency Plan (Sections 9-13) with Cheryl, Sonoltra, and Debra and incorporate feedback | November 15, 2024 8:00 AM | November 26, 2024 5:00 PM | 3384 | 3387 | As Soon As Possible | NA | 8 | 0d | November 15, 2024 8:00 AM | November 26, 2024 5:00 PM | 8 days | No | 11/15/24 | 11/26/24 | NA | 1
11779 | Review Sections 12-13 with RACI Reviewers and Incorporate Feedback | November 4, 2024 8:00 AM | November 8, 2024 5:00 PM | 3382FS+2d | 3886 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 11/4/24 | 11/8/24 | NA | 1
8047 | Review Rollout Contingency Plan (Sections 9-13) with ELT and incorporate feedback | November 27, 2024 8:00 AM | December 19, 2024 5:00 PM | 3385 | 3388 | As Soon As Possible | NA | 15 | 0d | November 27, 2024 8:00 AM | December 19, 2024 5:00 PM | 15 days | No | 11/27/24 | 12/19/24 | NA | 1
8048 | SPR 6 - Complete Draft CWS-CARES V1 Contingency Plan | December 19, 2024 5:00 PM | December 19, 2024 5:00 PM | 3387 | 3390 | As Soon As Possible | NA | 0 | 0d | December 19, 2024 5:00 PM | December 19, 2024 5:00 PM | 0 days | Yes | 12/19/24 | 12/19/24 | 12/30/24 | 1
8049 | Final Contingency Plan | December 20, 2024 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 131 | 0d | December 20, 2024 8:00 AM | June 27, 2025 5:00 PM | 130 days | No | 12/20/24 | 6/30/25 | NA | 1
8050 | Iterate Final Contingency Plan | December 20, 2024 8:00 AM | January 24, 2025 5:00 PM | 3388 | 3391 | As Soon As Possible | NA | 23 | 0d | December 20, 2024 8:00 AM | April 17, 2025 5:00 PM | 80 days | No | 12/20/24 | 1/24/25 | NA | 1
11651 | Draft Final Contingency Plan | January 27, 2025 8:00 AM | February 21, 2025 5:00 PM | 3390 | 3392 | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 1/27/25 | 2/21/25 | NA | 1
8051 | Review Final Contingency Plan with Work Group | February 24, 2025 8:00 AM | March 13, 2025 5:00 PM | 3391 | 3393 | As Soon As Possible | NA | 14 | 0d | April 18, 2025 8:00 AM | May 1, 2025 5:00 PM | 10 days | No | 2/24/25 | 3/13/25 | NA | 1
8052 | Incorporate feedback from Work Group on Final Contingency Plan | March 14, 2025 8:00 AM | March 21, 2025 5:00 PM | 3392 | 3394 | As Soon As Possible | NA | 6 | 0d | May 2, 2025 8:00 AM | May 15, 2025 5:00 PM | 10 days | No | 3/14/25 | 3/21/25 | NA | 1
8053 | Submit Final Contingency Plan to RACI Reviewers | March 24, 2025 8:00 AM | April 1, 2025 5:00 PM | 3393 | 3395 | As Soon As Possible | NA | 6 | 0d | May 16, 2025 8:00 AM | May 29, 2025 5:00 PM | 9 days | No | 3/24/25 | 4/1/25 | NA | 1
8054 | Incorporate Feedback from RACI Reviewers | April 2, 2025 8:00 AM | April 9, 2025 5:00 PM | 3394 | 3396FS+6d | As Soon As Possible | NA | 6 | 0d | May 30, 2025 8:00 AM | June 16, 2025 5:00 PM | 12 days | No | 4/2/25 | 4/9/25 | NA | 1
8055 | Present Final Contingency Plan to ELT | April 18, 2025 8:00 AM | April 18, 2025 5:00 PM | 3395FS+6d | 3397 | As Soon As Possible | NA | 1 | 0d | June 17, 2025 8:00 AM | June 17, 2025 5:00 PM | 1 | No | 4/18/25 | 4/18/25 | NA | 1
11707 | Review Final Contingency Plan with ELT | April 21, 2025 8:00 AM | May 2, 2025 5:00 PM | 3396 | 3398 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 4/21/25 | 5/2/25 | NA | 1
8056 | Incorporate feedback from ELT | May 5, 2025 8:00 AM | May 13, 2025 5:00 PM | 3397 | 3399FS+20d | As Soon As Possible | NA | 7 | 0d | June 18, 2025 8:00 AM | June 24, 2025 5:00 PM | 5 days | No | 5/5/25 | 5/13/25 | NA | 1
8057 | Finalize Contingency Plan | June 12, 2025 8:00 AM | June 25, 2025 5:00 PM | 3398FS+20d | 3400FS+3d | As Soon As Possible | NA | 10 | 0d | June 25, 2025 8:00 AM | June 27, 2025 5:00 PM | 3 days | No | 6/12/25 | 6/25/25 | NA | 1
8058 | SPR 6 - Complete Final CWS-CARES V1 Contingency Plan | June 30, 2025 5:00 PM | June 30, 2025 5:00 PM | 3399FS+3d | 3872 | As Soon As Possible | NA | 0 | 0d | June 27, 2025 5:00 PM | June 27, 2025 5:00 PM | 0 days | Yes | 6/30/25 | 6/30/25 | 6/30/25 | 1
8059 | Develop Pilot Plan - Version 1 | November 7, 2022 8:00 AM | December 21, 2023 5:00 PM |  |  | As Soon As Possible | NA | 280 | 0d | November 7, 2022 8:00 AM | December 21, 2023 5:00 PM | 280 days | No | 11/7/22 | 12/21/23 | NA | 1
8060 | Initiate and facilitate working group discussions and create pilot planning approach document | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 3196SS | 3403 | As Soon As Possible | NA | 73 | 0d | November 7, 2022 8:00 AM | February 24, 2023 5:00 PM | 73 days | No | 11/7/22 | 2/24/23 | NA | 1
8062 | Gain input on the approach from impacted teams and finalize approach | February 1, 2023 8:00 AM | February 24, 2023 5:00 PM | 3402 | 3404 | As Soon As Possible | NA | 17 | 0d | February 1, 2023 8:00 AM | February 24, 2023 5:00 PM | 17 days | No | 2/1/23 | 2/24/23 | NA | 1
8063 | Create Pilot Plan DED | January 9, 2023 8:00 AM | January 13, 2023 5:00 PM | 3403 | 3405 | As Soon As Possible | NA | 5 | 0d | January 9, 2023 8:00 AM | January 13, 2023 5:00 PM | 5 days | No | 1/9/23 | 1/13/23 | NA | 1
8064 | Review Pilot Plan DED with State Implementation Team | January 17, 2023 8:00 AM | January 20, 2023 5:00 PM | 3404 | 3406 | As Soon As Possible | NA | 4 | 0d | January 17, 2023 8:00 AM | January 20, 2023 5:00 PM | 4 days | No | 1/17/23 | 1/20/23 | NA | 1
8065 | Update and Finalize Pilot Plan DED | January 23, 2023 8:00 AM | January 27, 2023 5:00 PM | 3405 | 3407 | As Soon As Possible | NA | 5 | 0d | January 23, 2023 8:00 AM | January 27, 2023 5:00 PM | 5 days | No | 1/23/23 | 1/27/23 | NA | 1
8066 | Create Pilot Plan Draft | January 30, 2023 8:00 AM | August 25, 2023 5:00 PM | 3406 | 3408FS-5d | As Soon As Possible | NA | 146 | 0d | January 30, 2023 8:00 AM | August 25, 2023 5:00 PM | 146 days | No | 1/30/23 | 8/25/23 | NA | 1
8067 | Review Pilot Plan Draft with State Implementation Team | August 21, 2023 8:00 AM | August 25, 2023 5:00 PM | 3407FS-5d | 3409FF | As Soon As Possible | NA | 5 | 0d | August 21, 2023 8:00 AM | August 25, 2023 5:00 PM | 5 days | No | 8/21/23 | 8/25/23 | NA | 1
8068 | Incorporate Feedback from State Implementation Team | August 22, 2023 8:00 AM | August 25, 2023 5:00 PM | 3408FF | 3410FF | As Soon As Possible | NA | 4 | 0d | August 22, 2023 8:00 AM | August 25, 2023 5:00 PM | 4 days | No | 8/22/23 | 8/25/23 | NA | 1
8069 | Facilitate Review of Pilot Plan Draft with Impacted Teams (Pilot Work Group / ELT) | August 21, 2023 8:00 AM | August 25, 2023 5:00 PM | 3409FF | 3411FF | As Soon As Possible | NA | 5 | 0d | August 21, 2023 8:00 AM | August 25, 2023 5:00 PM | 5 days | No | 8/21/23 | 8/25/23 | NA | 1
8070 | Incorporate Feedback from Impacted Teams (Pilot Work Group / ELT) | August 21, 2023 8:00 AM | August 25, 2023 5:00 PM | 3410FF | 3412FS+10d | As Soon As Possible | NA | 5 | 0d | August 21, 2023 8:00 AM | August 25, 2023 5:00 PM | 5 days | No | 8/21/23 | 8/25/23 | NA | 1
8071 | Review and Incorporate BOD Feedback | September 12, 2023 8:00 AM | September 21, 2023 5:00 PM | 3411FS+10d | 3413 | As Soon As Possible | NA | 8 | 0d | September 12, 2023 8:00 AM | September 21, 2023 5:00 PM | 8 days | No | 9/12/23 | 9/21/23 | NA | 1
8072 | Finalize Pilot Plan - Includes the BOD Approval | September 22, 2023 8:00 AM | September 29, 2023 5:00 PM | 3412 | 3414 | As Soon As Possible | NA | 6 | 0d | September 22, 2023 8:00 AM | September 29, 2023 5:00 PM | 6 days | No | 9/22/23 | 9/29/23 | NA | 1
8073 | SPR 6 - Complete Pilot Plan | September 29, 2023 5:00 PM | September 29, 2023 5:00 PM | 3413 | 3416,3417FS+5d | As Soon As Possible | NA | 0 | 0d | September 29, 2023 5:00 PM | September 29, 2023 5:00 PM | 0 days | Yes | 9/29/23 | 9/29/23 | 9/29/23 | 1
8074 | Pilot Plan Version 1 Follow-up | October 2, 2023 8:00 AM | December 21, 2023 5:00 PM |  |  | As Soon As Possible | NA | 56 | 0d | October 2, 2023 8:00 AM | December 21, 2023 5:00 PM | 56 days | No | 10/2/23 | 12/21/23 | NA | 1
8075 | Incorporate County feedback on Pilot Plan | October 2, 2023 8:00 AM | October 27, 2023 5:00 PM | 3414 | 3417SS+5d | As Soon As Possible | NA | 20 | 0d | October 2, 2023 8:00 AM | October 27, 2023 5:00 PM | 20 days | No | 10/2/23 | 10/27/23 | NA | 1
8076 | Provide BOD with a long-term schedule of what needs to be included in future iterations of the Pilot Plan | October 9, 2023 8:00 AM | December 21, 2023 5:00 PM | 3414FS+5d,3416SS+5d | 3419FS+5d | As Soon As Possible | NA | 51 | 0d | October 9, 2023 8:00 AM | December 21, 2023 5:00 PM | 51 days | No | 10/9/23 | 12/21/23 | NA | 1
11052 | Develop Pilot Tech Solution | January 2, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 169 | 0d | January 2, 2024 8:00 AM | June 19, 2025 5:00 PM | 369 days | No | 1/2/24 | 8/30/24 | NA | 1
11053 | Develop Draft Technical Pilot Solution | January 2, 2024 8:00 AM | March 29, 2024 5:00 PM | 3417FS+5d | 3421FS+43d,3420FF | As Soon As Possible | NA | 62 | 0d | January 2, 2024 8:00 AM | March 29, 2024 5:00 PM | 62 days | No | 1/2/24 | 3/29/24 | NA | 1
11054 | Provide Q1 BOD Update: Status Update on Progress of Tech Solution | March 29, 2024 8:00 AM | March 29, 2024 5:00 PM | 3419FF | 3421 | As Soon As Possible | NA | 1 | 0d | March 29, 2024 8:00 AM | March 29, 2024 5:00 PM | 1 | No | 3/29/24 | 3/29/24 | NA | 1
11055 | Review Technical Solution with Selected Pilot Counties' IT Reps and ELT | June 3, 2024 8:00 AM | June 12, 2024 5:00 PM | 3419FS+43d,3420 | 3423FS+20d,3422SS+13d | As Soon As Possible | NA | 8 | 0d | June 3, 2024 8:00 AM | August 29, 2024 5:00 PM | 63 days | No | 6/3/24 | 6/12/24 | NA | 1
11056 | Provide Q2 BOD Update: Status Update on Progress of Tech Solution | June 20, 2024 8:00 AM | June 20, 2024 5:00 PM | 3421SS+13d | 3426FS+18d,3425 | As Soon As Possible | NA | 1 | 0d | June 20, 2024 8:00 AM | June 20, 2024 5:00 PM | 1 | No | 6/20/24 | 6/20/24 | NA | 1
11057 | Conduct BOD Review of Tech Solution Recommendation | July 12, 2024 8:00 AM | July 18, 2024 5:00 PM | 3421FS+20d | 3429 | As Soon As Possible | NA | 5 | 0d | July 29, 2024 8:00 AM | August 23, 2024 5:00 PM | 20 days | No | 7/12/24 | 7/18/24 | NA | 1
11058 | Provide Q3 BOD Pilot Update | August 15, 2024 8:00 AM | August 15, 2024 5:00 PM | 3426FS+19d | 3429 | As Soon As Possible | NA | 1 | 0d | August 15, 2024 8:00 AM | August 15, 2024 5:00 PM | 1 | No | 8/15/24 | 8/15/24 | NA | 1
11059 | Prepare pilot Budget Analysis | June 21, 2024 8:00 AM | July 18, 2024 5:00 PM | 3422 | 3429 | As Soon As Possible | NA | 19 | 0d | June 21, 2024 8:00 AM | July 31, 2024 5:00 PM | 28 days | No | 6/21/24 | 7/18/24 | NA | 1
11060 | Provide Q3 BOD Update: Submit Pilot Budget Analysis to the BOD | July 18, 2024 8:00 AM | July 18, 2024 5:00 PM | 3422FS+18d | 3424FS+19d,3427FS+11d | As Soon As Possible | NA | 1 | 0d | July 18, 2024 8:00 AM | July 18, 2024 5:00 PM | 1 | No | 7/18/24 | 7/18/24 | NA | 1
11782 | Document new Pilot options for consideration (Option A and B) | August 5, 2024 8:00 AM | August 30, 2024 5:00 PM | 3426FS+11d | 3428SS | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 8/5/24 | 8/30/24 | NA | 1
11781 | Conduct Review of Options A and B with Internal Team | August 5, 2024 8:00 AM | August 30, 2024 5:00 PM | 3427SS | 3429SS | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 8/5/24 | 8/30/24 | NA | 1
11780 | Present findings from Review of Options A and B to Smaller Pilot Workgroup | August 5, 2024 8:00 AM | August 30, 2024 5:00 PM | 3428SS,3423,3424,3425 | 3886 | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 8/5/24 | 8/30/24 | NA | 1
11073 | Develop Pilot Plan - Version 2 | January 2, 2024 8:00 AM | July 19, 2024 5:00 PM |  |  | As Soon As Possible | NA | 139 | 0d | January 2, 2024 8:00 AM | June 28, 2024 5:00 PM | 125 days | No | 1/2/24 | 7/19/24 | NA | 1
11074 | Update Pilot Plan Version 2 and Integrate Requested Revisions / Feedback | January 2, 2024 8:00 AM | June 3, 2024 5:00 PM | 3192 | 3432SS+80d | As Soon As Possible | NA | 106 | 0d | January 2, 2024 8:00 AM | June 3, 2024 5:00 PM | 106 days | No | 1/2/24 | 6/3/24 | NA | 1
11075 | Conduct RACI, ELT, and BOD Pilot Review Processes | April 26, 2024 8:00 AM | June 28, 2024 5:00 PM | 3431SS+80d | 3433FS+1d | As Soon As Possible | NA | 45 | 0d | April 26, 2024 8:00 AM | May 29, 2024 5:00 PM | 23 days | No | 4/26/24 | 6/28/24 | NA | 1
11076 | Submit and Review Final Pilot Plan with BOD | July 2, 2024 8:00 AM | July 12, 2024 5:00 PM | 3432FS+1d | 3434FS+5d | As Soon As Possible | NA | 8 | 0d | June 4, 2024 8:00 AM | June 28, 2024 5:00 PM | 19 days | No | 7/2/24 | 7/12/24 | NA | 1
11077 | Final Pilot Plan Version 2 Approved | July 19, 2024 5:00 PM | July 19, 2024 5:00 PM | 3433FS+5d | 3436FS+115d | As Soon As Possible | NA | 0 | 0d | June 28, 2024 5:00 PM | June 28, 2024 5:00 PM | 0 days | Yes | 7/19/24 | 7/19/24 | NA | 1
11083 | Develop Pilot Plan - Version 2A | January 6, 2025 8:00 AM | April 17, 2025 5:00 PM |  |  | As Soon As Possible | NA | 71 | 0d | January 6, 2025 8:00 AM | November 24, 2025 5:00 PM | 185 days | No | 1/6/25 | 4/17/25 | NA | 1
11084 | Get BOD Decision About Direction of Pilot | January 6, 2025 8:00 AM | January 16, 2025 5:00 PM | 3434FS+115d | 3437FS+20d,3878SS+3d | As Soon As Possible | NA | 9 | 0d | January 6, 2025 8:00 AM | January 16, 2025 5:00 PM | 134 days | No | 1/6/25 | 1/16/25 | NA | 1
11085 | Draft Pilot Plan Version 2A | February 18, 2025 8:00 AM | March 17, 2025 5:00 PM | 3436FS+20d | 3438FS+13d,3440 | As Soon As Possible | NA | 20 | 0d | February 18, 2025 8:00 AM | March 17, 2025 5:00 PM | 19 days | No | 2/18/25 | 3/17/25 | NA | 1
11086 | Seek Pilot Plan Version 2A Approval | April 7, 2025 8:00 AM | April 17, 2025 5:00 PM | 3437FS+13d | 3441 | As Soon As Possible | NA | 9 | 0d | April 7, 2025 8:00 AM | April 17, 2025 5:00 PM | 20 days | No | 4/7/25 | 4/17/25 | NA | 1
13138 | Selection of Pilot Counties | April 2, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 4/2/25 | 6/2/25 | NA | 1
13139 | Solicit the Volunteers from CWDA | April 2, 2025 8:00 AM | April 25, 2025 5:00 PM | 3437 | 3441FS+9d | As Soon As Possible | NA | 18 | 0d | NA | NA | 0 days? | No | 4/2/25 | 4/25/25 | NA | 1
13140 | Pilot Counties Approved by BOD | May 9, 2025 8:00 AM | May 15, 2025 5:00 PM | 3440FS+9d,3438 | 3442 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 5/9/25 | 5/15/25 | NA | 1
13141 | Send Formal Notification to Pilot and Non-Pilot Counties | May 16, 2025 8:00 AM | June 2, 2025 5:00 PM | 3441 | 3444FS+20d | As Soon As Possible | NA | 11 | 0d | NA | NA | 0 days? | No | 5/16/25 | 6/2/25 | NA | 1
12557 | Develop Pilot Plan - Version 3 | July 1, 2025 8:00 AM | November 24, 2025 5:00 PM |  |  | As Soon As Possible | NA | 102 | 215d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.62
11657 | Draft Pilot Plan - Version 3 | July 1, 2025 8:00 AM | July 25, 2025 5:00 PM | 3442FS+20d | 3445 | As Soon As Possible | NA | 18 | 0d | July 1, 2025 8:00 AM | July 25, 2025 5:00 PM | 0 days | No | 7/1/25 | 7/25/25 | NA | 1
11785 | Review Pilot Plan Version 3 with ELT | July 28, 2025 8:00 AM | August 29, 2025 5:00 PM | 3444 | 3446 | As Soon As Possible | NA | 25 | 0d | July 28, 2025 8:00 AM | August 29, 2025 5:00 PM | 0 days | No | 7/28/25 | 8/29/25 | NA | 1
11784 | Incorporate Feedback of ELT for Pilot Plan Version 3 | September 9, 2025 8:00 AM | September 22, 2025 5:00 PM | 3445 | 3447FS+4d | As Soon As Possible | NA | 10 | 5d | September 9, 2025 8:00 AM | September 22, 2025 5:00 PM | 0 days | No | 9/9/25 | NA | NA | 0.94999999999999996
11656 | Review Pilot Plan Version 3 with BOD | September 29, 2025 8:00 AM | October 31, 2025 5:00 PM | 3446FS+4d | 3448 | As Soon As Possible | NA | 25 | 215d | September 29, 2025 8:00 AM | October 31, 2025 5:00 PM | 0 days | No | 9/29/25 | NA | NA | 0.20000000000000001
11783 | Incorporate Feedback from BOD for Pilot Plan Version 3 | November 3, 2025 8:00 AM | November 17, 2025 5:00 PM | 3447 | 3449 | As Soon As Possible | NA | 10 | 215d | November 3, 2025 8:00 AM | November 17, 2025 5:00 PM | 0 days | No | NA | NA | NA | 0
11655 | Final Pilot Plan Version 3 Approved | November 18, 2025 8:00 AM | November 24, 2025 5:00 PM | 3448 | 3886 | As Soon As Possible | NA | 5 | 215d | November 18, 2025 8:00 AM | November 24, 2025 5:00 PM | 0 days | No | NA | NA | NA | 0
8100 | Maintain CARES Implementation Toolkit (Prior to Executive Briefing/Kickoff) - SOW Task 2.12 | March 13, 2023 8:00 AM | August 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 350 | 0d | March 13, 2023 8:00 AM | August 1, 2024 5:00 PM | 350 days | No | 3/13/23 | 8/1/24 | NA | 1
8101 | Review ToolKit list | March 13, 2023 8:00 AM | April 19, 2023 5:00 PM | 3192 | 3452,3457 | Start No Earlier Than | 3/16/23 | 27 | 0d | March 13, 2023 8:00 AM | April 19, 2023 5:00 PM | 27 days | No | 3/13/23 | 4/19/23 | NA | 1
8102 | Review Org Assessment spreadsheet and update as needed | April 20, 2023 8:00 AM | July 6, 2023 5:00 PM | 3451 | 3453SS | As Soon As Possible | NA | 54 | 0d | April 20, 2023 8:00 AM | July 6, 2023 5:00 PM | 54 days | No | 4/20/23 | 7/6/23 | NA | 1
8103 | Review Executive Briefing slides and update as needed | April 20, 2023 8:00 AM | July 6, 2023 5:00 PM | 3452SS | 3454SS | As Soon As Possible | NA | 54 | 0d | April 20, 2023 8:00 AM | July 6, 2023 5:00 PM | 54 days | No | 4/20/23 | 7/6/23 | NA | 1
8104 | Review Kickoff slides and update as needed | April 20, 2023 8:00 AM | July 28, 2023 5:00 PM | 3453SS | 3455SS | As Soon As Possible | NA | 70 | 0d | April 20, 2023 8:00 AM | July 28, 2023 5:00 PM | 70 days | No | 4/20/23 | 7/28/23 | NA | 1
8105 | Review Org Go-Live Readiness Checklist and update as needed | April 20, 2023 8:00 AM | July 6, 2023 5:00 PM | 3454SS | 3456 | As Soon As Possible | NA | 54 | 0d | April 20, 2023 8:00 AM | July 6, 2023 5:00 PM | 54 days | No | 4/20/23 | 7/6/23 | NA | 1
8106 | Review Org Go-Live Readiness Dashboard and update as needed | July 5, 2024 8:00 AM | August 1, 2024 5:00 PM | 5071,3455 | 3460 | As Soon As Possible | NA | 20 | 0d | July 5, 2024 8:00 AM | August 1, 2024 5:00 PM | 20 days | No | 7/5/24 | 8/1/24 | NA | 1
8111 | Toolkit Review for WOA 12 Completed | April 19, 2023 5:00 PM | April 19, 2023 5:00 PM | 3451 | 3872 | As Soon As Possible | NA | 0 | 0d | April 19, 2023 5:00 PM | April 19, 2023 5:00 PM | 0 days | Yes | 4/19/23 | 4/19/23 | NA | 1
8112 | Coordinate, Collaborate, and Support State and CWDS Teams - SOW Task 2.11 | August 2, 2022 8:00 AM | April 14, 2023 5:00 PM |  |  | As Soon As Possible | NA | 175 | 0d | August 2, 2022 8:00 AM | April 14, 2023 5:00 PM | 175 days | No | 8/2/22 | 4/14/23 | NA | 1
8113 | Collaborate with Service Managers and Product Development Leads | August 2, 2022 8:00 AM | September 13, 2022 5:00 PM |  |  | As Soon As Possible | NA | 30 | 0d | August 2, 2022 8:00 AM | September 13, 2022 5:00 PM | 30 days | No | 8/2/22 | 9/13/22 | NA | 1
8114 | Develop Implementation/SM/PDL collaboration process | August 2, 2022 8:00 AM | August 22, 2022 5:00 PM | 3241,3456 | 3461 | As Soon As Possible | NA | 15 | 0d | August 2, 2022 8:00 AM | August 22, 2022 5:00 PM | 15 days | No | 8/2/22 | 8/22/22 | NA | 1
8115 | Review with State team | August 24, 2022 8:00 AM | September 7, 2022 5:00 PM | 3460 | 3462FS+4d | As Soon As Possible | NA | 10 | 0d | August 24, 2022 8:00 AM | September 7, 2022 5:00 PM | 10 days | No | 8/24/22 | 9/7/22 | NA | 1
8116 | Present collaboration process to Service Manager Workgroup | September 13, 2022 8:00 AM | September 13, 2022 5:00 PM | 3461FS+4d | 3463 | As Soon As Possible | NA | 1 | 0d | September 13, 2022 8:00 AM | September 13, 2022 5:00 PM | 1 | No | 9/13/22 | 9/13/22 | NA | 1
8117 | Initiate collaboration with SMs/PDLs | September 13, 2022 5:00 PM | September 13, 2022 5:00 PM | 3462 | 3482 | As Soon As Possible | NA | 0 | 0d | September 13, 2022 5:00 PM | September 13, 2022 5:00 PM | 0 days | Yes | 9/13/22 | 9/13/22 | NA | 1
8118 | Fresno Support Plan - Implementation | March 27, 2023 8:00 AM | April 14, 2023 5:00 PM |  |  | As Soon As Possible | NA | 14 | 0d | March 27, 2023 8:00 AM | April 14, 2023 5:00 PM | 14 days | No | 3/27/23 | 4/14/23 | NA | 1
8119 | Change Management Support - Implementation | March 27, 2023 8:00 AM | April 14, 2023 5:00 PM |  |  | As Soon As Possible | NA | 14 | 0d | March 27, 2023 8:00 AM | April 14, 2023 5:00 PM | 14 days | No | 3/27/23 | 4/14/23 | NA | 1
8120 | Send name, state agency, and the start/end dates to Matt so Fresno can create a temporary INTRA (County network) account | March 27, 2023 8:00 AM | April 6, 2023 5:00 PM | 3192 | 3467FF,3468FF,3469SS | As Soon As Possible | NA | 8 | 0d | March 27, 2023 8:00 AM | April 6, 2023 5:00 PM | 8 days | No | 3/27/23 | 4/6/23 | NA | 1
8121 | Conduct feasibility of using CARES for purposeful Placements Matching | April 6, 2023 8:00 AM | April 6, 2023 5:00 PM | 3466FF | 3468SS | As Soon As Possible | NA | 1 | 0d | April 6, 2023 8:00 AM | April 6, 2023 5:00 PM | 1 | No | 4/6/23 | 4/6/23 | NA | 1
8122 | Ask Staff Development about using outside curriculum in the computer lab | April 6, 2023 8:00 AM | April 6, 2023 5:00 PM | 3466FF,3467SS | 3469FS-8d | As Soon As Possible | NA | 1 | 0d | April 6, 2023 8:00 AM | April 6, 2023 5:00 PM | 1 | No | 4/6/23 | 4/6/23 | NA | 1
8123 | Develop a Site visit summary and send to the County | March 27, 2023 8:00 AM | April 14, 2023 5:00 PM | 3466SS,3468FS-8d | 3482 | As Soon As Possible | NA | 14 | 0d | March 27, 2023 8:00 AM | April 14, 2023 5:00 PM | 14 days | No | 3/27/23 | 4/14/23 | NA | 1
8124 | Phase 1: Engage Orgs in Planning and Preparation Activities | November 7, 2022 8:00 AM | September 22, 2026 5:00 PM |  |  | As Soon As Possible | NA | 970 | 8d | November 7, 2022 8:00 AM | February 27, 2025 5:00 PM | 576 days | No | 11/7/22 | NA | NA | 0.91000000000000003
8125 | Executive Briefings | November 7, 2022 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 180 | 0d | November 7, 2022 8:00 AM | July 28, 2023 5:00 PM | 180 days | No | 11/7/22 | 7/28/23 | NA | 1
8126 | Develop Executive Briefing presentation | November 7, 2022 8:00 AM | December 13, 2022 5:00 PM | 3192 | 3473,3477SS,3478SS | Must Start On | 12/1/22 | 24 | 0d | November 7, 2022 8:00 AM | December 13, 2022 5:00 PM | 24 days | No | 11/7/22 | 12/13/22 | NA | 1
8127 | Review Executive Briefing materials with State | December 7, 2022 8:00 AM | December 13, 2022 5:00 PM | 3472 | 3474 | As Soon As Possible | NA | 5 | 0d | December 7, 2022 8:00 AM | December 13, 2022 5:00 PM | 5 days | No | 12/7/22 | 12/13/22 | NA | 1
8128 | Incorporate State feedback on Executive Briefing materials | December 7, 2022 8:00 AM | December 13, 2022 5:00 PM | 3473 | 3475FS+2d | As Soon As Possible | NA | 5 | 0d | December 7, 2022 8:00 AM | December 13, 2022 5:00 PM | 5 days | No | 12/7/22 | 12/13/22 | NA | 1
8129 | Incorporate feedback from county consultants | December 16, 2022 8:00 AM | January 4, 2023 5:00 PM | 3474FS+2d | 3476FS+2d | As Soon As Possible | NA | 12 | 0d | December 16, 2022 8:00 AM | January 4, 2023 5:00 PM | 12 days | No | 12/16/22 | 1/4/23 | NA | 1
8130 | Submit final Executive Briefing presentation to State | January 9, 2023 8:00 AM | January 10, 2023 5:00 PM | 3475FS+2d | 3479 | As Soon As Possible | NA | 2 | 0d | January 9, 2023 8:00 AM | January 10, 2023 5:00 PM | 2 days | No | 1/9/23 | 1/10/23 | NA | 1
8131 | Create approach and timeline for Executive Briefings | December 1, 2022 8:00 AM | February 14, 2023 5:00 PM | 3472SS | 3479,5609FS+7d,3480FS+7d | As Soon As Possible | NA | 51 | 0d | December 1, 2022 8:00 AM | February 14, 2023 5:00 PM | 51 days | No | 12/1/22 | 2/14/23 | NA | 1
8132 | Draft letter to Org Sponsors (Directors/Deputy Directors) | November 28, 2022 8:00 AM | December 12, 2022 5:00 PM | 3472SS | 3479 | As Soon As Possible | NA | 11 | 0d | November 28, 2022 8:00 AM | December 12, 2022 5:00 PM | 11 days | No | 11/28/22 | 12/12/22 | NA | 1
8133 | Review approach, timeline, and letter with State | February 6, 2023 8:00 AM | March 10, 2023 5:00 PM | 3477,3478,3476 | 3481 | As Soon As Possible | NA | 24 | 0d | February 6, 2023 8:00 AM | March 10, 2023 5:00 PM | 24 days | No | 2/6/23 | 3/10/23 | NA | 1
8134 | Communicate with CWDA March mtg that engagement is beginning and to expect the Directors letter | February 27, 2023 8:00 AM | March 10, 2023 5:00 PM | 3477FS+7d | 3482 | As Soon As Possible | NA | 10 | 0d | February 27, 2023 8:00 AM | March 10, 2023 5:00 PM | 10 days | No | 2/27/23 | 3/10/23 | NA | 1
8135 | Incorporate State feedback on approach, timeline, and letter | February 24, 2023 8:00 AM | March 17, 2023 5:00 PM | 3479 | 3482FS+29d | As Soon As Possible | NA | 16 | 0d | February 24, 2023 8:00 AM | March 17, 2023 5:00 PM | 16 days | No | 2/24/23 | 3/17/23 | NA | 1
8136 | Send letter to Org Sponsors | May 1, 2023 8:00 AM | May 3, 2023 5:00 PM | 3481FS+29d,3463,3469,3480 | 3483 | As Soon As Possible | NA | 3 | 0d | May 1, 2023 8:00 AM | May 3, 2023 5:00 PM | 3 days | No | 5/1/23 | 5/3/23 | NA | 1
8137 | Schedule Executive Briefings | May 4, 2023 8:00 AM | June 16, 2023 5:00 PM | 3482 | 3484FS+19d | As Soon As Possible | NA | 31 | 0d | May 4, 2023 8:00 AM | June 16, 2023 5:00 PM | 31 days | No | 5/4/23 | 6/16/23 | NA | 1
8138 | Conduct Executive Briefings | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM | 3483FS+19d | 3486FS+1d,3487FS+1d,3491,3494FS+335d | As Soon As Possible | NA | 10 | 0d | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM | 10 days | No | 7/17/23 | 7/28/23 | NA | 1
8150 | Establish Org Implementation Teams | August 1, 2023 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 480 | 0d | August 1, 2023 8:00 AM | January 16, 2025 5:00 PM | 367 days | No | 8/1/23 | 6/30/25 | NA | 1
8151 | Identify / Collect names of Implementation Coordinators from Orgs | August 1, 2023 8:00 AM | September 29, 2023 5:00 PM | 3484FS+1d | 3491FS-10d | As Soon As Possible | NA | 43 | 0d | August 1, 2023 8:00 AM | September 29, 2023 5:00 PM | 43 days | No | 8/1/23 | 9/29/23 | NA | 1
8152 | Draft letter to Implementation Coordinators with instructions for establishing Org Implementation Teams | August 1, 2023 8:00 AM | August 18, 2023 5:00 PM | 3484FS+1d | 3488 | As Soon As Possible | NA | 14 | 0d | August 1, 2023 8:00 AM | August 18, 2023 5:00 PM | 14 days | No | 8/1/23 | 8/18/23 | NA | 1
8153 | Send letter to Implementation Coordinators with instructions for establishing Org Implementation Teams | August 21, 2023 8:00 AM | September 29, 2023 5:00 PM | 3487 | 3491SS+15d | As Soon As Possible | NA | 29 | 0d | August 21, 2023 8:00 AM | September 29, 2023 5:00 PM | 29 days | No | 8/21/23 | 9/29/23 | NA | 1
8155 | Kickoff Meetings with Org Implementation Teams | September 11, 2023 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 452 | 0d | September 11, 2023 8:00 AM | January 16, 2025 5:00 PM | 339 days | No | 9/11/23 | 6/30/25 | NA | 1
8156 | Schedule Kickoff Meetings | September 11, 2023 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 410 | 0d | September 11, 2023 8:00 AM | December 30, 2024 5:00 PM | 327 days | No | 9/11/23 | 4/30/25 | NA | 1
8157 | Schedule Kickoff Meetings - Counties' Child Welfare Service Depts | September 11, 2023 8:00 AM | October 27, 2023 5:00 PM | 3484,3486FS-10d,3488SS+15d | 3557SS+10d,5117FS+6d,5150FS+2d,3554SS-60d,5148FS-44d,3502FS+34d,3496SS+10d,3492FS+319d | As Soon As Possible | NA | 35 | 0d | September 11, 2023 8:00 AM | October 27, 2023 5:00 PM | 35 days | No | 9/11/23 | 10/27/23 | NA | 1
13043 | Conduct Executive Briefings - Probation Depts. | February 10, 2025 8:00 AM | February 28, 2025 5:00 PM | 3491FS+319d | 3493FS+20d | As Soon As Possible | NA | 14 | 0d | NA | NA | 0 days? | No | 2/10/25 | 2/28/25 | NA | 1
8159 | Schedule Kickoff Meetings - Counties' Probation Depts | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 3492FS+20d | 3497 | As Soon As Possible | NA | 22 | 0d | August 26, 2024 8:00 AM | September 24, 2024 5:00 PM | 22 days | No | 4/1/25 | 4/30/25 | NA | 1
8160 | Schedule Kickoff Meetings - Tribes | November 27, 2024 8:00 AM | December 30, 2024 5:00 PM | 3484FS+335d | 3499FS+22d | As Soon As Possible | NA | 21 | 0d | November 27, 2024 8:00 AM | December 30, 2024 5:00 PM | 21 days | No | 11/27/24 | 12/30/24 | NA | 1
8161 | Conduct Kickoff Meetings | September 25, 2023 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 442 | 0d | September 25, 2023 8:00 AM | January 16, 2025 5:00 PM | 329 days | No | 9/25/23 | 6/30/25 | NA | 1
8162 | Conduct Kickoff Meetings - Counties' Child Welfare Service Depts | September 25, 2023 8:00 AM | November 14, 2023 5:00 PM | 3491SS+10d | 3886 | As Soon As Possible | NA | 36 | 0d | September 25, 2023 8:00 AM | November 14, 2023 5:00 PM | 36 days | No | 9/25/23 | 11/14/23 | NA | 1
8164 | Conduct Kickoff Meetings - Counties' Probation Depts (Wave I) | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 3493 | 3498,3563SS+12d | As Soon As Possible | NA | 21 | 0d | September 25, 2024 8:00 AM | October 24, 2024 5:00 PM | 22 days | No | 5/1/25 | 5/30/25 | NA | 1
11789 | Conduct Kickoff Meetings - Counties' Probation Depts (Wave II) | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 3497 | 3886 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
8165 | Conduct Kickoff Meetings - Tribes | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 3494FS+22d | 3561 | As Soon As Possible | NA | 19 | 0d | January 3, 2025 8:00 AM | January 16, 2025 5:00 PM | 10 days | No | 2/3/25 | 2/28/25 | NA | 1
8166 | Implementation Updates to County Directors | January 8, 2024 8:00 AM | August 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 145 | 0d | January 8, 2024 8:00 AM | July 29, 2024 5:00 PM | 141 days | No | 1/8/24 | 8/2/24 | NA | 1
8167 | 1st Quarter 2024 Updates | January 8, 2024 8:00 AM | February 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | January 8, 2024 8:00 AM | February 2, 2024 5:00 PM | 19 days | No | 1/8/24 | 2/2/24 | NA | 1
8168 | Draft email to County Directors to inform them of Implementation Team Activities since July 2023 executive Briefings and to share Go-Live Readiness Checklist dashboard | January 8, 2024 8:00 AM | January 12, 2024 5:00 PM | 3491FS+34d | 3503,3504SS | As Soon As Possible | NA | 5 | 0d | January 8, 2024 8:00 AM | January 12, 2024 5:00 PM | 5 days | No | 1/8/24 | 1/12/24 | NA | 1
8169 | Review email with State Implementation Management Team and incorporate feedback | January 16, 2024 8:00 AM | January 22, 2024 5:00 PM | 3502 | 3505 | As Soon As Possible | NA | 5 | 0d | January 16, 2024 8:00 AM | January 22, 2024 5:00 PM | 5 days | No | 1/16/24 | 1/22/24 | NA | 1
8170 | Determine appropriate distribution list for email | January 8, 2024 8:00 AM | January 19, 2024 5:00 PM | 3502SS | 3505FS+5d | As Soon As Possible | NA | 9 | 0d | January 8, 2024 8:00 AM | January 19, 2024 5:00 PM | 9 days | No | 1/8/24 | 1/19/24 | NA | 1
8171 | Distribute email to County Directors | January 29, 2024 8:00 AM | February 2, 2024 5:00 PM | 3504FS+5d,3503 | 3507FS+107d | As Soon As Possible | NA | 5 | 0d | January 29, 2024 8:00 AM | February 2, 2024 5:00 PM | 5 days | No | 1/29/24 | 2/2/24 | NA | 1
8172 | 2nd Quarter 2024 Updates | July 9, 2024 8:00 AM | August 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | July 1, 2024 8:00 AM | July 29, 2024 5:00 PM | 20 days | No | 7/9/24 | 8/2/24 | NA | 1
8173 | Create 58 PPT files – one for each County in template | July 9, 2024 8:00 AM | July 17, 2024 5:00 PM | 3505FS+107d | 3508 | As Soon As Possible | NA | 7 | 0d | July 1, 2024 8:00 AM | July 8, 2024 5:00 PM | 5 days | No | 7/9/24 | 7/17/24 | NA | 1
8174 | Send county-specific files & Draft Email to IL team members for review | July 18, 2024 8:00 AM | July 19, 2024 5:00 PM | 3507 | 3509 | As Soon As Possible | NA | 2 | 0d | July 9, 2024 8:00 AM | July 15, 2024 5:00 PM | 5 days | No | 7/18/24 | 7/19/24 | NA | 1
8175 | ILs review PPT files with ICs w/ instructions for ICs to update County Executives with cc: to SPOCs for awareness | July 22, 2024 8:00 AM | July 26, 2024 5:00 PM | 3508 | 3510SS | As Soon As Possible | NA | 5 | 0d | July 16, 2024 8:00 AM | July 22, 2024 5:00 PM | 5 days | No | 7/22/24 | 7/26/24 | NA | 1
8176 | ICs communicate status to County Executives | July 22, 2024 8:00 AM | July 26, 2024 5:00 PM | 3509SS | 3511 | As Soon As Possible | NA | 5 | 0d | July 16, 2024 8:00 AM | July 22, 2024 5:00 PM | 5 days | No | 7/22/24 | 7/26/24 | NA | 1
8177 | Email PPT files to County Executives from Imp Mailbox with cc to ICs and SPOCs | July 29, 2024 8:00 AM | August 2, 2024 5:00 PM | 3510 | 3516 | As Soon As Possible | NA | 5 | 0d | July 23, 2024 8:00 AM | July 29, 2024 5:00 PM | 5 days | No | 7/29/24 | 8/2/24 | NA | 1
8178 | Initiate CDSS Engagement | October 2, 2023 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 395 | 0d | October 30, 2023 8:00 AM | January 6, 2025 5:00 PM | 296 days | No | 10/2/23 | 4/30/25 | NA | 1
8179 | CFSD | October 30, 2023 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 314 | 0d | October 30, 2023 8:00 AM | October 30, 2024 5:00 PM | 253 days | No | 10/30/23 | 1/31/25 | NA | 1
8180 | Establish CFSD Implementation Team | October 30, 2023 8:00 AM | February 16, 2024 5:00 PM | 3192 | 3515FS+101d,3520FS+29d | As Soon As Possible | NA | 74 | 0d | October 30, 2023 8:00 AM | February 16, 2024 5:00 PM | 74 days | No | 10/30/23 | 2/16/24 | NA | 1
8181 | Schedule Kickoff Meeting with CFSD Implementation Team | July 15, 2024 8:00 AM | August 23, 2024 5:00 PM | 3514FS+101d | 3516FS+14d | As Soon As Possible | NA | 30 | 0d | July 15, 2024 8:00 AM | July 26, 2024 5:00 PM | 10 days | No | 7/15/24 | 8/23/24 | NA | 1
8182 | Conduct Kickoff Meeting with CFSD Implementation Team | September 13, 2024 8:00 AM | November 4, 2024 5:00 PM | 3515FS+14d,3511 | 3517SS+3d | As Soon As Possible | NA | 37 | 0d | August 5, 2024 8:00 AM | August 30, 2024 5:00 PM | 20 days | No | 9/13/24 | 11/4/24 | NA | 1
8183 | Schedule Organization Assessment | September 18, 2024 8:00 AM | November 22, 2024 5:00 PM | 3516SS+3d | 3518SS+17d | As Soon As Possible | NA | 47 | 0d | September 27, 2024 8:00 AM | October 10, 2024 5:00 PM | 10 days | No | 9/18/24 | 11/22/24 | NA | 1
8184 | CFSD - Conduct Organization Assessment | October 11, 2024 8:00 AM | January 31, 2025 5:00 PM | 3517SS+17d | 3886 | As Soon As Possible | NA | 75 | 0d | October 11, 2024 8:00 AM | October 30, 2024 5:00 PM | 14 days | No | 10/11/24 | 1/31/25 | NA | 1
8185 | CCLD | April 2, 2024 8:00 AM | October 9, 2024 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | April 2, 2024 8:00 AM | January 6, 2025 5:00 PM | 193 days | No | 4/2/24 | 10/9/24 | NA | 1
8186 | Establish CCLD Implementation Team | April 2, 2024 8:00 AM | August 20, 2024 5:00 PM | 3514FS+29d | 3521SS+34d | As Soon As Possible | NA | 99 | 0d | April 2, 2024 8:00 AM | June 28, 2024 5:00 PM | 63 days | No | 4/2/24 | 8/20/24 | NA | 1
8187 | Schedule Kickoff Meeting with CCLD Implementation Team | May 20, 2024 8:00 AM | July 8, 2024 5:00 PM | 3520SS+34d | 3522FS+14d,3523FS+9d | As Soon As Possible | NA | 34 | 0d | July 29, 2024 8:00 AM | August 5, 2024 5:00 PM | 6 days | No | 5/20/24 | 7/8/24 | NA | 1
8188 | Conduct Kickoff Meeting with CDSS Implementation Team | July 29, 2024 8:00 AM | July 31, 2024 5:00 PM | 3521FS+14d | 3886 | As Soon As Possible | NA | 3 | 0d | September 2, 2024 8:00 AM | September 9, 2024 5:00 PM | 6 days | No | 7/29/24 | 7/31/24 | NA | 1
8189 | Schedule Organization Assessment | July 22, 2024 8:00 AM | August 2, 2024 5:00 PM | 3521FS+9d | 3524FS+30d | As Soon As Possible | NA | 10 | 0d | October 21, 2024 8:00 AM | November 1, 2024 5:00 PM | 10 days | No | 7/22/24 | 8/2/24 | NA | 1
8190 | CCLD - Conduct Organization Assessment | September 16, 2024 8:00 AM | October 9, 2024 5:00 PM | 3523FS+30d | 3562 | As Soon As Possible | NA | 18 | 0d | December 10, 2024 8:00 AM | January 6, 2025 5:00 PM | 18 days | No | 9/16/24 | 10/9/24 | NA | 1
8191 | RADD | October 2, 2023 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 313 | 0d | April 2, 2024 8:00 AM | December 27, 2024 5:00 PM | 188 days | No | 10/2/23 | 12/31/24 | NA | 1
8192 | Establish RADD Implementation Team | October 2, 2023 8:00 AM | September 5, 2024 5:00 PM |  |  | As Soon As Possible | NA | 234 | 0d | April 2, 2024 8:00 AM | June 28, 2024 5:00 PM | 63 days | No | 10/2/23 | 9/5/24 | NA | 1
11664 | Conduct discovery sessions with RADD | October 2, 2023 8:00 AM | March 29, 2024 5:00 PM | 3192 | 3528FS+21d,3529FS+21d | Start No Earlier Than | 10/2/23 | 123 | 0d | NA | NA | 0 days? | No | 10/2/23 | 3/29/24 | NA | 1
11663 | Develop recommended RADD Implementation Team structure | May 1, 2024 8:00 AM | May 29, 2024 5:00 PM | 3527FS+21d | 3886 | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/29/24 | NA | 1
11662 | Present recommended RADD Implementation Team structure to RADD leadership | May 1, 2024 8:00 AM | May 29, 2024 5:00 PM | 3527FS+21d | 3530FS+44d | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/29/24 | NA | 1
11661 | Incorporate feedback from RADD leadership | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 3529FS+44d | 3531SS+4d | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
11660 | Prepare presentation materials for RADD Implementation Team Kickoff Meeting | August 7, 2024 8:00 AM | September 5, 2024 5:00 PM | 3530SS+4d | 3532SS | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/7/24 | 9/5/24 | NA | 1
8193 | Schedule Kickoff Meeting with RADD Implementation Team | August 7, 2024 8:00 AM | August 27, 2024 5:00 PM | 3531SS | 3533FS+37d | As Soon As Possible | NA | 15 | 0d | September 2, 2024 8:00 AM | September 6, 2024 5:00 PM | 5 days | No | 8/7/24 | 8/27/24 | NA | 1
8194 | Conduct Kickoff Meeting with RADD Implementation Team | October 18, 2024 8:00 AM | October 24, 2024 5:00 PM | 3532FS+37d | 3534 | As Soon As Possible | NA | 5 | 0d | September 30, 2024 8:00 AM | October 4, 2024 5:00 PM | 5 days | No | 10/18/24 | 10/24/24 | NA | 1
8195 | Schedule Organization Assessment | October 25, 2024 8:00 AM | November 7, 2024 5:00 PM | 3533 | 3535FS+1d | As Soon As Possible | NA | 10 | 0d | October 14, 2024 8:00 AM | October 25, 2024 5:00 PM | 10 days | No | 10/25/24 | 11/7/24 | NA | 1
8196 | RADD - Conduct Organization Assessment | November 12, 2024 8:00 AM | December 31, 2024 5:00 PM | 3534FS+1d | 3561 | As Soon As Possible | NA | 33 | 0d | December 3, 2024 8:00 AM | December 27, 2024 5:00 PM | 18 days | No | 11/12/24 | 12/31/24 | NA | 1
11799 | Office of Equity | August 1, 2024 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 187 | 0d | NA | NA | 0 days? | No | 8/1/24 | 4/30/25 | NA | 1
11808 | Schedule Executive Briefing | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 3192 | 3538,3546SS | Start No Earlier Than | 8/1/24 | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
11807 | Conduct Executive Briefing - Office of Equity | September 2, 2024 8:00 AM | September 10, 2024 5:00 PM | 3537 | 3539FS+38d | As Soon As Possible | NA | 7 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/10/24 | NA | 1
11806 | Conduct Discovery Sessions | November 4, 2024 8:00 AM | November 27, 2024 5:00 PM | 3538FS+38d | 3540 | As Soon As Possible | NA | 17 | 0d | NA | NA | 0 days? | No | 11/4/24 | 11/27/24 | NA | 1
11805 | Propose Implementation Team Structure | December 2, 2024 8:00 AM | December 26, 2024 5:00 PM | 3539 | 3541 | As Soon As Possible | NA | 18 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/26/24 | NA | 1
11804 | Establish Office of Equity Implementation Team | December 27, 2024 8:00 AM | January 28, 2025 5:00 PM | 3540 | 3542FS+2d | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/27/24 | 1/28/25 | NA | 1
11803 | Schedule Kickoff Meeting with Office of Equity Implementation Team | January 31, 2025 8:00 AM | February 6, 2025 5:00 PM | 3541FS+2d | 3543 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 1/31/25 | 2/6/25 | NA | 1
11802 | Conduct Kickoff Meeting with Office of Equity Implementation Team | February 7, 2025 8:00 AM | March 13, 2025 5:00 PM | 3542 | 3544 | As Soon As Possible | NA | 24 | 0d | NA | NA | 0 days? | No | 2/7/25 | 3/13/25 | NA | 1
11801 | Conduct Organization Assessment - Office of Equity | March 14, 2025 8:00 AM | April 30, 2025 5:00 PM | 3543 | 3886 | As Soon As Possible | NA | 33 | 0d | NA | NA | 0 days? | No | 3/14/25 | 4/30/25 | NA | 1
11798 | Finance & Accounting Division | August 1, 2024 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 145 | 0d | NA | NA | 0 days? | No | 8/1/24 | 2/28/25 | NA | 1
11797 | Schedule Executive Briefing | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 3537SS | 3547 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
11796 | Conduct Executive Briefing - Finance & Accounting Division | September 2, 2024 8:00 AM | September 6, 2024 5:00 PM | 3546 | 3548 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/6/24 | NA | 1
11795 | Propose Implementation Team Structure | September 9, 2024 8:00 AM | September 10, 2024 5:00 PM | 3547 | 3549FS+2d,3550FS+8d | As Soon As Possible | NA | 2 | 0d | NA | NA | 0 days? | No | 9/9/24 | 9/10/24 | NA | 1
11794 | Establish Office of Finance & Accounting Division Implementation Team | September 13, 2024 8:00 AM | September 20, 2024 5:00 PM | 3548FS+2d | 3886 | As Soon As Possible | NA | 6 | 0d | NA | NA | 0 days? | No | 9/13/24 | 9/20/24 | NA | 1
11793 | Schedule Kickoff Meeting with Office of Finance & Accounting Division Implementation Team | September 23, 2024 8:00 AM | October 7, 2024 5:00 PM | 3548FS+8d | 3551FS+39d | As Soon As Possible | NA | 11 | 0d | NA | NA | 0 days? | No | 9/23/24 | 10/7/24 | NA | 1
11792 | Conduct Kickoff Meeting with Office of Finance & Accounting Division Implementation Team | December 5, 2024 8:00 AM | December 5, 2024 5:00 PM | 3550FS+39d | 3552FS+24d | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 12/5/24 | 12/5/24 | NA | 1
11791 | Conduct Organization Assessment - Finance & Accounting Division | January 13, 2025 8:00 AM | February 28, 2025 5:00 PM | 3551FS+24d | 3886 | As Soon As Possible | NA | 33 | 0d | NA | NA | 0 days? | No | 1/13/25 | 2/28/25 | NA | 1
8204 | Conduct Org Assessments | June 29, 2023 8:00 AM | July 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 512 | 0d | June 29, 2023 8:00 AM | February 27, 2025 5:00 PM | 417 days | No | 6/29/23 | 7/15/25 | NA | 1
8205 | Develop timeline for Org Assessments with input from OCM and Training | June 29, 2023 8:00 AM | July 13, 2023 5:00 PM | 3491SS-60d | 3555 | As Soon As Possible | NA | 10 | 0d | June 29, 2023 8:00 AM | July 13, 2023 5:00 PM | 10 days | No | 6/29/23 | 7/13/23 | NA | 1
8206 | Review timeline with State | July 14, 2023 8:00 AM | July 20, 2023 5:00 PM | 3554 | 3556 | As Soon As Possible | NA | 5 | 0d | July 14, 2023 8:00 AM | July 20, 2023 5:00 PM | 5 days | No | 7/14/23 | 7/20/23 | NA | 1
8207 | Incorporate State feedback on approach and timeline | July 21, 2023 8:00 AM | July 27, 2023 5:00 PM | 3555 | 3557 | As Soon As Possible | NA | 5 | 0d | July 21, 2023 8:00 AM | July 27, 2023 5:00 PM | 5 days | No | 7/21/23 | 7/27/23 | NA | 1
8208 | Schedule Org Assessments - Counties' Child Welfare Service Depts | October 9, 2023 8:00 AM | November 21, 2023 5:00 PM | 3491SS+10d,3556 | 3558SS-5d | As Soon As Possible | NA | 31 | 0d | October 9, 2023 8:00 AM | November 21, 2023 5:00 PM | 31 days | No | 10/9/23 | 11/21/23 | NA | 1
8209 | Prepare IL Team to conduct Assessments | October 2, 2023 8:00 AM | October 20, 2023 5:00 PM | 3557SS-5d | 3559FS+7d | As Soon As Possible | NA | 15 | 0d | October 2, 2023 8:00 AM | October 20, 2023 5:00 PM | 15 days | No | 10/2/23 | 10/20/23 | NA | 1
8210 | Conduct Assessments - Counties' Child Welfare Service Depts | November 1, 2023 8:00 AM | December 15, 2023 5:00 PM | 3558FS+7d | 3872FS+452d,3560SS+5d,3567SS+24d | As Soon As Possible | NA | 30 | 0d | November 1, 2023 8:00 AM | December 15, 2023 5:00 PM | 30 days | No | 11/1/23 | 12/15/23 | NA | 1
8211 | IL conducts Assessments follow up to complete spreadsheet - Counties' Child Welfare Service Depts | November 8, 2023 8:00 AM | January 9, 2024 5:00 PM | 3559SS+5d | 3561 | As Soon As Possible | NA | 40 | 0d | November 8, 2023 8:00 AM | January 9, 2024 5:00 PM | 40 days | No | 11/8/23 | 1/9/24 | NA | 1
8212 | Schedule Org Assessments - Tribes | March 3, 2025 8:00 AM | March 13, 2025 5:00 PM | 3499,3535,3560 | 3562FS+20d | As Soon As Possible | NA | 9 | 0d | January 17, 2025 8:00 AM | January 30, 2025 5:00 PM | 9 days | No | 3/3/25 | 3/13/25 | NA | 1
8213 | Conduct Org Assessments - Tribes | April 14, 2025 8:00 AM | May 8, 2025 5:00 PM | 3561FS+20d,3524 | 3872 | As Soon As Possible | NA | 19 | 0d | January 31, 2025 8:00 AM | February 27, 2025 5:00 PM | 19 days | No | 4/14/25 | 5/8/25 | NA | 1
12256 | Schedule Org Assessments - Counties' Probation Depts. | May 19, 2025 8:00 AM | June 30, 2025 5:00 PM | 3497SS+12d | 3564SS+10d | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 5/19/25 | 6/30/25 | NA | 1
12255 | Conduct Org Assessments - Counties' Probation Depts. | June 3, 2025 8:00 AM | July 15, 2025 5:00 PM | 3563SS+10d | 3886 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 6/3/25 | 7/15/25 | NA | 1
8214 | Prepare for Org Readiness Meetings | December 4, 2023 8:00 AM | September 22, 2026 5:00 PM |  |  | As Soon As Possible | NA | 704 | 8d | December 4, 2023 8:00 AM | November 21, 2024 5:00 PM | 246 days | No | 12/4/23 | NA | NA | 0.66000000000000003
8215 | Prepare for January 2024 Org Readiness Meetings | December 4, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | December 4, 2023 8:00 AM | December 15, 2023 5:00 PM | 10 days | No | 12/4/23 | 12/15/23 | NA | 1
8216 | Collaborate with OCM and Trainings teams to develop agenda for January Org Readiness Meetings | December 8, 2023 8:00 AM | December 13, 2023 5:00 PM | 3559SS+24d | 3568FF-3d | As Soon As Possible | NA | 4 | 0d | December 8, 2023 8:00 AM | December 13, 2023 5:00 PM | 4 days | No | 12/8/23 | 12/13/23 | NA | 1
8217 | Create presentation materials | December 4, 2023 8:00 AM | December 8, 2023 5:00 PM | 3567FF-3d | 3569 | As Soon As Possible | NA | 5 | 0d | December 4, 2023 8:00 AM | December 8, 2023 5:00 PM | 5 days | No | 12/4/23 | 12/8/23 | NA | 1
8218 | Review presentation materials and incorporate feedback | December 11, 2023 8:00 AM | December 15, 2023 5:00 PM | 3568 | 3704FS+9d,3571FS+18d | As Soon As Possible | NA | 5 | 0d | December 11, 2023 8:00 AM | December 15, 2023 5:00 PM | 5 days | No | 12/11/23 | 12/15/23 | NA | 1
8219 | Prepare for February 2024 Org Readiness Meetings | January 16, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 12 | 0d | January 16, 2024 8:00 AM | January 31, 2024 5:00 PM | 12 days | No | 1/16/24 | 1/31/24 | NA | 1
8220 | Collaborate with OCM and Trainings teams to develop agenda for February Org Readiness Meetings | January 16, 2024 8:00 AM | January 19, 2024 5:00 PM | 3569FS+18d | 3572 | As Soon As Possible | NA | 4 | 0d | January 16, 2024 8:00 AM | January 19, 2024 5:00 PM | 4 days | No | 1/16/24 | 1/19/24 | NA | 1
8221 | Create presentation materials | January 22, 2024 8:00 AM | January 26, 2024 5:00 PM | 3571 | 3573 | As Soon As Possible | NA | 5 | 0d | January 22, 2024 8:00 AM | January 26, 2024 5:00 PM | 5 days | No | 1/22/24 | 1/26/24 | NA | 1
8222 | Review presentation materials and incorporate feedback | January 29, 2024 8:00 AM | January 31, 2024 5:00 PM | 3572 | 3575FS+2d | As Soon As Possible | NA | 3 | 0d | January 29, 2024 8:00 AM | January 31, 2024 5:00 PM | 3 days | No | 1/29/24 | 1/31/24 | NA | 1
8223 | Prepare for March 2024 Org Readiness Meetings | February 5, 2024 8:00 AM | February 23, 2024 5:00 PM |  |  | As Soon As Possible | NA | 14 | 0d | February 5, 2024 8:00 AM | February 23, 2024 5:00 PM | 14 days | No | 2/5/24 | 2/23/24 | NA | 1
8224 | Collaborate with OCM and Trainings teams to develop agenda for March Org Readiness Meetings | February 5, 2024 8:00 AM | February 9, 2024 5:00 PM | 3573FS+2d | 3576 | As Soon As Possible | NA | 5 | 0d | February 5, 2024 8:00 AM | February 9, 2024 5:00 PM | 5 days | No | 2/5/24 | 2/9/24 | NA | 1
8225 | Create presentation materials | February 12, 2024 8:00 AM | February 16, 2024 5:00 PM | 3575 | 3577 | As Soon As Possible | NA | 5 | 0d | February 12, 2024 8:00 AM | February 16, 2024 5:00 PM | 5 days | No | 2/12/24 | 2/16/24 | NA | 1
8226 | Review presentation materials and incorporate feedback | February 20, 2024 8:00 AM | February 23, 2024 5:00 PM | 3576 | 3579FS+5d | As Soon As Possible | NA | 4 | 0d | February 20, 2024 8:00 AM | February 23, 2024 5:00 PM | 4 days | No | 2/20/24 | 2/23/24 | NA | 1
8227 | Prepare for April 2024 Org Readiness Meetings | March 4, 2024 8:00 AM | March 22, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | March 4, 2024 8:00 AM | March 22, 2024 5:00 PM | 15 days | No | 3/4/24 | 3/22/24 | NA | 1
8228 | Collaborate with OCM and Trainings teams to develop agenda for April Org Readiness Meetings | March 4, 2024 8:00 AM | March 8, 2024 5:00 PM | 3577FS+5d | 3580 | As Soon As Possible | NA | 5 | 0d | March 4, 2024 8:00 AM | March 8, 2024 5:00 PM | 5 days | No | 3/4/24 | 3/8/24 | NA | 1
8229 | Create presentation materials | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 3579 | 3581 | As Soon As Possible | NA | 5 | 0d | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 5 days | No | 3/11/24 | 3/15/24 | NA | 1
8230 | Review presentation materials and incorporate feedback | March 18, 2024 8:00 AM | March 22, 2024 5:00 PM | 3580 | 3583FS+5d | As Soon As Possible | NA | 5 | 0d | March 18, 2024 8:00 AM | March 22, 2024 5:00 PM | 5 days | No | 3/18/24 | 3/22/24 | NA | 1
8231 | Prepare for May 2024 Org Readiness Meetings | April 2, 2024 8:00 AM | April 26, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | April 2, 2024 8:00 AM | April 26, 2024 5:00 PM | 19 days | No | 4/2/24 | 4/26/24 | NA | 1
8232 | Collaborate with OCM and Trainings teams to develop agenda for May Org Readiness Meetings | April 2, 2024 8:00 AM | April 5, 2024 5:00 PM | 3581FS+5d | 3584 | As Soon As Possible | NA | 4 | 0d | April 2, 2024 8:00 AM | April 5, 2024 5:00 PM | 4 days | No | 4/2/24 | 4/5/24 | NA | 1
8233 | Create presentation materials | April 8, 2024 8:00 AM | April 12, 2024 5:00 PM | 3583 | 3585 | As Soon As Possible | NA | 5 | 0d | April 8, 2024 8:00 AM | April 12, 2024 5:00 PM | 5 days | No | 4/8/24 | 4/12/24 | NA | 1
8234 | Prepare for April 2024 Org Readiness Meetings: Review presentation materials and incorporate feedback | April 15, 2024 8:00 AM | April 26, 2024 5:00 PM | 3584 | 3587FS+2d | As Soon As Possible | NA | 10 | 0d | April 15, 2024 8:00 AM | April 26, 2024 5:00 PM | 10 days | No | 4/15/24 | 4/26/24 | NA | 1
8235 | Prepare for June 2024 Org Readiness Meetings | May 1, 2024 8:00 AM | May 21, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | May 1, 2024 8:00 AM | May 21, 2024 5:00 PM | 15 days | No | 5/1/24 | 5/21/24 | NA | 1
8236 | Collaborate with OCM and Trainings teams to develop agenda for June Org Readiness Meetings | May 1, 2024 8:00 AM | May 7, 2024 5:00 PM | 3585FS+2d | 3588 | As Soon As Possible | NA | 5 | 0d | May 1, 2024 8:00 AM | May 7, 2024 5:00 PM | 5 days | No | 5/1/24 | 5/7/24 | NA | 1
8237 | Create presentation materials | May 8, 2024 8:00 AM | May 14, 2024 5:00 PM | 3587 | 3589 | As Soon As Possible | NA | 5 | 0d | May 8, 2024 8:00 AM | May 14, 2024 5:00 PM | 5 days | No | 5/8/24 | 5/14/24 | NA | 1
8238 | Review presentation materials and incorporate feedback | May 15, 2024 8:00 AM | May 21, 2024 5:00 PM | 3588 | 3591FS+7d | As Soon As Possible | NA | 5 | 0d | May 15, 2024 8:00 AM | May 21, 2024 5:00 PM | 5 days | No | 5/15/24 | 5/21/24 | NA | 1
8239 | Prepare for July 2024 Org Readiness Meetings | June 3, 2024 8:00 AM | June 21, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | June 3, 2024 8:00 AM | June 21, 2024 5:00 PM | 15 days | No | 6/3/24 | 6/21/24 | NA | 1
8240 | Collaborate with OCM and Trainings teams to develop agenda for July Org Readiness Meetings | June 3, 2024 8:00 AM | June 7, 2024 5:00 PM | 3589FS+7d | 3592 | As Soon As Possible | NA | 5 | 0d | June 3, 2024 8:00 AM | June 7, 2024 5:00 PM | 5 days | No | 6/3/24 | 6/7/24 | NA | 1
8241 | Create presentation materials | June 10, 2024 8:00 AM | June 14, 2024 5:00 PM | 3591 | 3593 | As Soon As Possible | NA | 5 | 0d | June 10, 2024 8:00 AM | June 14, 2024 5:00 PM | 5 days | No | 6/10/24 | 6/14/24 | NA | 1
8242 | Review presentation materials and incorporate feedback | June 17, 2024 8:00 AM | June 21, 2024 5:00 PM | 3592 | 3595FS+5d | As Soon As Possible | NA | 5 | 0d | June 17, 2024 8:00 AM | June 21, 2024 5:00 PM | 5 days | No | 6/17/24 | 6/21/24 | NA | 1
8243 | Prepare for August 2024 Org Readiness Meetings | July 1, 2024 8:00 AM | July 22, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | July 1, 2024 8:00 AM | July 22, 2024 5:00 PM | 15 days | No | 7/1/24 | 7/22/24 | NA | 1
8244 | Collaborate with OCM and Trainings teams to develop agenda for August Org Readiness Meetings | July 1, 2024 8:00 AM | July 8, 2024 5:00 PM | 3593FS+5d | 3596 | As Soon As Possible | NA | 5 | 0d | July 1, 2024 8:00 AM | July 8, 2024 5:00 PM | 5 days | No | 7/1/24 | 7/8/24 | NA | 1
8245 | Create presentation materials | July 9, 2024 8:00 AM | July 15, 2024 5:00 PM | 3595 | 3597 | As Soon As Possible | NA | 5 | 0d | July 9, 2024 8:00 AM | July 15, 2024 5:00 PM | 5 days | No | 7/9/24 | 7/15/24 | NA | 1
8246 | Review presentation materials and incorporate feedback | July 16, 2024 8:00 AM | July 22, 2024 5:00 PM | 3596 | 3599FS+7d | As Soon As Possible | NA | 5 | 0d | July 16, 2024 8:00 AM | July 22, 2024 5:00 PM | 5 days | No | 7/16/24 | 7/22/24 | NA | 1
8247 | Prepare for September 2024 Org Readiness Meetings | August 1, 2024 8:00 AM | August 21, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | August 1, 2024 8:00 AM | August 21, 2024 5:00 PM | 15 days | No | 8/1/24 | 8/21/24 | NA | 1
8248 | Collaborate with OCM and Trainings teams to develop agenda for September Org Readiness Meetings | August 1, 2024 8:00 AM | August 7, 2024 5:00 PM | 3597FS+7d | 3600 | As Soon As Possible | NA | 5 | 0d | August 1, 2024 8:00 AM | August 7, 2024 5:00 PM | 5 days | No | 8/1/24 | 8/7/24 | NA | 1
8249 | Create presentation materials | August 8, 2024 8:00 AM | August 14, 2024 5:00 PM | 3599 | 3601 | As Soon As Possible | NA | 5 | 0d | August 8, 2024 8:00 AM | August 14, 2024 5:00 PM | 5 days | No | 8/8/24 | 8/14/24 | NA | 1
8250 | Review presentation materials and incorporate feedback | August 15, 2024 8:00 AM | August 21, 2024 5:00 PM | 3600 | 3603FS+7d | As Soon As Possible | NA | 5 | 0d | August 15, 2024 8:00 AM | August 21, 2024 5:00 PM | 5 days | No | 8/15/24 | 8/21/24 | NA | 1
8251 | Prepare for October 2024 Org Readiness Meetings | September 2, 2024 8:00 AM | September 20, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | September 2, 2024 8:00 AM | September 20, 2024 5:00 PM | 15 days | No | 9/2/24 | 9/20/24 | NA | 1
8252 | Collaborate with OCM and Trainings teams to develop agenda for October Org Readiness Meetings | September 2, 2024 8:00 AM | September 6, 2024 5:00 PM | 3601FS+7d | 3604 | As Soon As Possible | NA | 5 | 0d | September 2, 2024 8:00 AM | September 6, 2024 5:00 PM | 5 days | No | 9/2/24 | 9/6/24 | NA | 1
8253 | Create presentation materials | September 9, 2024 8:00 AM | September 13, 2024 5:00 PM | 3603 | 3605 | As Soon As Possible | NA | 5 | 0d | September 9, 2024 8:00 AM | September 13, 2024 5:00 PM | 5 days | No | 9/9/24 | 9/13/24 | NA | 1
8254 | Review presentation materials and incorporate feedback | September 16, 2024 8:00 AM | September 20, 2024 5:00 PM | 3604 | 3607FS+5d | As Soon As Possible | NA | 5 | 0d | September 16, 2024 8:00 AM | September 20, 2024 5:00 PM | 5 days | No | 9/16/24 | 9/20/24 | NA | 1
8255 | Prepare for November 2024 Org Readiness Meetings | September 30, 2024 8:00 AM | October 18, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | September 30, 2024 8:00 AM | October 18, 2024 5:00 PM | 15 days | No | 9/30/24 | 10/18/24 | NA | 1
8256 | Collaborate with OCM and Trainings teams to develop agenda for November Org Readiness Meetings | September 30, 2024 8:00 AM | October 4, 2024 5:00 PM | 3605FS+5d | 3608 | As Soon As Possible | NA | 5 | 0d | September 30, 2024 8:00 AM | October 4, 2024 5:00 PM | 5 days | No | 9/30/24 | 10/4/24 | NA | 1
8257 | Create presentation materials | October 7, 2024 8:00 AM | October 11, 2024 5:00 PM | 3607 | 3609 | As Soon As Possible | NA | 5 | 0d | October 7, 2024 8:00 AM | October 11, 2024 5:00 PM | 5 days | No | 10/7/24 | 10/11/24 | NA | 1
8258 | Review presentation materials and incorporate feedback | October 14, 2024 8:00 AM | October 18, 2024 5:00 PM | 3608 | 3611FS+8d | As Soon As Possible | NA | 5 | 0d | October 14, 2024 8:00 AM | October 18, 2024 5:00 PM | 5 days | No | 10/14/24 | 10/18/24 | NA | 1
8259 | Prepare for December 2024 Org Readiness Meetings | October 31, 2024 8:00 AM | November 21, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | October 31, 2024 8:00 AM | November 21, 2024 5:00 PM | 15 days | No | 10/31/24 | 11/21/24 | NA | 1
8260 | Collaborate with OCM and Trainings teams to develop agenda for December Org Readiness Meetings | October 31, 2024 8:00 AM | November 6, 2024 5:00 PM | 3609FS+8d | 3612 | As Soon As Possible | NA | 5 | 0d | October 31, 2024 8:00 AM | November 6, 2024 5:00 PM | 5 days | No | 10/31/24 | 11/6/24 | NA | 1
8261 | Create presentation materials | November 7, 2024 8:00 AM | November 14, 2024 5:00 PM | 3611 | 3613 | As Soon As Possible | NA | 5 | 0d | November 7, 2024 8:00 AM | November 14, 2024 5:00 PM | 5 days | No | 11/7/24 | 11/14/24 | NA | 1
8262 | Review presentation materials and incorporate feedback | November 15, 2024 8:00 AM | November 21, 2024 5:00 PM | 3612 | 3872,3615FS+4d | As Soon As Possible | NA | 5 | 0d | November 15, 2024 8:00 AM | November 21, 2024 5:00 PM | 5 days | No | 11/15/24 | 11/21/24 | NA | 1
11897 | Prepare for January 2025 Org Readiness Meetings | December 2, 2024 8:00 AM | December 20, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 12/2/24 | 12/20/24 | NA | 1
11898 | Collaborate with OCM and Trainings teams to develop agenda for January Org Readiness Meetings | December 2, 2024 8:00 AM | December 6, 2024 5:00 PM | 3613FS+4d | 3616 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 12/2/24 | 12/6/24 | NA | 1
11899 | Create presentation materials | December 9, 2024 8:00 AM | December 13, 2024 5:00 PM | 3615 | 3617 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 12/9/24 | 12/13/24 | NA | 1
11900 | Review presentation materials and incorporate feedback | December 16, 2024 8:00 AM | December 20, 2024 5:00 PM | 3616 | 3619FS+6d | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 12/16/24 | 12/20/24 | NA | 1
11901 | Prepare for February 2025 Org Readiness Meetings | January 2, 2025 8:00 AM | January 23, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 1/2/25 | 1/23/25 | NA | 1
11902 | Collaborate with OCM and Trainings teams to develop agenda for February Org Readiness Meetings | January 2, 2025 8:00 AM | January 8, 2025 5:00 PM | 3617FS+6d | 3620 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 1/2/25 | 1/8/25 | NA | 1
11903 | Create presentation materials | January 9, 2025 8:00 AM | January 15, 2025 5:00 PM | 3619 | 3621 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 1/9/25 | 1/15/25 | NA | 1
11904 | Review presentation materials and incorporate feedback | January 16, 2025 8:00 AM | January 23, 2025 5:00 PM | 3620 | 3623FS+6d | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 1/16/25 | 1/23/25 | NA | 1
11905 | Prepare for March 2025 Org Readiness Meetings | February 3, 2025 8:00 AM | February 24, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 2/3/25 | 2/24/25 | NA | 1
11906 | Collaborate with OCM and Trainings teams to develop agenda for March Org Readiness Meetings | February 3, 2025 8:00 AM | February 7, 2025 5:00 PM | 3621FS+6d | 3624 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 2/3/25 | 2/7/25 | NA | 1
11907 | Create presentation materials | February 10, 2025 8:00 AM | February 14, 2025 5:00 PM | 3623 | 3625 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 2/10/25 | 2/14/25 | NA | 1
11908 | Review presentation materials and incorporate feedback | February 18, 2025 8:00 AM | February 24, 2025 5:00 PM | 3624 | 3627FS+4d | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 2/18/25 | 2/24/25 | NA | 1
11909 | Prepare for April 2025 Org Readiness Meetings | March 3, 2025 8:00 AM | March 21, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 3/3/25 | 3/21/25 | NA | 1
11910 | Collaborate with OCM and Trainings teams to develop agenda for April Org Readiness Meetings | March 3, 2025 8:00 AM | March 7, 2025 5:00 PM | 3625FS+4d | 3628 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 3/3/25 | 3/7/25 | NA | 1
11911 | Create presentation materials | March 10, 2025 8:00 AM | March 14, 2025 5:00 PM | 3627 | 3629 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 3/10/25 | 3/14/25 | NA | 1
11912 | Review presentation materials and incorporate feedback | March 17, 2025 8:00 AM | March 21, 2025 5:00 PM | 3628 | 3631FS+5d | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 3/17/25 | 3/21/25 | NA | 1
11913 | Prepare for May 2025 Org Readiness Meetings | April 1, 2025 8:00 AM | April 21, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 4/1/25 | 4/21/25 | NA | 1
11914 | Collaborate with OCM and Trainings teams to develop agenda for May Org Readiness Meetings | April 1, 2025 8:00 AM | April 7, 2025 5:00 PM | 3629FS+5d | 3632 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 4/1/25 | 4/7/25 | NA | 1
11915 | Create presentation materials | April 8, 2025 8:00 AM | April 14, 2025 5:00 PM | 3631 | 3633 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 4/8/25 | 4/14/25 | NA | 1
11916 | Review presentation materials and incorporate feedback | April 15, 2025 8:00 AM | April 21, 2025 5:00 PM | 3632 | 3635FS+7d | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 4/15/25 | 4/21/25 | NA | 1
11917 | Prepare for June 2025 Org Readiness Meetings | May 1, 2025 8:00 AM | May 21, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 5/1/25 | 5/21/25 | NA | 1
11918 | Collaborate with OCM and Trainings teams to develop agenda for June Org Readiness Meetings | May 1, 2025 8:00 AM | May 7, 2025 5:00 PM | 3633FS+7d | 3636 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 5/1/25 | 5/7/25 | NA | 1
11919 | Create presentation materials | May 8, 2025 8:00 AM | May 14, 2025 5:00 PM | 3635 | 3637 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 5/8/25 | 5/14/25 | NA | 1
11920 | Review presentation materials and incorporate feedback | May 15, 2025 8:00 AM | May 21, 2025 5:00 PM | 3636 | 3639FS+6d | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 5/15/25 | 5/21/25 | NA | 1
11921 | Prepare for July 2025 Org Readiness Meetings | June 2, 2025 8:00 AM | June 20, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 6/2/25 | 6/20/25 | NA | 1
11922 | Collaborate with OCM and Trainings teams to develop agenda for July Org Readiness Meetings | June 2, 2025 8:00 AM | June 6, 2025 5:00 PM | 3637FS+6d | 3640 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 6/2/25 | 6/6/25 | NA | 1
11923 | Create presentation materials | June 9, 2025 8:00 AM | June 13, 2025 5:00 PM | 3639 | 3641 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 6/9/25 | 6/13/25 | NA | 1
11924 | Review presentation materials and incorporate feedback | June 16, 2025 8:00 AM | June 20, 2025 5:00 PM | 3640 | 3643FS+6d | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 6/16/25 | 6/20/25 | NA | 1
11925 | Prepare for August 2025 Org Readiness Meetings | July 1, 2025 8:00 AM | July 22, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 7/1/25 | 7/22/25 | NA | 1
11926 | Collaborate with OCM and Trainings teams to develop agenda for August Org Readiness Meetings | July 1, 2025 8:00 AM | July 8, 2025 5:00 PM | 3641FS+6d | 3644 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 7/1/25 | 7/8/25 | NA | 1
11927 | Create presentation materials | July 9, 2025 8:00 AM | July 15, 2025 5:00 PM | 3643 | 3645 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 7/9/25 | 7/15/25 | NA | 1
11928 | Review presentation materials and incorporate feedback | July 16, 2025 8:00 AM | July 22, 2025 5:00 PM | 3644 | 3647FS+7d | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 7/16/25 | 7/22/25 | NA | 1
11929 | Prepare for September 2025 Org Readiness Meetings | August 1, 2025 8:00 AM | August 21, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 8/1/25 | 8/21/25 | NA | 1
11930 | Collaborate with OCM and Trainings teams to develop agenda for September Org Readiness Meetings | August 1, 2025 8:00 AM | August 7, 2025 5:00 PM | 3645FS+7d | 3648 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 8/1/25 | 8/7/25 | NA | 1
11931 | Create presentation materials | August 8, 2025 8:00 AM | August 14, 2025 5:00 PM | 3647 | 3649 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 8/8/25 | 8/14/25 | NA | 1
11932 | Review presentation materials and incorporate feedback | August 15, 2025 8:00 AM | August 21, 2025 5:00 PM | 3648 | 3651FS+6d | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 8/15/25 | 8/21/25 | NA | 1
11933 | Prepare for October 2025 Org Readiness Meetings | September 2, 2025 8:00 AM | September 22, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 9/2/25 | 9/22/25 | NA | 1
11934 | Collaborate with OCM and Trainings teams to develop agenda for October Org Readiness Meetings | September 2, 2025 8:00 AM | September 8, 2025 5:00 PM | 3649FS+6d | 3652 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 9/2/25 | 9/8/25 | NA | 1
11935 | Create presentation materials | September 9, 2025 8:00 AM | September 15, 2025 5:00 PM | 3651 | 3653 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 9/9/25 | 9/15/25 | NA | 1
11936 | Review presentation materials and incorporate feedback | September 16, 2025 8:00 AM | September 22, 2025 5:00 PM | 3652 | 3655FS+6d | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 9/16/25 | 9/22/25 | NA | 1
11937 | Prepare for November 2025 Org Readiness Meetings | October 1, 2025 8:00 AM | October 21, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 8d | NA | NA | 15 days | No | 10/1/25 | NA | NA | 0.53000000000000003
11938 | Collaborate with OCM and Trainings teams to develop agenda for November Org Readiness Meetings | October 1, 2025 8:00 AM | October 7, 2025 5:00 PM | 3653FS+6d | 3656 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 10/1/25 | 10/7/25 | NA | 1
11939 | Create presentation materials | October 8, 2025 8:00 AM | October 14, 2025 5:00 PM | 3655 | 3657 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | 10/8/25 | NA | NA | 0.59999999999999998
11940 | Review presentation materials and incorporate feedback | October 15, 2025 8:00 AM | October 21, 2025 5:00 PM | 3656 | 3659FS+8d | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11941 | Prepare for December 2025 Org Readiness Meetings | November 3, 2025 8:00 AM | November 24, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 8d | NA | NA | 15 days | No | NA | NA | NA | 0
11942 | Collaborate with OCM and Trainings teams to develop agenda for December Org Readiness Meetings | November 3, 2025 8:00 AM | November 7, 2025 5:00 PM | 3657FS+8d | 3660 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11943 | Create presentation materials | November 10, 2025 8:00 AM | November 17, 2025 5:00 PM | 3659 | 3661 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11944 | Review presentation materials and incorporate feedback | November 18, 2025 8:00 AM | November 24, 2025 5:00 PM | 3660 | 3663FS+3d | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11945 | Prepare for January 2026 Org Readiness Meetings | December 1, 2025 8:00 AM | December 19, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 8d | NA | NA | 15 days | No | NA | NA | NA | 0
11946 | Collaborate with OCM and Trainings teams to develop agenda for January Org Readiness Meetings | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 3661FS+3d | 3664 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11947 | Create presentation materials | December 8, 2025 8:00 AM | December 12, 2025 5:00 PM | 3663 | 3665 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11948 | Review presentation materials and incorporate feedback | December 15, 2025 8:00 AM | December 19, 2025 5:00 PM | 3664 | 3667FS+7d | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11949 | Prepare for February 2026 Org Readiness Meetings | January 2, 2026 8:00 AM | January 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 15 | 8d | NA | NA | 15 days | No | NA | NA | NA | 0
11950 | Collaborate with OCM and Trainings teams to develop agenda for February Org Readiness Meetings | January 2, 2026 8:00 AM | January 8, 2026 5:00 PM | 3665FS+7d | 3668 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11951 | Create presentation materials | January 9, 2026 8:00 AM | January 15, 2026 5:00 PM | 3667 | 3669 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11952 | Review presentation materials and incorporate feedback | January 16, 2026 8:00 AM | January 23, 2026 5:00 PM | 3668 | 3671FS+5d | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11953 | Prepare for March 2026 Org Readiness Meetings | February 2, 2026 8:00 AM | February 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 15 | 8d | NA | NA | 15 days | No | NA | NA | NA | 0
11954 | Collaborate with OCM and Trainings teams to develop agenda for March Org Readiness Meetings | February 2, 2026 8:00 AM | February 6, 2026 5:00 PM | 3669FS+5d | 3672 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11955 | Create presentation materials | February 9, 2026 8:00 AM | February 13, 2026 5:00 PM | 3671 | 3673 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11956 | Review presentation materials and incorporate feedback | February 17, 2026 8:00 AM | February 23, 2026 5:00 PM | 3672 | 3675FS+4d | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11957 | Prepare for April 2026 Org Readiness Meetings | March 2, 2026 8:00 AM | March 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 15 | 8d | NA | NA | 15 days | No | NA | NA | NA | 0
11958 | Collaborate with OCM and Trainings teams to develop agenda for April Org Readiness Meetings | March 2, 2026 8:00 AM | March 6, 2026 5:00 PM | 3673FS+4d | 3676 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11959 | Create presentation materials | March 9, 2026 8:00 AM | March 13, 2026 5:00 PM | 3675 | 3677 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11960 | Review presentation materials and incorporate feedback | March 16, 2026 8:00 AM | March 20, 2026 5:00 PM | 3676 | 3679FS+7d | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11961 | Prepare for May 2026 Org Readiness Meetings | April 2, 2026 8:00 AM | April 22, 2026 5:00 PM |  |  | As Soon As Possible | NA | 15 | 8d | NA | NA | 15 days | No | NA | NA | NA | 0
11962 | Collaborate with OCM and Trainings teams to develop agenda for May Org Readiness Meetings | April 2, 2026 8:00 AM | April 8, 2026 5:00 PM | 3677FS+7d | 3680 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11963 | Create presentation materials | April 9, 2026 8:00 AM | April 15, 2026 5:00 PM | 3679 | 3681 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11964 | Review presentation materials and incorporate feedback | April 16, 2026 8:00 AM | April 22, 2026 5:00 PM | 3680 | 3683FS+6d | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11965 | Prepare for June 2026 Org Readiness Meetings | May 1, 2026 8:00 AM | May 21, 2026 5:00 PM |  |  | As Soon As Possible | NA | 15 | 8d | NA | NA | 15 days | No | NA | NA | NA | 0
11966 | Collaborate with OCM and Trainings teams to develop agenda for June Org Readiness Meetings | May 1, 2026 8:00 AM | May 7, 2026 5:00 PM | 3681FS+6d | 3684 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11967 | Create presentation materials | May 8, 2026 8:00 AM | May 14, 2026 5:00 PM | 3683 | 3685 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11968 | Review presentation materials and incorporate feedback | May 15, 2026 8:00 AM | May 21, 2026 5:00 PM | 3684 | 3687FS+5d | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11969 | Prepare for July 2026 Org Readiness Meetings | June 1, 2026 8:00 AM | June 19, 2026 5:00 PM |  |  | As Soon As Possible | NA | 15 | 8d | NA | NA | 15 days | No | NA | NA | NA | 0
11970 | Collaborate with OCM and Trainings teams to develop agenda for July Org Readiness Meetings | June 1, 2026 8:00 AM | June 5, 2026 5:00 PM | 3685FS+5d | 3688 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11971 | Create presentation materials | June 8, 2026 8:00 AM | June 12, 2026 5:00 PM | 3687 | 3689 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11972 | Review presentation materials and incorporate feedback | June 15, 2026 8:00 AM | June 19, 2026 5:00 PM | 3688 | 3691FS+7d | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11973 | Prepare for August 2026 Org Readiness Meetings | July 1, 2026 8:00 AM | July 22, 2026 5:00 PM |  |  | As Soon As Possible | NA | 15 | 8d | NA | NA | 15 days | No | NA | NA | NA | 0
11974 | Collaborate with OCM and Trainings teams to develop agenda for August Org Readiness Meetings | July 1, 2026 8:00 AM | July 8, 2026 5:00 PM | 3689FS+7d | 3692 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11975 | Create presentation materials | July 9, 2026 8:00 AM | July 15, 2026 5:00 PM | 3691 | 3693 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11976 | Review presentation materials and incorporate feedback | July 16, 2026 8:00 AM | July 22, 2026 5:00 PM | 3692 | 3695FS+7d | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11977 | Prepare for September 2026 Org Readiness Meetings | August 3, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | As Soon As Possible | NA | 15 | 8d | NA | NA | 15 days | No | NA | NA | NA | 0
11978 | Collaborate with OCM and Trainings teams to develop agenda for September Org Readiness Meetings | August 3, 2026 8:00 AM | August 7, 2026 5:00 PM | 3693FS+7d | 3696 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11979 | Create presentation materials | August 10, 2026 8:00 AM | August 14, 2026 5:00 PM | 3695 | 3697 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11980 | Review presentation materials and incorporate feedback | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM | 3696 | 3699FS+6d | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11981 | Prepare for October 2026 Org Readiness Meetings | September 1, 2026 8:00 AM | September 22, 2026 5:00 PM |  |  | As Soon As Possible | NA | 15 | 8d | NA | NA | 15 days | No | NA | NA | NA | 0
11982 | Collaborate with OCM and Trainings teams to develop agenda for October Org Readiness Meetings | September 1, 2026 8:00 AM | September 8, 2026 5:00 PM | 3697FS+6d | 3700 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11983 | Create presentation materials | September 9, 2026 8:00 AM | September 15, 2026 5:00 PM | 3699 | 3701 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
11984 | Review presentation materials and incorporate feedback | September 16, 2026 8:00 AM | September 22, 2026 5:00 PM | 3700 | 3886 | As Soon As Possible | NA | 5 | 8d | NA | NA | 5 days | No | NA | NA | NA | 0
8266 | Conduct Org Readiness Meetings | January 2, 2024 8:00 AM | January 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 518 | 175d | January 2, 2024 8:00 AM | January 22, 2025 5:00 PM | 266 days | No | 1/2/24 | NA | NA | 0.87
8267 | Conduct January 2024 Org Readiness Meetings | January 2, 2024 8:00 AM | February 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | January 2, 2024 8:00 AM | February 1, 2024 5:00 PM | 22 days | No | 1/2/24 | 2/1/24 | NA | 1
8270 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | January 2, 2024 8:00 AM | January 31, 2024 5:00 PM | 3569FS+9d | 3705,3707,3711 | As Soon As Possible | NA | 21 | 0d | January 2, 2024 8:00 AM | January 31, 2024 5:00 PM | 21 days | No | 1/2/24 | 1/31/24 | NA | 1
8271 | Upload Go-Live Readiness checklist data into ChangeScout | February 1, 2024 8:00 AM | February 1, 2024 5:00 PM | 3704 | 3707 | As Soon As Possible | NA | 1 | 0d | February 1, 2024 8:00 AM | February 1, 2024 5:00 PM | 1 | No | 2/1/24 | 2/1/24 | NA | 1
8272 | Generate January 2024 Org Readiness Report | February 2, 2024 8:00 AM | February 16, 2024 5:00 PM |  |  | As Soon As Possible | NA | 11 | 0d | February 2, 2024 8:00 AM | February 16, 2024 5:00 PM | 11 days | No | 2/2/24 | 2/16/24 | NA | 1
8273 | Generate report from ChangeScout highlighting Org engagement for the month and status of readiness checklist activities | February 2, 2024 8:00 AM | February 8, 2024 5:00 PM | 3704,3705 | 3708 | As Soon As Possible | NA | 5 | 0d | February 2, 2024 8:00 AM | February 8, 2024 5:00 PM | 5 days | No | 2/2/24 | 2/8/24 | NA | 1
8274 | Review January Org Readiness Report with State Implementation Lead | February 9, 2024 8:00 AM | February 15, 2024 5:00 PM | 3707 | 3709 | As Soon As Possible | NA | 5 | 0d | February 9, 2024 8:00 AM | February 15, 2024 5:00 PM | 5 days | No | 2/9/24 | 2/15/24 | NA | 1
8275 | Review January Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | February 16, 2024 8:00 AM | February 16, 2024 5:00 PM | 3708 | 3716 | As Soon As Possible | NA | 1 | 0d | February 16, 2024 8:00 AM | February 16, 2024 5:00 PM | 1 | No | 2/16/24 | 2/16/24 | NA | 1
8287 | Conduct February 2024 Org Readiness Meetings | February 1, 2024 8:00 AM | March 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | February 1, 2024 8:00 AM | March 1, 2024 5:00 PM | 21 days | No | 2/1/24 | 3/1/24 | NA | 1
8290 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM | 3704 | 3712,3714,3718 | As Soon As Possible | NA | 20 | 0d | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM | 20 days | No | 2/1/24 | 2/29/24 | NA | 1
8291 | Conduct February 2024 Org Readiness Meetings: Upload Go-Live Readiness checklist data into ChangeScout | March 1, 2024 8:00 AM | March 1, 2024 5:00 PM | 3711 | 3714 | As Soon As Possible | NA | 1 | 0d | March 1, 2024 8:00 AM | March 1, 2024 5:00 PM | 1 | No | 3/1/24 | 3/1/24 | NA | 1
8292 | Generate February 2024 Org Readiness Report | March 4, 2024 8:00 AM | March 22, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | March 4, 2024 8:00 AM | March 22, 2024 5:00 PM | 15 days | No | 3/4/24 | 3/22/24 | NA | 1
8293 | Generate report from ChangeScout highlighting Org engagement for the month and status of readiness checklist activities | March 4, 2024 8:00 AM | March 8, 2024 5:00 PM | 3711,3712 | 3715 | As Soon As Possible | NA | 5 | 0d | March 4, 2024 8:00 AM | March 8, 2024 5:00 PM | 5 days | No | 3/4/24 | 3/8/24 | NA | 1
8294 | Review February Org Readiness Report with State Implementation Lead | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 3714 | 3716 | As Soon As Possible | NA | 5 | 0d | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 5 days | No | 3/11/24 | 3/15/24 | NA | 1
8295 | Review February Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | March 18, 2024 8:00 AM | March 22, 2024 5:00 PM | 3715,3709 | 3723 | As Soon As Possible | NA | 5 | 0d | March 18, 2024 8:00 AM | March 22, 2024 5:00 PM | 5 days | No | 3/18/24 | 3/22/24 | NA | 1
8296 | Conduct March 2024 Org Readiness Meetings | March 1, 2024 8:00 AM | April 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | March 1, 2024 8:00 AM | April 2, 2024 5:00 PM | 22 days | No | 3/1/24 | 4/2/24 | NA | 1
8297 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM | 3711 | 3719,3721,3725 | As Soon As Possible | NA | 21 | 0d | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM | 21 days | No | 3/1/24 | 3/29/24 | NA | 1
8298 | Upload Go-Live Readiness checklist data into ChangeScout | April 2, 2024 8:00 AM | April 2, 2024 5:00 PM | 3718 | 3721 | As Soon As Possible | NA | 1 | 0d | April 2, 2024 8:00 AM | April 2, 2024 5:00 PM | 1 | No | 4/2/24 | 4/2/24 | NA | 1
8299 | Generate March 2024 Org Readiness Report | April 3, 2024 8:00 AM | April 11, 2024 5:00 PM |  |  | As Soon As Possible | NA | 7 | 0d | April 3, 2024 8:00 AM | April 11, 2024 5:00 PM | 7 days | No | 4/3/24 | 4/11/24 | NA | 1
8300 | Generate report from ChangeScout highlighting Org engagement for the month and status of readiness checklist activities | April 3, 2024 8:00 AM | April 9, 2024 5:00 PM | 3718,3719 | 3722 | As Soon As Possible | NA | 5 | 0d | April 3, 2024 8:00 AM | April 9, 2024 5:00 PM | 5 days | No | 4/3/24 | 4/9/24 | NA | 1
8301 | Review March Org Readiness Report with State Implementation Lead | April 10, 2024 8:00 AM | April 10, 2024 5:00 PM | 3721 | 3723 | As Soon As Possible | NA | 1 | 0d | April 10, 2024 8:00 AM | April 10, 2024 5:00 PM | 1 | No | 4/10/24 | 4/10/24 | NA | 1
8302 | Review March Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | April 11, 2024 8:00 AM | April 11, 2024 5:00 PM | 3722,3716 | 3730 | As Soon As Possible | NA | 1 | 0d | April 11, 2024 8:00 AM | April 11, 2024 5:00 PM | 1 | No | 4/11/24 | 4/11/24 | NA | 1
8303 | Conduct April 2024 Org Readiness Meetings | April 2, 2024 8:00 AM | May 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | April 2, 2024 8:00 AM | May 1, 2024 5:00 PM | 22 days | No | 4/2/24 | 5/1/24 | NA | 1
8304 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | April 2, 2024 8:00 AM | April 30, 2024 5:00 PM | 3718 | 3726,3728,3732 | As Soon As Possible | NA | 21 | 0d | April 2, 2024 8:00 AM | April 30, 2024 5:00 PM | 21 days | No | 4/2/24 | 4/30/24 | NA | 1
8305 | Upload Go-Live Readiness checklist data into ChangeScout | May 1, 2024 8:00 AM | May 1, 2024 5:00 PM | 3725 | 3728 | As Soon As Possible | NA | 1 | 0d | May 1, 2024 8:00 AM | May 1, 2024 5:00 PM | 1 | No | 5/1/24 | 5/1/24 | NA | 1
8306 | Generate April 2024 Org Readiness Report | May 2, 2024 8:00 AM | May 17, 2024 5:00 PM |  |  | As Soon As Possible | NA | 12 | 0d | May 2, 2024 8:00 AM | May 17, 2024 5:00 PM | 12 days | No | 5/2/24 | 5/17/24 | NA | 1
8307 | Generate report from ChangeScout highlighting Org engagement for the month and status of readiness checklist activities | May 2, 2024 8:00 AM | May 8, 2024 5:00 PM | 3725,3726 | 3729 | As Soon As Possible | NA | 5 | 0d | May 2, 2024 8:00 AM | May 8, 2024 5:00 PM | 5 days | No | 5/2/24 | 5/8/24 | NA | 1
8308 | Review April Org Readiness Report with State Implementation Lead | May 9, 2024 8:00 AM | May 15, 2024 5:00 PM | 3728 | 3730 | As Soon As Possible | NA | 5 | 0d | May 9, 2024 8:00 AM | May 15, 2024 5:00 PM | 5 days | No | 5/9/24 | 5/15/24 | NA | 1
8309 | Review April Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | May 16, 2024 8:00 AM | May 17, 2024 5:00 PM | 3729,3723 | 3737 | As Soon As Possible | NA | 2 | 0d | May 16, 2024 8:00 AM | May 17, 2024 5:00 PM | 2 days | No | 5/16/24 | 5/17/24 | NA | 1
8310 | Conduct May 2024 Org Readiness Meetings | May 1, 2024 8:00 AM | June 3, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | May 1, 2024 8:00 AM | June 3, 2024 5:00 PM | 23 days | No | 5/1/24 | 6/3/24 | NA | 1
8311 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM | 3725 | 3733,3735,3739 | As Soon As Possible | NA | 22 | 0d | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM | 22 days | No | 5/1/24 | 5/31/24 | NA | 1
8312 | Upload Go-Live Readiness checklist data into ChangeScout | June 3, 2024 8:00 AM | June 3, 2024 5:00 PM | 3732 | 3735 | As Soon As Possible | NA | 1 | 0d | June 3, 2024 8:00 AM | June 3, 2024 5:00 PM | 1 | No | 6/3/24 | 6/3/24 | NA | 1
8313 | Generate May 2024 Org Readiness Report | June 4, 2024 8:00 AM | June 21, 2024 5:00 PM |  |  | As Soon As Possible | NA | 14 | 0d | June 4, 2024 8:00 AM | June 21, 2024 5:00 PM | 14 days | No | 6/4/24 | 6/21/24 | NA | 1
8314 | Generate report from ChangeScout highlighting Org engagement for the month and status of readiness checklist activities | June 4, 2024 8:00 AM | June 10, 2024 5:00 PM | 3732,3733 | 3736 | As Soon As Possible | NA | 5 | 0d | June 4, 2024 8:00 AM | June 10, 2024 5:00 PM | 5 days | No | 6/4/24 | 6/10/24 | NA | 1
8315 | Review May Org Readiness Report with State Implementation Lead | June 11, 2024 8:00 AM | June 17, 2024 5:00 PM | 3735 | 3737 | As Soon As Possible | NA | 5 | 0d | June 11, 2024 8:00 AM | June 17, 2024 5:00 PM | 5 days | No | 6/11/24 | 6/17/24 | NA | 1
8316 | Review May Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | June 18, 2024 8:00 AM | June 21, 2024 5:00 PM | 3736,3730 | 3744 | As Soon As Possible | NA | 4 | 0d | June 18, 2024 8:00 AM | June 21, 2024 5:00 PM | 4 days | No | 6/18/24 | 6/21/24 | NA | 1
8317 | Conduct June 2024 Org Readiness Meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM | 21 days | No | 6/3/24 | 7/1/24 | NA | 1
8318 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | June 3, 2024 8:00 AM | June 28, 2024 5:00 PM | 3732 | 3740,3742,3746 | As Soon As Possible | NA | 20 | 0d | June 3, 2024 8:00 AM | June 28, 2024 5:00 PM | 20 days | No | 6/3/24 | 6/28/24 | NA | 1
8319 | Upload Go-Live Readiness checklist data into ChangeScout | July 1, 2024 8:00 AM | July 1, 2024 5:00 PM | 3739 | 3742 | As Soon As Possible | NA | 1 | 0d | July 1, 2024 8:00 AM | July 1, 2024 5:00 PM | 1 | No | 7/1/24 | 7/1/24 | NA | 1
8320 | Generate June 2024 Org Readiness Report | July 2, 2024 8:00 AM | July 23, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | July 2, 2024 8:00 AM | July 23, 2024 5:00 PM | 15 days | No | 7/2/24 | 7/23/24 | NA | 1
8321 | Generate report from ChangeScout highlighting Org engagement for the month and status of readiness checklist activities | July 2, 2024 8:00 AM | July 9, 2024 5:00 PM | 3739,3740 | 3743 | As Soon As Possible | NA | 5 | 0d | July 2, 2024 8:00 AM | July 9, 2024 5:00 PM | 5 days | No | 7/2/24 | 7/9/24 | NA | 1
8322 | Review June Org Readiness Report with State Implementation Lead | July 10, 2024 8:00 AM | July 16, 2024 5:00 PM | 3742 | 3744 | As Soon As Possible | NA | 5 | 0d | July 10, 2024 8:00 AM | July 16, 2024 5:00 PM | 5 days | No | 7/10/24 | 7/16/24 | NA | 1
8323 | Review June Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | July 17, 2024 8:00 AM | July 23, 2024 5:00 PM | 3743,3737 | 3751 | As Soon As Possible | NA | 5 | 0d | July 17, 2024 8:00 AM | July 23, 2024 5:00 PM | 5 days | No | 7/17/24 | 7/23/24 | NA | 1
8324 | Conduct July 2024 Org Readiness Meetings | July 1, 2024 8:00 AM | August 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | July 1, 2024 8:00 AM | August 1, 2024 5:00 PM | 23 days | No | 7/1/24 | 8/1/24 | NA | 1
8327 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM | 3739 | 3747,3749,3753 | As Soon As Possible | NA | 22 | 0d | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM | 22 days | No | 7/1/24 | 7/31/24 | NA | 1
8328 | Upload Go-Live Readiness checklist data into ChangeScout | August 1, 2024 8:00 AM | August 1, 2024 5:00 PM | 3746 | 3750 | As Soon As Possible | NA | 1 | 0d | August 1, 2024 8:00 AM | August 1, 2024 5:00 PM | 1 | No | 8/1/24 | 8/1/24 | NA | 1
8329 | Generate July 2024 Org Readiness Report | August 1, 2024 8:00 AM | August 21, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | September 3, 2024 8:00 AM | September 23, 2024 5:00 PM | 15 days | No | 8/1/24 | 8/21/24 | NA | 1
8330 | Generate report from ChangeScout highlighting Org engagement for the month and status of readiness checklist activities | August 1, 2024 8:00 AM | August 7, 2024 5:00 PM | 3746 | 3750 | As Soon As Possible | NA | 5 | 0d | September 3, 2024 8:00 AM | September 9, 2024 5:00 PM | 5 days | No | 8/1/24 | 8/7/24 | NA | 1
8331 | Review July Org Readiness Report with State Implementation Lead | August 8, 2024 8:00 AM | August 14, 2024 5:00 PM | 3749,3747 | 3751 | As Soon As Possible | NA | 5 | 0d | September 10, 2024 8:00 AM | September 16, 2024 5:00 PM | 5 days | No | 8/8/24 | 8/14/24 | NA | 1
8332 | Review July Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | August 15, 2024 8:00 AM | August 21, 2024 5:00 PM | 3750,3744 | 3758FS-6d | As Soon As Possible | NA | 5 | 0d | September 17, 2024 8:00 AM | September 23, 2024 5:00 PM | 5 days | No | 8/15/24 | 8/21/24 | NA | 1
8333 | Conduct August 2024 Org Readiness Meetings | August 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | August 1, 2024 8:00 AM | September 2, 2024 5:00 PM | 23 days | No | 8/1/24 | 9/2/24 | NA | 1
8336 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 3746 | 3754,3756,3760 | As Soon As Possible | NA | 22 | 0d | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 22 days | No | 8/1/24 | 8/30/24 | NA | 1
8337 | Upload Go-Live Readiness checklist data into ChangeScout | September 2, 2024 8:00 AM | September 2, 2024 5:00 PM | 3753 | 3757 | As Soon As Possible | NA | 1 | 0d | September 2, 2024 8:00 AM | September 2, 2024 5:00 PM | 1 | No | 9/2/24 | 9/2/24 | NA | 1
8338 | Generate August 2024 Org Readiness Report | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM | 21 days | No | 9/2/24 | 9/30/24 | NA | 1
8339 | Generate report from ChangeScout highlighting Org engagement for the month and status of readiness checklist activities | September 2, 2024 8:00 AM | September 6, 2024 5:00 PM | 3753 | 3757 | As Soon As Possible | NA | 5 | 0d | September 2, 2024 8:00 AM | September 6, 2024 5:00 PM | 5 days | No | 9/2/24 | 9/6/24 | NA | 1
8340 | Review August Org Readiness Report with State Implementation Lead | September 9, 2024 8:00 AM | September 13, 2024 5:00 PM | 3756,3754 | 3758 | As Soon As Possible | NA | 5 | 0d | September 9, 2024 8:00 AM | September 13, 2024 5:00 PM | 5 days | No | 9/9/24 | 9/13/24 | NA | 1
8341 | Review August Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | September 24, 2024 8:00 AM | September 30, 2024 5:00 PM | 3757,3751FS-6d | 3765 | Start No Earlier Than | 9/24/24 | 5 | 0d | September 24, 2024 8:00 AM | September 30, 2024 5:00 PM | 5 days | No | 9/24/24 | 9/30/24 | NA | 1
8342 | Conduct September 2024 Org Readiness Meetings | September 2, 2024 8:00 AM | October 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM | 21 days | No | 9/2/24 | 10/1/24 | NA | 1
8343 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM | 3753 | 3761,3763,3767 | As Soon As Possible | NA | 21 | 0d | September 2, 2024 8:00 AM | September 27, 2024 5:00 PM | 20 days | No | 9/2/24 | 9/30/24 | NA | 1
8344 | Upload Go-Live Readiness checklist data into ChangeScout | October 1, 2024 8:00 AM | October 1, 2024 5:00 PM | 3760 | 3768 | As Soon As Possible | NA | 1 | 0d | September 30, 2024 8:00 AM | September 30, 2024 5:00 PM | 1 | No | 10/1/24 | 10/1/24 | NA | 1
8345 | Generate September 2024 Org Readiness Report | October 1, 2024 8:00 AM | October 21, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | September 30, 2024 8:00 AM | October 18, 2024 5:00 PM | 15 days | No | 10/1/24 | 10/21/24 | NA | 1
8346 | Generate report from ChangeScout highlighting Org engagement for the month and status of readiness checklist activities | October 1, 2024 8:00 AM | October 7, 2024 5:00 PM | 3760 | 3764 | As Soon As Possible | NA | 5 | 0d | September 30, 2024 8:00 AM | October 4, 2024 5:00 PM | 5 days | No | 10/1/24 | 10/7/24 | NA | 1
8347 | Review September Org Readiness Report with State Implementation Lead | October 8, 2024 8:00 AM | October 14, 2024 5:00 PM | 3763 | 3765 | As Soon As Possible | NA | 5 | 0d | October 7, 2024 8:00 AM | October 11, 2024 5:00 PM | 5 days | No | 10/8/24 | 10/14/24 | NA | 1
8348 | Review September Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | October 15, 2024 8:00 AM | October 21, 2024 5:00 PM | 3764,3758 | 3772 | As Soon As Possible | NA | 5 | 0d | October 14, 2024 8:00 AM | October 18, 2024 5:00 PM | 5 days | No | 10/15/24 | 10/21/24 | NA | 1
8349 | Conduct October 2024 Org Readiness Meetings | October 1, 2024 8:00 AM | November 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 24 | 0d | September 30, 2024 8:00 AM | October 31, 2024 5:00 PM | 24 days | No | 10/1/24 | 11/1/24 | NA | 1
8352 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM | 3760 | 3768,3770,3774 | As Soon As Possible | NA | 23 | 0d | September 30, 2024 8:00 AM | October 30, 2024 5:00 PM | 23 days | No | 10/1/24 | 10/31/24 | NA | 1
8353 | Upload Go-Live Readiness checklist data into ChangeScout | November 1, 2024 8:00 AM | November 1, 2024 5:00 PM | 3767,3761 | 3775 | As Soon As Possible | NA | 1 | 0d | October 31, 2024 8:00 AM | October 31, 2024 5:00 PM | 1 | No | 11/1/24 | 11/1/24 | NA | 1
8354 | Generate October 2024 Org Readiness Report | November 1, 2024 8:00 AM | November 22, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | October 31, 2024 8:00 AM | November 21, 2024 5:00 PM | 15 days | No | 11/1/24 | 11/22/24 | NA | 1
8355 | Generate report from ChangeScout highlighting Org engagement for the month and status of readiness checklist activities | November 1, 2024 8:00 AM | November 7, 2024 5:00 PM | 3767 | 3771 | As Soon As Possible | NA | 5 | 0d | October 31, 2024 8:00 AM | November 6, 2024 5:00 PM | 5 days | No | 11/1/24 | 11/7/24 | NA | 1
8356 | Review October Org Readiness Report with State Implementation Lead | November 8, 2024 8:00 AM | November 15, 2024 5:00 PM | 3770 | 3772 | As Soon As Possible | NA | 5 | 0d | November 7, 2024 8:00 AM | November 14, 2024 5:00 PM | 5 days | No | 11/8/24 | 11/15/24 | NA | 1
8357 | Review October Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | November 18, 2024 8:00 AM | November 22, 2024 5:00 PM | 3771,3765 | 3779 | As Soon As Possible | NA | 5 | 0d | November 15, 2024 8:00 AM | November 21, 2024 5:00 PM | 5 days | No | 11/18/24 | 11/22/24 | NA | 1
8358 | Conduct November 2024 Org Readiness Meetings | November 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | October 31, 2024 8:00 AM | November 27, 2024 5:00 PM | 19 days | No | 11/1/24 | 12/2/24 | NA | 1
8361 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | November 1, 2024 8:00 AM | November 27, 2024 5:00 PM | 3767 | 3775,3777,3781 | As Soon As Possible | NA | 18 | 0d | October 31, 2024 8:00 AM | November 26, 2024 5:00 PM | 18 days | No | 11/1/24 | 11/27/24 | NA | 1
8362 | Upload Go-Live Readiness checklist data into ChangeScout | December 2, 2024 8:00 AM | December 2, 2024 5:00 PM | 3774,3768 | 3782 | As Soon As Possible | NA | 1 | 0d | November 27, 2024 8:00 AM | November 27, 2024 5:00 PM | 1 | No | 12/2/24 | 12/2/24 | NA | 1
8363 | Generate November 2024 Org Readiness Report | December 2, 2024 8:00 AM | December 20, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | November 27, 2024 8:00 AM | December 19, 2024 5:00 PM | 15 days | No | 12/2/24 | 12/20/24 | NA | 1
8364 | Generate report from ChangeScout highlighting Org engagement for the month and status of readiness checklist activities | December 2, 2024 8:00 AM | December 6, 2024 5:00 PM | 3774 | 3778 | As Soon As Possible | NA | 5 | 0d | November 27, 2024 8:00 AM | December 5, 2024 5:00 PM | 5 days | No | 12/2/24 | 12/6/24 | NA | 1
8365 | Review November Org Readiness Report with State Implementation Lead | December 9, 2024 8:00 AM | December 13, 2024 5:00 PM | 3777 | 3779 | As Soon As Possible | NA | 5 | 0d | December 6, 2024 8:00 AM | December 12, 2024 5:00 PM | 5 days | No | 12/9/24 | 12/13/24 | NA | 1
8366 | Review November Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | December 16, 2024 8:00 AM | December 20, 2024 5:00 PM | 3778,3772 | 3786 | As Soon As Possible | NA | 5 | 0d | December 13, 2024 8:00 AM | December 19, 2024 5:00 PM | 5 days | No | 12/16/24 | 12/20/24 | NA | 1
8367 | Conduct December 2024 Org Readiness Meetings | December 2, 2024 8:00 AM | January 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | November 27, 2024 8:00 AM | December 31, 2024 5:00 PM | 22 days | No | 12/2/24 | 1/2/25 | NA | 1
8370 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 3774 | 3782,3784,3788 | As Soon As Possible | NA | 21 | 0d | November 27, 2024 8:00 AM | December 30, 2024 5:00 PM | 21 days | No | 12/2/24 | 12/31/24 | NA | 1
8371 | Upload Go-Live Readiness checklist data into ChangeScout | January 2, 2025 8:00 AM | January 2, 2025 5:00 PM | 3781,3775 | 3785 | As Soon As Possible | NA | 1 | 0d | December 31, 2024 8:00 AM | December 31, 2024 5:00 PM | 1 | No | 1/2/25 | 1/2/25 | NA | 1
8372 | Generate December 2024 Org Readiness Report | January 2, 2025 8:00 AM | January 23, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | December 31, 2024 8:00 AM | January 22, 2025 5:00 PM | 15 days | No | 1/2/25 | 1/23/25 | NA | 1
8373 | Generate report from ChangeScout highlighting Org engagement for the month and status of readiness checklist activities | January 2, 2025 8:00 AM | January 8, 2025 5:00 PM | 3781 | 3785 | As Soon As Possible | NA | 5 | 0d | December 31, 2024 8:00 AM | January 7, 2025 5:00 PM | 5 days | No | 1/2/25 | 1/8/25 | NA | 1
8374 | Review December Org Readiness Report with State Implementation Lead | January 9, 2025 8:00 AM | January 15, 2025 5:00 PM | 3784,3782 | 3786 | As Soon As Possible | NA | 5 | 0d | January 8, 2025 8:00 AM | January 14, 2025 5:00 PM | 5 days | No | 1/9/25 | 1/15/25 | NA | 1
8375 | Review December Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | January 16, 2025 8:00 AM | January 23, 2025 5:00 PM | 3785,3779 | 3872 | As Soon As Possible | NA | 5 | 0d | January 15, 2025 8:00 AM | January 22, 2025 5:00 PM | 5 days | No | 1/16/25 | 1/23/25 | NA | 1
11985 | Conduct January 2025 Org Readiness Meetings | January 2, 2025 8:00 AM | February 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 22 days | No | 1/2/25 | 2/3/25 | NA | 1
11986 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 3781 | 3789,3791,3795 | As Soon As Possible | NA | 21 | 0d | NA | NA | 21 days | No | 1/2/25 | 1/31/25 | NA | 1
11987 | Upload Go-Live Readiness checklist data into ChangeScout | February 3, 2025 8:00 AM | February 3, 2025 5:00 PM | 3788 | 3792 | As Soon As Possible | NA | 1 | 0d | NA | NA | 1 | No | 2/3/25 | 2/3/25 | NA | 1
11988 | Generate January 2025 Org Readiness Report | February 3, 2025 8:00 AM | February 24, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 2/3/25 | 2/24/25 | NA | 1
11989 | Generate report from ChangeScout highlighting Org engagement for the month and status of readiness checklist activities | February 3, 2025 8:00 AM | February 7, 2025 5:00 PM | 3788 | 3792 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 2/3/25 | 2/7/25 | NA | 1
11990 | Review January Org Readiness Report with State Implementation Lead | February 10, 2025 8:00 AM | February 14, 2025 5:00 PM | 3789,3791 | 3793 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 2/10/25 | 2/14/25 | NA | 1
11991 | Review January Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | February 18, 2025 8:00 AM | February 24, 2025 5:00 PM | 3792 | 3796 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 2/18/25 | 2/24/25 | NA | 1
11992 | Conduct February 2025 Org Readiness Meetings | February 3, 2025 8:00 AM | March 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 22 days | No | 2/3/25 | 3/3/25 | NA | 1
11993 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 3788 | 3796,3798,3802 | As Soon As Possible | NA | 19 | 0d | NA | NA | 21 days | No | 2/3/25 | 2/28/25 | NA | 1
11994 | Upload Go-Live Readiness checklist data into ChangeScout | March 3, 2025 8:00 AM | March 3, 2025 5:00 PM | 3793,3795 | 3799 | As Soon As Possible | NA | 1 | 0d | NA | NA | 1 | No | 3/3/25 | 3/3/25 | NA | 1
11995 | Generate February 2025 Org Readiness Report | March 3, 2025 8:00 AM | March 21, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 3/3/25 | 3/21/25 | NA | 1
11996 | Generate report from ChangeScout highlighting Org engagement for the month and status of readiness checklist activities | March 3, 2025 8:00 AM | March 7, 2025 5:00 PM | 3795 | 3799 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 3/3/25 | 3/7/25 | NA | 1
11997 | Review February Org Readiness Report with State Implementation Lead | March 10, 2025 8:00 AM | March 14, 2025 5:00 PM | 3796,3798 | 3800 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 3/10/25 | 3/14/25 | NA | 1
11998 | Review February Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | March 17, 2025 8:00 AM | March 21, 2025 5:00 PM | 3799 | 3803 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 3/17/25 | 3/21/25 | NA | 1
11999 | Conduct March 2025 Org Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 22 days | No | 3/3/25 | 4/1/25 | NA | 1
12000 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | March 3, 2025 8:00 AM | March 28, 2025 5:00 PM | 3795 | 3803,3805,3809 | As Soon As Possible | NA | 20 | 0d | NA | NA | 21 days | No | 3/3/25 | 3/28/25 | NA | 1
12001 | Verify Updated Go-Live Readiness checklist data | April 1, 2025 8:00 AM | April 1, 2025 5:00 PM | 3800,3802 | 3806 | As Soon As Possible | NA | 1 | 0d | NA | NA | 1 | No | 4/1/25 | 4/1/25 | NA | 1
12002 | Generate March 2025 Org Readiness Report | April 1, 2025 8:00 AM | April 21, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 4/1/25 | 4/21/25 | NA | 1
12003 | Generate report/dashboard highlighting Org engagement for the month and status of readiness checklist activities | April 1, 2025 8:00 AM | April 7, 2025 5:00 PM | 3802 | 3806 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 4/1/25 | 4/7/25 | NA | 1
12004 | Review March Org Readiness Report with State Implementation Lead | April 8, 2025 8:00 AM | April 14, 2025 5:00 PM | 3803,3805 | 3807 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 4/8/25 | 4/14/25 | NA | 1
12005 | Review March Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | April 15, 2025 8:00 AM | April 21, 2025 5:00 PM | 3806 | 3810 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 4/15/25 | 4/21/25 | NA | 1
12006 | Conduct April 2025 Org Readiness Meetings | April 1, 2025 8:00 AM | May 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 22 days | No | 4/1/25 | 5/1/25 | NA | 1
12007 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 3802 | 3810,3812,3816 | As Soon As Possible | NA | 22 | 0d | NA | NA | 21 days | No | 4/1/25 | 4/30/25 | NA | 1
12008 | Verify Updated Go-Live Readiness checklist data | May 1, 2025 8:00 AM | May 1, 2025 5:00 PM | 3807,3809 | 3813 | As Soon As Possible | NA | 1 | 0d | NA | NA | 1 | No | 5/1/25 | 5/1/25 | NA | 1
12009 | Generate April 2025 Org Readiness Report | May 1, 2025 8:00 AM | May 21, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 5/1/25 | 5/21/25 | NA | 1
12010 | Generate report/dashboard highlighting Org engagement for the month and status of readiness checklist activities | May 1, 2025 8:00 AM | May 7, 2025 5:00 PM | 3809 | 3813 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 5/1/25 | 5/7/25 | NA | 1
12011 | Review April Org Readiness Report with State Implementation Lead | May 8, 2025 8:00 AM | May 14, 2025 5:00 PM | 3810,3812 | 3814 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 5/8/25 | 5/14/25 | NA | 1
12012 | Review April Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | May 15, 2025 8:00 AM | May 21, 2025 5:00 PM | 3813 | 3817 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 5/15/25 | 5/21/25 | NA | 1
12013 | Conduct May 2025 Org Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 22 days | No | 5/1/25 | 6/2/25 | NA | 1
12014 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 3809 | 3817,3819,3823 | As Soon As Possible | NA | 21 | 0d | NA | NA | 21 days | No | 5/1/25 | 5/30/25 | NA | 1
12015 | Verify Updated Go-Live Readiness checklist data | June 2, 2025 8:00 AM | June 2, 2025 5:00 PM | 3814,3816 | 3820 | As Soon As Possible | NA | 1 | 0d | NA | NA | 1 | No | 6/2/25 | 6/2/25 | NA | 1
12016 | Generate May 2025 Org Readiness Report | June 2, 2025 8:00 AM | June 20, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 6/2/25 | 6/20/25 | NA | 1
12017 | Generate report/dashboard highlighting Org engagement for the month and status of readiness checklist activities | June 2, 2025 8:00 AM | June 6, 2025 5:00 PM | 3816 | 3820 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 6/2/25 | 6/6/25 | NA | 1
12018 | Review May Org Readiness Report with State Implementation Lead | June 9, 2025 8:00 AM | June 13, 2025 5:00 PM | 3817,3819 | 3821 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 6/9/25 | 6/13/25 | NA | 1
12019 | Review May Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | June 16, 2025 8:00 AM | June 20, 2025 5:00 PM | 3820 | 3824 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 6/16/25 | 6/20/25 | NA | 1
12020 | Conduct June 2025 Org Readiness Meetings | June 2, 2025 8:00 AM | July 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 22 days | No | 6/2/25 | 7/1/25 | NA | 1
12021 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 3816 | 3824,3826,3830 | As Soon As Possible | NA | 21 | 0d | NA | NA | 21 days | No | 6/2/25 | 6/30/25 | NA | 1
12022 | Verify Updated Go-Live Readiness checklist data | July 1, 2025 8:00 AM | July 1, 2025 5:00 PM | 3821,3823 | 3827 | As Soon As Possible | NA | 1 | 0d | NA | NA | 1 | No | 7/1/25 | 7/1/25 | NA | 1
12023 | Generate June 2025 Org Readiness Report | July 1, 2025 8:00 AM | July 22, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 7/1/25 | 7/22/25 | NA | 1
12024 | Generate report/dashboard highlighting Org engagement for the month and status of readiness checklist activities | July 1, 2025 8:00 AM | July 8, 2025 5:00 PM | 3823 | 3827 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 7/1/25 | 7/8/25 | NA | 1
12025 | Review June Org Readiness Report with State Implementation Lead | July 9, 2025 8:00 AM | July 15, 2025 5:00 PM | 3824,3826 | 3828 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 7/9/25 | 7/15/25 | NA | 1
12026 | Review June Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | July 16, 2025 8:00 AM | July 22, 2025 5:00 PM | 3827 | 3831 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 7/16/25 | 7/22/25 | NA | 1
12027 | Conduct July 2025 Org Readiness Meetings | July 1, 2025 8:00 AM | August 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 22 days | No | 7/1/25 | 8/1/25 | NA | 1
12028 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 3823 | 3831,3833,3837 | As Soon As Possible | NA | 22 | 0d | NA | NA | 21 days | No | 7/1/25 | 7/31/25 | NA | 1
12029 | Verify Updated Go-Live Readiness checklist data | August 1, 2025 8:00 AM | August 1, 2025 5:00 PM | 3828,3830 | 3834 | As Soon As Possible | NA | 1 | 0d | NA | NA | 1 | No | 8/1/25 | 8/1/25 | NA | 1
12030 | Generate July 2025 Org Readiness Report | August 1, 2025 8:00 AM | August 21, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 8/1/25 | 8/21/25 | NA | 1
12031 | Generate report/dashboard highlighting Org engagement for the month and status of readiness checklist activities | August 1, 2025 8:00 AM | August 7, 2025 5:00 PM | 3830 | 3834 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 8/1/25 | 8/7/25 | NA | 1
12032 | Review July Org Readiness Report with State Implementation Lead | August 8, 2025 8:00 AM | August 14, 2025 5:00 PM | 3831,3833 | 3835 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 8/8/25 | 8/14/25 | NA | 1
12033 | Review July Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | August 15, 2025 8:00 AM | August 21, 2025 5:00 PM | 3834 | 3838 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 8/15/25 | 8/21/25 | NA | 1
12034 | Conduct August 2025 Org Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 22 days | No | 8/1/25 | 9/2/25 | NA | 1
12035 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 3830 | 3838,3840,3844 | As Soon As Possible | NA | 21 | 0d | NA | NA | 21 days | No | 8/1/25 | 8/29/25 | NA | 1
12036 | Verify Updated Go-Live Readiness checklist data | September 2, 2025 8:00 AM | September 2, 2025 5:00 PM | 3835,3837 | 3841 | As Soon As Possible | NA | 1 | 0d | NA | NA | 1 | No | 9/2/25 | 9/2/25 | NA | 1
12037 | Generate August 2025 Org Readiness Report | September 2, 2025 8:00 AM | September 22, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | NA | NA | 15 days | No | 9/2/25 | 9/22/25 | NA | 1
12038 | Generate report/dashboard highlighting Org engagement for the month and status of readiness checklist activities | September 2, 2025 8:00 AM | September 8, 2025 5:00 PM | 3837 | 3841 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 9/2/25 | 9/8/25 | NA | 1
12039 | Review August Org Readiness Report with State Implementation Lead | September 9, 2025 8:00 AM | September 15, 2025 5:00 PM | 3838,3840 | 3842 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 9/9/25 | 9/15/25 | NA | 1
12040 | Review August Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | September 16, 2025 8:00 AM | September 22, 2025 5:00 PM | 3841 | 3845 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 9/16/25 | 9/22/25 | NA | 1
12041 | Conduct September 2025 Org Readiness Meetings | September 2, 2025 8:00 AM | October 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 22 days | No | 9/2/25 | 10/1/25 | NA | 1
12042 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 3837 | 3845,3847,3851 | As Soon As Possible | NA | 21 | 0d | NA | NA | 21 days | No | 9/2/25 | 9/30/25 | NA | 1
12043 | Verify Updated Go-Live Readiness checklist data | October 1, 2025 8:00 AM | October 1, 2025 5:00 PM | 3842,3844 | 3848 | As Soon As Possible | NA | 1 | 0d | NA | NA | 1 | No | 10/1/25 | 10/1/25 | NA | 1
12044 | Generate September 2025 Org Readiness Report | October 1, 2025 8:00 AM | October 21, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 205d | NA | NA | 15 days | No | 10/1/25 | NA | NA | 0.53000000000000003
12045 | Generate report/dashboard highlighting Org engagement for the month and status of readiness checklist activities | October 1, 2025 8:00 AM | October 7, 2025 5:00 PM | 3844 | 3848 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 10/1/25 | 10/7/25 | NA | 1
12046 | Review September Org Readiness Report with State Implementation Lead | October 8, 2025 8:00 AM | October 14, 2025 5:00 PM | 3845,3847 | 3849 | As Soon As Possible | NA | 5 | 205d | NA | NA | 5 days | No | 10/8/25 | NA | NA | 0.59999999999999998
12047 | Review September Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | October 15, 2025 8:00 AM | October 21, 2025 5:00 PM | 3848 | 3852 | As Soon As Possible | NA | 5 | 205d | NA | NA | 5 days | No | NA | NA | NA | 0
12048 | Conduct October 2025 Org Readiness Meetings | October 1, 2025 8:00 AM | November 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 24 | 197d | NA | NA | 22 days | No | 10/1/25 | NA | NA | 0.34000000000000002
12049 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 3844 | 3852,3854,3858 | As Soon As Possible | NA | 23 | 175d | NA | NA | 21 days | No | 10/1/25 | NA | NA | 0.34999999999999998
12050 | Verify Updated Go-Live Readiness checklist data | November 3, 2025 8:00 AM | November 3, 2025 5:00 PM | 3849,3851 | 3855 | As Soon As Possible | NA | 1 | 197d | NA | NA | 1 | No | NA | NA | NA | 0
12051 | Generate October 2025 Org Readiness Report | November 3, 2025 8:00 AM | November 24, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 193d | NA | NA | 15 days | No | NA | NA | NA | 0
12052 | Generate report/dashboard highlighting Org engagement for the month and status of readiness checklist activities | November 3, 2025 8:00 AM | November 7, 2025 5:00 PM | 3851 | 3855 | As Soon As Possible | NA | 5 | 193d | NA | NA | 5 days | No | NA | NA | NA | 0
12053 | Review October Org Readiness Report with State Implementation Lead | November 10, 2025 8:00 AM | November 17, 2025 5:00 PM | 3852,3854 | 3856 | As Soon As Possible | NA | 5 | 193d | NA | NA | 5 days | No | NA | NA | NA | 0
12054 | Review October Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | November 18, 2025 8:00 AM | November 24, 2025 5:00 PM | 3855 | 3859 | As Soon As Possible | NA | 5 | 193d | NA | NA | 5 days | No | NA | NA | NA | 0
12055 | Conduct November 2025 Org Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 175d | NA | NA | 22 days | No | NA | NA | NA | 0
12056 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 3851 | 3859,3861,3865 | As Soon As Possible | NA | 18 | 175d | NA | NA | 21 days | No | NA | NA | NA | 0
12057 | Verify Updated Go-Live Readiness checklist data | December 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 3856,3858 | 3862 | As Soon As Possible | NA | 1 | 190d | NA | NA | 1 | No | NA | NA | NA | 0
12058 | Generate November 2025 Org Readiness Report | December 1, 2025 8:00 AM | December 19, 2025 5:00 PM |  |  | As Soon As Possible | NA | 15 | 186d | NA | NA | 15 days | No | NA | NA | NA | 0
12059 | Generate report/dashboard highlighting Org engagement for the month and status of readiness checklist activities | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 3858 | 3862 | As Soon As Possible | NA | 5 | 186d | NA | NA | 5 days | No | NA | NA | NA | 0
12060 | Review November Org Readiness Report with State Implementation Lead | December 8, 2025 8:00 AM | December 12, 2025 5:00 PM | 3859,3861 | 3863 | As Soon As Possible | NA | 5 | 186d | NA | NA | 5 days | No | NA | NA | NA | 0
12061 | Review November Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | December 15, 2025 8:00 AM | December 19, 2025 5:00 PM | 3862 | 3866 | As Soon As Possible | NA | 5 | 186d | NA | NA | 5 days | No | NA | NA | NA | 0
12062 | Conduct December 2025 Org Readiness Meetings | December 1, 2025 8:00 AM | January 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 23 | 175d | NA | NA | 22 days | No | NA | NA | NA | 0
12063 | Update Go-Live Readiness Checklist, Document meeting notes and answer Org questions as needed | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 3858 | 3866,3868 | As Soon As Possible | NA | 22 | 175d | NA | NA | 21 days | No | NA | NA | NA | 0
12064 | Verify Updated Go-Live Readiness checklist data | January 2, 2026 8:00 AM | January 2, 2026 5:00 PM | 3863,3865 | 3869 | As Soon As Possible | NA | 1 | 179d | NA | NA | 1 | No | NA | NA | NA | 0
12065 | Generate December 2025 Org Readiness Report | January 2, 2026 8:00 AM | January 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 15 | 175d | NA | NA | 15 days | No | NA | NA | NA | 0
12066 | Generate report/dashboard highlighting Org engagement for the month and status of readiness checklist activities | January 2, 2026 8:00 AM | January 8, 2026 5:00 PM | 3865 | 3869 | As Soon As Possible | NA | 5 | 175d | NA | NA | 5 days | No | NA | NA | NA | 0
12067 | Review December Org Readiness Report with State Implementation Lead | January 9, 2026 8:00 AM | January 15, 2026 5:00 PM | 3866,3868 | 3870 | As Soon As Possible | NA | 5 | 175d | NA | NA | 5 days | No | NA | NA | NA | 0
12068 | Review December Org Readiness Report with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | January 16, 2026 8:00 AM | January 23, 2026 5:00 PM | 3869 | 3886 | As Soon As Possible | NA | 5 | 175d | NA | NA | 5 days | No | NA | NA | NA | 0
8376 | Phase 2: Readiness and Cutover | October 6, 2025 8:00 AM | December 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 300 | -50d | October 6, 2025 8:00 AM | October 23, 2026 5:00 PM | 265 days | No | 10/6/25 | NA | NA | 0.01
8377 | Begin Readiness and Cutover Phase | October 6, 2025 8:00 AM | October 6, 2025 5:00 PM | 3559FS+452d,3225,3320,3400,3457,3562,3613,3786 | 3873 | As Soon As Possible | NA | 1 | 0d | October 6, 2025 8:00 AM | October 6, 2025 5:00 PM | 1 | No | 10/6/25 | 10/6/25 | NA | 1
8378 | CARES V1 Train the Trainer | August 7, 2026 8:00 AM | September 18, 2026 5:00 PM | 5617SS,3872 | 3874 | As Soon As Possible | NA | 30 | -50d | June 18, 2026 8:00 AM | July 30, 2026 5:00 PM | 30 days | No | NA | NA | NA | 0
8379 | CARES V1 End-User Training | September 21, 2026 8:00 AM | December 16, 2026 5:00 PM | 3873 | 3886 | As Soon As Possible | NA | 60 | -50d | July 31, 2026 8:00 AM | October 23, 2026 5:00 PM | 60 days | No | NA | NA | NA | 0
8380 | CARES V1 Pilot | October 16, 2026 8:00 AM | November 30, 2026 5:00 PM | 5626SS | 3886 | As Soon As Possible | NA | 29 | -38d | August 28, 2026 8:00 AM | October 9, 2026 5:00 PM | 30 days | No | NA | NA | NA | 0
8381 | Phase 3: Go-Live and Support Phase | January 9, 2025 8:00 AM | June 7, 2027 5:00 PM |  |  | As Soon As Possible | NA | 603 | 88d | September 2, 2024 8:00 AM | April 19, 2027 5:00 PM | 657 days | No | 1/9/25 | NA | NA | 0.51000000000000001
8386 | Go-Live Support Plan | January 9, 2025 8:00 AM | December 17, 2025 5:00 PM |  |  | As Soon As Possible | NA | 237 | 199d | August 29, 2025 8:00 AM | December 17, 2025 5:00 PM | 76 days | No | 1/9/25 | NA | NA | 0.81000000000000005
13070 | Identify impacted teams across the Project​ | January 9, 2025 8:00 AM | February 5, 2025 5:00 PM | 3436SS+3d | 3879SS+11d | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 1/9/25 | 2/5/25 | NA | 1
13071 | Draft DED of the Go-Live Plan with support from impacted teams​ (CDSS, PaaS, Product, Strat Comms) | January 27, 2025 8:00 AM | February 28, 2025 5:00 PM | 3878SS+11d | 3880FS+16d | As Soon As Possible | NA | 24 | 0d | NA | NA | 0 days? | No | 1/27/25 | 2/28/25 | NA | 1
13072 | Send DED to RACI Reviewers and Incorporate the Feedback | March 25, 2025 8:00 AM | April 2, 2025 5:00 PM | 3879FS+16d | 3881FS+12d,3882FS-1d | As Soon As Possible | NA | 6 | 0d | NA | NA | 0 days? | No | 3/25/25 | 4/2/25 | NA | 1
13073 | Present DED to ELT and Incorporate the Feedback | April 21, 2025 8:00 AM | April 29, 2025 5:00 PM | 3880FS+12d | 3886 | As Soon As Possible | NA | 7 | 0d | NA | NA | 0 days? | No | 4/21/25 | 4/29/25 | NA | 1
8387 | Create Go-Live Support Plan | April 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 3880FS-1d | 3883 | As Soon As Possible | NA | 150 | 199d | August 29, 2025 8:00 AM | October 31, 2025 5:00 PM | 45 days | No | 4/2/25 | NA | NA | 0.90000000000000002
13074 | Send Go-Live Support Plan to RACI Reviewers and Incorporate the Feedback | November 3, 2025 8:00 AM | November 17, 2025 5:00 PM | 3882 | 3884 | As Soon As Possible | NA | 10 | 199d | NA | NA | 0 days? | No | NA | NA | NA | 0
13075 | Present Go-Live Support Plan to ELT and Incorporate the Feedback | November 18, 2025 8:00 AM | December 5, 2025 5:00 PM | 3883 | 3885 | As Soon As Possible | NA | 13 | 199d | NA | NA | 0 days? | No | NA | NA | NA | 0
8389 | Complete Go-Live Support Plan | December 8, 2025 8:00 AM | December 17, 2025 5:00 PM | 3884 | 3886,5689FS+29d,5864FS+29d,6039FS+29d,6214FS+29d,6367FS+29d,6542FS+29d,6716FS+29d,6891FS+29d,7066FS+29d,7241FS+29d,7398FS+29d,7555FS+29d,7730FS+29d,7905FS+29d,8073FS+29d,8248FS+29d,8422FS+29d,8597FS+29d,8772FS+29d,8947FS+29d,9122FS+29d,9278FS+29d,9449F... | As Soon As Possible | NA | 8 | 199d | December 17, 2025 5:00 PM | December 17, 2025 5:00 PM | 0 days | No | NA | NA | NA | 0
8390 | CARES V1 Go-Live and Support | December 17, 2026 8:00 AM | January 15, 2027 5:00 PM | 3874,3875,5629,3885,3528,3381,3386,3429,3496,3518,3522,3544,3549,3552,3701,3870,3449,3498,3564,3881 | 3887,3889SS | As Soon As Possible | NA | 20 | -50d | October 27, 2026 8:00 AM | November 24, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
8391 | SPR 6 - Complete the CWS-CARES V1 Implementation | January 15, 2027 5:00 PM | January 15, 2027 5:00 PM | 3886 | 3893 | As Soon As Possible | NA | 0 | -50d | November 24, 2026 5:00 PM | November 24, 2026 5:00 PM | 0 days | Yes | NA | NA | 10/30/26 | 0
8392 | Knowledge Transfer Plan | December 17, 2026 8:00 AM | June 7, 2027 5:00 PM |  |  | As Soon As Possible | NA | 117 | 88d | October 27, 2026 8:00 AM | April 19, 2027 5:00 PM | 117 days | No | NA | NA | NA | 0
8393 | Create Knowledge Transfer Plan | December 17, 2026 8:00 AM | February 23, 2027 5:00 PM | 3886SS | 3890 | As Soon As Possible | NA | 45 | 88d | October 27, 2026 8:00 AM | January 4, 2027 5:00 PM | 45 days | No | NA | NA | NA | 0
8394 | Review and Incorporate Feedback to Knowledge Transfer Plan | February 24, 2027 8:00 AM | April 7, 2027 5:00 PM | 3889 | 3891 | As Soon As Possible | NA | 30 | 88d | January 5, 2027 8:00 AM | February 17, 2027 5:00 PM | 30 days | No | NA | NA | NA | 0
8395 | Complete Knowledge Transfer Plan | April 7, 2027 5:00 PM | April 7, 2027 5:00 PM | 3890 | 3892 | As Soon As Possible | NA | 0 | 88d | February 17, 2027 5:00 PM | February 17, 2027 5:00 PM | 0 days | Yes | NA | NA | NA | 0
8396 | Execute Knowledge Transfer Plan | April 8, 2027 8:00 AM | June 7, 2027 5:00 PM | 3891 | 3893 | As Soon As Possible | NA | 42 | 88d | February 18, 2027 8:00 AM | April 19, 2027 5:00 PM | 42 days | No | NA | NA | NA | 0
8397 | Complete Execution of Knowledge Transfer Plan | June 7, 2027 5:00 PM | June 7, 2027 5:00 PM | 3892,3887 |  | As Soon As Possible | NA | 0 | 88d | April 19, 2027 5:00 PM | April 19, 2027 5:00 PM | 0 days | Yes | NA | NA | NA | 0
13712 | Sandbox Activities | May 1, 2025 8:00 AM | August 14, 2026 5:00 PM |  |  | As Soon As Possible | NA | 325 | 289d | NA | NA | 0 days? | No | 5/1/25 | NA | NA | 0.38
43979 | Prepare and Support Sandbox for Cohort 1 Users (EUST 2 code) - Part I | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 3915SS | 3896 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
43980 | Prepare and Support Sandbox for Cohort 1 Users (EUST 2 code) - Part II | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 3895 | 3897 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
43981 | Prepare and Support Sandbox for Cohort 1 Users (EUST 2 code) - Part III | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 3896 | 3898FS-1d | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
43982 | Launch Sandbox for Cohort 1 Users (EUST 2 code) | July 31, 2025 8:00 AM | July 31, 2025 5:00 PM | 3897FS-1d | 3899 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 7/31/25 | 7/31/25 | NA | 1
43983 | Prepare and Support Sandbox for Cohort 1 Users (EUST 2 code) - Part IV | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 3898 | 3900 | As Soon As Possible | NA | 21 | 344d | NA | NA | 0 days? | No | NA | NA | NA | 0
43984 | Prepare and Support Sandbox for Cohort 1 Users (EUST 2 code) - Part V | September 2, 2025 8:00 AM | October 1, 2025 5:00 PM | 3899 | 3901SS | As Soon As Possible | NA | 22 | 344d | NA | NA | 0 days? | No | NA | NA | NA | 0
43985 | Prepare and Support Sandbox for Cohort 2 Users (EUST 2 code) - Part I | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 3900SS | 3902 | As Soon As Possible | NA | 21 | 344d | NA | NA | 0 days? | No | NA | NA | NA | 0
43986 | Prepare and Support Sandbox for Cohort 2 Users (EUST 2 code) - Part II | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 3901 | 3903FS-1d | As Soon As Possible | NA | 23 | 344d | NA | NA | 0 days? | No | NA | NA | NA | 0
43987 | Launch Sandbox for Cohort 2 Users (EUST 2 code) | October 31, 2025 8:00 AM | October 31, 2025 5:00 PM | 3902FS-1d | 3904 | As Soon As Possible | NA | 1 | 344d | NA | NA | 0 s? | No | NA | NA | NA | 0
43988 | Prepare and Support Sandbox for Cohort 2 Users (EUST 2 code) - Part III | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 3903 | 3905 | As Soon As Possible | NA | 18 | 344d | NA | NA | 0 days? | No | NA | NA | NA | 0
43989 | Prepare and Support Sandbox for Cohort 3 Users (EUST 2 code) - Part I | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 3904 | 3906 | As Soon As Possible | NA | 22 | 344d | NA | NA | 0 days? | No | NA | NA | NA | 0
43990 | Prepare and Support Sandbox for Cohort 3 Users (EUST 2 code) - Part II | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 3905 | 3907FS-1d | As Soon As Possible | NA | 20 | 344d | NA | NA | 0 days? | No | NA | NA | NA | 0
43991 | Launch Sandbox for Cohort 3 Users (EUST 2 code) | January 30, 2026 8:00 AM | January 30, 2026 5:00 PM | 3906FS-1d | 3908 | As Soon As Possible | NA | 1 | 344d | NA | NA | 0 s? | No | NA | NA | NA | 0
43992 | Prepare and Support Sandbox for Cohort 3 Users (EUST 2 code) - Part III | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 3907 | 3909SS | As Soon As Possible | NA | 19 | 344d | NA | NA | 0 days? | No | NA | NA | NA | 0
43993 | Prepare and Support Sandbox for Cohort 4 Users (EUST 3 code) - Part I | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 3908SS | 3910 | As Soon As Possible | NA | 19 | 344d | NA | NA | 0 days? | No | NA | NA | NA | 0
43994 | Prepare and Support Sandbox for Cohort 4 Users (EUST 3 code) - Part II | March 2, 2026 8:00 AM | March 30, 2026 5:00 PM | 3909 | 3911 | As Soon As Possible | NA | 21 | 344d | NA | NA | 0 days? | No | NA | NA | NA | 0
43971 | Prepare and Support Sandbox for Cohort 4 Users (EUST 3 code) - Part III | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 3910 | 3912FS-1d | As Soon As Possible | NA | 22 | 344d | NA | NA | 0 days? | No | NA | NA | NA | 0
43972 | Launch Sandbox for Cohort 4 Users (EUST 3 code) | April 30, 2026 8:00 AM | April 30, 2026 5:00 PM | 3911FS-1d | 3913 | As Soon As Possible | NA | 1 | 344d | NA | NA | 0 s? | No | NA | NA | NA | 0
43973 | Prepare and Support Sandbox for Cohort 4 Users (EUST 3 code) - Part IV | May 1, 2026 8:00 AM | May 28, 2026 5:00 PM | 3912 |  | As Soon As Possible | NA | 19 | 344d | NA | NA | 0 days? | No | NA | NA | NA | 0
13720 | Cohort 1 Group 1 | May 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 128 | 486d | NA | NA | 0 days? | No | 5/1/25 | NA | NA | 0.89000000000000001
13721 | Prepare and Support Sandbox for Cohort 1 Group 1 Users (EUST 2 code) | May 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  | 3895SS | Start No Earlier Than | 5/1/25 | 128 | 486d | NA | NA | 0 days? | No | 5/1/25 | NA | NA | 0.89000000000000001
13722 | Sandbox Launch for Cohort 1 Group 1 Users (EUST 2 code) | July 31, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/31/25 | 1 | 0d | NA | NA | 0 s? | No | 7/31/25 | 7/31/25 | NA | 1
13723 | Cohort 1 Group 2 | August 11, 2025 8:00 AM | September 25, 2025 5:00 PM |  |  | As Soon As Possible | NA | 33 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/25/25 | NA | 1
13724 | Draft, review, and distribute email communications to Cohort 1 Group 2 Organizations to determine Cohort 1 Group 2 Sandbox Users | August 11, 2025 8:00 AM | August 20, 2025 5:00 PM |  | 3919,3920 | Start No Earlier Than | 8/11/25 | 8 | 0d | NA | NA | 0 days? | No | 8/11/25 | 8/20/25 | NA | 1
13725 | Complete follow up with Counties on responses and object IDs | August 21, 2025 8:00 AM | September 5, 2025 5:00 PM | 3918 | 3921FS-4d | As Soon As Possible | NA | 11 | 0d | NA | NA | 0 days? | No | 8/21/25 | 9/5/25 | NA | 1
13726 | Confirm Cohort 1 Group 2 Users | August 21, 2025 8:00 AM | September 5, 2025 5:00 PM | 3918 | 3923,3922 | As Soon As Possible | NA | 11 | 0d | NA | NA | 0 days? | No | 8/21/25 | 9/5/25 | NA | 1
13727 | Send invites or email communication list for Orientation/Kickoff, User Access Support Office Hours, and Training Webinars | September 2, 2025 8:00 AM | September 5, 2025 5:00 PM | 3919FS-4d |  | As Soon As Possible | NA | 4 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/5/25 | NA | 1
13728 | Review/finalize Sandbox User Orientation for Cohort 1 Group 2 and conduct Dry Run | September 8, 2025 8:00 AM | September 12, 2025 5:00 PM | 3920 | 3924 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 9/8/25 | 9/12/25 | NA | 1
13729 | Create transactional sample data for expected data volume of Cohort 1 Group 2 users | September 8, 2025 8:00 AM | September 19, 2025 5:00 PM | 3920 |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/8/25 | 9/19/25 | NA | 1
13730 | Conduct Sandbox Orientation with Cohort 1 Group 2 | September 15, 2025 8:00 AM | September 16, 2025 5:00 PM | 3922 | 3925,3926 | As Soon As Possible | NA | 2 | 0d | NA | NA | 0 days? | No | 9/15/25 | 9/16/25 | NA | 1
13731 | Activate Cohort 1 Group 2 Users | September 17, 2025 8:00 AM | September 17, 2025 5:00 PM | 3924 | 3928,3927 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 9/17/25 | 9/17/25 | NA | 1
13732 | Conduct User Access Support Office Hours for Cohort 1 Group 2 | September 17, 2025 8:00 AM | September 22, 2025 5:00 PM | 3924 |  | As Soon As Possible | NA | 4 | 0d | NA | NA | 0 days? | No | 9/17/25 | 9/22/25 | NA | 1
13733 | Confirm user logins to Sandbox Environment prior to Sandbox Training and assign all Enablement training content in Sandbox | September 18, 2025 8:00 AM | September 22, 2025 5:00 PM | 3925 |  | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 9/18/25 | 9/22/25 | NA | 1
13734 | Complete bulk re-asssignment of transactional sample data to active users and identify list of users not receiving data | September 18, 2025 8:00 AM | September 23, 2025 5:00 PM | 3925 | 3929FS-1d | As Soon As Possible | NA | 4 | 0d | NA | NA | 0 days? | No | 9/18/25 | 9/23/25 | NA | 1
13713 | Conduct Sandbox Training Webinars for Cohort 1 Group 2 | September 23, 2025 8:00 AM | September 25, 2025 5:00 PM | 3928FS-1d |  | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 9/23/25 | 9/25/25 | NA | 1
13714 | Cohort 1 Group 3 | August 21, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 50 | 486d | NA | NA | 0 days? | No | 8/21/25 | NA | NA | 0.68999999999999995
13715 | Verify County Connection to CWS-CARES and Whitelisting for Cohort 1 Group 3. | August 21, 2025 8:00 AM | October 20, 2025 5:00 PM |  |  | Start No Earlier Than | 8/21/25 | 42 | 0d | NA | NA | 0 days? | No | 8/21/25 | 10/20/25 | NA | 1
13716 | Draft, review, and distribute email communications to Cohort 1 Group 3 Organizations to determine Cohort 1 Group 3 Sandbox Users | September 15, 2025 8:00 AM | September 19, 2025 5:00 PM |  | 3933,3934 | Start No Earlier Than | 9/15/25 | 5 | 0d | NA | NA | 0 days? | No | 9/15/25 | 9/19/25 | NA | 1
13717 | Complete follow up with Counties on responses and object IDs | September 22, 2025 8:00 AM | October 10, 2025 5:00 PM | 3932 |  | As Soon As Possible | NA | 15 | 500d | NA | NA | 0 days? | No | 9/22/25 | NA | NA | 0.90000000000000002
13735 | Confirm Cohort 1 Group 3 Users | September 22, 2025 8:00 AM | October 3, 2025 5:00 PM | 3932 | 3935,3937 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/22/25 | 10/3/25 | NA | 1
13736 | Send invites or email communication list for Orientation/Kickoff, User Access Support Office Hours, and Training Webinars | October 6, 2025 8:00 AM | October 10, 2025 5:00 PM | 3934 | 3936 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 10/6/25 | 10/10/25 | NA | 1
13737 | Review/finalize Sandbox User Orientation for Cohort 1 Group 3 and conduct Dry Run | October 13, 2025 8:00 AM | October 17, 2025 5:00 PM | 3935 | 3938 | As Soon As Possible | NA | 5 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
13738 | Create transactional sample data for expected data volume of Cohort 1 Group 3 users | October 6, 2025 8:00 AM | October 22, 2025 5:00 PM | 3934 |  | As Soon As Possible | NA | 13 | 492d | NA | NA | 0 days? | No | NA | NA | NA | 0
13744 | Conduct Sandbox Orientation with Cohort 1 Group 3 | October 20, 2025 8:00 AM | October 21, 2025 5:00 PM | 3936 | 3939,3940 | As Soon As Possible | NA | 2 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
13745 | Activate Cohort 1 Group 3 Users | October 22, 2025 8:00 AM | October 22, 2025 5:00 PM | 3938 | 3941 | As Soon As Possible | NA | 1 | 486d | NA | NA | 0 s? | No | NA | NA | NA | 0
13746 | Conduct User Access Support Office Hours for Cohort 1 Group 3 | October 22, 2025 8:00 AM | October 27, 2025 5:00 PM | 3938 |  | As Soon As Possible | NA | 4 | 489d | NA | NA | 0 days? | No | NA | NA | NA | 0
13747 | Confirm user logins to Sandbox Environment prior to Sandbox Training and assign all Enablement training content in Sandbox | October 23, 2025 8:00 AM | October 27, 2025 5:00 PM | 3939 | 3942FS-1d | As Soon As Possible | NA | 3 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
13748 | Complete bulk re-asssignment of transactional sample data to active users and identify list of users not receiving data | October 27, 2025 8:00 AM | October 28, 2025 5:00 PM | 3941FS-1d | 3943FS-1d | As Soon As Possible | NA | 2 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
13749 | Conduct Sandbox Training Webinars for Cohort 1 Group 3 | October 28, 2025 8:00 AM | October 30, 2025 5:00 PM | 3942FS-1d |  | As Soon As Possible | NA | 3 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
43893 | Update FAQ Prior to Cohort 2 Activities | September 15, 2025 8:00 AM | October 17, 2025 5:00 PM |  |  | As Soon As Possible | NA | 25 | 495d | NA | NA | 0 days? | No | 9/15/25 | NA | NA | 0.81000000000000005
43894 | Update Sandbox FAQ document ahead of Cohort 2 | September 15, 2025 8:00 AM | September 26, 2025 5:00 PM |  | 3946 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/15/25 | 9/26/25 | NA | 1
43895 | Review updated Sandbox FAQ with all impacted teams with Sandbox activities, then review with Implementation Leadership | September 29, 2025 8:00 AM | October 3, 2025 5:00 PM | 3945 | 3947FS-1d | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 9/29/25 | 10/3/25 | NA | 1
43896 | Incorporate Sandbox FAQ updates | October 3, 2025 8:00 AM | October 3, 2025 5:00 PM | 3946FS-1d | 3948 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 10/3/25 | 10/3/25 | NA | 1
43891 | Conduct ELT review of Sandbox FAQ updates | October 6, 2025 8:00 AM | October 10, 2025 5:00 PM | 3947 | 3949FS-1d | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 10/6/25 | 10/10/25 | NA | 1
43892 | Incorporate ELT feedback for Sandbox FAQ updates | October 10, 2025 8:00 AM | October 10, 2025 5:00 PM | 3948FS-1d | 3950 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 10/10/25 | 10/10/25 | NA | 1
43890 | Complete ADA review of updated Sandbox FAQ | October 13, 2025 8:00 AM | October 15, 2025 5:00 PM | 3949 | 3951 | As Soon As Possible | NA | 3 | 495d | NA | NA | 0 days? | No | NA | NA | NA | 0
43889 | Publish updated Sandbox FAQ to the Implementation Portal | October 16, 2025 8:00 AM | October 17, 2025 5:00 PM | 3950 |  | As Soon As Possible | NA | 2 | 495d | NA | NA | 0 days? | No | NA | NA | NA | 0
13742 | Cohort 2 | September 15, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 34 | 486d | NA | NA | 0 days? | No | 9/15/25 | NA | NA | 0.40000000000000002
13743 | Draft, review, and distribute email communications to Cohort 2 Organizations to determine Cohort 2 Sandbox Users | September 15, 2025 8:00 AM | September 19, 2025 5:00 PM |  | 3954 | Start No Earlier Than | 9/15/25 | 5 | 0d | NA | NA | 0 days? | No | 9/15/25 | 9/19/25 | NA | 1
13754 | Confirm Cohort 2 Users | September 22, 2025 8:00 AM | October 3, 2025 5:00 PM | 3953 | 3955,3957 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/22/25 | 10/3/25 | NA | 1
13755 | Send invites or email communication list for Orientation/Kickoff, User Access Support Office Hours, and Training Webinars | October 6, 2025 8:00 AM | October 10, 2025 5:00 PM | 3954 | 3956,3957 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 10/6/25 | 10/10/25 | NA | 1
13756 | Review/finalize Sandbox User Orientation for Cohort 2 and conduct Dry Run | October 13, 2025 8:00 AM | October 17, 2025 5:00 PM | 3955 | 3958 | As Soon As Possible | NA | 5 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
13757 | Create transactional sample data for expected data volume of Cohort 2 users | October 13, 2025 8:00 AM | October 22, 2025 5:00 PM | 3955,3954 |  | As Soon As Possible | NA | 8 | 492d | NA | NA | 0 days? | No | NA | NA | NA | 0
13758 | Conduct Sandbox Orientation with Cohort 2 | October 20, 2025 8:00 AM | October 21, 2025 5:00 PM | 3956 | 3959,3960 | As Soon As Possible | NA | 2 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
13759 | Activate Cohort 2 Users | October 22, 2025 8:00 AM | October 22, 2025 5:00 PM | 3958 | 3961,3962 | As Soon As Possible | NA | 1 | 437d | NA | NA | 0 s? | No | NA | NA | NA | 0
13760 | Conduct User Access Support Office Hours for Cohort 2 | October 22, 2025 8:00 AM | October 27, 2025 5:00 PM | 3958 |  | As Soon As Possible | NA | 4 | 489d | NA | NA | 0 days? | No | NA | NA | NA | 0
13761 | Confirm user logins to Sandbox Environment prior to Sandbox Training and assign all Enablement training content in Sandbox | October 23, 2025 8:00 AM | October 27, 2025 5:00 PM | 3959 |  | As Soon As Possible | NA | 3 | 489d | NA | NA | 0 days? | No | NA | NA | NA | 0
13718 | Complete bulk re-asssignment of transactional sample data to active users and identify list of users not receiving data | October 23, 2025 8:00 AM | October 28, 2025 5:00 PM | 3959 | 3963FS-1d | As Soon As Possible | NA | 4 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
13719 | Conduct Sandbox Training Webinars for Cohort 2 | October 28, 2025 8:00 AM | October 30, 2025 5:00 PM | 3962FS-1d | 3965FS+6d | As Soon As Possible | NA | 3 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
43899 | Conduct Retrospective for Cohort 2 | November 10, 2025 8:00 AM | December 5, 2025 5:00 PM |  |  | As Soon As Possible | NA | 18 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
43900 | Conduct retrospective about Sandbox operations, identify opportunities for continuous improvements | November 10, 2025 8:00 AM | November 19, 2025 5:00 PM | 3963FS+6d | 3966 | As Soon As Possible | NA | 7 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
43898 | Review identified opportunities for Sandbox operations improvements with ELT and incorporate agreed upon improvements into Sandbox operations | November 20, 2025 8:00 AM | December 5, 2025 5:00 PM | 3965 | 3971FS-5d | As Soon As Possible | NA | 11 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
13709 | Continued Planning for Sandbox | August 25, 2025 8:00 AM | September 12, 2025 5:00 PM |  |  | As Soon As Possible | NA | 14 | 0d | NA | NA | 0 days? | No | 8/25/25 | 9/12/25 | NA | 1
13710 | Expand Sandbox schedule tasks until October 2026, with input from PaaS SI, CDI, and State - including EUST, Tech, and PMO | August 25, 2025 8:00 AM | September 12, 2025 5:00 PM |  | 3969FS-1d | Start No Earlier Than | 8/25/25 | 14 | 0d | NA | NA | 0 days? | No | 8/25/25 | 9/12/25 | NA | 1
13711 | Present additional Sandbox Schedule Change Request (SCR) for review | September 12, 2025 8:00 AM | September 12, 2025 5:00 PM | 3968FS-1d |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 9/12/25 | 9/12/25 | NA | 1
43917 | Update FAQ Prior to Cohort 3 Activities | December 1, 2025 8:00 AM | January 13, 2026 5:00 PM |  |  | As Soon As Possible | NA | 30 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
43918 | Update Sandbox FAQ document ahead of Cohort 3 | December 1, 2025 8:00 AM | December 8, 2025 5:00 PM | 3966FS-5d | 3972 | As Soon As Possible | NA | 6 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
43919 | Review updated Sandbox FAQ with all impacted teams involved with Sandbox activities, followed by a final review with Implementation Leadership | December 9, 2025 8:00 AM | December 16, 2025 5:00 PM | 3971 | 3973 | As Soon As Possible | NA | 6 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
43920 | Incorporate Sandbox FAQ updates | December 17, 2025 8:00 AM | December 18, 2025 5:00 PM | 3972 | 3974 | As Soon As Possible | NA | 2 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
43921 | Conduct ELT review of Sandbox FAQ updates | December 19, 2025 8:00 AM | January 2, 2026 5:00 PM | 3973 | 3975 | As Soon As Possible | NA | 9 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
43922 | Incorporate ELT feedback for Sandbox FAQ updates | January 5, 2026 8:00 AM | January 6, 2026 5:00 PM | 3974 | 3976 | As Soon As Possible | NA | 2 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
43923 | Complete ADA review of updated Sandbox FAQ | January 7, 2026 8:00 AM | January 9, 2026 5:00 PM | 3975 | 3977 | As Soon As Possible | NA | 3 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
43924 | Publish updated Sandbox FAQ to the Implementation Portal | January 12, 2026 8:00 AM | January 13, 2026 5:00 PM | 3976 |  | As Soon As Possible | NA | 2 | 437d | NA | NA | 0 days? | No | NA | NA | NA | 0
43925 | Cohort 3 | November 17, 2025 8:00 AM | January 22, 2026 5:00 PM |  |  | As Soon As Possible | NA | 45 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43926 | Draft, review, and distribute email communications to Cohort 3 Organizations to determine Cohort 3 Sandbox Users | November 17, 2025 8:00 AM | November 21, 2025 5:00 PM |  | 3980 | Start No Earlier Than | 11/17/25 | 5 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43927 | Complete follow up with Counties on responses and object IDs | November 24, 2025 8:00 AM | December 19, 2025 5:00 PM | 3979 | 3981SS | As Soon As Possible | NA | 19 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43928 | Confirm Cohort 3 Users | November 24, 2025 8:00 AM | December 12, 2025 5:00 PM | 3980SS | 3982 | As Soon As Possible | NA | 14 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43929 | Send email communication with registration links for Orientation/Kickoff, User Access Support Office Hours, and Training Webinars | December 15, 2025 8:00 AM | December 19, 2025 5:00 PM | 3981 | 3983FS+8d | As Soon As Possible | NA | 5 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43930 | Review/finalize Sandbox User Orientation for Cohort 3 and conduct Dry Run | January 5, 2026 8:00 AM | January 9, 2026 5:00 PM | 3982FS+8d | 3984SS | As Soon As Possible | NA | 5 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43931 | Create Jira ticket to request setup of Cohort 3 users | January 5, 2026 8:00 AM | January 12, 2026 5:00 PM | 3983SS | 3985SS | As Soon As Possible | NA | 6 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43932 | Create transactional sample data for expected data volume of Cohort 3 users | January 5, 2026 8:00 AM | January 14, 2026 5:00 PM | 3984SS | 3986FS-3d | As Soon As Possible | NA | 8 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43933 | Conduct Sandbox Orientation with Cohort 3 | January 12, 2026 8:00 AM | January 13, 2026 5:00 PM | 3985FS-3d | 3987 | As Soon As Possible | NA | 2 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43934 | Activate Cohort 3 Users | January 14, 2026 8:00 AM | January 14, 2026 5:00 PM | 3986 | 3988FS-1d | As Soon As Possible | NA | 1 | 372d | NA | NA | 0 s? | No | NA | NA | NA | 0
43935 | Conduct User Access Support Office Hours for Cohort 3 | January 14, 2026 8:00 AM | January 20, 2026 5:00 PM | 3987FS-1d | 3989FS-2d | As Soon As Possible | NA | 4 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43936 | Confirm user logins to Sandbox Environment prior to Sandbox Training and assign all Enablement training content in Sandbox | January 16, 2026 8:00 AM | January 20, 2026 5:00 PM | 3988FS-2d | 3990FS-1d | As Soon As Possible | NA | 2 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43937 | Complete bulk re-asssignment of transactional sample data to active users and identify list of users not receiving data | January 20, 2026 8:00 AM | January 21, 2026 5:00 PM | 3989FS-1d | 3991FS-1d | As Soon As Possible | NA | 2 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43938 | Conduct Sandbox Training Webinars for Cohort 3 | January 21, 2026 8:00 AM | January 22, 2026 5:00 PM | 3990FS-1d | 3993FS+11d | As Soon As Possible | NA | 2 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43939 | Conduct Retrospective for Cohort 3 | February 9, 2026 8:00 AM | March 6, 2026 5:00 PM |  |  | As Soon As Possible | NA | 19 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43940 | Conduct retrospective about Sandbox operations, identify opportunities for continuous improvements | February 9, 2026 8:00 AM | February 19, 2026 5:00 PM | 3991FS+11d | 3994 | As Soon As Possible | NA | 8 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43941 | Review identified opportunities for Sandbox operations improvements with ELT and incorporate agreed upon improvements into Sandbox operations | February 20, 2026 8:00 AM | March 6, 2026 5:00 PM | 3993 | 3996FS+5d | As Soon As Possible | NA | 11 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43942 | Update FAQ Prior to Cohort 4 Activities | March 16, 2026 8:00 AM | April 17, 2026 5:00 PM |  |  | As Soon As Possible | NA | 24 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43943 | Update Sandbox FAQ document ahead of Cohort 4 | March 16, 2026 8:00 AM | March 20, 2026 5:00 PM | 3994FS+5d | 3997 | As Soon As Possible | NA | 5 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43944 | Review updated Sandbox FAQ with all impacted teams involved with Sandbox activities, followed by a final review with Implementation Leadership | March 23, 2026 8:00 AM | March 27, 2026 5:00 PM | 3996 | 3998 | As Soon As Possible | NA | 5 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43945 | Incorporate Sandbox FAQ updates | March 30, 2026 8:00 AM | April 1, 2026 5:00 PM | 3997 | 3999FS-1d | As Soon As Possible | NA | 2 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43946 | Conduct ELT review of Sandbox FAQ updates | April 1, 2026 8:00 AM | April 9, 2026 5:00 PM | 3998FS-1d | 4000 | As Soon As Possible | NA | 7 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43947 | Incorporate ELT feedback for Sandbox FAQ updates | April 10, 2026 8:00 AM | April 10, 2026 5:00 PM | 3999 | 4001 | As Soon As Possible | NA | 1 | 372d | NA | NA | 0 s? | No | NA | NA | NA | 0
43909 | Complete ADA review of updated Sandbox FAQ | April 13, 2026 8:00 AM | April 15, 2026 5:00 PM | 4000 | 4002 | As Soon As Possible | NA | 3 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43910 | Publish updated Sandbox FAQ to the Implementation Portal | April 16, 2026 8:00 AM | April 17, 2026 5:00 PM | 4001 |  | As Soon As Possible | NA | 2 | 372d | NA | NA | 0 days? | No | NA | NA | NA | 0
43911 | Cohort 4 | February 17, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 52 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43912 | Draft, review, and distribute email communications to Cohort 4 Organizations to determine Cohort 4 Sandbox Users | February 17, 2026 8:00 AM | February 25, 2026 5:00 PM |  | 4005 | Start No Earlier Than | 2/17/26 | 7 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43913 | Complete follow up with Counties on responses and object IDs. | February 26, 2026 8:00 AM | March 26, 2026 5:00 PM | 4004 | 4006SS | As Soon As Possible | NA | 21 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43914 | Confirm Cohort 4 Users | February 26, 2026 8:00 AM | March 19, 2026 5:00 PM | 4005SS | 4007SS+2d | As Soon As Possible | NA | 16 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43915 | Draft, review, and distribute email communications to Cohort 1-3 Organizations to provide advanced note about EUST 3 code in the V1 Readiness Environment | March 2, 2026 8:00 AM | March 11, 2026 5:00 PM | 4006SS+2d | 4008FS+7d | As Soon As Possible | NA | 8 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43948 | Send email communication with registration links for Orientation/Kickoff, User Access Support Office Hours, and Training Webinars | March 23, 2026 8:00 AM | March 27, 2026 5:00 PM | 4007FS+7d | 4009FS+9d,4012SS | As Soon As Possible | NA | 5 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43949 | Review/finalize Sandbox User Orientation for Cohort 4 and conduct Dry Run | April 13, 2026 8:00 AM | April 17, 2026 5:00 PM | 4008FS+9d | 4010SS | As Soon As Possible | NA | 5 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43950 | Create Jira ticket to request setup of Cohort 4 users | April 13, 2026 8:00 AM | April 20, 2026 5:00 PM | 4009SS | 4011SS | As Soon As Possible | NA | 6 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43916 | Create transactional sample data for expected data volume of Cohort 4 users | April 13, 2026 8:00 AM | April 22, 2026 5:00 PM | 4010SS | 4013SS+1d | As Soon As Possible | NA | 8 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43905 | Draft, review, and distribute email communications to all Sandbox users about the upcoming code drop | March 23, 2026 8:00 AM | March 27, 2026 5:00 PM | 4008SS |  | As Soon As Possible | NA | 5 | 386d | NA | NA | 0 days? | No | NA | NA | NA | 0
43906 | Load EUST 3 code into the V1 Readiness Environment and confirm any critical fixes from EUST 3 are deployed | April 14, 2026 8:00 AM | April 17, 2026 5:00 PM | 4011SS+1d | 4014 | As Soon As Possible | NA | 4 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43907 | Conduct Sandbox Orientation with Cohort 4 | April 20, 2026 8:00 AM | April 21, 2026 5:00 PM | 4013 | 4015 | As Soon As Possible | NA | 2 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43951 | Activate Cohort 4 Users | April 22, 2026 8:00 AM | April 22, 2026 5:00 PM | 4014 | 4016FS-1d | As Soon As Possible | NA | 1 | 289d | NA | NA | 0 s? | No | NA | NA | NA | 0
43952 | Conduct User Access Support Office Hours for Cohort 4 | April 22, 2026 8:00 AM | April 27, 2026 5:00 PM | 4015FS-1d | 4017FS-2d | As Soon As Possible | NA | 4 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43956 | Confirm user logins to Sandbox Environment prior to Sandbox Training and assign all Enablement training content in Sandbox | April 24, 2026 8:00 AM | April 27, 2026 5:00 PM | 4016FS-2d | 4018FS-1d | As Soon As Possible | NA | 2 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43957 | Complete bulk re-asssignment of transactional sample data to active users and identify list of users not receiving data | April 27, 2026 8:00 AM | April 28, 2026 5:00 PM | 4017FS-1d | 4019FS-1d | As Soon As Possible | NA | 2 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43958 | Conduct Sandbox Training Webinars for Cohort 4 | April 28, 2026 8:00 AM | April 30, 2026 5:00 PM | 4018FS-1d | 4021FS+6d | As Soon As Possible | NA | 3 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43959 | Conduct Retrospective for Cohort 4 | May 11, 2026 8:00 AM | August 14, 2026 5:00 PM |  |  | As Soon As Possible | NA | 68 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43953 | Conduct retrospective about Sandbox operations, identify opportunities for continuous improvements | May 11, 2026 8:00 AM | May 20, 2026 5:00 PM | 4019FS+6d | 4022 | As Soon As Possible | NA | 8 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43954 | Review identified opportunities for Sandbox operations improvements with ELT and incorporate agreed upon improvements into Sandbox operations | May 21, 2026 8:00 AM | June 5, 2026 5:00 PM | 4021 | 4023FS+29d | As Soon As Possible | NA | 11 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43955 | Draft, review, and distribute email communications to all Sandbox users about the upcoming code drop | July 20, 2026 8:00 AM | July 24, 2026 5:00 PM | 4022FS+29d | 4024FS+10d | As Soon As Possible | NA | 5 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
43908 | Load the latest code into the V1 Readiness Environment, following completion of Process Simulation activities | August 10, 2026 8:00 AM | August 14, 2026 5:00 PM | 4023FS+10d |  | As Soon As Possible | NA | 5 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
8398 | Training | July 25, 2022 8:00 AM | September 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 1050 | 257d | July 25, 2022 8:00 AM | September 30, 2026 5:00 PM | 1050 days | No | 7/25/22 | NA | NA | 0.79000000000000004
8399 | High-level Training Approach for ILT | August 8, 2022 8:00 AM | October 26, 2022 5:00 PM |  |  | As Soon As Possible | NA | 57 | 0d | August 8, 2022 8:00 AM | October 26, 2022 5:00 PM | 57 days | No | 8/8/22 | 10/26/22 | NA | 1
8400 | Continue to incorporate ILT input into V1 training roll-out recommendation and cost | August 8, 2022 8:00 AM | October 3, 2022 5:00 PM | 3192FS+47d | 4028FS-9d | As Soon As Possible | NA | 40 | 0d | August 8, 2022 8:00 AM | October 3, 2022 5:00 PM | 40 days | No | 8/8/22 | 10/3/22 | NA | 1
8401 | Conduct and Finalize cost analysis for SPR6 | September 20, 2022 8:00 AM | October 26, 2022 5:00 PM | 4027FS-9d | 4034 | As Soon As Possible | NA | 27 | 0d | September 20, 2022 8:00 AM | October 26, 2022 5:00 PM | 27 days | No | 9/20/22 | 10/26/22 | NA | 1
8402 | RFA Release Support | October 3, 2022 8:00 AM | July 22, 2025 5:00 PM |  |  | As Soon As Possible | NA | 701 | 0d | October 3, 2022 8:00 AM | July 12, 2024 5:00 PM | 444 days | No | 10/3/22 | 7/22/25 | NA | 1
8403 | Release 0.7.0 | October 3, 2022 8:00 AM | December 15, 2022 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | October 3, 2022 8:00 AM | December 15, 2022 5:00 PM | 51 days | No | 10/3/22 | 12/15/22 | NA | 1
8404 | Develop Training Impact Analysis | October 3, 2022 8:00 AM | October 31, 2022 5:00 PM | 3192 | 4032FF | As Soon As Possible | NA | 21 | 0d | October 3, 2022 8:00 AM | October 31, 2022 5:00 PM | 21 days | No | 10/3/22 | 10/31/22 | NA | 1
8405 | Review with the State Team, Sign Off | October 17, 2022 8:00 AM | October 31, 2022 5:00 PM | 4031FF | 4033 | As Soon As Possible | NA | 11 | 0d | October 17, 2022 8:00 AM | October 31, 2022 5:00 PM | 11 days | No | 10/17/22 | 10/31/22 | NA | 1
8406 | Update Training Material | October 24, 2022 8:00 AM | November 21, 2022 5:00 PM | 4032 | 4034 | As Soon As Possible | NA | 20 | 0d | October 24, 2022 8:00 AM | November 21, 2022 5:00 PM | 20 days | No | 10/24/22 | 11/21/22 | NA | 1
8407 | Review with State Review Team | November 16, 2022 8:00 AM | November 30, 2022 5:00 PM | 4033,4028 | 4035 | As Soon As Possible | NA | 9 | 0d | November 16, 2022 8:00 AM | November 30, 2022 5:00 PM | 9 days | No | 11/16/22 | 11/30/22 | NA | 1
8408 | Incorporate Feedback | November 28, 2022 8:00 AM | November 29, 2022 5:00 PM | 4034 | 4036 | As Soon As Possible | NA | 2 | 0d | November 28, 2022 8:00 AM | November 29, 2022 5:00 PM | 2 days | No | 11/28/22 | 11/29/22 | NA | 1
8409 | Update Training Material to be ADA Compliant | November 29, 2022 8:00 AM | November 29, 2022 5:00 PM | 4035 | 4037 | As Soon As Possible | NA | 1 | 0d | November 29, 2022 8:00 AM | November 29, 2022 5:00 PM | 1 | No | 11/29/22 | 11/29/22 | NA | 1
8410 | Upload Training Material to Implementation Portal | November 30, 2022 8:00 AM | December 6, 2022 5:00 PM | 4036 | 4038FS+5d | As Soon As Possible | NA | 5 | 0d | November 30, 2022 8:00 AM | December 6, 2022 5:00 PM | 5 days | No | 11/30/22 | 12/6/22 | NA | 1
8411 | Provide Webinar training on new user facing enhancements and fixes | December 5, 2022 8:00 AM | December 7, 2022 5:00 PM | 4037FS+5d | 4039 | As Soon As Possible | NA | 3 | 0d | December 5, 2022 8:00 AM | December 7, 2022 5:00 PM | 3 days | No | 12/5/22 | 12/7/22 | NA | 1
8412 | Release 0.7.0 Completed | December 15, 2022 8:00 AM | December 15, 2022 5:00 PM | 4038 | 4041FS+30d | As Soon As Possible | NA | 1 | 0d | December 15, 2022 8:00 AM | December 15, 2022 5:00 PM | 1 | No | 12/15/22 | 12/15/22 | NA | 1
8413 | Release 0.8.0 | February 1, 2023 8:00 AM | March 21, 2023 5:00 PM |  |  | As Soon As Possible | NA | 34 | 0d | February 1, 2023 8:00 AM | March 21, 2023 5:00 PM | 34 days | No | 2/1/23 | 3/21/23 | NA | 1
8414 | Develop Training Impact Analysis | February 1, 2023 8:00 AM | February 21, 2023 5:00 PM | 4039FS+30d | 4042FF | As Soon As Possible | NA | 14 | 0d | February 1, 2023 8:00 AM | February 21, 2023 5:00 PM | 14 days | No | 2/1/23 | 2/21/23 | NA | 1
8415 | Review with the State Team, Sign Off | February 10, 2023 8:00 AM | February 27, 2023 5:00 PM | 4041FF | 4043 | As Soon As Possible | NA | 11 | 0d | February 10, 2023 8:00 AM | February 27, 2023 5:00 PM | 11 days | No | 2/10/23 | 2/27/23 | NA | 1
8416 | Update Training Material | February 17, 2023 8:00 AM | March 6, 2023 5:00 PM | 4042 | 4044 | As Soon As Possible | NA | 11 | 0d | February 17, 2023 8:00 AM | March 6, 2023 5:00 PM | 11 days | No | 2/17/23 | 3/6/23 | NA | 1
8417 | Review with State Review Team | March 7, 2023 8:00 AM | March 8, 2023 5:00 PM | 4043 | 4045 | As Soon As Possible | NA | 2 | 0d | March 7, 2023 8:00 AM | March 8, 2023 5:00 PM | 2 days | No | 3/7/23 | 3/8/23 | NA | 1
8418 | Incorporate Feedback | March 9, 2023 8:00 AM | March 10, 2023 5:00 PM | 4044 | 4046FS-1d | As Soon As Possible | NA | 2 | 0d | March 9, 2023 8:00 AM | March 10, 2023 5:00 PM | 2 days | No | 3/9/23 | 3/10/23 | NA | 1
8419 | Update Training Material to be ADA Compliant | March 10, 2023 8:00 AM | March 13, 2023 5:00 PM | 4045FS-1d | 4047FS-1d,4048SS | As Soon As Possible | NA | 2 | 0d | March 10, 2023 8:00 AM | March 13, 2023 5:00 PM | 2 days | No | 3/10/23 | 3/13/23 | NA | 1
8420 | Upload Training Material to Implementation Portal | March 13, 2023 8:00 AM | March 13, 2023 5:00 PM | 4046FS-1d | 4049 | As Soon As Possible | NA | 1 | 0d | March 13, 2023 8:00 AM | March 13, 2023 5:00 PM | 1 | No | 3/13/23 | 3/13/23 | NA | 1
8421 | Provide Webinar training on new user facing enhancements and fixes | March 10, 2023 8:00 AM | March 13, 2023 5:00 PM | 4046SS | 4049FS+5d | As Soon As Possible | NA | 2 | 0d | March 10, 2023 8:00 AM | March 13, 2023 5:00 PM | 2 days | No | 3/10/23 | 3/13/23 | NA | 1
8422 | Release 0.8.0 Completed | March 21, 2023 8:00 AM | March 21, 2023 5:00 PM | 4048FS+5d,4047 | 4051 | As Soon As Possible | NA | 1 | 0d | March 21, 2023 8:00 AM | March 21, 2023 5:00 PM | 1 | No | 3/21/23 | 3/21/23 | NA | 1
8423 | Release 0.9.0 | May 5, 2023 8:00 AM | August 1, 2023 5:00 PM |  |  | As Soon As Possible | NA | 61 | 0d | May 5, 2023 8:00 AM | August 1, 2023 5:00 PM | 61 days | No | 5/5/23 | 8/1/23 | NA | 1
8424 | Develop Training Impact Analysis | May 5, 2023 8:00 AM | May 22, 2023 5:00 PM | 4049 | 4052 | As Soon As Possible | NA | 12 | 0d | May 5, 2023 8:00 AM | May 22, 2023 5:00 PM | 12 days | No | 5/5/23 | 5/22/23 | NA | 1
8425 | Review with the State Team, Sign Off | May 23, 2023 8:00 AM | May 24, 2023 5:00 PM | 4051 | 4053FS-1d,4060FS-1d | As Soon As Possible | NA | 2 | 0d | May 23, 2023 8:00 AM | May 24, 2023 5:00 PM | 2 days | No | 5/23/23 | 5/24/23 | NA | 1
8426 | Update Training Material | May 24, 2023 8:00 AM | June 16, 2023 5:00 PM | 4052FS-1d | 4054FF | As Soon As Possible | NA | 17 | 0d | May 24, 2023 8:00 AM | June 16, 2023 5:00 PM | 17 days | No | 5/24/23 | 6/16/23 | NA | 1
8427 | Review with County Consultants and State IMP Review Team | June 15, 2023 8:00 AM | June 16, 2023 5:00 PM | 4053FF | 4055FF | As Soon As Possible | NA | 2 | 0d | June 15, 2023 8:00 AM | June 16, 2023 5:00 PM | 2 days | No | 6/15/23 | 6/16/23 | NA | 1
8428 | Incorporate Feedback | June 14, 2023 8:00 AM | June 16, 2023 5:00 PM | 4054FF | 4056FF | As Soon As Possible | NA | 3 | 0d | June 14, 2023 8:00 AM | June 16, 2023 5:00 PM | 3 days | No | 6/14/23 | 6/16/23 | NA | 1
8429 | Update Training Material to be ADA Compliant | June 15, 2023 8:00 AM | June 16, 2023 5:00 PM | 4055FF | 4057SS+1d | As Soon As Possible | NA | 2 | 0d | June 15, 2023 8:00 AM | June 16, 2023 5:00 PM | 2 days | No | 6/15/23 | 6/16/23 | NA | 1
8430 | Upload Training Material to Implementation Portal | June 16, 2023 8:00 AM | June 16, 2023 5:00 PM | 4056SS+1d | 4058FS+1d | As Soon As Possible | NA | 1 | 0d | June 16, 2023 8:00 AM | June 16, 2023 5:00 PM | 1 | No | 6/16/23 | 6/16/23 | NA | 1
8431 | Provide Webinar training on new user facing enhancements and fixes | June 20, 2023 8:00 AM | June 20, 2023 5:00 PM | 4057FS+1d | 4059 | As Soon As Possible | NA | 1 | 0d | June 20, 2023 8:00 AM | June 20, 2023 5:00 PM | 1 | No | 6/20/23 | 6/20/23 | NA | 1
8432 | Release 0.9.0 Completed | June 21, 2023 8:00 AM | June 22, 2023 5:00 PM | 4058 | 4062FS+21d | As Soon As Possible | NA | 2 | 0d | June 21, 2023 8:00 AM | June 22, 2023 5:00 PM | 2 days | No | 6/21/23 | 6/22/23 | NA | 1
8433 | Update Self-Directed Learning Videos | May 24, 2023 8:00 AM | August 1, 2023 5:00 PM | 4052FS-1d | 4063 | As Soon As Possible | NA | 48 | 0d | May 24, 2023 8:00 AM | August 1, 2023 5:00 PM | 48 days | No | 5/24/23 | 8/1/23 | NA | 1
8434 | Release 0.10.0 | July 25, 2023 8:00 AM | September 29, 2023 5:00 PM |  |  | As Soon As Possible | NA | 48 | 0d | July 25, 2023 8:00 AM | September 29, 2023 5:00 PM | 48 days | No | 7/25/23 | 9/29/23 | NA | 1
8435 | Develop Training Impact Analysis | July 25, 2023 8:00 AM | August 7, 2023 5:00 PM | 4059FS+21d | 4063,4073FS+31d | As Soon As Possible | NA | 10 | 0d | July 25, 2023 8:00 AM | August 7, 2023 5:00 PM | 10 days | No | 7/25/23 | 8/7/23 | NA | 1
8436 | Review with the State Team, Sign Off | August 8, 2023 8:00 AM | August 14, 2023 5:00 PM | 4062,4060 | 4064FS+10d | As Soon As Possible | NA | 5 | 0d | August 8, 2023 8:00 AM | August 14, 2023 5:00 PM | 5 days | No | 8/8/23 | 8/14/23 | NA | 1
8437 | Update Training Material | August 29, 2023 8:00 AM | September 15, 2023 5:00 PM | 4063FS+10d | 4065FF-3d,4071SS | As Soon As Possible | NA | 13 | 0d | August 29, 2023 8:00 AM | September 15, 2023 5:00 PM | 13 days | No | 8/29/23 | 9/15/23 | NA | 1
8438 | Review with County Consultants and State IMP Review Team | September 12, 2023 8:00 AM | September 12, 2023 5:00 PM | 4064FF-3d | 4066 | As Soon As Possible | NA | 1 | 0d | September 12, 2023 8:00 AM | September 12, 2023 5:00 PM | 1 | No | 9/12/23 | 9/12/23 | NA | 1
8439 | Incorporate Feedback | September 13, 2023 8:00 AM | September 15, 2023 5:00 PM | 4065 | 4067FF | As Soon As Possible | NA | 3 | 0d | September 13, 2023 8:00 AM | September 15, 2023 5:00 PM | 3 days | No | 9/13/23 | 9/15/23 | NA | 1
8440 | Update Training Material to be ADA Compliant | September 13, 2023 8:00 AM | September 15, 2023 5:00 PM | 4066FF | 4068FF | As Soon As Possible | NA | 3 | 0d | September 13, 2023 8:00 AM | September 15, 2023 5:00 PM | 3 days | No | 9/13/23 | 9/15/23 | NA | 1
8441 | Upload Training Material to Implementation Portal | September 15, 2023 8:00 AM | September 15, 2023 5:00 PM | 4067FF | 4069 | As Soon As Possible | NA | 1 | 0d | September 15, 2023 8:00 AM | September 15, 2023 5:00 PM | 1 | No | 9/15/23 | 9/15/23 | NA | 1
8442 | Provide Webinar training on new user facing enhancements and fixes | September 18, 2023 8:00 AM | September 19, 2023 5:00 PM | 4068 | 4070FS+1d | As Soon As Possible | NA | 2 | 0d | September 18, 2023 8:00 AM | September 19, 2023 5:00 PM | 2 days | No | 9/18/23 | 9/19/23 | NA | 1
8443 | Release 0.10.0 Completed | September 21, 2023 8:00 AM | September 22, 2023 5:00 PM | 4069FS+1d | 4074 | As Soon As Possible | NA | 2 | 0d | September 21, 2023 8:00 AM | September 22, 2023 5:00 PM | 2 days | No | 9/21/23 | 9/22/23 | NA | 1
8444 | Update Self Directed Learning Videos | August 29, 2023 8:00 AM | September 29, 2023 5:00 PM | 4064SS | 4073SS+15d | As Soon As Possible | NA | 23 | 0d | August 29, 2023 8:00 AM | September 29, 2023 5:00 PM | 23 days | No | 8/29/23 | 9/29/23 | NA | 1
8445 | Release 0.11.0 | September 21, 2023 8:00 AM | February 27, 2024 5:00 PM |  |  | As Soon As Possible | NA | 107 | 0d | September 21, 2023 8:00 AM | February 27, 2024 5:00 PM | 107 days | No | 9/21/23 | 2/27/24 | NA | 1
8446 | Develop Training Impact Analysis | September 21, 2023 8:00 AM | October 25, 2023 5:00 PM | 4062FS+31d,4071SS+15d | 4074,4084FS+30d | As Soon As Possible | NA | 25 | 0d | September 21, 2023 8:00 AM | October 25, 2023 5:00 PM | 25 days | No | 9/21/23 | 10/25/23 | NA | 1
8447 | Review with the State Team, Sign Off | October 26, 2023 8:00 AM | November 1, 2023 5:00 PM | 4073,4070 | 4075FS+10d | As Soon As Possible | NA | 5 | 0d | October 26, 2023 8:00 AM | November 1, 2023 5:00 PM | 5 days | No | 10/26/23 | 11/1/23 | NA | 1
8448 | Update Training Material | November 17, 2023 8:00 AM | December 7, 2023 5:00 PM | 4074FS+10d | 4082SS,4076 | As Soon As Possible | NA | 13 | 0d | November 17, 2023 8:00 AM | December 7, 2023 5:00 PM | 13 days | No | 11/17/23 | 12/7/23 | NA | 1
8449 | Review with County Consultants and State IMP Review Team | December 8, 2023 8:00 AM | December 8, 2023 5:00 PM | 4075 | 4077,4080 | As Soon As Possible | NA | 1 | 0d | December 8, 2023 8:00 AM | December 8, 2023 5:00 PM | 1 | No | 12/8/23 | 12/8/23 | NA | 1
8450 | Incorporate Feedback | December 11, 2023 8:00 AM | December 13, 2023 5:00 PM | 4076 | 4078FF,4079FF | As Soon As Possible | NA | 3 | 0d | December 11, 2023 8:00 AM | December 13, 2023 5:00 PM | 3 days | No | 12/11/23 | 12/13/23 | NA | 1
8451 | Update Training Material to be ADA Compliant | December 11, 2023 8:00 AM | December 13, 2023 5:00 PM | 4077FF | 4085 | As Soon As Possible | NA | 3 | 0d | December 11, 2023 8:00 AM | December 13, 2023 5:00 PM | 3 days | No | 12/11/23 | 12/13/23 | NA | 1
8452 | Upload Training Material to Implementation Portal | December 13, 2023 8:00 AM | December 13, 2023 5:00 PM | 4077FF | 4085 | As Soon As Possible | NA | 1 | 0d | December 13, 2023 8:00 AM | December 13, 2023 5:00 PM | 1 | No | 12/13/23 | 12/13/23 | NA | 1
8453 | Provide Webinar training on new user facing enhancements and fixes | December 11, 2023 8:00 AM | December 11, 2023 5:00 PM | 4076 | 4081FS+1d | As Soon As Possible | NA | 1 | 0d | December 11, 2023 8:00 AM | December 11, 2023 5:00 PM | 1 | No | 12/11/23 | 12/11/23 | NA | 1
8454 | Release 0.11.0 Completed | December 13, 2023 8:00 AM | December 14, 2023 5:00 PM | 4080FS+1d | 4085 | As Soon As Possible | NA | 2 | 0d | December 13, 2023 8:00 AM | December 14, 2023 5:00 PM | 2 days | No | 12/13/23 | 12/14/23 | NA | 1
8455 | Update Self Directed Learning Videos | November 17, 2023 8:00 AM | February 27, 2024 5:00 PM | 4075SS | 4086 | As Soon As Possible | NA | 67 | 0d | November 17, 2023 8:00 AM | February 27, 2024 5:00 PM | 67 days | No | 11/17/23 | 2/27/24 | NA | 1
8456 | Release 0.12.0 | December 12, 2023 8:00 AM | April 26, 2024 5:00 PM |  |  | As Soon As Possible | NA | 94 | 0d | December 12, 2023 8:00 AM | April 26, 2024 5:00 PM | 94 days | No | 12/12/23 | 4/26/24 | NA | 1
8457 | Develop Training Impact Analysis | December 12, 2023 8:00 AM | March 1, 2024 5:00 PM | 4073FS+30d | 4085FF,4095FS+16d | As Soon As Possible | NA | 55 | 0d | December 12, 2023 8:00 AM | March 1, 2024 5:00 PM | 55 days | No | 12/12/23 | 3/1/24 | NA | 1
8458 | Review with the State Team, Sign Off | February 1, 2024 8:00 AM | March 1, 2024 5:00 PM | 4084FF,4078,4079,4081 | 4086 | As Soon As Possible | NA | 21 | 0d | February 1, 2024 8:00 AM | March 1, 2024 5:00 PM | 21 days | No | 2/1/24 | 3/1/24 | NA | 1
8459 | Update Training Material | March 4, 2024 8:00 AM | March 15, 2024 5:00 PM | 4085,4082 | 4087,4093SS+10d | As Soon As Possible | NA | 10 | 0d | March 4, 2024 8:00 AM | March 15, 2024 5:00 PM | 10 days | No | 3/4/24 | 3/15/24 | NA | 1
8460 | Review with County Consultants and State IMP Review Team | March 18, 2024 8:00 AM | March 18, 2024 5:00 PM | 4086 | 4088 | As Soon As Possible | NA | 1 | 0d | March 18, 2024 8:00 AM | March 18, 2024 5:00 PM | 1 | No | 3/18/24 | 3/18/24 | NA | 1
8461 | Incorporate Feedback | March 19, 2024 8:00 AM | March 21, 2024 5:00 PM | 4087 | 4089FF,4090FF | As Soon As Possible | NA | 3 | 0d | March 19, 2024 8:00 AM | March 21, 2024 5:00 PM | 3 days | No | 3/19/24 | 3/21/24 | NA | 1
8462 | Update Training Material to be ADA Compliant | March 19, 2024 8:00 AM | March 21, 2024 5:00 PM | 4088FF | 4091 | As Soon As Possible | NA | 3 | 0d | March 19, 2024 8:00 AM | March 21, 2024 5:00 PM | 3 days | No | 3/19/24 | 3/21/24 | NA | 1
8463 | Upload Training Material to Implementation Portal | March 21, 2024 8:00 AM | March 21, 2024 5:00 PM | 4088FF | 4091 | As Soon As Possible | NA | 1 | 0d | March 21, 2024 8:00 AM | March 21, 2024 5:00 PM | 1 | No | 3/21/24 | 3/21/24 | NA | 1
8464 | Provide Webinar training on new user facing enhancements and fixes | March 22, 2024 8:00 AM | March 25, 2024 5:00 PM | 4090,4089 | 4092 | As Soon As Possible | NA | 2 | 0d | March 22, 2024 8:00 AM | March 25, 2024 5:00 PM | 2 days | No | 3/22/24 | 3/25/24 | NA | 1
8465 | Release 0.12.0 Completed | April 25, 2024 8:00 AM | April 26, 2024 5:00 PM | 4093,4091 | 4097 | As Soon As Possible | NA | 2 | 0d | April 25, 2024 8:00 AM | April 26, 2024 5:00 PM | 2 days | No | 4/25/24 | 4/26/24 | NA | 1
8466 | Update Self Directed Learning Videos | March 18, 2024 8:00 AM | April 24, 2024 5:00 PM | 4086SS+10d | 4092 | As Soon As Possible | NA | 27 | 0d | March 18, 2024 8:00 AM | April 24, 2024 5:00 PM | 27 days | No | 3/18/24 | 4/24/24 | NA | 1
8467 | Release 0.13.0 Training Material | March 26, 2024 8:00 AM | July 12, 2024 5:00 PM |  |  | As Soon As Possible | NA | 76 | 0d | March 26, 2024 8:00 AM | July 12, 2024 5:00 PM | 76 days | No | 3/26/24 | 7/12/24 | NA | 1
8468 | Develop Training Impact Analysis | March 26, 2024 8:00 AM | April 19, 2024 5:00 PM | 4084FS+16d | 4096 | As Soon As Possible | NA | 18 | 0d | March 26, 2024 8:00 AM | April 19, 2024 5:00 PM | 18 days | No | 3/26/24 | 4/19/24 | NA | 1
8469 | Review with the State Team, Sign Off | April 22, 2024 8:00 AM | April 26, 2024 5:00 PM | 4095 | 4097 | As Soon As Possible | NA | 5 | 0d | April 22, 2024 8:00 AM | April 26, 2024 5:00 PM | 5 days | No | 4/22/24 | 4/26/24 | NA | 1
8470 | Update Training Material | April 29, 2024 8:00 AM | June 14, 2024 5:00 PM | 4096,4092 | 4098 | As Soon As Possible | NA | 34 | 0d | April 29, 2024 8:00 AM | June 14, 2024 5:00 PM | 34 days | No | 4/29/24 | 6/14/24 | NA | 1
8471 | Review with County Consultants and State IMP Review Team | June 17, 2024 8:00 AM | June 18, 2024 5:00 PM | 4097 | 4099,4103FS+1d | As Soon As Possible | NA | 2 | 0d | June 17, 2024 8:00 AM | June 18, 2024 5:00 PM | 2 days | No | 6/17/24 | 6/18/24 | NA | 1
8472 | Incorporate Feedback | June 19, 2024 8:00 AM | June 21, 2024 5:00 PM | 4098 | 4102 | As Soon As Possible | NA | 3 | 0d | June 19, 2024 8:00 AM | June 21, 2024 5:00 PM | 3 days | No | 6/19/24 | 6/21/24 | NA | 1
8473 | Update Training Material to be ADA Compliant | June 25, 2024 8:00 AM | June 25, 2024 5:00 PM | 4102 | 4101FF | As Soon As Possible | NA | 1 | 0d | June 25, 2024 8:00 AM | June 25, 2024 5:00 PM | 1 | No | 6/25/24 | 6/25/24 | NA | 1
8474 | Upload Training Material to Implementation Portal | June 25, 2024 8:00 AM | June 25, 2024 5:00 PM | 4100FF | 4104 | As Soon As Possible | NA | 1 | 0d | June 25, 2024 8:00 AM | June 25, 2024 5:00 PM | 1 | No | 6/25/24 | 6/25/24 | NA | 1
8475 | Provide Webinar training on new user facing enhancements and fixes | June 24, 2024 8:00 AM | June 24, 2024 5:00 PM | 4099 | 4100 | As Soon As Possible | NA | 1 | 0d | June 24, 2024 8:00 AM | June 24, 2024 5:00 PM | 1 | No | 6/24/24 | 6/24/24 | NA | 1
8476 | Update Self Directed Learning Videos | June 20, 2024 8:00 AM | July 10, 2024 5:00 PM | 4098FS+1d | 4104,4106FS-1d | As Soon As Possible | NA | 14 | 0d | June 20, 2024 8:00 AM | July 10, 2024 5:00 PM | 14 days | No | 6/20/24 | 7/10/24 | NA | 1
8477 | Release 0.13.0 Completed | July 11, 2024 8:00 AM | July 12, 2024 5:00 PM | 4103,4101 | 4925 | As Soon As Possible | NA | 2 | 0d | July 11, 2024 8:00 AM | July 12, 2024 5:00 PM | 2 days | No | 7/11/24 | 7/12/24 | NA | 1
12094 | Release 0.14.0 Training Material | July 10, 2024 8:00 AM | October 7, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 76 days | No | 7/10/24 | 10/7/24 | NA | 1
12095 | Develop Training Impact Analysis | July 10, 2024 8:00 AM | August 8, 2024 5:00 PM | 4103FS-1d | 4107 | As Soon As Possible | NA | 22 | 0d | NA | NA | 18 days | No | 7/10/24 | 8/8/24 | NA | 1
12096 | Review with the State Team, Sign Off | August 9, 2024 8:00 AM | August 15, 2024 5:00 PM | 4106 | 4108FS+1d,4114FS+1d | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 8/9/24 | 8/15/24 | NA | 1
12097 | Update Training Material | August 19, 2024 8:00 AM | September 6, 2024 5:00 PM | 4107FS+1d | 4109 | As Soon As Possible | NA | 15 | 0d | NA | NA | 34 days | No | 8/19/24 | 9/6/24 | NA | 1
12098 | Review with County Consultants and State IMP Review Team | September 9, 2024 8:00 AM | September 16, 2024 5:00 PM | 4108 | 4110,4113FF | As Soon As Possible | NA | 6 | 0d | NA | NA | 2 days | No | 9/9/24 | 9/16/24 | NA | 1
12099 | Incorporate Feedback | September 17, 2024 8:00 AM | September 18, 2024 5:00 PM | 4109 | 4111 | As Soon As Possible | NA | 2 | 0d | NA | NA | 3 days | No | 9/17/24 | 9/18/24 | NA | 1
12100 | Update Training Material to be ADA Compliant - RFA 0.14.0 | September 19, 2024 8:00 AM | September 20, 2024 5:00 PM | 4110 | 4112FF | As Soon As Possible | NA | 2 | 0d | NA | NA | 1 day | No | 9/19/24 | 9/20/24 | NA | 1
12101 | Upload Training Material to Implementation Portal | September 20, 2024 8:00 AM | September 20, 2024 5:00 PM | 4111FF | 4116 | As Soon As Possible | NA | 1 | 0d | NA | NA | 1 | No | 9/20/24 | 9/20/24 | NA | 1
12102 | Provide Webinar training on new user facing enhancements and fixes | September 16, 2024 8:00 AM | September 16, 2024 5:00 PM | 4109FF | 4118FS+4d | As Soon As Possible | NA | 1 | 0d | NA | NA | 1 | No | 9/16/24 | 9/16/24 | NA | 1
12103 | Update Self Directed Learning Videos | August 19, 2024 8:00 AM | September 12, 2024 5:00 PM | 4107FS+1d | 4115 | As Soon As Possible | NA | 19 | 0d | NA | NA | 14 days | No | 8/19/24 | 9/12/24 | NA | 1
12104 | Review Self Directed Learning Videos - RFA 0.14.0 | September 13, 2024 8:00 AM | October 4, 2024 5:00 PM | 4114 | 4116 | As Soon As Possible | NA | 16 | 0d | NA | NA | 0 days | No | 9/13/24 | 10/4/24 | NA | 1
12105 | Release RFA 0.14.0 Completed | October 7, 2024 8:00 AM | October 7, 2024 5:00 PM | 4115,4112 | 4925 | As Soon As Possible | NA | 1 | 0d | NA | NA | 2 s | No | 10/7/24 | 10/7/24 | NA | 1
12106 | Release 0.15.0 Training Material | September 23, 2024 8:00 AM | January 10, 2025 5:00 PM |  |  | As Soon As Possible | NA | 75 | 0d | NA | NA | 76 days | No | 9/23/24 | 1/10/25 | NA | 1
12107 | Develop Training Impact Analysis | September 23, 2024 8:00 AM | October 23, 2024 5:00 PM | 4113FS+4d | 4119SS | As Soon As Possible | NA | 23 | 0d | NA | NA | 18 days | No | 9/23/24 | 10/23/24 | NA | 1
12108 | Complete "Whats New" Document | September 23, 2024 8:00 AM | October 23, 2024 5:00 PM | 4118SS | 4120FS+9d | As Soon As Possible | NA | 23 | 0d | NA | NA | 5 days | No | 9/23/24 | 10/23/24 | NA | 1
12109 | Update Training Material | November 6, 2024 8:00 AM | November 22, 2024 5:00 PM | 4119FS+9d | 4121FS+1d,4126SS+6d | As Soon As Possible | NA | 12 | 0d | NA | NA | 34 days | No | 11/6/24 | 11/22/24 | NA | 1
12110 | Review with County Consultants and State IMP Review Team | November 26, 2024 8:00 AM | December 6, 2024 5:00 PM | 4120FS+1d | 4122 | As Soon As Possible | NA | 7 | 0d | NA | NA | 2 days | No | 11/26/24 | 12/6/24 | NA | 1
12111 | Incorporate Feedback | December 9, 2024 8:00 AM | December 11, 2024 5:00 PM | 4121 | 4123 | As Soon As Possible | NA | 3 | 0d | NA | NA | 3 days | No | 12/9/24 | 12/11/24 | NA | 1
12112 | Update Training Material to be ADA Compliant - RFA 0.15.0 | December 12, 2024 8:00 AM | December 13, 2024 5:00 PM | 4122 | 4124FS-1d | As Soon As Possible | NA | 2 | 0d | NA | NA | 1 day | No | 12/12/24 | 12/13/24 | NA | 1
12113 | Upload Training Material to Implementation Portal | December 13, 2024 8:00 AM | December 16, 2024 5:00 PM | 4123FS-1d | 4125FF | As Soon As Possible | NA | 2 | 0d | NA | NA | 1 day | No | 12/13/24 | 12/16/24 | NA | 1
12114 | Provide Webinar training on new user facing enhancements and fixes | December 16, 2024 8:00 AM | December 16, 2024 5:00 PM | 4124FF | 4129FS+6d | As Soon As Possible | NA | 1 | 0d | NA | NA | 1 | No | 12/16/24 | 12/16/24 | NA | 1
12115 | Update Self Directed Learning Videos | November 15, 2024 8:00 AM | January 10, 2025 5:00 PM | 4120SS+6d | 4127 | As Soon As Possible | NA | 37 | 0d | NA | NA | 14 days | No | 11/15/24 | 1/10/25 | NA | 1
12117 | Release 0.15.0 Completed | January 10, 2025 5:00 PM | January 10, 2025 5:00 PM | 4126 | 4925 | As Soon As Possible | NA | 0 | 0d | NA | NA | 2 days | Yes | 1/10/25 | 1/10/25 | NA | 1
12118 | Release 0.16.0 Training Material | December 26, 2024 8:00 AM | April 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 78 | 0d | NA | NA | 76 days | No | 12/26/24 | 4/18/25 | NA | 1
12119 | Develop Training Impact Analysis | December 26, 2024 8:00 AM | January 28, 2025 5:00 PM | 4125FS+6d | 4130SS | As Soon As Possible | NA | 22 | 0d | NA | NA | 18 days | No | 12/26/24 | 1/28/25 | NA | 1
12120 | Complete "Whats New" Document | December 26, 2024 8:00 AM | January 28, 2025 5:00 PM | 4129SS | 4131 | As Soon As Possible | NA | 22 | 0d | NA | NA | 5 days | No | 12/26/24 | 1/28/25 | NA | 1
12121 | Update Training Material | January 29, 2025 8:00 AM | February 25, 2025 5:00 PM | 4130 | 4132,4137 | As Soon As Possible | NA | 19 | 0d | NA | NA | 34 days | No | 1/29/25 | 2/25/25 | NA | 1
12122 | Review with County Consultants and State IMP Review Team | February 26, 2025 8:00 AM | February 27, 2025 5:00 PM | 4131 | 4133 | As Soon As Possible | NA | 2 | 0d | NA | NA | 2 days | No | 2/26/25 | 2/27/25 | NA | 1
12123 | Incorporate Feedback | February 28, 2025 8:00 AM | March 3, 2025 5:00 PM | 4132 | 4134 | As Soon As Possible | NA | 2 | 0d | NA | NA | 3 days | No | 2/28/25 | 3/3/25 | NA | 1
12124 | Update Training Material to be ADA Compliant - RFA 0.16.0 | March 4, 2025 8:00 AM | March 7, 2025 5:00 PM | 4133 | 4135 | As Soon As Possible | NA | 4 | 0d | NA | NA | 1 day | No | 3/4/25 | 3/7/25 | NA | 1
12125 | Upload Training Material to Implementation Portal | March 10, 2025 8:00 AM | March 12, 2025 5:00 PM | 4134 | 4136FS+1d | As Soon As Possible | NA | 3 | 0d | NA | NA | 1 day | No | 3/10/25 | 3/12/25 | NA | 1
12126 | Provide Webinar training on new user facing enhancements and fixes | March 14, 2025 8:00 AM | March 17, 2025 5:00 PM | 4135FS+1d | 4141FS+2d | As Soon As Possible | NA | 2 | 0d | NA | NA | 1 day | No | 3/14/25 | 3/17/25 | NA | 1
12127 | Update Self Directed Learning Videos | February 26, 2025 8:00 AM | March 21, 2025 5:00 PM | 4131 | 4138 | As Soon As Possible | NA | 18 | 0d | NA | NA | 14 days | No | 2/26/25 | 3/21/25 | NA | 1
12128 | Review Self Directed Learning Videos - RFA 0.16.0 | March 24, 2025 8:00 AM | April 17, 2025 5:00 PM | 4137 | 4139 | As Soon As Possible | NA | 18 | 0d | NA | NA | 0 days | No | 3/24/25 | 4/17/25 | NA | 1
12129 | Release 0.16.0 Completed | April 18, 2025 8:00 AM | April 18, 2025 5:00 PM | 4138 | 4925 | As Soon As Possible | NA | 1 | 0d | NA | NA | 2 s | No | 4/18/25 | 4/18/25 | NA | 1
12130 | Release 0.17.0 Training Material | March 20, 2025 8:00 AM | July 22, 2025 5:00 PM |  |  | As Soon As Possible | NA | 86 | 0d | NA | NA | 76 days | No | 3/20/25 | 7/22/25 | NA | 1
12131 | Develop Training Impact Analysis | March 20, 2025 8:00 AM | April 21, 2025 5:00 PM | 4136FS+2d | 4142SS | As Soon As Possible | NA | 22 | 0d | NA | NA | 18 days | No | 3/20/25 | 4/21/25 | NA | 1
12132 | Complete "Whats New" Document | March 20, 2025 8:00 AM | April 21, 2025 5:00 PM | 4141SS | 4143FS+18d | As Soon As Possible | NA | 22 | 0d | NA | NA | 5 days | No | 3/20/25 | 4/21/25 | NA | 1
12133 | Update Training Material | May 16, 2025 8:00 AM | June 6, 2025 5:00 PM | 4142FS+18d | 4144 | As Soon As Possible | NA | 15 | 0d | NA | NA | 34 days | No | 5/16/25 | 6/6/25 | NA | 1
12134 | Review with County Consultants and State IMP Review Team | June 9, 2025 8:00 AM | June 13, 2025 5:00 PM | 4143 | 4145 | As Soon As Possible | NA | 5 | 0d | NA | NA | 2 days | No | 6/9/25 | 6/13/25 | NA | 1
12135 | Incorporate Feedback | June 16, 2025 8:00 AM | June 17, 2025 5:00 PM | 4144 | 4146FF | As Soon As Possible | NA | 2 | 0d | NA | NA | 3 days | No | 6/16/25 | 6/17/25 | NA | 1
12136 | Update Training Material to be ADA Compliant - RFA 0.17.0 | June 17, 2025 8:00 AM | June 17, 2025 5:00 PM | 4145FF | 4147,4149 | As Soon As Possible | NA | 1 | 0d | NA | NA | 1 | No | 6/17/25 | 6/17/25 | NA | 1
12137 | Upload Training Material to Implementation Portal | June 18, 2025 8:00 AM | June 20, 2025 5:00 PM | 4146 | 4148FS+18d | As Soon As Possible | NA | 3 | 0d | NA | NA | 1 day | No | 6/18/25 | 6/20/25 | NA | 1
12138 | Provide Webinar training on new user facing enhancements and fixes | July 18, 2025 8:00 AM | July 21, 2025 5:00 PM | 4147FS+18d | 4150 | As Soon As Possible | NA | 2 | 0d | NA | NA | 1 day | No | 7/18/25 | 7/21/25 | NA | 1
12139 | Update Self Directed Learning Videos - RFA 0.17.0 | June 18, 2025 8:00 AM | July 18, 2025 5:00 PM | 4146 | 4150 | As Soon As Possible | NA | 22 | 0d | NA | NA | 14 days | No | 6/18/25 | 7/18/25 | NA | 1
12140 | Release 0.17.0 Completed | July 22, 2025 8:00 AM | July 22, 2025 5:00 PM | 4148,4149 | 4925 | As Soon As Possible | NA | 1 | 0d | NA | NA | 2 s | No | 7/22/25 | 7/22/25 | NA | 1
8478 | Continue to update Captivate training videos with Current RFA Functionality | September 5, 2022 8:00 AM | April 4, 2023 5:00 PM |  |  | As Soon As Possible | NA | 143 | 0d | September 5, 2022 8:00 AM | April 4, 2023 5:00 PM | 143 days | No | 9/5/22 | 4/4/23 | NA | 1
8479 | Module 2: Tribal RFA | September 5, 2022 8:00 AM | November 15, 2022 5:00 PM |  |  | As Soon As Possible | NA | 50 | 0d | September 5, 2022 8:00 AM | November 15, 2022 5:00 PM | 50 days | No | 9/5/22 | 11/15/22 | NA | 1
8480 | Develop Story Board Power Point of Updates needed to Module | September 5, 2022 8:00 AM | September 12, 2022 5:00 PM | 3192SS+60d | 4154 | As Soon As Possible | NA | 5 | 0d | September 5, 2022 8:00 AM | September 12, 2022 5:00 PM | 5 days | No | 9/5/22 | 9/12/22 | NA | 1
8481 | Present Storyboard to State Review Team and get feedback | September 12, 2022 8:00 AM | September 16, 2022 5:00 PM | 4153 | 4155 | As Soon As Possible | NA | 5 | 0d | September 12, 2022 8:00 AM | September 16, 2022 5:00 PM | 5 days | No | 9/12/22 | 9/16/22 | NA | 1
8482 | Update Storyboard with feedback | September 19, 2022 8:00 AM | September 23, 2022 5:00 PM | 4154 | 4156 | As Soon As Possible | NA | 5 | 0d | September 19, 2022 8:00 AM | September 23, 2022 5:00 PM | 5 days | No | 9/19/22 | 9/23/22 | NA | 1
8483 | Update Captivate Video | September 26, 2022 8:00 AM | October 26, 2022 5:00 PM | 4155 | 4157FS+5d | As Soon As Possible | NA | 23 | 0d | September 26, 2022 8:00 AM | October 26, 2022 5:00 PM | 23 days | No | 9/26/22 | 10/26/22 | NA | 1
8484 | Review Draft Captivate with State Review Team and get feedback | October 17, 2022 8:00 AM | October 25, 2022 5:00 PM | 4156FS+5d | 4158 | As Soon As Possible | NA | 7 | 0d | October 17, 2022 8:00 AM | October 25, 2022 5:00 PM | 7 days | No | 10/17/22 | 10/25/22 | NA | 1
8485 | Update Captivate module with State feedback, including ADA | October 24, 2022 8:00 AM | October 28, 2022 5:00 PM | 4157 | 4159 | As Soon As Possible | NA | 5 | 0d | October 24, 2022 8:00 AM | October 28, 2022 5:00 PM | 5 days | No | 10/24/22 | 10/28/22 | NA | 1
8486 | Finalize Updated Captivate Training Module | October 26, 2022 8:00 AM | November 15, 2022 5:00 PM | 4158 | 4160 | As Soon As Possible | NA | 14 | 0d | October 26, 2022 8:00 AM | November 15, 2022 5:00 PM | 14 days | No | 10/26/22 | 11/15/22 | NA | 1
8487 | Module 2: Tribal RFA Complete | November 15, 2022 5:00 PM | November 15, 2022 5:00 PM | 4159 | 4162FS-4d | As Soon As Possible | NA | 0 | 0d | November 15, 2022 5:00 PM | November 15, 2022 5:00 PM | 0 days | Yes | 11/15/22 | 11/15/22 | NA | 1
8488 | Module 3 RFA: Receipt, Record, Submission and Assignment of Application | October 17, 2022 8:00 AM | January 10, 2023 5:00 PM |  |  | As Soon As Possible | NA | 57 | 0d | October 17, 2022 8:00 AM | January 10, 2023 5:00 PM | 57 days | No | 10/17/22 | 1/10/23 | NA | 1
8489 | Develop Story Board Power Point of Updates needed to Module | October 17, 2022 8:00 AM | October 26, 2022 5:00 PM | 4160FS-4d | 4163FS-1d | As Soon As Possible | NA | 8 | 0d | October 17, 2022 8:00 AM | October 26, 2022 5:00 PM | 8 days | No | 10/17/22 | 10/26/22 | NA | 1
8490 | Present Storyboard to State Review Team and get feedback | October 26, 2022 8:00 AM | November 1, 2022 5:00 PM | 4162FS-1d | 4164 | As Soon As Possible | NA | 5 | 0d | October 26, 2022 8:00 AM | November 1, 2022 5:00 PM | 5 days | No | 10/26/22 | 11/1/22 | NA | 1
8491 | Update Storyboard with feedback | November 2, 2022 8:00 AM | November 4, 2022 5:00 PM | 4163 | 4165 | As Soon As Possible | NA | 3 | 0d | November 2, 2022 8:00 AM | November 4, 2022 5:00 PM | 3 days | No | 11/2/22 | 11/4/22 | NA | 1
8492 | Update Captivate Video | November 2, 2022 8:00 AM | December 5, 2022 5:00 PM | 4164 | 4166 | As Soon As Possible | NA | 21 | 0d | November 2, 2022 8:00 AM | December 5, 2022 5:00 PM | 21 days | No | 11/2/22 | 12/5/22 | NA | 1
8493 | Review Draft Captivate with State Review Team and get feedback | December 15, 2022 8:00 AM | December 27, 2022 5:00 PM | 4165 | 4167FS+4d | As Soon As Possible | NA | 8 | 0d | December 15, 2022 8:00 AM | December 27, 2022 5:00 PM | 8 days | No | 12/15/22 | 12/27/22 | NA | 1
8494 | Update Captivate module with State feedback, including ADA | January 4, 2023 8:00 AM | January 10, 2023 5:00 PM | 4166FS+4d | 4168FS-1d | As Soon As Possible | NA | 5 | 0d | January 4, 2023 8:00 AM | January 10, 2023 5:00 PM | 5 days | No | 1/4/23 | 1/10/23 | NA | 1
8495 | Finalize Updated Captivate Training Module | January 10, 2023 8:00 AM | January 10, 2023 5:00 PM | 4167FS-1d | 4169 | As Soon As Possible | NA | 1 | 0d | January 10, 2023 8:00 AM | January 10, 2023 5:00 PM | 1 | No | 1/10/23 | 1/10/23 | NA | 1
8496 | Module 3 RFA: Receipt, Record, Submission and Assignment of Application Complete | January 10, 2023 5:00 PM | January 10, 2023 5:00 PM | 4168 | 4171FS-4d | As Soon As Possible | NA | 0 | 0d | January 10, 2023 5:00 PM | January 10, 2023 5:00 PM | 0 days | Yes | 1/10/23 | 1/10/23 | NA | 1
8497 | Module 4 RFA: Adding Contacts and Activities | January 3, 2023 8:00 AM | March 24, 2023 5:00 PM |  |  | As Soon As Possible | NA | 57 | 0d | January 3, 2023 8:00 AM | March 24, 2023 5:00 PM | 57 days | No | 1/3/23 | 3/24/23 | NA | 1
8498 | Develop Story Board Power Point of Updates needed to Module | January 3, 2023 8:00 AM | January 10, 2023 5:00 PM | 4169FS-4d | 4172FS+3d | As Soon As Possible | NA | 6 | 0d | January 3, 2023 8:00 AM | January 10, 2023 5:00 PM | 6 days | No | 1/3/23 | 1/10/23 | NA | 1
8499 | Present Storyboard to State Review Team and get feedback | January 17, 2023 8:00 AM | January 31, 2023 5:00 PM | 4171FS+3d | 4173FS+1d | As Soon As Possible | NA | 11 | 0d | January 17, 2023 8:00 AM | January 31, 2023 5:00 PM | 11 days | No | 1/17/23 | 1/31/23 | NA | 1
8500 | Update Storyboard with feedback | January 25, 2023 8:00 AM | February 6, 2023 5:00 PM | 4172FS+1d | 4174 | As Soon As Possible | NA | 9 | 0d | January 25, 2023 8:00 AM | February 6, 2023 5:00 PM | 9 days | No | 1/25/23 | 2/6/23 | NA | 1
8501 | Update Captivate Video | February 10, 2023 8:00 AM | February 23, 2023 5:00 PM | 4173 | 4175 | As Soon As Possible | NA | 9 | 0d | February 10, 2023 8:00 AM | February 23, 2023 5:00 PM | 9 days | No | 2/10/23 | 2/23/23 | NA | 1
8502 | Review Draft Captivate with State Review Team and get feedback | February 24, 2023 8:00 AM | March 17, 2023 5:00 PM | 4174 | 4176FF | As Soon As Possible | NA | 16 | 0d | February 24, 2023 8:00 AM | March 17, 2023 5:00 PM | 16 days | No | 2/24/23 | 3/17/23 | NA | 1
8503 | Update Captivate module with State feedback, including ADA | March 14, 2023 8:00 AM | March 17, 2023 5:00 PM | 4175FF | 4177 | As Soon As Possible | NA | 4 | 0d | March 14, 2023 8:00 AM | March 17, 2023 5:00 PM | 4 days | No | 3/14/23 | 3/17/23 | NA | 1
8504 | Finalize Updated Captivate Training Module | March 20, 2023 8:00 AM | March 24, 2023 5:00 PM | 4176 | 4178 | As Soon As Possible | NA | 5 | 0d | March 20, 2023 8:00 AM | March 24, 2023 5:00 PM | 5 days | No | 3/20/23 | 3/24/23 | NA | 1
8505 | Module 4 RFA: Adding Contacts and Activities Completed | March 24, 2023 5:00 PM | March 24, 2023 5:00 PM | 4177 | 4180FS-10d | As Soon As Possible | NA | 0 | 0d | March 24, 2023 5:00 PM | March 24, 2023 5:00 PM | 0 days | Yes | 3/24/23 | 3/24/23 | NA | 1
8506 | Module 5 RFA: Home Assessment | March 13, 2023 8:00 AM | April 4, 2023 5:00 PM |  |  | As Soon As Possible | NA | 16 | 0d | March 13, 2023 8:00 AM | April 4, 2023 5:00 PM | 16 days | No | 3/13/23 | 4/4/23 | NA | 1
8507 | Develop Story Board Power Point of Updates needed to Module | March 13, 2023 8:00 AM | March 17, 2023 5:00 PM | 4178FS-10d | 4181FS+5d | As Soon As Possible | NA | 5 | 0d | March 13, 2023 8:00 AM | March 17, 2023 5:00 PM | 5 days | No | 3/13/23 | 3/17/23 | NA | 1
8508 | Present Storyboard to State Review Team and get feedback | March 27, 2023 8:00 AM | March 30, 2023 5:00 PM | 4180FS+5d | 4182FS-14d | As Soon As Possible | NA | 4 | 0d | March 27, 2023 8:00 AM | March 30, 2023 5:00 PM | 4 days | No | 3/27/23 | 3/30/23 | NA | 1
8509 | Update Storyboard with feedback | March 13, 2023 8:00 AM | March 28, 2023 5:00 PM | 4181FS-14d | 4183FS-1d | As Soon As Possible | NA | 12 | 0d | March 13, 2023 8:00 AM | March 28, 2023 5:00 PM | 12 days | No | 3/13/23 | 3/28/23 | NA | 1
8510 | Update Captivate Video | March 28, 2023 8:00 AM | March 31, 2023 5:00 PM | 4182FS-1d | 4184 | As Soon As Possible | NA | 3 | 0d | March 28, 2023 8:00 AM | March 31, 2023 5:00 PM | 3 days | No | 3/28/23 | 3/31/23 | NA | 1
8511 | Review Draft Captivate with State Review Team and get feedback | April 3, 2023 8:00 AM | April 3, 2023 5:00 PM | 4183 | 4185 | As Soon As Possible | NA | 1 | 0d | April 3, 2023 8:00 AM | April 3, 2023 5:00 PM | 1 | No | 4/3/23 | 4/3/23 | NA | 1
8512 | Update Captivate module with State feedback, including ADA | April 4, 2023 8:00 AM | April 4, 2023 5:00 PM | 4184 | 4186FS-1d | As Soon As Possible | NA | 1 | 0d | April 4, 2023 8:00 AM | April 4, 2023 5:00 PM | 1 | No | 4/4/23 | 4/4/23 | NA | 1
8513 | Finalize Updated Captivate Training Module | April 4, 2023 8:00 AM | April 4, 2023 5:00 PM | 4185FS-1d | 4187 | As Soon As Possible | NA | 1 | 0d | April 4, 2023 8:00 AM | April 4, 2023 5:00 PM | 1 | No | 4/4/23 | 4/4/23 | NA | 1
8514 | Module 5 RFA: Applicant Background Checks, Orientation and Training Completed | April 4, 2023 5:00 PM | April 4, 2023 5:00 PM | 4186 | 4925 | As Soon As Possible | NA | 0 | 0d | April 4, 2023 5:00 PM | April 4, 2023 5:00 PM | 0 days | Yes | 4/4/23 | 4/4/23 | NA | 1
8515 | Develop V1 Training Approach | July 25, 2022 8:00 AM | February 3, 2023 5:00 PM |  |  | As Soon As Possible | NA | 133 | 0d | July 25, 2022 8:00 AM | February 3, 2023 5:00 PM | 133 days | No | 7/25/22 | 2/3/23 | NA | 1
8516 | Develop CWS-CARES Personas - Leverage OCM analysis | July 25, 2022 8:00 AM | August 26, 2022 5:00 PM | 3192SS+35d | 4190 | As Soon As Possible | NA | 25 | 0d | July 25, 2022 8:00 AM | August 26, 2022 5:00 PM | 25 days | No | 7/25/22 | 8/26/22 | NA | 1
8517 | Develop Draft Audience Analysis | August 30, 2022 8:00 AM | September 13, 2022 5:00 PM | 4189 | 4191 | As Soon As Possible | NA | 10 | 0d | August 30, 2022 8:00 AM | September 13, 2022 5:00 PM | 10 days | No | 8/30/22 | 9/13/22 | NA | 1
8518 | Review Draft Audience Analysis with State | September 13, 2022 8:00 AM | September 19, 2022 5:00 PM | 4190 | 4192 | As Soon As Possible | NA | 5 | 0d | September 13, 2022 8:00 AM | September 19, 2022 5:00 PM | 5 days | No | 9/13/22 | 9/19/22 | NA | 1
8519 | Review with Training advisory group | September 20, 2022 8:00 AM | September 26, 2022 5:00 PM | 4191 | 4195 | As Soon As Possible | NA | 5 | 0d | September 20, 2022 8:00 AM | September 26, 2022 5:00 PM | 5 days | No | 9/20/22 | 9/26/22 | NA | 1
8520 | Update Draft Audience Analysis based on feedback from State Review | October 6, 2022 8:00 AM | October 12, 2022 5:00 PM | 4195 | 4194 | As Soon As Possible | NA | 5 | 0d | October 6, 2022 8:00 AM | October 12, 2022 5:00 PM | 5 days | No | 10/6/22 | 10/12/22 | NA | 1
8521 | Submit final V1 Audience Analysis | October 12, 2022 5:00 PM | October 12, 2022 5:00 PM | 4193 | 4196 | As Soon As Possible | NA | 0 | 0d | October 12, 2022 5:00 PM | October 12, 2022 5:00 PM | 0 days | Yes | 10/12/22 | 10/12/22 | NA | 1
8522 | Finalize Audience Analysis | September 27, 2022 8:00 AM | October 24, 2022 5:00 PM | 4192 | 4193 | As Soon As Possible | NA | 20 | 0d | September 27, 2022 8:00 AM | October 24, 2022 5:00 PM | 20 days | No | 9/27/22 | 10/24/22 | NA | 1
8523 | Complete high-level functional analysis | October 13, 2022 8:00 AM | November 2, 2022 5:00 PM | 4194 | 4197 | As Soon As Possible | NA | 15 | 0d | October 13, 2022 8:00 AM | November 2, 2022 5:00 PM | 15 days | No | 10/13/22 | 11/2/22 | NA | 1
8524 | Complete curriculum outline | October 27, 2022 8:00 AM | November 9, 2022 5:00 PM | 4196 | 4198,4200SS | As Soon As Possible | NA | 10 | 0d | October 27, 2022 8:00 AM | November 9, 2022 5:00 PM | 10 days | No | 10/27/22 | 11/9/22 | NA | 1
8525 | Review with state review team | November 10, 2022 8:00 AM | November 17, 2022 5:00 PM | 4197 | 4199 | As Soon As Possible | NA | 5 | 0d | November 10, 2022 8:00 AM | November 17, 2022 5:00 PM | 5 days | No | 11/10/22 | 11/17/22 | NA | 1
8526 | Review with training advisory group | November 17, 2022 8:00 AM | December 14, 2022 5:00 PM | 4198 | 4204 | As Soon As Possible | NA | 18 | 0d | November 17, 2022 8:00 AM | December 14, 2022 5:00 PM | 18 days | No | 11/17/22 | 12/14/22 | NA | 1
8527 | Develop V1 Training Data Approach | October 27, 2022 8:00 AM | November 9, 2022 5:00 PM | 4197SS | 4201FS-5d | As Soon As Possible | NA | 10 | 0d | October 27, 2022 8:00 AM | November 9, 2022 5:00 PM | 10 days | No | 10/27/22 | 11/9/22 | NA | 1
8528 | Develop Draft Training Approach | November 3, 2022 8:00 AM | November 17, 2022 5:00 PM | 4200FS-5d | 4202FS-1d | As Soon As Possible | NA | 10 | 0d | November 3, 2022 8:00 AM | November 17, 2022 5:00 PM | 10 days | No | 11/3/22 | 11/17/22 | NA | 1
8529 | Review Draft Training Approach with the State | November 17, 2022 8:00 AM | November 23, 2022 5:00 PM | 4201FS-1d | 4203 | As Soon As Possible | NA | 5 | 0d | November 17, 2022 8:00 AM | November 23, 2022 5:00 PM | 5 days | No | 11/17/22 | 11/23/22 | NA | 1
8530 | Review with state advisory group | November 28, 2022 8:00 AM | December 14, 2022 5:00 PM | 4202 | 4204 | As Soon As Possible | NA | 13 | 0d | November 28, 2022 8:00 AM | December 14, 2022 5:00 PM | 13 days | No | 11/28/22 | 12/14/22 | NA | 1
8531 | Finalize Training Approach | December 15, 2022 8:00 AM | December 23, 2022 5:00 PM | 4203,4199 | 4205 | As Soon As Possible | NA | 7 | 0d | December 15, 2022 8:00 AM | December 23, 2022 5:00 PM | 7 days | No | 12/15/22 | 12/23/22 | NA | 1
8532 | Update Draft Training Approach based on feedback from State Review | December 20, 2022 8:00 AM | January 3, 2023 5:00 PM | 4204 | 4206 | As Soon As Possible | NA | 9 | 0d | December 20, 2022 8:00 AM | January 3, 2023 5:00 PM | 9 days | No | 12/20/22 | 1/3/23 | NA | 1
8533 | Submit final V1 Training Approach | January 4, 2023 8:00 AM | February 3, 2023 5:00 PM | 4205 | 4208FS-6d | As Soon As Possible | NA | 22 | 0d | January 4, 2023 8:00 AM | February 3, 2023 5:00 PM | 22 days | No | 1/4/23 | 2/3/23 | NA | 1
8534 | Develop CARES V1 Training Plan - Version 1 | December 21, 2022 8:00 AM | March 30, 2023 5:00 PM |  |  | As Soon As Possible | NA | 68 | 0d | December 21, 2022 8:00 AM | March 30, 2023 5:00 PM | 68 days | No | 12/21/22 | 3/30/23 | NA | 1
8535 | Develop Training Curriculum Plan | December 21, 2022 8:00 AM | February 22, 2023 5:00 PM | 4206FS-6d | 4209SS | As Soon As Possible | NA | 42 | 0d | December 21, 2022 8:00 AM | February 22, 2023 5:00 PM | 42 days | No | 12/21/22 | 2/22/23 | NA | 1
8536 | Determine overall purpose and scope | December 21, 2022 8:00 AM | January 9, 2023 5:00 PM | 4208SS | 4210FS+7d | As Soon As Possible | NA | 12 | 0d | December 21, 2022 8:00 AM | January 9, 2023 5:00 PM | 12 days | No | 12/21/22 | 1/9/23 | NA | 1
8537 | Review with state review teams | January 20, 2023 8:00 AM | January 27, 2023 5:00 PM | 4209FS+7d | 4211FS-8d | As Soon As Possible | NA | 6 | 0d | January 20, 2023 8:00 AM | January 27, 2023 5:00 PM | 6 days | No | 1/20/23 | 1/27/23 | NA | 1
8538 | Review with training advisory group | January 18, 2023 8:00 AM | January 26, 2023 5:00 PM | 4210FS-8d | 4212 | As Soon As Possible | NA | 7 | 0d | January 18, 2023 8:00 AM | January 26, 2023 5:00 PM | 7 days | No | 1/18/23 | 1/26/23 | NA | 1
8539 | Determine training methodology, approach and timeline | January 27, 2023 8:00 AM | February 1, 2023 5:00 PM | 4211 | 4213SS | As Soon As Possible | NA | 4 | 0d | January 27, 2023 8:00 AM | February 1, 2023 5:00 PM | 4 days | No | 1/27/23 | 2/1/23 | NA | 1
8540 | Determine assumptions, risks and constraints with mitigations | January 27, 2023 8:00 AM | February 2, 2023 5:00 PM | 4212SS | 4214FS-15d | As Soon As Possible | NA | 5 | 0d | January 27, 2023 8:00 AM | February 2, 2023 5:00 PM | 5 days | No | 1/27/23 | 2/2/23 | NA | 1
8541 | Develop style guide and design of training materials | January 10, 2023 8:00 AM | February 10, 2023 5:00 PM | 4213FS-15d | 4215FS-5d | As Soon As Possible | NA | 23 | 0d | January 10, 2023 8:00 AM | February 10, 2023 5:00 PM | 23 days | No | 1/10/23 | 2/10/23 | NA | 1
8542 | Develop Training Journey Map | January 25, 2023 8:00 AM | February 22, 2023 5:00 PM | 4214FS-5d | 4216 | As Soon As Possible | NA | 20 | 0d | January 25, 2023 8:00 AM | February 22, 2023 5:00 PM | 20 days | No | 1/25/23 | 2/22/23 | NA | 1
8543 | Review with state review teams | February 23, 2023 8:00 AM | March 1, 2023 5:00 PM | 4215 | 4217 | As Soon As Possible | NA | 5 | 0d | February 23, 2023 8:00 AM | March 1, 2023 5:00 PM | 5 days | No | 2/23/23 | 3/1/23 | NA | 1
8544 | Review with training advisory group | March 2, 2023 8:00 AM | March 8, 2023 5:00 PM | 4216 | 4218 | As Soon As Possible | NA | 5 | 0d | March 2, 2023 8:00 AM | March 8, 2023 5:00 PM | 5 days | No | 3/2/23 | 3/8/23 | NA | 1
8545 | Determine review and feedback process and schedule | March 2, 2023 8:00 AM | March 9, 2023 5:00 PM | 4217 | 4219SS | As Soon As Possible | NA | 6 | 0d | March 2, 2023 8:00 AM | March 9, 2023 5:00 PM | 6 days | No | 3/2/23 | 3/9/23 | NA | 1
8546 | Determine training delivery plan | March 2, 2023 8:00 AM | March 15, 2023 5:00 PM | 4218SS | 4220FS-30d | As Soon As Possible | NA | 10 | 0d | March 2, 2023 8:00 AM | March 15, 2023 5:00 PM | 10 days | No | 3/2/23 | 3/15/23 | NA | 1
8547 | Determine data approach for training environment | February 1, 2023 8:00 AM | February 15, 2023 5:00 PM | 4219FS-30d | 4221SS | As Soon As Possible | NA | 11 | 0d | February 1, 2023 8:00 AM | February 15, 2023 5:00 PM | 11 days | No | 2/1/23 | 2/15/23 | NA | 1
8548 | Determine tools for training material development | February 1, 2023 8:00 AM | February 10, 2023 5:00 PM | 4220SS | 4222FS-18d | As Soon As Possible | NA | 8 | 0d | February 1, 2023 8:00 AM | February 10, 2023 5:00 PM | 8 days | No | 2/1/23 | 2/10/23 | NA | 1
8549 | Develop the e-learning plan for development and delivery | January 18, 2023 8:00 AM | February 10, 2023 5:00 PM | 4221FS-18d | 4223FS+5d | As Soon As Possible | NA | 18 | 0d | January 18, 2023 8:00 AM | February 10, 2023 5:00 PM | 18 days | No | 1/18/23 | 2/10/23 | NA | 1
8550 | Review with state review teams | February 21, 2023 8:00 AM | February 28, 2023 5:00 PM | 4222FS+5d | 4224 | As Soon As Possible | NA | 6 | 0d | February 21, 2023 8:00 AM | February 28, 2023 5:00 PM | 6 days | No | 2/21/23 | 2/28/23 | NA | 1
8551 | Review with training advisory group | February 28, 2023 8:00 AM | March 22, 2023 5:00 PM | 4223 | 4225FS+2d | As Soon As Possible | NA | 17 | 0d | February 28, 2023 8:00 AM | March 22, 2023 5:00 PM | 17 days | No | 2/28/23 | 3/22/23 | NA | 1
8552 | Present CWS-CARES V1 Training Plan to ELT | March 27, 2023 8:00 AM | March 27, 2023 5:00 PM | 4224FS+2d | 4226FS-1d | As Soon As Possible | NA | 1 | 0d | March 27, 2023 8:00 AM | March 27, 2023 5:00 PM | 1 | No | 3/27/23 | 3/27/23 | NA | 1
8553 | Complete V1 Training Plan Draft | March 27, 2023 8:00 AM | March 29, 2023 5:00 PM | 4225FS-1d | 4227SS | As Soon As Possible | NA | 3 | 0d | March 27, 2023 8:00 AM | March 29, 2023 5:00 PM | 3 days | No | 3/27/23 | 3/29/23 | NA | 1
8554 | Review V1 Training Plan Draft with State | March 27, 2023 8:00 AM | March 29, 2023 5:00 PM | 4226SS | 4228 | As Soon As Possible | NA | 3 | 0d | March 27, 2023 8:00 AM | March 29, 2023 5:00 PM | 3 days | No | 3/27/23 | 3/29/23 | NA | 1
8555 | Finalize CWS-CARES V1 Training Plan | March 30, 2023 8:00 AM | March 30, 2023 5:00 PM | 4227 | 4229,4231FS+93d | As Soon As Possible | NA | 1 | 0d | March 30, 2023 8:00 AM | March 30, 2023 5:00 PM | 1 | No | 3/30/23 | 3/30/23 | NA | 1
8556 | SPR 6 - Training Plan Update (CWS - CARES V1) | March 30, 2023 5:00 PM | March 30, 2023 5:00 PM | 4228 | 4231 | As Soon As Possible | NA | 0 | 0d | March 30, 2023 5:00 PM | March 30, 2023 5:00 PM | 0 days | Yes | 3/30/23 | 3/30/23 | 3/30/23 | 1
8557 | Develop CARES V1 Training Plan - Version 2 | August 14, 2023 8:00 AM | May 9, 2024 5:00 PM |  |  | As Soon As Possible | NA | 185 | 0d | August 14, 2023 8:00 AM | May 9, 2024 5:00 PM | 185 days | No | 8/14/23 | 5/9/24 | NA | 1
8558 | Review V1 Training Plan - Version 1 and identify initial gaps and updates | August 14, 2023 8:00 AM | October 2, 2023 5:00 PM | 4228FS+93d,4229 | 4232FS+14d | As Soon As Possible | NA | 35 | 0d | August 14, 2023 8:00 AM | October 2, 2023 5:00 PM | 35 days | No | 8/14/23 | 10/2/23 | NA | 1
8559 | Create outline with updated content based on gaps | October 23, 2023 8:00 AM | October 27, 2023 5:00 PM | 4231FS+14d | 4233 | As Soon As Possible | NA | 5 | 0d | October 23, 2023 8:00 AM | October 27, 2023 5:00 PM | 5 days | No | 10/23/23 | 10/27/23 | NA | 1
8560 | Review outline of recommended updates on content with State Training Team and Leadership Team | October 30, 2023 8:00 AM | November 3, 2023 5:00 PM | 4232 | 4234 | As Soon As Possible | NA | 5 | 0d | October 30, 2023 8:00 AM | November 3, 2023 5:00 PM | 5 days | No | 10/30/23 | 11/3/23 | NA | 1
8561 | Draft updated content based on outline | November 6, 2023 8:00 AM | December 15, 2023 5:00 PM | 4233 | 4235 | As Soon As Possible | NA | 27 | 0d | November 6, 2023 8:00 AM | December 15, 2023 5:00 PM | 27 days | No | 11/6/23 | 12/15/23 | NA | 1
8562 | Edit/validate all updates | December 18, 2023 8:00 AM | December 20, 2023 5:00 PM | 4234 | 4236 | As Soon As Possible | NA | 3 | 0d | December 18, 2023 8:00 AM | December 20, 2023 5:00 PM | 3 days | No | 12/18/23 | 12/20/23 | NA | 1
8563 | Review updated Training Plan with Internal Team | December 21, 2023 8:00 AM | December 22, 2023 5:00 PM | 4235 | 4237FS+4d | As Soon As Possible | NA | 2 | 0d | December 21, 2023 8:00 AM | December 22, 2023 5:00 PM | 2 days | No | 12/21/23 | 12/22/23 | NA | 1
8564 | Review updated Training Plan with State Training Leads | January 2, 2024 8:00 AM | January 18, 2024 5:00 PM | 4236FS+4d | 4238FF | As Soon As Possible | NA | 12 | 0d | January 2, 2024 8:00 AM | January 18, 2024 5:00 PM | 12 days | No | 1/2/24 | 1/18/24 | NA | 1
8565 | Incorporate feedback/comments from State Training Leads | January 8, 2024 8:00 AM | January 18, 2024 5:00 PM | 4237FF | 4239FS-4d | As Soon As Possible | NA | 8 | 0d | January 8, 2024 8:00 AM | January 18, 2024 5:00 PM | 8 days | No | 1/8/24 | 1/18/24 | NA | 1
8566 | Review updated Training Plan with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | January 12, 2024 8:00 AM | January 19, 2024 5:00 PM | 4238FS-4d | 4240 | As Soon As Possible | NA | 5 | 0d | January 12, 2024 8:00 AM | January 19, 2024 5:00 PM | 5 days | No | 1/12/24 | 1/19/24 | NA | 1
8567 | Incorporate feedback/comments from State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | January 22, 2024 8:00 AM | March 15, 2024 5:00 PM | 4239 | 4241 | As Soon As Possible | NA | 39 | 0d | January 22, 2024 8:00 AM | March 15, 2024 5:00 PM | 39 days | No | 1/22/24 | 3/15/24 | NA | 1
8568 | Review updated Training Plan with RACI required reviewers | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 4240 | 4242 | As Soon As Possible | NA | 5 | 0d | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 5 days | No | 3/11/24 | 3/15/24 | NA | 1
8569 | Incorporate feedback/comments from RACI team | March 18, 2024 8:00 AM | March 18, 2024 5:00 PM | 4241 | 4243 | As Soon As Possible | NA | 1 | 0d | March 18, 2024 8:00 AM | March 18, 2024 5:00 PM | 1 | No | 3/18/24 | 3/18/24 | NA | 1
8570 | Prepare PPT for ELT and send with draft Training Plan and all accompanying documents | March 19, 2024 8:00 AM | March 21, 2024 5:00 PM | 4242 | 4244FS+10d,4245FF | As Soon As Possible | NA | 3 | 0d | March 19, 2024 8:00 AM | March 21, 2024 5:00 PM | 3 days | No | 3/19/24 | 3/21/24 | NA | 1
8571 | Present Training Plan Version 2 to ELT | April 8, 2024 8:00 AM | April 8, 2024 5:00 PM | 4243FS+10d | 4246 | As Soon As Possible | NA | 1 | 0d | April 8, 2024 8:00 AM | April 8, 2024 5:00 PM | 1 | No | 4/8/24 | 4/8/24 | NA | 1
8572 | Send Training Plan to ELT with all accompanying documents | March 21, 2024 8:00 AM | March 21, 2024 5:00 PM | 4243FF | 4246 | As Soon As Possible | NA | 1 | 0d | March 21, 2024 8:00 AM | March 21, 2024 5:00 PM | 1 | No | 3/21/24 | 3/21/24 | NA | 1
8573 | Incorporate ELT feedback and finalize | April 9, 2024 8:00 AM | May 8, 2024 5:00 PM | 4244,4245 | 4247 | As Soon As Possible | NA | 22 | 0d | April 9, 2024 8:00 AM | May 8, 2024 5:00 PM | 22 days | No | 4/9/24 | 5/8/24 | NA | 1
8574 | CARES V1 Training Plan - Version 2: Send PMO the ADA version | May 9, 2024 8:00 AM | May 9, 2024 5:00 PM | 4246 | 4925,4249FS+151d | As Soon As Possible | NA | 1 | 0d | May 9, 2024 8:00 AM | May 9, 2024 5:00 PM | 1 | No | 5/9/24 | 5/9/24 | NA | 1
12558 | Develop CARES V1 Training Plan - Version 3 | December 16, 2024 8:00 AM | August 20, 2025 5:00 PM |  |  | As Soon As Possible | NA | 171 | 0d | NA | NA | 0 days? | No | 12/16/24 | 8/20/25 | NA | 1
12559 | Review V1 Training Plan - Version 1 and identify initial gaps and updates | December 16, 2024 8:00 AM | January 8, 2025 5:00 PM | 4247FS+151d | 4250 | As Soon As Possible | NA | 16 | 0d | NA | NA | 0 days? | No | 12/16/24 | 1/8/25 | NA | 1
12560 | Create outline with updated content based on gaps | January 9, 2025 8:00 AM | January 15, 2025 5:00 PM | 4249 | 4251 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 1/9/25 | 1/15/25 | NA | 1
12561 | Review outline of recommended updates on content with State Training Team and Leadership Team | January 16, 2025 8:00 AM | January 22, 2025 5:00 PM | 4250 | 4252 | As Soon As Possible | NA | 4 | 0d | NA | NA | 0 days? | No | 1/16/25 | 1/22/25 | NA | 1
12562 | Draft updated content based on outline | January 23, 2025 8:00 AM | February 5, 2025 5:00 PM | 4251 | 4255,4253 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 1/23/25 | 2/5/25 | NA | 1
13056 | Design V1 Training Plan | February 6, 2025 8:00 AM | March 6, 2025 5:00 PM | 4252 | 4254 | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/6/25 | 3/6/25 | NA | 1
13057 | Develop V1 Training Plan | March 7, 2025 8:00 AM | May 30, 2025 5:00 PM | 4253 | 4255SS+55d | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 3/7/25 | 5/30/25 | NA | 1
12563 | Edit/validate all updates | May 27, 2025 8:00 AM | June 2, 2025 5:00 PM | 4252,4254SS+55d | 4256 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 5/27/25 | 6/2/25 | NA | 1
12564 | Review updated Training Plan with Internal Team | June 3, 2025 8:00 AM | June 6, 2025 5:00 PM | 4255 | 4257FS+2d,4259FS+2d | As Soon As Possible | NA | 4 | 0d | NA | NA | 0 days? | No | 6/3/25 | 6/6/25 | NA | 1
12565 | Review updated Training Plan with State Training Leads | June 11, 2025 8:00 AM | June 17, 2025 5:00 PM | 4256FS+2d | 4258,4261SS | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 6/11/25 | 6/17/25 | NA | 1
12566 | Incorporate feedback/comments from State Training Leads | June 18, 2025 8:00 AM | June 18, 2025 5:00 PM | 4257 |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/18/25 | 6/18/25 | NA | 1
12567 | Review updated Training Plan with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | June 11, 2025 8:00 AM | June 17, 2025 5:00 PM | 4256FS+2d | 4260,4261SS,4263 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 6/11/25 | 6/17/25 | NA | 1
12568 | Incorporate feedback/comments from State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | June 18, 2025 8:00 AM | June 18, 2025 5:00 PM | 4259 |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/18/25 | 6/18/25 | NA | 1
12569 | Review updated Training Plan with RACI required reviewers | June 11, 2025 8:00 AM | June 17, 2025 5:00 PM | 4257SS,4259SS | 4262 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 6/11/25 | 6/17/25 | NA | 1
12570 | Incorporate feedback/comments from RACI team | June 18, 2025 8:00 AM | June 18, 2025 5:00 PM | 4261 |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/18/25 | 6/18/25 | NA | 1
12571 | Prepare PPT for ELT and send with draft Training Plan Version 3 and all accompanying documents | June 18, 2025 8:00 AM | June 19, 2025 5:00 PM | 4259 | 4265FF | As Soon As Possible | NA | 2 | 0d | NA | NA | 0 days? | No | 6/18/25 | 6/19/25 | NA | 1
12572 | Present Training Plan Version 3 to ELT | June 23, 2025 8:00 AM | June 23, 2025 5:00 PM | 4265FS+1d | 4266 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/23/25 | 6/23/25 | NA | 1
12573 | Send Training Plan Version 3 to ELT with all accompanying documents | June 19, 2025 8:00 AM | June 19, 2025 5:00 PM | 4263FF | 4264FS+1d | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/19/25 | 6/19/25 | NA | 1
13679 | ELT Review and Feedback of Training Plan Version 3 | June 24, 2025 8:00 AM | July 18, 2025 5:00 PM | 4264 | 4267SS+18d | As Soon As Possible | NA | 18 | 0d | NA | NA | 0 days? | No | 6/24/25 | 7/18/25 | NA | 1
12574 | Incorporate ELT feedback and finalize | July 21, 2025 8:00 AM | July 23, 2025 5:00 PM | 4266SS+18d | 4268 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 7/21/25 | 7/23/25 | NA | 1
13680 | Route and Review Training Plan Version 3 with Counties | July 24, 2025 8:00 AM | August 6, 2025 5:00 PM | 4267 | 4269 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/24/25 | 8/6/25 | NA | 1
13681 | Incorporate Feedback From Counties | August 7, 2025 8:00 AM | August 13, 2025 5:00 PM | 4268 | 4270 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 8/7/25 | 8/13/25 | NA | 1
13682 | ELT Review and approval of County updates | August 14, 2025 8:00 AM | August 18, 2025 5:00 PM | 4269 | 4271FF | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 8/14/25 | 8/18/25 | NA | 1
13683 | ELT approval of Training Plan Version 3 | August 18, 2025 8:00 AM | August 18, 2025 5:00 PM | 4270FF | 4272FS+1d | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 8/18/25 | 8/18/25 | NA | 1
12575 | CARES V1 Training Plan - Version 3: Send PMO the ADA version | August 20, 2025 8:00 AM | August 20, 2025 5:00 PM | 4271FS+1d | 4925 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 8/20/25 | 8/20/25 | NA | 1
13667 | Develop, Review, and Finalize Implementation Organizations Training Plan | July 1, 2025 8:00 AM | February 27, 2026 5:00 PM |  |  | As Soon As Possible | NA | 166 | 406d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.56000000000000005
13668 | Conduct Implementation Organizations Training Plan meetings – Part I | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 4275,4277SS | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
13669 | Conduct Implementation Organizations Training Plan meetings – Part II | August 11, 2025 8:00 AM | September 19, 2025 5:00 PM | 4274 | 4276 | As Soon As Possible | NA | 29 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/19/25 | NA | 1
13670 | Conduct Implementation Organizations Training Plan meetings – Part III | September 22, 2025 8:00 AM | October 31, 2025 5:00 PM | 4275 | 4280 | As Soon As Possible | NA | 30 | 406d | NA | NA | 0 days? | No | 9/22/25 | NA | NA | 0.5
13671 | Draft Implementation Organizations Training Plans – Part I | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM | 4274SS | 4278 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
13672 | Draft Implementation Organizations Training Plans – Part II | August 11, 2025 8:00 AM | September 19, 2025 5:00 PM | 4277 | 4279 | As Soon As Possible | NA | 29 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/19/25 | NA | 1
13673 | Draft Implementation Organizations Training Plans – Part III | September 22, 2025 8:00 AM | October 31, 2025 5:00 PM | 4278 | 4280 | As Soon As Possible | NA | 30 | 406d | NA | NA | 0 days? | No | 9/22/25 | NA | NA | 0.5
13674 | Draft Implementation Organizations Training Plans – Part IV | November 3, 2025 8:00 AM | December 12, 2025 5:00 PM | 4276,4279 | 4281 | As Soon As Possible | NA | 28 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
13675 | Complete Draft Implementation Organizations Training Plans | December 15, 2025 8:00 AM | December 19, 2025 5:00 PM | 4280 | 4282FS+8d | As Soon As Possible | NA | 5 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
13676 | Review Implementation Organizations Training Plans | January 5, 2026 8:00 AM | February 13, 2026 5:00 PM | 4281FS+8d | 4283SS+19d | As Soon As Possible | NA | 29 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
13677 | Finalize Implementation Organizations Training Plans | February 2, 2026 8:00 AM | February 26, 2026 5:00 PM | 4282SS+19d | 4284 | As Soon As Possible | NA | 18 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
13678 | Complete Implementation Organizations Training Plans | February 27, 2026 8:00 AM | February 27, 2026 5:00 PM | 4283 |  | As Soon As Possible | NA | 1 | 406d | NA | NA | 0 s? | No | NA | NA | NA | 0
8575 | Fresno Support Plan - Training | March 16, 2023 8:00 AM | May 3, 2023 5:00 PM |  |  | As Soon As Possible | NA | 34 | 0d | March 16, 2023 8:00 AM | May 3, 2023 5:00 PM | 34 days | No | 3/16/23 | 5/3/23 | NA | 1
8576 | Initial Planning - Training | March 16, 2023 8:00 AM | April 5, 2023 5:00 PM |  |  | As Soon As Possible | NA | 14 | 0d | March 16, 2023 8:00 AM | April 5, 2023 5:00 PM | 14 days | No | 3/16/23 | 4/5/23 | NA | 1
8577 | Obtain list of training participants and their roles | March 16, 2023 8:00 AM | March 30, 2023 5:00 PM | 3192 | 4288,4289,5049FS-2d | As Soon As Possible | NA | 11 | 0d | March 16, 2023 8:00 AM | March 30, 2023 5:00 PM | 11 days | No | 3/16/23 | 3/30/23 | NA | 1
8578 | Conduct High-level gap analysis of typical RFA training vs. what the Org needs/expects and any tailoring required for Fresno-specific business practices | March 31, 2023 8:00 AM | March 31, 2023 5:00 PM | 4287 | 4291 | As Soon As Possible | NA | 0 | 0d | March 31, 2023 8:00 AM | March 31, 2023 5:00 PM | 0 days | Yes | 3/31/23 | 3/31/23 | NA | 1
8579 | Plan and execute onsite training coordination | March 31, 2023 8:00 AM | April 5, 2023 5:00 PM | 4287 | 4292 | As Soon As Possible | NA | 3 | 0d | March 31, 2023 8:00 AM | April 5, 2023 5:00 PM | 3 days | No | 3/31/23 | 4/5/23 | NA | 1
8580 | Training | March 27, 2023 8:00 AM | April 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 24 | 0d | March 27, 2023 8:00 AM | April 28, 2023 5:00 PM | 24 days | No | 3/27/23 | 4/28/23 | NA | 1
8581 | Develop in-person training for Fresno RFA Staff to be delivered in-person with coaching to promote adoption and usage (Emphasize: Uploading documents, and creating tasks, activities and meetings. Emergency Placement workflow in CARES RFA) | April 3, 2023 8:00 AM | April 21, 2023 5:00 PM | 4288 | 4292SS+5d,4293SS-4d | As Soon As Possible | NA | 15 | 0d | April 3, 2023 8:00 AM | April 21, 2023 5:00 PM | 15 days | No | 4/3/23 | 4/21/23 | NA | 1
8582 | Develop training environment data and applications to meet in-person training for Fresno RFA staff | April 10, 2023 8:00 AM | April 21, 2023 5:00 PM | 4291SS+5d,4289 | 4296 | As Soon As Possible | NA | 10 | 0d | April 10, 2023 8:00 AM | April 21, 2023 5:00 PM | 10 days | No | 4/10/23 | 4/21/23 | NA | 1
8583 | Review and Update current training quick guides for RFA (simplify with more screen shots rather than written instruction) | March 27, 2023 8:00 AM | April 21, 2023 5:00 PM | 4291SS-4d | 4294FS-3d | As Soon As Possible | NA | 19 | 0d | March 27, 2023 8:00 AM | April 21, 2023 5:00 PM | 19 days | No | 3/27/23 | 4/21/23 | NA | 1
8584 | Develop a baseline survey for Determining Proficiency | April 19, 2023 8:00 AM | April 28, 2023 5:00 PM | 4293FS-3d | 4305 | As Soon As Possible | NA | 8 | 0d | April 19, 2023 8:00 AM | April 28, 2023 5:00 PM | 8 days | No | 4/19/23 | 4/28/23 | NA | 1
8585 | Training Survey - Training | April 24, 2023 8:00 AM | May 3, 2023 5:00 PM |  |  | As Soon As Possible | NA | 8 | 0d | April 24, 2023 8:00 AM | May 3, 2023 5:00 PM | 8 days | No | 4/24/23 | 5/3/23 | NA | 1
8586 | Provide After Training Support | April 24, 2023 8:00 AM | May 3, 2023 5:00 PM | 4292 | 4305 | As Soon As Possible | NA | 8 | 0d | April 24, 2023 8:00 AM | May 3, 2023 5:00 PM | 8 days | No | 4/24/23 | 5/3/23 | NA | 1
8587 | Development Training Materials | February 2, 2023 8:00 AM | June 11, 2026 5:00 PM |  |  | As Soon As Possible | NA | 842 | 334d | February 2, 2023 8:00 AM | March 27, 2026 5:00 PM | 790 days | No | 2/2/23 | NA | NA | 0.78000000000000003
8588 | Participate in Inception Meetings | February 2, 2023 8:00 AM | June 11, 2026 5:00 PM |  |  | As Soon As Possible | NA | 842 | 334d | February 2, 2023 8:00 AM | March 27, 2026 5:00 PM | 790 days | No | 2/2/23 | NA | NA | 0.78000000000000003
8589 | Service Provider Profile/Services | March 13, 2023 8:00 AM | April 17, 2023 5:00 PM |  |  | As Soon As Possible | NA | 25 | 0d | March 13, 2023 8:00 AM | April 17, 2023 5:00 PM | 25 days | No | 3/13/23 | 4/17/23 | NA | 1
8590 | Develop scope of Module | March 13, 2023 8:00 AM | April 17, 2023 5:00 PM | 3192SS+194d | 4305 | As Soon As Possible | NA | 25 | 0d | March 13, 2023 8:00 AM | April 17, 2023 5:00 PM | 25 days | No | 3/13/23 | 4/17/23 | NA | 1
8614 | Setup myTailhead Training Environment | February 2, 2023 8:00 AM | June 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 102 | 0d | February 2, 2023 8:00 AM | June 28, 2023 5:00 PM | 102 days | No | 2/2/23 | 6/28/23 | NA | 1
8615 | Setup the Access | February 2, 2023 8:00 AM | February 17, 2023 5:00 PM | 3192 | 4303SS+6d | As Soon As Possible | NA | 12 | 0d | February 2, 2023 8:00 AM | February 17, 2023 5:00 PM | 12 days | No | 2/2/23 | 2/17/23 | NA | 1
8616 | Collaborate with Enterprise Architect to Setup Training Environment for Training Team | February 10, 2023 8:00 AM | June 28, 2023 5:00 PM | 4302SS+6d | 4305FS+9d | As Soon As Possible | NA | 96 | 0d | February 10, 2023 8:00 AM | June 28, 2023 5:00 PM | 96 days | No | 2/10/23 | 6/28/23 | NA | 1
8617 | Develop CARES Global Programs | July 13, 2023 8:00 AM | March 13, 2026 5:00 PM |  |  | As Soon As Possible | NA | 669 | 396d | July 13, 2023 8:00 AM | February 27, 2026 5:00 PM | 659 days | No | 7/13/23 | NA | NA | 0.80000000000000004
11499 | CARES Basics | July 13, 2023 8:00 AM | March 13, 2026 5:00 PM | 4303FS+9d,4294,4296,4300 | 4306SS | As Soon As Possible | NA | 669 | 396d | July 13, 2023 8:00 AM | February 27, 2026 5:00 PM | 659 days | No | 7/13/23 | NA | NA | 0.83999999999999997
11500 | CARES Navigation | July 13, 2023 8:00 AM | March 13, 2026 5:00 PM | 4305SS | 4925 | As Soon As Possible | NA | 669 | 376d | July 13, 2023 8:00 AM | February 27, 2026 5:00 PM | 659 days | No | 7/13/23 | NA | NA | 0.83999999999999997
8634 | Addresses Module | September 20, 2023 8:00 AM | February 9, 2024 5:00 PM | 4349FS-4d | 4311 | As Soon As Possible | NA | 97 | 0d | September 20, 2023 8:00 AM | February 9, 2024 5:00 PM | 97 days | No | 9/20/23 | 2/9/24 | NA | 1
8635 | Persons Overview | January 16, 2024 8:00 AM | May 31, 2024 5:00 PM | 4351 | 4309SS,4316SS+6d | As Soon As Possible | NA | 96 | 0d | January 16, 2024 8:00 AM | May 31, 2024 5:00 PM | 96 days | No | 1/16/24 | 5/31/24 | NA | 1
8636 | Persons Records | January 16, 2024 8:00 AM | June 14, 2024 5:00 PM | 4352,4308SS | 4329,4310SS+9d,4317 | As Soon As Possible | NA | 106 | 0d | January 16, 2024 8:00 AM | June 14, 2024 5:00 PM | 106 days | No | 1/16/24 | 6/14/24 | NA | 1
11507 | Approval/Audit History | January 29, 2024 8:00 AM | March 13, 2026 5:00 PM | 4309SS+9d | 4925 | As Soon As Possible | NA | 534 | 376d | January 29, 2024 8:00 AM | February 27, 2026 5:00 PM | 524 days | No | 1/29/24 | NA | NA | 0.81000000000000005
11506 | Person(s) | April 16, 2024 8:00 AM | March 13, 2026 5:00 PM | 4307 | 4312SS | As Soon As Possible | NA | 480 | 396d | April 16, 2024 8:00 AM | July 26, 2024 5:00 PM | 72 days | No | 4/16/24 | NA | NA | 0.78000000000000003
11505 | Contact Log and Tribal Inquiries | April 16, 2024 8:00 AM | March 13, 2026 5:00 PM | 4311SS | 4313SS | As Soon As Possible | NA | 480 | 396d | April 16, 2024 8:00 AM | July 26, 2024 5:00 PM | 72 days | No | 4/16/24 | NA | NA | 0.78000000000000003
11503 | Task | April 16, 2024 8:00 AM | March 13, 2026 5:00 PM | 4312SS | 4314SS | As Soon As Possible | NA | 480 | 396d | April 16, 2024 8:00 AM | July 26, 2024 5:00 PM | 72 days | No | 4/16/24 | NA | NA | 0.78000000000000003
11502 | Documents | April 16, 2024 8:00 AM | March 13, 2026 5:00 PM | 4313SS | 4315SS | As Soon As Possible | NA | 480 | 396d | April 16, 2024 8:00 AM | July 26, 2024 5:00 PM | 72 days | No | 4/16/24 | NA | NA | 0.78000000000000003
11501 | Case Management Engagement: Family Transfer Request | April 16, 2024 8:00 AM | March 13, 2026 5:00 PM | 4314SS | 4925 | As Soon As Possible | NA | 480 | 376d | April 16, 2024 8:00 AM | July 26, 2024 5:00 PM | 72 days | No | 4/16/24 | NA | NA | 0.78000000000000003
13060 | Supervisor Assign Secondary | January 24, 2025 8:00 AM | March 13, 2026 5:00 PM | 4308SS+6d | 4925 | As Soon As Possible | NA | 285 | 376d | NA | NA | 0 days? | No | 1/24/25 | NA | NA | 0.64000000000000001
13061 | Addresses - Holistic | December 17, 2024 8:00 AM | March 13, 2026 5:00 PM | 4309 | 4925 | As Soon As Possible | NA | 310 | 376d | NA | NA | 0 days? | No | 12/17/24 | NA | NA | 0.66000000000000003
8644 | Screening | February 27, 2023 8:00 AM | March 7, 2024 5:00 PM |  |  | As Soon As Possible | NA | 258 | 0d | February 27, 2023 8:00 AM | March 7, 2024 5:00 PM | 258 days | No | 2/27/23 | 3/7/24 | NA | 1
8661 | Screening Modules | February 27, 2023 8:00 AM | February 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 235 | 0d | February 27, 2023 8:00 AM | February 2, 2024 5:00 PM | 235 days | No | 2/27/23 | 2/2/24 | NA | 1
8662 | Screening Discovery | February 27, 2023 8:00 AM | March 24, 2023 5:00 PM | 3192 | 4321,4322 | Start No Earlier Than | 2/27/23 | 20 | 0d | February 27, 2023 8:00 AM | March 24, 2023 5:00 PM | 20 days | No | 2/27/23 | 3/24/23 | NA | 1
8663 | Screening Overview Module | March 27, 2023 8:00 AM | May 5, 2023 5:00 PM | 4320 | 4323 | As Soon As Possible | NA | 29 | 0d | March 27, 2023 8:00 AM | May 5, 2023 5:00 PM | 29 days | No | 3/27/23 | 5/5/23 | NA | 1
8664 | Screening Page Module | March 27, 2023 8:00 AM | May 5, 2023 5:00 PM | 4320 | 4323,4324,4325,4326,4327,4328 | As Soon As Possible | NA | 29 | 0d | March 27, 2023 8:00 AM | May 5, 2023 5:00 PM | 29 days | No | 3/27/23 | 5/5/23 | NA | 1
8665 | Screening Add Persons Module | May 8, 2023 8:00 AM | June 16, 2023 5:00 PM | 4322,4321 | 4324SS | As Soon As Possible | NA | 29 | 0d | May 8, 2023 8:00 AM | June 16, 2023 5:00 PM | 29 days | No | 5/8/23 | 6/16/23 | NA | 1
8666 | Screening Address Module | May 8, 2023 8:00 AM | June 16, 2023 5:00 PM | 4322,4323SS | 4325SS | As Soon As Possible | NA | 29 | 0d | May 8, 2023 8:00 AM | June 16, 2023 5:00 PM | 29 days | No | 5/8/23 | 6/16/23 | NA | 1
8667 | Screening Add Allegations Module | May 8, 2023 8:00 AM | June 16, 2023 5:00 PM | 4322,4324SS | 4326SS | As Soon As Possible | NA | 29 | 0d | May 8, 2023 8:00 AM | June 16, 2023 5:00 PM | 29 days | No | 5/8/23 | 6/16/23 | NA | 1
8668 | Welcome to CARES myTrailhead Module | May 8, 2023 8:00 AM | June 16, 2023 5:00 PM | 4322,4325SS | 4327SS | As Soon As Possible | NA | 29 | 0d | May 8, 2023 8:00 AM | June 16, 2023 5:00 PM | 29 days | No | 5/8/23 | 6/16/23 | NA | 1
8669 | Identify Safety Alerts Module | May 8, 2023 8:00 AM | June 16, 2023 5:00 PM | 4322,4326SS | 4328SS | As Soon As Possible | NA | 29 | 0d | May 8, 2023 8:00 AM | June 16, 2023 5:00 PM | 29 days | No | 5/8/23 | 6/16/23 | NA | 1
8670 | CARES Basics Module | May 8, 2023 8:00 AM | June 16, 2023 5:00 PM | 4322,4327SS | 4329,4330,4331 | As Soon As Possible | NA | 29 | 0d | May 8, 2023 8:00 AM | June 16, 2023 5:00 PM | 29 days | No | 5/8/23 | 6/16/23 | NA | 1
8671 | Supervisors Review / Promotions Module | June 19, 2023 8:00 AM | July 28, 2023 5:00 PM | 4328,4309 | 4330SS | As Soon As Possible | NA | 29 | 0d | June 19, 2023 8:00 AM | July 28, 2023 5:00 PM | 29 days | No | 6/19/23 | 7/28/23 | NA | 1
8672 | Tribal Inquiry Module | June 19, 2023 8:00 AM | July 28, 2023 5:00 PM | 4328,4329SS | 4331SS | As Soon As Possible | NA | 29 | 0d | June 19, 2023 8:00 AM | July 28, 2023 5:00 PM | 29 days | No | 6/19/23 | 7/28/23 | NA | 1
8673 | Screening Contacts Module | June 19, 2023 8:00 AM | February 2, 2024 5:00 PM | 4328,4330SS | 4332,4333 | As Soon As Possible | NA | 157 | 0d | June 19, 2023 8:00 AM | February 2, 2024 5:00 PM | 157 days | No | 6/19/23 | 2/2/24 | NA | 1
8674 | Screening Safely Surrender Baby Module | July 31, 2023 8:00 AM | September 28, 2023 5:00 PM | 4331 | 4333SS | Finish No Earlier Than | 9/28/23 | 43 | 0d | July 31, 2023 8:00 AM | September 28, 2023 5:00 PM | 43 days | No | 7/31/23 | 9/28/23 | NA | 1
8676 | Screening Assignments Module | July 31, 2023 8:00 AM | August 11, 2023 5:00 PM | 4331,4332SS | 4334FS-2d | Finish No Earlier Than | 8/11/23 | 10 | 0d | July 31, 2023 8:00 AM | August 11, 2023 5:00 PM | 10 days | No | 7/31/23 | 8/11/23 | NA | 1
8677 | Screening Worker Submission Module | August 10, 2023 8:00 AM | September 13, 2023 5:00 PM | 4333FS-2d | 4336 | Finish No Earlier Than | 9/13/23 | 24 | 0d | August 10, 2023 8:00 AM | September 13, 2023 5:00 PM | 24 days | No | 8/10/23 | 9/13/23 | NA | 1
8679 | Module Review and Milestone Completion | December 26, 2023 8:00 AM | March 7, 2024 5:00 PM |  |  | As Soon As Possible | NA | 50 | 0d | December 26, 2023 8:00 AM | March 7, 2024 5:00 PM | 50 days | No | 12/26/23 | 3/7/24 | NA | 1
8680 | Provide review of all CARESV1 Training Material for approval | December 26, 2023 8:00 AM | January 18, 2024 5:00 PM | 4334 | 4337 | Start No Earlier Than | 12/26/23 | 16 | 0d | December 26, 2023 8:00 AM | January 18, 2024 5:00 PM | 16 days | No | 12/26/23 | 1/18/24 | NA | 1
8681 | Provide completed feedback forms according to timelines | January 19, 2024 8:00 AM | January 19, 2024 5:00 PM | 4336 | 4338 | Start No Earlier Than | 1/19/24 | 1 | 0d | January 19, 2024 8:00 AM | January 19, 2024 5:00 PM | 1 | No | 1/19/24 | 1/19/24 | NA | 1
8682 | State Team Final Course Review | January 22, 2024 8:00 AM | February 20, 2024 5:00 PM | 4337 | 4339 | Start No Earlier Than | 1/22/24 | 21 | 0d | January 22, 2024 8:00 AM | February 20, 2024 5:00 PM | 21 days | No | 1/22/24 | 2/20/24 | NA | 1
8683 | State Team Final Sign-Off of Course Material | February 21, 2024 8:00 AM | March 6, 2024 5:00 PM | 4338 | 4340 | Start No Earlier Than | 2/21/24 | 11 | 0d | February 21, 2024 8:00 AM | March 6, 2024 5:00 PM | 11 days | No | 2/21/24 | 3/6/24 | NA | 1
8684 | Milestone Complete | March 7, 2024 8:00 AM | March 7, 2024 5:00 PM | 4339 | 4341 | Start No Earlier Than | 3/7/24 | 1 | 0d | March 7, 2024 8:00 AM | March 7, 2024 5:00 PM | 1 | No | 3/7/24 | 3/7/24 | NA | 1
8692 | Development Training Materials: Screening Completed | March 7, 2024 5:00 PM | March 7, 2024 5:00 PM | 4340 | 4925 | Finish No Earlier Than | 3/7/24 | 0 | 0d | March 7, 2024 5:00 PM | March 7, 2024 5:00 PM | 0 days | Yes | 3/7/24 | 3/7/24 | NA | 1
8693 | Investigations/Engagement | June 16, 2023 8:00 AM | February 23, 2024 5:00 PM |  |  | As Soon As Possible | NA | 172 | 0d | June 16, 2023 8:00 AM | February 23, 2024 5:00 PM | 172 days | No | 6/16/23 | 2/23/24 | NA | 1
8694 | Investigations-Engagement Modules | June 16, 2023 8:00 AM | February 23, 2024 5:00 PM |  |  | As Soon As Possible | NA | 172 | 0d | June 16, 2023 8:00 AM | February 23, 2024 5:00 PM | 172 days | No | 6/16/23 | 2/23/24 | NA | 1
8695 | Investigations/Engagement Discovery | June 16, 2023 8:00 AM | July 21, 2023 5:00 PM | 3192 | 4345FS+32d,4346FS+3d,4349FS+3d,4353FS+13d,4355FS+14d,4347FS+3d | As Soon As Possible | NA | 25 | 0d | June 16, 2023 8:00 AM | July 21, 2023 5:00 PM | 25 days | No | 6/16/23 | 7/21/23 | NA | 1
8712 | Investigations Overview Module | September 7, 2023 8:00 AM | February 23, 2024 5:00 PM | 4344FS+32d | 4357 | As Soon As Possible | NA | 115 | 0d | September 7, 2023 8:00 AM | February 23, 2024 5:00 PM | 115 days | No | 9/7/23 | 2/23/24 | NA | 1
8713 | Homepage - Supervisor Module | July 27, 2023 8:00 AM | November 27, 2023 5:00 PM | 4344FS+3d | 4348SS,4357 | As Soon As Possible | NA | 84 | 0d | July 27, 2023 8:00 AM | November 27, 2023 5:00 PM | 84 days | No | 7/27/23 | 11/27/23 | NA | 1
8714 | Homepage - Worker Module | July 27, 2023 8:00 AM | November 27, 2023 5:00 PM | 4344FS+3d | 4348SS,4357 | As Soon As Possible | NA | 84 | 0d | July 27, 2023 8:00 AM | November 27, 2023 5:00 PM | 84 days | No | 7/27/23 | 11/27/23 | NA | 1
8715 | Investigation Investigative Folio Assignment Module | July 27, 2023 8:00 AM | September 29, 2023 5:00 PM | 4346SS,4347SS | 4356FS+5d,4357 | As Soon As Possible | NA | 46 | 0d | July 27, 2023 8:00 AM | September 29, 2023 5:00 PM | 46 days | No | 7/27/23 | 9/29/23 | NA | 1
8717 | Investigations Review the Investigations Pages-Worker Module | July 27, 2023 8:00 AM | September 29, 2023 5:00 PM | 4344FS+3d | 4307FS-4d,4350FS-11d,4351FS-11d,4352FS-11d,4357 | As Soon As Possible | NA | 46 | 0d | July 27, 2023 8:00 AM | September 29, 2023 5:00 PM | 46 days | No | 7/27/23 | 9/29/23 | NA | 1
8720 | Investigation Documents Module | September 11, 2023 8:00 AM | December 22, 2023 5:00 PM | 4349FS-11d | 4357 | As Soon As Possible | NA | 72 | 0d | September 11, 2023 8:00 AM | December 22, 2023 5:00 PM | 72 days | No | 9/11/23 | 12/22/23 | NA | 1
8721 | Investigation Persons Overview Module | September 11, 2023 8:00 AM | January 12, 2024 5:00 PM | 4349FS-11d | 4308,4357 | As Soon As Possible | NA | 85 | 0d | September 11, 2023 8:00 AM | January 12, 2024 5:00 PM | 85 days | No | 9/11/23 | 1/12/24 | NA | 1
8722 | Investigation Persons Records Module | September 11, 2023 8:00 AM | January 12, 2024 5:00 PM | 4349FS-11d | 4309,4357 | As Soon As Possible | NA | 85 | 0d | September 11, 2023 8:00 AM | January 12, 2024 5:00 PM | 85 days | No | 9/11/23 | 1/12/24 | NA | 1
8723 | Investigation Safely Surrendered Baby Module | August 10, 2023 8:00 AM | October 18, 2023 5:00 PM | 4344FS+13d | 4354FS-5d,4357 | As Soon As Possible | NA | 49 | 0d | August 10, 2023 8:00 AM | October 18, 2023 5:00 PM | 49 days | No | 8/10/23 | 10/18/23 | NA | 1
8724 | Investigation Fatality/Near Fatality | October 12, 2023 8:00 AM | February 22, 2024 5:00 PM | 4353FS-5d | 4357 | As Soon As Possible | NA | 89 | 0d | October 12, 2023 8:00 AM | February 22, 2024 5:00 PM | 89 days | No | 10/12/23 | 2/22/24 | NA | 1
8725 | Investigation Commercial Sexual Exploitation CSEC | August 11, 2023 8:00 AM | January 12, 2024 5:00 PM | 4344FS+14d | 4357 | As Soon As Possible | NA | 105 | 0d | August 11, 2023 8:00 AM | January 12, 2024 5:00 PM | 105 days | No | 8/11/23 | 1/12/24 | NA | 1
8727 | Investigation Determine Allegations | October 9, 2023 8:00 AM | December 22, 2023 5:00 PM | 4348FS+5d | 4357 | As Soon As Possible | NA | 52 | 0d | October 9, 2023 8:00 AM | December 22, 2023 5:00 PM | 52 days | No | 10/9/23 | 12/22/23 | NA | 1
8741 | Investigations/Engagement Completed | February 23, 2024 5:00 PM | February 23, 2024 5:00 PM | 4345,4346,4347,4348,4349,4350,4351,4352,4353,4354,4355,4356 | 4925 | As Soon As Possible | NA | 0 | 0d | February 23, 2024 5:00 PM | February 23, 2024 5:00 PM | 0 days | Yes | 2/23/24 | 2/23/24 | NA | 1
8742 | Investigations/Determination | July 17, 2023 8:00 AM | January 26, 2024 5:00 PM |  |  | As Soon As Possible | NA | 133 | 0d | July 17, 2023 8:00 AM | January 26, 2024 5:00 PM | 133 days | No | 7/17/23 | 1/26/24 | NA | 1
8743 | Investigations/Determination Modules | July 17, 2023 8:00 AM | January 26, 2024 5:00 PM |  |  | As Soon As Possible | NA | 133 | 0d | July 17, 2023 8:00 AM | January 26, 2024 5:00 PM | 133 days | No | 7/17/23 | 1/26/24 | NA | 1
8744 | Investigations/Determination Discovery | July 17, 2023 8:00 AM | August 11, 2023 5:00 PM | 3192 | 4361FS+17d,4362FS+39d,4363FS+39d,4364FS+39d | As Soon As Possible | NA | 20 | 0d | July 17, 2023 8:00 AM | August 11, 2023 5:00 PM | 20 days | No | 7/17/23 | 8/11/23 | NA | 1
8761 | Allegation Conclusion Module | September 7, 2023 8:00 AM | January 12, 2024 5:00 PM | 4360FS+17d | 4365 | As Soon As Possible | NA | 87 | 0d | September 7, 2023 8:00 AM | January 12, 2024 5:00 PM | 87 days | No | 9/7/23 | 1/12/24 | NA | 1
8763 | Investigation Disposition Module | October 9, 2023 8:00 AM | December 15, 2023 5:00 PM | 4360FS+39d | 4365 | As Soon As Possible | NA | 47 | 0d | October 9, 2023 8:00 AM | December 15, 2023 5:00 PM | 47 days | No | 10/9/23 | 12/15/23 | NA | 1
8766 | Worker Submission for Approval Module | October 9, 2023 8:00 AM | December 15, 2023 5:00 PM | 4360FS+39d | 4365 | As Soon As Possible | NA | 47 | 0d | October 9, 2023 8:00 AM | December 15, 2023 5:00 PM | 47 days | No | 10/9/23 | 12/15/23 | NA | 1
8767 | Supervisor Approval Module | October 9, 2023 8:00 AM | January 26, 2024 5:00 PM | 4360FS+39d | 4365 | As Soon As Possible | NA | 74 | 0d | October 9, 2023 8:00 AM | January 26, 2024 5:00 PM | 74 days | No | 10/9/23 | 1/26/24 | NA | 1
8784 | Investigations/Determination Completed | January 26, 2024 5:00 PM | January 26, 2024 5:00 PM | 4361,4362,4363,4364 | 4925 | As Soon As Possible | NA | 0 | 0d | January 26, 2024 5:00 PM | January 26, 2024 5:00 PM | 0 days | Yes | 1/26/24 | 1/26/24 | NA | 1
10500 | Process Areas | May 28, 2024 8:00 AM | May 14, 2026 5:00 PM |  |  | As Soon As Possible | NA | 494 | 353d | June 30, 2023 8:00 AM | February 27, 2026 5:00 PM | 667 days | No | 5/28/24 | NA | NA | 0.72999999999999998
10501 | Case Management | May 28, 2024 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 418 | 429d | June 30, 2023 8:00 AM | December 8, 2025 5:00 PM | 612 days | No | 5/28/24 | NA | NA | 0.84999999999999998
10503 | Group 1 Placement (Milestones 1, 2, 6, 8, 15, 19, 20) | May 28, 2024 8:00 AM | April 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 214 | 0d | May 28, 2024 8:00 AM | March 4, 2025 5:00 PM | 193 days | No | 5/28/24 | 4/3/25 | NA | 1
10535 | Placement: Training | May 28, 2024 8:00 AM | April 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 214 | 0d | May 28, 2024 8:00 AM | March 4, 2025 5:00 PM | 193 days | No | 5/28/24 | 4/3/25 | NA | 1
11088 | End-To-End Business Scenarios - (MS 1,2,6,8) | May 28, 2024 8:00 AM | August 23, 2024 5:00 PM |  |  | As Soon As Possible | NA | 63 | 0d | May 28, 2024 8:00 AM | July 12, 2024 5:00 PM | 33 days | No | 5/28/24 | 8/23/24 | NA | 1
10536 | Develop End-To-End Business Scenarios | May 28, 2024 8:00 AM | June 28, 2024 5:00 PM | 5379SS+10d | 4381,4372FS+12d | As Soon As Possible | NA | 24 | 0d | May 28, 2024 8:00 AM | June 27, 2024 5:00 PM | 23 days | No | 5/28/24 | 6/28/24 | NA | 1
10537 | Review End-To-End Business Scenarios with VPODs | July 18, 2024 8:00 AM | August 16, 2024 5:00 PM | 4371FS+12d | 4373FF+5d | As Soon As Possible | NA | 22 | 0d | June 28, 2024 8:00 AM | July 5, 2024 5:00 PM | 5 days | No | 7/18/24 | 8/16/24 | NA | 1
10538 | Incorporate VPODs Feedback | July 22, 2024 8:00 AM | August 23, 2024 5:00 PM | 4372FF+5d | 4374FF | As Soon As Possible | NA | 25 | 0d | June 28, 2024 8:00 AM | July 5, 2024 5:00 PM | 5 days | No | 7/22/24 | 8/23/24 | NA | 1
10539 | Finalize End-To-End Business Scenarios | July 25, 2024 8:00 AM | August 23, 2024 5:00 PM | 4373FF | 4538,4385 | As Soon As Possible | NA | 22 | 0d | July 8, 2024 8:00 AM | July 12, 2024 5:00 PM | 5 days | No | 7/25/24 | 8/23/24 | NA | 1
11089 | End-To-End Business Scenarios - (MS 15, 19) | May 28, 2024 8:00 AM | September 20, 2024 5:00 PM |  |  | As Soon As Possible | NA | 83 | 0d | May 28, 2024 8:00 AM | August 9, 2024 5:00 PM | 53 days | No | 5/28/24 | 9/20/24 | NA | 1
11090 | Develop End-To-End Business Scenarios | May 28, 2024 8:00 AM | August 16, 2024 5:00 PM | 5379SS+10d | 4381,4377FS+5d | As Soon As Possible | NA | 58 | 0d | May 28, 2024 8:00 AM | July 26, 2024 5:00 PM | 43 days | No | 5/28/24 | 8/16/24 | NA | 1
11091 | Review End-To-End Business Scenarios with VPODs | August 26, 2024 8:00 AM | September 6, 2024 5:00 PM | 4376FS+5d | 4378FF+5d | As Soon As Possible | NA | 10 | 0d | July 29, 2024 8:00 AM | August 2, 2024 5:00 PM | 5 days | No | 8/26/24 | 9/6/24 | NA | 1
11092 | Incorporate VPODs Feedback | September 2, 2024 8:00 AM | September 13, 2024 5:00 PM | 4377FF+5d | 4379 | As Soon As Possible | NA | 10 | 0d | July 29, 2024 8:00 AM | August 2, 2024 5:00 PM | 5 days | No | 9/2/24 | 9/13/24 | NA | 1
11093 | MS 15, 19, 20 - Finalize End-To-End Business Scenarios | September 16, 2024 8:00 AM | September 20, 2024 5:00 PM | 4378 | 4538,4385 | As Soon As Possible | NA | 5 | 0d | August 5, 2024 8:00 AM | August 9, 2024 5:00 PM | 5 days | No | 9/16/24 | 9/20/24 | NA | 1
10540 | Milestone 06 - Case Management Engagement | October 31, 2024 8:00 AM | April 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 103 | 0d | September 30, 2024 8:00 AM | February 10, 2025 5:00 PM | 90 days | No | 10/31/24 | 4/3/25 | NA | 1
10541 | MS06 - Develop Training Curriculum Map | October 31, 2024 8:00 AM | November 14, 2024 5:00 PM | 4371,579SS+29d,4376 | 4382 | As Soon As Possible | NA | 10 | 0d | September 30, 2024 8:00 AM | November 8, 2024 5:00 PM | 30 days | No | 10/31/24 | 11/14/24 | NA | 1
12674 | MS06 - Complete Training Wireframe | November 15, 2024 8:00 AM | December 2, 2024 5:00 PM | 4381 | 4383 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 11/15/24 | 12/2/24 | NA | 1
10542 | Review Training Curriculum with TAW & VPOD | December 3, 2024 8:00 AM | December 31, 2024 5:00 PM | 4382 | 4384 | As Soon As Possible | NA | 20 | 0d | November 12, 2024 8:00 AM | November 25, 2024 5:00 PM | 10 days | No | 12/3/24 | 12/31/24 | NA | 1
10543 | Incorporate Feedback from VPOD & TAW | January 2, 2025 8:00 AM | January 8, 2025 5:00 PM | 4383 | 4386 | As Soon As Possible | NA | 5 | 0d | November 19, 2024 8:00 AM | December 4, 2024 5:00 PM | 10 days | No | 1/2/25 | 1/8/25 | NA | 1
10545 | Identify Critical Scenarios For EUST | November 4, 2024 8:00 AM | November 18, 2024 5:00 PM | 4374,234FS+266d,4379 | 4386SS+10d,4450,4465 | As Soon As Possible | NA | 10 | 0d | November 4, 2024 8:00 AM | November 18, 2024 5:00 PM | 10 days | No | 11/4/24 | 11/18/24 | NA | 1
10546 | MS 06 - Develop Training Content | January 9, 2025 8:00 AM | January 23, 2025 5:00 PM | 4385SS+10d,4384 | 4387 | As Soon As Possible | NA | 10 | 0d | November 19, 2024 8:00 AM | January 17, 2025 5:00 PM | 40 days | No | 1/9/25 | 1/23/25 | NA | 1
10547 | Review Training Content with TAW & VPOD | January 24, 2025 8:00 AM | February 6, 2025 5:00 PM | 4386 | 4388 | As Soon As Possible | NA | 10 | 0d | December 19, 2024 8:00 AM | January 27, 2025 5:00 PM | 25 days | No | 1/24/25 | 2/6/25 | NA | 1
10548 | Incorporate Feedback from TAW & VPOD | February 7, 2025 8:00 AM | February 13, 2025 5:00 PM | 4387 | 4389 | As Soon As Possible | NA | 5 | 0d | January 21, 2025 8:00 AM | February 3, 2025 5:00 PM | 10 days | No | 2/7/25 | 2/13/25 | NA | 1
10549 | MS 06 - Finalize Training Content | February 14, 2025 8:00 AM | February 14, 2025 5:00 PM | 4388 | 4538,5611,5612,4390 | As Soon As Possible | NA | 1 | 0d | February 4, 2025 8:00 AM | February 10, 2025 5:00 PM | 5 s | No | 2/14/25 | 2/14/25 | NA | 1
13058 | MS 06 - Finalize Training Dataset in the EUST 2 Env | February 18, 2025 8:00 AM | February 24, 2025 5:00 PM | 4389 | 5611,5612,4391FS+11d | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 2/18/25 | 2/24/25 | NA | 1
13077 | MS 06 - Finalize Salesforce Enablement | March 12, 2025 8:00 AM | April 3, 2025 5:00 PM | 4390FS+11d | 5611,5612 | As Soon As Possible | NA | 16 | 0d | NA | NA | 0 days? | No | 3/12/25 | 4/3/25 | NA | 1
10550 | Milestone 08 - Placement | October 31, 2024 8:00 AM | April 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 103 | 0d | September 30, 2024 8:00 AM | February 19, 2025 5:00 PM | 96 days | No | 10/31/24 | 4/3/25 | NA | 1
10555 | MS08 - Develop Training Curriculum Map | October 31, 2024 8:00 AM | November 14, 2024 5:00 PM | 588FS+22d | 4394 | As Soon As Possible | NA | 10 | 0d | September 30, 2024 8:00 AM | November 26, 2024 5:00 PM | 41 days | No | 10/31/24 | 11/14/24 | NA | 1
11714 | MS08 - Complete Training Wireframe | November 15, 2024 8:00 AM | December 2, 2024 5:00 PM | 4393 | 4395,4398 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 11/15/24 | 12/2/24 | NA | 1
10556 | Review Training Curriculum with TAW & VPOD | December 3, 2024 8:00 AM | December 31, 2024 5:00 PM | 4394 | 4396 | As Soon As Possible | NA | 20 | 0d | November 26, 2024 8:00 AM | December 12, 2024 5:00 PM | 11 days | No | 12/3/24 | 12/31/24 | NA | 1
10557 | Incorporate Feedback from VPOD & TAW | January 2, 2025 8:00 AM | January 8, 2025 5:00 PM | 4395 | 4398 | As Soon As Possible | NA | 5 | 0d | December 5, 2024 8:00 AM | December 19, 2024 5:00 PM | 11 days | No | 1/2/25 | 1/8/25 | NA | 1
10559 | Identify Critical Scenarios For EUST | November 4, 2024 8:00 AM | November 18, 2024 5:00 PM | 279FS+271d | 4398 | As Soon As Possible | NA | 10 | 0d | November 4, 2024 8:00 AM | November 18, 2024 5:00 PM | 10 days | No | 11/4/24 | 11/18/24 | NA | 1
10560 | MS08 - Develop Training Content | January 9, 2025 8:00 AM | January 23, 2025 5:00 PM | 4394,4396,4397 | 4399 | As Soon As Possible | NA | 10 | 0d | November 26, 2024 8:00 AM | January 28, 2025 5:00 PM | 41 days | No | 1/9/25 | 1/23/25 | NA | 1
10561 | Review Training Content with TAW & VPOD | January 24, 2025 8:00 AM | February 6, 2025 5:00 PM | 4398 | 4400 | As Soon As Possible | NA | 10 | 0d | December 27, 2024 8:00 AM | February 4, 2025 5:00 PM | 26 days | No | 1/24/25 | 2/6/25 | NA | 1
10562 | Incorporate Feedback from TAW & VPOD | February 7, 2025 8:00 AM | February 13, 2025 5:00 PM | 4399 | 4401 | As Soon As Possible | NA | 5 | 0d | January 28, 2025 8:00 AM | February 11, 2025 5:00 PM | 11 days | No | 2/7/25 | 2/13/25 | NA | 1
10563 | MS 08 - Finalize Training Content | February 14, 2025 8:00 AM | February 14, 2025 5:00 PM | 4400 | 4538,5611,5612,4402 | As Soon As Possible | NA | 1 | 0d | February 11, 2025 8:00 AM | February 19, 2025 5:00 PM | 6 s | No | 2/14/25 | 2/14/25 | NA | 1
13059 | MS 08 - Finalize Training Dataset in the EUST 2 Env | February 18, 2025 8:00 AM | February 24, 2025 5:00 PM | 4401 | 5611,5612,4403FS+11d | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 2/18/25 | 2/24/25 | NA | 1
13078 | MS 08 - Finalize Salesforce Enablement | March 12, 2025 8:00 AM | April 3, 2025 5:00 PM | 4402FS+11d | 5611,5612 | As Soon As Possible | NA | 16 | 0d | NA | NA | 0 days? | No | 3/12/25 | 4/3/25 | NA | 1
10564 | Milestone 15 - Court Hearing Framework | November 18, 2024 8:00 AM | April 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 92 | 0d | September 30, 2024 8:00 AM | March 4, 2025 5:00 PM | 105 days | No | 11/18/24 | 4/3/25 | NA | 1
10569 | MS15 - Develop Training Curriculum Map | November 18, 2024 8:00 AM | December 3, 2024 5:00 PM | 579SS+40d | 4406 | As Soon As Possible | NA | 10 | 0d | September 30, 2024 8:00 AM | November 25, 2024 5:00 PM | 40 days | No | 11/18/24 | 12/3/24 | NA | 1
11716 | MS15 - Complete Training Wireframe | December 4, 2024 8:00 AM | December 17, 2024 5:00 PM | 4405 | 4407 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 12/4/24 | 12/17/24 | NA | 1
10570 | Review Training Curriculum with TAW & VPOD | December 18, 2024 8:00 AM | January 9, 2025 5:00 PM | 4406 | 4408 | As Soon As Possible | NA | 15 | 0d | November 26, 2024 8:00 AM | December 11, 2024 5:00 PM | 10 days | No | 12/18/24 | 1/9/25 | NA | 1
10571 | Incorporate Feedback from VPOD & TAW | January 10, 2025 8:00 AM | January 16, 2025 5:00 PM | 4407 | 4411 | As Soon As Possible | NA | 5 | 0d | December 5, 2024 8:00 AM | December 18, 2024 5:00 PM | 10 days | No | 1/10/25 | 1/16/25 | NA | 1
10573 | Identify Critical Scenarios For EUST | November 20, 2024 8:00 AM | December 19, 2024 5:00 PM | 4410SS-20d | 4411 | As Soon As Possible | NA | 20 | 0d | November 20, 2024 8:00 AM | January 28, 2025 5:00 PM | 45 days | No | 11/20/24 | 12/19/24 | NA | 1
11718 | Finalize Critical Scenarios For EUST | December 20, 2024 8:00 AM | January 28, 2025 5:00 PM | 437FF | 4409SS-20d | As Soon As Possible | NA | 25 | 0d | NA | NA | 0 days? | No | 12/20/24 | 1/28/25 | NA | 1
10574 | MS 15 - Develop Training Content | January 17, 2025 8:00 AM | February 7, 2025 5:00 PM | 4408,4409 | 4412 | As Soon As Possible | NA | 15 | 0d | December 5, 2024 8:00 AM | February 10, 2025 5:00 PM | 45 days | No | 1/17/25 | 2/7/25 | NA | 1
10575 | Review Training Content with TAW & VPOD | February 10, 2025 8:00 AM | February 24, 2025 5:00 PM | 4411 | 4413 | As Soon As Possible | NA | 10 | 0d | December 19, 2024 8:00 AM | February 18, 2025 5:00 PM | 40 days | No | 2/10/25 | 2/24/25 | NA | 1
10576 | Incorporate Feedback from TAW & VPOD | February 25, 2025 8:00 AM | March 3, 2025 5:00 PM | 4412 | 4414FF | As Soon As Possible | NA | 5 | 0d | February 11, 2025 8:00 AM | February 25, 2025 5:00 PM | 10 days | No | 2/25/25 | 3/3/25 | NA | 1
10577 | MS 15 - Finalize Training Content | March 3, 2025 8:00 AM | March 3, 2025 5:00 PM | 4413FF | 4538,4415 | As Soon As Possible | NA | 1 | 0d | February 26, 2025 8:00 AM | March 4, 2025 5:00 PM | 5 s | No | 3/3/25 | 3/3/25 | NA | 1
13079 | MS 15 - Finalize Salesforce Enablement | March 12, 2025 8:00 AM | April 3, 2025 5:00 PM | 4414 | 5611,5612 | As Soon As Possible | NA | 16 | 0d | NA | NA | 0 days? | No | 3/12/25 | 4/3/25 | NA | 1
10578 | Milestone 19 - Request Determination | December 4, 2024 8:00 AM | April 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 82 | 0d | September 30, 2024 8:00 AM | March 3, 2025 5:00 PM | 104 days | No | 12/4/24 | 4/3/25 | NA | 1
10583 | MS19 - Develop Training Curriculum Map | December 4, 2024 8:00 AM | December 17, 2024 5:00 PM | 579FS+1d | 4418 | As Soon As Possible | NA | 10 | 0d | September 30, 2024 8:00 AM | December 11, 2024 5:00 PM | 50 days | No | 12/4/24 | 12/17/24 | NA | 1
11719 | MS19 - Complete Training Wireframe | December 18, 2024 8:00 AM | January 2, 2025 5:00 PM | 4417 | 4419 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 12/18/24 | 1/2/25 | NA | 1
10584 | Review Training Curriculum with TAW & VPOD | January 3, 2025 8:00 AM | January 24, 2025 5:00 PM | 4418 | 4420 | As Soon As Possible | NA | 15 | 0d | December 12, 2024 8:00 AM | December 26, 2024 5:00 PM | 10 days | No | 1/3/25 | 1/24/25 | NA | 1
10585 | Incorporate Feedback from VPOD & TAW | January 27, 2025 8:00 AM | January 31, 2025 5:00 PM | 4419 | 4422 | As Soon As Possible | NA | 5 | 0d | December 19, 2024 8:00 AM | January 3, 2025 5:00 PM | 10 days | No | 1/27/25 | 1/31/25 | NA | 1
10587 | Identify Critical Scenarios For EUST | January 14, 2025 8:00 AM | January 28, 2025 5:00 PM | 466FF | 4425 | As Soon As Possible | NA | 10 | 0d | January 14, 2025 8:00 AM | January 28, 2025 5:00 PM | 10 days | No | 1/14/25 | 1/28/25 | NA | 1
10588 | MS 19 - Develop Training Content | February 3, 2025 8:00 AM | February 14, 2025 5:00 PM | 468SS,469SS,4420 | 4423 | As Soon As Possible | NA | 10 | 0d | December 12, 2024 8:00 AM | February 10, 2025 5:00 PM | 40 days | No | 2/3/25 | 2/14/25 | NA | 1
10589 | Review Training Content with TAW & VPOD | February 18, 2025 8:00 AM | February 24, 2025 5:00 PM | 4422 | 4424 | As Soon As Possible | NA | 5 | 0d | January 13, 2025 8:00 AM | February 14, 2025 5:00 PM | 24 days | No | 2/18/25 | 2/24/25 | NA | 1
10590 | Incorporate Feedback from TAW & VPOD | February 25, 2025 8:00 AM | February 28, 2025 5:00 PM | 4423 | 4425 | As Soon As Possible | NA | 4 | 0d | February 10, 2025 8:00 AM | February 24, 2025 5:00 PM | 10 days | No | 2/25/25 | 2/28/25 | NA | 1
10591 | MS 19 - Finalize Training Content | March 3, 2025 8:00 AM | March 3, 2025 5:00 PM | 4424,4421 | 4538,5611,5612,4426FS+6d | As Soon As Possible | NA | 1 | 0d | February 25, 2025 8:00 AM | March 3, 2025 5:00 PM | 5 s | No | 3/3/25 | 3/3/25 | NA | 1
13080 | MS 19 - Finalize Salesforce Enablement | March 12, 2025 8:00 AM | April 3, 2025 5:00 PM | 4425FS+6d | 5611,5612 | As Soon As Possible | NA | 16 | 0d | NA | NA | 0 days? | No | 3/12/25 | 4/3/25 | NA | 1
10592 | Milestone 20/20.1 - Redetermine Eligibility | December 4, 2024 8:00 AM | April 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 82 | 0d | September 30, 2024 8:00 AM | February 26, 2025 5:00 PM | 101 days | No | 12/4/24 | 4/3/25 | NA | 1
10597 | MS20/20.1 - Develop Training Curriculum Map | December 4, 2024 8:00 AM | December 17, 2024 5:00 PM | 579FS+1d | 4429 | As Soon As Possible | NA | 10 | 0d | September 30, 2024 8:00 AM | November 25, 2024 5:00 PM | 40 days | No | 12/4/24 | 12/17/24 | NA | 1
11721 | MS20/20.1 - Complete Training Wireframe | December 18, 2024 8:00 AM | January 2, 2025 5:00 PM | 4428 | 4430 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 12/18/24 | 1/2/25 | NA | 1
10598 | Review Training Curriculum with TAW & VPOD | January 3, 2025 8:00 AM | January 24, 2025 5:00 PM | 4429 | 4431 | As Soon As Possible | NA | 15 | 0d | November 26, 2024 8:00 AM | December 11, 2024 5:00 PM | 10 days | No | 1/3/25 | 1/24/25 | NA | 1
10599 | Incorporate Feedback from VPOD & TAW | January 27, 2025 8:00 AM | January 31, 2025 5:00 PM | 4430 | 4433 | As Soon As Possible | NA | 5 | 0d | December 5, 2024 8:00 AM | December 18, 2024 5:00 PM | 10 days | No | 1/27/25 | 1/31/25 | NA | 1
10601 | Identify Critical Scenarios For EUST | January 14, 2025 8:00 AM | January 28, 2025 5:00 PM | 499FF | 4436 | As Soon As Possible | NA | 10 | 0d | January 14, 2025 8:00 AM | January 28, 2025 5:00 PM | 10 days | No | 1/14/25 | 1/28/25 | NA | 1
10602 | MS 20/20.1 - Develop Training Content | February 3, 2025 8:00 AM | February 14, 2025 5:00 PM | 501SS,502SS,503SS,4431 | 4434 | As Soon As Possible | NA | 10 | 0d | December 9, 2024 8:00 AM | February 5, 2025 5:00 PM | 40 days | No | 2/3/25 | 2/14/25 | NA | 1
10603 | Review Training Content with TAW & VPOD | February 18, 2025 8:00 AM | February 24, 2025 5:00 PM | 4433 | 4435 | As Soon As Possible | NA | 5 | 0d | January 8, 2025 8:00 AM | February 11, 2025 5:00 PM | 24 days | No | 2/18/25 | 2/24/25 | NA | 1
10604 | Incorporate Feedback from TAW & VPOD | February 25, 2025 8:00 AM | February 28, 2025 5:00 PM | 4434 | 4436 | As Soon As Possible | NA | 4 | 0d | February 5, 2025 8:00 AM | February 19, 2025 5:00 PM | 10 days | No | 2/25/25 | 2/28/25 | NA | 1
10605 | MS 20/20.1 - Finalize Training Content | March 3, 2025 8:00 AM | March 3, 2025 5:00 PM | 4435,4432 | 4538,5611,5612,4437FS+6d | As Soon As Possible | NA | 1 | 0d | February 20, 2025 8:00 AM | February 26, 2025 5:00 PM | 5 s | No | 3/3/25 | 3/3/25 | NA | 1
13081 | MS 20/20.1 - Finalize Salesforce Enablement | March 12, 2025 8:00 AM | April 3, 2025 5:00 PM | 4436FS+6d | 5611,5612 | As Soon As Possible | NA | 16 | 0d | NA | NA | 0 days? | No | 3/12/25 | 4/3/25 | NA | 1
10606 | Group 2 On-Going Case Work (Milestones 6.1, 7) | June 17, 2024 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 404 | 429d | June 30, 2023 8:00 AM | December 5, 2025 5:00 PM | 611 days | No | 6/17/24 | NA | NA | 0.81999999999999995
10620 | On-Going Case Work: Training | June 17, 2024 8:00 AM | August 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 34 | 0d | June 30, 2023 8:00 AM | December 5, 2025 5:00 PM | 611 days | No | 6/17/24 | 8/2/24 | NA | 1
10621 | Develop End-To-End Business Scenarios | June 17, 2024 8:00 AM | June 28, 2024 5:00 PM | 5416SS,5422SS,5410SS | 4441FS+12d | As Soon As Possible | NA | 10 | 0d | June 17, 2024 8:00 AM | June 28, 2024 5:00 PM | 10 days | No | 6/17/24 | 6/28/24 | NA | 1
10622 | Review End-To-End Business Scenarios with VPODs | July 18, 2024 8:00 AM | July 26, 2024 5:00 PM | 4440FS+12d | 4442 | As Soon As Possible | NA | 7 | 0d | July 1, 2024 8:00 AM | July 8, 2024 5:00 PM | 5 days | No | 7/18/24 | 7/26/24 | NA | 1
10623 | Incorporate VPODs Feedback | July 29, 2024 8:00 AM | August 2, 2024 5:00 PM | 4441 | 4443FF | As Soon As Possible | NA | 5 | 0d | July 1, 2024 8:00 AM | July 8, 2024 5:00 PM | 5 days | No | 7/29/24 | 8/2/24 | NA | 1
10624 | Finalize End-To-End Business Scenarios | July 30, 2024 8:00 AM | August 2, 2024 5:00 PM | 4442FF | 4538 | As Soon As Possible | NA | 4 | 0d | July 9, 2024 8:00 AM | July 12, 2024 5:00 PM | 4 days | No | 7/30/24 | 8/2/24 | NA | 1
12163 | On-Going Case Work (MS 9): Training | June 17, 2024 8:00 AM | August 27, 2024 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | June 30, 2023 8:00 AM | December 5, 2025 5:00 PM | 611 days | No | 6/17/24 | 8/27/24 | NA | 1
12164 | Develop End-To-End Business Scenarios | June 17, 2024 8:00 AM | June 28, 2024 5:00 PM | 3192 | 4446FS+9d | As Soon As Possible | NA | 10 | 0d | NA | NA | 10 days | No | 6/17/24 | 6/28/24 | NA | 1
12165 | MS 09: Review End-To-End Business Scenarios with VPODs | July 15, 2024 8:00 AM | July 19, 2024 5:00 PM | 4445FS+9d | 4447 | As Soon As Possible | NA | 5 | 0d | NA | NA | 5 days | No | 7/15/24 | 7/19/24 | NA | 1
12166 | MS 09: Incorporate VPODs Feedback | July 22, 2024 8:00 AM | August 2, 2024 5:00 PM | 4446 | 4448FS+10d | As Soon As Possible | NA | 10 | 0d | NA | NA | 5 days | No | 7/22/24 | 8/2/24 | NA | 1
12167 | MS 09: Finalize End-To-End Business Scenarios | August 19, 2024 8:00 AM | August 27, 2024 5:00 PM | 4447FS+10d | 4925 | As Soon As Possible | NA | 7 | 0d | NA | NA | 4 days | No | 8/19/24 | 8/27/24 | NA | 1
11094 | Milestone 6.1 - Prevention Services | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 169 | 467d | April 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 174 days | No | 4/1/25 | NA | NA | 0.88
11095 | MS 6.1 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 601,4385 | 4451FF,4460 | As Soon As Possible | NA | 90 | 0d | April 1, 2025 8:00 AM | May 27, 2025 5:00 PM | 40 days | No | 4/1/25 | 8/6/25 | NA | 1
11096 | MS 6.1 - Review Training Curriculum with VPODs | May 28, 2025 8:00 AM | August 6, 2025 5:00 PM | 4450FF | 4452FF,4454SS+1d | As Soon As Possible | NA | 50 | 0d | May 28, 2025 8:00 AM | June 10, 2025 5:00 PM | 10 days | No | 5/28/25 | 8/6/25 | NA | 1
11097 | MS 6.1 - Incorporate VPODs Feedback | June 4, 2025 8:00 AM | August 6, 2025 5:00 PM | 4451FF | 4453FF | As Soon As Possible | NA | 45 | 0d | June 4, 2025 8:00 AM | June 17, 2025 5:00 PM | 10 days | No | 6/4/25 | 8/6/25 | NA | 1
11098 | MS 6.1 - Finalize Training Curriculum | June 18, 2025 8:00 AM | August 6, 2025 5:00 PM | 4452FF | 4463 | As Soon As Possible | NA | 35 | 0d | June 18, 2025 8:00 AM | June 24, 2025 5:00 PM | 5 days | No | 6/18/25 | 8/6/25 | NA | 1
11099 | MS 6.1 - Validate and Provide Feedback on Critical Scenarios for the EUST | May 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 4451SS+1d |  | As Soon As Possible | NA | 128 | 467d | May 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 128 days | No | 5/29/25 | NA | NA | 0.73999999999999999
13936 | BD 3 - MS 6.1 - Discovery and Develop Training Curriculum (Build Drop Update) | August 11, 2025 8:00 AM | September 3, 2025 5:00 PM | 308FS+193d,310FS+193d | 4456SS | As Soon As Possible | NA | 17 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/3/25 | NA | 1
13938 | BD 3 - MS 6.1 - Review Training Curriculum with VPODs(Build Drop Update) | August 11, 2025 8:00 AM | September 3, 2025 5:00 PM | 4455SS | 4457SS | As Soon As Possible | NA | 17 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/3/25 | NA | 1
13937 | BD 3 - MS 6.1 - Incorporate VPODs Feedback(Build Drop Update) | August 11, 2025 8:00 AM | September 3, 2025 5:00 PM | 4456SS | 4458FS-11d,4459FS-11d | As Soon As Possible | NA | 17 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/3/25 | NA | 1
13935 | BD 3 - MS 6.1 - Finalize Training Curriculum (Build Drop Update) | August 19, 2025 8:00 AM | September 3, 2025 5:00 PM | 4457FS-11d |  | As Soon As Possible | NA | 11 | 0d | NA | NA | 0 days? | No | 8/19/25 | 9/3/25 | NA | 1
13934 | MS 6.1 - Develop Training Content - Quick Guides, Knowledge Base Articles (Build Drop Update) | August 19, 2025 8:00 AM | September 3, 2025 5:00 PM | 4457FS-11d | 4460FS+2d | As Soon As Possible | NA | 11 | 0d | NA | NA | 0 days? | No | 8/19/25 | 9/3/25 | NA | 1
11100 | MS 6.1 - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | September 8, 2025 8:00 AM | October 6, 2025 5:00 PM | 4450,748SS,749SS,750SS,751SS,752SS,753SS,4459FS+2d | 4461FS+4d | As Soon As Possible | NA | 21 | 0d | May 30, 2025 8:00 AM | July 29, 2025 5:00 PM | 42 days | No | 9/8/25 | 10/6/25 | NA | 1
11101 | BD 3 - MS 6.1 - Review Training Content with VPOD & TAW (Build Drop Update) | October 13, 2025 8:00 AM | October 20, 2025 5:00 PM | 4460FS+4d | 4462 | As Soon As Possible | NA | 6 | 76d | June 27, 2025 8:00 AM | August 4, 2025 5:00 PM | 26 days | No | NA | NA | NA | 0
11102 | BD 3 - MS 6.1 - Incorporate Feedback from VPOD & TAW (Build Drop Update) | October 21, 2025 8:00 AM | November 3, 2025 5:00 PM | 4461 | 4463 | As Soon As Possible | NA | 10 | 76d | July 29, 2025 8:00 AM | August 11, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
11103 | MS 6.1 - Finalize Training Content | November 4, 2025 8:00 AM | November 10, 2025 5:00 PM | 4462,4453 | 4538,5611,5612,4780,4781,4893 | As Soon As Possible | NA | 5 | 76d | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
10625 | Milestone 07/7.1 - Case Plan | April 1, 2025 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 207 | 429d | April 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 174 days | No | 4/1/25 | NA | NA | 0.76000000000000001
10626 | MS 07/7.1 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 601,4385 | 4466FF | As Soon As Possible | NA | 90 | 0d | April 1, 2025 8:00 AM | May 27, 2025 5:00 PM | 40 days | No | 4/1/25 | 8/6/25 | NA | 1
10627 | MS 07/7.1 - Review Training Curriculum with VPODs | May 28, 2025 8:00 AM | August 6, 2025 5:00 PM | 4465FF | 4467FF,4469SS+1d | As Soon As Possible | NA | 50 | 0d | May 28, 2025 8:00 AM | June 10, 2025 5:00 PM | 10 days | No | 5/28/25 | 8/6/25 | NA | 1
10628 | MS 07/7.1 - Incorporate VPODs Feedback | June 4, 2025 8:00 AM | August 6, 2025 5:00 PM | 4466FF | 4468FF | As Soon As Possible | NA | 45 | 0d | June 4, 2025 8:00 AM | June 17, 2025 5:00 PM | 10 days | No | 6/4/25 | 8/6/25 | NA | 1
10629 | MS 07/7.1 - Finalize Training Curriculum | June 18, 2025 8:00 AM | August 6, 2025 5:00 PM | 4467FF | 4478 | As Soon As Possible | NA | 35 | 0d | June 18, 2025 8:00 AM | June 24, 2025 5:00 PM | 5 days | No | 6/18/25 | 8/6/25 | NA | 1
10630 | MS 07/7.1 - Validate and Provide Feedback on Critical Scenarios for the EUST | May 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 4466SS+1d | 4478FS-76d | As Soon As Possible | NA | 128 | 135d | May 29, 2025 8:00 AM | November 28, 2025 5:00 PM | 128 days | No | 5/29/25 | NA | NA | 0.73999999999999999
13930 | BD 3 - MS 7/7.1 - Discovery and Develop Training Curriculum (Build Drop Update) | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 702,703,704,705,706,707,730,731,732,733,734,735 | 4471SS | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.75
13932 | BD 3 - MS 7/7.1 - Review Training Curriculum with VPODs(Build Drop Update) | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 4470SS | 4472SS | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.75
13933 | BD 3 - MS 7/7.1 - Incorporate VPODs Feedback(Build Drop Update) | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 4471SS | 4473FS-52d | As Soon As Possible | NA | 59 | 36.92d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.75
13931 | BD - 3 MS 7/7.1: Finalize Training Curriculum (Build Drop Update) | August 20, 2025 8:00 AM | October 31, 2025 5:00 PM | 4472FS-52d | 4474SS+4d | As Soon As Possible | NA | 52 | 485d | NA | NA | 0 days? | No | 8/20/25 | NA | NA | 0.70999999999999996
13929 | BD 3 - MS 7/7.1 - Develop Training Content - Quick Guides, Knowledge Base Articles (Build Drop Update) | August 26, 2025 8:00 AM | October 31, 2025 5:00 PM | 4473SS+4d,731 | 4475,4893 | As Soon As Possible | NA | 48 | 21.08d | NA | NA | 0 days? | No | 8/26/25 | NA | NA | 0.68999999999999995
10631 | BD 3 - MS 7/7.1 - Develop Training Content On-Demand Programs and Lessons (Build Drop Update) | November 3, 2025 8:00 AM | December 22, 2025 5:00 PM | 748SS,749SS,750SS,751SS,752SS,753SS,4474,719,720,721,722 | 4476,4490SS | As Soon As Possible | NA | 34 | 21.08d | May 30, 2025 8:00 AM | July 29, 2025 5:00 PM | 42 days | No | NA | NA | NA | 0
10632 | BD 3 - MS 7/7.1 - Review Training Content with VPOD & TAW (Build Drop Update) | December 23, 2025 8:00 AM | January 5, 2026 5:00 PM | 4475 | 4477 | As Soon As Possible | NA | 8 | 26d | June 27, 2025 8:00 AM | August 4, 2025 5:00 PM | 26 days | No | NA | NA | NA | 0
10633 | BD 3 - MS 7/7.1 - Incorporate Feedback from VPOD & TAW (Build Drop Update) | January 6, 2026 8:00 AM | January 16, 2026 5:00 PM | 4476 | 4478 | As Soon As Possible | NA | 9 | 26d | July 29, 2025 8:00 AM | August 11, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10634 | MS 07/7.1 - Finalize Training Content | January 20, 2026 8:00 AM | January 26, 2026 5:00 PM | 4477,4468,4469FS-76d | 4538,5611,5612,4782,4783,4904 | Start No Earlier Than | 12/1/25 | 5 | 26d | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
10635 | Milestone 09 - Case Management - Engagement and Services | April 1, 2025 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 207 | 429d | June 30, 2023 8:00 AM | December 5, 2025 5:00 PM | 611 days | No | 4/1/25 | NA | NA | 0.81999999999999995
10640 | MS 09 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 601 | 4481FF,4490 | As Soon As Possible | NA | 90 | 0d | April 1, 2025 8:00 AM | May 27, 2025 5:00 PM | 40 days | No | 4/1/25 | 8/6/25 | NA | 1
10641 | MS 09 - Review Training Curriculum with VPODs | May 28, 2025 8:00 AM | August 6, 2025 5:00 PM | 4480FF | 4482FF | As Soon As Possible | NA | 50 | 0d | May 28, 2025 8:00 AM | June 10, 2025 5:00 PM | 10 days | No | 5/28/25 | 8/6/25 | NA | 1
10642 | MS 09 - Incorporate VPODs Feedback | June 4, 2025 8:00 AM | August 6, 2025 5:00 PM | 4481FF | 4483FF | As Soon As Possible | NA | 45 | 0d | June 4, 2025 8:00 AM | June 17, 2025 5:00 PM | 10 days | No | 6/4/25 | 8/6/25 | NA | 1
10643 | MS 09 - Finalize Training Curriculum | June 18, 2025 8:00 AM | August 6, 2025 5:00 PM | 4482FF | 4493 | As Soon As Possible | NA | 35 | 0d | June 18, 2025 8:00 AM | June 24, 2025 5:00 PM | 5 days | No | 6/18/25 | 8/6/25 | NA | 1
10644 | MS 09 - Validate and Provide Feedback on Critical Scenarios for the EUST | April 29, 2025 8:00 AM | October 27, 2025 5:00 PM | 349FS+330d | 4493 | As Soon As Possible | NA | 127 | 81d | June 30, 2023 8:00 AM | January 3, 2024 5:00 PM | 127 days | No | 4/29/25 | NA | NA | 0.91000000000000003
13926 | BD 3 - MS 9 - Discovery and Develop Training Curriculum (Build Drop Update) | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 339FS+402d,340FS+402d,341FS+402d,342FS+402d,343FS+402d,345FS+402d,346FS+402d,347FS+402d,348FS+402d,349FS+402d | 4486SS | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.75
13927 | BD 3 - MS 9 - Review Training Curriculum with VPODs(Build Drop Update) | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 4485SS | 4487SS | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.75
13928 | BD 3 - MS 9 - Incorporate VPODs Feedback(Build Drop Update) | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 4486SS | 4488FS-52d | As Soon As Possible | NA | 59 | 36.92d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.75
13925 | BD 3 - MS 9: Finalize Training Curriculum (Build Drop Update) | August 20, 2025 8:00 AM | October 31, 2025 5:00 PM | 4487FS-52d | 4489SS+4d | As Soon As Possible | NA | 52 | 485d | NA | NA | 0 days? | No | 8/20/25 | NA | NA | 0.70999999999999996
13924 | BD 3 - MS 9 - Develop Training Content - Quick Guides, Knowledge Base Articles (Build Drop Update) | August 26, 2025 8:00 AM | October 31, 2025 5:00 PM | 4488SS+4d | 4893 | As Soon As Possible | NA | 48 | 466d | NA | NA | 0 days? | No | 8/26/25 | NA | NA | 0.68999999999999995
10645 | BD 3 - MS 9 - Develop Training Content - On Demand Programs and Lessons (Build Drop Update) | November 3, 2025 8:00 AM | December 22, 2025 5:00 PM | 4480,351,352,353,354,355,4475SS | 4491 | As Soon As Possible | NA | 34 | 26d | May 28, 2025 8:00 AM | November 14, 2025 5:00 PM | 120 days | No | 11/3/25 | NA | NA | 0.62
10646 | BD 3 - MS 9 - Review Training Content with VPOD & TAW (Build Drop Update) | December 23, 2025 8:00 AM | January 5, 2026 5:00 PM | 4490 | 4492 | As Soon As Possible | NA | 8 | 26d | June 25, 2025 8:00 AM | November 20, 2025 5:00 PM | 104 days | No | NA | NA | NA | 0
10647 | BD 3 - MS 9 - Incorporate Feedback from VPOD & TAW (Build Drop Update) | January 6, 2026 8:00 AM | January 16, 2026 5:00 PM | 4491 | 4493 | As Soon As Possible | NA | 9 | 26d | November 14, 2025 8:00 AM | November 28, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10648 | MS 09 - Finalize Training Content | January 20, 2026 8:00 AM | January 26, 2026 5:00 PM | 4492,4483,4484 | 4538,5611,5612,4784,4785,4904 | As Soon As Possible | NA | 5 | 26d | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
10649 | Group 3 Finish a Case (Milestones 10, 11, 13) | August 12, 2024 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 365 | 410d | August 21, 2024 8:00 AM | December 8, 2025 5:00 PM | 326 days | No | 8/12/24 | NA | NA | 0.78000000000000003
10669 | Finish a Case: Training (MS 10, 11) | August 12, 2024 8:00 AM | October 11, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | August 21, 2024 8:00 AM | December 8, 2025 5:00 PM | 326 days | No | 8/12/24 | 10/11/24 | NA | 1
10670 | MS10, 11 - Develop End-To-End Business Scenarios | August 12, 2024 8:00 AM | September 20, 2024 5:00 PM | 5429SS,5436SS | 4506,4497 | As Soon As Possible | NA | 30 | 0d | August 21, 2024 8:00 AM | October 4, 2024 5:00 PM | 33 days | No | 8/12/24 | 9/20/24 | NA | 1
10671 | Review End-To-End Business Scenarios with VPODs | September 23, 2024 8:00 AM | September 27, 2024 5:00 PM | 4496 | 4498FS-5d | As Soon As Possible | NA | 5 | 0d | September 23, 2024 8:00 AM | October 4, 2024 5:00 PM | 10 days | No | 9/23/24 | 9/27/24 | NA | 1
10672 | Incorporate VPODs Feedback | September 23, 2024 8:00 AM | October 4, 2024 5:00 PM | 4497FS-5d | 4499 | As Soon As Possible | NA | 10 | 0d | September 30, 2024 8:00 AM | October 11, 2024 5:00 PM | 10 days | No | 9/23/24 | 10/4/24 | NA | 1
10673 | MS10, 11 - Finalize End-To-End Business Scenarios | October 7, 2024 8:00 AM | October 11, 2024 5:00 PM | 4498 | 4538 | As Soon As Possible | NA | 5 | 0d | October 14, 2024 8:00 AM | October 18, 2024 5:00 PM | 5 days | No | 10/7/24 | 10/11/24 | NA | 1
12576 | Finish a Case: Training (MS 13) | October 2, 2024 8:00 AM | December 11, 2024 5:00 PM |  |  | As Soon As Possible | NA | 48 | 0d | NA | NA | 0 days? | No | 10/2/24 | 12/11/24 | NA | 1
12577 | MS13 - Develop End-To-End Business Scenarios | October 2, 2024 8:00 AM | November 18, 2024 5:00 PM | 674SS+22d | 4502 | As Soon As Possible | NA | 33 | 0d | NA | NA | 0 days? | No | 10/2/24 | 11/18/24 | NA | 1
12578 | Review End-To-End Business Scenarios with VPODs | November 19, 2024 8:00 AM | November 25, 2024 5:00 PM | 4501 | 4503FF+5d | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 11/19/24 | 11/25/24 | NA | 1
12579 | Incorporate VPODs Feedback | November 19, 2024 8:00 AM | December 4, 2024 5:00 PM | 4502FF+5d | 4504 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 11/19/24 | 12/4/24 | NA | 1
12580 | MS13 - Finalize End-To-End Business Scenarios | December 5, 2024 8:00 AM | December 11, 2024 5:00 PM | 4503 | 4506 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 12/5/24 | 12/11/24 | NA | 1
10674 | Milestone 10 - Case Closure | June 3, 2025 8:00 AM | December 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 136 | 437d | June 2, 2025 8:00 AM | December 8, 2025 5:00 PM | 132 days | No | 6/3/25 | NA | NA | 0.75
10675 | BD 4 - MS 10 - Discovery and Develop Training Curriculum (Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 4496,699FS+18d,4504,631FF,632FF | 4507SS,4512,4508SS | As Soon As Possible | NA | 26 | 0d | June 2, 2025 8:00 AM | July 14, 2025 5:00 PM | 30 days | No | 9/5/25 | 10/10/25 | NA | 1
10676 | BD 4- MS 10 - Review Training Curriculum with VPODs(Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 4506SS |  | As Soon As Possible | NA | 26 | 0d | July 15, 2025 8:00 AM | July 28, 2025 5:00 PM | 10 days | No | 9/5/25 | 10/10/25 | NA | 1
10677 | BD 4 - MS 10 - Incorporate VPODs Feedback(Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 4506SS | 4509 | As Soon As Possible | NA | 26 | 0d | July 22, 2025 8:00 AM | August 4, 2025 5:00 PM | 10 days | No | 9/5/25 | 10/10/25 | NA | 1
10678 | BD 4 - MS 10: Finalize Training Curriculum (Build Drop Update) | October 13, 2025 8:00 AM | October 17, 2025 5:00 PM | 4508 | 4515,4511,4512 | As Soon As Possible | NA | 5 | 53d | August 5, 2025 8:00 AM | August 11, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
10679 | MS 10 - Validate and Provide Feedback on Critical Scenarios for the EUST | June 3, 2025 8:00 AM | October 3, 2025 5:00 PM | 384FF | 4515 | As Soon As Possible | NA | 87 | 97d | July 28, 2025 8:00 AM | November 28, 2025 5:00 PM | 87 days | No | 6/3/25 | NA | NA | 0.95999999999999996
13923 | BD 4 -MS 10 - Develop Training Content - Knowledge Base Articles, Quick Guides (Build Drop Update) | October 20, 2025 8:00 AM | October 24, 2025 5:00 PM | 4509,632 | 4893 | As Soon As Possible | NA | 5 | 471d | NA | NA | 0 days? | No | NA | NA | NA | 0
10680 | BD 4 -MS 10 - Develop Training Content - On-Demad Programs and Lessons (Build Drop Update) | October 20, 2025 8:00 AM | November 10, 2025 5:00 PM | 4506,386SS,387SS,4509,632 | 4513 | As Soon As Possible | NA | 16 | 53d | July 31, 2025 8:00 AM | November 14, 2025 5:00 PM | 75 days | No | NA | NA | NA | 0
10681 | BD 3 - MS 10 - Review Training Content with VPOD & TAW (Build Drop Update) | November 12, 2025 8:00 AM | November 24, 2025 5:00 PM | 4512 | 4514 | As Soon As Possible | NA | 9 | 53d | August 14, 2025 8:00 AM | November 21, 2025 5:00 PM | 70 days | No | NA | NA | NA | 0
10682 | BD 3 - MS 10 - Incorporate Feedback from VPOD & TAW (Build Drop Update) | November 25, 2025 8:00 AM | December 8, 2025 5:00 PM | 4513 | 4515 | As Soon As Possible | NA | 9 | 53d | November 17, 2025 8:00 AM | December 1, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10683 | MS 10 - Finalize Training Content | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 4514,4509,4510 | 4538,5611,5612,4786,4787,4899 | As Soon As Possible | NA | 5 | 53d | December 2, 2025 8:00 AM | December 8, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
10684 | Milestone 11 - Aftercare and Re-entry | June 3, 2025 8:00 AM | December 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 136 | 437d | June 2, 2025 8:00 AM | December 8, 2025 5:00 PM | 132 days | No | 6/3/25 | NA | NA | 0.75
10689 | BD 4- MS 11 - Discovery and Develop Training Curriculum (Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 715FS-21d,716FS-21d,717FS-21d,743FS-21d,744FS-21d,745FS-21d | 4518FF,4523 | As Soon As Possible | NA | 26 | 0d | June 2, 2025 8:00 AM | July 14, 2025 5:00 PM | 30 days | No | 9/5/25 | 10/10/25 | NA | 1
10690 | BD 4 - MS 11 - Review Training Curriculum with VPODs(Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 4517FF | 4519FF | As Soon As Possible | NA | 26 | 0d | July 15, 2025 8:00 AM | July 28, 2025 5:00 PM | 10 days | No | 9/5/25 | 10/10/25 | NA | 1
10691 | BD 4 - MS 11 - Incorporate VPODs Feedback(Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 4518FF | 4520 | As Soon As Possible | NA | 26 | 0d | July 22, 2025 8:00 AM | August 4, 2025 5:00 PM | 10 days | No | 9/5/25 | 10/10/25 | NA | 1
10692 | BD 4 - MS 11: Finalize Training Curriculum (Build Drop Update) | October 13, 2025 8:00 AM | October 17, 2025 5:00 PM | 4519 | 4526,4521,4523 | As Soon As Possible | NA | 5 | 53d | August 5, 2025 8:00 AM | August 11, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
13922 | BD 4 - MS 11: Develop Training Content - Quick Guides, Knowledge Base Articles (Build Drop Update) | October 20, 2025 8:00 AM | October 24, 2025 5:00 PM | 4520,597,598,599 | 4893 | As Soon As Possible | NA | 5 | 471d | NA | NA | 0 days? | No | NA | NA | NA | 0
10693 | MS 11 - Validate and Provide Feedback on Critical Scenarios for the EUST | June 3, 2025 8:00 AM | October 3, 2025 5:00 PM | 745FF | 4526 | As Soon As Possible | NA | 87 | 97d | July 28, 2025 8:00 AM | November 28, 2025 5:00 PM | 87 days | No | 6/3/25 | NA | NA | 0.95999999999999996
10694 | BD 4 - MS 11: Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | October 20, 2025 8:00 AM | November 10, 2025 5:00 PM | 4517,761SS,762SS,763SS,4520,597,598,599 | 4524 | As Soon As Possible | NA | 16 | 53d | July 31, 2025 8:00 AM | November 14, 2025 5:00 PM | 75 days | No | NA | NA | NA | 0
10695 | BD 4 - MS 11 - Review Training Content with VPOD & TAW (Build Drop Update) | November 12, 2025 8:00 AM | November 24, 2025 5:00 PM | 4523 | 4525 | As Soon As Possible | NA | 9 | 53d | August 14, 2025 8:00 AM | November 21, 2025 5:00 PM | 70 days | No | NA | NA | NA | 0
10696 | BD 4 - MS 11 - Incorporate Feedback from VPOD & TAW (Build Drop Update) | November 25, 2025 8:00 AM | December 8, 2025 5:00 PM | 4524 | 4526 | As Soon As Possible | NA | 9 | 53d | November 17, 2025 8:00 AM | December 1, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10697 | MS 11 - Finalize Training Content | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 4525,4520,4522 | 4538,5611,5612,4788,4789,4899 | As Soon As Possible | NA | 5 | 53d | December 2, 2025 8:00 AM | December 8, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
10698 | Milestone 13 - Adoption | June 3, 2025 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 163 | 410d | June 2, 2025 8:00 AM | December 8, 2025 5:00 PM | 132 days | No | 6/3/25 | NA | NA | 0.70999999999999996
10703 | BD 4 - MS 13 - Discovery and Develop Training Curriculum (Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 709FS-21d,710FS-21d,711FF+5d,712FF+5d,713FF+5d,737FF+5d,738FF+5d,739FF+5d,740FF+5d,741FF+5d | 4529FF,4534 | As Soon As Possible | NA | 26 | 0d | June 2, 2025 8:00 AM | July 14, 2025 5:00 PM | 30 days | No | 9/5/25 | 10/10/25 | NA | 1
10704 | BD 4 - MS 13 - Review Training Curriculum with VPODs(Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 4528FF | 4530FF | As Soon As Possible | NA | 26 | 0d | July 15, 2025 8:00 AM | July 28, 2025 5:00 PM | 10 days | No | 9/5/25 | 10/10/25 | NA | 1
10705 | BD 4 - MS 13 - Incorporate VPODs Feedback(Build Drop Update) | September 5, 2025 8:00 AM | October 10, 2025 5:00 PM | 4529FF | 4531 | As Soon As Possible | NA | 26 | 0d | July 22, 2025 8:00 AM | August 4, 2025 5:00 PM | 10 days | No | 9/5/25 | 10/10/25 | NA | 1
10706 | BD 4 - MS 13: Finalize Training Curriculum (Build Drop Update) | October 13, 2025 8:00 AM | October 17, 2025 5:00 PM | 4530 | 4537,4532FS+15d,4534FS+15d | As Soon As Possible | NA | 5 | 26d | August 5, 2025 8:00 AM | August 11, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
13917 | BD 4 -MS 13 - Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Update) | November 10, 2025 8:00 AM | November 17, 2025 5:00 PM | 4531FS+15d,590,591,592,593,594,595 | 4893 | As Soon As Possible | NA | 5 | 456d | NA | NA | 0 days? | No | NA | NA | NA | 0
10707 | MS 13 - Validate and Provide Feedback on Critical Scenarios for the EUST | June 3, 2025 8:00 AM | October 3, 2025 5:00 PM | 741FF | 4537 | As Soon As Possible | NA | 87 | 97d | July 28, 2025 8:00 AM | November 28, 2025 5:00 PM | 87 days | No | 6/3/25 | NA | NA | 0.95999999999999996
10708 | BD 4 -MS 13 - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | November 10, 2025 8:00 AM | December 22, 2025 5:00 PM | 4528,755SS,756SS,757SS,758SS,759SS,4531FS+15d,590,591,592,593,594,595 | 4535 | As Soon As Possible | NA | 29 | 26d | July 31, 2025 8:00 AM | November 14, 2025 5:00 PM | 75 days | No | NA | NA | NA | 0
10709 | BD 4 - MS 13 - Review Training Content with VPOD & TAW ( Build Drop Update) | December 23, 2025 8:00 AM | January 5, 2026 5:00 PM | 4534 | 4536 | As Soon As Possible | NA | 8 | 26d | August 14, 2025 8:00 AM | November 21, 2025 5:00 PM | 70 days | No | NA | NA | NA | 0
10710 | BD 4 - MS 13 - Incorporate Feedback from VPOD & TAW (Buiild Drop Update) | January 6, 2026 8:00 AM | January 16, 2026 5:00 PM | 4535 | 4537 | As Soon As Possible | NA | 9 | 26d | November 17, 2025 8:00 AM | December 1, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10711 | MS 13 - Finalize Training Content | January 20, 2026 8:00 AM | January 26, 2026 5:00 PM | 4536,4531,4533 | 4538,5611,5612,4790,4791,4904 | As Soon As Possible | NA | 5 | 26d | December 2, 2025 8:00 AM | December 8, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
10712 | Case Management Process Area Completed | January 26, 2026 5:00 PM | January 26, 2026 5:00 PM | 4374,4389,4401,4414,4425,4436,4443,4478,4493,4499,4515,4526,4537,5382,5388,5394,5400,5406,5419,5425,5433,5440,5448,5413,4379,4463 | 4925 | As Soon As Possible | NA | 0 | 409d | December 8, 2025 5:00 PM | December 8, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
10713 | Courts | June 28, 2024 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 395 | 429d | September 20, 2023 8:00 AM | January 2, 2026 5:00 PM | 573 days | No | 6/28/24 | NA | NA | 0.84999999999999998
10715 | Group 1 Courts Processing (Milestones 14, 16, 17, 18) | June 28, 2024 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 395 | 429d | September 20, 2023 8:00 AM | January 2, 2026 5:00 PM | 573 days | No | 6/28/24 | NA | NA | 0.84999999999999998
10741 | Courts Processing: Training | June 28, 2024 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 395 | 429d | September 20, 2023 8:00 AM | January 2, 2026 5:00 PM | 573 days | No | 6/28/24 | NA | NA | 0.84999999999999998
10742 | Develop End-To-End Business Scenarios | June 28, 2024 8:00 AM | August 1, 2024 5:00 PM | 5453SS | 4547,4543FF | As Soon As Possible | NA | 24 | 0d | June 28, 2024 8:00 AM | August 1, 2024 5:00 PM | 24 days | No | 6/28/24 | 8/1/24 | NA | 1
10743 | Review End-To-End Business Scenarios with VPODs | July 19, 2024 8:00 AM | August 1, 2024 5:00 PM | 4542FF | 4544FF+5d | As Soon As Possible | NA | 10 | 0d | July 19, 2024 8:00 AM | August 1, 2024 5:00 PM | 10 days | No | 7/19/24 | 8/1/24 | NA | 1
10744 | Incorporate VPODs Feedback | July 26, 2024 8:00 AM | August 8, 2024 5:00 PM | 4543FF+5d | 4545 | As Soon As Possible | NA | 10 | 0d | July 26, 2024 8:00 AM | August 8, 2024 5:00 PM | 10 days | No | 7/26/24 | 8/8/24 | NA | 1
10745 | MS14, 16, 17, 18 - Finalize End-To-End Business Scenarios | August 9, 2024 8:00 AM | August 14, 2024 5:00 PM | 4544 | 4925 | As Soon As Possible | NA | 4 | 0d | August 9, 2024 8:00 AM | August 14, 2024 5:00 PM | 4 days | No | 8/9/24 | 8/14/24 | NA | 1
10746 | Milestone 14 - Warrants | April 1, 2025 8:00 AM | November 14, 2025 5:00 PM |  |  | As Soon As Possible | NA | 160 | 476d | September 20, 2023 8:00 AM | December 29, 2025 5:00 PM | 570 days | No | 4/1/25 | NA | NA | 0.93999999999999995
10747 | MS 14 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 4542,864 | 4548FF | As Soon As Possible | NA | 90 | 0d | April 1, 2025 8:00 AM | June 24, 2025 5:00 PM | 60 days | No | 4/1/25 | 8/6/25 | NA | 1
10748 | Review Training Curriculum with VPODs | June 25, 2025 8:00 AM | August 6, 2025 5:00 PM | 4547FF | 4549FF | As Soon As Possible | NA | 30 | 0d | June 25, 2025 8:00 AM | July 9, 2025 5:00 PM | 10 days | No | 6/25/25 | 8/6/25 | NA | 1
10749 | Incorporate VPODs Feedback | July 2, 2025 8:00 AM | August 6, 2025 5:00 PM | 4548FF | 4550FF | As Soon As Possible | NA | 25 | 0d | July 2, 2025 8:00 AM | July 16, 2025 5:00 PM | 10 days | No | 7/2/25 | 8/6/25 | NA | 1
10750 | MS 14 - Finalize Training Curriculum | July 17, 2025 8:00 AM | August 6, 2025 5:00 PM | 4549FF | 4552FS+2d | As Soon As Possible | NA | 15 | 0d | July 17, 2025 8:00 AM | July 23, 2025 5:00 PM | 5 days | No | 7/17/25 | 8/6/25 | NA | 1
10751 | MS 14 - Validate and Provide Feedback on Critical Scenarios for the EUST | May 19, 2025 8:00 AM | November 14, 2025 5:00 PM | 409FS+289d |  | As Soon As Possible | NA | 126 | 476d | September 20, 2023 8:00 AM | March 22, 2024 5:00 PM | 126 days | No | 5/19/25 | NA | NA | 0.81000000000000005
13915 | BD 3 - MS 14: - Discovery and Develop Training Curriculum (Build Drop Update) | August 11, 2025 8:00 AM | September 3, 2025 5:00 PM | 4550FS+2d | 4553SS,4554SS | As Soon As Possible | NA | 17 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/3/25 | NA | 1
13916 | BD 3 - MS 14: - Review Training Curriculum with VPODs(Build Drop Update) | August 11, 2025 8:00 AM | September 3, 2025 5:00 PM | 4552SS |  | As Soon As Possible | NA | 17 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/3/25 | NA | 1
13914 | BD 3 - MS 14: - Incorporate VPODs Feedback(Build Drop Update) | August 11, 2025 8:00 AM | September 3, 2025 5:00 PM | 4552SS | 4555FS-10d | As Soon As Possible | NA | 17 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/3/25 | NA | 1
13913 | BD 3 - MS 14: Finalize Training Curriculum (Build Drop Update) | August 20, 2025 8:00 AM | September 3, 2025 5:00 PM | 4554FS-10d | 4556SS | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 8/20/25 | 9/3/25 | NA | 1
10752 | BD 3 - MS 14: - Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Update) | August 20, 2025 8:00 AM | September 3, 2025 5:00 PM | 411SS,4555SS | 4557FS-6d | As Soon As Possible | NA | 10 | 0d | June 25, 2025 8:00 AM | December 5, 2025 5:00 PM | 114 days | No | 8/20/25 | 9/3/25 | NA | 1
13912 | BD 3 - MS 14: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | August 26, 2025 8:00 AM | September 3, 2025 5:00 PM | 4556FS-6d | 4558FS+2d | As Soon As Possible | NA | 6 | 0d | NA | NA | 0 days? | No | 8/26/25 | 9/3/25 | NA | 1
10753 | BD 3 - MS 14: - Review Training Content with VPOD & TAW (Build Drop Update) | September 8, 2025 8:00 AM | September 19, 2025 5:00 PM | 4557FS+2d | 4559 | As Soon As Possible | NA | 10 | 0d | July 28, 2025 8:00 AM | December 12, 2025 5:00 PM | 97 days | No | 9/8/25 | 9/19/25 | NA | 1
10754 | BD 3 - MS 14: - Incorporate Feedback from VPOD & TAW (Build Drop Update) | September 22, 2025 8:00 AM | October 3, 2025 5:00 PM | 4558 | 4560 | As Soon As Possible | NA | 10 | 0d | December 8, 2025 8:00 AM | December 19, 2025 5:00 PM | 10 days | No | 9/22/25 | 10/3/25 | NA | 1
10755 | MS 14 - Finalize Training Content | October 6, 2025 8:00 AM | October 10, 2025 5:00 PM | 4559 | 4606,5611,5612,4792,4793,4893 | As Soon As Possible | NA | 5 | 0d | December 22, 2025 8:00 AM | December 29, 2025 5:00 PM | 5 days | No | 10/6/25 | 10/10/25 | NA | 1
10756 | Milestone 16 - Jurisdiction and Disposition Hearing | April 1, 2025 8:00 AM | December 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 180 | 53d | April 1, 2025 8:00 AM | January 2, 2026 5:00 PM | 192 days | No | 4/1/25 | NA | NA | 0.83999999999999997
10761 | MS 16 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 864 | 4563FF | As Soon As Possible | NA | 90 | 0d | April 1, 2025 8:00 AM | June 24, 2025 5:00 PM | 60 days | No | 4/1/25 | 8/6/25 | NA | 1
10762 | Review Training Curriculum with VPODs | June 25, 2025 8:00 AM | August 6, 2025 5:00 PM | 4562FF | 4564FF | As Soon As Possible | NA | 30 | 0d | June 25, 2025 8:00 AM | July 9, 2025 5:00 PM | 10 days | No | 6/25/25 | 8/6/25 | NA | 1
10763 | Incorporate VPODs Feedback | July 2, 2025 8:00 AM | August 6, 2025 5:00 PM | 4563FF | 4565FF | As Soon As Possible | NA | 25 | 0d | July 2, 2025 8:00 AM | July 16, 2025 5:00 PM | 10 days | No | 7/2/25 | 8/6/25 | NA | 1
10764 | MS 16 - Finalize Training Curriculum | July 17, 2025 8:00 AM | August 6, 2025 5:00 PM | 4564FF | 4575 | As Soon As Possible | NA | 15 | 0d | July 17, 2025 8:00 AM | July 23, 2025 5:00 PM | 5 days | No | 7/17/25 | 8/6/25 | NA | 1
10765 | MS 16 - Validate and Provide Feedback on Critical Scenarios for the EUST | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 884SS-20d | 4575 | As Soon As Possible | NA | 126 | 59d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 6/2/25 | NA | NA | 0.73999999999999999
13910 | BD 3 - MS 16: - Discovery and Develop Training Curriculum (Build Drop Update) | August 11, 2025 8:00 AM | September 26, 2025 5:00 PM | 867,868,869,882,883,884 | 4568SS | As Soon As Possible | NA | 34 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/26/25 | NA | 1
13911 | BD 3 - MS 16: - Review Training Curriculum with VPODs(Build Drop Update) | August 11, 2025 8:00 AM | September 26, 2025 5:00 PM | 4567SS | 4569SS | As Soon As Possible | NA | 34 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/26/25 | NA | 1
13909 | BD 3 - MS 16: - Incorporate VPODs Feedback(Build Drop Update) | August 11, 2025 8:00 AM | September 26, 2025 5:00 PM | 4568SS | 4570FS-27d | As Soon As Possible | NA | 34 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/26/25 | NA | 1
13908 | BD 3 - MS 16: Finalize Training Curriculum (Build Drop Update) | August 20, 2025 8:00 AM | September 26, 2025 5:00 PM | 4569FS-27d | 4571FS-23d | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 8/20/25 | 9/26/25 | NA | 1
10766 | BD 3 - MS 16: - Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Update) | August 26, 2025 8:00 AM | September 26, 2025 5:00 PM | 4570FS-23d,882,883,884 | 4572FS+5d,4893 | As Soon As Possible | NA | 23 | 0d | June 25, 2025 8:00 AM | December 10, 2025 5:00 PM | 117 days | No | 8/26/25 | 9/26/25 | NA | 1
13907 | BD 3 - MS 16: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update | October 6, 2025 8:00 AM | November 10, 2025 5:00 PM | 4571FS+5d,882,883,884 | 4573 | As Soon As Possible | NA | 26 | 53d | NA | NA | 0 days? | No | 10/6/25 | NA | NA | 0.19
10767 | BD 3- MS 16: - Review Training Content with VPOD & TAW (Build Drop Update) | November 12, 2025 8:00 AM | November 24, 2025 5:00 PM | 4572 | 4574 | As Soon As Possible | NA | 9 | 53d | July 28, 2025 8:00 AM | December 17, 2025 5:00 PM | 100 days | No | NA | NA | NA | 0
10768 | BD 3 - MS 16: - Incorporate Feedback from VPOD & TAW (Build Drop Update) | November 25, 2025 8:00 AM | December 8, 2025 5:00 PM | 4573 | 4575 | As Soon As Possible | NA | 9 | 53d | December 11, 2025 8:00 AM | December 24, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10769 | MS 16 - Finalize Training Content | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 4574,4565,4566 | 4606,5611,5612,4794,4795,4899 | As Soon As Possible | NA | 5 | 53d | December 26, 2025 8:00 AM | January 2, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
10770 | Milestone 17 - Status Review | April 1, 2025 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 207 | 429d | April 1, 2025 8:00 AM | December 29, 2025 5:00 PM | 189 days | No | 4/1/25 | NA | NA | 0.77000000000000002
10775 | MS 17 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 864 | 4578FF | As Soon As Possible | NA | 90 | 0d | April 1, 2025 8:00 AM | June 24, 2025 5:00 PM | 60 days | No | 4/1/25 | 8/6/25 | NA | 1
10776 | Review Training Curriculum with VPODs | June 25, 2025 8:00 AM | August 6, 2025 5:00 PM | 4577FF | 4579FF | As Soon As Possible | NA | 30 | 0d | June 25, 2025 8:00 AM | July 9, 2025 5:00 PM | 10 days | No | 6/25/25 | 8/6/25 | NA | 1
10777 | Incorporate VPODs Feedback | July 2, 2025 8:00 AM | August 6, 2025 5:00 PM | 4578FF | 4580FF | As Soon As Possible | NA | 25 | 0d | July 2, 2025 8:00 AM | July 16, 2025 5:00 PM | 10 days | No | 7/2/25 | 8/6/25 | NA | 1
10778 | MS 17 - Finalize Training Curriculum | July 17, 2025 8:00 AM | August 6, 2025 5:00 PM | 4579FF | 4590 | As Soon As Possible | NA | 15 | 0d | July 17, 2025 8:00 AM | July 23, 2025 5:00 PM | 5 days | No | 7/17/25 | 8/6/25 | NA | 1
10779 | MS 17 - Validate and Provide Feedback on Critical Scenarios for the EUST | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 889SS-20d | 4590 | As Soon As Possible | NA | 126 | 59d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 6/2/25 | NA | NA | 0.73999999999999999
13905 | BD 3 - MS 17: - Discovery and Develop Training Curriculum (Build Drop Update) | August 11, 2025 8:00 AM | October 24, 2025 5:00 PM | 871,872,873,874,886,887,888,889 | 4583SS | As Soon As Possible | NA | 54 | 490d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.81000000000000005
13906 | BD 3 - MS 17: - Review Training Curriculum with VPODs(Build Drop Update) | August 11, 2025 8:00 AM | October 24, 2025 5:00 PM | 4582SS | 4584SS | As Soon As Possible | NA | 54 | 490d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.81000000000000005
13904 | BD 3 - MS 17: - Incorporate VPODs Feedback(Build Drop Update) | August 11, 2025 8:00 AM | October 24, 2025 5:00 PM | 4583SS | 4585SS+7d | As Soon As Possible | NA | 54 | 490d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.81000000000000005
13903 | BD 3 - MS 17: Finalize Training Curriculum (Build Drop Update) | August 20, 2025 8:00 AM | October 24, 2025 5:00 PM | 4584SS+7d | 4586SS+4d | As Soon As Possible | NA | 47 | 490d | NA | NA | 0 days? | No | 8/20/25 | NA | NA | 0.79000000000000004
10780 | BD 4 - MS 17: - Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Update) | August 26, 2025 8:00 AM | October 24, 2025 5:00 PM | 4585SS+4d,886,887,888,889 | 4587FS+10d,4893 | As Soon As Possible | NA | 43 | 26d | June 25, 2025 8:00 AM | December 5, 2025 5:00 PM | 114 days | No | 8/26/25 | NA | NA | 0.77000000000000002
13902 | BD 4 - MS 17: - Develop Training Content - On-Demand Programs and Lessos (Build Drop Update) | November 10, 2025 8:00 AM | December 22, 2025 5:00 PM | 4586FS+10d,886,887,888,889 | 4588 | As Soon As Possible | NA | 29 | 26d | NA | NA | 0 days? | No | NA | NA | NA | 0
10781 | BD 3 - MS 17: - Review Training Content with VPOD & TAW (Build Drop Update) | December 23, 2025 8:00 AM | January 5, 2026 5:00 PM | 4587 | 4589 | As Soon As Possible | NA | 8 | 26d | July 28, 2025 8:00 AM | December 12, 2025 5:00 PM | 97 days | No | NA | NA | NA | 0
10782 | BD 3 - MS 17: - Incorporate Feedback from VPOD & TAW (Build Drop Update) | January 6, 2026 8:00 AM | January 16, 2026 5:00 PM | 4588 | 4590 | As Soon As Possible | NA | 9 | 26d | December 8, 2025 8:00 AM | December 19, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10783 | MS 17 - Finalize Training Content | January 20, 2026 8:00 AM | January 26, 2026 5:00 PM | 4589,4580,4581 | 4606,5611,5612,4796,4797,4904 | As Soon As Possible | NA | 5 | 26d | December 22, 2025 8:00 AM | December 29, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
10784 | Milestone 18 - Other Hearing | April 1, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 169 | 467d | April 1, 2025 8:00 AM | December 29, 2025 5:00 PM | 189 days | No | 4/1/25 | NA | NA | 0.85999999999999999
10789 | MS 18 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 864 | 4593FF | As Soon As Possible | NA | 90 | 0d | April 1, 2025 8:00 AM | June 24, 2025 5:00 PM | 60 days | No | 4/1/25 | 8/6/25 | NA | 1
10790 | Review Training Curriculum with VPODs | June 25, 2025 8:00 AM | August 6, 2025 5:00 PM | 4592FF | 4594FF | As Soon As Possible | NA | 30 | 0d | June 25, 2025 8:00 AM | July 9, 2025 5:00 PM | 10 days | No | 6/25/25 | 8/6/25 | NA | 1
10791 | Incorporate VPODs Feedback | July 2, 2025 8:00 AM | August 6, 2025 5:00 PM | 4593FF | 4595FF | As Soon As Possible | NA | 25 | 0d | July 2, 2025 8:00 AM | July 16, 2025 5:00 PM | 10 days | No | 7/2/25 | 8/6/25 | NA | 1
10792 | MS 18 - Finalize Training Curriculum | July 17, 2025 8:00 AM | August 6, 2025 5:00 PM | 4594FF | 4605 | As Soon As Possible | NA | 15 | 0d | July 17, 2025 8:00 AM | July 23, 2025 5:00 PM | 5 days | No | 7/17/25 | 8/6/25 | NA | 1
10793 | MS 18 - Validate and Provide Feedback on Critical Scenarios for the EUST | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 893SS-20d |  | As Soon As Possible | NA | 126 | 467d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 6/2/25 | NA | NA | 0.73999999999999999
13900 | BD 3 - MS 18 - Discovery and Develop Training Curriculum (Build Drop Update) | August 11, 2025 8:00 AM | September 2, 2025 5:00 PM | 876,877,878,879,891,892,893,894 | 4598SS | As Soon As Possible | NA | 16 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/2/25 | NA | 1
13901 | BD 3 - MS 18 - Review Training Curriculum with VPODs(Build Drop Update) | August 11, 2025 8:00 AM | September 2, 2025 5:00 PM | 4597SS | 4599FF | As Soon As Possible | NA | 16 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/2/25 | NA | 1
13899 | BD 3 - MS 18 - Incorporate VPODs Feedback(Build Drop Update) | August 11, 2025 8:00 AM | September 2, 2025 5:00 PM | 4598FF | 4600FS-9d | As Soon As Possible | NA | 16 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/2/25 | NA | 1
13898 | BD 3 - MS 18: Finalize Training Curriculum (Build Drop Update) | August 20, 2025 8:00 AM | September 2, 2025 5:00 PM | 4599FS-9d | 4601FS-5d | As Soon As Possible | NA | 9 | 0d | NA | NA | 0 days? | No | 8/20/25 | 9/2/25 | NA | 1
10794 | BD 3 - MS 18 - Develop Training Content - Quick Guides, Knowledge Base Articles (Build Drop Update) | August 26, 2025 8:00 AM | September 2, 2025 5:00 PM | 4600FS-5d,891,892,893 | 4602FS+3d | As Soon As Possible | NA | 5 | 0d | June 25, 2025 8:00 AM | December 5, 2025 5:00 PM | 114 days | No | 8/26/25 | 9/2/25 | NA | 1
13897 | BD 3 - MS 18 - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | September 8, 2025 8:00 AM | October 6, 2025 5:00 PM | 4601FS+3d | 4603 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/8/25 | 10/6/25 | NA | 1
10795 | BD 3 - MS 18 - Review Training Content with VPOD & TAW (Build Drop Update) | October 7, 2025 8:00 AM | October 20, 2025 5:00 PM | 4602 | 4604 | As Soon As Possible | NA | 10 | 76d | July 28, 2025 8:00 AM | December 12, 2025 5:00 PM | 97 days | No | 10/7/25 | NA | NA | 0.40000000000000002
10796 | BD 3 - MS 18 - Incorporate Feedback from VPOD & TAW (Build Drop Update) | October 21, 2025 8:00 AM | November 3, 2025 5:00 PM | 4603 | 4605 | As Soon As Possible | NA | 10 | 76d | December 8, 2025 8:00 AM | December 19, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10797 | MS 18 - Finalize Training Content | November 4, 2025 8:00 AM | November 10, 2025 5:00 PM | 4604,4595 | 4606,5611,5612,4798,4799,4893 | As Soon As Possible | NA | 5 | 76d | December 22, 2025 8:00 AM | December 29, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
10798 | Courts Process Area Completed | January 26, 2026 5:00 PM | January 26, 2026 5:00 PM | 4560,4575,4590,4605 | 4925 | As Soon As Possible | NA | 0 | 409d | January 2, 2026 5:00 PM | January 2, 2026 5:00 PM | 0 days | Yes | NA | NA | NA | 0
10799 | Eligibility | August 5, 2024 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 370 | 409d | November 1, 2024 8:00 AM | December 5, 2025 5:00 PM | 273 days | No | 8/5/24 | NA | NA | 0.88
10801 | Group 1 Eligibility (Milestones 21) | August 5, 2024 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 370 | 409d | November 1, 2024 8:00 AM | December 5, 2025 5:00 PM | 273 days | No | 8/5/24 | NA | NA | 0.88
10809 | Eligibility: Training | August 5, 2024 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 370 | 409d | November 1, 2024 8:00 AM | December 5, 2025 5:00 PM | 273 days | No | 8/5/24 | NA | NA | 0.88
10810 | MS21 - Develop End-To-End Business Scenarios | August 5, 2024 8:00 AM | August 23, 2024 5:00 PM | 5479SS+5d | 4611FF+10d | As Soon As Possible | NA | 15 | 0d | November 1, 2024 8:00 AM | December 20, 2024 5:00 PM | 33 days | No | 8/5/24 | 8/23/24 | NA | 1
10811 | Review End-To-End Business Scenarios with VPODs | August 26, 2024 8:00 AM | September 6, 2024 5:00 PM | 4610FF+10d | 4612FF+5d | As Soon As Possible | NA | 10 | 0d | December 9, 2024 8:00 AM | December 20, 2024 5:00 PM | 10 days | No | 8/26/24 | 9/6/24 | NA | 1
10812 | Incorporate VPODs Feedback | August 26, 2024 8:00 AM | September 13, 2024 5:00 PM | 4611FF+5d | 4613 | As Soon As Possible | NA | 10 | 0d | December 16, 2024 8:00 AM | December 30, 2024 5:00 PM | 10 days | No | 8/26/24 | 9/13/24 | NA | 1
10813 | MS 21 - Finalize End-To-End Business Scenarios | September 16, 2024 8:00 AM | September 20, 2024 5:00 PM | 4612 | 4615FS+89d | As Soon As Possible | NA | 5 | 0d | December 31, 2024 8:00 AM | January 7, 2025 5:00 PM | 5 days | No | 9/16/24 | 9/20/24 | NA | 1
10814 | Milestone 21 - Eligibility Programs | February 3, 2025 8:00 AM | January 26, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 26d | January 8, 2025 8:00 AM | December 5, 2025 5:00 PM | 230 days | No | 2/3/25 | NA | NA | 0.88
10815 | MS 21 - Develop Training Curriculum | February 3, 2025 8:00 AM | August 6, 2025 5:00 PM | 4613FS+89d | 4616FF,4617FF,4621FS+2d | As Soon As Possible | NA | 129 | 0d | January 8, 2025 8:00 AM | March 7, 2025 5:00 PM | 41 days | No | 2/3/25 | 8/6/25 | NA | 1
11723 | MS 21 - Complete Training Curriculum | March 4, 2025 8:00 AM | August 6, 2025 5:00 PM | 4615FF | 4617FF | As Soon As Possible | NA | 109 | 0d | NA | NA | 0 days? | No | 3/4/25 | 8/6/25 | NA | 1
10816 | Review Training Curriculum with VPODs | April 3, 2025 8:00 AM | August 6, 2025 5:00 PM | 4615FF,4616FF | 4618FF | As Soon As Possible | NA | 88 | 0d | March 10, 2025 8:00 AM | March 21, 2025 5:00 PM | 10 days | No | 4/3/25 | 8/6/25 | NA | 1
10817 | Incorporate VPODs Feedback | April 10, 2025 8:00 AM | August 6, 2025 5:00 PM | 4617FF | 4619FF | As Soon As Possible | NA | 83 | 0d | March 17, 2025 8:00 AM | March 28, 2025 5:00 PM | 10 days | No | 4/10/25 | 8/6/25 | NA | 1
10818 | MS 21 - Finalize Training Curriculum | April 24, 2025 8:00 AM | August 6, 2025 5:00 PM | 4618FF | 4629 | As Soon As Possible | NA | 73 | 0d | April 1, 2025 8:00 AM | April 7, 2025 5:00 PM | 5 days | No | 4/24/25 | 8/6/25 | NA | 1
10819 | MS 21 - Validate and Provide Feedback on Critical Scenarios for the EUST | July 21, 2025 8:00 AM | November 28, 2025 5:00 PM | 1242FF | 4629FS-3d | As Soon As Possible | NA | 92 | 62d | July 21, 2025 8:00 AM | November 28, 2025 5:00 PM | 92 days | No | 7/21/25 | NA | NA | 0.64000000000000001
13894 | BD 3 - MS 21: - Discovery and Develop Training Curriculum (Build Drop Update) | August 11, 2025 8:00 AM | September 2, 2025 5:00 PM | 4615FS+2d | 4622SS | As Soon As Possible | NA | 16 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/2/25 | NA | 1
13895 | BD 3 - MS 21: - Review Training Curriculum with VPODs(Build Drop Update) | August 11, 2025 8:00 AM | September 2, 2025 5:00 PM | 4621SS | 4623FF | As Soon As Possible | NA | 16 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/2/25 | NA | 1
13893 | BD 3 - MS 21: - Incorporate VPODs Feedback(Build Drop Update) | August 11, 2025 8:00 AM | September 2, 2025 5:00 PM | 4622FF | 4624FS-9d | As Soon As Possible | NA | 16 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/2/25 | NA | 1
13892 | BD 3 - MS 21: Finalize Training Curriculum (Build Drop Update) | August 20, 2025 8:00 AM | September 2, 2025 5:00 PM | 4623FS-9d | 4625FS-5d | As Soon As Possible | NA | 9 | 0d | NA | NA | 0 days? | No | 8/20/25 | 9/2/25 | NA | 1
10820 | BD 3 - MS 21: - Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Update) | August 26, 2025 8:00 AM | September 2, 2025 5:00 PM | 4624FS-5d | 4626FS+48d,4893 | As Soon As Possible | NA | 5 | 0d | May 30, 2025 8:00 AM | November 7, 2025 5:00 PM | 114 days | No | 8/26/25 | 9/2/25 | NA | 1
13891 | BD 3 - MS 21: - Develop Training Content - On -Demand Programs and Lessons (Build Drop Update) | November 10, 2025 8:00 AM | December 22, 2025 5:00 PM | 4625FS+48d | 4627 | As Soon As Possible | NA | 29 | 26d | NA | NA | 0 days? | No | NA | NA | NA | 0
10821 | BD 3 - MS 21: - Review Training Content with VPOD& TAW (Build Drop Update) | December 23, 2025 8:00 AM | January 5, 2026 5:00 PM | 4626 | 4628 | As Soon As Possible | NA | 8 | 26d | July 1, 2025 8:00 AM | November 17, 2025 5:00 PM | 97 days | No | NA | NA | NA | 0
10822 | BD 3 - MS 21: - Incorporate Feedback from VPOD& TAW (Build Drop Update) | January 6, 2026 8:00 AM | January 16, 2026 5:00 PM | 4627 | 4629 | As Soon As Possible | NA | 9 | 26d | November 10, 2025 8:00 AM | November 24, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10823 | MS 21 - Finalize Training Content | January 20, 2026 8:00 AM | January 26, 2026 5:00 PM | 4628,4619,4620FS-3d | 4630,5611,5612,4800,4801,4904 | Start No Earlier Than | 12/1/25 | 5 | 26d | December 1, 2025 8:00 AM | December 5, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
10824 | Eligibility Process Area Completed | January 26, 2026 5:00 PM | January 26, 2026 5:00 PM | 4629 | 4925 | Start No Earlier Than | 12/5/25 | 0 | 409d | December 5, 2025 5:00 PM | December 5, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
10825 | Resource Family Approval | August 12, 2024 8:00 AM | April 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 423 | 351d | September 23, 2024 8:00 AM | December 30, 2025 5:00 PM | 318 days | No | 8/12/24 | NA | NA | 0.34999999999999998
10827 | Group 1 Resource Family Approval (Milestones 26/26.1, 27, 28) | August 12, 2024 8:00 AM | April 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 423 | -32d | September 23, 2024 8:00 AM | December 30, 2025 5:00 PM | 318 days | No | 8/12/24 | NA | NA | 0.34999999999999998
10847 | Resource Family Approval: Training | August 12, 2024 8:00 AM | September 27, 2024 5:00 PM |  |  | As Soon As Possible | NA | 35 | 0d | September 23, 2024 8:00 AM | December 30, 2025 5:00 PM | 318 days | No | 8/12/24 | 9/27/24 | NA | 1
10848 | MS26/26.1, 27, 28 - Develop End-To-End Business Scenarios | August 12, 2024 8:00 AM | August 27, 2024 5:00 PM | 5487SS+5d | 4639,4635FS+8d | As Soon As Possible | NA | 12 | 0d | September 23, 2024 8:00 AM | November 6, 2024 5:00 PM | 33 days | No | 8/12/24 | 8/27/24 | NA | 1
10849 | Review End-To-End Business Scenarios with VPODs | September 9, 2024 8:00 AM | September 13, 2024 5:00 PM | 4634FS+8d | 4636FF+5d | As Soon As Possible | NA | 5 | 0d | October 24, 2024 8:00 AM | November 6, 2024 5:00 PM | 10 days | No | 9/9/24 | 9/13/24 | NA | 1
10850 | Incorporate VPODs Feedback | September 9, 2024 8:00 AM | September 20, 2024 5:00 PM | 4635FF+5d | 4637 | As Soon As Possible | NA | 10 | 0d | October 31, 2024 8:00 AM | November 14, 2024 5:00 PM | 10 days | No | 9/9/24 | 9/20/24 | NA | 1
10851 | MS26/26.1, 27, 28 - Finalize End-To-End Business Scenarios | September 23, 2024 8:00 AM | September 27, 2024 5:00 PM | 4636 | 4925 | As Soon As Possible | NA | 5 | 0d | November 15, 2024 8:00 AM | November 21, 2024 5:00 PM | 5 days | No | 9/23/24 | 9/27/24 | NA | 1
10852 | Milestone 26/26.1 - Maintain Resource Family Home | June 2, 2025 8:00 AM | March 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 203 | -13d | May 5, 2025 8:00 AM | December 26, 2025 5:00 PM | 164 days | No | 6/2/25 | NA | NA | 0.33000000000000002
10853 | BD 5 - MS 26/26.1: - Discovery and Develop Training Curriculum (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 4634,1008,1011FS-19d,1029FS-19d | 4640SS | As Soon As Possible | NA | 30 | -13d | May 5, 2025 8:00 AM | September 10, 2025 5:00 PM | 90 days | No | NA | NA | NA | 0
10854 | BD 5 - MS 26/26.1: - Review Training Curriculum with VPODs(Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 4639SS | 4641FF | As Soon As Possible | NA | 30 | -13d | September 11, 2025 8:00 AM | September 24, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10855 | BD 5 - MS 26/26.1: - Incorporate VPODs Feedback(Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 4640FF | 4642FS-5d,4644FS-5d | As Soon As Possible | NA | 30 | -13d | September 18, 2025 8:00 AM | October 1, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10856 | BD 5 - MS 26/26.1: Finalize Training Curriculum (Build Drop Update) | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 4641FS-5d | 4648 | As Soon As Possible | NA | 5 | 48d | October 2, 2025 8:00 AM | October 8, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
10857 | MS 26/26.1 - Validate and Provide Feedback on Critical Scenarios for the EUST | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 1035FF | 4648 | As Soon As Possible | NA | 126 | 59d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 6/2/25 | NA | NA | 0.73999999999999999
13890 | BD 5 - MS 26/26.1: - Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Update) | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 4641FS-5d,1427 | 4645FS+12d | As Soon As Possible | NA | 5 | -13d | NA | NA | 0 days? | No | NA | NA | NA | 0
10858 | BD 5 - MS 26/26.1: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | January 5, 2026 8:00 AM | February 13, 2026 5:00 PM | 4644FS+12d | 4646 | As Soon As Possible | NA | 29 | -13d | May 30, 2025 8:00 AM | November 26, 2025 5:00 PM | 126 days | No | NA | NA | NA | 0
10859 | BD 5 - MS 26/26.1: - Review Training Content with VPOD & TAW (Build Drop Update) | February 17, 2026 8:00 AM | March 2, 2026 5:00 PM | 4645 | 4647 | As Soon As Possible | NA | 10 | -13d | July 1, 2025 8:00 AM | December 11, 2025 5:00 PM | 114 days | No | NA | NA | NA | 0
10860 | BD 5 - MS 26/26.1: - Incorporate Feedback from VPOD & TAW (Build Drop Update) | March 3, 2026 8:00 AM | March 16, 2026 5:00 PM | 4646 | 4648 | As Soon As Possible | NA | 10 | -13d | December 5, 2025 8:00 AM | December 18, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10861 | MS 26/26.1 - Finalize Training Content | March 17, 2026 8:00 AM | March 23, 2026 5:00 PM | 4647,4642,4643 | 4671,5611,5612,4806,4807 | As Soon As Possible | NA | 5 | -13d | December 19, 2025 8:00 AM | December 26, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
10862 | Milestone 27 - Complaints | June 2, 2025 8:00 AM | March 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 203 | -13d | May 5, 2025 8:00 AM | December 30, 2025 5:00 PM | 166 days | No | 6/2/25 | NA | NA | 0.33000000000000002
10867 | BD 5 - MS 27: - Discovery and Develop Training Curriculum (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 1008,1019SS+19d,1020SS | 4651SS | As Soon As Possible | NA | 30 | -13d | May 5, 2025 8:00 AM | September 10, 2025 5:00 PM | 90 days | No | NA | NA | NA | 0
10868 | BD 5 - MS 27: - Review Training Curriculum with VPODs(Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 4650SS | 4652SS | As Soon As Possible | NA | 30 | -13d | September 11, 2025 8:00 AM | September 24, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10869 | BD 5 - MS 27: - Incorporate VPODs Feedback(Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 4651SS | 4653FS-5d,4655FS-5d | As Soon As Possible | NA | 30 | -13d | September 18, 2025 8:00 AM | October 1, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10870 | BD 5- MS 27: Finalize Training Curriculum (Build Drop Update) | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 4652FS-5d | 4659 | As Soon As Possible | NA | 5 | 48d | October 2, 2025 8:00 AM | October 8, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
10871 | MS 27 - Validate and Provide Feedback on Critical Scenarios for the EUST | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 1040FF | 4659 | As Soon As Possible | NA | 126 | 59d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 6/2/25 | NA | NA | 0.73999999999999999
13889 | BD 5 - MS 27: - Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Update) | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 4652FS-5d | 4656FS+12d | As Soon As Possible | NA | 5 | -13d | NA | NA | 0 days? | No | NA | NA | NA | 0
10872 | BD 5 - MS 27: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | January 5, 2026 8:00 AM | February 13, 2026 5:00 PM | 4655FS+12d | 4657 | As Soon As Possible | NA | 29 | -13d | June 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 126 days | No | NA | NA | NA | 0
10873 | BD 5 - MS 27: - Review Training Content with VPOD & TAW (Build Drop Update) | February 17, 2026 8:00 AM | March 2, 2026 5:00 PM | 4656 | 4658 | As Soon As Possible | NA | 10 | -13d | July 3, 2025 8:00 AM | December 15, 2025 5:00 PM | 114 days | No | NA | NA | NA | 0
10874 | BD 5 - MS 27: - Incorporate Feedback from VPOD & TAW (Build Drop Update) | March 3, 2026 8:00 AM | March 16, 2026 5:00 PM | 4657 | 4659 | As Soon As Possible | NA | 10 | -13d | December 9, 2025 8:00 AM | December 22, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10875 | MS 27 - Finalize Training Content | March 17, 2026 8:00 AM | March 23, 2026 5:00 PM | 4658,4653,4654 | 4671,5611,5612,4808,4809 | As Soon As Possible | NA | 5 | -13d | December 23, 2025 8:00 AM | December 30, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
10876 | Milestone 28 - Legal Action | June 2, 2025 8:00 AM | April 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 222 | -32d | May 5, 2025 8:00 AM | December 30, 2025 5:00 PM | 166 days | No | 6/2/25 | NA | NA | 0.31
10881 | BD 5 - MS 28: - Discovery and Develop Training Curriculum (Build Drop Update) | December 1, 2025 8:00 AM | January 13, 2026 5:00 PM | 1024FS-19d,1025FS-19d,1026FS-19d | 4662SS | As Soon As Possible | NA | 30 | -32d | May 5, 2025 8:00 AM | September 10, 2025 5:00 PM | 90 days | No | NA | NA | NA | 0
10882 | BD 5 - MS 28: - Review Training Curriculum with VPODs(Build Drop Update) | December 1, 2025 8:00 AM | January 13, 2026 5:00 PM | 4661SS | 4663SS | As Soon As Possible | NA | 30 | -32d | September 11, 2025 8:00 AM | September 24, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10883 | BD 5 - MS 28: - Incorporate VPODs Feedback(Build Drop Update) | December 1, 2025 8:00 AM | January 13, 2026 5:00 PM | 4662SS | 4664FS-5d,4666FS-5d | As Soon As Possible | NA | 30 | -32d | September 18, 2025 8:00 AM | October 1, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10884 | BD 5 - MS 28: Finalize Training Curriculum (Build Drop Update) | January 7, 2026 8:00 AM | January 13, 2026 5:00 PM | 4663FS-5d | 4670 | As Soon As Possible | NA | 5 | 29d | October 2, 2025 8:00 AM | October 8, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
10885 | MS 28 - Validate and Provide Feedback on Critical Scenarios for the EUST | June 2, 2025 8:00 AM | December 26, 2025 5:00 PM | 1044FF | 4670 | As Soon As Possible | NA | 126 | 40d | June 2, 2025 8:00 AM | November 28, 2025 5:00 PM | 126 days | No | 6/2/25 | NA | NA | 0.69999999999999996
13888 | BD 5 - MS 28: - Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Update) | January 7, 2026 8:00 AM | January 13, 2026 5:00 PM | 4663FS-5d | 4667FS+12d | As Soon As Possible | NA | 5 | -32d | NA | NA | 0 days? | No | NA | NA | NA | 0
10886 | BD 5 - MS 28: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | February 2, 2026 8:00 AM | March 13, 2026 5:00 PM | 4666FS+12d | 4668 | As Soon As Possible | NA | 29 | -32d | June 3, 2025 8:00 AM | December 1, 2025 5:00 PM | 126 days | No | NA | NA | NA | 0
10887 | BD 5 - MS 28: - Review Training Content with VPOD & TAW (Build Drop Update) | March 16, 2026 8:00 AM | March 27, 2026 5:00 PM | 4667 | 4669 | As Soon As Possible | NA | 10 | -32d | July 3, 2025 8:00 AM | December 15, 2025 5:00 PM | 114 days | No | NA | NA | NA | 0
10888 | BD 5 - MS 28: - Incorporate Feedback from VPOD & TAW (Build Drop Update) | March 30, 2026 8:00 AM | April 13, 2026 5:00 PM | 4668 | 4670 | As Soon As Possible | NA | 10 | -32d | December 9, 2025 8:00 AM | December 22, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10889 | MS 28 - Finalize Training Content | April 14, 2026 8:00 AM | April 20, 2026 5:00 PM | 4669,4664,4665 | 4671,5611,5612,4810,4811 | As Soon As Possible | NA | 5 | -32d | December 23, 2025 8:00 AM | December 30, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
10890 | Resource Family Approval Process Area Completed | April 20, 2026 5:00 PM | April 20, 2026 5:00 PM | 4648,4659,4670 | 4925 | As Soon As Possible | NA | 0 | 351d | December 30, 2025 5:00 PM | December 30, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
10891 | Financial Management | December 2, 2024 8:00 AM | May 14, 2026 5:00 PM |  |  | As Soon As Possible | NA | 364 | 334d | December 16, 2024 8:00 AM | February 3, 2026 5:00 PM | 284 days | No | 12/2/24 | NA | NA | 0.55000000000000004
10893 | Group 1 Financial Management (Milestones 23/23.1, 24) | December 2, 2024 8:00 AM | May 14, 2026 5:00 PM |  |  | As Soon As Possible | NA | 364 | 334d | December 16, 2024 8:00 AM | February 3, 2026 5:00 PM | 284 days | No | 12/2/24 | NA | NA | 0.55000000000000004
10907 | Financial Management: Training | December 2, 2024 8:00 AM | January 16, 2025 5:00 PM |  |  | As Soon As Possible | NA | 32 | 0d | December 16, 2024 8:00 AM | February 3, 2026 5:00 PM | 284 days | No | 12/2/24 | 1/16/25 | NA | 1
10908 | MS 23/23.1, 24 - Develop End-To-End Business Scenarios | December 2, 2024 8:00 AM | January 2, 2025 5:00 PM | 5507FS+5d | 4680FS-24d,4676FF,4684 | As Soon As Possible | NA | 22 | 0d | December 16, 2024 8:00 AM | January 16, 2025 5:00 PM | 22 days | No | 12/2/24 | 1/2/25 | NA | 1
10909 | Review End-To-End Business Scenarios with VPODs | December 18, 2024 8:00 AM | January 2, 2025 5:00 PM | 4675FF | 4677FF+5d | As Soon As Possible | NA | 10 | 0d | January 3, 2025 8:00 AM | January 16, 2025 5:00 PM | 10 days | No | 12/18/24 | 1/2/25 | NA | 1
10910 | Incorporate VPODs Feedback | December 26, 2024 8:00 AM | January 9, 2025 5:00 PM | 4676FF+5d | 4678 | As Soon As Possible | NA | 10 | 0d | January 10, 2025 8:00 AM | January 24, 2025 5:00 PM | 10 days | No | 12/26/24 | 1/9/25 | NA | 1
10911 | MS 23/23.1, 24 - Finalize End-To-End Business Scenarios | January 10, 2025 8:00 AM | January 16, 2025 5:00 PM | 4677 | 4925 | As Soon As Possible | NA | 5 | 0d | January 27, 2025 8:00 AM | January 31, 2025 5:00 PM | 5 days | No | 1/10/25 | 1/16/25 | NA | 1
10912 | Milestone 23/23.1/23.2 - Track Administrative Costs | April 1, 2025 8:00 AM | May 14, 2026 5:00 PM |  |  | As Soon As Possible | NA | 283 | -50d | April 1, 2025 8:00 AM | February 3, 2026 5:00 PM | 213 days | No | 4/1/25 | NA | NA | 0.51000000000000001
10913 | MS 23/23.1/23.2 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 4675FS-24d,1008 | 4681FF | As Soon As Possible | NA | 90 | 0d | April 1, 2025 8:00 AM | June 3, 2025 5:00 PM | 45 days | No | 4/1/25 | 8/6/25 | NA | 1
10914 | Review Training Curriculum with VPODs | June 4, 2025 8:00 AM | August 6, 2025 5:00 PM | 4680FF | 4682FF | As Soon As Possible | NA | 45 | 0d | June 4, 2025 8:00 AM | June 17, 2025 5:00 PM | 10 days | No | 6/4/25 | 8/6/25 | NA | 1
10915 | Incorporate VPODs Feedback | June 25, 2025 8:00 AM | August 6, 2025 5:00 PM | 4681FF | 4683FF | As Soon As Possible | NA | 30 | 0d | June 11, 2025 8:00 AM | June 24, 2025 5:00 PM | 10 days | No | 6/25/25 | 8/6/25 | NA | 1
10916 | MS 23/23.1/23.2 - Finalize Training Curriculum | June 25, 2025 8:00 AM | August 6, 2025 5:00 PM | 4682FF | 4693 | As Soon As Possible | NA | 30 | 0d | June 25, 2025 8:00 AM | July 1, 2025 5:00 PM | 5 days | No | 6/25/25 | 8/6/25 | NA | 1
10917 | MS 23/23.1/23.2 - Validate and Provide Feedback on Critical Scenarios for the EUST | November 28, 2025 8:00 AM | January 23, 2026 5:00 PM | 4675,1157FF,1242FF | 4693 | As Soon As Possible | NA | 38 | 22d | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 days | No | NA | NA | NA | 0
13885 | BD 5 - MS 23/23.1/23.2: - Discovery and Develop Training Curriculum (Build Drop Update) | December 26, 2025 8:00 AM | February 9, 2026 5:00 PM | 1146FS-19d,1147FS-19d | 4686SS | As Soon As Possible | NA | 30 | -50d | NA | NA | 0 days? | No | NA | NA | NA | 0
13887 | BD 5 - MS 23/23.1/23.2: - Review Training Curriculum with VPODs(Build Drop Update) | December 26, 2025 8:00 AM | February 9, 2026 5:00 PM | 4685SS | 4687SS | As Soon As Possible | NA | 30 | -50d | NA | NA | 0 days? | No | NA | NA | NA | 0
13886 | BD 5 - MS 23/23.1/23.2: - Incorporate VPODs Feedback(Build Drop Update) | December 26, 2025 8:00 AM | February 2, 2026 5:00 PM | 4686SS | 4688 | As Soon As Possible | NA | 25 | -50d | NA | NA | 0 days? | No | NA | NA | NA | 0
13884 | BD 5 - MS 17: Finalize Training Curriculum (Build Drop Update) | February 3, 2026 8:00 AM | February 9, 2026 5:00 PM | 4687 | 4689SS | As Soon As Possible | NA | 5 | -50d | NA | NA | 0 days? | No | NA | NA | NA | 0
13883 | BD 5 - MS 23/23.1/23.2: - Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Update) | February 3, 2026 8:00 AM | February 9, 2026 5:00 PM | 4688SS,1154,1155,1156 | 4690FS+12d,4898 | As Soon As Possible | NA | 5 | -50d | NA | NA | 0 days? | No | NA | NA | NA | 0
10918 | BD 5- MS 23/23.1/23.2: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | February 27, 2026 8:00 AM | April 9, 2026 5:00 PM | 1167SS-36d,1249SS-36d,4689FS+12d | 4691 | As Soon As Possible | NA | 29 | -50d | October 8, 2025 8:00 AM | January 5, 2026 5:00 PM | 60 days | No | NA | NA | NA | 0
10919 | BD 5 - MS 23/23.1/23.2: - Review Training Content with VPOD & TAW (Build Drop Update) | April 10, 2026 8:00 AM | April 23, 2026 5:00 PM | 4690 | 4692 | As Soon As Possible | NA | 10 | -50d | October 22, 2025 8:00 AM | January 20, 2026 5:00 PM | 60 days | No | NA | NA | NA | 0
10920 | BD 5 - MS 23/23.1/23.2: - Incorporate Feedback from VPOD & TAW (Build Drop Update) | April 24, 2026 8:00 AM | May 7, 2026 5:00 PM | 4691 | 4693 | As Soon As Possible | NA | 10 | -50d | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 10 days | No | NA | NA | NA | 0
10921 | MS 23/23.1 - Finalize Training Content | May 8, 2026 8:00 AM | May 14, 2026 5:00 PM | 4692,4683,4684 | 4709,5611,5612,4802,4803 | As Soon As Possible | NA | 5 | -50d | January 28, 2026 8:00 AM | February 3, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
10922 | Milestone 24 - Track Assistance Costs | March 24, 2025 8:00 AM | March 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 251 | -13d | April 1, 2025 8:00 AM | February 3, 2026 5:00 PM | 213 days | No | 3/24/25 | NA | NA | 0.53000000000000003
10927 | MS 24 - Develop Training Curriculum | April 1, 2025 8:00 AM | August 6, 2025 5:00 PM | 1008 | 4696FF | As Soon As Possible | NA | 90 | 0d | April 1, 2025 8:00 AM | June 3, 2025 5:00 PM | 45 days | No | 4/1/25 | 8/6/25 | NA | 1
10928 | Review Training Curriculum with VPODs | March 24, 2025 8:00 AM | August 6, 2025 5:00 PM | 4695FF | 4697FF | As Soon As Possible | NA | 45 | 0d | June 4, 2025 8:00 AM | June 17, 2025 5:00 PM | 10 days | No | 3/24/25 | 8/6/25 | NA | 1
10929 | Incorporate VPODs Feedback | June 11, 2025 8:00 AM | August 6, 2025 5:00 PM | 4696FF | 4698FF | As Soon As Possible | NA | 40 | 0d | June 11, 2025 8:00 AM | June 24, 2025 5:00 PM | 10 days | No | 6/11/25 | 8/6/25 | NA | 1
10930 | MS 24 - Finalize Training Curriculum | June 25, 2025 8:00 AM | August 6, 2025 5:00 PM | 4697FF | 4708 | As Soon As Possible | NA | 30 | 0d | June 25, 2025 8:00 AM | July 1, 2025 5:00 PM | 5 days | No | 6/25/25 | 8/6/25 | NA | 1
10931 | MS 24 - Validate and Provide Feedback on Critical Scenarios for the EUST | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 1161FF | 4708 | As Soon As Possible | NA | 38 | 59d | October 6, 2025 8:00 AM | November 28, 2025 5:00 PM | 38 days | No | 10/6/25 | NA | NA | 0.13
13880 | BD 5 - MS 24: - Discovery and Develop Training Curriculum (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 1149FS-19d,1150FS-19d,1151FS-19d,1159FS-19d,1160FS-19d,1161FS-19d | 4701SS | As Soon As Possible | NA | 30 | -13d | NA | NA | 0 days? | No | NA | NA | NA | 0
13882 | BD 5 - MS 24: - Review Training Curriculum with VPODs(Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 4700SS | 4702SS | As Soon As Possible | NA | 30 | -13d | NA | NA | 0 days? | No | NA | NA | NA | 0
13881 | BD 5 - MS 24: - Incorporate VPODs Feedback(Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 4701SS | 4703FS-5d | As Soon As Possible | NA | 30 | -13d | NA | NA | 0 days? | No | NA | NA | NA | 0
13879 | BD 5 - MS 24: Finalize Training Curriculum (Build Drop Update) | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 4702FS-5d | 4704SS | As Soon As Possible | NA | 5 | -13d | NA | NA | 0 days? | No | NA | NA | NA | 0
13878 | BD 5 - MS 24: - Develop Training Content - Quick Guides, Knoweldge Articles (Build Drop Update) | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 4703SS | 4705FS+12d | As Soon As Possible | NA | 5 | -13d | NA | NA | 0 days? | No | NA | NA | NA | 0
10932 | BD 5 - MS 24: - Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | January 5, 2026 8:00 AM | February 13, 2026 5:00 PM | 1171SS-36d,4704FS+12d | 4706 | As Soon As Possible | NA | 29 | -13d | October 8, 2025 8:00 AM | January 5, 2026 5:00 PM | 60 days | No | NA | NA | NA | 0
10933 | BD 5 - MS 24: - Review Training Content with VPOD& TAW (Build Drop Update) | February 17, 2026 8:00 AM | March 2, 2026 5:00 PM | 4705 | 4707 | As Soon As Possible | NA | 10 | -13d | October 22, 2025 8:00 AM | January 20, 2026 5:00 PM | 60 days | No | NA | NA | NA | 0
10934 | BD 5 - MS 24: - Incorporate Feedback from VPOD& TAW (Build Drop Update) | March 3, 2026 8:00 AM | March 16, 2026 5:00 PM | 4706 | 4708 | As Soon As Possible | NA | 10 | -13d | January 13, 2026 8:00 AM | January 27, 2026 5:00 PM | 10 days | No | NA | NA | NA | 0
10935 | MS 24 - Finalize Training Content | March 17, 2026 8:00 AM | March 23, 2026 5:00 PM | 4707,4698,4699 | 4709,5611,5612,4804,4805 | As Soon As Possible | NA | 5 | -13d | January 28, 2026 8:00 AM | February 3, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
10936 | Financial Management Process Area Completed | May 14, 2026 5:00 PM | May 14, 2026 5:00 PM | 4693,4708 | 4925FS-1d | As Soon As Possible | NA | 0 | 334d | February 3, 2026 5:00 PM | February 3, 2026 5:00 PM | 0 days | Yes | NA | NA | NA | 0
10937 | Reports | October 31, 2025 8:00 AM | March 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 96 | 12d | September 5, 2025 8:00 AM | February 27, 2026 5:00 PM | 120 days | No | NA | NA | NA | 0
10939 | Group 1 Reports (Milestones 29, 30) | October 31, 2025 8:00 AM | March 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 96 | -13d | September 5, 2025 8:00 AM | February 27, 2026 5:00 PM | 120 days | No | NA | NA | NA | 0
10949 | BD 5 - MS 29,30 - Discovery and Develop Training Curriculum (Build Drop Update) | October 31, 2025 8:00 AM | January 12, 2026 5:00 PM | 545SS+37d,523SS+37d,524SS+37d | 4713SS | As Soon As Possible | NA | 48 | 30d | September 5, 2025 8:00 AM | January 14, 2026 5:00 PM | 90 days | No | NA | NA | NA | 0
10950 | BD 5 - MS 29,30 - Review Training Curriculum with VPODs (Build Drop Update) | October 31, 2025 8:00 AM | January 12, 2026 5:00 PM | 4712SS | 4714SS | As Soon As Possible | NA | 48 | 30d | January 15, 2026 8:00 AM | January 29, 2026 5:00 PM | 10 days | No | NA | NA | NA | 0
10951 | BD 5 - MS 29,30 - Incorporate VPODs Feedback (Build Drop Update) | October 31, 2025 8:00 AM | January 12, 2026 5:00 PM | 4713SS | 4715FS-23d | As Soon As Possible | NA | 48 | 30d | January 23, 2026 8:00 AM | February 5, 2026 5:00 PM | 10 days | No | NA | NA | NA | 0
10952 | MS 29, 30 - Finalize Training Curriculum | December 9, 2025 8:00 AM | January 12, 2026 5:00 PM | 4714FS-23d | 4720 | As Soon As Possible | NA | 23 | 30d | February 6, 2026 8:00 AM | February 12, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
13877 | BD 5 - MS 29,30- Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Update) | December 9, 2025 8:00 AM | January 12, 2026 5:00 PM | 549FS-12d | 4717 | As Soon As Possible | NA | 23 | -13d | NA | NA | 0 days? | No | NA | NA | NA | 0
10954 | BD 5 - MS 29,30- Develop Training Content - On-Demand Programs and Lessons (Build Drop Update) | January 13, 2026 8:00 AM | February 13, 2026 5:00 PM | 529SS,530SS,551SS,4716 | 4718 | As Soon As Possible | NA | 23 | -13d | November 6, 2025 8:00 AM | February 5, 2026 5:00 PM | 61 days | No | NA | NA | NA | 0
10955 | BD 5 - MS 29,30 - Review Training Content with VPOD & TAW (Build Drop Update) | February 17, 2026 8:00 AM | March 2, 2026 5:00 PM | 4717 | 4719 | As Soon As Possible | NA | 10 | -13d | December 8, 2025 8:00 AM | February 12, 2026 5:00 PM | 46 days | No | NA | NA | NA | 0
10956 | BD 5 - MS 29,30 - Incorporate Feedback from VPOD & TAW (Build Drop Update) | March 3, 2026 8:00 AM | March 16, 2026 5:00 PM | 4718 | 4720 | As Soon As Possible | NA | 10 | -13d | February 6, 2026 8:00 AM | February 20, 2026 5:00 PM | 10 days | No | NA | NA | NA | 0
10957 | MS 29, 30 - Finalize Training Content | March 17, 2026 8:00 AM | March 23, 2026 5:00 PM | 4719,4715 | 4721,5611,5612,4909 | As Soon As Possible | NA | 5 | -13d | February 23, 2026 8:00 AM | February 27, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
10958 | Reports Process Area Completed | March 23, 2026 5:00 PM | March 23, 2026 5:00 PM | 4720 | 4925,4812,4813 | As Soon As Possible | NA | 0 | 370d | February 27, 2026 5:00 PM | February 27, 2026 5:00 PM | 0 days | Yes | NA | NA | NA | 0
10959 | Admin Console | January 9, 2025 8:00 AM | March 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 301 | 370d | March 10, 2025 8:00 AM | January 21, 2026 5:00 PM | 219 days | No | 1/9/25 | NA | NA | 0.20999999999999999
10961 | Group 1 Admin Console (Milestones 32 - Miscellaneous) | January 9, 2025 8:00 AM | March 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 301 | -13d | March 10, 2025 8:00 AM | January 21, 2026 5:00 PM | 219 days | No | 1/9/25 | NA | NA | 0.20999999999999999
10967 | MS 32 - Develop End-To-End Business Scenarios | January 9, 2025 8:00 AM | January 30, 2025 5:00 PM | 5521SS | 4728,4725FF | As Soon As Possible | NA | 15 | 0d | March 10, 2025 8:00 AM | March 28, 2025 5:00 PM | 15 days | No | 1/9/25 | 1/30/25 | NA | 1
10968 | Review End-To-End Business Scenarios with VPODs | January 16, 2025 8:00 AM | January 30, 2025 5:00 PM | 4724FF | 4726FF+5d | As Soon As Possible | NA | 10 | 0d | March 17, 2025 8:00 AM | March 28, 2025 5:00 PM | 10 days | No | 1/16/25 | 1/30/25 | NA | 1
10969 | Incorporate VPODs Feedback | January 24, 2025 8:00 AM | February 6, 2025 5:00 PM | 4725FF+5d | 4727 | As Soon As Possible | NA | 10 | 0d | March 24, 2025 8:00 AM | April 7, 2025 5:00 PM | 10 days | No | 1/24/25 | 2/6/25 | NA | 1
10970 | MS 32 - Finalize End-To-End Business Scenarios | February 7, 2025 8:00 AM | February 13, 2025 5:00 PM | 4726 | 4736 | As Soon As Possible | NA | 5 | 0d | April 8, 2025 8:00 AM | April 14, 2025 5:00 PM | 5 days | No | 2/7/25 | 2/13/25 | NA | 1
10971 | BD 5 - MS 32 - Discovery and Develop Training Curriculum (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 4724,1278,1280FS-19d,1282FS-19d | 4729SS | As Soon As Possible | NA | 30 | -13d | August 11, 2025 8:00 AM | September 22, 2025 5:00 PM | 30 days | No | NA | NA | NA | 0
10972 | BD 5 - MS 32 - Review Training Curriculum with VPODs (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 4728SS | 4730SS | As Soon As Possible | NA | 30 | -13d | September 23, 2025 8:00 AM | October 6, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10973 | BD 5 - MS 32 - Incorporate VPODs Feedback (Build Drop Update) | October 31, 2025 8:00 AM | December 15, 2025 5:00 PM | 4729SS | 4731FS-5d | As Soon As Possible | NA | 30 | -13d | September 30, 2025 8:00 AM | October 13, 2025 5:00 PM | 10 days | No | NA | NA | NA | 0
10974 | MS 32 - Finalize Training Curriculum | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 4730FS-5d | 4736,4732SS | As Soon As Possible | NA | 5 | -13d | October 14, 2025 8:00 AM | October 20, 2025 5:00 PM | 5 days | No | NA | NA | NA | 0
13876 | BD 5 - MS 32 - Develop Training Content - Quick Guides, Knowledge Articles (Build Drop Updates) | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 4731SS,1282 | 4733FS+12d | As Soon As Possible | NA | 5 | -13d | NA | NA | 0 days? | No | NA | NA | NA | 0
10976 | BD 5 - MS 32 - Develop Training Content - On-Demand Programs and Lessons (Build Drop Updates) | January 5, 2026 8:00 AM | February 13, 2026 5:00 PM | 4732FS+12d | 4734 | As Soon As Possible | NA | 29 | -13d | October 8, 2025 8:00 AM | December 22, 2025 5:00 PM | 52 days | No | NA | NA | NA | 0
10977 | BD 5 - MS 32 - Review Training Content with VPOD & TAW (Build Drop Update) | February 17, 2026 8:00 AM | March 2, 2026 5:00 PM | 4733 | 4735 | As Soon As Possible | NA | 10 | -13d | October 22, 2025 8:00 AM | January 6, 2026 5:00 PM | 51 days | No | NA | NA | NA | 0
10978 | BE 5 - MS 32 - Incorporate Feedback from VPOD & TAW (Build Drop Update) | March 3, 2026 8:00 AM | March 16, 2026 5:00 PM | 4734 | 4736 | As Soon As Possible | NA | 10 | -13d | December 30, 2025 8:00 AM | January 13, 2026 5:00 PM | 10 days | No | NA | NA | NA | 0
10979 | MS 32 - Finalize Training Content | March 17, 2026 8:00 AM | March 23, 2026 5:00 PM | 4735,4727,4731 | 4737,5611,5612,4814,4815 | As Soon As Possible | NA | 5 | -13d | January 14, 2026 8:00 AM | January 21, 2026 5:00 PM | 5 days | No | NA | NA | NA | 0
10980 | Admin Console Process Area Completed | March 23, 2026 5:00 PM | March 23, 2026 5:00 PM | 4736 | 4925 | As Soon As Possible | NA | 0 | 370d | January 21, 2026 5:00 PM | January 21, 2026 5:00 PM | 0 days | Yes | NA | NA | NA | 0
10981 | Information Sessions Completed for All Process Areas | August 15, 2025 5:00 PM | August 15, 2025 5:00 PM | 5444FS+9mo,5479FS+9mo,5487FS+9mo,5493FS+9mo,5499FS+9mo,5507FS+9mo,5513FS+9mo,5521FS+6mo,5410FS+9mo | 4925 | As Soon As Possible | NA | 0 | 519d | September 4, 2025 5:00 PM | September 4, 2025 5:00 PM | 0 days | Yes | NA | NA | NA | 0
9646 | Develop Hardening Modules for MS 3,4,5 | April 8, 2024 8:00 AM | June 11, 2026 5:00 PM |  |  | As Soon As Possible | NA | 548 | 334d | April 8, 2024 8:00 AM | November 14, 2024 5:00 PM | 156 days | No | 4/8/24 | NA | NA | 0.64000000000000001
9647 | Start Hardening Activities | April 8, 2024 8:00 AM | April 8, 2024 8:00 AM | 3192 | 4742,4743,4744,4745,4746,4747,4756,4757,4758,4759,4760,4769,4770 | Start No Earlier Than | 4/8/24 | 0 | 0d | April 8, 2024 8:00 AM | April 8, 2024 8:00 AM | 0 days | Yes | 4/8/24 | 4/8/24 | NA | 1
9648 | Hardening M3 Screening | April 8, 2024 8:00 AM | February 7, 2025 5:00 PM |  |  | As Soon As Possible | NA | 212 | 0d | April 8, 2024 8:00 AM | November 14, 2024 5:00 PM | 156 days | No | 4/8/24 | 2/7/25 | NA | 1
9649 | Hardening: M3 Screening Page-Start the Screening Page Updates | April 8, 2024 8:00 AM | May 3, 2024 5:00 PM | 4740 | 4743SS | As Soon As Possible | NA | 20 | 0d | April 8, 2024 8:00 AM | May 3, 2024 5:00 PM | 20 days | No | 4/8/24 | 5/3/24 | NA | 1
9650 | Hardening: M3 Add Person(s) | April 8, 2024 8:00 AM | April 19, 2024 5:00 PM | 4740,4742SS | 4744SS | As Soon As Possible | NA | 10 | 0d | April 8, 2024 8:00 AM | April 19, 2024 5:00 PM | 10 days | No | 4/8/24 | 4/19/24 | NA | 1
9651 | Hardening: M3 Screening Worker Submission | April 8, 2024 8:00 AM | August 2, 2024 5:00 PM | 4740,4743SS | 4745SS | As Soon As Possible | NA | 83 | 0d | April 8, 2024 8:00 AM | November 14, 2024 5:00 PM | 156 days | No | 4/8/24 | 8/2/24 | NA | 1
9652 | Hardening: M3 Screening Add Address | April 8, 2024 8:00 AM | August 2, 2024 5:00 PM | 4740,4744SS | 4746SS | As Soon As Possible | NA | 83 | 0d | April 8, 2024 8:00 AM | November 14, 2024 5:00 PM | 156 days | No | 4/8/24 | 8/2/24 | NA | 1
9653 | Hardening: M3 Screening Overview | April 8, 2024 8:00 AM | June 14, 2024 5:00 PM | 4740,4745SS | 4747SS | As Soon As Possible | NA | 49 | 0d | April 8, 2024 8:00 AM | June 14, 2024 5:00 PM | 49 days | No | 4/8/24 | 6/14/24 | NA | 1
9654 | Hardening Module: Screening Cross Reports | April 8, 2024 8:00 AM | August 2, 2024 5:00 PM | 4740,4746SS | 4756SS,4748 | As Soon As Possible | NA | 83 | 0d | April 8, 2024 8:00 AM | November 14, 2024 5:00 PM | 156 days | No | 4/8/24 | 8/2/24 | NA | 1
12168 | Hardening M3 Screening Sprint Discovery | August 5, 2024 8:00 AM | August 23, 2024 5:00 PM | 4747 | 4749 | As Soon As Possible | NA | 15 | 0d | NA | NA | 0 days? | No | 8/5/24 | 8/23/24 | NA | 1
12169 | Hardening M3 Screening Sprint Review | August 26, 2024 8:00 AM | September 27, 2024 5:00 PM | 4748 | 4750 | As Soon As Possible | NA | 25 | 0d | NA | NA | 0 days? | No | 8/26/24 | 9/27/24 | NA | 1
12170 | Hardening M3 Screening Analysis | September 30, 2024 8:00 AM | October 11, 2024 5:00 PM | 4749 | 4751FS+13d | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/30/24 | 10/11/24 | NA | 1
12171 | Hardening M3 Screening Updates (Re-skin) | October 31, 2024 8:00 AM | December 4, 2024 5:00 PM | 4750FS+13d | 4752,5296FS-3d | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/31/24 | 12/4/24 | NA | 1
12581 | Hardening M3 Screening Reformat (Re-skin) | December 5, 2024 8:00 AM | January 7, 2025 5:00 PM | 4751 | 4753 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 12/5/24 | 1/7/25 | NA | 1
12172 | Hardening M3 Screening Review (Re-skin) | January 8, 2025 8:00 AM | February 6, 2025 5:00 PM | 4752 | 4754 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 1/8/25 | 2/6/25 | NA | 1
12173 | Hardening M3 Screening Complete (Re-skin) | February 7, 2025 8:00 AM | February 7, 2025 5:00 PM | 4753 | 4925 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 2/7/25 | 2/7/25 | NA | 1
9655 | Hardening M4 Investigations-Engagement | April 8, 2024 8:00 AM | February 7, 2025 5:00 PM |  |  | As Soon As Possible | NA | 212 | 0d | April 8, 2024 8:00 AM | November 14, 2024 5:00 PM | 156 days | No | 4/8/24 | 2/7/25 | NA | 1
9656 | Hardening: Module: Investigations Contacts | April 8, 2024 8:00 AM | August 2, 2024 5:00 PM | 4740,4747SS | 4757SS | As Soon As Possible | NA | 83 | 0d | April 8, 2024 8:00 AM | November 14, 2024 5:00 PM | 156 days | No | 4/8/24 | 8/2/24 | NA | 1
9657 | Hardening: Module: Related Investigations/Associate Referrals | April 8, 2024 8:00 AM | August 2, 2024 5:00 PM | 4740,4756SS | 4758SS | As Soon As Possible | NA | 83 | 0d | April 8, 2024 8:00 AM | November 14, 2024 5:00 PM | 156 days | No | 4/8/24 | 8/2/24 | NA | 1
9658 | Hardening: M4 Investigative Folio Assignments | April 8, 2024 8:00 AM | August 2, 2024 5:00 PM | 4740,4757SS | 4759SS | As Soon As Possible | NA | 83 | 0d | April 8, 2024 8:00 AM | November 14, 2024 5:00 PM | 156 days | No | 4/8/24 | 8/2/24 | NA | 1
9659 | Hardening: M4 Investigations Fatality/Near Fatality | April 8, 2024 8:00 AM | August 2, 2024 5:00 PM | 4740,4758SS | 4760SS | As Soon As Possible | NA | 83 | 0d | April 8, 2024 8:00 AM | November 14, 2024 5:00 PM | 156 days | No | 4/8/24 | 8/2/24 | NA | 1
9660 | Hardening: M4 Investigation Documents | April 8, 2024 8:00 AM | August 2, 2024 5:00 PM | 4740,4759SS | 4769SS,4761 | As Soon As Possible | NA | 83 | 0d | April 8, 2024 8:00 AM | November 14, 2024 5:00 PM | 156 days | No | 4/8/24 | 8/2/24 | NA | 1
12174 | Hardening M4 Investigations-Engagement Discovery | August 5, 2024 8:00 AM | August 23, 2024 5:00 PM | 4760 | 4762 | As Soon As Possible | NA | 15 | 0d | NA | NA | 0 days? | No | 8/5/24 | 8/23/24 | NA | 1
12175 | Hardening M4 Investigations-Engagement Review | August 26, 2024 8:00 AM | September 27, 2024 5:00 PM | 4761 | 4763 | As Soon As Possible | NA | 25 | 0d | NA | NA | 0 days? | No | 8/26/24 | 9/27/24 | NA | 1
12176 | Hardening M4 Investigations-Engagement Analysis | September 30, 2024 8:00 AM | October 11, 2024 5:00 PM | 4762 | 4764FS+13d | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/30/24 | 10/11/24 | NA | 1
12177 | Hardening M4 Investigations-Engagement Updates (Re-skin) | October 31, 2024 8:00 AM | December 4, 2024 5:00 PM | 4763FS+13d | 4765 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/31/24 | 12/4/24 | NA | 1
12582 | Hardening M4 Investigations-Engagement Reformat (Re-skin) | December 5, 2024 8:00 AM | January 7, 2025 5:00 PM | 4764 | 4766 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 12/5/24 | 1/7/25 | NA | 1
12178 | Hardening M4 Investigations-Engagement Review | January 8, 2025 8:00 AM | February 6, 2025 5:00 PM | 4765 | 4767 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 1/8/25 | 2/6/25 | NA | 1
12179 | Hardening M4 Investigations-Engagement Complete | February 7, 2025 8:00 AM | February 7, 2025 5:00 PM | 4766 | 4925 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 2/7/25 | 2/7/25 | NA | 1
9662 | Hardening M5 Investigations-Determination | April 8, 2024 8:00 AM | June 11, 2026 5:00 PM |  |  | As Soon As Possible | NA | 548 | 334d | April 8, 2024 8:00 AM | November 14, 2024 5:00 PM | 156 days | No | 4/8/24 | NA | NA | 0.26000000000000001
9663 | Hardening: Module: Create and Send Cross Reports | April 8, 2024 8:00 AM | August 2, 2024 5:00 PM | 4740,4760SS | 4770SS,4771 | As Soon As Possible | NA | 83 | 0d | April 8, 2024 8:00 AM | November 14, 2024 5:00 PM | 156 days | No | 4/8/24 | 8/2/24 | NA | 1
9666 | Hardening: M5 Investigations CACI | April 8, 2024 8:00 AM | May 31, 2024 5:00 PM | 4740,4769SS | 4925 | As Soon As Possible | NA | 39 | 0d | April 8, 2024 8:00 AM | May 31, 2024 5:00 PM | 39 days | No | 4/8/24 | 5/31/24 | NA | 1
12180 | Hardening M5 Investigations-Determination Discovery | August 5, 2024 8:00 AM | August 23, 2024 5:00 PM | 4769 | 4772 | As Soon As Possible | NA | 15 | 0d | NA | NA | 0 days? | No | 8/5/24 | 8/23/24 | NA | 1
12181 | Hardening M5 Investigations-Determination Review | August 26, 2024 8:00 AM | September 27, 2024 5:00 PM | 4771 | 4773 | As Soon As Possible | NA | 25 | 0d | NA | NA | 0 days? | No | 8/26/24 | 9/27/24 | NA | 1
12182 | Hardening M5 Investigations-Determination Analysis | September 30, 2024 8:00 AM | October 11, 2024 5:00 PM | 4772 | 4774FS+13d | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/30/24 | 10/11/24 | NA | 1
12183 | Hardening M5 Investigations-Determination Updates (Re-skin) | October 31, 2024 8:00 AM | December 4, 2024 5:00 PM | 4773FS+13d | 4775 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/31/24 | 12/4/24 | NA | 1
12583 | Hardening M5 Investigations-Determination Reformat (Re-skin) | December 5, 2024 8:00 AM | January 7, 2025 5:00 PM | 4774 | 4776 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 12/5/24 | 1/7/25 | NA | 1
12184 | Hardening M5 Investigations-Determination Review (Re-skin) | January 8, 2025 8:00 AM | February 6, 2025 5:00 PM | 4775 | 4777 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 1/8/25 | 2/6/25 | NA | 1
12185 | Hardening M5 Investigations-Determination Complete (Re-skin) | February 7, 2025 8:00 AM | February 7, 2025 5:00 PM | 4776 | 4925 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 2/7/25 | 2/7/25 | NA | 1
13819 | Develop Hardening Modules for All Milestones | April 6, 2026 5:00 PM | June 11, 2026 5:00 PM |  |  | As Soon As Possible | NA | 47 | 334d | NA | NA | 0 days? | No | NA | NA | NA | 0
13820 | Hardening Work Starts | April 6, 2026 5:00 PM | April 6, 2026 5:00 PM | 1850 | 4780,4781,4782,4783,4784,4785,4786,4787,4788,4789,4790,4791,4792,4793,4794,4795,4796,4797,4798,4799,4800,4801,4802,4803,4804,4805,4806,4807,4808,4809,4810,4811,4812,4813,4814,4815 | As Soon As Possible | NA | 0 | 335d | NA | NA | 0 days? | Yes | NA | NA | NA | 0
13835 | MS 6.1 - Prevention Services - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4463 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13836 | MS 6.1 - Prevention Services - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4463 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13854 | MS 7/7.1 - Case Plan - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4478 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13855 | MS 7/7.1 - Case Plan - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4478 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13856 | MS 9 - Case Management - Engagement and Services - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4493 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13857 | MS 9 - Case Management - Engagement and Services - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4493 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13858 | MS 10/10.1 - Case Closure - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4515 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13859 | MS 10/10.1 - Case Closure - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4515 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13860 | MS 11 - After Care and Re-entry - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4526 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13861 | MS 11 - After Care and Re-entry - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4526 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13862 | MS 13 - Adoptions - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4537 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13863 | MS 13 - Adoptions - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4537 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13864 | MS 14 - Warrants - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4560 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13865 | MS 14 - Warrants - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4560 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13866 | MS 16 - Jurisdiction and Disposition Hearing - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4575 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13867 | MS 16 - Jurisdiction and Disposition Hearing - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4575 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13868 | MS 17 - Status Reviews - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4590 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13869 | MS 17 - Status Reviews - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4590 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13870 | MS 18 - Other Hearing - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4605 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13871 | MS 18 - Other Hearing - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4605 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13872 | MS 21 - Eligibility Program - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4629 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13873 | MS 21 - Eligibility Program - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4629 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13874 | MS 23/23.1/23.2 - Track Administrative Costs - Hardening - Update Quick Guides, Knowledge Base Articles | May 15, 2026 8:00 AM | June 11, 2026 5:00 PM | 4779,4693 |  | As Soon As Possible | NA | 19 | 334d | NA | NA | 0 days? | No | NA | NA | NA | 0
13875 | MS 23/23.1/23.2 - Track Administrative Costs - Hardening - Update On-Demand Programs and Lessons | May 15, 2026 8:00 AM | June 11, 2026 5:00 PM | 4779,4693 |  | As Soon As Possible | NA | 19 | 334d | NA | NA | 0 days? | No | NA | NA | NA | 0
13837 | MS 24 - Track Assistance Costs - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4708 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13838 | MS 24 - Track Assistance Costs - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4708 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13839 | MS 26/26.1 - Maintain Resource Family Home - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4648 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13840 | MS 26/26.1 - Maintain Resource Family Home - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4648 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13841 | MS 27 - Complaints - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4659 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13842 | MS 27 - Complaints - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4659 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13843 | MS 28 - Legal Action - Hardening - Update Quick Guides, Knowledge Base Articles | April 21, 2026 8:00 AM | May 15, 2026 5:00 PM | 4779,4670 |  | As Soon As Possible | NA | 19 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
13844 | MS 28 - Legal Action - Hardening - Update On-Demand Programs and Lessons | April 21, 2026 8:00 AM | May 15, 2026 5:00 PM | 4779,4670 |  | As Soon As Possible | NA | 19 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
13845 | MS 29/30 - Reports - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4721 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13846 | MS 29/30 - Reports - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4721 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13847 | MS 32 - Admin Console - Hardening - Update Quick Guides, Knowledge Base Articles | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4736 |  | As Soon As Possible | NA | 19 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
13848 | MS 32 - Admin Console - Hardening - Update On-Demand Programs and Lessons | April 7, 2026 8:00 AM | May 1, 2026 5:00 PM | 4779,4736 | 4816 | As Soon As Possible | NA | 19 | 335d | NA | NA | 0 days? | No | NA | NA | NA | 0
13849 | Hardening Work Completed | May 4, 2026 8:00 AM | May 4, 2026 5:00 PM | 4815 | 4914,4918 | As Soon As Possible | NA | 1 | 335d | NA | NA | 0 s? | No | NA | NA | NA | 0
9669 | Develop Strategy (Approach and Roadmap) for Developing and Delivering ILT | August 14, 2023 8:00 AM | February 27, 2026 5:00 PM |  |  | As Soon As Possible | NA | 637 | 386d | August 14, 2023 8:00 AM | March 27, 2026 5:00 PM | 657 days | No | 8/14/23 | NA | NA | 0.90000000000000002
9677 | Develop ILT Strategy | August 14, 2023 8:00 AM | January 18, 2024 5:00 PM |  |  | As Soon As Possible | NA | 107 | 0d | August 14, 2023 8:00 AM | January 18, 2024 5:00 PM | 107 days | No | 8/14/23 | 1/18/24 | NA | 1
9678 | Develop ILT Strategy Document | August 14, 2023 8:00 AM | December 6, 2023 5:00 PM | 3192 | 4820 | Must Start On | 8/14/23 | 79 | 0d | August 14, 2023 8:00 AM | December 6, 2023 5:00 PM | 79 days | No | 8/14/23 | 12/6/23 | NA | 1
9679 | Conduct Internal Review | December 7, 2023 8:00 AM | December 12, 2023 5:00 PM | 4819 | 4821 | As Soon As Possible | NA | 4 | 0d | December 7, 2023 8:00 AM | December 12, 2023 5:00 PM | 4 days | No | 12/7/23 | 12/12/23 | NA | 1
9680 | Conduct State Review | December 13, 2023 8:00 AM | January 18, 2024 5:00 PM | 4820 | 4822 | As Soon As Possible | NA | 24 | 0d | December 13, 2023 8:00 AM | January 18, 2024 5:00 PM | 24 days | No | 12/13/23 | 1/18/24 | NA | 1
9681 | ILT Strategy Completed | January 18, 2024 5:00 PM | January 18, 2024 5:00 PM | 4821 | 4824FS+25d,4854FS+109d | As Soon As Possible | NA | 0 | 0d | January 18, 2024 5:00 PM | January 18, 2024 5:00 PM | 0 days | Yes | 1/18/24 | 1/18/24 | NA | 1
9682 | Execute ILT Strategy | February 26, 2024 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 352 | 0d | February 26, 2024 8:00 AM | June 26, 2025 5:00 PM | 337 days | No | 2/26/24 | 7/18/25 | NA | 1
9683 | Organize Training Logistics Plan Meetings with 58 Organizations for ILT Development - Part I | February 26, 2024 8:00 AM | March 26, 2024 5:00 PM | 4822FS+25d | 4831SS,4841SS,4825,4843SS+54d | As Soon As Possible | NA | 22 | 0d | February 26, 2024 8:00 AM | June 26, 2025 5:00 PM | 337 days | No | 2/26/24 | 3/26/24 | NA | 1
11729 | Organize Training Logistics Plan Meetings with 58 Organizations for ILT Development - Part II | March 27, 2024 8:00 AM | April 26, 2024 5:00 PM | 4824 | 4826 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 3/27/24 | 4/26/24 | NA | 1
11728 | Organize Training Logistics Plan Meetings with 58 Organizations for ILT Development - Part III | April 29, 2024 8:00 AM | May 29, 2024 5:00 PM | 4825 | 4827 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/29/24 | 5/29/24 | NA | 1
11727 | Organize Training Logistics Plan Meetings with 58 Organizations for ILT Development - Part IV | May 30, 2024 8:00 AM | June 28, 2024 5:00 PM | 4826 | 4828 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/30/24 | 6/28/24 | NA | 1
11726 | Organize Training Logistics Plan Meetings with 58 Organizations for ILT Development - Part V | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM | 4827 | 4829 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
11725 | Organize Training Logistics Plan Meetings with 58 Organizations for ILT Development - Part VI | August 1, 2024 8:00 AM | August 19, 2024 5:00 PM | 4828 | 4830,4884FF+1d | As Soon As Possible | NA | 13 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/19/24 | NA | 1
11724 | Finalize Training Logistics Plan Meetings with 58 Organizations for ILT Development | August 20, 2024 8:00 AM | September 17, 2024 5:00 PM | 4829 | 4840FS+92d,4847FS+111d | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 8/20/24 | 9/17/24 | NA | 1
9684 | Complete Logistics check sheet for each Org with the survey information and Distribute to each Org ahead of the meeting - Part I | February 26, 2024 8:00 AM | March 26, 2024 5:00 PM | 4824SS | 4841SS,4832 | As Soon As Possible | NA | 22 | 0d | February 26, 2024 8:00 AM | June 26, 2025 5:00 PM | 337 days | No | 2/26/24 | 3/26/24 | NA | 1
11738 | Complete Logistics check sheet for each Org with the survey information and Distribute to each Org ahead of the meeting - Part II | March 27, 2024 8:00 AM | April 26, 2024 5:00 PM | 4831 | 4833 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 3/27/24 | 4/26/24 | NA | 1
11737 | Complete Logistics check sheet for each Org with the survey information and Distribute to each Org ahead of the meeting - Part III | April 29, 2024 8:00 AM | May 29, 2024 5:00 PM | 4832 | 4834 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/29/24 | 5/29/24 | NA | 1
11736 | Complete Logistics check sheet for each Org with the survey information and Distribute to each Org ahead of the meeting - Part IV | May 30, 2024 8:00 AM | June 28, 2024 5:00 PM | 4833 | 4835 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/30/24 | 6/28/24 | NA | 1
11735 | Complete Logistics check sheet for each Org with the survey information and Distribute to each Org ahead of the meeting - Part V | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM | 4834 | 4836 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
11734 | Complete Logistics check sheet for each Org with the survey information and Distribute to each Org ahead of the meeting - Part VI | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 4835 | 4837 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
11733 | Complete Logistics check sheet for each County with the survey information and Distribute to each Org ahead of the meeting - Part VII | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM | 4836 | 4838 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
11732 | Complete Logistics check sheet for each County with the survey information and Distribute to each Org ahead of the meeting - Part VIII | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM | 4837 | 4839 | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
11731 | Complete Logistics check sheet for each County with the survey information and Distribute to each Org ahead of the meeting | November 1, 2024 8:00 AM | November 12, 2024 5:00 PM | 4838 | 4840 | As Soon As Possible | NA | 7 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/12/24 | NA | 1
11730 | Planning for Organizing Training Logistics Plan Meetings with Organizations for ILT Development | February 3, 2025 8:00 AM | July 18, 2025 5:00 PM | 4839,4830FS+92d | 5630 | As Soon As Possible | NA | 116 | 0d | NA | NA | 0 days? | No | 2/3/25 | 7/18/25 | NA | 1
9685 | Begin development of ILT Wireframe and Session Templates for development | February 26, 2024 8:00 AM | June 28, 2024 5:00 PM | 4824SS,4831SS | 5630 | As Soon As Possible | NA | 88 | 0d | February 26, 2024 8:00 AM | June 28, 2024 5:00 PM | 88 days | No | 2/26/24 | 6/28/24 | NA | 1
9686 | Develop ILT Training Materials | May 13, 2024 8:00 AM | February 27, 2026 5:00 PM |  |  | As Soon As Possible | NA | 451 | 386d | May 13, 2024 8:00 AM | March 27, 2026 5:00 PM | 471 days | No | 5/13/24 | NA | NA | 0.70999999999999996
11747 | Identifying needs for preparing ILT Training Materials | May 13, 2024 8:00 AM | June 10, 2024 5:00 PM | 4824SS+54d | 4844 | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 5/13/24 | 6/10/24 | NA | 1
11746 | Identify the key elements for the ILT Training Materials | June 11, 2024 8:00 AM | July 5, 2024 5:00 PM | 4843 | 4845 | As Soon As Possible | NA | 18 | 0d | NA | NA | 0 days? | No | 6/11/24 | 7/5/24 | NA | 1
11745 | Design the Curriculum Map & Templates | July 8, 2024 8:00 AM | August 2, 2024 5:00 PM | 4844 | 4846 | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 7/8/24 | 8/2/24 | NA | 1
11744 | Pre Work for ILT Training Materials (Curriculum Maps and Templates) | August 5, 2024 8:00 AM | August 30, 2024 5:00 PM | 4845 | 4847 | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 8/5/24 | 8/30/24 | NA | 1
11740 | Develop ILT Training Materials - Cycle 2 | March 3, 2025 8:00 AM | June 27, 2025 5:00 PM | 4830FS+111d,4846 | 4848 | As Soon As Possible | NA | 83 | 0d | NA | NA | 0 days? | No | 3/3/25 | 6/27/25 | NA | 1
11739 | Review ILT Training Materials - Cycle 2 | June 30, 2025 8:00 AM | July 25, 2025 5:00 PM | 4847 | 4849 | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 6/30/25 | 7/25/25 | NA | 1
9687 | Incorporate Review Feedback for ILT Training Materials - Cycle 2 | July 28, 2025 8:00 AM | August 22, 2025 5:00 PM | 4848 | 4850 | As Soon As Possible | NA | 20 | 0d | May 13, 2024 8:00 AM | September 27, 2024 5:00 PM | 98 days | No | 7/28/25 | 8/22/25 | NA | 1
9688 | Finalize ILT Training Materials - Cycle 2 | August 25, 2025 8:00 AM | September 10, 2025 5:00 PM | 4849 | 4851 | As Soon As Possible | NA | 12 | 0d | September 2, 2024 8:00 AM | December 30, 2024 5:00 PM | 82 days | No | 8/25/25 | 9/10/25 | NA | 1
9689 | Develop ILT Training Materials - Cycle 3 | September 11, 2025 8:00 AM | November 21, 2025 5:00 PM | 4850 | 4852 | As Soon As Possible | NA | 51 | 386d | April 30, 2025 8:00 AM | August 28, 2025 5:00 PM | 85 days | No | 9/11/25 | NA | NA | 0.42999999999999999
9690 | Develop ILT Training Materials - Cycle 4 | November 24, 2025 8:00 AM | February 27, 2026 5:00 PM | 4851 | 4925 | As Soon As Possible | NA | 65 | 386d | November 26, 2025 8:00 AM | March 27, 2026 5:00 PM | 83 days | No | NA | NA | NA | 0
9697 | Develop Training Delivery Logistics | June 25, 2024 8:00 AM | August 20, 2025 5:00 PM |  |  | As Soon As Possible | NA | 291 | 0d | June 25, 2024 8:00 AM | December 20, 2024 5:00 PM | 125 days | No | 6/25/24 | 8/20/25 | NA | 1
11768 | Complete Discovery for Creating Training Delivery Logistics | June 25, 2024 8:00 AM | July 25, 2024 5:00 PM | 4822FS+109d | 4855 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 6/25/24 | 7/25/24 | NA | 1
11767 | Continue discovery process for creating Training Delivery Logistics | July 26, 2024 8:00 AM | August 20, 2024 5:00 PM | 4854 | 4856FS+80d,4876 | As Soon As Possible | NA | 18 | 0d | NA | NA | 0 days? | No | 7/26/24 | 8/20/24 | NA | 1
11766 | Create Training Delivery Logistics | December 16, 2024 8:00 AM | February 14, 2025 5:00 PM | 4855FS+80d | 4857 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 12/16/24 | 2/14/25 | NA | 1
11765 | Continue Creating Training Delivery Logistics | February 18, 2025 8:00 AM | June 3, 2025 5:00 PM | 4856 | 4858 | As Soon As Possible | NA | 74 | 0d | NA | NA | 0 days? | No | 2/18/25 | 6/3/25 | NA | 1
11764 | Review updated Training Delivery Logistics with Implementation Lead | June 4, 2025 8:00 AM | June 6, 2025 5:00 PM | 4857 | 4859FS+2d,4861FS+2d | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 6/4/25 | 6/6/25 | NA | 1
11763 | Review updated Training Delivery Logistics with State Training Leads / Implementation Leads | June 11, 2025 8:00 AM | June 17, 2025 5:00 PM | 4858FS+2d | 4860,4863SS | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 6/11/25 | 6/17/25 | NA | 1
11762 | Incorporate feedback/comments from State Training Leads/Implementation Leads | June 18, 2025 8:00 AM | June 18, 2025 5:00 PM | 4859 |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/18/25 | 6/18/25 | NA | 1
11761 | Review updated Training Delivery Logistics with State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | June 11, 2025 8:00 AM | June 17, 2025 5:00 PM | 4858FS+2d | 4862 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 6/11/25 | 6/17/25 | NA | 1
11760 | Incorporate feedback/comments from State Customer Relations Director, Stakeholder Relations Chief, and Implementation Manager | June 18, 2025 8:00 AM | June 18, 2025 5:00 PM | 4861 |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/18/25 | 6/18/25 | NA | 1
11759 | Review updated Training Delivery Logistics with RACI required reviewers | June 11, 2025 8:00 AM | June 17, 2025 5:00 PM | 4859SS | 4864,4865 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 6/11/25 | 6/17/25 | NA | 1
11758 | Incorporate feedback/comments from RACI team | June 18, 2025 8:00 AM | June 18, 2025 5:00 PM | 4863 |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/18/25 | 6/18/25 | NA | 1
11757 | Prepare PPT for ELT and send with draft Training Delivery Logistics and all accompanying documents | June 18, 2025 8:00 AM | June 19, 2025 5:00 PM | 4863 | 4866FF | As Soon As Possible | NA | 2 | 0d | NA | NA | 0 days? | No | 6/18/25 | 6/19/25 | NA | 1
11756 | Send Training Delivery Logistics to ELT with all accompanying documents | June 19, 2025 8:00 AM | June 19, 2025 5:00 PM | 4865FF | 4867FS+1d | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/19/25 | 6/19/25 | NA | 1
11755 | Present Training Delivery Logistics to ELT | June 23, 2025 8:00 AM | June 23, 2025 5:00 PM | 4866FS+1d | 4868 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/23/25 | 6/23/25 | NA | 1
13684 | ELT Review and Feedback of Training Delivery Logistics | June 24, 2025 8:00 AM | July 18, 2025 5:00 PM | 4867 | 4869SS+18d | As Soon As Possible | NA | 18 | 0d | NA | NA | 0 days? | No | 6/24/25 | 7/18/25 | NA | 1
11754 | Incorporate ELT feedback and finalize | July 21, 2025 8:00 AM | July 23, 2025 5:00 PM | 4868SS+18d | 4870 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 7/21/25 | 7/23/25 | NA | 1
13685 | Route and Review Training Delivery Logistics with Counties | July 24, 2025 8:00 AM | August 6, 2025 5:00 PM | 4869 | 4871 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/24/25 | 8/6/25 | NA | 1
13686 | Incorporate Feedback From Counties | August 7, 2025 8:00 AM | August 13, 2025 5:00 PM | 4870 | 4872 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 8/7/25 | 8/13/25 | NA | 1
13687 | ELT Review and approval of County updates | August 14, 2025 8:00 AM | August 18, 2025 5:00 PM | 4871 | 4873FF | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 8/14/25 | 8/18/25 | NA | 1
13688 | ELT approval of Training Delivery Logistics | August 18, 2025 8:00 AM | August 18, 2025 5:00 PM | 4872FF | 4874FS+1d | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 8/18/25 | 8/18/25 | NA | 1
11753 | Complete Training Delivery Logistics | August 20, 2025 8:00 AM | August 20, 2025 5:00 PM | 4873FS+1d | 5630 | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 8/20/25 | 8/20/25 | NA | 1
12584 | Develop Train the Trainer Curriculum | July 24, 2023 8:00 AM | October 3, 2025 5:00 PM |  |  | As Soon As Possible | NA | 553 | 0d | NA | NA | 0 days? | No | 7/24/23 | 10/3/25 | NA | 1
11752 | Complete Discovery of Train-the-Trainer (T3) Curriculum | September 2, 2024 8:00 AM | October 11, 2024 5:00 PM | 4855 | 4877FS+65d | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 9/2/24 | 10/11/24 | NA | 1
12585 | Develop Draft of Train-the-Trainer (T3) Curriculum | January 21, 2025 8:00 AM | February 28, 2025 5:00 PM | 4876FS+65d | 4878 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 1/21/25 | 2/28/25 | NA | 1
11751 | Review Draft of Train-the-Trainer (T3) Curriculum | March 3, 2025 8:00 AM | July 11, 2025 5:00 PM | 4877 | 4879 | As Soon As Possible | NA | 92 | 0d | NA | NA | 0 days? | No | 3/3/25 | 7/11/25 | NA | 1
11750 | Design Train-the-Trainer (T3) Curriculum | July 14, 2025 8:00 AM | August 14, 2025 5:00 PM | 4878 | 4880 | As Soon As Possible | NA | 24 | 0d | NA | NA | 0 days? | No | 7/14/25 | 8/14/25 | NA | 1
11749 | Review Design of Train-the-Trainer (T3) Curriculum | August 15, 2025 8:00 AM | August 21, 2025 5:00 PM | 4879 | 4881 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 8/15/25 | 8/21/25 | NA | 1
9698 | Build Train-the-Trainer (T3) Curriculum | August 22, 2025 8:00 AM | September 25, 2025 5:00 PM | 4880 | 4882 | As Soon As Possible | NA | 24 | 0d | June 25, 2024 8:00 AM | November 5, 2024 5:00 PM | 95 days | No | 8/22/25 | 9/25/25 | NA | 1
13042 | Review Build Train-the-Trainer (T3) Curriculum | September 26, 2025 8:00 AM | October 2, 2025 5:00 PM | 4881 | 4883FS+1d | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 9/26/25 | 10/2/25 | NA | 1
13041 | Complete Train-the-Trainer (T3) Curriculum | October 3, 2025 5:00 PM | October 3, 2025 5:00 PM | 4882FS+1d | 5630,4886 | As Soon As Possible | NA | 0 | 0d | NA | NA | 0 days? | Yes | 10/3/25 | 10/3/25 | NA | 1
9699 | Develop CWS-CARES Glossary | July 24, 2023 8:00 AM | August 20, 2024 5:00 PM | 4829FF+1d | 4922FS+112d | As Soon As Possible | NA | 271 | 0d | November 6, 2024 8:00 AM | December 20, 2024 5:00 PM | 30 days | No | 7/24/23 | 8/20/24 | NA | 1
13049 | Develop the TTT Materials | October 6, 2025 8:00 AM | June 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 170 | 335d | NA | NA | 0 days? | No | NA | NA | NA | 0
13050 | Identify TTT Materials Needed | October 6, 2025 8:00 AM | October 24, 2025 5:00 PM | 4883 | 4887 | As Soon As Possible | NA | 15 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
13051 | Develop the TTT Materials | October 27, 2025 8:00 AM | November 17, 2025 5:00 PM | 4886 | 4888 | As Soon As Possible | NA | 15 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
13052 | Review the TTT Materials | November 18, 2025 8:00 AM | December 9, 2025 5:00 PM | 4887 | 4889 | As Soon As Possible | NA | 15 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
13053 | Incorporate Feedback and Finalize the TTT Materials | December 10, 2025 8:00 AM | December 31, 2025 5:00 PM | 4888 | 4925 | As Soon As Possible | NA | 15 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
13771 | Publish Training Materials | November 3, 2025 8:00 AM | June 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 150 | 335d | NA | NA | 0 days? | No | NA | NA | NA | 0
13779 | Set 1 Drops 1-4 QG and KBAs and 36 On-Demand Programs | November 3, 2025 8:00 AM | December 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 29 | 456d | NA | NA | 0 days? | No | NA | NA | NA | 0
13780 | Configure Enablement for Staging Evnironment | November 3, 2025 8:00 AM | November 14, 2025 5:00 PM |  | 4893 | Start No Earlier Than | 11/3/25 | 9 | 457d | NA | NA | 0 days? | No | NA | NA | NA | 0
13781 | Publish Completed Training Quick Guides, Knowledge Base Articles, and On-Demand Programs to Staging for User Feedback | November 18, 2025 8:00 AM | November 18, 2025 5:00 PM | 4892,4474,4489,4511,4521,4532,4571,4586,4625,4463,4560,4605 | 4894 | As Soon As Possible | NA | 1 | 456d | NA | NA | 0 s? | No | NA | NA | NA | 0
13782 | Link Materials for Staging Environment | November 19, 2025 8:00 AM | November 25, 2025 5:00 PM | 4893 | 4895 | As Soon As Possible | NA | 5 | 456d | NA | NA | 0 days? | No | NA | NA | NA | 0
13783 | Test On-Demand Training Programs | November 26, 2025 8:00 AM | December 8, 2025 5:00 PM | 4894 | 4896 | As Soon As Possible | NA | 8 | 456d | NA | NA | 0 days? | No | NA | NA | NA | 0
13784 | Enable User Access and Assign On-Demand Programs | December 9, 2025 8:00 AM | December 15, 2025 5:00 PM | 4895 |  | As Soon As Possible | NA | 5 | 456d | NA | NA | 0 days? | No | NA | NA | NA | 0
13785 | Set 2 Drops 1-5 QG and KBAs and 61 On-Demand Programs | February 10, 2026 8:00 AM | March 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 34 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
13786 | Configure Enablement for EUST 3 Evnironment | February 10, 2026 8:00 AM | February 13, 2026 5:00 PM | 4689 | 4899 | As Soon As Possible | NA | 4 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
13787 | Publish Completed Training Quick Guides, Knowledge Base Articles, and On-Demand Programs to EUST 3 Envt | February 17, 2026 8:00 AM | February 17, 2026 5:00 PM | 4898,4515,4526,4575 | 4900 | As Soon As Possible | NA | 1 | 385d | NA | NA | 0 s? | No | NA | NA | NA | 0
13788 | Link Materials for EUST 3 Environment | February 18, 2026 8:00 AM | February 24, 2026 5:00 PM | 4899 | 4901 | As Soon As Possible | NA | 5 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
13789 | Test On-Demand Training Programs | February 25, 2026 8:00 AM | March 3, 2026 5:00 PM | 4900 | 4902 | As Soon As Possible | NA | 5 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
13790 | Enable User Access and Assign On-Demand Programs | March 4, 2026 8:00 AM | March 30, 2026 5:00 PM | 4901 |  | As Soon As Possible | NA | 19 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
13791 | Set 3 Updates to QGs and KBAs and 81 On-Demand Programs | January 27, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 24 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
13792 | Publish Completed Training Quick Guides, Knowledge Base Articles, and On-Demand Programs to EUST 3 Envt | January 27, 2026 8:00 AM | January 27, 2026 5:00 PM | 4478,4537,4493,4590,4629 | 4905 | As Soon As Possible | NA | 1 | 405d | NA | NA | 0 s? | No | NA | NA | NA | 0
13793 | Link Materials for EUST 3 Envt | January 28, 2026 8:00 AM | February 3, 2026 5:00 PM | 4904 | 4906 | As Soon As Possible | NA | 5 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
13772 | Test On-Demand Training Programs | February 4, 2026 8:00 AM | February 17, 2026 5:00 PM | 4905 | 4907 | As Soon As Possible | NA | 9 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
13773 | Enable User Access and On-Demand Programs | February 18, 2026 8:00 AM | March 2, 2026 5:00 PM | 4906 |  | As Soon As Possible | NA | 9 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
13774 | Set 4 Updates to QGs and KBAs and 104 On-Demand Programs | March 24, 2026 8:00 AM | April 6, 2026 5:00 PM |  |  | As Soon As Possible | NA | 9 | 381d | NA | NA | 0 days? | No | NA | NA | NA | 0
13775 | Publish Completed Training Quick Guides, Knowledge Base Articles, and On-Demand Programs to EUST 3 Envt | March 24, 2026 8:00 AM | March 24, 2026 5:00 PM | 4720 | 4910 | As Soon As Possible | NA | 1 | 381d | NA | NA | 0 s? | No | NA | NA | NA | 0
13776 | Link Materials for EUST 3 Envt | March 25, 2026 8:00 AM | March 30, 2026 5:00 PM | 4909 | 4911 | As Soon As Possible | NA | 4 | 381d | NA | NA | 0 days? | No | NA | NA | NA | 0
13777 | Test On-Demand Training Programs | April 1, 2026 8:00 AM | April 2, 2026 5:00 PM | 4910 | 4912 | As Soon As Possible | NA | 2 | 381d | NA | NA | 0 days? | No | NA | NA | NA | 0
13799 | Enable User Access and On-Demand Programs | April 3, 2026 8:00 AM | April 6, 2026 5:00 PM | 4911 |  | As Soon As Possible | NA | 2 | 381d | NA | NA | 0 days? | No | NA | NA | NA | 0
13800 | Set 5 All Training Materials (After Hardening Updates Complete) | May 5, 2026 8:00 AM | June 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 26 | 335d | NA | NA | 0 days? | No | NA | NA | NA | 0
13801 | Publish Completed Training Quick Guides, Knowledge Base Articles, and On-Demand Programs to Sandbox Envt | May 5, 2026 8:00 AM | May 5, 2026 5:00 PM | 4816 | 4915 | As Soon As Possible | NA | 1 | 335d | NA | NA | 0 s? | No | NA | NA | NA | 0
13802 | Link Materials for Sandbox Envt | May 6, 2026 8:00 AM | May 12, 2026 5:00 PM | 4914 | 4916 | As Soon As Possible | NA | 5 | 335d | NA | NA | 0 days? | No | NA | NA | NA | 0
13778 | Test On-Demand Training Programs for Sandbox Envt | May 13, 2026 8:00 AM | May 27, 2026 5:00 PM | 4915 | 4917 | As Soon As Possible | NA | 10 | 335d | NA | NA | 0 days? | No | NA | NA | NA | 0
13767 | Enable User Access and On-Demand Programs for Sandbox Envt | May 28, 2026 8:00 AM | June 10, 2026 5:00 PM | 4916 |  | As Soon As Possible | NA | 10 | 335d | NA | NA | 0 days? | No | NA | NA | NA | 0
13768 | Configure Enablement for Production Environment | May 5, 2026 8:00 AM | May 11, 2026 5:00 PM | 4816 | 4919 | As Soon As Possible | NA | 5 | 349d | NA | NA | 0 days? | No | NA | NA | NA | 0
13769 | Publish Completed Training Quick Guides and Knowledge Base Articles to Prodcution Envt | May 12, 2026 8:00 AM | May 12, 2026 5:00 PM | 4918 | 4920 | As Soon As Possible | NA | 1 | 349d | NA | NA | 0 s? | No | NA | NA | NA | 0
13794 | Link Materials for Production Envt | May 13, 2026 8:00 AM | May 20, 2026 5:00 PM | 4919 |  | As Soon As Possible | NA | 6 | 349d | NA | NA | 0 days? | No | NA | NA | NA | 0
12586 | Update CWS CARES Glossary | February 3, 2025 8:00 AM | June 11, 2026 5:00 PM |  |  | As Soon As Possible | NA | 341 | 334d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.26000000000000001
9700 | Update CWS-CARES Glossary with Terms from Milestone 3,4,5,6,7,8,9,15,19,20, 21 | February 3, 2025 8:00 AM | March 7, 2025 5:00 PM | 4884FS+112d | 4925,4923FS+175d | As Soon As Possible | NA | 24 | 0d | December 20, 2024 5:00 PM | December 20, 2024 5:00 PM | 0 days | No | 2/3/25 | 3/7/25 | NA | 1
9701 | Update CWS CARES Glossary with Terms from Milestone 6.1,7,9,10,11,13,14,16,17,18 | November 17, 2025 8:00 AM | December 19, 2025 5:00 PM | 4922FS+175d | 4924FS+22d | As Soon As Possible | NA | 24 | 386d | September 2, 2024 8:00 AM | February 27, 2026 5:00 PM | 373 days | No | NA | NA | NA | 0
9702 | Updae CWS CARES Glossary with Terms from all Milestones | January 26, 2026 8:00 AM | February 27, 2026 5:00 PM | 4923FS+22d | 4925 | As Soon As Possible | NA | 24 | 386d | July 13, 2023 8:00 AM | February 27, 2026 5:00 PM | 659 days | No | NA | NA | NA | 0
9703 | Develop after-training evaluations | May 14, 2026 8:00 AM | June 11, 2026 5:00 PM | 4924,4104,4187,4247,4306,4310,4315,4341,4357,4365,4538,4545,4606,4630,4637,4671,4678,4709FS-1d,4721,4737,4738,4770,4922,4116,4127,4139,4150,4448,4754,4767,4777,4316,4317,4272,4852,4889 |  | As Soon As Possible | NA | 20 | 334d | March 2, 2026 8:00 AM | March 27, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
9704 | Training Advisory Workgroup Engagement | April 2, 2024 8:00 AM | September 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 629 | 18d | April 2, 2024 8:00 AM | September 30, 2026 5:00 PM | 629 days | No | 4/2/24 | NA | NA | 0.60999999999999999
9705 | Training Advisory Workgroup Engagement 1 | April 2, 2024 8:00 AM | May 31, 2024 5:00 PM | 3192 | 4928 | Start No Earlier Than | 4/1/24 | 43 | 0d | April 2, 2024 8:00 AM | May 31, 2024 5:00 PM | 43 days | No | 4/2/24 | 5/31/24 | NA | 1
9706 | Training Advisory Workgroup Engagement 2 | June 3, 2024 8:00 AM | July 31, 2024 5:00 PM | 4927 | 4929 | Start No Earlier Than | 6/1/24 | 42 | 0d | June 3, 2024 8:00 AM | July 31, 2024 5:00 PM | 42 days | No | 6/3/24 | 7/31/24 | NA | 1
9707 | Training Advisory Workgroup Engagement 3 | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 4928 | 4930 | Start No Earlier Than | 8/1/24 | 22 | 0d | August 1, 2024 8:00 AM | September 27, 2024 5:00 PM | 42 days | No | 8/1/24 | 8/30/24 | NA | 1
11680 | Training Advisory Workgroup Engagement 4 | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM | 4929 | 4931 | Start No Earlier Than | 7/1/24 | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
11681 | Training Advisory Workgroup Engagement 5 | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM | 4930 | 4932 | Start No Earlier Than | 8/1/24 | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
11682 | Training Advisory Workgroup Engagement 6 | November 1, 2024 8:00 AM | November 27, 2024 5:00 PM | 4931 | 4933 | Start No Earlier Than | 9/1/24 | 18 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/27/24 | NA | 1
11683 | Training Advisory Workgroup Engagement 7 | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 4932 | 4934 | Start No Earlier Than | 10/1/24 | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
11684 | Training Advisory Workgroup Engagement 8 | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 4933 | 4935 | Start No Earlier Than | 11/1/24 | 21 | 0d | NA | NA | 0 days? | No | 1/2/25 | 1/31/25 | NA | 1
11685 | Training Advisory Workgroup Engagement 9 | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 4934 | 4936 | Start No Earlier Than | 12/1/24 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
11686 | Training Advisory Workgroup Engagement 10 | March 3, 2025 8:00 AM | March 28, 2025 5:00 PM | 4935 | 4937 | Start No Earlier Than | 1/1/25 | 20 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/28/25 | NA | 1
11687 | Training Advisory Workgroup Engagement 11 | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 4936 | 4938 | Start No Earlier Than | 2/1/25 | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
11688 | Training Advisory Workgroup Engagement 12 | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 4937 | 4939 | Start No Earlier Than | 3/1/25 | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
11689 | Training Advisory Workgroup Engagement 13 | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 4938 | 4940 | Start No Earlier Than | 4/1/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
11690 | Training Advisory Workgroup Engagement 14 | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 4939 | 4941 | Start No Earlier Than | 5/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
11691 | Training Advisory Workgroup Engagement 15 | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 4940 | 4942 | Start No Earlier Than | 6/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
11692 | Training Advisory Workgroup Engagement 16 | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 4941 | 4943 | Start No Earlier Than | 7/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
11693 | Training Advisory Workgroup Engagement 17 | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 4942 | 4944 | Start No Earlier Than | 8/1/25 | 23 | 18d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.34999999999999998
11694 | Training Advisory Workgroup Engagement 18 | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 4943 | 4945 | Start No Earlier Than | 9/1/25 | 18 | 18d | NA | NA | 0 days? | No | NA | NA | NA | 0
11695 | Training Advisory Workgroup Engagement 19 | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 4944 | 4946 | Start No Earlier Than | 10/1/25 | 22 | 18d | NA | NA | 0 days? | No | NA | NA | NA | 0
11696 | Training Advisory Workgroup Engagement 20 | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 4945 | 4947 | Start No Earlier Than | 11/1/25 | 20 | 18d | NA | NA | 0 days? | No | NA | NA | NA | 0
11697 | Training Advisory Workgroup Engagement 21 | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 4946 | 4948 | Start No Earlier Than | 12/1/25 | 19 | 18d | NA | NA | 0 days? | No | NA | NA | NA | 0
11698 | Training Advisory Workgroup Engagement 22 | March 2, 2026 8:00 AM | March 30, 2026 5:00 PM | 4947 | 4949 | Start No Earlier Than | 1/1/26 | 21 | 18d | NA | NA | 0 days? | No | NA | NA | NA | 0
11699 | Training Advisory Workgroup Engagement 23 | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 4948 | 4950 | Start No Earlier Than | 2/1/26 | 22 | 18d | NA | NA | 0 days? | No | NA | NA | NA | 0
11700 | Training Advisory Workgroup Engagement 24 | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 4949 | 4951 | Start No Earlier Than | 3/1/26 | 20 | 18d | NA | NA | 0 days? | No | NA | NA | NA | 0
11701 | Training Advisory Workgroup Engagement 25 | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 4950 | 4952 | Start No Earlier Than | 4/1/26 | 22 | 18d | NA | NA | 0 days? | No | NA | NA | NA | 0
11702 | Training Advisory Workgroup Engagement 26 | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 4951 | 4953 | Start No Earlier Than | 5/1/26 | 22 | 18d | NA | NA | 0 days? | No | NA | NA | NA | 0
11703 | Training Advisory Workgroup Engagement 27 | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 4952 | 4954 | Start No Earlier Than | 6/1/26 | 21 | 18d | NA | NA | 0 days? | No | NA | NA | NA | 0
11704 | Training Advisory Workgroup Engagement 28 | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 4953 | 5630 | Start No Earlier Than | 7/1/26 | 21 | 18d | NA | NA | 0 days? | No | NA | NA | NA | 0
9720 | Organizational Change Management (OCM) | August 15, 2022 8:00 AM | December 11, 2026 5:00 PM |  |  | As Soon As Possible | NA | 1084 | 208d | August 15, 2022 8:00 AM | December 29, 2026 5:00 PM | 1095 days | No | 8/15/22 | NA | NA | 0.81999999999999995
9721 | Create template for weekly Jira status reporting | October 10, 2022 8:00 AM | January 30, 2023 5:00 PM |  |  | As Soon As Possible | NA | 75 | 0d | October 10, 2022 8:00 AM | January 30, 2023 5:00 PM | 75 days | No | 10/10/22 | 1/30/23 | NA | 1
9722 | Create definitions for the status of each workflow component of workflow | October 10, 2022 8:00 AM | October 13, 2022 5:00 PM | 3192SS+87d | 4958 | As Soon As Possible | NA | 4 | 0d | October 10, 2022 8:00 AM | October 13, 2022 5:00 PM | 4 days | No | 10/10/22 | 10/13/22 | NA | 1
9723 | Review WDR presentation materials to understand reporting needs | October 11, 2022 8:00 AM | October 12, 2022 5:00 PM | 4957 | 4959 | As Soon As Possible | NA | 2 | 0d | October 11, 2022 8:00 AM | October 12, 2022 5:00 PM | 2 days | No | 10/11/22 | 10/12/22 | NA | 1
9724 | Collaborate with JIRA SME to discuss options for presenting a more granular view of status | October 17, 2022 8:00 AM | January 27, 2023 5:00 PM | 4958 | 4960 | As Soon As Possible | NA | 69 | 0d | October 17, 2022 8:00 AM | January 27, 2023 5:00 PM | 69 days | No | 10/17/22 | 1/27/23 | NA | 1
9725 | Develop prototype Jira status report | October 14, 2022 8:00 AM | January 27, 2023 5:00 PM | 4959 | 4961SS | As Soon As Possible | NA | 70 | 0d | October 14, 2022 8:00 AM | January 27, 2023 5:00 PM | 70 days | No | 10/14/22 | 1/27/23 | NA | 1
9726 | Share prototype Jira status report with Nichole, Cheryl, and Sonoltra | October 14, 2022 8:00 AM | December 22, 2022 5:00 PM | 4960SS | 4962FS+14d | As Soon As Possible | NA | 47 | 0d | October 14, 2022 8:00 AM | December 22, 2022 5:00 PM | 47 days | No | 10/14/22 | 12/22/22 | NA | 1
9727 | Incorporate feedback as needed | January 17, 2023 8:00 AM | January 25, 2023 5:00 PM | 4961FS+14d | 4963FS+3d | As Soon As Possible | NA | 7 | 0d | January 17, 2023 8:00 AM | January 25, 2023 5:00 PM | 7 days | No | 1/17/23 | 1/25/23 | NA | 1
9728 | Finalize Jira reporting template and begin using it for weekly updates | January 30, 2023 5:00 PM | January 30, 2023 5:00 PM | 4962FS+3d | 4988 | As Soon As Possible | NA | 0 | 0d | January 30, 2023 5:00 PM | January 30, 2023 5:00 PM | 0 days | Yes | 1/30/23 | 1/30/23 | NA | 1
9729 | Review and Leverage existing CARES-Live OCM plan to develop the CWS-CARES OCM plan Version 1 & Version 2 | August 15, 2022 8:00 AM | May 20, 2025 5:00 PM |  |  | As Soon As Possible | NA | 692 | 0d | August 15, 2022 8:00 AM | July 19, 2024 5:00 PM | 483 days | No | 8/15/22 | 5/20/25 | NA | 1
9730 | Review and analyze existing OCM Plan | August 15, 2022 8:00 AM | September 2, 2022 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | August 15, 2022 8:00 AM | September 2, 2022 5:00 PM | 15 days | No | 8/15/22 | 9/2/22 | NA | 1
9731 | Obtain existing OCM Plan (RFA) | August 15, 2022 8:00 AM | August 15, 2022 5:00 PM | 3192FS+52d | 4967 | As Soon As Possible | NA | 1 | 0d | August 15, 2022 8:00 AM | August 15, 2022 5:00 PM | 1 | No | 8/15/22 | 8/15/22 | NA | 1
9732 | Read existing OCM Plan (RFA) - Deliverable Task 5.1 | August 16, 2022 8:00 AM | August 16, 2022 5:00 PM | 4966 | 4968 | As Soon As Possible | NA | 1 | 0d | August 16, 2022 8:00 AM | August 16, 2022 5:00 PM | 1 | No | 8/16/22 | 8/16/22 | NA | 1
9733 | Create tracker to capture notes and proposed Review other examples of OCM plans, review lessons learned, and conduct visioning session with Michelle to align on OCM plan goals, outline, and structure. edits to the OCM Plan | August 17, 2022 8:00 AM | August 19, 2022 5:00 PM | 4967 | 4969 | As Soon As Possible | NA | 3 | 0d | August 17, 2022 8:00 AM | August 19, 2022 5:00 PM | 3 days | No | 8/17/22 | 8/19/22 | NA | 1
9734 | Create DED for OCM Plan | August 22, 2022 8:00 AM | September 2, 2022 5:00 PM | 4968 | 4971FS-10d | As Soon As Possible | NA | 10 | 0d | August 22, 2022 8:00 AM | September 2, 2022 5:00 PM | 10 days | No | 8/22/22 | 9/2/22 | NA | 1
9735 | Develop initial draft of OCM Plan | August 22, 2022 8:00 AM | September 16, 2022 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | August 22, 2022 8:00 AM | September 16, 2022 5:00 PM | 19 days | No | 8/22/22 | 9/16/22 | NA | 1
9736 | Develop outline | August 22, 2022 8:00 AM | August 26, 2022 5:00 PM | 4969FS-10d | 4972 | As Soon As Possible | NA | 5 | 0d | August 22, 2022 8:00 AM | August 26, 2022 5:00 PM | 5 days | No | 8/22/22 | 8/26/22 | NA | 1
9737 | Create storyboard | August 29, 2022 8:00 AM | September 2, 2022 5:00 PM | 4971 | 4973 | As Soon As Possible | NA | 5 | 0d | August 29, 2022 8:00 AM | September 2, 2022 5:00 PM | 5 days | No | 8/29/22 | 9/2/22 | NA | 1
9738 | Build content | September 5, 2022 8:00 AM | September 12, 2022 5:00 PM | 4972 | 4974 | As Soon As Possible | NA | 5 | 0d | September 5, 2022 8:00 AM | September 12, 2022 5:00 PM | 5 days | No | 9/5/22 | 9/12/22 | NA | 1
9739 | Complete initial draft | September 12, 2022 8:00 AM | September 16, 2022 5:00 PM | 4973 | 4976 | As Soon As Possible | NA | 5 | 0d | September 12, 2022 8:00 AM | September 16, 2022 5:00 PM | 5 days | No | 9/12/22 | 9/16/22 | NA | 1
9740 | Develop draft of OCM Plan for State team review (CARES RACI) | September 19, 2022 8:00 AM | November 10, 2022 5:00 PM |  |  | As Soon As Possible | NA | 39 | 0d | September 19, 2022 8:00 AM | November 10, 2022 5:00 PM | 39 days | No | 9/19/22 | 11/10/22 | NA | 1
9741 | Refine content | September 19, 2022 8:00 AM | September 23, 2022 5:00 PM | 4974 | 4977 | As Soon As Possible | NA | 5 | 0d | September 19, 2022 8:00 AM | September 23, 2022 5:00 PM | 5 days | No | 9/19/22 | 9/23/22 | NA | 1
9742 | Conduct reviews with Deloitte and State Implementation Leads | September 27, 2022 8:00 AM | September 27, 2022 5:00 PM | 4976 | 4978 | As Soon As Possible | NA | 1 | 0d | September 27, 2022 8:00 AM | September 27, 2022 5:00 PM | 1 | No | 9/27/22 | 9/27/22 | NA | 1
9743 | Share with SMEs and County Consultants | September 28, 2022 8:00 AM | October 4, 2022 5:00 PM | 4977 | 4979FS+8d | As Soon As Possible | NA | 5 | 0d | September 28, 2022 8:00 AM | October 4, 2022 5:00 PM | 5 days | No | 9/28/22 | 10/4/22 | NA | 1
9744 | Incorporate feedback from reviewers | October 17, 2022 8:00 AM | November 4, 2022 5:00 PM | 4978FS+8d | 4980 | As Soon As Possible | NA | 15 | 0d | October 17, 2022 8:00 AM | November 4, 2022 5:00 PM | 15 days | No | 10/17/22 | 11/4/22 | NA | 1
9745 | Review updated OCM Plan with PaaS SI Team, IV&V Team, Project Directors, ELT and BOD | October 27, 2022 8:00 AM | November 10, 2022 5:00 PM | 4979 | 4982 | As Soon As Possible | NA | 11 | 0d | October 27, 2022 8:00 AM | November 10, 2022 5:00 PM | 11 days | No | 10/27/22 | 11/10/22 | NA | 1
9746 | Incorporate feedback from CARES reviewers | November 14, 2022 8:00 AM | November 14, 2022 5:00 PM |  |  | As Soon As Possible | NA | 1 | 0d | November 14, 2022 8:00 AM | November 14, 2022 5:00 PM | 1 | No | 11/14/22 | 11/14/22 | NA | 1
9747 | Create comment matrix and document feedback on the OCM Plan | November 14, 2022 8:00 AM | November 14, 2022 5:00 PM | 4980 | 4984FS+5d | As Soon As Possible | NA | 1 | 0d | November 14, 2022 8:00 AM | November 14, 2022 5:00 PM | 1 | No | 11/14/22 | 11/14/22 | NA | 1
9748 | Update OCM Plan based on reviewer feedback | November 22, 2022 8:00 AM | November 29, 2022 5:00 PM |  |  | As Soon As Possible | NA | 4 | 0d | November 22, 2022 8:00 AM | November 29, 2022 5:00 PM | 4 days | No | 11/22/22 | 11/29/22 | NA | 1
9749 | State reviews Plan with comments and provides signoff/approval | November 22, 2022 8:00 AM | November 29, 2022 5:00 PM | 4982FS+5d | 4985 | As Soon As Possible | NA | 4 | 0d | November 22, 2022 8:00 AM | November 29, 2022 5:00 PM | 4 days | No | 11/22/22 | 11/29/22 | NA | 1
9750 | SPR 6 - Organizational Change Management (OCM) Plan Update (CWS-CARES V1) | November 29, 2022 5:00 PM | November 29, 2022 5:00 PM | 4984 | 4988FS+308d | As Soon As Possible | NA | 0 | 0d | November 29, 2022 5:00 PM | November 29, 2022 5:00 PM | 0 days | Yes | 11/29/22 | 11/29/22 | 11/29/22 | 1
9751 | CWS-CARES Organizational Change Management Plan Version 2 | February 26, 2024 8:00 AM | May 20, 2025 5:00 PM |  |  | As Soon As Possible | NA | 311 | 0d | February 26, 2024 8:00 AM | July 19, 2024 5:00 PM | 102 days | No | 2/26/24 | 5/20/25 | NA | 1
9752 | Review and analyze existing OCM Plan | February 26, 2024 8:00 AM | March 19, 2024 5:00 PM |  |  | As Soon As Possible | NA | 17 | 0d | February 26, 2024 8:00 AM | March 19, 2024 5:00 PM | 17 days | No | 2/26/24 | 3/19/24 | NA | 1
9753 | Review existing OCM Plan and create tracker to capture notes and review other examples of OCM plans, review lessons learned, and conduct visioning session with Michelle to align on OCM plan goals, outline, and structure. | February 26, 2024 8:00 AM | March 19, 2024 5:00 PM | 4985FS+308d,4963 | 4990 | As Soon As Possible | NA | 17 | 0d | February 26, 2024 8:00 AM | March 19, 2024 5:00 PM | 17 days | No | 2/26/24 | 3/19/24 | NA | 1
9756 | Develop initial draft of updated OCM Plan | March 20, 2024 8:00 AM | April 26, 2024 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | March 20, 2024 8:00 AM | April 26, 2024 5:00 PM | 27 days | No | 3/20/24 | 4/26/24 | NA | 1
9757 | Develop outline | March 20, 2024 8:00 AM | March 28, 2024 5:00 PM | 4988 | 4991 | As Soon As Possible | NA | 7 | 0d | March 20, 2024 8:00 AM | March 28, 2024 5:00 PM | 7 days | No | 3/20/24 | 3/28/24 | NA | 1
9758 | Finalize the Outline of Updated OCM Plan | March 29, 2024 8:00 AM | April 5, 2024 5:00 PM | 4990 | 4992 | As Soon As Possible | NA | 5 | 0d | March 29, 2024 8:00 AM | April 5, 2024 5:00 PM | 5 days | No | 3/29/24 | 4/5/24 | NA | 1
9759 | Build content | April 8, 2024 8:00 AM | April 19, 2024 5:00 PM | 4991 | 4993 | As Soon As Possible | NA | 10 | 0d | April 8, 2024 8:00 AM | April 19, 2024 5:00 PM | 10 days | No | 4/8/24 | 4/19/24 | NA | 1
9760 | Complete Reviews and Update Initial draft | April 22, 2024 8:00 AM | April 26, 2024 5:00 PM | 4992 | 4995 | As Soon As Possible | NA | 5 | 0d | April 22, 2024 8:00 AM | April 26, 2024 5:00 PM | 5 days | No | 4/22/24 | 4/26/24 | NA | 1
9761 | Develop draft of updated OCM Plan for State team review (CARES RACI) | April 29, 2024 8:00 AM | October 14, 2024 5:00 PM |  |  | As Soon As Possible | NA | 119 | 0d | April 29, 2024 8:00 AM | July 19, 2024 5:00 PM | 58 days | No | 4/29/24 | 10/14/24 | NA | 1
9762 | Refine Proposed content | April 29, 2024 8:00 AM | May 3, 2024 5:00 PM | 4993 | 4996SS | As Soon As Possible | NA | 5 | 0d | April 29, 2024 8:00 AM | May 3, 2024 5:00 PM | 5 days | No | 4/29/24 | 5/3/24 | NA | 1
9763 | Create comment matrix and document feedback on the updated OCM Plan | April 29, 2024 8:00 AM | May 3, 2024 5:00 PM | 4995SS | 4997 | As Soon As Possible | NA | 5 | 0d | April 29, 2024 8:00 AM | May 3, 2024 5:00 PM | 5 days | No | 4/29/24 | 5/3/24 | NA | 1
9764 | Conduct reviews of OCM Plan V2 with Internal Leadership | May 6, 2024 8:00 AM | May 10, 2024 5:00 PM | 4996 | 4998 | As Soon As Possible | NA | 5 | 0d | May 6, 2024 8:00 AM | May 10, 2024 5:00 PM | 5 days | No | 5/6/24 | 5/10/24 | NA | 1
9765 | Share Tracker with State Leads and Request Feedback | May 13, 2024 8:00 AM | May 22, 2024 5:00 PM | 4997 | 4999 | As Soon As Possible | NA | 8 | 0d | May 13, 2024 8:00 AM | May 22, 2024 5:00 PM | 8 days | No | 5/13/24 | 5/22/24 | NA | 1
9766 | Incorporate feedback from reviewers | May 23, 2024 8:00 AM | May 31, 2024 5:00 PM | 4998 | 5000FS+15d | As Soon As Possible | NA | 6 | 0d | May 23, 2024 8:00 AM | May 31, 2024 5:00 PM | 6 days | No | 5/23/24 | 5/31/24 | NA | 1
12192 | Complete initial updates in the OCM Plan V2 file with appropriate Project Teams | June 24, 2024 8:00 AM | July 8, 2024 5:00 PM | 4999FS+15d | 5001 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 6/24/24 | 7/8/24 | NA | 1
12193 | Complete internal OCM Team review of initial updates in the OCM Plan V2 file | July 9, 2024 8:00 AM | July 11, 2024 5:00 PM | 5000 | 5002 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 7/9/24 | 7/11/24 | NA | 1
12194 | Complete internal leadership review and Implementation Delivery Owner review of the initial updates in the OCM Plan V2 file | July 12, 2024 8:00 AM | July 19, 2024 5:00 PM | 5001 | 5003FS+3d | As Soon As Possible | NA | 6 | 0d | NA | NA | 0 days? | No | 7/12/24 | 7/19/24 | NA | 1
12195 | Incorporate feedback and schedule walkthroughs of the OCM Plan V2 file updates with State Implementation Management Team | July 25, 2024 8:00 AM | August 2, 2024 5:00 PM | 5002FS+3d | 5004FS+4d | As Soon As Possible | NA | 7 | 0d | NA | NA | 0 days? | No | 7/25/24 | 8/2/24 | NA | 1
12196 | Complete State Implementation Management Team offline reviews and walkthroughs | August 9, 2024 8:00 AM | August 15, 2024 5:00 PM | 5003FS+4d | 5005 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 8/9/24 | 8/15/24 | NA | 1
12197 | Incorporate feedback from State Implementation Management Team | August 16, 2024 8:00 AM | August 20, 2024 5:00 PM | 5004 | 5006 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 8/16/24 | 8/20/24 | NA | 1
9767 | Review updated OCM Plan with PaaS SI Team, IV&V Team, Project Directors, and ELT | August 21, 2024 8:00 AM | September 3, 2024 5:00 PM | 5005 | 5007 | As Soon As Possible | NA | 10 | 0d | June 24, 2024 8:00 AM | July 8, 2024 5:00 PM | 10 days | No | 8/21/24 | 9/3/24 | NA | 1
9768 | Incorporate Feedback from PaaS SI Team, IV&V Team, Project Directors, and ELT | September 4, 2024 8:00 AM | September 10, 2024 5:00 PM | 5006 | 5008 | As Soon As Possible | NA | 5 | 0d | July 9, 2024 8:00 AM | July 12, 2024 5:00 PM | 4 days | No | 9/4/24 | 9/10/24 | NA | 1
12199 | Review updated OCM Plan with ELT | September 11, 2024 8:00 AM | September 30, 2024 5:00 PM | 5007 | 5009 | As Soon As Possible | NA | 14 | 0d | NA | NA | 0 days? | No | 9/11/24 | 9/30/24 | NA | 1
12200 | Incorporate feedback from ELT | October 1, 2024 8:00 AM | October 7, 2024 5:00 PM | 5008 | 5010 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/7/24 | NA | 1
9769 | State reviews updated OCM Plan with comments and provides signoff/approval | October 8, 2024 8:00 AM | October 14, 2024 5:00 PM | 5009 | 5621,5012FS+75d | As Soon As Possible | NA | 5 | 0d | July 15, 2024 8:00 AM | July 19, 2024 5:00 PM | 5 days | No | 10/8/24 | 10/14/24 | NA | 1
12587 | CWS-CARES Organizational Change Management Plan - Final Version | February 5, 2025 8:00 AM | March 5, 2025 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/5/25 | 3/5/25 | NA | 1
12588 | Review OCM Plan v2 and identify areas to include for updates in the proposed tracker for Final OCM Plan | February 5, 2025 8:00 AM | February 11, 2025 5:00 PM | 5010FS+75d | 5013 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 2/5/25 | 2/11/25 | NA | 1
12589 | Develop tracker with proposed updates for Final OCM Plan | February 12, 2025 8:00 AM | February 19, 2025 5:00 PM | 5012 | 5014 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 2/12/25 | 2/19/25 | NA | 1
12590 | Complete internal review of tracker with proposed updates for Final OCM Plan | February 20, 2025 8:00 AM | February 26, 2025 5:00 PM | 5013 | 5015 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 2/20/25 | 2/26/25 | NA | 1
12591 | Complete State Leadership review of tracker with proposed updates for Final OCM Plan and seek approval to begin updated draft | February 27, 2025 8:00 AM | March 5, 2025 5:00 PM | 5014 | 5017 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 2/27/25 | 3/5/25 | NA | 1
12592 | Develop draft of Final OCM Plan for review (includes CARES RACI) | March 6, 2025 8:00 AM | May 20, 2025 5:00 PM |  |  | As Soon As Possible | NA | 53 | 0d | NA | NA | 0 days? | No | 3/6/25 | 5/20/25 | NA | 1
12593 | Complete updates from the approved tracker for the Final OCM Plan | March 6, 2025 8:00 AM | March 26, 2025 5:00 PM | 5015 | 5018 | As Soon As Possible | NA | 15 | 0d | NA | NA | 0 days? | No | 3/6/25 | 3/26/25 | NA | 1
12594 | Conduct reviews of the Final OCM Plan with internal OCM Team and complete QA | March 27, 2025 8:00 AM | April 3, 2025 5:00 PM | 5017 | 5019 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 3/27/25 | 4/3/25 | NA | 1
12595 | Conduct reviews of the Final OCM Plan with internal leadership, State OCM Lead, Implementation Delivery Owners, and Training Lead | April 4, 2025 8:00 AM | April 14, 2025 5:00 PM | 5018 | 5020 | As Soon As Possible | NA | 7 | 0d | NA | NA | 0 days? | No | 4/4/25 | 4/14/25 | NA | 1
12596 | Incorporate feedback from reviewers | April 15, 2025 8:00 AM | April 17, 2025 5:00 PM | 5019 | 5021 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 4/15/25 | 4/17/25 | NA | 1
12597 | Conduct reviews of the Final OCM Plan with State Implementation Management Team | April 18, 2025 8:00 AM | April 24, 2025 5:00 PM | 5020 | 5022 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 4/18/25 | 4/24/25 | NA | 1
12598 | Incorporate feedback from reviewers | April 25, 2025 8:00 AM | April 29, 2025 5:00 PM | 5021 | 5023 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 4/25/25 | 4/29/25 | NA | 1
12599 | Conduct reviews of the Final OCM Plan with RACI reviewers | April 30, 2025 8:00 AM | May 6, 2025 5:00 PM | 5022 | 5024 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 4/30/25 | 5/6/25 | NA | 1
12600 | Incorporate feedback from reviewers | May 7, 2025 8:00 AM | May 9, 2025 5:00 PM | 5023 | 5025 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 5/7/25 | 5/9/25 | NA | 1
12601 | Conduct ELT review of the Final OCM Plan and incorporate feedback | May 12, 2025 8:00 AM | May 16, 2025 5:00 PM | 5024 | 5026 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 5/12/25 | 5/16/25 | NA | 1
12602 | State reviews Final OCM Plan with comments and provides signoff/approval | May 19, 2025 8:00 AM | May 20, 2025 5:00 PM | 5025 | 5630 | As Soon As Possible | NA | 2 | 0d | NA | NA | 0 days? | No | 5/19/25 | 5/20/25 | NA | 1
9771 | Develop baseline as-is process documentation - Deliverable Task 5.4 | August 18, 2022 8:00 AM | June 21, 2024 5:00 PM |  |  | As Soon As Possible | NA | 461 | 0d | August 18, 2022 8:00 AM | July 5, 2024 5:00 PM | 470 days | No | 8/18/22 | 6/21/24 | NA | 1
9772 | Create As-Is Process Maps for Assessments | August 18, 2022 8:00 AM | August 31, 2022 5:00 PM | 3192FS+55d | 5029FS-3d | As Soon As Possible | NA | 10 | 0d | August 18, 2022 8:00 AM | August 31, 2022 5:00 PM | 10 days | No | 8/18/22 | 8/31/22 | NA | 1
9773 | Create As-Is Process Maps for General Capabilities | August 29, 2022 8:00 AM | September 12, 2022 5:00 PM | 5028FS-3d | 5030FS-5d | As Soon As Possible | NA | 10 | 0d | August 29, 2022 8:00 AM | September 12, 2022 5:00 PM | 10 days | No | 8/29/22 | 9/12/22 | NA | 1
9774 | Create As-Is Process Maps for Case Planning | September 5, 2022 8:00 AM | September 19, 2022 5:00 PM | 5029FS-5d | 5031FS-10d | As Soon As Possible | NA | 10 | 0d | September 5, 2022 8:00 AM | September 19, 2022 5:00 PM | 10 days | No | 9/5/22 | 9/19/22 | NA | 1
9775 | Create As-Is Process Maps for Services | September 5, 2022 8:00 AM | September 19, 2022 5:00 PM | 5030FS-10d | 5032FS+10d | As Soon As Possible | NA | 10 | 0d | September 5, 2022 8:00 AM | September 19, 2022 5:00 PM | 10 days | No | 9/5/22 | 9/19/22 | NA | 1
9776 | Create As-Is Process Maps for Licensing | October 3, 2022 8:00 AM | October 14, 2022 5:00 PM | 5031FS+10d | 5033FS-10d | As Soon As Possible | NA | 10 | 0d | October 3, 2022 8:00 AM | October 14, 2022 5:00 PM | 10 days | No | 10/3/22 | 10/14/22 | NA | 1
9777 | Create As-Is Process Maps for RM Services | October 3, 2022 8:00 AM | October 14, 2022 5:00 PM | 5032FS-10d | 5034FS+15d | As Soon As Possible | NA | 10 | 0d | October 3, 2022 8:00 AM | October 14, 2022 5:00 PM | 10 days | No | 10/3/22 | 10/14/22 | NA | 1
9778 | Create As-Is Process Maps for Placement | November 2, 2022 8:00 AM | January 27, 2023 5:00 PM | 5033FS+15d | 5035FS+15d | As Soon As Possible | NA | 57 | 0d | November 2, 2022 8:00 AM | January 27, 2023 5:00 PM | 57 days | No | 11/2/22 | 1/27/23 | NA | 1
9779 | Create As-Is Process Maps for Court Processing | January 9, 2023 8:00 AM | January 30, 2023 5:00 PM | 5034FS+15d | 5036FS-15d | As Soon As Possible | NA | 15 | 0d | January 9, 2023 8:00 AM | January 30, 2023 5:00 PM | 15 days | No | 1/9/23 | 1/30/23 | NA | 1
9780 | Create As-Is Process Maps for Eligibility | January 23, 2023 8:00 AM | February 27, 2023 5:00 PM | 5035FS-15d | 5037FS+14d | As Soon As Possible | NA | 25 | 0d | January 23, 2023 8:00 AM | February 27, 2023 5:00 PM | 25 days | No | 1/23/23 | 2/27/23 | NA | 1
9781 | Create As-Is Process Maps for CM Adoptions | March 20, 2023 8:00 AM | March 31, 2023 5:00 PM | 5036FS+14d | 5038FS+2d | As Soon As Possible | NA | 9 | 0d | March 20, 2023 8:00 AM | March 31, 2023 5:00 PM | 9 days | No | 3/20/23 | 3/31/23 | NA | 1
9782 | Create As-Is Process Maps for Financial Management | April 5, 2023 8:00 AM | May 12, 2023 5:00 PM | 5037FS+2d | 5039FS-10d,5046 | As Soon As Possible | NA | 28 | 0d | April 5, 2023 8:00 AM | May 12, 2023 5:00 PM | 28 days | No | 4/5/23 | 5/12/23 | NA | 1
9783 | Create As-Is Process Maps for Quality Assurance and Reporting | April 5, 2023 8:00 AM | April 18, 2023 5:00 PM | 5038FS-10d | 5046,5040FS+23d | As Soon As Possible | NA | 10 | 0d | April 5, 2023 8:00 AM | April 18, 2023 5:00 PM | 10 days | No | 4/5/23 | 4/18/23 | NA | 1
9784 | Create As-Is Process Maps for Administration | May 22, 2023 8:00 AM | June 9, 2023 5:00 PM | 5039FS+23d | 5046,5041 | As Soon As Possible | NA | 14 | 0d | May 22, 2023 8:00 AM | June 9, 2023 5:00 PM | 14 days | No | 5/22/23 | 6/9/23 | NA | 1
9785 | Review and Verify As-Is Process Maps for Administration with Service Managers | June 12, 2023 8:00 AM | June 16, 2023 5:00 PM | 5040 | 5046,5042FS+39d | As Soon As Possible | NA | 5 | 0d | June 12, 2023 8:00 AM | June 16, 2023 5:00 PM | 5 days | No | 6/12/23 | 6/16/23 | NA | 1
9786 | Create As-Is Process Maps for Probation | August 14, 2023 8:00 AM | August 31, 2023 5:00 PM | 5041FS+39d | 5043 | As Soon As Possible | NA | 14 | 0d | August 14, 2023 8:00 AM | August 31, 2023 5:00 PM | 14 days | No | 8/14/23 | 8/31/23 | NA | 1
9787 | Review and Verify As-Is Process for Probation with SMEs | September 1, 2023 8:00 AM | October 6, 2023 5:00 PM | 5042 | 5046,5044FS-2d | As Soon As Possible | NA | 25 | 0d | September 1, 2023 8:00 AM | October 6, 2023 5:00 PM | 25 days | No | 9/1/23 | 10/6/23 | NA | 1
9788 | Create As-Is Process Maps for CDSS | October 5, 2023 8:00 AM | February 23, 2024 5:00 PM | 5043FS-2d | 5046,5045 | As Soon As Possible | NA | 95 | 0d | October 5, 2023 8:00 AM | February 23, 2024 5:00 PM | 95 days | No | 10/5/23 | 2/23/24 | NA | 1
9789 | Continue baseline CDSS As-Is business process map reviews and support discovery conversations. | February 26, 2024 8:00 AM | June 21, 2024 5:00 PM | 5044 | 5046 | As Soon As Possible | NA | 83 | 0d | February 26, 2024 8:00 AM | July 5, 2024 5:00 PM | 92 days | No | 2/26/24 | 6/21/24 | NA | 1
9790 | As-is Documentation Completed | June 21, 2024 5:00 PM | June 21, 2024 5:00 PM | 5038,5039,5040,5041,5043,5044,5045 | 5364FS-12d | As Soon As Possible | NA | 0 | 0d | July 5, 2024 5:00 PM | July 5, 2024 5:00 PM | 0 days | Yes | 6/21/24 | 6/21/24 | NA | 1
9791 | Fresno Support Plan - OCM | March 29, 2023 8:00 AM | May 3, 2023 5:00 PM |  |  | As Soon As Possible | NA | 25 | 0d | March 29, 2023 8:00 AM | May 3, 2023 5:00 PM | 25 days | No | 3/29/23 | 5/3/23 | NA | 1
9792 | Initial Planning - OCM | March 29, 2023 8:00 AM | March 30, 2023 5:00 PM |  |  | As Soon As Possible | NA | 2 | 0d | March 29, 2023 8:00 AM | March 30, 2023 5:00 PM | 2 days | No | 3/29/23 | 3/30/23 | NA | 1
9793 | Conduct business process discussions with Fresno and CDSS SMEs to define any business process change impacts specific to Fresno | March 29, 2023 8:00 AM | March 30, 2023 5:00 PM | 4287FS-2d | 5050FF,5052FS+3d,5053FS+5d | As Soon As Possible | NA | 2 | 0d | March 29, 2023 8:00 AM | March 30, 2023 5:00 PM | 2 days | No | 3/29/23 | 3/30/23 | NA | 1
9794 | Meet with Fresno/CDSS to discuss current state | March 30, 2023 8:00 AM | March 30, 2023 5:00 PM | 5049FF | 5057 | As Soon As Possible | NA | 1 | 0d | March 30, 2023 8:00 AM | March 30, 2023 5:00 PM | 1 | No | 3/30/23 | 3/30/23 | NA | 1
9795 | Change Management Support - OCM | April 6, 2023 8:00 AM | April 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 17 | 0d | April 6, 2023 8:00 AM | April 28, 2023 5:00 PM | 17 days | No | 4/6/23 | 4/28/23 | NA | 1
9796 | Draft rollout communication Plan (RFA Benefits/Value, timeline, expectations, training, support model) | April 6, 2023 8:00 AM | April 14, 2023 5:00 PM | 5049FS+3d | 5054SS+5d | As Soon As Possible | NA | 7 | 0d | April 6, 2023 8:00 AM | April 14, 2023 5:00 PM | 7 days | No | 4/6/23 | 4/14/23 | NA | 1
9797 | Determine 'H' drive cross walk requirements | April 10, 2023 8:00 AM | April 13, 2023 5:00 PM | 5049FS+5d | 5054SS+3d,5055 | As Soon As Possible | NA | 4 | 0d | April 10, 2023 8:00 AM | April 13, 2023 5:00 PM | 4 days | No | 4/10/23 | 4/13/23 | NA | 1
9798 | Identify Additional Change Management Support | April 13, 2023 8:00 AM | April 28, 2023 5:00 PM | 5053SS+3d,5052SS+5d | 5055SS+1d | As Soon As Possible | NA | 12 | 0d | April 13, 2023 8:00 AM | April 28, 2023 5:00 PM | 12 days | No | 4/13/23 | 4/28/23 | NA | 1
9799 | Execute 'H' Drive cross walk requirements' plan | April 14, 2023 8:00 AM | April 27, 2023 5:00 PM | 5053,5054SS+1d | 5621 | As Soon As Possible | NA | 10 | 0d | April 14, 2023 8:00 AM | April 27, 2023 5:00 PM | 10 days | No | 4/14/23 | 4/27/23 | NA | 1
9800 | Training Survey - OCM | April 3, 2023 8:00 AM | May 3, 2023 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | April 3, 2023 8:00 AM | May 3, 2023 5:00 PM | 23 days | No | 4/3/23 | 5/3/23 | NA | 1
9801 | Define post-training support structure | April 3, 2023 8:00 AM | May 3, 2023 5:00 PM | 5050 | 5621 | As Soon As Possible | NA | 23 | 0d | April 3, 2023 8:00 AM | May 3, 2023 5:00 PM | 23 days | No | 4/3/23 | 5/3/23 | NA | 1
9802 | Share As-Is process documentation with orgs | September 19, 2022 8:00 AM | September 30, 2022 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | September 19, 2022 8:00 AM | September 30, 2022 5:00 PM | 10 days | No | 9/19/22 | 9/30/22 | NA | 1
9803 | Develop approach for sharing As-Is process documentation with orgs | September 19, 2022 8:00 AM | September 23, 2022 5:00 PM | 3192FS+75d | 5060FS+4d | As Soon As Possible | NA | 5 | 0d | September 19, 2022 8:00 AM | September 23, 2022 5:00 PM | 5 days | No | 9/19/22 | 9/23/22 | NA | 1
9804 | Review approach with Implementation Team | September 30, 2022 8:00 AM | September 30, 2022 5:00 PM | 5059FS+4d | 5066 | As Soon As Possible | NA | 1 | 0d | September 30, 2022 8:00 AM | September 30, 2022 5:00 PM | 1 | No | 9/30/22 | 9/30/22 | NA | 1
9870 | Execute OCM plan- Deliverable Tasks 5.2 - 5.3, 5.7-5.8 | September 1, 2022 8:00 AM | December 11, 2026 5:00 PM |  |  | As Soon As Possible | NA | 1071 | 208d | September 1, 2022 8:00 AM | December 29, 2026 5:00 PM | 1082 days | No | 9/1/22 | NA | NA | 0.79000000000000004
9871 | Discover Phase | September 1, 2022 8:00 AM | September 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 1008 | 32d | September 1, 2022 8:00 AM | October 25, 2024 5:00 PM | 540 days | No | 9/1/22 | NA | NA | 0.92000000000000004
9872 | Configure Change Tool (ChangeScout) | September 1, 2022 8:00 AM | July 3, 2024 5:00 PM |  |  | As Soon As Possible | NA | 459 | 0d | September 1, 2022 8:00 AM | July 3, 2024 5:00 PM | 459 days | No | 9/1/22 | 7/3/24 | NA | 1
9873 | Define OCM Change Tool Requirements | September 1, 2022 8:00 AM | September 12, 2022 5:00 PM | 3192FS+65d | 5065FS+5d | As Soon As Possible | NA | 7 | 0d | September 1, 2022 8:00 AM | September 12, 2022 5:00 PM | 7 days | No | 9/1/22 | 9/12/22 | NA | 1
9874 | Facilitate ChangeScout demonstration | September 19, 2022 8:00 AM | September 23, 2022 5:00 PM | 5064FS+5d | 5066FS+5d | As Soon As Possible | NA | 5 | 0d | September 19, 2022 8:00 AM | September 23, 2022 5:00 PM | 5 days | No | 9/19/22 | 9/23/22 | NA | 1
9875 | State Decision about Tool selection | October 3, 2022 8:00 AM | February 8, 2023 5:00 PM | 5065FS+5d,5060 | 5067FS-2d | As Soon As Possible | NA | 87 | 0d | October 3, 2022 8:00 AM | February 8, 2023 5:00 PM | 87 days | No | 10/3/22 | 2/8/23 | NA | 1
9876 | Procure Change Tool Licenses | January 30, 2023 8:00 AM | July 17, 2023 5:00 PM | 5066FS-2d | 5068FS+78d | As Soon As Possible | NA | 117 | 0d | January 30, 2023 8:00 AM | July 17, 2023 5:00 PM | 117 days | No | 1/30/23 | 7/17/23 | NA | 1
9877 | Deliver training on Change Tool for users | November 6, 2023 8:00 AM | November 16, 2023 5:00 PM | 5067FS+78d | 5069 | As Soon As Possible | NA | 8 | 0d | November 6, 2023 8:00 AM | November 16, 2023 5:00 PM | 8 days | No | 11/6/23 | 11/16/23 | NA | 1
9878 | Begin Using Change Tool | November 17, 2023 8:00 AM | November 17, 2023 5:00 PM | 5068 | 5070FS+145d | As Soon As Possible | NA | 1 | 0d | November 17, 2023 8:00 AM | November 17, 2023 5:00 PM | 1 | No | 11/17/23 | 11/17/23 | NA | 1
9879 | Deliver Overview Training Post Tool Configuration | June 20, 2024 8:00 AM | July 3, 2024 5:00 PM | 5069FS+145d | 5071 | As Soon As Possible | NA | 10 | 0d | June 20, 2024 8:00 AM | July 3, 2024 5:00 PM | 10 days | No | 6/20/24 | 7/3/24 | NA | 1
9880 | Configure Change Tool Completed | July 3, 2024 5:00 PM | July 3, 2024 5:00 PM | 5070 | 3456 | As Soon As Possible | NA | 0 | 0d | July 3, 2024 5:00 PM | July 3, 2024 5:00 PM | 0 days | Yes | 7/3/24 | 7/3/24 | NA | 1
9881 | Visioning Session | November 2, 2022 8:00 AM | June 23, 2023 5:00 PM |  |  | As Soon As Possible | NA | 159 | 0d | November 2, 2022 8:00 AM | June 23, 2023 5:00 PM | 159 days | No | 11/2/22 | 6/23/23 | NA | 1
9882 | Identify participants | November 2, 2022 8:00 AM | November 16, 2022 5:00 PM | 3192SS+108d | 5074SS | As Soon As Possible | NA | 10 | 0d | November 2, 2022 8:00 AM | November 16, 2022 5:00 PM | 10 days | No | 11/2/22 | 11/16/22 | NA | 1
9883 | Schedule Session | November 2, 2022 8:00 AM | January 20, 2023 5:00 PM | 5073SS | 5075FS+35d,5077SS | As Soon As Possible | NA | 52 | 0d | November 2, 2022 8:00 AM | January 20, 2023 5:00 PM | 52 days | No | 11/2/22 | 1/20/23 | NA | 1
9884 | Complete Pre-Work & Survey | March 14, 2023 8:00 AM | March 21, 2023 5:00 PM | 5074FS+35d | 5078,5076 | As Soon As Possible | NA | 6 | 0d | March 14, 2023 8:00 AM | March 21, 2023 5:00 PM | 6 days | No | 3/14/23 | 3/21/23 | NA | 1
9885 | Review Session survey | March 22, 2023 8:00 AM | March 28, 2023 5:00 PM | 5075 | 5079 | As Soon As Possible | NA | 5 | 0d | March 22, 2023 8:00 AM | March 28, 2023 5:00 PM | 5 days | No | 3/22/23 | 3/28/23 | NA | 1
9886 | Develop materials for Session | November 2, 2022 8:00 AM | February 24, 2023 5:00 PM | 5074SS | 5078FS+44d | As Soon As Possible | NA | 76 | 0d | November 2, 2022 8:00 AM | February 24, 2023 5:00 PM | 76 days | No | 11/2/22 | 2/24/23 | NA | 1
9887 | Conduct Visioning Session | May 1, 2023 8:00 AM | May 1, 2023 5:00 PM | 5075,5077FS+44d | 5079 | As Soon As Possible | NA | 1 | 0d | May 1, 2023 8:00 AM | May 1, 2023 5:00 PM | 1 | No | 5/1/23 | 5/1/23 | NA | 1
9888 | Create Summary Report & Consolidate Leadership Action Plans (LAPs) | May 2, 2023 8:00 AM | May 12, 2023 5:00 PM | 5078,5076 | 5080,5081 | As Soon As Possible | NA | 9 | 0d | May 2, 2023 8:00 AM | May 12, 2023 5:00 PM | 9 days | No | 5/2/23 | 5/12/23 | NA | 1
9889 | Review Visioning Session Summary Report with State Leaders | May 15, 2023 8:00 AM | May 19, 2023 5:00 PM | 5079 | 5081SS | As Soon As Possible | NA | 5 | 0d | May 15, 2023 8:00 AM | May 19, 2023 5:00 PM | 5 days | No | 5/15/23 | 5/19/23 | NA | 1
9890 | Create Commitments and Connections Matrix Documents | May 15, 2023 8:00 AM | June 2, 2023 5:00 PM | 5079,5080SS | 5082FS+3d | As Soon As Possible | NA | 14 | 0d | May 15, 2023 8:00 AM | June 2, 2023 5:00 PM | 14 days | No | 5/15/23 | 6/2/23 | NA | 1
9891 | Review Commitments and Connections Matrix Documents with State leadership | June 8, 2023 8:00 AM | June 14, 2023 5:00 PM | 5081FS+3d | 5083FS+5d | As Soon As Possible | NA | 5 | 0d | June 8, 2023 8:00 AM | June 14, 2023 5:00 PM | 5 days | No | 6/8/23 | 6/14/23 | NA | 1
9892 | Present OCM Visioning Session to BOD | June 22, 2023 8:00 AM | June 22, 2023 5:00 PM | 5082FS+5d | 5084 | As Soon As Possible | NA | 1 | 0d | June 22, 2023 8:00 AM | June 22, 2023 5:00 PM | 1 | No | 6/22/23 | 6/22/23 | NA | 1
9893 | Distribute Commitments and Connections Matrix Documents | June 23, 2023 8:00 AM | June 23, 2023 5:00 PM | 5083 | 5085 | As Soon As Possible | NA | 1 | 0d | June 23, 2023 8:00 AM | June 23, 2023 5:00 PM | 1 | No | 6/23/23 | 6/23/23 | NA | 1
9894 | Visioning Session Completed | June 23, 2023 5:00 PM | June 23, 2023 5:00 PM | 5084 | 5087 | As Soon As Possible | NA | 0 | 0d | June 23, 2023 5:00 PM | June 23, 2023 5:00 PM | 0 days | Yes | 6/23/23 | 6/23/23 | NA | 1
9895 | OCM Visioning Session Follow-Up | August 11, 2023 8:00 AM | September 20, 2024 5:00 PM |  |  | As Soon As Possible | NA | 280 | 0d | August 11, 2023 8:00 AM | August 6, 2024 5:00 PM | 247 days | No | 8/11/23 | 9/20/24 | NA | 1
9896 | Draft and review Visioning Session Follow Up Focus Groups Approach with ELT | August 11, 2023 8:00 AM | September 29, 2023 5:00 PM | 5085 | 5088,5089FS+22d | As Soon As Possible | NA | 35 | 0d | August 11, 2023 8:00 AM | September 29, 2023 5:00 PM | 35 days | No | 8/11/23 | 9/29/23 | NA | 1
9897 | Schedule and deliver Visioning Session Follow Up Focus Groups | October 2, 2023 8:00 AM | February 8, 2024 5:00 PM | 5087 | 5091 | As Soon As Possible | NA | 88 | 0d | October 2, 2023 8:00 AM | February 8, 2024 5:00 PM | 88 days | No | 10/2/23 | 2/8/24 | NA | 1
9898 | Gather vision insights: Implementation Organizations | November 1, 2023 8:00 AM | February 8, 2024 5:00 PM | 5087FS+22d | 5090SS+43d | As Soon As Possible | NA | 66 | 0d | November 1, 2023 8:00 AM | February 8, 2024 5:00 PM | 66 days | No | 11/1/23 | 2/8/24 | NA | 1
9899 | Develop Report-Out of findings from Implementing Organizations and review with State Leadership | January 8, 2024 8:00 AM | February 23, 2024 5:00 PM | 5089SS+43d | 5091FS+7d | As Soon As Possible | NA | 33 | 0d | January 8, 2024 8:00 AM | February 23, 2024 5:00 PM | 33 days | No | 1/8/24 | 2/23/24 | NA | 1
9900 | Incorporate State Leadership Feedback for Focus Group Summary Report | March 6, 2024 8:00 AM | March 19, 2024 5:00 PM | 5090FS+7d,5088 | 5092 | As Soon As Possible | NA | 10 | 0d | March 6, 2024 8:00 AM | March 19, 2024 5:00 PM | 10 days | No | 3/6/24 | 3/19/24 | NA | 1
9901 | Complete Leadership Walkthroughs and Distribute Focus Group Summary Report to Participants (of the Focus Group) | March 20, 2024 8:00 AM | April 19, 2024 5:00 PM | 5091 | 5093 | As Soon As Possible | NA | 22 | 0d | March 20, 2024 8:00 AM | April 19, 2024 5:00 PM | 22 days | No | 3/20/24 | 4/19/24 | NA | 1
9902 | Develop Approach to support the development of one OCM vision statement | April 11, 2024 8:00 AM | June 17, 2024 5:00 PM | 5092 | 5094 | As Soon As Possible | NA | 47 | 0d | April 11, 2024 8:00 AM | June 17, 2024 5:00 PM | 47 days | No | 4/11/24 | 6/17/24 | NA | 1
11020 | Complete Review of the OCM Vision Statement Approach and Incorporate Feedback | June 18, 2024 8:00 AM | July 9, 2024 5:00 PM | 5093 | 5095FS+14d | As Soon As Possible | NA | 15 | 0d | June 18, 2024 8:00 AM | July 9, 2024 5:00 PM | 15 days | No | 6/18/24 | 7/9/24 | NA | 1
12201 | Seek approval on layout of OCM Vision Statement strategy session (inputs include: acceptance on format and length of session, participants, and activities). | July 30, 2024 8:00 AM | August 30, 2024 5:00 PM | 5094FS+14d | 5096FS+5d | As Soon As Possible | NA | 24 | 0d | NA | NA | 0 days? | No | 7/30/24 | 8/30/24 | NA | 1
12202 | Review session presentation with Vendor Imp Manager | September 9, 2024 8:00 AM | September 20, 2024 5:00 PM | 5095FS+5d | 5097 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/9/24 | 9/20/24 | NA | 1
9904 | Visioning Session Follow-up Completed | September 20, 2024 5:00 PM | September 20, 2024 5:00 PM | 5096 | 5621 | As Soon As Possible | NA | 0 | 0d | August 6, 2024 5:00 PM | August 6, 2024 5:00 PM | 0 days | Yes | 9/20/24 | 9/20/24 | NA | 1
9905 | Refine Stakeholder Analysis | November 21, 2022 8:00 AM | July 14, 2023 5:00 PM |  |  | As Soon As Possible | NA | 161 | 0d | November 21, 2022 8:00 AM | July 14, 2023 5:00 PM | 161 days | No | 11/21/22 | 7/14/23 | NA | 1
9906 | Review Stakeholder Analysis from WOA 9 | November 21, 2022 8:00 AM | December 15, 2022 5:00 PM | 3192SS+120d | 5100FS-9d | As Soon As Possible | NA | 17 | 0d | November 21, 2022 8:00 AM | December 15, 2022 5:00 PM | 17 days | No | 11/21/22 | 12/15/22 | NA | 1
9907 | Identify gaps (additional personas) that may need to be created | December 5, 2022 8:00 AM | January 24, 2023 5:00 PM | 5099FS-9d | 5101FS+10d | As Soon As Possible | NA | 34 | 0d | December 5, 2022 8:00 AM | January 24, 2023 5:00 PM | 34 days | No | 12/5/22 | 1/24/23 | NA | 1
9908 | Review with County Consultants and SMEs | February 8, 2023 8:00 AM | February 14, 2023 5:00 PM | 5100FS+10d | 5102 | As Soon As Possible | NA | 5 | 0d | February 8, 2023 8:00 AM | February 14, 2023 5:00 PM | 5 days | No | 2/8/23 | 2/14/23 | NA | 1
9909 | Update Stakeholder Analysis as needed | February 13, 2023 8:00 AM | March 1, 2023 5:00 PM | 5101 | 5104,5103FS+51d | As Soon As Possible | NA | 12 | 0d | February 13, 2023 8:00 AM | March 1, 2023 5:00 PM | 12 days | No | 2/13/23 | 3/1/23 | NA | 1
9910 | Update Additional Users List and Refine Stakeholder Analysis for WOA 12 | May 15, 2023 8:00 AM | July 14, 2023 5:00 PM | 5102FS+51d | 5104 | As Soon As Possible | NA | 43 | 0d | May 15, 2023 8:00 AM | July 14, 2023 5:00 PM | 43 days | No | 5/15/23 | 7/14/23 | NA | 1
9911 | Refine Stakeholder Analysis Completed | July 14, 2023 5:00 PM | July 14, 2023 5:00 PM | 5102,5103 | 5106 | As Soon As Possible | NA | 0 | 0d | July 14, 2023 5:00 PM | July 14, 2023 5:00 PM | 0 days | Yes | 7/14/23 | 7/14/23 | NA | 1
9912 | Establish OCM Advisory Workgroup | May 2, 2023 8:00 AM | October 18, 2023 5:00 PM |  |  | As Soon As Possible | NA | 119 | 0d | May 2, 2023 8:00 AM | October 18, 2023 5:00 PM | 119 days | No | 5/2/23 | 10/18/23 | NA | 1
9918 | Develop and Review materials for kickoff meeting | September 1, 2023 8:00 AM | October 11, 2023 5:00 PM | 5113FS-15d,5104 | 5114 | As Soon As Possible | NA | 28 | 0d | September 1, 2023 8:00 AM | October 11, 2023 5:00 PM | 28 days | No | 9/1/23 | 10/11/23 | NA | 1
9919 | Develop OCM Advisory Committee Charter | May 2, 2023 8:00 AM | May 15, 2023 5:00 PM | 3192 | 5108 | As Soon As Possible | NA | 10 | 0d | May 2, 2023 8:00 AM | May 15, 2023 5:00 PM | 10 days | No | 5/2/23 | 5/15/23 | NA | 1
9920 | Review OCM Advisory Committee Charter with internal OCM Team | May 16, 2023 8:00 AM | May 22, 2023 5:00 PM | 5107 | 5109FS+4d | As Soon As Possible | NA | 5 | 0d | May 16, 2023 8:00 AM | May 22, 2023 5:00 PM | 5 days | No | 5/16/23 | 5/22/23 | NA | 1
9921 | Review OCM Advisory Workgroup Charter with State Implementation Leads | May 30, 2023 8:00 AM | June 5, 2023 5:00 PM | 5108FS+4d | 5110FS+4d | As Soon As Possible | NA | 5 | 0d | May 30, 2023 8:00 AM | June 5, 2023 5:00 PM | 5 days | No | 5/30/23 | 6/5/23 | NA | 1
9922 | Review OCM Advisory Workgroup Charter with ELT and seek approval | June 12, 2023 8:00 AM | July 10, 2023 5:00 PM | 5109FS+4d | 5111 | As Soon As Possible | NA | 20 | 0d | June 12, 2023 8:00 AM | July 10, 2023 5:00 PM | 20 days | No | 6/12/23 | 7/10/23 | NA | 1
9923 | Begin collaboration with the regions to identify potential OCM Advisory Workgroup participants | July 11, 2023 8:00 AM | September 15, 2023 5:00 PM | 5110 | 5112 | As Soon As Possible | NA | 48 | 0d | July 11, 2023 8:00 AM | September 15, 2023 5:00 PM | 48 days | No | 7/11/23 | 9/15/23 | NA | 1
9924 | Seek Approval from ELT on Workgroup Participants List | September 18, 2023 8:00 AM | October 2, 2023 5:00 PM | 5111 | 5113FF | As Soon As Possible | NA | 11 | 0d | September 18, 2023 8:00 AM | October 2, 2023 5:00 PM | 11 days | No | 9/18/23 | 10/2/23 | NA | 1
9925 | Schedule OCM Advisory Workgroup kick-off Meeting | September 19, 2023 8:00 AM | October 2, 2023 5:00 PM | 5112FF | 5106FS-15d,5114FS+11d | As Soon As Possible | NA | 10 | 0d | September 19, 2023 8:00 AM | October 2, 2023 5:00 PM | 10 days | No | 9/19/23 | 10/2/23 | NA | 1
9926 | Conduct OCM Advisory Workgroup Kickoff Meeting | October 18, 2023 8:00 AM | October 18, 2023 5:00 PM | 5113FS+11d,5106 | 5115 | As Soon As Possible | NA | 1 | 0d | October 18, 2023 8:00 AM | October 18, 2023 5:00 PM | 1 | No | 10/18/23 | 10/18/23 | NA | 1
9927 | Establish OCM Advisory Workgroup Completed | October 18, 2023 5:00 PM | October 18, 2023 5:00 PM | 5114 | 5222FS+9d | As Soon As Possible | NA | 0 | 0d | October 18, 2023 5:00 PM | October 18, 2023 5:00 PM | 0 days | Yes | 10/18/23 | 10/18/23 | NA | 1
9939 | Conduct CWS-CARES OCM Engagement Survey #1 | November 27, 2023 8:00 AM | November 7, 2024 5:00 PM |  |  | As Soon As Possible | NA | 242 | 0d | November 27, 2023 8:00 AM | October 25, 2024 5:00 PM | 233 days | No | 11/27/23 | 11/7/24 | NA | 1
9940 | Develop Survey Approach | November 27, 2023 8:00 AM | December 11, 2023 5:00 PM | 3491FS+6d | 5118 | As Soon As Possible | NA | 11 | 0d | November 27, 2023 8:00 AM | December 11, 2023 5:00 PM | 11 days | No | 11/27/23 | 12/11/23 | NA | 1
9941 | Create Likert-scale survey questions | December 12, 2023 8:00 AM | February 16, 2024 5:00 PM | 5117 | 5119 | As Soon As Possible | NA | 46 | 0d | December 12, 2023 8:00 AM | February 16, 2024 5:00 PM | 46 days | No | 12/12/23 | 2/16/24 | NA | 1
9942 | Select survey tool | February 20, 2024 8:00 AM | February 22, 2024 5:00 PM | 5118 | 5120FS+93d | As Soon As Possible | NA | 3 | 0d | February 20, 2024 8:00 AM | February 22, 2024 5:00 PM | 3 days | No | 2/20/24 | 2/22/24 | NA | 1
9943 | Develop and Update communications about Survey to Orgs based on revise approach | July 8, 2024 8:00 AM | August 20, 2024 5:00 PM | 5119FS+93d | 5121FS+9d | As Soon As Possible | NA | 32 | 0d | July 8, 2024 8:00 AM | August 20, 2024 5:00 PM | 32 days | No | 7/8/24 | 8/20/24 | NA | 1
9944 | Launch CWS-CARES OCM Engagement Survey | September 3, 2024 8:00 AM | September 3, 2024 5:00 PM | 5120FS+9d | 5122SS | As Soon As Possible | NA | 1 | 0d | August 27, 2024 8:00 AM | August 27, 2024 5:00 PM | 1 | No | 9/3/24 | 9/3/24 | NA | 1
9945 | Survey window (Gather Feedback, Complete Preliminary Analysis, Send Reminders) | September 3, 2024 8:00 AM | September 30, 2024 5:00 PM | 5121SS | 5123FF | As Soon As Possible | NA | 20 | 0d | August 27, 2024 8:00 AM | September 16, 2024 5:00 PM | 15 days | No | 9/3/24 | 9/30/24 | NA | 1
9946 | Close survey | September 30, 2024 8:00 AM | September 30, 2024 5:00 PM | 5122FF | 5124SS | As Soon As Possible | NA | 1 | 0d | September 17, 2024 8:00 AM | September 17, 2024 5:00 PM | 1 | No | 9/30/24 | 9/30/24 | NA | 1
9947 | Analyze survey results | September 30, 2024 8:00 AM | October 10, 2024 5:00 PM | 5123SS | 5125 | As Soon As Possible | NA | 9 | 0d | September 17, 2024 8:00 AM | September 27, 2024 5:00 PM | 9 days | No | 9/30/24 | 10/10/24 | NA | 1
9948 | Create CWS-CARES OCM Engagement Survey Report | October 11, 2024 8:00 AM | November 7, 2024 5:00 PM | 5124 | 5217,5127FS+122d | As Soon As Possible | NA | 20 | 0d | September 30, 2024 8:00 AM | October 25, 2024 5:00 PM | 20 days | No | 10/11/24 | 11/7/24 | NA | 1
12603 | Conduct CWS-CARES OCM Engagement Survey #2 | May 9, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 5/9/25 | 8/8/25 | NA | 1
12604 | Review and Finalize the Survey Approach | May 9, 2025 8:00 AM | May 30, 2025 5:00 PM | 5125FS+122d | 5128 | As Soon As Possible | NA | 15 | 0d | NA | NA | 0 days? | No | 5/9/25 | 5/30/25 | NA | 1
12605 | Launch CWS-CARES OCM Engagement Survey | June 2, 2025 8:00 AM | June 2, 2025 5:00 PM | 5127 | 5129SS | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/2/25 | 6/2/25 | NA | 1
12606 | Survey window (Gather Feedback, Complete Preliminary Analysis, Send Reminders) | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 5128SS | 5130FF | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
12607 | Close survey | June 30, 2025 8:00 AM | June 30, 2025 5:00 PM | 5129FF | 5131SS | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 6/30/25 | 6/30/25 | NA | 1
12608 | Analyze survey results | June 30, 2025 8:00 AM | July 11, 2025 5:00 PM | 5130SS | 5132 | As Soon As Possible | NA | 9 | 0d | NA | NA | 0 days? | No | 6/30/25 | 7/11/25 | NA | 1
12609 | Create CWS-CARES OCM Engagement Survey Report | July 14, 2025 8:00 AM | August 8, 2025 5:00 PM | 5131 | 5134FS+84d | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 7/14/25 | 8/8/25 | NA | 1
12610 | Conduct CWS-CARES OCM Engagement Survey #3 | December 10, 2025 8:00 AM | March 12, 2026 5:00 PM |  |  | As Soon As Possible | NA | 63 | 32d | NA | NA | 0 days? | No | NA | NA | NA | 0
12611 | Review and Finalize the Survey Approach | December 10, 2025 8:00 AM | December 31, 2025 5:00 PM | 5132FS+84d | 5135 | As Soon As Possible | NA | 15 | 32d | NA | NA | 0 days? | No | NA | NA | NA | 0
12612 | Launch CWS-CARES OCM Engagement Survey | January 2, 2026 8:00 AM | January 2, 2026 5:00 PM | 5134 | 5136SS | As Soon As Possible | NA | 1 | 32d | NA | NA | 0 s? | No | NA | NA | NA | 0
12613 | Survey window (Gather Feedback, Complete Preliminary Analysis, Send Reminders) | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 5135SS | 5137FF | As Soon As Possible | NA | 20 | 32d | NA | NA | 0 days? | No | NA | NA | NA | 0
12614 | Close survey | January 30, 2026 8:00 AM | January 30, 2026 5:00 PM | 5136FF | 5138SS | As Soon As Possible | NA | 1 | 32d | NA | NA | 0 s? | No | NA | NA | NA | 0
12615 | Analyze survey results | January 30, 2026 8:00 AM | February 11, 2026 5:00 PM | 5137SS | 5139 | As Soon As Possible | NA | 9 | 32d | NA | NA | 0 days? | No | NA | NA | NA | 0
12616 | Create CWS-CARES OCM Engagement Survey Report | February 12, 2026 8:00 AM | March 12, 2026 5:00 PM | 5138 | 5141FS+61d | As Soon As Possible | NA | 20 | 32d | NA | NA | 0 days? | No | NA | NA | NA | 0
12617 | Conduct CWS-CARES OCM Engagement Survey #4 | June 10, 2026 8:00 AM | September 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 65 | 32d | NA | NA | 0 days? | No | NA | NA | NA | 0
12618 | Review and Finalize the Survey Approach | June 10, 2026 8:00 AM | June 30, 2026 5:00 PM | 5139FS+61d | 5142 | As Soon As Possible | NA | 15 | 32d | NA | NA | 0 days? | No | NA | NA | NA | 0
12619 | Launch CWS-CARES OCM Engagement Survey | July 1, 2026 8:00 AM | July 1, 2026 5:00 PM | 5141 | 5143SS | As Soon As Possible | NA | 1 | 32d | NA | NA | 0 s? | No | NA | NA | NA | 0
12620 | Survey window (Gather Feedback, Complete Preliminary Analysis, Send Reminders) | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 5142SS | 5144FF | As Soon As Possible | NA | 22 | 32d | NA | NA | 0 days? | No | NA | NA | NA | 0
12621 | Close survey | July 31, 2026 8:00 AM | July 31, 2026 5:00 PM | 5143FF | 5145SS | As Soon As Possible | NA | 1 | 32d | NA | NA | 0 s? | No | NA | NA | NA | 0
12622 | Analyze survey results | July 31, 2026 8:00 AM | August 12, 2026 5:00 PM | 5144SS | 5146 | As Soon As Possible | NA | 9 | 32d | NA | NA | 0 days? | No | NA | NA | NA | 0
12623 | Create CWS-CARES OCM Engagement Survey Report | August 13, 2026 8:00 AM | September 10, 2026 5:00 PM | 5145 | 5630 | As Soon As Possible | NA | 20 | 32d | NA | NA | 0 days? | No | NA | NA | NA | 0
9949 | OCM Training | August 30, 2023 8:00 AM | May 15, 2024 5:00 PM |  |  | As Soon As Possible | NA | 177 | 0d | August 30, 2023 8:00 AM | May 15, 2024 5:00 PM | 177 days | No | 8/30/23 | 5/15/24 | NA | 1
9950 | Create Approach and Plan for OCM Training Curriculum for Orgs | August 30, 2023 8:00 AM | November 9, 2023 5:00 PM | 3491FS-44d | 5150,5149 | As Soon As Possible | NA | 51 | 0d | August 30, 2023 8:00 AM | November 9, 2023 5:00 PM | 51 days | No | 8/30/23 | 11/9/23 | NA | 1
9951 | Review Approach and Plan of OCM Training Curriculum | November 13, 2023 8:00 AM | January 26, 2024 5:00 PM | 5148 | 5155 | As Soon As Possible | NA | 50 | 0d | November 13, 2023 8:00 AM | January 26, 2024 5:00 PM | 50 days | No | 11/13/23 | 1/26/24 | NA | 1
9952 | Create OCM training curriculum for Orgs | November 17, 2023 8:00 AM | December 11, 2023 5:00 PM | 3491FS+2d,5148 | 5151 | As Soon As Possible | NA | 15 | 0d | November 17, 2023 8:00 AM | December 11, 2023 5:00 PM | 15 days | No | 11/17/23 | 12/11/23 | NA | 1
9953 | Develop OCM training course objectives | December 12, 2023 8:00 AM | December 18, 2023 5:00 PM | 5150 | 5152 | As Soon As Possible | NA | 5 | 0d | December 12, 2023 8:00 AM | December 18, 2023 5:00 PM | 5 days | No | 12/12/23 | 12/18/23 | NA | 1
9954 | Create and Review first draft of OCM training course materials | December 19, 2023 8:00 AM | March 1, 2024 5:00 PM | 5151 | 5153FS-1d | As Soon As Possible | NA | 50 | 0d | December 19, 2023 8:00 AM | March 1, 2024 5:00 PM | 50 days | No | 12/19/23 | 3/1/24 | NA | 1
9955 | Schedule virtual OCM training course sessions for Orgs | March 1, 2024 8:00 AM | March 1, 2024 5:00 PM | 5152FS-1d | 5154 | As Soon As Possible | NA | 1 | 0d | March 1, 2024 8:00 AM | March 1, 2024 5:00 PM | 1 | No | 3/1/24 | 3/1/24 | NA | 1
9956 | Finalize OCM training course materials | March 4, 2024 8:00 AM | March 12, 2024 5:00 PM | 5153 | 5155FS-1d | As Soon As Possible | NA | 7 | 0d | March 4, 2024 8:00 AM | March 12, 2024 5:00 PM | 7 days | No | 3/4/24 | 3/12/24 | NA | 1
9957 | OCM Training: Deliver virtual OCM Training Courses | March 12, 2024 8:00 AM | May 15, 2024 5:00 PM | 5154FS-1d,5149 | 5621 | As Soon As Possible | NA | 46 | 0d | March 12, 2024 8:00 AM | May 15, 2024 5:00 PM | 46 days | No | 3/12/24 | 5/15/24 | NA | 1
9958 | Define Phase | December 7, 2022 8:00 AM | October 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 974 | 239d | December 7, 2022 8:00 AM | November 25, 2024 5:00 PM | 495 days | No | 12/7/22 | NA | NA | 0.76000000000000001
9959 | Implementation Communications Plan V1 | December 7, 2022 8:00 AM | July 21, 2023 5:00 PM |  |  | As Soon As Possible | NA | 156 | 0d | December 7, 2022 8:00 AM | July 21, 2023 5:00 PM | 156 days | No | 12/7/22 | 7/21/23 | NA | 1
9960 | Create outline of Communications Plan | December 7, 2022 8:00 AM | December 13, 2022 5:00 PM | 3192SS+130d | 5159 | As Soon As Possible | NA | 5 | 0d | December 7, 2022 8:00 AM | December 13, 2022 5:00 PM | 5 days | No | 12/7/22 | 12/13/22 | NA | 1
9961 | Create first draft of Communications Plan | December 14, 2022 8:00 AM | December 23, 2022 5:00 PM | 5158 | 5160FS+9d | As Soon As Possible | NA | 8 | 0d | December 14, 2022 8:00 AM | December 23, 2022 5:00 PM | 8 days | No | 12/14/22 | 12/23/22 | NA | 1
9962 | Create final draft of Communications Plan | January 3, 2023 8:00 AM | January 24, 2023 5:00 PM | 5159FS+9d | 5161FS+86d | As Soon As Possible | NA | 15 | 0d | January 3, 2023 8:00 AM | January 24, 2023 5:00 PM | 15 days | No | 1/3/23 | 1/24/23 | NA | 1
9963 | Review Communication Plan with State Leadership | May 30, 2023 8:00 AM | June 2, 2023 5:00 PM | 5160FS+86d | 5162FS-1d | As Soon As Possible | NA | 4 | 0d | May 30, 2023 8:00 AM | June 2, 2023 5:00 PM | 4 days | No | 5/30/23 | 6/2/23 | NA | 1
9964 | Incorporate feedback from State Leadership Reviews and Complete Walkthroughs | June 2, 2023 8:00 AM | June 8, 2023 5:00 PM | 5161FS-1d | 5163FS+3d | As Soon As Possible | NA | 5 | 0d | June 2, 2023 8:00 AM | June 8, 2023 5:00 PM | 5 days | No | 6/2/23 | 6/8/23 | NA | 1
9965 | Review with County Consultants and Engagement and Adoption Team | June 14, 2023 8:00 AM | June 30, 2023 5:00 PM | 5162FS+3d | 5164FS+7d | As Soon As Possible | NA | 13 | 0d | June 14, 2023 8:00 AM | June 30, 2023 5:00 PM | 13 days | No | 6/14/23 | 6/30/23 | NA | 1
9967 | Share Communications Plan with Oversight Teams and Incorporate Feedback | July 13, 2023 8:00 AM | July 20, 2023 5:00 PM | 5163FS+7d | 5165 | As Soon As Possible | NA | 6 | 0d | July 13, 2023 8:00 AM | July 20, 2023 5:00 PM | 6 days | No | 7/13/23 | 7/20/23 | NA | 1
9971 | Incorporate reviewer feedback into Communications Plan | July 21, 2023 8:00 AM | July 21, 2023 5:00 PM | 5164 | 5166 | As Soon As Possible | NA | 1 | 0d | July 21, 2023 8:00 AM | July 21, 2023 5:00 PM | 1 | No | 7/21/23 | 7/21/23 | NA | 1
9972 | Finalize Communications Plan | July 21, 2023 5:00 PM | July 21, 2023 5:00 PM | 5165 | 5279FS+25d,5169FS+152d | As Soon As Possible | NA | 0 | 0d | July 21, 2023 5:00 PM | July 21, 2023 5:00 PM | 0 days | Yes | 7/21/23 | 7/21/23 | NA | 1
9973 | Implementation Communications Plan Version 2 | March 4, 2024 8:00 AM | August 16, 2024 5:00 PM |  |  | As Soon As Possible | NA | 117 | 0d | March 4, 2024 8:00 AM | August 7, 2024 5:00 PM | 110 days | No | 3/4/24 | 8/16/24 | NA | 1
9974 | Review and analyze existing Implementation Communications Plan | March 4, 2024 8:00 AM | March 22, 2024 5:00 PM |  |  | As Soon As Possible | NA | 15 | 0d | March 4, 2024 8:00 AM | March 22, 2024 5:00 PM | 15 days | No | 3/4/24 | 3/22/24 | NA | 1
9975 | Review existing Implementation Communications Plan and create tracker to capture notes and review other examples of communications plans, review lessons learned, and conduct visioning session with Michelle to align on updated Implementation Communication | March 4, 2024 8:00 AM | March 22, 2024 5:00 PM | 5166FS+152d | 5171 | As Soon As Possible | NA | 15 | 0d | March 4, 2024 8:00 AM | March 22, 2024 5:00 PM | 15 days | No | 3/4/24 | 3/22/24 | NA | 1
9978 | Develop initial draft of updated Implementation Communications Plan | March 25, 2024 8:00 AM | May 17, 2024 5:00 PM |  |  | As Soon As Possible | NA | 39 | 0d | March 25, 2024 8:00 AM | May 17, 2024 5:00 PM | 39 days | No | 3/25/24 | 5/17/24 | NA | 1
9979 | Develop outline | March 25, 2024 8:00 AM | April 5, 2024 5:00 PM | 5169 | 5172FS+5d | As Soon As Possible | NA | 9 | 0d | March 25, 2024 8:00 AM | April 5, 2024 5:00 PM | 9 days | No | 3/25/24 | 4/5/24 | NA | 1
9980 | Review outline with State Leadership and Strategic Communications Team (parallel reviews) | April 15, 2024 8:00 AM | April 19, 2024 5:00 PM | 5171FS+5d | 5173 | As Soon As Possible | NA | 5 | 0d | April 15, 2024 8:00 AM | April 19, 2024 5:00 PM | 5 days | No | 4/15/24 | 4/19/24 | NA | 1
9981 | Build content based on updated outline | April 22, 2024 8:00 AM | May 3, 2024 5:00 PM | 5172 | 5174FS+5d | As Soon As Possible | NA | 10 | 0d | April 22, 2024 8:00 AM | May 3, 2024 5:00 PM | 10 days | No | 4/22/24 | 5/3/24 | NA | 1
9982 | Complete initial draft of the Tracker with Proposed Updates and complete internal reviews and Implementation Management Team Reviews | May 13, 2024 8:00 AM | May 17, 2024 5:00 PM | 5173FS+5d | 5176FF | As Soon As Possible | NA | 5 | 0d | May 13, 2024 8:00 AM | May 17, 2024 5:00 PM | 5 days | No | 5/13/24 | 5/17/24 | NA | 1
9983 | Develop draft of updated Implementation Communications Plan for State team review (CARES RACI) | May 13, 2024 8:00 AM | August 16, 2024 5:00 PM |  |  | As Soon As Possible | NA | 68 | 0d | May 13, 2024 8:00 AM | August 7, 2024 5:00 PM | 61 days | No | 5/13/24 | 8/16/24 | NA | 1
9984 | Refine content based on internal reviews | May 13, 2024 8:00 AM | May 17, 2024 5:00 PM | 5174FF | 5177 | As Soon As Possible | NA | 5 | 0d | May 13, 2024 8:00 AM | May 17, 2024 5:00 PM | 5 days | No | 5/13/24 | 5/17/24 | NA | 1
9985 | Create comment matrix and document feedback on the updated Implementation Communications Plan | May 20, 2024 8:00 AM | May 24, 2024 5:00 PM | 5176 | 5178 | As Soon As Possible | NA | 5 | 0d | May 20, 2024 8:00 AM | May 24, 2024 5:00 PM | 5 days | No | 5/20/24 | 5/24/24 | NA | 1
9986 | Conduct reviews of content with Deloitte and State Implementation Leads | May 28, 2024 8:00 AM | June 19, 2024 5:00 PM | 5177 | 5179 | As Soon As Possible | NA | 17 | 0d | May 28, 2024 8:00 AM | June 19, 2024 5:00 PM | 17 days | No | 5/28/24 | 6/19/24 | NA | 1
9987 | Complete reviews with Service Managers and County Consultants and Engagement & Adoption Team | June 20, 2024 8:00 AM | July 10, 2024 5:00 PM | 5178 | 5180 | As Soon As Possible | NA | 14 | 0d | June 20, 2024 8:00 AM | June 26, 2024 5:00 PM | 5 days | No | 6/20/24 | 7/10/24 | NA | 1
9988 | Incorporate feedback from reviewers | July 11, 2024 8:00 AM | July 17, 2024 5:00 PM | 5179 | 5181 | As Soon As Possible | NA | 5 | 0d | June 27, 2024 8:00 AM | July 3, 2024 5:00 PM | 5 days | No | 7/11/24 | 7/17/24 | NA | 1
9989 | Review updated Implementation Communications Plan with PaaS SI Team, IV&V Team, Project Directors, ELT and BOD | July 18, 2024 8:00 AM | July 24, 2024 5:00 PM | 5180 | 5182 | As Soon As Possible | NA | 5 | 0d | July 5, 2024 8:00 AM | July 11, 2024 5:00 PM | 5 days | No | 7/18/24 | 7/24/24 | NA | 1
9990 | Incorporate feedback from CARES reviewers | July 25, 2024 8:00 AM | August 6, 2024 5:00 PM | 5181 | 5183FS+1d | As Soon As Possible | NA | 9 | 0d | July 12, 2024 8:00 AM | July 24, 2024 5:00 PM | 9 days | No | 7/25/24 | 8/6/24 | NA | 1
9991 | State reviews updated Implementation Communications Plan with comments and provides signoff/approval | August 8, 2024 8:00 AM | August 16, 2024 5:00 PM | 5182FS+1d | 5217,5186FS+43d | As Soon As Possible | NA | 7 | 0d | July 25, 2024 8:00 AM | August 7, 2024 5:00 PM | 10 days | No | 8/8/24 | 8/16/24 | NA | 1
12631 | CWS-CARES Implementation Communications Plan Version 3 | October 17, 2024 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 71 | 0d | NA | NA | 0 days? | No | 10/17/24 | 1/31/25 | NA | 1
12632 | Develop tracker for Imp Comms Plan Review Version 3 | October 17, 2024 8:00 AM | November 14, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 10/17/24 | 11/14/24 | NA | 1
12633 | Review Imp Comms Plan v2 and identify areas to include for updates in the proposed tracker for Imp Comms Plan v3 | October 17, 2024 8:00 AM | October 23, 2024 5:00 PM | 5183FS+43d | 5187 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 10/17/24 | 10/23/24 | NA | 1
12634 | Develop tracker with proposed updates for Imp Comms Plan v3 | October 24, 2024 8:00 AM | October 30, 2024 5:00 PM | 5186 | 5188 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 10/24/24 | 10/30/24 | NA | 1
12635 | Complete internal review of tracker with proposed updates for Imp Comms Plan v3 | October 31, 2024 8:00 AM | November 6, 2024 5:00 PM | 5187 | 5189 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 10/31/24 | 11/6/24 | NA | 1
12636 | Complete State Leadership review of tracker with proposed updates for Imp Comms Plan v3 and seek approval to begin updated draft | November 7, 2024 8:00 AM | November 14, 2024 5:00 PM | 5188 | 5191 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 11/7/24 | 11/14/24 | NA | 1
12637 | Develop draft of Imp Comms Plan v3 for review (includes CARES RACI) | November 15, 2024 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 11/15/24 | 1/31/25 | NA | 1
12638 | Complete updates from the approved tracker for Imp Comms Plan v3 | November 15, 2024 8:00 AM | November 27, 2024 5:00 PM | 5189 | 5192 | As Soon As Possible | NA | 9 | 0d | NA | NA | 0 days? | No | 11/15/24 | 11/27/24 | NA | 1
12639 | Conduct reviews of Imp Comms Plan v3 with internal OCM Team and complete QA | December 2, 2024 8:00 AM | December 6, 2024 5:00 PM | 5191 | 5193 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/6/24 | NA | 1
12640 | Conduct reviews of Imp Comms Plan v3 with internal leadership, State OCM Lead, Implementation Delivery Owners, and Training Lead | December 9, 2024 8:00 AM | December 17, 2024 5:00 PM | 5192 | 5194 | As Soon As Possible | NA | 7 | 0d | NA | NA | 0 days? | No | 12/9/24 | 12/17/24 | NA | 1
12641 | Incorporate feedback from reviewers | December 18, 2024 8:00 AM | December 20, 2024 5:00 PM | 5193 | 5195FS+7d | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 12/18/24 | 12/20/24 | NA | 1
12642 | Conduct reviews of Imp Comms Plan v3 with State Implementation Management Team and incorporate feedback from reviewers | January 3, 2025 8:00 AM | January 9, 2025 5:00 PM | 5194FS+7d | 5196 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 1/3/25 | 1/9/25 | NA | 1
12643 | Conduct reviews of Imp Comms Plan v3 with RACI reviewers | January 10, 2025 8:00 AM | January 16, 2025 5:00 PM | 5195 | 5197 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 1/10/25 | 1/16/25 | NA | 1
12644 | Incorporate feedback from reviewers | January 17, 2025 8:00 AM | January 22, 2025 5:00 PM | 5196 | 5198 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 1/17/25 | 1/22/25 | NA | 1
12645 | Conduct ELT review of Imp Comms Plan v3 and incorporate feedback | January 23, 2025 8:00 AM | January 29, 2025 5:00 PM | 5197 | 5199 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 1/23/25 | 1/29/25 | NA | 1
12646 | State reviews Imp Comms Plan v3 with comments and provides signoff/approval | January 30, 2025 8:00 AM | January 31, 2025 5:00 PM | 5198 | 5202FS+60d | As Soon As Possible | NA | 2 | 0d | NA | NA | 0 days? | No | 1/30/25 | 1/31/25 | NA | 1
12647 | CWS-CARES Implementation Communications Plan Version 4 | April 30, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 107 | 0d | NA | NA | 0 days? | No | 4/30/25 | 9/30/25 | NA | 1
12648 | Develop tracker for Imp Comms Plan Review Version 4 | April 30, 2025 8:00 AM | May 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 4/30/25 | 5/28/25 | NA | 1
12649 | Review Imp Comms Plan v3 and identify areas to include for updates in the proposed tracker for Imp Comms Plan v4 | April 30, 2025 8:00 AM | May 6, 2025 5:00 PM | 5199FS+60d | 5203 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 4/30/25 | 5/6/25 | NA | 1
12650 | Develop tracker with proposed updates for Imp Comms Plan v4 | May 7, 2025 8:00 AM | May 13, 2025 5:00 PM | 5202 | 5204 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 5/7/25 | 5/13/25 | NA | 1
12651 | Complete internal review of tracker with proposed updates for Imp Comms Plan v4 | May 14, 2025 8:00 AM | May 20, 2025 5:00 PM | 5203 | 5205 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 5/14/25 | 5/20/25 | NA | 1
12652 | Complete State Leadership review of tracker with proposed updates for Imp Comms Plan v4 and seek approval to begin updated draft | May 21, 2025 8:00 AM | May 28, 2025 5:00 PM | 5204 | 5207 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 5/21/25 | 5/28/25 | NA | 1
12653 | Develop draft of Imp Comms Plan v4 for review (includes CARES RACI) | May 29, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 87 | 0d | NA | NA | 0 days? | No | 5/29/25 | 9/30/25 | NA | 1
12654 | Complete updates from the approved tracker for Imp Comms Plan v4 | May 29, 2025 8:00 AM | July 31, 2025 5:00 PM | 5205 | 5208FS+1d | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 5/29/25 | 7/31/25 | NA | 1
12655 | Conduct reviews of Imp Comms Plan v4 with internal OCM Team and complete QA | August 4, 2025 8:00 AM | August 8, 2025 5:00 PM | 5207FS+1d | 5209 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 8/4/25 | 8/8/25 | NA | 1
12656 | Conduct reviews of Imp Comms Plan v4 with internal leadership, State OCM Lead, Implementation Delivery Owners, and Training Lead | August 11, 2025 8:00 AM | August 19, 2025 5:00 PM | 5208 | 5210 | As Soon As Possible | NA | 7 | 0d | NA | NA | 0 days? | No | 8/11/25 | 8/19/25 | NA | 1
12657 | Incorporate feedback from reviewers | August 20, 2025 8:00 AM | August 22, 2025 5:00 PM | 5209 | 5211 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 8/20/25 | 8/22/25 | NA | 1
12658 | Conduct reviews of Imp Comms Plan v4 with State Implementation Management Team and incorporate feedback from reviewers | August 25, 2025 8:00 AM | August 29, 2025 5:00 PM | 5210 | 5212 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 8/25/25 | 8/29/25 | NA | 1
12659 | Conduct reviews of Imp Comms Plan v4 with RACI reviewers | September 2, 2025 8:00 AM | September 15, 2025 5:00 PM | 5211 | 5213 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/15/25 | NA | 1
12660 | Incorporate feedback from reviewers | September 16, 2025 8:00 AM | September 18, 2025 5:00 PM | 5212 | 5214 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 9/16/25 | 9/18/25 | NA | 1
12661 | Conduct ELT review of Imp Comms Plan v4 and incorporate feedback | September 19, 2025 8:00 AM | September 25, 2025 5:00 PM | 5213 | 5215 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 9/19/25 | 9/25/25 | NA | 1
12662 | State reviews Imp Comms Plan v4 with comments and provides signoff/approval | September 26, 2025 8:00 AM | September 30, 2025 5:00 PM | 5214 | 5630 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 9/26/25 | 9/30/25 | NA | 1
9992 | High Impact Org Strategy | November 8, 2024 8:00 AM | December 10, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | October 28, 2024 8:00 AM | November 25, 2024 5:00 PM | 20 days | No | 11/8/24 | 12/10/24 | NA | 1
9993 | Review results of OCM Engagement Survey #1 | November 8, 2024 8:00 AM | November 15, 2024 5:00 PM | 5125,5183 | 5218 | As Soon As Possible | NA | 5 | 0d | October 28, 2024 8:00 AM | November 1, 2024 5:00 PM | 5 days | No | 11/8/24 | 11/15/24 | NA | 1
9994 | Identify Orgs that will require Additional OCM Support | November 18, 2024 8:00 AM | November 22, 2024 5:00 PM | 5217 | 5219 | As Soon As Possible | NA | 5 | 0d | November 4, 2024 8:00 AM | November 8, 2024 5:00 PM | 5 days | No | 11/18/24 | 11/22/24 | NA | 1
9995 | Develop Presentation Materials with High Impact Org Support recommendations | November 25, 2024 8:00 AM | December 3, 2024 5:00 PM | 5218 | 5220 | As Soon As Possible | NA | 5 | 0d | November 12, 2024 8:00 AM | November 18, 2024 5:00 PM | 5 days | No | 11/25/24 | 12/3/24 | NA | 1
9996 | Present High Impact Org Strategy Recommendations to ELT | December 4, 2024 8:00 AM | December 10, 2024 5:00 PM | 5219 | 5621 | As Soon As Possible | NA | 5 | 0d | November 19, 2024 8:00 AM | November 25, 2024 5:00 PM | 5 days | No | 12/4/24 | 12/10/24 | NA | 1
9997 | OCM Advisory Workgroup Engagement | November 1, 2023 8:00 AM | October 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 747 | 239d | November 1, 2023 8:00 AM | October 30, 2024 5:00 PM | 251 days | No | 11/1/23 | NA | NA | 0.64000000000000001
9998 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 1 | November 1, 2023 8:00 AM | November 30, 2023 5:00 PM | 5115FS+9d | 5223 | As Soon As Possible | NA | 19 | 0d | November 1, 2023 8:00 AM | November 30, 2023 5:00 PM | 19 days | No | 11/1/23 | 11/30/23 | NA | 1
9999 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 2 | December 1, 2023 8:00 AM | December 13, 2023 5:00 PM | 5222 | 5224FS+11d | As Soon As Possible | NA | 9 | 0d | December 1, 2023 8:00 AM | December 13, 2023 5:00 PM | 9 days | No | 12/1/23 | 12/13/23 | NA | 1
10000 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 3 | January 2, 2024 8:00 AM | January 19, 2024 5:00 PM | 5223FS+11d | 5225FS+8d | As Soon As Possible | NA | 13 | 0d | January 2, 2024 8:00 AM | January 19, 2024 5:00 PM | 13 days | No | 1/2/24 | 1/19/24 | NA | 1
10001 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 4 | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM | 5224FS+8d | 5226 | As Soon As Possible | NA | 20 | 0d | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM | 20 days | No | 2/1/24 | 2/29/24 | NA | 1
10002 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 5 | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM | 5225 | 5227 | As Soon As Possible | NA | 21 | 0d | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM | 21 days | No | 3/1/24 | 3/29/24 | NA | 1
10003 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 6 | April 2, 2024 8:00 AM | April 30, 2024 5:00 PM | 5226 | 5228 | As Soon As Possible | NA | 21 | 0d | April 2, 2024 8:00 AM | April 30, 2024 5:00 PM | 21 days | No | 4/2/24 | 4/30/24 | NA | 1
10004 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 7 | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM | 5227 | 5229 | As Soon As Possible | NA | 22 | 0d | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM | 22 days | No | 5/1/24 | 5/31/24 | NA | 1
10005 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 8 | June 3, 2024 8:00 AM | June 28, 2024 5:00 PM | 5228 | 5230 | As Soon As Possible | NA | 20 | 0d | June 3, 2024 8:00 AM | June 28, 2024 5:00 PM | 20 days | No | 6/3/24 | 6/28/24 | NA | 1
10006 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 9 | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM | 5229 | 5231 | As Soon As Possible | NA | 22 | 0d | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM | 22 days | No | 7/1/24 | 7/31/24 | NA | 1
10007 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 10 | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 5230 | 5232 | As Soon As Possible | NA | 22 | 0d | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 22 days | No | 8/1/24 | 8/30/24 | NA | 1
10008 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 11 | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM | 5231 | 5233 | As Soon As Possible | NA | 21 | 0d | September 2, 2024 8:00 AM | September 27, 2024 5:00 PM | 20 days | No | 9/2/24 | 9/30/24 | NA | 1
10009 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 12 | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM | 5232 | 5621,5234 | As Soon As Possible | NA | 23 | 0d | September 30, 2024 8:00 AM | October 30, 2024 5:00 PM | 23 days | No | 10/1/24 | 10/31/24 | NA | 1
12203 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 13 | November 1, 2024 8:00 AM | November 27, 2024 5:00 PM | 5233 | 5235 | As Soon As Possible | NA | 18 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/27/24 | NA | 1
12204 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 14 | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 5234 | 5236 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
12205 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 15 | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 5235 | 5237 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 1/2/25 | 1/31/25 | NA | 1
12206 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 16 | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 5236 | 5238 | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
12207 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 17 | March 3, 2025 8:00 AM | March 28, 2025 5:00 PM | 5237 | 5239 | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/28/25 | NA | 1
12208 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 18 | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 5238 | 5240 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
12209 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 19 | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 5239 | 5241 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
12210 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 20 | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 5240 | 5242 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
12211 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 21 | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 5241 | 5243 | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
12212 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 22 | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 5242 | 5244 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
12213 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 23 | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 5243 | 5245 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
12214 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 24 | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 5244 | 5246 | As Soon As Possible | NA | 23 | 239d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.34999999999999998
12215 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 25 | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 5245 | 5247 | As Soon As Possible | NA | 18 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12216 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 26 | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 5246 | 5248 | As Soon As Possible | NA | 22 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12217 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 27 | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 5247 | 5249 | As Soon As Possible | NA | 20 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12218 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 28 | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 5248 | 5250 | As Soon As Possible | NA | 19 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12219 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 29 | March 2, 2026 8:00 AM | March 30, 2026 5:00 PM | 5249 | 5251 | As Soon As Possible | NA | 21 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12220 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 30 | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 5250 | 5252 | As Soon As Possible | NA | 22 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12221 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 31 | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 5251 | 5253 | As Soon As Possible | NA | 20 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12222 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 32 | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 5252 | 5254 | As Soon As Possible | NA | 22 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12223 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 33 | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 5253 | 5255 | As Soon As Possible | NA | 22 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12224 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 34 | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 5254 | 5256 | As Soon As Possible | NA | 21 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12225 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 35 | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 5255 | 5257 | As Soon As Possible | NA | 21 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12226 | Prepare materials and conduct monthly OCM Advisory Workgroup Meeting 36 | October 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 5256 | 5621 | As Soon As Possible | NA | 17 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
10015 | Develop Phase | February 27, 2023 8:00 AM | December 11, 2026 5:00 PM |  |  | As Soon As Possible | NA | 952 | 208d | February 27, 2023 8:00 AM | December 29, 2026 5:00 PM | 963 days | No | 2/27/23 | NA | NA | 0.78000000000000003
10016 | Create Sandbox Strategy | October 3, 2023 8:00 AM | February 21, 2025 5:00 PM |  |  | As Soon As Possible | NA | 347 | 422d | October 3, 2023 8:00 AM | July 16, 2024 5:00 PM | 196 days | No | 10/3/23 | NA | NA | 0.98999999999999999
10017 | Create and Incorporate Review Feedback for Sandbox Strategy DED | November 20, 2023 8:00 AM | January 5, 2024 5:00 PM | 3322FS+33d | 5261SS+13d,5266FS+26d | As Soon As Possible | NA | 31 | 0d | November 20, 2023 8:00 AM | January 5, 2024 5:00 PM | 31 days | No | 11/20/23 | 1/5/24 | NA | 1
10018 | Conduct Team/Peer Review with OCM Internal Team | December 11, 2023 8:00 AM | December 13, 2023 5:00 PM | 5260SS+13d | 5262SS | As Soon As Possible | NA | 3 | 0d | December 11, 2023 8:00 AM | December 13, 2023 5:00 PM | 3 days | No | 12/11/23 | 12/13/23 | NA | 1
10019 | Conduct Quality Review: OCM State Lead and OCM Vendor Lead | December 11, 2023 8:00 AM | December 13, 2023 5:00 PM | 5261SS | 5263 | As Soon As Possible | NA | 3 | 0d | December 11, 2023 8:00 AM | December 13, 2023 5:00 PM | 3 days | No | 12/11/23 | 12/13/23 | NA | 1
10020 | Implementation Manager Review: Vendor Implementation Manager | December 14, 2023 8:00 AM | December 21, 2023 5:00 PM | 5262 | 5264FS-1d | As Soon As Possible | NA | 6 | 0d | December 14, 2023 8:00 AM | December 21, 2023 5:00 PM | 6 days | No | 12/14/23 | 12/21/23 | NA | 1
10021 | State Implementation Review: State Implementation Managers (Debra/Cheryl/Sonoltra) | December 21, 2023 8:00 AM | December 29, 2023 5:00 PM | 5263FS-1d | 5266 | As Soon As Possible | NA | 6 | 0d | December 21, 2023 8:00 AM | December 29, 2023 5:00 PM | 6 days | No | 12/21/23 | 12/29/23 | NA | 1
10022 | Create First Draft of the Sandbox Strategy and Provide to State Leadership for Review | October 3, 2023 8:00 AM | February 23, 2024 5:00 PM | 3322 | 5267 | Start No Earlier Than | 10/3/23 | 97 | 0d | October 3, 2023 8:00 AM | February 23, 2024 5:00 PM | 97 days | No | 10/3/23 | 2/23/24 | NA | 1
10030 | Obtain DED Approval | February 14, 2024 8:00 AM | February 16, 2024 5:00 PM | 5260FS+26d,5264 | 5267 | As Soon As Possible | NA | 3 | 0d | February 14, 2024 8:00 AM | February 16, 2024 5:00 PM | 3 days | No | 2/14/24 | 2/16/24 | NA | 1
10031 | Complete Sandbox Strategy Reviews with the State Implementation Managers | February 26, 2024 8:00 AM | March 15, 2024 5:00 PM | 5265,5266 | 5268 | As Soon As Possible | NA | 15 | 0d | February 26, 2024 8:00 AM | March 15, 2024 5:00 PM | 15 days | No | 2/26/24 | 3/15/24 | NA | 1
10038 | Incorporate Feedback from State Imp Managers' Reviews | March 18, 2024 8:00 AM | March 20, 2024 5:00 PM | 5267 | 5269 | As Soon As Possible | NA | 3 | 0d | March 18, 2024 8:00 AM | March 20, 2024 5:00 PM | 3 days | No | 3/18/24 | 3/20/24 | NA | 1
10039 | Sandbox Strategy Review with Project Teams: CDSS, PaaS, Product, Service Desk, PVS, CDI, Engagement & Adoption / Strategic Communications, Technical, County Consultants, Independent Advisor, Independent Product Oversight, IV&V | March 21, 2024 8:00 AM | March 28, 2024 5:00 PM | 5268 | 5270 | As Soon As Possible | NA | 6 | 0d | March 21, 2024 8:00 AM | March 28, 2024 5:00 PM | 6 days | No | 3/21/24 | 3/28/24 | NA | 1
10040 | Incorporate Project Teams' feedback and address questions through small group meetings | March 29, 2024 8:00 AM | April 12, 2024 5:00 PM | 5269 | 5271FS+123d | As Soon As Possible | NA | 10 | 0d | March 29, 2024 8:00 AM | April 12, 2024 5:00 PM | 10 days | No | 3/29/24 | 4/12/24 | NA | 1
10041 | Develop Executive Summary slides for ELT and complete reviews with State Implementation Management Team | October 7, 2024 8:00 AM | October 18, 2024 5:00 PM | 5270FS+123d | 5272 | As Soon As Possible | NA | 10 | 0d | June 25, 2024 8:00 AM | July 3, 2024 5:00 PM | 7 days | No | 10/7/24 | 10/18/24 | NA | 1
10042 | Submit Sandbox Strategy to State Leadership: ELT | October 21, 2024 8:00 AM | October 29, 2024 5:00 PM | 5271 | 5273 | As Soon As Possible | NA | 7 | 0d | July 5, 2024 8:00 AM | July 12, 2024 5:00 PM | 6 days | No | 10/21/24 | 10/29/24 | NA | 1
10043 | Incorporate Feedback from ELT | October 30, 2024 8:00 AM | October 31, 2024 5:00 PM | 5272 | 5274 | As Soon As Possible | NA | 2 | 0d | July 15, 2024 8:00 AM | July 16, 2024 5:00 PM | 2 days | No | 10/30/24 | 10/31/24 | NA | 1
10044 | Sandbox Strategy Completed | October 31, 2024 5:00 PM | October 31, 2024 5:00 PM | 5273 | 5621,5275FS+49d | As Soon As Possible | NA | 0 | 0d | July 16, 2024 5:00 PM | July 16, 2024 5:00 PM | 0 days | Yes | 10/31/24 | 10/31/24 | NA | 1
13054 | Create a Follow-up Presentation for ELT and Receive Feedback | January 16, 2025 8:00 AM | February 18, 2025 5:00 PM | 5274FS+49d | 5276FS-1d | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/16/25 | 2/18/25 | NA | 1
13055 | Finalize the Updates for the Sandbox Strategy | February 18, 2025 8:00 AM | February 21, 2025 5:00 PM | 5275FS-1d | 5630 | As Soon As Possible | NA | 4 | 422d | NA | NA | 0 days? | No | 2/18/25 | NA | NA | 0.5
10045 | Video Series Program | August 28, 2023 8:00 AM | December 11, 2026 5:00 PM |  |  | As Soon As Possible | NA | 825 | 208d | August 28, 2023 8:00 AM | December 29, 2026 5:00 PM | 836 days | No | 8/28/23 | NA | NA | 0.47999999999999998
10046 | Video Series Approach and Proposed Schedule | August 28, 2023 8:00 AM | March 20, 2024 5:00 PM |  |  | As Soon As Possible | NA | 140 | 0d | August 28, 2023 8:00 AM | March 20, 2024 5:00 PM | 140 days | No | 8/28/23 | 3/20/24 | NA | 1
10047 | Create first draft of Video Series approach and proposed schedule | August 28, 2023 8:00 AM | September 11, 2023 5:00 PM | 5166FS+25d | 5280 | As Soon As Possible | NA | 10 | 0d | August 28, 2023 8:00 AM | September 11, 2023 5:00 PM | 10 days | No | 8/28/23 | 9/11/23 | NA | 1
10048 | Review draft Video Series approach and proposed schedule with State OCM Lead | September 12, 2023 8:00 AM | September 18, 2023 5:00 PM | 5279 | 5281 | As Soon As Possible | NA | 5 | 0d | September 12, 2023 8:00 AM | September 18, 2023 5:00 PM | 5 days | No | 9/12/23 | 9/18/23 | NA | 1
10049 | Incorporate feedback from State OCM Lead and Complete Internal Reviews | September 19, 2023 8:00 AM | September 29, 2023 5:00 PM | 5280 | 5282 | As Soon As Possible | NA | 9 | 0d | September 19, 2023 8:00 AM | September 29, 2023 5:00 PM | 9 days | No | 9/19/23 | 9/29/23 | NA | 1
10050 | Review draft Video Series approach and proposed schedule with State Leadership Team | October 2, 2023 8:00 AM | October 6, 2023 5:00 PM | 5281 | 5283 | As Soon As Possible | NA | 5 | 0d | October 2, 2023 8:00 AM | October 6, 2023 5:00 PM | 5 days | No | 10/2/23 | 10/6/23 | NA | 1
10051 | Incorporate feedback from State Leadership Team | October 9, 2023 8:00 AM | October 11, 2023 5:00 PM | 5282 | 5284FS+21d | As Soon As Possible | NA | 3 | 0d | October 9, 2023 8:00 AM | October 11, 2023 5:00 PM | 3 days | No | 10/9/23 | 10/11/23 | NA | 1
10052 | Review draft Video Series approach and proposed schedule with Service Managers and County Consultants | November 13, 2023 8:00 AM | November 17, 2023 5:00 PM | 5283FS+21d | 5285 | As Soon As Possible | NA | 5 | 0d | November 13, 2023 8:00 AM | November 17, 2023 5:00 PM | 5 days | No | 11/13/23 | 11/17/23 | NA | 1
10053 | Incorporate feedback from Service Managers and County Consultants | November 20, 2023 8:00 AM | November 22, 2023 5:00 PM | 5284 | 5286FS+6d | As Soon As Possible | NA | 3 | 0d | November 20, 2023 8:00 AM | November 22, 2023 5:00 PM | 3 days | No | 11/20/23 | 11/22/23 | NA | 1
10054 | Review draft Video Series approach and proposed schedule with Engagement and Adoption Team and Implementation Leads Team | December 5, 2023 8:00 AM | December 5, 2023 5:00 PM | 5285FS+6d | 5287 | As Soon As Possible | NA | 1 | 0d | December 5, 2023 8:00 AM | December 5, 2023 5:00 PM | 1 | No | 12/5/23 | 12/5/23 | NA | 1
10055 | Incorporate feedback from Engagement and Adoption Team and Implementation Leads Team | December 6, 2023 8:00 AM | December 7, 2023 5:00 PM | 5286 | 5289FS+6d | As Soon As Possible | NA | 2 | 0d | December 6, 2023 8:00 AM | December 7, 2023 5:00 PM | 2 days | No | 12/6/23 | 12/7/23 | NA | 1
10056 | Review draft Video Series approach and proposed schedule with OCM Advisory Workgroup | March 20, 2024 8:00 AM | March 20, 2024 5:00 PM | 5289FS+62d | 5293 | As Soon As Possible | NA | 1 | 0d | March 20, 2024 8:00 AM | March 20, 2024 5:00 PM | 1 | No | 3/20/24 | 3/20/24 | NA | 1
10057 | Complete final reviews with ELT and seek approval of Video Series approach and proposed schedule | December 18, 2023 8:00 AM | December 18, 2023 5:00 PM | 5287FS+6d | 5288FS+62d,5292FS-1d,5291FS+24d | As Soon As Possible | NA | 1 | 0d | December 18, 2023 8:00 AM | December 18, 2023 5:00 PM | 1 | No | 12/18/23 | 12/18/23 | NA | 1
10066 | OCM Video Series Development and Delivery | December 18, 2023 8:00 AM | December 11, 2026 5:00 PM |  |  | As Soon As Possible | NA | 749 | 208d | December 18, 2023 8:00 AM | December 11, 2026 5:00 PM | 749 days | No | 12/18/23 | NA | NA | 0.45000000000000001
10067 | Develop Value Hypothesis with the Product Team for the Video Series | January 25, 2024 8:00 AM | February 16, 2024 5:00 PM | 5289FS+24d | 5292FF+10d | As Soon As Possible | NA | 17 | 0d | January 25, 2024 8:00 AM | February 16, 2024 5:00 PM | 17 days | No | 1/25/24 | 2/16/24 | NA | 1
10068 | Develop and Complete Reviews of the 'Why CARES? A Case for Change' OCM Video | December 18, 2023 8:00 AM | March 29, 2024 5:00 PM | 5289FS-1d,5291FF+10d | 5293FS+9d | As Soon As Possible | NA | 71 | 0d | December 18, 2023 8:00 AM | March 29, 2024 5:00 PM | 71 days | No | 12/18/23 | 3/29/24 | NA | 1
10069 | Develop and Complete Reviews of the CWS-CARES OCM Video #2 | April 15, 2024 8:00 AM | July 31, 2024 5:00 PM | 5292FS+9d,5288 | 5295 | As Soon As Possible | NA | 76 | 0d | April 15, 2024 8:00 AM | July 31, 2024 5:00 PM | 76 days | No | 4/15/24 | 7/31/24 | NA | 1
11665 | Develop CWS-CARES 101 Video | August 1, 2024 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 145 | 0d | NA | NA | 0 days? | No | 8/1/24 | 2/28/25 | NA | 1
10070 | Develop Draft 'CWS-CARES 101' video Script and Complete Validation | August 1, 2024 8:00 AM | August 28, 2024 5:00 PM | 5293 | 5296 | As Soon As Possible | NA | 20 | 0d | August 1, 2024 8:00 AM | November 14, 2024 5:00 PM | 75 days | No | 8/1/24 | 8/28/24 | NA | 1
11669 | Develop 'CWS-CARES 101' video storyboard | December 2, 2024 8:00 AM | December 16, 2024 5:00 PM | 5295,1477FS+2d,4751FS-3d | 5297 | As Soon As Possible | NA | 11 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/16/24 | NA | 1
11668 | Complete reviews of 'CWS-CARES 101' video storyboard | December 17, 2024 8:00 AM | January 27, 2025 5:00 PM | 5296 | 5298 | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 12/17/24 | 1/27/25 | NA | 1
11667 | Incorporate ELT feedback and develop draft 'CWS-CARES 101' Vyond video | January 28, 2025 8:00 AM | February 10, 2025 5:00 PM | 5297 | 5299 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 1/28/25 | 2/10/25 | NA | 1
11666 | Complete reviews of 'CWS-CARES 101' Vyond video and launch | February 11, 2025 8:00 AM | February 28, 2025 5:00 PM | 5298 | 5302 | As Soon As Possible | NA | 13 | 0d | NA | NA | 0 days? | No | 2/11/25 | 2/28/25 | NA | 1
11670 | Develop and Launch Change Impact Video Series - 'CWS-CARES 101 Videos' | March 3, 2025 8:00 AM | June 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 319 | 337d | NA | NA | 0 days? | No | 3/3/25 | NA | NA | 0.42999999999999999
13604 | Develop and Launch 'CWS-CARES 101: Intake' Video | March 3, 2025 8:00 AM | June 26, 2025 5:00 PM |  |  | As Soon As Possible | NA | 82 | 0d | NA | NA | 0 days? | No | 3/3/25 | 6/26/25 | NA | 1
10071 | Develop CWS-CARES 101: Intake video script and complete validation | March 3, 2025 8:00 AM | April 4, 2025 5:00 PM | 5299 | 5303 | As Soon As Possible | NA | 24 | 0d | August 21, 2024 8:00 AM | October 15, 2024 5:00 PM | 40 days | No | 3/3/25 | 4/4/25 | NA | 1
11674 | Develop CWS-CARES 101: Intake storyboard | April 7, 2025 8:00 AM | April 21, 2025 5:00 PM | 5302 | 5304 | As Soon As Possible | NA | 11 | 0d | NA | NA | 0 days? | No | 4/7/25 | 4/21/25 | NA | 1
11673 | Complete reviews of CWS-CARES 101: Intake video storyboard, including ELT | April 22, 2025 8:00 AM | May 27, 2025 5:00 PM | 5303 | 5305 | As Soon As Possible | NA | 25 | 0d | NA | NA | 0 days? | No | 4/22/25 | 5/27/25 | NA | 1
11672 | Incorporate ELT feedback and develop draft CWS-CARES 101: Intake Vyond video | May 28, 2025 8:00 AM | June 10, 2025 5:00 PM | 5304 | 5306 | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 5/28/25 | 6/10/25 | NA | 1
11671 | Complete reviews of CWS-CARES 101: Intake Vyond video and launch | June 11, 2025 8:00 AM | June 26, 2025 5:00 PM | 5305 | 5630,5308SS+9d | As Soon As Possible | NA | 12 | 0d | NA | NA | 0 days? | No | 6/11/25 | 6/26/25 | NA | 1
13629 | Develop and Launch 'CWS-CARES 101: Placement and Eligibility' Video | June 24, 2025 8:00 AM | September 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 58 | 519d | NA | NA | 0 days? | No | 6/24/25 | NA | NA | 0.66000000000000003
13630 | Develop CWS-CARES 101: Placement & Eligibility video script and complete validation | June 24, 2025 8:00 AM | July 18, 2025 5:00 PM | 5306SS+9d | 5309,5332SS | As Soon As Possible | NA | 18 | 0d | NA | NA | 0 days? | No | 6/24/25 | 7/18/25 | NA | 1
13631 | Develop CWS-CARES 101: Placement & Eligibility video storyboard | July 21, 2025 8:00 AM | July 29, 2025 5:00 PM | 5308 | 5310 | As Soon As Possible | NA | 7 | 0d | NA | NA | 0 days? | No | 7/21/25 | 7/29/25 | NA | 1
13632 | Complete reviews of CWS-CARES 101: Placement & Eligibility video storyboard, including ELT | July 30, 2025 8:00 AM | August 22, 2025 5:00 PM | 5309 | 5311 | As Soon As Possible | NA | 18 | 519d | NA | NA | 0 days? | No | 7/30/25 | NA | NA | 0.75
13633 | Incorporate ELT feedback and develop draft CWS-CARES 101: Placement & Eligibility Vyond video | August 25, 2025 8:00 AM | September 2, 2025 5:00 PM | 5310 | 5312 | As Soon As Possible | NA | 6 | 519d | NA | NA | 0 days? | No | NA | NA | NA | 0
13634 | Complete reviews of CWS-CARES 101: Placement & Eligibility Vyond video and launch | September 3, 2025 8:00 AM | September 15, 2025 5:00 PM | 5311 | 5314 | As Soon As Possible | NA | 9 | 519d | NA | NA | 0 days? | No | NA | NA | NA | 0
13611 | Develop and Launch 'CWS-CARES 101: Ongoing Case Work and Finish a Case' Video | September 16, 2025 8:00 AM | December 12, 2025 5:00 PM |  |  | As Soon As Possible | NA | 62 | -4d | NA | NA | 0 days? | No | 9/16/25 | NA | NA | 0.31
13612 | Develop CWS-CARES 101: Ongoing Case Work & Finish a Case video script and complete validation | September 16, 2025 8:00 AM | October 9, 2025 5:00 PM | 5312 | 5315 | As Soon As Possible | NA | 18 | 0d | NA | NA | 0 days? | No | 9/16/25 | 10/9/25 | NA | 1
13613 | DevelopCWS-CARES 101: Ongoing Case Work & Finish a Case video storyboard | October 10, 2025 8:00 AM | October 21, 2025 5:00 PM | 5314 | 5316 | As Soon As Possible | NA | 8 | -4d | NA | NA | 0 days? | No | 10/10/25 | NA | NA | 0.12
13614 | Complete reviews of CWS-CARES 101: Ongoing Case Work & Finish a Case video storyboard, including ELT | October 22, 2025 8:00 AM | November 17, 2025 5:00 PM | 5315 | 5317 | As Soon As Possible | NA | 18 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13615 | Incorporate ELT feedback and develop CWS-CARES 101: Ongoing Case Work & Finish a Case Vyond video | November 18, 2025 8:00 AM | November 26, 2025 5:00 PM | 5316 | 5318FS+1d | As Soon As Possible | NA | 7 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13616 | Complete reviews of CWS-CARES 101: Ongoing Case Work & Finish a Case Vyond video and launch | December 1, 2025 8:00 AM | December 12, 2025 5:00 PM | 5317FS+1d | 5320 | As Soon As Possible | NA | 10 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13617 | Develop and Launch 'CWS-CARES 101: Court Processing' Video | December 15, 2025 8:00 AM | March 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 62 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13618 | Develop CWS-CARES 101: Court Processing video script and complete validation | December 15, 2025 8:00 AM | January 15, 2026 5:00 PM | 5318 | 5321,5338SS+12d | As Soon As Possible | NA | 22 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13619 | Develop CWS-CARES 101: Court Processing video storyboard | January 16, 2026 8:00 AM | January 27, 2026 5:00 PM | 5320 | 5322 | As Soon As Possible | NA | 7 | 98d | NA | NA | 0 days? | No | NA | NA | NA | 0
13620 | Complete reviews of CWS-CARES 101: Court Processing video storyboard, including ELT | January 28, 2026 8:00 AM | February 20, 2026 5:00 PM | 5321 | 5323 | As Soon As Possible | NA | 17 | 98d | NA | NA | 0 days? | No | NA | NA | NA | 0
13621 | Incorporate ELT feedback and develop draft CWS-CARES 101: Court Processing Vyond video | February 23, 2026 8:00 AM | March 3, 2026 5:00 PM | 5322 | 5324 | As Soon As Possible | NA | 7 | 98d | NA | NA | 0 days? | No | NA | NA | NA | 0
13622 | Complete reviews of CWS-CARES 101: Court Processing Vyond video and launch | March 4, 2026 8:00 AM | March 16, 2026 5:00 PM | 5323 | 5326 | As Soon As Possible | NA | 9 | 98d | NA | NA | 0 days? | No | NA | NA | NA | 0
13623 | Develop and Launch 'CWS-CARES 101: RFA/RM/FM & Admin' Video | March 17, 2026 8:00 AM | June 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 58 | 98d | NA | NA | 0 days? | No | NA | NA | NA | 0
13624 | Develop CWS-CARES 101: RFA/RM/FM & Admin video script and complete validation | March 17, 2026 8:00 AM | April 10, 2026 5:00 PM | 5324 | 5327 | As Soon As Possible | NA | 18 | 98d | NA | NA | 0 days? | No | NA | NA | NA | 0
13625 | Develop CWS-CARES 101: RFA/RM/FM & Admin video storyboard | April 13, 2026 8:00 AM | April 21, 2026 5:00 PM | 5326 | 5328 | As Soon As Possible | NA | 7 | 98d | NA | NA | 0 days? | No | NA | NA | NA | 0
13626 | Complete reviews of CWS-CARES 101: RFA/RM/FM & Admin video storyboard, including ELT | April 22, 2026 8:00 AM | May 15, 2026 5:00 PM | 5327 | 5329 | As Soon As Possible | NA | 18 | 98d | NA | NA | 0 days? | No | NA | NA | NA | 0
13627 | Incorporate ELT feedback and develop CWS-CARES 101: RFA/RM/FM & Admin Vyond video | May 18, 2026 8:00 AM | May 26, 2026 5:00 PM | 5328 | 5330 | As Soon As Possible | NA | 6 | 98d | NA | NA | 0 days? | No | NA | NA | NA | 0
13628 | Complete reviews of CWS-CARES 101: RFA/RM/FM & Admin Vyond video and launch | May 27, 2026 8:00 AM | June 8, 2026 5:00 PM | 5329 | 5630 | As Soon As Possible | NA | 9 | 98d | NA | NA | 0 days? | No | NA | NA | NA | 0
10073 | Develop and Launch the 'How to Promote System Adoption' video | June 24, 2025 8:00 AM | September 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 61 | 304d | June 20, 2025 8:00 AM | October 17, 2025 5:00 PM | 84 days | No | 6/24/25 | NA | NA | 0.68999999999999995
13635 | Develop 'How to Promote System Adoption' video script and complete validation | June 24, 2025 8:00 AM | July 18, 2025 5:00 PM | 5308SS | 5333 | As Soon As Possible | NA | 18 | 0d | NA | NA | 0 days? | No | 6/24/25 | 7/18/25 | NA | 1
13636 | Develop 'How to Promote System Adoption' video storyboard | July 21, 2025 8:00 AM | July 30, 2025 5:00 PM | 5332 | 5334 | As Soon As Possible | NA | 8 | 0d | NA | NA | 0 days? | No | 7/21/25 | 7/30/25 | NA | 1
13637 | Complete reviews of 'How to Promote System Adoption' video storyboard, including ELT | July 31, 2025 8:00 AM | August 25, 2025 5:00 PM | 5333 | 5335 | As Soon As Possible | NA | 18 | 304d | NA | NA | 0 days? | No | 7/31/25 | NA | NA | 0.90000000000000002
13638 | Incorporate ELT feedback and develop draft 'How to Promote System Adoption' Vyond video | August 26, 2025 8:00 AM | September 5, 2025 5:00 PM | 5334 | 5336 | As Soon As Possible | NA | 8 | 304d | NA | NA | 0 days? | No | NA | NA | NA | 0
13639 | Complete reviews of 'How to Promote System Adoption' Vyond video and launch | September 8, 2025 8:00 AM | September 18, 2025 5:00 PM | 5335 | 5361 | As Soon As Possible | NA | 9 | 304d | NA | NA | 0 days? | No | NA | NA | NA | 0
10074 | Develop and Launch the 'Day in the Life' video | January 2, 2026 8:00 AM | April 24, 2026 5:00 PM |  |  | As Soon As Possible | NA | 78 | -4d | January 2, 2026 8:00 AM | April 17, 2026 5:00 PM | 73 days | No | NA | NA | NA | 0
13640 | Develop 'Day in the Life' video script and complete validation | January 2, 2026 8:00 AM | January 27, 2026 5:00 PM | 5320SS+12d | 5339 | As Soon As Possible | NA | 17 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13641 | Develop 'Day in the Life' video storyboard | January 28, 2026 8:00 AM | February 6, 2026 5:00 PM | 5338 | 5340 | As Soon As Possible | NA | 8 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13642 | Complete reviews of 'Day in the Life' video storyboard, including ELT | February 9, 2026 8:00 AM | March 5, 2026 5:00 PM | 5339 | 5341 | As Soon As Possible | NA | 18 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13643 | Incorporate ELT feedback and develop draft 'Day in the Life' Vyond video | March 6, 2026 8:00 AM | March 16, 2026 5:00 PM | 5340 | 5342 | As Soon As Possible | NA | 7 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13644 | Complete reviews of 'Day in the Life' Vyond video and launch | March 17, 2026 8:00 AM | April 24, 2026 5:00 PM | 5341 | 5344,5361 | As Soon As Possible | NA | 28 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
10075 | Develop and Complete Reviews of the 'Preparing for CARES Go-Live' video | April 27, 2026 8:00 AM | August 17, 2026 5:00 PM |  |  | As Soon As Possible | NA | 79 | -4d | April 20, 2026 8:00 AM | July 24, 2026 5:00 PM | 68 days | No | NA | NA | NA | 0
13645 | Develop 'Preparing for CARES Go-Live' video script and complete validation | April 27, 2026 8:00 AM | May 21, 2026 5:00 PM | 5342 | 5346,5345 | As Soon As Possible | NA | 19 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13646 | Develop 'Preparing for CARES Go-Live' video storyboard | May 22, 2026 8:00 AM | June 2, 2026 5:00 PM | 5344 | 5346 | As Soon As Possible | NA | 7 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13647 | Complete reviews of 'Preparing for CARES Go-Live' video storyboard, including ELT | June 3, 2026 8:00 AM | June 29, 2026 5:00 PM | 5344,5345 | 5347 | As Soon As Possible | NA | 19 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13648 | Incorporate ELT feedback and develop draft 'Preparing for CARES Go-Live' Vyond video | June 30, 2026 8:00 AM | July 10, 2026 5:00 PM | 5346 | 5348 | As Soon As Possible | NA | 8 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13649 | Complete reviews of 'Preparing for CARES Go-Live' Vyond video and launch | July 13, 2026 8:00 AM | August 17, 2026 5:00 PM | 5347 | 5350SS,5361 | As Soon As Possible | NA | 26 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
10076 | Develop and Launch the 'What Happens Next?' video | July 13, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 80 | -4d | June 29, 2026 8:00 AM | October 2, 2026 5:00 PM | 68 days | No | NA | NA | NA | 0
13650 | Develop 'What Happens Next?' video script and complete validation | July 13, 2026 8:00 AM | August 7, 2026 5:00 PM | 5348SS | 5351 | As Soon As Possible | NA | 20 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13651 | Develop 'What Happens Next?' video storyboard | August 10, 2026 8:00 AM | August 19, 2026 5:00 PM | 5350 | 5352,5356SS+6d | As Soon As Possible | NA | 8 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13652 | Complete reviews of 'What Happens Next?' video storyboard, including ELT | August 20, 2026 8:00 AM | September 14, 2026 5:00 PM | 5351 | 5353 | As Soon As Possible | NA | 17 | 22d | NA | NA | 0 days? | No | NA | NA | NA | 0
13653 | Incorporate ELT feedback and develop draft 'What Happens Next?' Vyond video | September 15, 2026 8:00 AM | September 25, 2026 5:00 PM | 5352 | 5354 | As Soon As Possible | NA | 9 | 22d | NA | NA | 0 days? | No | NA | NA | NA | 0
13654 | Complete reviews of 'What Happens Next?' Vyond video and launch | September 28, 2026 8:00 AM | November 2, 2026 5:00 PM | 5353 | 5361 | As Soon As Possible | NA | 26 | 22d | NA | NA | 0 days? | No | NA | NA | NA | 0
10077 | Develop and Launch the 'Resources Overview' video | August 18, 2026 8:00 AM | December 11, 2026 5:00 PM |  |  | As Soon As Possible | NA | 80 | -4d | September 11, 2026 8:00 AM | December 11, 2026 5:00 PM | 63 days | No | NA | NA | NA | 0
13655 | Develop 'Resources Overview' video script and complete validation | August 18, 2026 8:00 AM | September 11, 2026 5:00 PM | 5351SS+6d | 5357 | As Soon As Possible | NA | 18 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13656 | Develop 'Resources Overview' video storyboard | September 14, 2026 8:00 AM | September 23, 2026 5:00 PM | 5356 | 5358 | As Soon As Possible | NA | 8 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13657 | Complete reviews of 'Resources Overview' video storyboard, including ELT | September 24, 2026 8:00 AM | October 19, 2026 5:00 PM | 5357 | 5359 | As Soon As Possible | NA | 18 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13658 | Incorporate ELT feedback and develop draft 'Resources Overview' Vyond video | October 20, 2026 8:00 AM | October 30, 2026 5:00 PM | 5358 | 5360 | As Soon As Possible | NA | 9 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
13659 | Complete reviews of 'Resources Overview' Vyond video and launch | November 2, 2026 8:00 AM | December 11, 2026 5:00 PM | 5359 | 5361 | As Soon As Possible | NA | 27 | -4d | NA | NA | 0 days? | No | NA | NA | NA | 0
10078 | Video Series Program Completed | December 11, 2026 5:00 PM | December 11, 2026 5:00 PM | 5360,5354,5348,5342,5336 | 5629FS-43d | As Soon As Possible | NA | 0 | -4d | December 29, 2026 5:00 PM | December 29, 2026 5:00 PM | 0 days | Yes | NA | NA | NA | 0
10079 | To-Be Process Documentation - Deliverable Task 5.5 | February 27, 2023 8:00 AM | March 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 769 | 152d | February 27, 2023 8:00 AM | January 29, 2026 5:00 PM | 734 days | No | 2/27/23 | NA | NA | 0.89000000000000001
10080 | Identify scope of baseline to-be documentation | February 27, 2023 8:00 AM | March 2, 2023 5:00 PM | 3192SS+184d | 5364,5365 | As Soon As Possible | NA | 4 | 0d | February 27, 2023 8:00 AM | March 2, 2023 5:00 PM | 4 days | No | 2/27/23 | 3/2/23 | NA | 1
10081 | Request Existing documentation from SMEs | May 24, 2023 8:00 AM | June 14, 2023 5:00 PM | 5046FS-12d,5363 | 5370 | As Soon As Possible | NA | 15 | 0d | May 24, 2023 8:00 AM | June 14, 2023 5:00 PM | 15 days | No | 5/24/23 | 6/14/23 | NA | 1
10082 | Determine LOE for Updating Documentation | March 3, 2023 8:00 AM | March 16, 2023 5:00 PM | 5363 | 5366 | As Soon As Possible | NA | 10 | 0d | March 3, 2023 8:00 AM | March 16, 2023 5:00 PM | 10 days | No | 3/3/23 | 3/16/23 | NA | 1
10083 | Assign Resources to completing updates | March 17, 2023 8:00 AM | March 30, 2023 5:00 PM | 5365 | 5367 | As Soon As Possible | NA | 10 | 0d | March 17, 2023 8:00 AM | March 30, 2023 5:00 PM | 10 days | No | 3/17/23 | 3/30/23 | NA | 1
10084 | Create Template for updating documentation | April 3, 2023 8:00 AM | April 14, 2023 5:00 PM | 5366 | 5368FS+39d,5528FS+63d | As Soon As Possible | NA | 10 | 0d | April 3, 2023 8:00 AM | April 14, 2023 5:00 PM | 10 days | No | 4/3/23 | 4/14/23 | NA | 1
10085 | Analyze to-be documentation and identify areas where org customization is needed | June 12, 2023 8:00 AM | September 26, 2023 5:00 PM | 5367FS+39d | 5372 | As Soon As Possible | NA | 75 | 0d | June 12, 2023 8:00 AM | September 26, 2023 5:00 PM | 75 days | No | 6/12/23 | 9/26/23 | NA | 1
10086 | Develop Screening To-Be Processes | April 10, 2023 8:00 AM | June 16, 2023 5:00 PM | 3192 | 5370 | As Soon As Possible | NA | 49 | 0d | April 10, 2023 8:00 AM | June 16, 2023 5:00 PM | 49 days | No | 4/10/23 | 6/16/23 | NA | 1
10087 | Review and Verify Screening To-Be Processes with Service Managers | June 19, 2023 8:00 AM | July 28, 2023 5:00 PM | 5369,5364 | 5372 | As Soon As Possible | NA | 29 | 0d | June 19, 2023 8:00 AM | July 28, 2023 5:00 PM | 29 days | No | 6/19/23 | 7/28/23 | NA | 1
10088 | Develop and Review Investigations: Engagement To-Be Processes | July 17, 2023 8:00 AM | December 8, 2023 5:00 PM | 3192 | 5372 | As Soon As Possible | NA | 101 | 0d | July 17, 2023 8:00 AM | December 8, 2023 5:00 PM | 101 days | No | 7/17/23 | 12/8/23 | NA | 1
10089 | Review and Verify Investigations - Engagement To-Be Processes with Service Managers | December 11, 2023 8:00 AM | December 15, 2023 5:00 PM | 5371,5368,5370 | 5630 | As Soon As Possible | NA | 5 | 0d | December 11, 2023 8:00 AM | December 15, 2023 5:00 PM | 5 days | No | 12/11/23 | 12/15/23 | NA | 1
10090 | Develop Investigations: Determination To-Be Processes | August 3, 2023 8:00 AM | December 22, 2023 5:00 PM | 3192 | 5630 | As Soon As Possible | NA | 98 | 0d | August 3, 2023 8:00 AM | December 22, 2023 5:00 PM | 98 days | No | 8/3/23 | 12/22/23 | NA | 1
10091 | Review and Verify Investigations - Determination To-Be Processes with Service Managers | May 13, 2024 8:00 AM | March 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 466 | 152d | January 2, 2024 8:00 AM | January 19, 2024 5:00 PM | 13 days | No | 5/13/24 | NA | NA | 0.85999999999999999
10329 | Process Areas | May 13, 2024 8:00 AM | March 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 466 | 152d | May 13, 2024 8:00 AM | January 29, 2026 5:00 PM | 431 days | No | 5/13/24 | NA | NA | 0.85999999999999999
10328 | Case Management | May 13, 2024 8:00 AM | December 29, 2025 5:00 PM |  |  | As Soon As Possible | NA | 410 | 157d | May 13, 2024 8:00 AM | January 29, 2026 5:00 PM | 431 days | No | 5/13/24 | NA | NA | 0.93999999999999995
10327 | Group 1 Placement (Milestones 1, 2, 6, 8, 15, 19, 20) | May 13, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 221 | 0d | May 13, 2024 8:00 AM | March 28, 2025 5:00 PM | 221 days | No | 5/13/24 | 3/28/25 | NA | 1
10297 | Milestone 06 - Case Management Engagement | May 13, 2024 8:00 AM | October 15, 2024 5:00 PM |  |  | As Soon As Possible | NA | 110 | 0d | May 13, 2024 8:00 AM | August 9, 2024 5:00 PM | 63 days | No | 5/13/24 | 10/15/24 | NA | 1
10298 | Develop To-Be Business Flows/Processes | May 13, 2024 8:00 AM | July 2, 2024 5:00 PM | 3192 | 5380FF+49d,5416SS+9d,5422SS+9d,5410SS+14d,4371SS+10d,4376SS+10d | As Soon As Possible | NA | 36 | 0d | May 13, 2024 8:00 AM | June 28, 2024 5:00 PM | 34 days | No | 5/13/24 | 7/2/24 | NA | 1
10299 | MS 06: Review To-Be Business Flows/Processes with VPODs | August 28, 2024 8:00 AM | September 10, 2024 5:00 PM | 5379FF+49d | 5381FF+5d | As Soon As Possible | NA | 10 | 0d | June 24, 2024 8:00 AM | June 28, 2024 5:00 PM | 5 days | No | 8/28/24 | 9/10/24 | NA | 1
10300 | MS 06: Incorporate VPODs Feedback | September 4, 2024 8:00 AM | September 17, 2024 5:00 PM | 5380FF+5d | 5382FF | As Soon As Possible | NA | 10 | 0d | June 24, 2024 8:00 AM | July 8, 2024 5:00 PM | 10 days | No | 9/4/24 | 9/17/24 | NA | 1
10301 | MS 06: Finalize To-Be Business Flows/Processes | September 11, 2024 8:00 AM | September 17, 2024 5:00 PM | 5381FF | 5383,4538,5550 | As Soon As Possible | NA | 5 | 0d | July 9, 2024 8:00 AM | July 12, 2024 5:00 PM | 4 days | No | 9/11/24 | 9/17/24 | NA | 1
10302 | MS 06: Review, Validate and Update To-Be Business Flows/Processes | September 18, 2024 8:00 AM | October 15, 2024 5:00 PM | 5382 | 5613 | As Soon As Possible | NA | 20 | 0d | July 15, 2024 8:00 AM | August 9, 2024 5:00 PM | 20 days | No | 9/18/24 | 10/15/24 | NA | 1
10303 | Milestone 08 - Placement | May 13, 2024 8:00 AM | October 15, 2024 5:00 PM |  |  | As Soon As Possible | NA | 110 | 0d | May 13, 2024 8:00 AM | August 9, 2024 5:00 PM | 63 days | No | 5/13/24 | 10/15/24 | NA | 1
10304 | Develop To-Be Business Flows/Processes | May 13, 2024 8:00 AM | July 2, 2024 5:00 PM | 3192 | 5386FF+49d,5416SS+9d,5422SS+9d,5410SS+14d,5391SS+11d | As Soon As Possible | NA | 36 | 0d | May 13, 2024 8:00 AM | June 28, 2024 5:00 PM | 34 days | No | 5/13/24 | 7/2/24 | NA | 1
10305 | MS 08: Review To-Be Business Flows/Processes with VPODs | August 28, 2024 8:00 AM | September 10, 2024 5:00 PM | 5385FF+49d | 5387FF+5d | As Soon As Possible | NA | 10 | 0d | June 24, 2024 8:00 AM | June 28, 2024 5:00 PM | 5 days | No | 8/28/24 | 9/10/24 | NA | 1
10306 | MS 08: Incorporate VPODs Feedback | September 4, 2024 8:00 AM | September 17, 2024 5:00 PM | 5386FF+5d | 5388FF | As Soon As Possible | NA | 10 | 0d | June 24, 2024 8:00 AM | July 8, 2024 5:00 PM | 10 days | No | 9/4/24 | 9/17/24 | NA | 1
10307 | MS 08: Finalize To-Be Business Flows/Processes | September 11, 2024 8:00 AM | September 17, 2024 5:00 PM | 5387FF | 5389,4538,5550 | As Soon As Possible | NA | 5 | 0d | July 9, 2024 8:00 AM | July 12, 2024 5:00 PM | 4 days | No | 9/11/24 | 9/17/24 | NA | 1
10308 | MS 08: Review, Validate and Update To-Be Business Flows/Processes | September 18, 2024 8:00 AM | October 15, 2024 5:00 PM | 5388 | 5613 | As Soon As Possible | NA | 20 | 0d | July 15, 2024 8:00 AM | August 9, 2024 5:00 PM | 20 days | No | 9/18/24 | 10/15/24 | NA | 1
10309 | Milestone 15 - Court Hearing Framework | May 28, 2024 8:00 AM | January 6, 2025 5:00 PM |  |  | As Soon As Possible | NA | 154 | 0d | May 28, 2024 8:00 AM | March 28, 2025 5:00 PM | 211 days | No | 5/28/24 | 1/6/25 | NA | 1
10310 | Develop To-Be Business Flows/Processes | May 28, 2024 8:00 AM | August 2, 2024 5:00 PM | 5385SS+11d | 5392FF+27d,5397SS,5403SS,5416SS+9d,5422SS+9d,5410SS+14d | As Soon As Possible | NA | 48 | 0d | May 28, 2024 8:00 AM | August 16, 2024 5:00 PM | 58 days | No | 5/28/24 | 8/2/24 | NA | 1
10311 | MS 15: Review To-Be Business Flows/Processes with VPODs | August 28, 2024 8:00 AM | September 10, 2024 5:00 PM | 5391FF+27d | 5393FF+5d | As Soon As Possible | NA | 10 | 0d | August 5, 2024 8:00 AM | August 16, 2024 5:00 PM | 10 days | No | 8/28/24 | 9/10/24 | NA | 1
10312 | MS 15: Incorporate VPODs Feedback | September 4, 2024 8:00 AM | September 17, 2024 5:00 PM | 5392FF+5d | 5394 | As Soon As Possible | NA | 10 | 0d | August 12, 2024 8:00 AM | August 23, 2024 5:00 PM | 10 days | No | 9/4/24 | 9/17/24 | NA | 1
10313 | MS 15: Finalize To-Be Business Flows/Processes | September 18, 2024 8:00 AM | September 24, 2024 5:00 PM | 5393 | 5395,4538,5550 | As Soon As Possible | NA | 5 | 0d | August 26, 2024 8:00 AM | August 30, 2024 5:00 PM | 5 days | No | 9/18/24 | 9/24/24 | NA | 1
10314 | MS 15: Review, Validate and Update To-Be Business Flows/Processes | December 6, 2024 8:00 AM | January 6, 2025 5:00 PM | 5394,440 | 5613 | As Soon As Possible | NA | 20 | 0d | March 3, 2025 8:00 AM | March 28, 2025 5:00 PM | 20 days | No | 12/6/24 | 1/6/25 | NA | 1
10315 | Milestone 19 - Request Determination | May 28, 2024 8:00 AM | December 18, 2024 5:00 PM |  |  | As Soon As Possible | NA | 143 | 0d | May 28, 2024 8:00 AM | March 27, 2025 5:00 PM | 210 days | No | 5/28/24 | 12/18/24 | NA | 1
10316 | Develop To-Be Business Flows/Processes | May 28, 2024 8:00 AM | August 16, 2024 5:00 PM | 5391SS | 5398FF+12d,5416SS+9d,5422SS+9d,5410SS+14d | As Soon As Possible | NA | 58 | 0d | May 28, 2024 8:00 AM | August 16, 2024 5:00 PM | 58 days | No | 5/28/24 | 8/16/24 | NA | 1
10317 | MS 19: Review To-Be Business Flows/Processes with VPODs | August 21, 2024 8:00 AM | September 5, 2024 5:00 PM | 5397FF+12d | 5399FF+3d | As Soon As Possible | NA | 12 | 0d | August 5, 2024 8:00 AM | August 16, 2024 5:00 PM | 10 days | No | 8/21/24 | 9/5/24 | NA | 1
10318 | MS 19: Incorporate VPODs Feedback | August 28, 2024 8:00 AM | September 10, 2024 5:00 PM | 5398FF+3d | 5400 | As Soon As Possible | NA | 10 | 0d | August 12, 2024 8:00 AM | August 23, 2024 5:00 PM | 10 days | No | 8/28/24 | 9/10/24 | NA | 1
10319 | MS 19: Finalize To-Be Business Flows/Processes | September 11, 2024 8:00 AM | September 17, 2024 5:00 PM | 5399 | 5401,4538,5550 | As Soon As Possible | NA | 5 | 0d | August 26, 2024 8:00 AM | August 30, 2024 5:00 PM | 5 days | No | 9/11/24 | 9/17/24 | NA | 1
10320 | MS 19: Review, Validate and Update To-Be Business Flows/Processes | November 19, 2024 8:00 AM | December 18, 2024 5:00 PM | 5400,469 | 5613 | As Soon As Possible | NA | 20 | 0d | February 28, 2025 8:00 AM | March 27, 2025 5:00 PM | 20 days | No | 11/19/24 | 12/18/24 | NA | 1
10321 | Milestone 20 - Redetermine Eligibility | May 28, 2024 8:00 AM | March 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 211 | 0d | May 28, 2024 8:00 AM | March 28, 2025 5:00 PM | 211 days | No | 5/28/24 | 3/28/25 | NA | 1
10322 | Develop To-Be Business Flows/Processes | May 28, 2024 8:00 AM | August 16, 2024 5:00 PM | 5391SS | 5404FF+12d,5416SS+9d,5422SS+9d,5410SS+14d | As Soon As Possible | NA | 58 | 0d | May 28, 2024 8:00 AM | August 16, 2024 5:00 PM | 58 days | No | 5/28/24 | 8/16/24 | NA | 1
10323 | MS 20: Review To-Be Business Flows/Processes with VPODs | August 26, 2024 8:00 AM | September 5, 2024 5:00 PM | 5403FF+12d | 5405FF+3d | As Soon As Possible | NA | 9 | 0d | August 5, 2024 8:00 AM | August 16, 2024 5:00 PM | 10 days | No | 8/26/24 | 9/5/24 | NA | 1
10324 | MS 20: Incorporate VPODs Feedback | August 28, 2024 8:00 AM | September 10, 2024 5:00 PM | 5404FF+3d | 5406 | As Soon As Possible | NA | 10 | 0d | August 12, 2024 8:00 AM | August 23, 2024 5:00 PM | 10 days | No | 8/28/24 | 9/10/24 | NA | 1
10325 | MS 20: Finalize To-Be Business Flows/Processes | September 11, 2024 8:00 AM | September 17, 2024 5:00 PM | 5405 | 5407,4538,5550 | As Soon As Possible | NA | 5 | 0d | August 26, 2024 8:00 AM | August 30, 2024 5:00 PM | 5 days | No | 9/11/24 | 9/17/24 | NA | 1
10326 | MS 20: Review, Validate and Update To-Be Business Flows/Processes | March 3, 2025 8:00 AM | March 28, 2025 5:00 PM | 5406,503 | 5613 | As Soon As Possible | NA | 20 | 0d | March 3, 2025 8:00 AM | March 28, 2025 5:00 PM | 20 days | No | 3/3/25 | 3/28/25 | NA | 1
10342 | Group 2 On-Going Case Work (Milestones 6.1, 7, 9) | June 10, 2024 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 353 | 195d | June 10, 2024 8:00 AM | January 29, 2026 5:00 PM | 412 days | No | 6/10/24 | NA | NA | 0.93000000000000005
10462 | Milestone 6.1 - Prevention Services | June 17, 2024 8:00 AM | October 14, 2024 5:00 PM |  |  | As Soon As Possible | NA | 85 | 0d | June 17, 2024 8:00 AM | August 30, 2024 5:00 PM | 54 days | No | 6/17/24 | 10/14/24 | NA | 1
10463 | Develop To-Be Business Flows/Processes | June 17, 2024 8:00 AM | July 2, 2024 5:00 PM | 5379SS+14d,5385SS+14d,5391SS+14d,5397SS+14d,5403SS+14d | 5411FS+39d,5429FS+29d,5436FS+29d,4440SS,4738FS+9mo,5443FS+27d | As Soon As Possible | NA | 12 | 0d | June 17, 2024 8:00 AM | June 28, 2024 5:00 PM | 10 days | No | 6/17/24 | 7/2/24 | NA | 1
10464 | MS 6.1: Review To-Be Business Flows/Processes with VPODs | August 28, 2024 8:00 AM | September 30, 2024 5:00 PM | 5410FS+39d | 5412FF+5d | As Soon As Possible | NA | 24 | 0d | July 1, 2024 8:00 AM | July 8, 2024 5:00 PM | 5 days | No | 8/28/24 | 9/30/24 | NA | 1
10465 | MS 6.1: Incorporate VPODs Feedback | September 24, 2024 8:00 AM | October 7, 2024 5:00 PM | 5411FF+5d | 5413 | As Soon As Possible | NA | 10 | 0d | July 1, 2024 8:00 AM | July 8, 2024 5:00 PM | 5 days | No | 9/24/24 | 10/7/24 | NA | 1
10466 | MS 6.1: Finalize To-Be Business Flows/Processes | October 8, 2024 8:00 AM | October 14, 2024 5:00 PM | 5412 | 4538,5550,5414FF | As Soon As Possible | NA | 5 | 0d | July 9, 2024 8:00 AM | July 12, 2024 5:00 PM | 4 days | No | 10/8/24 | 10/14/24 | NA | 1
10467 | MS 6.1: Review, Validate and Update To-Be Business Flows/Processes | August 28, 2024 8:00 AM | October 14, 2024 5:00 PM | 2504,5413FF | 5526,5613 | As Soon As Possible | NA | 20 | 0d | August 5, 2024 8:00 AM | August 30, 2024 5:00 PM | 20 days | No | 8/28/24 | 10/14/24 | NA | 1
10330 | Milestone 07 - Case Plan | June 10, 2024 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 353 | 195d | June 10, 2024 8:00 AM | January 29, 2026 5:00 PM | 412 days | No | 6/10/24 | NA | NA | 0.73999999999999999
10331 | Develop To-Be Business Flows/Processes | June 10, 2024 8:00 AM | July 2, 2024 5:00 PM | 5379SS+9d,5385SS+9d,5391SS+9d,5397SS+9d,5403SS+9d | 5420,5417FS+10d,5429FS+29d,5436FS+29d,4440SS,5443FS+27d | As Soon As Possible | NA | 17 | 0d | June 10, 2024 8:00 AM | June 28, 2024 5:00 PM | 15 days | No | 6/10/24 | 7/2/24 | NA | 1
10332 | MS 07: Review To-Be Business Flows/Processes with VPODs | July 18, 2024 8:00 AM | August 2, 2024 5:00 PM | 5416FS+10d | 5418FF+8d | As Soon As Possible | NA | 12 | 0d | July 1, 2024 8:00 AM | July 8, 2024 5:00 PM | 5 days | No | 7/18/24 | 8/2/24 | NA | 1
10333 | MS 07: Incorporate VPODs Feedback | August 8, 2024 8:00 AM | August 14, 2024 5:00 PM | 5417FF+8d | 5419 | As Soon As Possible | NA | 5 | 0d | July 1, 2024 8:00 AM | July 8, 2024 5:00 PM | 5 days | No | 8/8/24 | 8/14/24 | NA | 1
10334 | MS 07: Finalize To-Be Business Flows/Processes | August 15, 2024 8:00 AM | August 20, 2024 5:00 PM | 5418 | 4538,5550 | As Soon As Possible | NA | 4 | 0d | July 9, 2024 8:00 AM | July 12, 2024 5:00 PM | 4 days | No | 8/15/24 | 8/20/24 | NA | 1
10335 | Review, Validate and Update To-Be Business Flows/Processes | October 6, 2025 8:00 AM | October 31, 2025 5:00 PM | 5416,753 | 5526,5613 | As Soon As Possible | NA | 20 | 195d | December 31, 2025 8:00 AM | January 29, 2026 5:00 PM | 20 days | No | 10/6/25 | NA | NA | 0.25
10336 | Milestone 09 - Case Management - Engagement and Services | June 10, 2024 8:00 AM | October 14, 2024 5:00 PM |  |  | As Soon As Possible | NA | 90 | 0d | June 10, 2024 8:00 AM | July 29, 2024 5:00 PM | 35 days | No | 6/10/24 | 10/14/24 | NA | 1
10337 | Develop To-Be Business Flows/Processes | June 10, 2024 8:00 AM | July 2, 2024 5:00 PM | 5379SS+9d,5385SS+9d,5391SS+9d,5397SS+9d,5403SS+9d | 5423FS+39d,5429FS+29d,5436FS+29d,4440SS,5443FS+27d | As Soon As Possible | NA | 17 | 0d | June 10, 2024 8:00 AM | June 28, 2024 5:00 PM | 15 days | No | 6/10/24 | 7/2/24 | NA | 1
10338 | MS 09: Review To-Be Business Flows/Processes with VPODs | August 28, 2024 8:00 AM | September 30, 2024 5:00 PM | 5422FS+39d | 5424FF+5d | As Soon As Possible | NA | 24 | 0d | July 1, 2024 8:00 AM | July 8, 2024 5:00 PM | 5 days | No | 8/28/24 | 9/30/24 | NA | 1
10339 | MS 09: Incorporate VPODs Feedback | September 24, 2024 8:00 AM | October 7, 2024 5:00 PM | 5423FF+5d | 5425 | As Soon As Possible | NA | 10 | 0d | July 1, 2024 8:00 AM | July 8, 2024 5:00 PM | 5 days | No | 9/24/24 | 10/7/24 | NA | 1
10340 | MS 09: Finalize To-Be Business Flows/Processes | October 8, 2024 8:00 AM | October 14, 2024 5:00 PM | 5424 | 4538,5550,5426FF | As Soon As Possible | NA | 5 | 0d | July 9, 2024 8:00 AM | July 12, 2024 5:00 PM | 4 days | No | 10/8/24 | 10/14/24 | NA | 1
10341 | MS 09: Review, Validate and Update To-Be Business Flows/Processes | August 28, 2024 8:00 AM | October 14, 2024 5:00 PM | 355,5425FF | 5613 | As Soon As Possible | NA | 20 | 0d | July 1, 2024 8:00 AM | July 29, 2024 5:00 PM | 20 days | No | 8/28/24 | 10/14/24 | NA | 1
10361 | Group 3 Finish a Case (Milestones 10, 11, 13) | August 12, 2024 8:00 AM | December 29, 2025 5:00 PM |  |  | As Soon As Possible | NA | 347 | 157d | August 8, 2024 8:00 AM | January 29, 2026 5:00 PM | 370 days | No | 8/12/24 | NA | NA | 0.83999999999999997
10343 | Milestone 10 - Case Closure | August 12, 2024 8:00 AM | October 25, 2024 5:00 PM |  |  | As Soon As Possible | NA | 55 | 0d | August 8, 2024 8:00 AM | November 1, 2024 5:00 PM | 62 days | No | 8/12/24 | 10/25/24 | NA | 1
10344 | MS 10: Develop To-Be Business Flows/Processes | August 12, 2024 8:00 AM | August 19, 2024 5:00 PM | 5416FS+29d,5422FS+29d,5410FS+29d | 4496SS,5430 | As Soon As Possible | NA | 6 | 0d | August 8, 2024 8:00 AM | October 4, 2024 5:00 PM | 42 days | No | 8/12/24 | 8/19/24 | NA | 1
11675 | MS 10: Complete internal SME reviews of To-Be Business Flows/Processes and update proposed gaps | August 20, 2024 8:00 AM | September 27, 2024 5:00 PM | 5429 | 5431FF | As Soon As Possible | NA | 29 | 0d | NA | NA | 0 days? | No | 8/20/24 | 9/27/24 | NA | 1
10345 | MS 10: Review To-Be Business Flows/Processes with VPODs | September 17, 2024 8:00 AM | September 27, 2024 5:00 PM | 5430FF | 5432FF+5d | As Soon As Possible | NA | 9 | 0d | September 24, 2024 8:00 AM | October 4, 2024 5:00 PM | 9 days | No | 9/17/24 | 9/27/24 | NA | 1
10346 | MS 10: Incorporate VPODs Feedback | September 23, 2024 8:00 AM | October 4, 2024 5:00 PM | 5431FF+5d | 5433 | As Soon As Possible | NA | 10 | 0d | September 30, 2024 8:00 AM | October 11, 2024 5:00 PM | 10 days | No | 9/23/24 | 10/4/24 | NA | 1
10347 | MS10 - Finalize To-Be Business Flows/Processes | October 7, 2024 8:00 AM | October 11, 2024 5:00 PM | 5432 | 4538,5434 | As Soon As Possible | NA | 5 | 0d | October 14, 2024 8:00 AM | October 18, 2024 5:00 PM | 5 days | No | 10/7/24 | 10/11/24 | NA | 1
10348 | MS 10: Review, Validate and Update To-Be Business Flows/Processes | October 14, 2024 8:00 AM | October 25, 2024 5:00 PM | 5433 | 5613 | As Soon As Possible | NA | 10 | 0d | October 7, 2024 8:00 AM | November 1, 2024 5:00 PM | 20 days | No | 10/14/24 | 10/25/24 | NA | 1
10349 | Milestone 11 - Aftercare and Re-entry | August 12, 2024 8:00 AM | December 29, 2025 5:00 PM |  |  | As Soon As Possible | NA | 347 | 157d | August 8, 2024 8:00 AM | January 29, 2026 5:00 PM | 370 days | No | 8/12/24 | NA | NA | 0.75
10350 | MS 11: Develop To-Be Business Flows/Processes | August 12, 2024 8:00 AM | August 19, 2024 5:00 PM | 5416FS+29d,5422FS+29d,5410FS+29d | 5441,4496SS,5437 | As Soon As Possible | NA | 6 | 0d | August 8, 2024 8:00 AM | October 4, 2024 5:00 PM | 42 days | No | 8/12/24 | 8/19/24 | NA | 1
11676 | MS 11: Complete internal SME reviews of To-Be Business Flows/Processes and update proposed gaps | August 20, 2024 8:00 AM | September 27, 2024 5:00 PM | 5436 | 5438FF | As Soon As Possible | NA | 29 | 0d | NA | NA | 0 days? | No | 8/20/24 | 9/27/24 | NA | 1
10351 | MS 11: Review To-Be Business Flows/Processes with VPODs | September 17, 2024 8:00 AM | September 27, 2024 5:00 PM | 5437FF | 5439FF+5d | As Soon As Possible | NA | 9 | 0d | September 24, 2024 8:00 AM | October 4, 2024 5:00 PM | 9 days | No | 9/17/24 | 9/27/24 | NA | 1
10352 | MS 11: Incorporate VPODs Feedback | September 23, 2024 8:00 AM | October 4, 2024 5:00 PM | 5438FF+5d | 5440 | As Soon As Possible | NA | 10 | 0d | September 30, 2024 8:00 AM | October 11, 2024 5:00 PM | 10 days | No | 9/23/24 | 10/4/24 | NA | 1
10353 | MS 11: Finalize To-Be Business Flows/Processes | October 7, 2024 8:00 AM | October 11, 2024 5:00 PM | 5439 | 4538,5550 | As Soon As Possible | NA | 5 | 0d | October 14, 2024 8:00 AM | October 18, 2024 5:00 PM | 5 days | No | 10/7/24 | 10/11/24 | NA | 1
10354 | Review, Validate and Update To-Be Business Flows/Processes | December 1, 2025 8:00 AM | December 29, 2025 5:00 PM | 5436,763 | 5613 | As Soon As Possible | NA | 20 | 157d | December 31, 2025 8:00 AM | January 29, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
10355 | Milestone 13 - Adoption | August 12, 2024 8:00 AM | December 29, 2025 5:00 PM |  |  | As Soon As Possible | NA | 347 | 157d | August 8, 2024 8:00 AM | January 29, 2026 5:00 PM | 370 days | No | 8/12/24 | NA | NA | 0.79000000000000004
12227 | MS 13: Complete Discovery of To-Be Business Flows/Processes without Service Maps | August 12, 2024 8:00 AM | August 23, 2024 5:00 PM | 5416FS+27d,5422FS+27d,5410FS+27d | 5444FS+40d | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 8/12/24 | 8/23/24 | NA | 1
10356 | MS 13: Develop To-Be Business Flows/Processes | October 21, 2024 8:00 AM | November 25, 2024 5:00 PM | 5443FS+40d | 5449,4738FS+9mo,5445 | As Soon As Possible | NA | 25 | 0d | August 8, 2024 8:00 AM | October 4, 2024 5:00 PM | 42 days | No | 10/21/24 | 11/25/24 | NA | 1
11677 | MS 13: Complete internal SME reviews of To-Be Business Flows/Processes and update proposed gaps | November 26, 2024 8:00 AM | December 20, 2024 5:00 PM | 5444 | 5446FF | As Soon As Possible | NA | 17 | 0d | NA | NA | 0 days? | No | 11/26/24 | 12/20/24 | NA | 1
10357 | MS 13: Review To-Be Business Flows/Processes with VPODs | December 10, 2024 8:00 AM | December 20, 2024 5:00 PM | 5445FF | 5447FF+5d | As Soon As Possible | NA | 9 | 0d | September 24, 2024 8:00 AM | October 4, 2024 5:00 PM | 9 days | No | 12/10/24 | 12/20/24 | NA | 1
10358 | MS 13: Incorporate VPODs Feedback | December 16, 2024 8:00 AM | December 30, 2024 5:00 PM | 5446FF+5d | 5448 | As Soon As Possible | NA | 10 | 0d | September 30, 2024 8:00 AM | October 11, 2024 5:00 PM | 10 days | No | 12/16/24 | 12/30/24 | NA | 1
10359 | MS13: Finalize To-Be Business Flows/Processes | December 31, 2024 8:00 AM | January 7, 2025 5:00 PM | 5447 | 4538,5550FS+66d | As Soon As Possible | NA | 5 | 0d | October 14, 2024 8:00 AM | October 18, 2024 5:00 PM | 5 days | No | 12/31/24 | 1/7/25 | NA | 1
10360 | MS 13: Review, Validate and Update To-Be Business Flows/Processes | December 1, 2025 8:00 AM | December 29, 2025 5:00 PM | 5444,759 | 5526,5613 | As Soon As Possible | NA | 20 | 157d | December 31, 2025 8:00 AM | January 29, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
10387 | Courts | June 28, 2024 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 339 | 195d | June 28, 2024 8:00 AM | January 29, 2026 5:00 PM | 398 days | No | 6/28/24 | NA | NA | 0.83999999999999997
10386 | Group 1 Courts Processing (Milestones 14, 16, 17, 18) | June 28, 2024 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 339 | 195d | June 28, 2024 8:00 AM | January 29, 2026 5:00 PM | 398 days | No | 6/28/24 | NA | NA | 0.83999999999999997
10362 | Milestone 14 - Warrants | June 28, 2024 8:00 AM | November 8, 2024 5:00 PM |  |  | As Soon As Possible | NA | 95 | 0d | June 28, 2024 8:00 AM | September 11, 2024 5:00 PM | 53 days | No | 6/28/24 | 11/8/24 | NA | 1
10363 | Develop To-Be Business Flows/Processes | June 28, 2024 8:00 AM | August 2, 2024 5:00 PM | 793FS-40d | 5454FF+41d,4542SS | As Soon As Possible | NA | 25 | 0d | June 28, 2024 8:00 AM | July 31, 2024 5:00 PM | 23 days | No | 6/28/24 | 8/2/24 | NA | 1
10364 | MS 14: Review To-Be Business Flows/Processes with VPODs | September 17, 2024 8:00 AM | September 30, 2024 5:00 PM | 5453FF+41d | 5455FF+5d | As Soon As Possible | NA | 10 | 0d | July 18, 2024 8:00 AM | July 31, 2024 5:00 PM | 10 days | No | 9/17/24 | 9/30/24 | NA | 1
10365 | MS 14: Incorporate VPODs Feedback | September 24, 2024 8:00 AM | October 11, 2024 5:00 PM | 5454FF+5d | 5456FF | As Soon As Possible | NA | 14 | 0d | July 25, 2024 8:00 AM | August 7, 2024 5:00 PM | 10 days | No | 9/24/24 | 10/11/24 | NA | 1
10366 | MS 14: Finalize To-Be Business Flows/Processes | October 7, 2024 8:00 AM | October 11, 2024 5:00 PM | 5455FF | 5457 | As Soon As Possible | NA | 5 | 0d | August 8, 2024 8:00 AM | August 14, 2024 5:00 PM | 5 days | No | 10/7/24 | 10/11/24 | NA | 1
10367 | MS 14: Review, Validate and Update To-Be Business Flows/Processes | October 14, 2024 8:00 AM | November 8, 2024 5:00 PM | 5456,411 | 5526,5613 | As Soon As Possible | NA | 20 | 0d | August 15, 2024 8:00 AM | September 11, 2024 5:00 PM | 20 days | No | 10/14/24 | 11/8/24 | NA | 1
10368 | Milestone 16 - Jurisdiction and Disposition Hearing | June 28, 2024 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 339 | 195d | June 28, 2024 8:00 AM | January 29, 2026 5:00 PM | 398 days | No | 6/28/24 | NA | NA | 0.79000000000000004
10369 | Develop To-Be Business Flows/Processes | June 28, 2024 8:00 AM | August 9, 2024 5:00 PM | 793FS-40d | 5460FF | As Soon As Possible | NA | 30 | 0d | June 28, 2024 8:00 AM | July 31, 2024 5:00 PM | 23 days | No | 6/28/24 | 8/9/24 | NA | 1
10370 | MS 16: Review To-Be Business Flows/Processes with VPODs | August 5, 2024 8:00 AM | August 9, 2024 5:00 PM | 5459FF | 5461FF+5d | As Soon As Possible | NA | 5 | 0d | July 18, 2024 8:00 AM | July 31, 2024 5:00 PM | 10 days | No | 8/5/24 | 8/9/24 | NA | 1
10371 | MS 16: Incorporate VPODs Feedback | August 5, 2024 8:00 AM | August 16, 2024 5:00 PM | 5460FF+5d | 5462 | As Soon As Possible | NA | 10 | 0d | July 25, 2024 8:00 AM | August 7, 2024 5:00 PM | 10 days | No | 8/5/24 | 8/16/24 | NA | 1
10372 | MS 16: Finalize To-Be Business Flows/Processes | August 19, 2024 8:00 AM | August 23, 2024 5:00 PM | 5461 | 5463 | As Soon As Possible | NA | 5 | 0d | August 8, 2024 8:00 AM | August 14, 2024 5:00 PM | 5 days | No | 8/19/24 | 8/23/24 | NA | 1
10373 | Review, Validate and Update To-Be Business Flows/Processes | October 6, 2025 8:00 AM | October 31, 2025 5:00 PM | 5462,899 | 5613 | As Soon As Possible | NA | 20 | 195d | December 31, 2025 8:00 AM | January 29, 2026 5:00 PM | 20 days | No | 10/6/25 | NA | NA | 0.25
10374 | Milestone 17 - Status Review | June 28, 2024 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 339 | 195d | June 28, 2024 8:00 AM | January 29, 2026 5:00 PM | 398 days | No | 6/28/24 | NA | NA | 0.79000000000000004
10375 | Develop To-Be Business Flows/Processes | June 28, 2024 8:00 AM | August 9, 2024 5:00 PM | 793FS-40d | 5466FF | As Soon As Possible | NA | 30 | 0d | June 28, 2024 8:00 AM | July 31, 2024 5:00 PM | 23 days | No | 6/28/24 | 8/9/24 | NA | 1
10376 | Review To-Be Business Flows/Processes with VPODs | August 5, 2024 8:00 AM | August 9, 2024 5:00 PM | 5465FF | 5467FF+5d | As Soon As Possible | NA | 5 | 0d | July 18, 2024 8:00 AM | July 31, 2024 5:00 PM | 10 days | No | 8/5/24 | 8/9/24 | NA | 1
10377 | Incorporate VPODs Feedback | August 5, 2024 8:00 AM | August 16, 2024 5:00 PM | 5466FF+5d | 5468 | As Soon As Possible | NA | 10 | 0d | July 25, 2024 8:00 AM | August 7, 2024 5:00 PM | 10 days | No | 8/5/24 | 8/16/24 | NA | 1
10378 | MS17 - Finalize To-Be Business Flows/Processes | August 19, 2024 8:00 AM | August 23, 2024 5:00 PM | 5467 | 5469 | As Soon As Possible | NA | 5 | 0d | August 8, 2024 8:00 AM | August 14, 2024 5:00 PM | 5 days | No | 8/19/24 | 8/23/24 | NA | 1
10379 | Review, Validate and Update To-Be Business Flows/Processes | October 6, 2025 8:00 AM | October 31, 2025 5:00 PM | 5468,904 | 5613 | As Soon As Possible | NA | 20 | 195d | December 31, 2025 8:00 AM | January 29, 2026 5:00 PM | 20 days | No | 10/6/25 | NA | NA | 0.25
10380 | Milestone 18 - Other Hearing | June 28, 2024 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 339 | 195d | June 28, 2024 8:00 AM | January 29, 2026 5:00 PM | 398 days | No | 6/28/24 | NA | NA | 0.79000000000000004
10381 | Develop To-Be Business Flows/Processes | June 28, 2024 8:00 AM | August 9, 2024 5:00 PM | 793FS-40d | 5472FF | As Soon As Possible | NA | 30 | 0d | June 28, 2024 8:00 AM | July 31, 2024 5:00 PM | 23 days | No | 6/28/24 | 8/9/24 | NA | 1
10382 | Review To-Be Business Flows/Processes with VPODs | August 5, 2024 8:00 AM | August 9, 2024 5:00 PM | 5471FF | 5473FF+5d | As Soon As Possible | NA | 5 | 0d | July 18, 2024 8:00 AM | July 31, 2024 5:00 PM | 10 days | No | 8/5/24 | 8/9/24 | NA | 1
10383 | Incorporate VPODs Feedback | August 5, 2024 8:00 AM | August 16, 2024 5:00 PM | 5472FF+5d | 5474,5487SS | As Soon As Possible | NA | 10 | 0d | July 25, 2024 8:00 AM | August 7, 2024 5:00 PM | 10 days | No | 8/5/24 | 8/16/24 | NA | 1
10384 | MS18 - Finalize To-Be Business Flows/Processes | August 19, 2024 8:00 AM | August 23, 2024 5:00 PM | 5473 | 5475 | As Soon As Possible | NA | 5 | 0d | August 8, 2024 8:00 AM | August 14, 2024 5:00 PM | 5 days | No | 8/19/24 | 8/23/24 | NA | 1
10385 | Review, Validate and Update To-Be Business Flows/Processes | October 6, 2025 8:00 AM | October 31, 2025 5:00 PM | 5474,908 | 5613 | As Soon As Possible | NA | 20 | 195d | December 31, 2025 8:00 AM | January 29, 2026 5:00 PM | 20 days | No | 10/6/25 | NA | NA | 0.25
10395 | Eligibility | July 29, 2024 8:00 AM | January 27, 2026 5:00 PM |  |  | As Soon As Possible | NA | 376 | 138d | October 21, 2024 8:00 AM | January 24, 2025 5:00 PM | 64 days | No | 7/29/24 | NA | NA | 0.66000000000000003
10394 | Group 1 Eligibility (Milestones 21) | July 29, 2024 8:00 AM | January 27, 2026 5:00 PM |  |  | As Soon As Possible | NA | 376 | 138d | October 21, 2024 8:00 AM | January 24, 2025 5:00 PM | 64 days | No | 7/29/24 | NA | NA | 0.66000000000000003
10388 | Milestone 21 - Eligibility Programs | July 29, 2024 8:00 AM | January 27, 2026 5:00 PM |  |  | As Soon As Possible | NA | 376 | 138d | October 21, 2024 8:00 AM | January 24, 2025 5:00 PM | 64 days | No | 7/29/24 | NA | NA | 0.66000000000000003
10389 | Develop To-Be Business Flows/Processes | July 29, 2024 8:00 AM | August 16, 2024 5:00 PM | 1189SS-10d | 5480FS+5d,4610SS+5d,4738FS+9mo | As Soon As Possible | NA | 15 | 0d | October 21, 2024 8:00 AM | December 10, 2024 5:00 PM | 34 days | No | 7/29/24 | 8/16/24 | NA | 1
10390 | MS 21: Review To-Be Business Flows/Processes with VPODs | August 26, 2024 8:00 AM | September 5, 2024 5:00 PM | 5479FS+5d | 5481FF+3d | Finish No Earlier Than | 4/1/21 | 9 | 0d | November 25, 2024 8:00 AM | December 10, 2024 5:00 PM | 10 days | No | 8/26/24 | 9/5/24 | NA | 1
10391 | MS 21: Incorporate VPODs Feedback | August 26, 2024 8:00 AM | September 10, 2024 5:00 PM | 5480FF+3d | 5482 | As Soon As Possible | NA | 10 | 0d | December 4, 2024 8:00 AM | December 17, 2024 5:00 PM | 10 days | No | 8/26/24 | 9/10/24 | NA | 1
10392 | MS 21: Finalize To-Be Business Flows/Processes | September 11, 2024 8:00 AM | September 17, 2024 5:00 PM | 5481 | 5483 | As Soon As Possible | NA | 5 | 0d | December 18, 2024 8:00 AM | December 24, 2024 5:00 PM | 5 days | No | 9/11/24 | 9/17/24 | NA | 1
10393 | Review, Validate and Update To-Be Business Flows/Processes | December 29, 2025 8:00 AM | January 27, 2026 5:00 PM | 5482,1249 | 5613 | As Soon As Possible | NA | 20 | 138d | December 26, 2024 8:00 AM | January 24, 2025 5:00 PM | 20 days | No | NA | NA | NA | 0
10415 | Resource Family Approval | August 5, 2024 8:00 AM | February 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 389 | 171d | September 9, 2024 8:00 AM | January 29, 2026 5:00 PM | 348 days | No | 8/5/24 | NA | NA | 0.72999999999999998
10414 | Group 1 Resource Family Approval (Milestones 26, 27, 28) | August 5, 2024 8:00 AM | February 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 389 | 171d | September 9, 2024 8:00 AM | January 29, 2026 5:00 PM | 348 days | No | 8/5/24 | NA | NA | 0.72999999999999998
10396 | Milestone 26 - Maintain Resource Family Home | August 5, 2024 8:00 AM | January 29, 2026 5:00 PM |  |  | As Soon As Possible | NA | 373 | 187d | September 9, 2024 8:00 AM | January 29, 2026 5:00 PM | 348 days | No | 8/5/24 | NA | NA | 0.72999999999999998
10397 | MS 26: Develop To-Be Business Flows/Processes | August 5, 2024 8:00 AM | September 11, 2024 5:00 PM | 5473SS | 5491FS+2d,5488FF,4634SS+5d,4738FS+9mo,5493SS | As Soon As Possible | NA | 28 | 0d | September 9, 2024 8:00 AM | October 23, 2024 5:00 PM | 33 days | No | 8/5/24 | 9/11/24 | NA | 1
10398 | MS 26: Review To-Be Business Flows/Processes with VPODs | August 29, 2024 8:00 AM | September 11, 2024 5:00 PM | 5487FF | 5489FF+5d | As Soon As Possible | NA | 10 | 0d | October 10, 2024 8:00 AM | October 23, 2024 5:00 PM | 10 days | No | 8/29/24 | 9/11/24 | NA | 1
10399 | MS 26: Incorporate VPODs Feedback | September 5, 2024 8:00 AM | September 18, 2024 5:00 PM | 5488FF+5d | 5490 | As Soon As Possible | NA | 10 | 0d | October 17, 2024 8:00 AM | October 30, 2024 5:00 PM | 10 days | No | 9/5/24 | 9/18/24 | NA | 1
10400 | MS 26: Finalize To-Be Business Flows/Processes | September 19, 2024 8:00 AM | September 25, 2024 5:00 PM | 5489 | 5491 | As Soon As Possible | NA | 5 | 0d | October 31, 2024 8:00 AM | November 6, 2024 5:00 PM | 5 days | No | 9/19/24 | 9/25/24 | NA | 1
10401 | Review, Validate and Update To-Be Business Flows/Processes | December 31, 2025 8:00 AM | January 29, 2026 5:00 PM | 5487FS+2d,1053FS+2d,5490 | 5526 | As Soon As Possible | NA | 20 | 187d | December 31, 2025 8:00 AM | January 29, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
10402 | Milestone 27 - Complaints | August 5, 2024 8:00 AM | January 27, 2026 5:00 PM |  |  | As Soon As Possible | NA | 371 | 189d | September 9, 2024 8:00 AM | January 29, 2026 5:00 PM | 348 days | No | 8/5/24 | NA | NA | 0.72999999999999998
10403 | MS 27: Develop To-Be Business Flows/Processes | August 5, 2024 8:00 AM | September 11, 2024 5:00 PM | 5487SS | 5497,5494FF,4738FS+9mo,5499SS | As Soon As Possible | NA | 28 | 0d | September 9, 2024 8:00 AM | October 23, 2024 5:00 PM | 33 days | No | 8/5/24 | 9/11/24 | NA | 1
10404 | MS 27: Review To-Be Business Flows/Processes with VPODs | August 29, 2024 8:00 AM | September 11, 2024 5:00 PM | 5493FF | 5495FF+5d | As Soon As Possible | NA | 10 | 0d | October 10, 2024 8:00 AM | October 23, 2024 5:00 PM | 10 days | No | 8/29/24 | 9/11/24 | NA | 1
10405 | MS 27: Incorporate VPODs Feedback | September 5, 2024 8:00 AM | September 18, 2024 5:00 PM | 5494FF+5d | 5496 | As Soon As Possible | NA | 10 | 0d | October 17, 2024 8:00 AM | October 30, 2024 5:00 PM | 10 days | No | 9/5/24 | 9/18/24 | NA | 1
10406 | MS 27: Finalize To-Be Business Flows/Processes | September 19, 2024 8:00 AM | September 25, 2024 5:00 PM | 5495 | 5497 | As Soon As Possible | NA | 5 | 0d | October 31, 2024 8:00 AM | November 6, 2024 5:00 PM | 5 days | No | 9/19/24 | 9/25/24 | NA | 1
10407 | Review, Validate and Update To-Be Business Flows/Processes | December 29, 2025 8:00 AM | January 27, 2026 5:00 PM | 5493,1058,5496 | 5526 | As Soon As Possible | NA | 20 | 189d | December 31, 2025 8:00 AM | January 29, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
10408 | Milestone 28 - Legal Action | August 5, 2024 8:00 AM | February 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 389 | 171d | September 9, 2024 8:00 AM | January 29, 2026 5:00 PM | 348 days | No | 8/5/24 | NA | NA | 0.72999999999999998
10409 | MS 28: Develop To-Be Business Flows/Processes | August 5, 2024 8:00 AM | September 11, 2024 5:00 PM | 5493SS | 5503,5500FF,4738FS+9mo | As Soon As Possible | NA | 28 | 0d | September 9, 2024 8:00 AM | October 23, 2024 5:00 PM | 33 days | No | 8/5/24 | 9/11/24 | NA | 1
10410 | MS 28: Review To-Be Business Flows/Processes with VPODs | August 29, 2024 8:00 AM | September 11, 2024 5:00 PM | 5499FF | 5501FF+5d | As Soon As Possible | NA | 10 | 0d | October 10, 2024 8:00 AM | October 23, 2024 5:00 PM | 10 days | No | 8/29/24 | 9/11/24 | NA | 1
10411 | MS 28: Incorporate VPODs Feedback | September 5, 2024 8:00 AM | September 18, 2024 5:00 PM | 5500FF+5d | 5502 | As Soon As Possible | NA | 10 | 0d | October 17, 2024 8:00 AM | October 30, 2024 5:00 PM | 10 days | No | 9/5/24 | 9/18/24 | NA | 1
10412 | MS 28: Finalize To-Be Business Flows/Processes | September 19, 2024 8:00 AM | September 25, 2024 5:00 PM | 5501 | 5503,5536 | As Soon As Possible | NA | 5 | 0d | October 31, 2024 8:00 AM | November 6, 2024 5:00 PM | 5 days | No | 9/19/24 | 9/25/24 | NA | 1
10413 | Review, Validate and Update To-Be Business Flows/Processes | January 26, 2026 8:00 AM | February 23, 2026 5:00 PM | 5499,1062,5502 | 5526 | As Soon As Possible | NA | 20 | 171d | December 31, 2025 8:00 AM | January 29, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
10429 | Financial Management | October 21, 2024 8:00 AM | March 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 353 | 101d | October 21, 2024 8:00 AM | January 29, 2026 5:00 PM | 318 days | No | 10/21/24 | NA | NA | 0.69999999999999996
10428 | Group 1 Financial Management (Milestones 23, 24) | October 21, 2024 8:00 AM | March 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 353 | 101d | October 21, 2024 8:00 AM | January 29, 2026 5:00 PM | 318 days | No | 10/21/24 | NA | NA | 0.69999999999999996
10416 | Milestone 23 - Track Administrative Costs | October 21, 2024 8:00 AM | March 20, 2026 5:00 PM |  |  | As Soon As Possible | NA | 353 | 101d | October 21, 2024 8:00 AM | January 29, 2026 5:00 PM | 318 days | No | 10/21/24 | NA | NA | 0.69999999999999996
10417 | MS 23: Develop To-Be Business Flows/Processes | October 21, 2024 8:00 AM | November 20, 2024 5:00 PM | 1189 | 5511,5508FF,4675FS+5d,4738FS+9mo | As Soon As Possible | NA | 22 | 0d | October 21, 2024 8:00 AM | November 20, 2024 5:00 PM | 22 days | No | 10/21/24 | 11/20/24 | NA | 1
10418 | MS 23: Review To-Be Business Flows/Processes with VPODs | November 6, 2024 8:00 AM | November 20, 2024 5:00 PM | 5507FF | 5509FF+5d | As Soon As Possible | NA | 10 | 0d | November 6, 2024 8:00 AM | November 20, 2024 5:00 PM | 10 days | No | 11/6/24 | 11/20/24 | NA | 1
10419 | MS 23: Incorporate VPODs Feedback | November 14, 2024 8:00 AM | November 27, 2024 5:00 PM | 5508FF+5d | 5510 | As Soon As Possible | NA | 10 | 0d | November 14, 2024 8:00 AM | November 27, 2024 5:00 PM | 10 days | No | 11/14/24 | 11/27/24 | NA | 1
10420 | MS 23: Finalize To-Be Business Flows/Processes | December 2, 2024 8:00 AM | December 6, 2024 5:00 PM | 5509 | 5511 | As Soon As Possible | NA | 5 | 0d | December 2, 2024 8:00 AM | December 6, 2024 5:00 PM | 5 days | No | 12/2/24 | 12/6/24 | NA | 1
10421 | Review, Validate and Update To-Be Business Flows/Processes | February 23, 2026 8:00 AM | March 20, 2026 5:00 PM | 5507,1167,1249,5510 | 5613 | As Soon As Possible | NA | 20 | 101d | December 31, 2025 8:00 AM | January 29, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
10422 | Milestone 24 - Track Assistance Costs | October 21, 2024 8:00 AM | January 27, 2026 5:00 PM |  |  | As Soon As Possible | NA | 316 | 138d | October 21, 2024 8:00 AM | January 29, 2026 5:00 PM | 318 days | No | 10/21/24 | NA | NA | 0.69999999999999996
10423 | MS 24: Develop To-Be Business Flows/Processes | October 21, 2024 8:00 AM | November 20, 2024 5:00 PM | 1189 | 5517,5514FF,4738FS+9mo | As Soon As Possible | NA | 22 | 0d | October 21, 2024 8:00 AM | November 20, 2024 5:00 PM | 22 days | No | 10/21/24 | 11/20/24 | NA | 1
10424 | MS 24: Review To-Be Business Flows/Processes with VPODs | November 6, 2024 8:00 AM | November 20, 2024 5:00 PM | 5513FF | 5515FF+5d | As Soon As Possible | NA | 10 | 0d | November 6, 2024 8:00 AM | November 20, 2024 5:00 PM | 10 days | No | 11/6/24 | 11/20/24 | NA | 1
10425 | MS 24: Incorporate VPODs Feedback | November 14, 2024 8:00 AM | November 27, 2024 5:00 PM | 5514FF+5d | 5516 | As Soon As Possible | NA | 10 | 0d | November 14, 2024 8:00 AM | November 27, 2024 5:00 PM | 10 days | No | 11/14/24 | 11/27/24 | NA | 1
10426 | MS 24: Finalize To-Be Business Flows/Processes | December 2, 2024 8:00 AM | December 6, 2024 5:00 PM | 5515 | 5517 | As Soon As Possible | NA | 5 | 0d | December 2, 2024 8:00 AM | December 6, 2024 5:00 PM | 5 days | No | 12/2/24 | 12/6/24 | NA | 1
10427 | Review, Validate and Update To-Be Business Flows/Processes | December 29, 2025 8:00 AM | January 27, 2026 5:00 PM | 5513,1171,5516 | 5526,5613 | As Soon As Possible | NA | 20 | 138d | December 31, 2025 8:00 AM | January 29, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
10436 | Admin Console | January 9, 2025 8:00 AM | January 12, 2026 5:00 PM |  |  | As Soon As Possible | NA | 253 | 148d | February 24, 2025 8:00 AM | January 14, 2026 5:00 PM | 225 days | No | 1/9/25 | NA | NA | 0.80000000000000004
10435 | Group 1 Admin Console (Milestones 32) | January 9, 2025 8:00 AM | January 12, 2026 5:00 PM |  |  | As Soon As Possible | NA | 253 | 148d | February 24, 2025 8:00 AM | January 14, 2026 5:00 PM | 225 days | No | 1/9/25 | NA | NA | 0.80000000000000004
10434 | Milestone 32 - Miscellaneous | January 9, 2025 8:00 AM | January 12, 2026 5:00 PM |  |  | As Soon As Possible | NA | 253 | 148d | February 24, 2025 8:00 AM | January 14, 2026 5:00 PM | 225 days | No | 1/9/25 | NA | NA | 0.80000000000000004
10438 | MS 32: Develop To-Be Business Flows/Processes | January 9, 2025 8:00 AM | January 30, 2025 5:00 PM | 1261FS-45d | 5525,5522FF,4724SS,4738FS+6mo | As Soon As Possible | NA | 15 | 0d | February 24, 2025 8:00 AM | March 14, 2025 5:00 PM | 15 days | No | 1/9/25 | 1/30/25 | NA | 1
10439 | MS 32: Review To-Be Business Flows/Processes with VPODs | January 16, 2025 8:00 AM | January 30, 2025 5:00 PM | 5521FF | 5523FF+5d | As Soon As Possible | NA | 10 | 0d | March 3, 2025 8:00 AM | March 14, 2025 5:00 PM | 10 days | No | 1/16/25 | 1/30/25 | NA | 1
10440 | MS 32: Incorporate VPODs Feedback | January 24, 2025 8:00 AM | February 6, 2025 5:00 PM | 5522FF+5d | 5524 | As Soon As Possible | NA | 10 | 0d | March 10, 2025 8:00 AM | March 21, 2025 5:00 PM | 10 days | No | 1/24/25 | 2/6/25 | NA | 1
10441 | MS 32: Finalize To-Be Business Flows/Processes | February 7, 2025 8:00 AM | February 13, 2025 5:00 PM | 5523 | 5525 | As Soon As Possible | NA | 5 | 0d | March 24, 2025 8:00 AM | March 28, 2025 5:00 PM | 5 days | No | 2/7/25 | 2/13/25 | NA | 1
10442 | Review, Validate and Update To-Be Business Flows/Processes | December 29, 2025 8:00 AM | January 12, 2026 5:00 PM | 5521,1284,5524 | 5526,5613 | As Soon As Possible | NA | 10 | 148d | December 31, 2025 8:00 AM | January 14, 2026 5:00 PM | 10 days | No | NA | NA | NA | 0
10100 | Deliverable Task 5.5 Completed | February 23, 2026 5:00 PM | February 23, 2026 5:00 PM | 5517,5525,5503,5420,5449,5457,5414,5491,5497 | 5630 | Start No Earlier Than | 1/29/26 | 0 | 171d | January 29, 2026 5:00 PM | January 29, 2026 5:00 PM | 0 days | Yes | NA | NA | NA | 0
10101 | Change Impact Analysis - Deliverable Task 5.6 | July 17, 2023 8:00 AM | December 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 100 | 0d | July 17, 2023 8:00 AM | December 7, 2023 5:00 PM | 100 days | No | 7/17/23 | 12/7/23 | NA | 1
10102 | Develop template for Change Impact Assessment | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM | 5367FS+63d | 5529 | As Soon As Possible | NA | 10 | 0d | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM | 10 days | No | 7/17/23 | 7/28/23 | NA | 1
10103 | Develop scoring criteria for rating degree of impact for people, process, and technology change impacts | July 31, 2023 8:00 AM | August 11, 2023 5:00 PM | 5528 | 5530FS-7d | As Soon As Possible | NA | 10 | 0d | July 31, 2023 8:00 AM | August 11, 2023 5:00 PM | 10 days | No | 7/31/23 | 8/11/23 | NA | 1
10104 | Complete Change Impact Assessment Template Review with State and Incorporate Feedback | August 3, 2023 8:00 AM | August 25, 2023 5:00 PM | 5529FS-7d | 5531FS+14d | As Soon As Possible | NA | 17 | 0d | August 3, 2023 8:00 AM | August 25, 2023 5:00 PM | 17 days | No | 8/3/23 | 8/25/23 | NA | 1
10105 | Develop Change Impacts for Intake Screening | September 18, 2023 8:00 AM | November 15, 2023 5:00 PM | 5530FS+14d | 5532FS-19d | As Soon As Possible | NA | 42 | 0d | September 18, 2023 8:00 AM | November 15, 2023 5:00 PM | 42 days | No | 9/18/23 | 11/15/23 | NA | 1
10106 | Review and validate Initial change impacts for Intake Screening with SMEs | November 16, 2023 8:00 AM | December 7, 2023 5:00 PM | 5531FS-19d | 5533 | As Soon As Possible | NA | 14 | 0d | November 16, 2023 8:00 AM | December 7, 2023 5:00 PM | 14 days | No | 11/16/23 | 12/7/23 | NA | 1
10107 | Change Impact Assessment for Intake Screening Complete | December 7, 2023 5:00 PM | December 7, 2023 5:00 PM | 5532 | 5541FS+26d,5542FS+56d | As Soon As Possible | NA | 0 | 0d | December 7, 2023 5:00 PM | December 7, 2023 5:00 PM | 0 days | Yes | 12/7/23 | 12/7/23 | NA | 1
10120 | Deliver Phase | February 27, 2023 8:00 AM | October 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 920 | 239d | February 27, 2023 8:00 AM | March 21, 2025 5:00 PM | 519 days | No | 2/27/23 | NA | NA | 0.69999999999999996
12663 | Deliver Initial Intake To-Be Process Maps and Change Impacts (Intake: Screening, Investigations: Engagement, and Investigations: Determination) | September 26, 2024 8:00 AM | October 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 25 | 0d | NA | NA | 0 days? | No | 9/26/24 | 10/30/24 | NA | 1
12664 | Develop draft materials (includes: introductory video, packet with to-be maps and change impacts) | September 26, 2024 8:00 AM | October 11, 2024 5:00 PM | 5502 | 5537 | As Soon As Possible | NA | 12 | 0d | NA | NA | 0 days? | No | 9/26/24 | 10/11/24 | NA | 1
12665 | Complete internal reviews of materials and incorporate feedback | October 14, 2024 8:00 AM | October 18, 2024 5:00 PM | 5536 | 5538 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 10/14/24 | 10/18/24 | NA | 1
12666 | Complete State Implementation Management reviews of materials and incorporate feedback | October 21, 2024 8:00 AM | October 25, 2024 5:00 PM | 5537 | 5539 | As Soon As Possible | NA | 5 | 0d | NA | NA | 0 days? | No | 10/21/24 | 10/25/24 | NA | 1
12667 | Complete ADA compliance and finalize materials for IL November Monthly Readiness Meetings | October 28, 2024 8:00 AM | October 30, 2024 5:00 PM | 5538 | 5630 | As Soon As Possible | NA | 3 | 0d | NA | NA | 0 days? | No | 10/28/24 | 10/30/24 | NA | 1
10131 | Information Sessions | January 18, 2024 8:00 AM | February 27, 2026 5:00 PM |  |  | As Soon As Possible | NA | 531 | 405d | January 18, 2024 8:00 AM | March 21, 2025 5:00 PM | 296 days | No | 1/18/24 | NA | NA | 0.69999999999999996
10136 | Develop Process Information Session 1: Intake Resources (process flows, change impacts, draft worksheets, invitation communications) | January 18, 2024 8:00 AM | March 8, 2024 5:00 PM | 5533FS+26d | 5543 | As Soon As Possible | NA | 36 | 0d | January 18, 2024 8:00 AM | March 8, 2024 5:00 PM | 36 days | No | 1/18/24 | 3/8/24 | NA | 1
10137 | Support Process Information Session Overviews at March 2024 RUGS meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM | 5533FS+56d | 5544 | As Soon As Possible | NA | 21 | 0d | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM | 21 days | No | 3/1/24 | 3/29/24 | NA | 1
10140 | Complete Reviews of Process Information Session 1: Intake Resources with Implementation Leads, Training, and Implementation Management Team and incorporate feedback | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 5541 | 5544FS+21d | As Soon As Possible | NA | 5 | 0d | March 11, 2024 8:00 AM | March 15, 2024 5:00 PM | 5 days | No | 3/11/24 | 3/15/24 | NA | 1
10141 | Complete Reviews of Process Information Session 1: Intake Resources with the OCM Advisory Workgroup and incorporate feedback | April 17, 2024 8:00 AM | April 24, 2024 5:00 PM | 5543FS+21d,5542 | 5545SS+200d | As Soon As Possible | NA | 6 | 0d | April 17, 2024 8:00 AM | April 24, 2024 5:00 PM | 6 days | No | 4/17/24 | 4/24/24 | NA | 1
10142 | Complete Reviews of Process Information Session 1: Intake Resources with the Service Managers and County Consultants and incorporate feedback | February 3, 2025 8:00 AM | March 10, 2025 5:00 PM | 5544SS+200d | 5546 | As Soon As Possible | NA | 25 | 0d | August 26, 2024 8:00 AM | October 4, 2024 5:00 PM | 30 days | No | 2/3/25 | 3/10/25 | NA | 1
10143 | Schedule Process Information Session 1: Intake Regional Sessions | March 11, 2025 8:00 AM | March 17, 2025 5:00 PM | 5545 | 5547 | As Soon As Possible | NA | 5 | 0d | October 7, 2024 8:00 AM | October 11, 2024 5:00 PM | 5 days | No | 3/11/25 | 3/17/25 | NA | 1
10144 | Conduct Dry Run for Process Information Session 1: Intake | March 18, 2025 8:00 AM | March 24, 2025 5:00 PM | 5546 | 5548FS+4d | As Soon As Possible | NA | 5 | 0d | October 14, 2024 8:00 AM | October 18, 2024 5:00 PM | 5 days | No | 3/18/25 | 3/24/25 | NA | 1
10145 | Complete Final Preparations for Process Information Session 1: Intake Regional Sessions | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 5547FS+4d | 5549 | As Soon As Possible | NA | 22 | 0d | November 4, 2024 8:00 AM | January 23, 2025 5:00 PM | 53 days | No | 4/1/25 | 4/30/25 | NA | 1
11678 | Deliver Process Information Session 1: Intake Regional Sessions | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 5548 | 5630 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
10146 | Develop Process Information Session 2: Case Management Resources (process flows, change impacts, draft worksheets, invitation communications) | April 15, 2025 8:00 AM | April 28, 2025 5:00 PM | 5382,5388,5394,5400,5406,5413,5419,5425,5440,5448FS+66d | 5551 | As Soon As Possible | NA | 10 | 0d | October 21, 2024 8:00 AM | November 1, 2024 5:00 PM | 10 days | No | 4/15/25 | 4/28/25 | NA | 1
10147 | Complete Reviews of Process Information Session 2: Case Management Resources with Implementation Leads, Training, and Implementation Management Team and incorporate feedback | April 29, 2025 8:00 AM | May 9, 2025 5:00 PM | 5550 | 5552FS+2d | As Soon As Possible | NA | 9 | 0d | November 4, 2024 8:00 AM | November 15, 2024 5:00 PM | 9 days | No | 4/29/25 | 5/9/25 | NA | 1
10148 | Complete Reviews of Process Information Session 2: Case Management Resources with the OCM Advisory Workgroup and incorporate feedback | May 14, 2025 8:00 AM | May 21, 2025 5:00 PM | 5551FS+2d | 5553FS+2d | As Soon As Possible | NA | 6 | 0d | November 20, 2024 8:00 AM | November 27, 2024 5:00 PM | 6 days | No | 5/14/25 | 5/21/25 | NA | 1
10149 | Complete Reviews of Process Information Session 2: Case Management Resources with the Service Managers and County Consultants and incorporate feedback | May 27, 2025 8:00 AM | June 9, 2025 5:00 PM | 5552FS+2d | 5554 | As Soon As Possible | NA | 10 | 0d | December 4, 2024 8:00 AM | December 17, 2024 5:00 PM | 10 days | No | 5/27/25 | 6/9/25 | NA | 1
10150 | Schedule Process Information Session 2: Case Management Regional Sessions | June 10, 2025 8:00 AM | June 16, 2025 5:00 PM | 5553 | 5555 | As Soon As Possible | NA | 5 | 0d | December 18, 2024 8:00 AM | December 24, 2024 5:00 PM | 5 days | No | 6/10/25 | 6/16/25 | NA | 1
10151 | Conduct Dry Run for Process Information Session 2: Case Management | June 17, 2025 8:00 AM | June 23, 2025 5:00 PM | 5554 | 5556FS+5d | As Soon As Possible | NA | 5 | 0d | December 26, 2024 8:00 AM | January 2, 2025 5:00 PM | 5 days | No | 6/17/25 | 6/23/25 | NA | 1
10152 | Deliver Process Information Session 2: Placement Regional Sessions - Part 1 | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 5555FS+5d | 5557 | As Soon As Possible | NA | 22 | 0d | January 24, 2025 8:00 AM | March 21, 2025 5:00 PM | 40 days | No | 7/1/25 | 7/31/25 | NA | 1
11679 | Deliver Process Information Session 2: Placement Regional Sessions - Part 2 | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 5556 | 5621,5558 | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
12668 | Deliver Process Information Session 3: Ongoing Case Work and Finish a Case Regional Sessions - Part 1 | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 5557 | 5559,5560SS | As Soon As Possible | NA | 21 | 0d | January 24, 2025 8:00 AM | March 21, 2025 5:00 PM | 40 days | No | 9/2/25 | 9/30/25 | NA | 1
12669 | Deliver Process Information Session 3: Ongoing Case Work and Finish a Case Regional Sessions - Part 2 | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 5558 | 5562 | As Soon As Possible | NA | 23 | 167d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.34999999999999998
13689 | Deliver Process Information Session: Probation - Part 1 | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 5558SS | 5561FS+41d | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
13690 | Deliver Process Information Session: Probation - Part 2 | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 5560FS+41d | 5564 | As Soon As Possible | NA | 22 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
12670 | Deliver Process Information Session 4: Court Processing Regional Sessions - Part 1 | November 3, 2025 8:00 AM | December 12, 2025 5:00 PM | 5559 | 5563,5565FS+13d | As Soon As Possible | NA | 28 | 167d | January 24, 2025 8:00 AM | March 21, 2025 5:00 PM | 40 days | No | NA | NA | NA | 0
12671 | Deliver Process Information Session 4: Court Processing Regional Sessions - Part 2 | December 15, 2025 8:00 AM | January 12, 2026 5:00 PM | 5562 |  | As Soon As Possible | NA | 19 | 438d | NA | NA | 0 days? | No | NA | NA | NA | 0
13691 | Deliver Process Information Session: CDSS | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 5561 | 5621 | As Soon As Possible | NA | 20 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
12672 | Deliver Process Information Session 5: RFA/RM/FM/Admin Regional Sessions - Part 1 | January 5, 2026 8:00 AM | February 13, 2026 5:00 PM | 5562FS+13d | 5566 | As Soon As Possible | NA | 29 | 167d | January 24, 2025 8:00 AM | March 21, 2025 5:00 PM | 40 days | No | NA | NA | NA | 0
12673 | Deliver Process Information Session 5: RFA/RM/FM/Admin Regional Sessions - Part 2 | February 17, 2026 8:00 AM | February 27, 2026 5:00 PM | 5565 | 5630 | As Soon As Possible | NA | 9 | 167d | NA | NA | 0 days? | No | NA | NA | NA | 0
10162 | Communications | February 27, 2023 8:00 AM | October 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 920 | 239d | February 27, 2023 8:00 AM | July 31, 2024 5:00 PM | 359 days | No | 2/27/23 | NA | NA | 0.68999999999999995
10163 | Draft and distribute monthly communications products | July 3, 2023 8:00 AM | October 23, 2026 5:00 PM |  |  | As Soon As Possible | NA | 832 | 239d | July 3, 2023 8:00 AM | July 31, 2024 5:00 PM | 271 days | No | 7/3/23 | NA | NA | 0.68999999999999995
10164 | Draft and distribute monthly communications products 1 | July 3, 2023 8:00 AM | July 31, 2023 5:00 PM | 3192 | 5570 | Start No Earlier Than | 7/1/23 | 20 | 0d | July 3, 2023 8:00 AM | July 31, 2023 5:00 PM | 20 days | No | 7/3/23 | 7/31/23 | NA | 1
10165 | Draft and distribute monthly communications products 2 | August 1, 2023 8:00 AM | August 31, 2023 5:00 PM | 5569 | 5571 | Start No Earlier Than | 8/1/23 | 23 | 0d | August 1, 2023 8:00 AM | August 31, 2023 5:00 PM | 23 days | No | 8/1/23 | 8/31/23 | NA | 1
10166 | Draft and distribute monthly communications products 3 | September 1, 2023 8:00 AM | September 29, 2023 5:00 PM | 5570 | 5572 | Start No Earlier Than | 9/1/23 | 20 | 0d | September 1, 2023 8:00 AM | September 29, 2023 5:00 PM | 20 days | No | 9/1/23 | 9/29/23 | NA | 1
10167 | Draft and distribute monthly communications products 4 | October 2, 2023 8:00 AM | October 31, 2023 5:00 PM | 5571 | 5573 | Start No Earlier Than | 10/1/23 | 22 | 0d | October 2, 2023 8:00 AM | October 31, 2023 5:00 PM | 22 days | No | 10/2/23 | 10/31/23 | NA | 1
10168 | Draft and distribute monthly communications products 5 | November 1, 2023 8:00 AM | November 30, 2023 5:00 PM | 5572 | 5574 | Start No Earlier Than | 11/1/23 | 19 | 0d | November 1, 2023 8:00 AM | November 30, 2023 5:00 PM | 19 days | No | 11/1/23 | 11/30/23 | NA | 1
10169 | Draft and distribute monthly communications products 6 | December 1, 2023 8:00 AM | December 29, 2023 5:00 PM | 5573 | 5575 | Start No Earlier Than | 12/1/23 | 20 | 0d | December 1, 2023 8:00 AM | December 29, 2023 5:00 PM | 20 days | No | 12/1/23 | 12/29/23 | NA | 1
10170 | Draft and distribute monthly communications products 7 | January 2, 2024 8:00 AM | January 31, 2024 5:00 PM | 5574 | 5576 | Start No Earlier Than | 1/1/24 | 21 | 0d | January 2, 2024 8:00 AM | January 31, 2024 5:00 PM | 21 days | No | 1/2/24 | 1/31/24 | NA | 1
10171 | Draft and distribute monthly communications products 8 | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM | 5575 | 5577 | Start No Earlier Than | 2/1/24 | 20 | 0d | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM | 20 days | No | 2/1/24 | 2/29/24 | NA | 1
10172 | Draft and distribute monthly communications products 9 | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM | 5576 | 5578 | Start No Earlier Than | 3/1/24 | 21 | 0d | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM | 21 days | No | 3/1/24 | 3/29/24 | NA | 1
10173 | Draft and distribute monthly communications products 10 | April 2, 2024 8:00 AM | April 30, 2024 5:00 PM | 5577 | 5579 | Start No Earlier Than | 4/1/24 | 21 | 0d | April 2, 2024 8:00 AM | April 30, 2024 5:00 PM | 21 days | No | 4/2/24 | 4/30/24 | NA | 1
10174 | Draft and distribute monthly communications products 11 | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM | 5578 | 5580 | Start No Earlier Than | 5/1/24 | 22 | 0d | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM | 22 days | No | 5/1/24 | 5/31/24 | NA | 1
10175 | Draft and distribute monthly communications products 12 | June 3, 2024 8:00 AM | June 28, 2024 5:00 PM | 5579 | 5581 | Start No Earlier Than | 6/1/24 | 20 | 0d | June 3, 2024 8:00 AM | June 28, 2024 5:00 PM | 20 days | No | 6/3/24 | 6/28/24 | NA | 1
10176 | Draft and distribute monthly communications products 13 | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM | 5580 | 5609,5582 | Start No Earlier Than | 7/1/24 | 22 | 0d | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM | 22 days | No | 7/1/24 | 7/31/24 | NA | 1
12228 | Draft and distribute monthly communications products 14 | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM | 5581 | 5583 | Start No Earlier Than | 8/1/24 | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
12229 | Draft and distribute monthly communications products 15 | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM | 5582 | 5584 | Start No Earlier Than | 9/1/24 | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
12230 | Draft and distribute monthly communications products 16 | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM | 5583 | 5585 | Start No Earlier Than | 10/1/24 | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
12231 | Draft and distribute monthly communications products 17 | November 1, 2024 8:00 AM | November 27, 2024 5:00 PM | 5584 | 5586 | Start No Earlier Than | 11/1/24 | 18 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/27/24 | NA | 1
12232 | Draft and distribute monthly communications products 18 | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM | 5585 | 5587 | Start No Earlier Than | 12/1/24 | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
12233 | Draft and distribute monthly communications products 19 | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM | 5586 | 5588 | Start No Earlier Than | 1/1/25 | 21 | 0d | NA | NA | 0 days? | No | 1/2/25 | 1/31/25 | NA | 1
12234 | Draft and distribute monthly communications products 20 | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM | 5587 | 5589 | Start No Earlier Than | 2/1/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
12235 | Draft and distribute monthly communications products 21 | March 3, 2025 8:00 AM | March 28, 2025 5:00 PM | 5588 | 5590 | Start No Earlier Than | 3/1/25 | 20 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/28/25 | NA | 1
12236 | Draft and distribute monthly communications products 22 | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM | 5589 | 5591 | Start No Earlier Than | 4/1/25 | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
12237 | Draft and distribute monthly communications products 23 | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM | 5590 | 5592 | Start No Earlier Than | 5/1/25 | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
12238 | Draft and distribute monthly communications products 24 | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM | 5591 | 5593 | Start No Earlier Than | 6/1/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
12239 | Draft and distribute monthly communications products 25 | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM | 5592 | 5594 | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
12240 | Draft and distribute monthly communications products 26 | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 5593 | 5595 | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
12241 | Draft and distribute monthly communications products 27 | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 5594 | 5596 | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
12242 | Draft and distribute monthly communications products 28 | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 5595 | 5597 | Start No Earlier Than | 10/1/25 | 23 | 239d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.34999999999999998
12243 | Draft and distribute monthly communications products 29 | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM | 5596 | 5598 | Start No Earlier Than | 11/1/25 | 18 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12244 | Draft and distribute monthly communications products 30 | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 5597 | 5599 | Start No Earlier Than | 12/1/25 | 22 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12245 | Draft and distribute monthly communications products 31 | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM | 5598 | 5600 | Start No Earlier Than | 1/1/26 | 20 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12246 | Draft and distribute monthly communications products 32 | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 5599 | 5601 | Start No Earlier Than | 2/1/26 | 19 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12247 | Draft and distribute monthly communications products 33 | March 2, 2026 8:00 AM | March 30, 2026 5:00 PM | 5600 | 5602 | Start No Earlier Than | 3/1/26 | 21 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12248 | Draft and distribute monthly communications products 34 | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM | 5601 | 5603 | Start No Earlier Than | 4/1/26 | 22 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12249 | Draft and distribute monthly communications products 35 | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM | 5602 | 5604 | Start No Earlier Than | 5/1/26 | 20 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12250 | Draft and distribute monthly communications products 36 | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 5603 | 5605 | Start No Earlier Than | 6/1/26 | 22 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12251 | Draft and distribute monthly communications products 37 | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 5604 | 5606 | Start No Earlier Than | 7/1/26 | 22 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12252 | Draft and distribute monthly communications products 38 | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM | 5605 | 5607 | Start No Earlier Than | 8/1/26 | 21 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12253 | Draft and distribute monthly communications products 39 | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 5606 | 5608 | Start No Earlier Than | 9/1/26 | 21 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
12254 | Draft and distribute monthly communications products 40 | October 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 5607 | 5621 | Start No Earlier Than | 10/1/26 | 17 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
10180 | Create communication plan for CWDA updates (potentially monthly decks for CWDA mtgs) | February 27, 2023 8:00 AM | March 13, 2023 5:00 PM | 3477FS+7d,5581 | 5621 | As Soon As Possible | NA | 11 | 0d | February 27, 2023 8:00 AM | March 13, 2023 5:00 PM | 11 days | No | 2/27/23 | 3/13/23 | NA | 1
10982 | Content Integration - Pilot | May 1, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | As Soon As Possible | NA | 67 | -40d | March 27, 2026 8:00 AM | June 19, 2026 5:00 PM | 59 days | No | NA | NA | NA | 0
10983 | Integrate Final Product Updates into Online Training Content | May 15, 2026 8:00 AM | July 16, 2026 5:00 PM | 1856FF-5d,4389,4401,4425,4436,4478,4493,4515,4526,4537,4560,4575,4590,4605,4629,4648,4659,4670,4693,4708,4720,4736,4463,4390,4402,4391,4403,4415,4426,4437 | 5629,5616 | As Soon As Possible | NA | 43 | -50d | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 43 days | No | NA | NA | NA | 0
10984 | Integrate Final Product Updates into ILT Content | May 15, 2026 8:00 AM | August 5, 2026 5:00 PM | 1856FF+8d,4389,4401,4425,4436,4478,4493,4515,4526,4537,4560,4575,4590,4605,4629,4648,4659,4670,4693,4708,4720,4736,4463,4390,4402,4391,4403,4415,4426,4437 | 5629,5617 | As Soon As Possible | NA | 57 | -49d | March 27, 2026 8:00 AM | June 17, 2026 5:00 PM | 57 days | No | NA | NA | NA | 0
10985 | Integrate Final Product Updates into To-Be Processes | May 1, 2026 8:00 AM | June 19, 2026 5:00 PM | 1856FF+10d,5383,5389,5395,5401,5407,5420,5426,5434,5441,5449,5457,5463,5469,5475,5483,5511,5517,5525,5414 | 5629 | As Soon As Possible | NA | 35 | 73d | May 1, 2026 8:00 AM | June 19, 2026 5:00 PM | 35 days | No | NA | NA | NA | 0
10986 | Training, Pilot, and Production Execution | January 28, 2026 8:00 AM | December 15, 2026 5:00 PM |  |  | As Soon As Possible | NA | 222 | 68d | February 3, 2026 8:00 AM | October 26, 2026 5:00 PM | 185 days | No | NA | NA | NA | 0
10987 | Training Delivery | July 17, 2026 8:00 AM | December 14, 2026 5:00 PM |  |  | As Soon As Possible | NA | 103 | -50d | June 2, 2026 8:00 AM | October 23, 2026 5:00 PM | 102 days | No | NA | NA | NA | 0
10988 | Deliver Self Paced Online Training | July 17, 2026 8:00 AM | November 30, 2026 5:00 PM | 5611 | 5624SS+5d,5617SS+15d | As Soon As Possible | NA | 93 | -50d | June 2, 2026 8:00 AM | July 14, 2026 5:00 PM | 30 days | No | NA | NA | NA | 0
10989 | Deliver TTT Training | August 7, 2026 8:00 AM | September 17, 2026 5:00 PM | 5616SS+15d,5612 | 5624,5618,3873SS | As Soon As Possible | NA | 29 | -50d | June 18, 2026 8:00 AM | July 30, 2026 5:00 PM | 30 days | No | NA | NA | NA | 0
10990 | Deliver ILT | September 18, 2026 8:00 AM | December 14, 2026 5:00 PM | 5617,1904,1905,534,554,562 | 5620FF,5619FF | As Soon As Possible | NA | 59 | -32d | July 31, 2026 8:00 AM | October 23, 2026 5:00 PM | 60 days | No | NA | NA | NA | 0
10991 | Deliver Refresher Training | December 1, 2026 8:00 AM | December 14, 2026 5:00 PM | 5618FF | 5620FS-40d | As Soon As Possible | NA | 10 | -32d | October 12, 2026 8:00 AM | October 23, 2026 5:00 PM | 10 days | No | NA | NA | NA | 0
10992 | Complete Final Sandbox Participation | October 15, 2026 8:00 AM | December 14, 2026 5:00 PM | 5618FF,5619FS-40d | 5630 | As Soon As Possible | NA | 40 | -32d | August 28, 2026 8:00 AM | October 23, 2026 5:00 PM | 40 days | No | NA | NA | NA | 0
10288 | Go-Live | October 26, 2026 8:00 AM | October 26, 2026 5:00 PM | 5010,5055,5057,5097,5155,5220,5233,5274,5609,5557,5257,5608,5564 |  | As Soon As Possible | NA | 1 | 239d | October 26, 2026 8:00 AM | October 26, 2026 5:00 PM | 1 | No | NA | NA | NA | 0
10993 | Pilot Execution | January 28, 2026 8:00 AM | December 14, 2026 5:00 PM |  |  | As Soon As Possible | NA | 221 | -48d | February 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 184 days | No | NA | NA | NA | 0
10994 | Set-up Pilot Infrastructure | January 28, 2026 8:00 AM | April 23, 2026 5:00 PM | 562,564,554,1855FS-73d | 5626 | As Soon As Possible | NA | 60 | 73d | February 3, 2026 8:00 AM | April 29, 2026 5:00 PM | 60 days | No | NA | NA | NA | 0
10995 | Conduct Pilot Users' Training | September 18, 2026 8:00 AM | October 15, 2026 5:00 PM | 5616SS+5d,5617 | 5626,5625SS+8d | As Soon As Possible | NA | 20 | -49d | July 31, 2026 8:00 AM | August 27, 2026 5:00 PM | 20 days | No | NA | NA | NA | 0
10996 | Pilot Readiness Review and Go-No-Go Decision | September 30, 2026 8:00 AM | October 13, 2026 5:00 PM | 2415,2416,2417FS+5d,2438,2440,2442,5624SS+8d | 5626 | As Soon As Possible | NA | 10 | -47d | August 27, 2026 5:00 PM | August 27, 2026 5:00 PM | 0 days | No | NA | NA | NA | 0
10997 | Conduct Pilot | October 16, 2026 8:00 AM | November 30, 2026 5:00 PM | 5623,5625,5624 | 5627,5628,3875SS | As Soon As Possible | NA | 29 | -49d | August 28, 2026 8:00 AM | October 9, 2026 5:00 PM | 30 days | No | NA | NA | NA | 0
10998 | Pilot Remediation | December 1, 2026 8:00 AM | December 14, 2026 5:00 PM | 5626 | 5629 | As Soon As Possible | NA | 10 | -48d | October 12, 2026 8:00 AM | October 23, 2026 5:00 PM | 10 days | No | NA | NA | NA | 0
10999 | Production Readiness Review and Go-No-Go Decision | December 1, 2026 8:00 AM | December 14, 2026 5:00 PM | 5626,3049,2983,2152,1859 | 5629FS+1d,5630 | As Soon As Possible | NA | 10 | -49d | October 12, 2026 8:00 AM | October 23, 2026 5:00 PM | 10 days | No | NA | NA | NA | 0
11000 | Production Execution | December 15, 2026 5:00 PM | December 15, 2026 5:00 PM | 5627,5628FS+1d,5611,5612,5613,5361FS-43d | 5630,3886 | As Soon As Possible | NA | 0 | -49d | October 26, 2026 5:00 PM | October 26, 2026 5:00 PM | 0 days | Yes | NA | NA | NA | 0
6686 | Go-Live CWS-CARES V1 | October 26, 2026 5:00 PM | October 26, 2026 5:00 PM | 5629,5628,5620,2392,1855,4840,4841,4874,5306,5549,4883,4954,5372,5373,5026,5146,5215,5276,5330,5526,5539,5566,5642 | 5643FS+4d | Must Finish On | 10/26/26 | 0 | -33d | October 26, 2026 5:00 PM | October 26, 2026 5:00 PM | 0 days | Yes | NA | NA | NA | 0
23981 | Implementation - CW - Counties | April 1, 2021 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 1443 | 195d | NA | NA | 0 days? | No | 4/1/21 | NA | NA | 0.33000000000000002
23982 | CARES V1 - Alameda CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.29999999999999999
23983 | Alameda CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
23984 | Alameda CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 6d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
23985 | Alameda CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  | 5636 | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
23986 | Alameda CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM | 5635 | 5637 | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
23987 | Alameda CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM | 5636 | 5638 | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
23988 | Alameda CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM | 5637 | 5639 | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
23989 | Alameda CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 5638 | 5640 | Start No Earlier Than | 1/2/26 | 40 | 68d | NA | NA | 0 days? | No | NA | NA | NA | 0
23990 | Alameda CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM | 5639 | 5641 | Start No Earlier Than | 4/1/26 | 43 | 48d | NA | NA | 0 days? | No | NA | NA | NA | 0
23991 | Alameda CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM | 5640 | 5642 | Start No Earlier Than | 7/1/26 | 43 | 27d | NA | NA | 0 days? | No | NA | NA | NA | 0
23992 | Alameda CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM | 5641 | 5630 | Start No Earlier Than | 10/1/26 | 12 | 6d | NA | NA | 0 days? | No | NA | NA | NA | 0
23993 | Alameda CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 5630FS+4d |  | As Soon As Possible | NA | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
23994 | Alameda CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
23995 | Alameda CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
23996 | Alameda CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
23997 | Alameda CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
23998 | Alameda CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
23999 | Alameda CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
24000 | Alameda CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
24001 | Alameda CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
24002 | Alameda CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
24003 | Alameda CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
24004 | Alameda CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
24005 | Alameda CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
24006 | Alameda CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
24007 | Alameda CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
24008 | Alameda CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
24009 | Alameda CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
24010 | Alameda CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
24011 | Alameda CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
24012 | Alameda CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
24013 | Alameda CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
24014 | Alameda CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
24015 | Alameda CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
24016 | Alameda CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
24017 | Alameda CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
24018 | Alameda CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
24019 | Alameda CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
24020 | Alameda CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
24021 | Alameda CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
24022 | Alameda CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
24023 | Alameda CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
24024 | Alameda CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
24025 | Alameda CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24026 | Alameda CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24027 | Alameda CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
24028 | Alameda CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24029 | Alameda CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
24030 | Alameda CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
24031 | Alameda CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
24032 | Alameda CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
24033 | Alameda CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
24034 | Alameda CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
24035 | Alameda CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
24036 | Alameda CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
24037 | Alameda CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 5688SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
24038 | Alameda CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 5687SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
24039 | Alameda CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 5690SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24040 | Alameda CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 5689SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24041 | Alameda CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
24042 | Alameda CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 5693SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
24043 | Alameda CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 5692SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
24044 | Alameda CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24045 | Alameda CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 5696SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
24046 | Alameda CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 5695SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
24047 | Alameda CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24048 | Alameda CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 5699SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24049 | Alameda CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 5698SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24050 | Alameda CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24051 | Alameda CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 5702SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
24052 | Alameda CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 5701SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
24053 | Alameda CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
24054 | Alameda CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.32000000000000001
24055 | Alameda CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
24056 | Alameda CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 5707 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
24057 | Alameda CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 5706 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
24058 | Alameda CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
24059 | Alameda CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
24060 | Alameda CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
24061 | Alameda CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24062 | Alameda CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 5713 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
24063 | Alameda CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 5712 | 5714 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
24064 | Alameda CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 5713 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
24065 | Alameda CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24066 | Alameda CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals (if | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 5717 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
24067 | Alameda CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 5716 | 5718 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
24068 | Alameda CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 5717 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24069 | Alameda CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24070 | Alameda CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 5721 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
24071 | Alameda CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 5720 | 5722 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24072 | Alameda CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 5721 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24073 | Alameda CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24074 | Alameda CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 5725 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24075 | Alameda CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 5724 | 5726 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24076 | Alameda CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 5725 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24077 | Alameda CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24078 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24079 | Alameda CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.39000000000000001
24080 | Alameda CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.67000000000000004
24081 | Alameda CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 5732SS | As Soon As Possible | NA | 490 | 405d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.80000000000000004
24082 | Alameda CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 5731SS | 5733 | As Soon As Possible | NA | 490 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.59999999999999998
24083 | Alameda CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 5732 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24084 | Alameda CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
24085 | Alameda CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
24086 | Alameda CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
24087 | Alameda CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 5739 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
24088 | Alameda CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.68999999999999995
24089 | Alameda CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 5737 | 5740,5742SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
24090 | Alameda CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 5739 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
24091 | Alameda CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
24092 | Alameda CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 5739SS | 5743SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
24093 | Alameda CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 5742SS | 5744,5747,5745SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
24094 | Alameda CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 5743 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24095 | Alameda CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 5743SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24096 | Alameda CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24097 | Alameda CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 5743 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
24098 | Alameda CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.65000000000000002
24099 | Alameda CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 5750SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
24100 | Alameda CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 5749SS | 5751SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.59999999999999998
24101 | Alameda CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 5750SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.40000000000000002
24102 | Alameda CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
24103 | Alameda CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
24104 | Alameda CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 5760 | 5755SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
24105 | Alameda CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 5754SS | 5757 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
24106 | Alameda CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 508d | NA | NA | 0 days? | No | 7/21/25 | NA | NA | 0.67000000000000004
24107 | Alameda CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 5755 | 5758 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
24108 | Alameda CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 5757 |  | As Soon As Possible | NA | 21 | 508d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
24109 | Alameda CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
24110 | Alameda CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 5754,5761SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
24111 | Alameda CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 5760SS | 5765,5762 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
24112 | Alameda CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 5761 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24113 | Alameda CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
24114 | Alameda CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24115 | Alameda CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 5761 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
24116 | Alameda CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24117 | Alameda CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24118 | Alameda CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24119 | Alameda CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24120 | Alameda CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24121 | Alameda CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24122 | Alameda CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24123 | Alameda CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24124 | Alameda CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24125 | Alameda CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24126 | Alameda CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24127 | Alameda CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24128 | Alameda CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
24129 | Alameda CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
24130 | Alameda CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 5787 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
24131 | Alameda CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
24132 | Alameda CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
24133 | Alameda CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24134 | Alameda CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24135 | Alameda CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 5794 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24136 | Alameda CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 5795 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24137 | Alameda CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 5780 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
24138 | Alameda CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24139 | Alameda CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 5800SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24140 | Alameda CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 5801SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24141 | Alameda CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 5802SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24142 | Alameda CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 5803SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24143 | Alameda CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 5804SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24144 | Alameda CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 5785 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24145 | Alameda CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 5786 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24146 | Alameda CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
24147 | Alameda CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 5806FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24148 | Alameda CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
24149 | Alameda CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 5806SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
24150 | Alameda CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 5789SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24151 | Alameda CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 5790SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24152 | Alameda CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 5791SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24153 | Alameda CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 5792SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24154 | Alameda CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 5793SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24155 | Alameda CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24156 | Alameda CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 5797FS+12d,5799SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24157 | CARES V1 - Alpine CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.34999999999999998
24158 | Alpine CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
24159 | Alpine CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
24160 | Alpine CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
24161 | Alpine CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
24162 | Alpine CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
24163 | Alpine CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
24164 | Alpine CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24165 | Alpine CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
24166 | Alpine CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
24167 | Alpine CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
24168 | Alpine CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
24169 | Alpine CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.40000000000000002
24170 | Alpine CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.65000000000000002
24171 | Alpine CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
24172 | Alpine CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
24173 | Alpine CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
24174 | Alpine CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
24175 | Alpine CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
24176 | Alpine CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
24177 | Alpine CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
24178 | Alpine CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
24179 | Alpine CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
24180 | Alpine CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
24181 | Alpine CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
24182 | Alpine CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
24183 | Alpine CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
24184 | Alpine CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
24185 | Alpine CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
24186 | Alpine CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
24187 | Alpine CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
24188 | Alpine CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
24189 | Alpine CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
24190 | Alpine CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
24191 | Alpine CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
24192 | Alpine CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/30/25 | NA | 1
24193 | Alpine CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
24194 | Alpine CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
24195 | Alpine CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
24196 | Alpine CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
24197 | Alpine CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
24198 | Alpine CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
24199 | Alpine CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
24200 | Alpine CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24201 | Alpine CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24202 | Alpine CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
24203 | Alpine CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24204 | Alpine CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
24205 | Alpine CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
24206 | Alpine CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
24207 | Alpine CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
24208 | Alpine CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
24209 | Alpine CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
24210 | Alpine CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
24211 | Alpine CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
24212 | Alpine CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 5863SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
24213 | Alpine CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 5862SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
24214 | Alpine CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 5865SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24215 | Alpine CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 5864SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24216 | Alpine CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
24217 | Alpine CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 5868SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
24218 | Alpine CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 5867SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
24219 | Alpine CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24220 | Alpine CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 5871SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
24221 | Alpine CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 5870SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
24222 | Alpine CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24223 | Alpine CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 5874SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24224 | Alpine CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 5873SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24225 | Alpine CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24226 | Alpine CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 5877SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
24227 | Alpine CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 5876SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
24228 | Alpine CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
24229 | Alpine CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.34000000000000002
24230 | Alpine CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
24231 | Alpine CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 5882 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
24232 | Alpine CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 5881 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
24233 | Alpine CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
24234 | Alpine CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
24235 | Alpine CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
24236 | Alpine CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24237 | Alpine CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 5888 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
24238 | Alpine CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 5887 | 5889 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
24239 | Alpine CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 5888 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
24240 | Alpine CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24241 | Alpine CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals (if | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 5892 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
24242 | Alpine CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 5891 | 5893 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
24243 | Alpine CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 5892 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24244 | Alpine CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24245 | Alpine CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 5896 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.59999999999999998
24246 | Alpine CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 5895 | 5897 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24247 | Alpine CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 5896 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24248 | Alpine CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24249 | Alpine CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 5900 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24250 | Alpine CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 5899 | 5901 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24251 | Alpine CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 5900 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24252 | Alpine CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24253 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24254 | Alpine CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.46999999999999997
24255 | Alpine CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
24256 | Alpine CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 5907SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
24257 | Alpine CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 5906SS | 5908 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
24258 | Alpine CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 5907 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24259 | Alpine CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
24260 | Alpine CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
24261 | Alpine CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
24262 | Alpine CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 5914 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
24263 | Alpine CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.60999999999999999
24264 | Alpine CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 5912 | 5915,5917SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
24265 | Alpine CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 5914 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
24266 | Alpine CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
24267 | Alpine CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 5914SS | 5918SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
24268 | Alpine CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 5917SS | 5919,5922,5920SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
24269 | Alpine CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 5918 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24270 | Alpine CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 5918SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24271 | Alpine CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24272 | Alpine CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 5918 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
24273 | Alpine CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.70999999999999996
24274 | Alpine CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 5925SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.94999999999999996
24275 | Alpine CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 5924SS | 5926SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.59999999999999998
24276 | Alpine CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 5925SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.59999999999999998
24277 | Alpine CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
24278 | Alpine CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
24279 | Alpine CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 5935 | 5930SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
24280 | Alpine CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 5929SS | 5932 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
24281 | Alpine CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
24282 | Alpine CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 5930 | 5933 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
24283 | Alpine CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 5932 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
24284 | Alpine CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.27000000000000002
24285 | Alpine CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 5929,5936SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
24286 | Alpine CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 5935SS | 5940,5937 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.40000000000000002
24287 | Alpine CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 5936 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24288 | Alpine CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
24289 | Alpine CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24290 | Alpine CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 5936 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
24291 | Alpine CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24292 | Alpine CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24293 | Alpine CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24294 | Alpine CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24295 | Alpine CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24296 | Alpine CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24297 | Alpine CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24298 | Alpine CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24299 | Alpine CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24300 | Alpine CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24301 | Alpine CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24302 | Alpine CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24303 | Alpine CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
24304 | Alpine CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 5.0000000000000003E-2
24305 | Alpine CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 5962 | Start No Earlier Than | 7/1/25 | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.59999999999999998
24306 | Alpine CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
24307 | Alpine CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
24308 | Alpine CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24309 | Alpine CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24310 | Alpine CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 5969 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24311 | Alpine CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 5970 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24312 | Alpine CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 5955 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
24313 | Alpine CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24314 | Alpine CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 5975SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24315 | Alpine CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 5976SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24316 | Alpine CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 5977SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24317 | Alpine CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 5978SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24318 | Alpine CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 5979SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24319 | Alpine CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 5960 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24320 | Alpine CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 5961 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24321 | Alpine CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
24322 | Alpine CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 5981FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24323 | Alpine CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
24324 | Alpine CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 5981SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
24325 | Alpine CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 5964SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24326 | Alpine CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 5965SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24327 | Alpine CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 5966SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24328 | Alpine CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 5967SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24329 | Alpine CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 5968SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24330 | Alpine CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24331 | Alpine CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 5972FS+12d,5974SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24332 | CARES V1 - Amador CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.28999999999999998
24333 | Amador CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
24334 | Amador CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
24335 | Amador CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
24336 | Amador CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
24337 | Amador CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
24338 | Amador CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
24339 | Amador CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24340 | Amador CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
24341 | Amador CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
24342 | Amador CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
24343 | Amador CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
24344 | Amador CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
24345 | Amador CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.65000000000000002
24346 | Amador CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
24347 | Amador CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
24348 | Amador CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
24349 | Amador CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
24350 | Amador CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
24351 | Amador CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
24352 | Amador CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
24353 | Amador CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
24354 | Amador CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
24355 | Amador CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
24356 | Amador CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
24357 | Amador CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
24358 | Amador CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
24359 | Amador CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
24360 | Amador CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
24361 | Amador CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
24362 | Amador CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
24363 | Amador CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
24364 | Amador CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
24365 | Amador CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
24366 | Amador CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
24367 | Amador CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/30/25 | NA | 1
24368 | Amador CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
24369 | Amador CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
24370 | Amador CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
24371 | Amador CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
24372 | Amador CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
24373 | Amador CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
24374 | Amador CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
24375 | Amador CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24376 | Amador CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24377 | Amador CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
24378 | Amador CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24379 | Amador CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
24380 | Amador CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
24381 | Amador CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
24382 | Amador CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
24383 | Amador CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
24384 | Amador CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
24385 | Amador CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
24386 | Amador CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
24387 | Amador CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 6038SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
24388 | Amador CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 6037SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
24389 | Amador CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 6040SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24390 | Amador CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 6039SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24391 | Amador CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
24392 | Amador CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 6043SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
24393 | Amador CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 6042SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
24394 | Amador CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24395 | Amador CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 6046SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
24396 | Amador CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 6045SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
24397 | Amador CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24398 | Amador CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 6049SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24399 | Amador CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 6048SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24400 | Amador CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24401 | Amador CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 6052SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
24402 | Amador CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 6051SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
24403 | Amador CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
24404 | Amador CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.34000000000000002
24405 | Amador CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
24406 | Amador CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 6057 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
24407 | Amador CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 6056 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
24408 | Amador CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
24409 | Amador CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
24410 | Amador CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
24411 | Amador CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24412 | Amador CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 6063 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
24413 | Amador CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 6062 | 6064 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
24414 | Amador CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 6063 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
24415 | Amador CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24416 | Amador CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals (if | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 6067 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
24417 | Amador CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 6066 | 6068 | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
24418 | Amador CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 6067 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24419 | Amador CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24420 | Amador CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 6071 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24421 | Amador CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 6070 | 6072 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24422 | Amador CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 6071 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24423 | Amador CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24424 | Amador CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 6075 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24425 | Amador CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 6074 | 6076 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24426 | Amador CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 6075 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24427 | Amador CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24428 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24429 | Amador CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.34999999999999998
24430 | Amador CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.56999999999999995
24431 | Amador CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 6082SS | Start No Earlier Than | 3/19/24 | 490 | 405d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.59999999999999998
24432 | Amador CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 6081SS | 6083 | As Soon As Possible | NA | 490 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.59999999999999998
24433 | Amador CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 6082 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24434 | Amador CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
24435 | Amador CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
24436 | Amador CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
24437 | Amador CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 6089 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
24438 | Amador CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.60999999999999999
24439 | Amador CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 6087 | 6090,6092SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
24440 | Amador CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 6089 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
24441 | Amador CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
24442 | Amador CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 6089SS | 6093SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
24443 | Amador CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 6092SS | 6094,6097,6095SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
24444 | Amador CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 6093 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24445 | Amador CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 6093SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24446 | Amador CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24447 | Amador CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 6093 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
24448 | Amador CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.54000000000000004
24449 | Amador CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 6100SS | Start No Earlier Than | 2/3/25 | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.40000000000000002
24450 | Amador CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 6099SS | 6101SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.59999999999999998
24451 | Amador CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 6100SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.59999999999999998
24452 | Amador CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
24453 | Amador CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
24454 | Amador CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 6110 | 6105SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
24455 | Amador CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 6104SS | 6107 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
24456 | Amador CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
24457 | Amador CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 6105 | 6108 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
24458 | Amador CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 6107 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
24459 | Amador CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
24460 | Amador CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 6104,6111SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
24461 | Amador CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 6110SS | 6115,6112 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
24462 | Amador CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 6111 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24463 | Amador CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
24464 | Amador CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24465 | Amador CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 6111 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
24466 | Amador CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24467 | Amador CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24468 | Amador CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24469 | Amador CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24470 | Amador CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24471 | Amador CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24472 | Amador CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24473 | Amador CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24474 | Amador CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24475 | Amador CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24476 | Amador CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24477 | Amador CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24478 | Amador CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
24479 | Amador CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 5.0000000000000003E-2
24480 | Amador CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 6137 | Start No Earlier Than | 7/1/25 | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.59999999999999998
24481 | Amador CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
24482 | Amador CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
24483 | Amador CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24484 | Amador CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24485 | Amador CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 6144 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24486 | Amador CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 6145 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24487 | Amador CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 6130 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
24488 | Amador CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24489 | Amador CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6150SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24490 | Amador CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6151SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24491 | Amador CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6152SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24492 | Amador CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6153SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24493 | Amador CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6154SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24494 | Amador CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 6135 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24495 | Amador CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 6136 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24496 | Amador CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
24497 | Amador CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 6156FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24498 | Amador CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
24499 | Amador CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 6156SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
24500 | Amador CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6139SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24501 | Amador CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6140SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24502 | Amador CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6141SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24503 | Amador CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6142SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24504 | Amador CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6143SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24505 | Amador CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24506 | Amador CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 6147FS+12d,6149SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24507 | CARES V1 - Colusa CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.28999999999999998
24508 | Colusa CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
24509 | Colusa CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
24510 | Colusa CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
24511 | Colusa CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
24512 | Colusa CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
24513 | Colusa CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
24514 | Colusa CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24515 | Colusa CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
24516 | Colusa CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
24517 | Colusa CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
24518 | Colusa CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
24519 | Colusa CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
24520 | Colusa CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
24521 | Colusa CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
24522 | Colusa CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
24523 | Colusa CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
24524 | Colusa CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
24525 | Colusa CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
24526 | Colusa CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
24527 | Colusa CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
24528 | Colusa CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
24529 | Colusa CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
24530 | Colusa CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
24531 | Colusa CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
24532 | Colusa CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
24533 | Colusa CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
24534 | Colusa CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
24535 | Colusa CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
24536 | Colusa CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
24537 | Colusa CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
24538 | Colusa CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
24539 | Colusa CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
24540 | Colusa CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
24541 | Colusa CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
24542 | Colusa CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
24543 | Colusa CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
24544 | Colusa CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
24545 | Colusa CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
24546 | Colusa CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
24547 | Colusa CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
24548 | Colusa CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
24549 | Colusa CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
24550 | Colusa CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24551 | Colusa CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24552 | Colusa CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
24553 | Colusa CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24554 | Colusa CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
24555 | Colusa CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
24556 | Colusa CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
24557 | Colusa CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
24558 | Colusa CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
24559 | Colusa CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
24560 | Colusa CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
24561 | Colusa CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
24562 | Colusa CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 6213SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
24563 | Colusa CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 6212SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
24564 | Colusa CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 6215SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24565 | Colusa CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 6214SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24566 | Colusa CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
24567 | Colusa CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 6218SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
24568 | Colusa CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 6217SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
24569 | Colusa CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24570 | Colusa CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 6221SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
24571 | Colusa CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 6220SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
24572 | Colusa CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24573 | Colusa CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 6224SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24574 | Colusa CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 6223SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24575 | Colusa CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24576 | Colusa CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 6227SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
24577 | Colusa CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 6226SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
24578 | Colusa CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
24579 | Colusa CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.52000000000000002
24580 | Colusa CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
24581 | Colusa CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 6232 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
24582 | Colusa CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 6231 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
24583 | Colusa CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
24584 | Colusa CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
24585 | Colusa CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
24586 | Colusa CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24587 | Colusa CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OC | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 6238 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
24588 | Colusa CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 6237 | 6239 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
24589 | Colusa CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 6238 |  | As Soon As Possible | NA | 63 | 0d | NA | NA | 0 days? | No | 9/2/25 | 12/1/25 | NA | 1
24590 | Colusa CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24591 | Colusa CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 6242 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
24592 | Colusa CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 6241 | 6243 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24593 | Colusa CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 6242 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24594 | Colusa CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24595 | Colusa CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 6246 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
24596 | Colusa CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 6245 | 6247 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24597 | Colusa CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 6246 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24598 | Colusa CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24599 | Colusa CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 6250 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24600 | Colusa CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 6249 | 6251 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24601 | Colusa CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 6250 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24602 | Colusa CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24603 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24604 | Colusa CW-Technical | January 1, 2025 8:00 AM | July 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 382 | 314d | NA | NA | 0 days? | No | 1/1/25 | NA | NA | 0.31
24605 | Colusa CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
24606 | Colusa CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
24607 | Colusa CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
24608 | Colusa CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 6260 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
24609 | Colusa CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
24610 | Colusa CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 6258 | 6261 | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
24611 | Colusa CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 6260 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
24612 | Colusa CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
24613 | Colusa CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
24614 | Colusa CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 6265SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
24615 | Colusa CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 6264SS | 6267 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
24616 | Colusa CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
24617 | Colusa CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 6265 | 6268 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
24618 | Colusa CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 6267 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
24619 | Colusa CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24620 | Colusa CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24621 | Colusa CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24622 | Colusa CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24623 | Colusa CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24624 | Colusa CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24625 | Colusa CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24626 | Colusa CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24627 | Colusa CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24628 | Colusa CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24629 | Colusa CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24630 | Colusa CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24631 | Colusa CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
24632 | Colusa CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
24633 | Colusa CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 6290 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
24634 | Colusa CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
24635 | Colusa CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
24636 | Colusa CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24637 | Colusa CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24638 | Colusa CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 6297 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24639 | Colusa CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 6298 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24640 | Colusa CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 6283 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
24641 | Colusa CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24642 | Colusa CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6303SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24643 | Colusa CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6304SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24644 | Colusa CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6305SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24645 | Colusa CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6306SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24646 | Colusa CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6307SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24647 | Colusa CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 6288 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24648 | Colusa CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 6289 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24649 | Colusa CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
24650 | Colusa CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 6309FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24651 | Colusa CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
24652 | Colusa CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 6309SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
24653 | Colusa CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6292SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24654 | Colusa CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6293SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24655 | Colusa CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6294SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24656 | Colusa CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6295SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24657 | Colusa CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6296SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24658 | Colusa CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24659 | Colusa CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 6300FS+12d,6302SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24660 | CARES V1 - Contra Costa CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.34999999999999998
24661 | Contra Costa CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
24662 | Contra Costa CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
24663 | Contra Costa CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
24664 | Contra Costa CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
24665 | Contra Costa CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
24666 | Contra Costa CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
24667 | Contra Costa CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24668 | Contra Costa CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
24669 | Contra Costa CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
24670 | Contra Costa CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
24671 | Contra Costa CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
24672 | Contra Costa CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
24673 | Contra Costa CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
24674 | Contra Costa CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
24675 | Contra Costa CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
24676 | Contra Costa CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
24677 | Contra Costa CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
24678 | Contra Costa CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
24679 | Contra Costa CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
24680 | Contra Costa CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
24681 | Contra Costa CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
24682 | Contra Costa CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
24683 | Contra Costa CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
24684 | Contra Costa CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
24685 | Contra Costa CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
24686 | Contra Costa CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
24687 | Contra Costa CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
24688 | Contra Costa CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
24689 | Contra Costa CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
24690 | Contra Costa CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
24691 | Contra Costa CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
24692 | Contra Costa CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
24693 | Contra Costa CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
24694 | Contra Costa CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
24695 | Contra Costa CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
24696 | Contra Costa CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
24697 | Contra Costa CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
24698 | Contra Costa CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
24699 | Contra Costa CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
24700 | Contra Costa CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
24701 | Contra Costa CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
24702 | Contra Costa CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
24703 | Contra Costa CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24704 | Contra Costa CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24705 | Contra Costa CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
24706 | Contra Costa CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24707 | Contra Costa CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
24708 | Contra Costa CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
24709 | Contra Costa CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
24710 | Contra Costa CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
24711 | Contra Costa CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
24712 | Contra Costa CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
24713 | Contra Costa CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
24714 | Contra Costa CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
24715 | Contra Costa CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 6366SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
24716 | Contra Costa CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 6365SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
24717 | Contra Costa CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 6368SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24718 | Contra Costa CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 6367SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24719 | Contra Costa CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
24720 | Contra Costa CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 6371SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
24721 | Contra Costa CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 6370SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
24722 | Contra Costa CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24723 | Contra Costa CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 6374SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
24724 | Contra Costa CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 6373SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
24725 | Contra Costa CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24726 | Contra Costa CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 6377SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24727 | Contra Costa CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 6376SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24728 | Contra Costa CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24729 | Contra Costa CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 6380SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
24730 | Contra Costa CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 6379SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
24731 | Contra Costa CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
24732 | Contra Costa CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.46999999999999997
24733 | Contra Costa CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
24734 | Contra Costa CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 6385 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
24735 | Contra Costa CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 6384 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
24736 | Contra Costa CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
24737 | Contra Costa CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
24738 | Contra Costa CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
24739 | Contra Costa CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24740 | Contra Costa CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 6391 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
24741 | Contra Costa CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 6390 | 6392 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
24742 | Contra Costa CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 6391 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
24743 | Contra Costa CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24744 | Contra Costa CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 6395 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
24745 | Contra Costa CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 6394 | 6396 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24746 | Contra Costa CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 6395 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24747 | Contra Costa CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24748 | Contra Costa CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 6399 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
24749 | Contra Costa CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 6398 | 6400 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24750 | Contra Costa CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 6399 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24751 | Contra Costa CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24752 | Contra Costa CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 6403 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24753 | Contra Costa CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 6402 | 6404 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24754 | Contra Costa CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 6403 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24755 | Contra Costa CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24756 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24757 | Contra Costa CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.45000000000000001
24758 | Contra Costa CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.89000000000000001
24759 | Contra Costa CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 6410SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
24760 | Contra Costa CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 6409SS | 6411 | As Soon As Possible | NA | 490 | 28.8d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.80000000000000004
24761 | Contra Costa CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 6410 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.59999999999999998
24762 | Contra Costa CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
24763 | Contra Costa CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
24764 | Contra Costa CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
24765 | Contra Costa CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 6417 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
24766 | Contra Costa CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
24767 | Contra Costa CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 6415 | 6418,6420SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
24768 | Contra Costa CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 6417 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
24769 | Contra Costa CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
24770 | Contra Costa CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 6417SS | 6421SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
24771 | Contra Costa CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 6420SS | 6422,6425,6423SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
24772 | Contra Costa CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 6421 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24773 | Contra Costa CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 6421SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24774 | Contra Costa CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24775 | Contra Costa CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 6421 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
24776 | Contra Costa CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.69999999999999996
24777 | Contra Costa CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 6428SS | Start No Earlier Than | 2/3/25 | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
24778 | Contra Costa CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 6427SS | 6429SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
24779 | Contra Costa CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 6428SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
24780 | Contra Costa CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
24781 | Contra Costa CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
24782 | Contra Costa CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 6438 | 6433SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
24783 | Contra Costa CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 6432SS | 6435 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
24784 | Contra Costa CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
24785 | Contra Costa CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 6433 | 6436 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
24786 | Contra Costa CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 6435 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
24787 | Contra Costa CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
24788 | Contra Costa CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 6432,6439SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
24789 | Contra Costa CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 6438SS | 6443,6440 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
24790 | Contra Costa CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 6439 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24791 | Contra Costa CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
24792 | Contra Costa CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24793 | Contra Costa CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 6439 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
24794 | Contra Costa CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24795 | Contra Costa CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24796 | Contra Costa CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24797 | Contra Costa CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24798 | Contra Costa CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24799 | Contra Costa CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24800 | Contra Costa CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24801 | Contra Costa CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24802 | Contra Costa CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24803 | Contra Costa CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24804 | Contra Costa CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24805 | Contra Costa CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24806 | Contra Costa CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
24807 | Contra Costa CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 2.9999999999999999E-2
24808 | Contra Costa CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 6465 | Start No Earlier Than | 7/1/25 | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
24809 | Contra Costa CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
24810 | Contra Costa CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
24811 | Contra Costa CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24812 | Contra Costa CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24813 | Contra Costa CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 6472 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24814 | Contra Costa CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 6473 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24815 | Contra Costa CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 6458 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
24816 | Contra Costa CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24817 | Contra Costa CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6478SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24818 | Contra Costa CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6479SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24819 | Contra Costa CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6480SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24820 | Contra Costa CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6481SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24821 | Contra Costa CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6482SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24822 | Contra Costa CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 6463 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24823 | Contra Costa CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 6464 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24824 | Contra Costa CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
24825 | Contra Costa CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 6484FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24826 | Contra Costa CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
24827 | Contra Costa CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 6484SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
24828 | Contra Costa CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6467SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24829 | Contra Costa CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6468SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24830 | Contra Costa CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6469SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24831 | Contra Costa CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6470SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24832 | Contra Costa CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6471SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24833 | Contra Costa CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24834 | Contra Costa CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 6475FS+12d,6477SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
24835 | CARES V1 - Del Norte CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.23000000000000001
24836 | Del Norte CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
24837 | Del Norte CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
24838 | Del Norte CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
24839 | Del Norte CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
24840 | Del Norte CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
24841 | Del Norte CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
24842 | Del Norte CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24843 | Del Norte CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
24844 | Del Norte CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
24845 | Del Norte CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
24846 | Del Norte CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
24847 | Del Norte CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.42999999999999999
24848 | Del Norte CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.65000000000000002
24849 | Del Norte CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
24850 | Del Norte CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
24851 | Del Norte CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
24852 | Del Norte CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
24853 | Del Norte CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
24854 | Del Norte CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
24855 | Del Norte CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
24856 | Del Norte CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
24857 | Del Norte CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
24858 | Del Norte CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
24859 | Del Norte CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
24860 | Del Norte CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
24861 | Del Norte CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
24862 | Del Norte CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
24863 | Del Norte CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
24864 | Del Norte CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
24865 | Del Norte CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
24866 | Del Norte CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
24867 | Del Norte CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
24868 | Del Norte CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
24869 | Del Norte CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
24870 | Del Norte CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/30/25 | NA | 1
24871 | Del Norte CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
24872 | Del Norte CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
24873 | Del Norte CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
24874 | Del Norte CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
24875 | Del Norte CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
24876 | Del Norte CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
24877 | Del Norte CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
24878 | Del Norte CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24879 | Del Norte CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24880 | Del Norte CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
24881 | Del Norte CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24882 | Del Norte CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
24883 | Del Norte CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
24884 | Del Norte CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
24885 | Del Norte CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
24886 | Del Norte CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
24887 | Del Norte CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
24888 | Del Norte CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
24889 | Del Norte CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.94999999999999996
24890 | Del Norte CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 6541SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
24891 | Del Norte CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 6540SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
24892 | Del Norte CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 6543SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24893 | Del Norte CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 6542SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24894 | Del Norte CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
24895 | Del Norte CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 6546SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
24896 | Del Norte CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 6545SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
24897 | Del Norte CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24898 | Del Norte CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 6549SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
24899 | Del Norte CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 6548SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
24900 | Del Norte CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24901 | Del Norte CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 6552SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24902 | Del Norte CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 6551SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
24903 | Del Norte CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
24904 | Del Norte CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 6555SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
24905 | Del Norte CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 6554SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
24906 | Del Norte CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
24907 | Del Norte CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.34000000000000002
24908 | Del Norte CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
24909 | Del Norte CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 6560 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
24910 | Del Norte CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 6559 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
24911 | Del Norte CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
24912 | Del Norte CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
24913 | Del Norte CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
24914 | Del Norte CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24915 | Del Norte CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 6566 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
24916 | Del Norte CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 6565 | 6567 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
24917 | Del Norte CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 6566 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
24918 | Del Norte CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24919 | Del Norte CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 6570 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
24920 | Del Norte CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 6569 | 6571 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24921 | Del Norte CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 6570 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24922 | Del Norte CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24923 | Del Norte CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 6574 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
24924 | Del Norte CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 6573 | 6575 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24925 | Del Norte CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 6574 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
24926 | Del Norte CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24927 | Del Norte CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 6578 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24928 | Del Norte CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 6577 | 6579 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24929 | Del Norte CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 6578 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24930 | Del Norte CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24931 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24932 | Del Norte CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.20000000000000001
24933 | Del Norte CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24934 | Del Norte CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 6585SS | Start No Earlier Than | 3/19/24 | 490 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24935 | Del Norte CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 6584SS | 6586 | As Soon As Possible | NA | 490 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24936 | Del Norte CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 6585 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24937 | Del Norte CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
24938 | Del Norte CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
24939 | Del Norte CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
24940 | Del Norte CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
24941 | Del Norte CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 6592,6594SS | Start No Earlier Than | 8/11/25 | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
24942 | Del Norte CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 6591 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
24943 | Del Norte CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
24944 | Del Norte CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 6591SS | 6595SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
24945 | Del Norte CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 6594SS | 6596,6599,6597SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24946 | Del Norte CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 6595 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24947 | Del Norte CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 6595SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24948 | Del Norte CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24949 | Del Norte CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 6595 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
24950 | Del Norte CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.62
24951 | Del Norte CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 6602SS | Start No Earlier Than | 2/3/25 | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
24952 | Del Norte CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 6601SS | 6603SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
24953 | Del Norte CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 6602SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
24954 | Del Norte CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
24955 | Del Norte CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
24956 | Del Norte CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 6612 | 6607SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
24957 | Del Norte CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 6606SS | 6609 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
24958 | Del Norte CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
24959 | Del Norte CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 6607 | 6610 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
24960 | Del Norte CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 6609 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
24961 | Del Norte CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
24962 | Del Norte CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 6606,6613SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
24963 | Del Norte CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 6612SS | 6617,6614 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24964 | Del Norte CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 6613 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24965 | Del Norte CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
24966 | Del Norte CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
24967 | Del Norte CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 6613 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
24968 | Del Norte CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24969 | Del Norte CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24970 | Del Norte CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24971 | Del Norte CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24972 | Del Norte CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24973 | Del Norte CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24974 | Del Norte CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24975 | Del Norte CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24976 | Del Norte CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24977 | Del Norte CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24978 | Del Norte CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24979 | Del Norte CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
24980 | Del Norte CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
24981 | Del Norte CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
24982 | Del Norte CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 6639 | Start No Earlier Than | 7/1/25 | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
24983 | Del Norte CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
24984 | Del Norte CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
24985 | Del Norte CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24986 | Del Norte CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
24987 | Del Norte CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 6646 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24988 | Del Norte CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 6647 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24989 | Del Norte CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 6632 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
24990 | Del Norte CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
24991 | Del Norte CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6652SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24992 | Del Norte CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6653SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24993 | Del Norte CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6654SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24994 | Del Norte CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6655SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24995 | Del Norte CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6656SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
24996 | Del Norte CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 6637 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24997 | Del Norte CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 6638 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
24998 | Del Norte CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
24999 | Del Norte CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 6658FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25000 | Del Norte CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
25001 | Del Norte CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 6658SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
25002 | Del Norte CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6641SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25003 | Del Norte CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6642SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25004 | Del Norte CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6643SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25005 | Del Norte CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6644SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25006 | Del Norte CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6645SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25007 | Del Norte CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25008 | Del Norte CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 6649FS+12d,6651SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25009 | CARES V1 - El Dorado CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.28999999999999998
25010 | El Dorado CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
25011 | El Dorado CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
25012 | El Dorado CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
25013 | El Dorado CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
25014 | El Dorado CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
25015 | El Dorado CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
25016 | El Dorado CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25017 | El Dorado CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
25018 | El Dorado CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
25019 | El Dorado CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
25020 | El Dorado CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
25021 | El Dorado CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
25022 | El Dorado CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
25023 | El Dorado CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
25024 | El Dorado CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
25025 | El Dorado CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
25026 | El Dorado CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
25027 | El Dorado CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
25028 | El Dorado CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
25029 | El Dorado CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
25030 | El Dorado CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
25031 | El Dorado CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
25032 | El Dorado CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
25033 | El Dorado CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
25034 | El Dorado CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
25035 | El Dorado CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
25036 | El Dorado CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
25037 | El Dorado CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
25038 | El Dorado CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
25039 | El Dorado CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
25040 | El Dorado CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
25041 | El Dorado CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
25042 | El Dorado CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
25043 | El Dorado CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
25044 | El Dorado CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
25045 | El Dorado CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
25046 | El Dorado CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
25047 | El Dorado CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
25048 | El Dorado CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
25049 | El Dorado CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
25050 | El Dorado CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
25051 | El Dorado CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
25052 | El Dorado CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
25053 | El Dorado CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25054 | El Dorado CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
25055 | El Dorado CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25056 | El Dorado CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
25057 | El Dorado CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
25058 | El Dorado CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
25059 | El Dorado CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
25060 | El Dorado CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
25061 | El Dorado CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
25062 | El Dorado CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
25063 | El Dorado CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
25064 | El Dorado CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 6715SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
25065 | El Dorado CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 6714SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
25066 | El Dorado CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 6717SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25067 | El Dorado CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 6716SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25068 | El Dorado CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
25069 | El Dorado CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 6720SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
25070 | El Dorado CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 6719SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
25071 | El Dorado CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25072 | El Dorado CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 6723SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
25073 | El Dorado CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 6722SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
25074 | El Dorado CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25075 | El Dorado CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 6726SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25076 | El Dorado CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 6725SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25077 | El Dorado CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25078 | El Dorado CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 6729SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
25079 | El Dorado CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 6728SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
25080 | El Dorado CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
25081 | El Dorado CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.33000000000000002
25082 | El Dorado CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
25083 | El Dorado CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 6734 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
25084 | El Dorado CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 6733 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
25085 | El Dorado CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
25086 | El Dorado CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
25087 | El Dorado CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
25088 | El Dorado CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25089 | El Dorado CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 6740 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
25090 | El Dorado CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 6739 | 6741 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
25091 | El Dorado CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 6740 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
25092 | El Dorado CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25093 | El Dorado CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 6744 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
25094 | El Dorado CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 6743 | 6745 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.59999999999999998
25095 | El Dorado CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 6744 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25096 | El Dorado CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25097 | El Dorado CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 6748 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25098 | El Dorado CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 6747 | 6749 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25099 | El Dorado CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 6748 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25100 | El Dorado CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25101 | El Dorado CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 6752 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25102 | El Dorado CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 6751 | 6753 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25103 | El Dorado CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 6752 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25104 | El Dorado CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25105 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25106 | El Dorado CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.35999999999999999
25107 | El Dorado CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.58999999999999997
25108 | El Dorado CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 6759SS | As Soon As Possible | NA | 490 | 405d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.59999999999999998
25109 | El Dorado CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 6758SS | 6760 | As Soon As Possible | NA | 490 | 19.2d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.59999999999999998
25110 | El Dorado CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 6759 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.40000000000000002
25111 | El Dorado CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
25112 | El Dorado CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
25113 | El Dorado CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
25114 | El Dorado CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 6766 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
25115 | El Dorado CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.83999999999999997
25116 | El Dorado CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 6764 | 6767,6769SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
25117 | El Dorado CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 6766 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.59999999999999998
25118 | El Dorado CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.22
25119 | El Dorado CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 6766SS | 6770SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
25120 | El Dorado CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 6769SS | 6771,6774,6772SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.59999999999999998
25121 | El Dorado CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 6770 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25122 | El Dorado CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 6770SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25123 | El Dorado CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25124 | El Dorado CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 6770 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
25125 | El Dorado CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.40999999999999998
25126 | El Dorado CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 6777SS | Start No Earlier Than | 2/3/25 | 190 | 114d | NA | NA | 0 days? | No | NA | NA | NA | 0
25127 | El Dorado CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 6776SS | 6778SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.59999999999999998
25128 | El Dorado CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 6777SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.59999999999999998
25129 | El Dorado CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
25130 | El Dorado CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
25131 | El Dorado CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 6787 | 6782SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
25132 | El Dorado CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 6781SS | 6784 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
25133 | El Dorado CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
25134 | El Dorado CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 6782 | 6785 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
25135 | El Dorado CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 6784 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
25136 | El Dorado CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
25137 | El Dorado CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 6781,6788SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
25138 | El Dorado CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 6787SS | 6792,6789 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
25139 | El Dorado CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 6788 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25140 | El Dorado CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
25141 | El Dorado CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25142 | El Dorado CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 6788 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
25143 | El Dorado CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25144 | El Dorado CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25145 | El Dorado CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25146 | El Dorado CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25147 | El Dorado CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25148 | El Dorado CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25149 | El Dorado CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25150 | El Dorado CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25151 | El Dorado CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25152 | El Dorado CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25153 | El Dorado CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25154 | El Dorado CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25155 | El Dorado CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
25156 | El Dorado CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 5.0000000000000003E-2
25157 | El Dorado CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 6814 | Start No Earlier Than | 7/1/25 | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.59999999999999998
25158 | El Dorado CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
25159 | El Dorado CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
25160 | El Dorado CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
25161 | El Dorado CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
25162 | El Dorado CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 6821 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25163 | El Dorado CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 6822 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25164 | El Dorado CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 6807 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
25165 | El Dorado CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25166 | El Dorado CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6827SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25167 | El Dorado CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6828SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25168 | El Dorado CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6829SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25169 | El Dorado CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6830SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25170 | El Dorado CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 6831SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25171 | El Dorado CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 6812 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25172 | El Dorado CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 6813 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25173 | El Dorado CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
25174 | El Dorado CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 6833FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25175 | El Dorado CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
25176 | El Dorado CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 6833SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
25177 | El Dorado CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6816SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25178 | El Dorado CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6817SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25179 | El Dorado CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6818SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25180 | El Dorado CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6819SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25181 | El Dorado CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6820SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25182 | El Dorado CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25183 | El Dorado CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 6824FS+12d,6826SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25184 | CARES V1 - Glenn CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.37
25185 | Glenn CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
25186 | Glenn CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
25187 | Glenn CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
25188 | Glenn CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
25189 | Glenn CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
25190 | Glenn CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
25191 | Glenn CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25192 | Glenn CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
25193 | Glenn CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
25194 | Glenn CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
25195 | Glenn CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
25196 | Glenn CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
25197 | Glenn CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
25198 | Glenn CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
25199 | Glenn CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
25200 | Glenn CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
25201 | Glenn CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
25202 | Glenn CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
25203 | Glenn CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
25204 | Glenn CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
25205 | Glenn CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
25206 | Glenn CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
25207 | Glenn CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
25208 | Glenn CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
25209 | Glenn CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
25210 | Glenn CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
25211 | Glenn CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
25212 | Glenn CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
25213 | Glenn CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
25214 | Glenn CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
25215 | Glenn CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
25216 | Glenn CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
25217 | Glenn CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
25218 | Glenn CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
25219 | Glenn CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
25220 | Glenn CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
25221 | Glenn CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
25222 | Glenn CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
25223 | Glenn CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
25224 | Glenn CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
25225 | Glenn CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
25226 | Glenn CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
25227 | Glenn CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
25228 | Glenn CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25229 | Glenn CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
25230 | Glenn CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25231 | Glenn CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
25232 | Glenn CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
25233 | Glenn CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
25234 | Glenn CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
25235 | Glenn CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
25236 | Glenn CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
25237 | Glenn CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
25238 | Glenn CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
25239 | Glenn CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 6890SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
25240 | Glenn CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 6889SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
25241 | Glenn CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 6892SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25242 | Glenn CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 6891SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25243 | Glenn CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
25244 | Glenn CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 6895SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
25245 | Glenn CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 6894SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
25246 | Glenn CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25247 | Glenn CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 6898SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
25248 | Glenn CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 6897SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
25249 | Glenn CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25250 | Glenn CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 6901SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25251 | Glenn CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 6900SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25252 | Glenn CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25253 | Glenn CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 6904SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
25254 | Glenn CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 6903SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
25255 | Glenn CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
25256 | Glenn CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.51000000000000001
25257 | Glenn CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
25258 | Glenn CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 6909 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
25259 | Glenn CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 6908 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
25260 | Glenn CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
25261 | Glenn CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
25262 | Glenn CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
25263 | Glenn CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25264 | Glenn CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 6915 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
25265 | Glenn CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 6914 | 6916 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
25266 | Glenn CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 6915 |  | As Soon As Possible | NA | 63 | 0d | NA | NA | 0 days? | No | 9/2/25 | 12/1/25 | NA | 1
25267 | Glenn CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25268 | Glenn CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 6919 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
25269 | Glenn CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 6918 | 6920 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
25270 | Glenn CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 6919 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25271 | Glenn CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25272 | Glenn CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 6923 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25273 | Glenn CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 6922 | 6924 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25274 | Glenn CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 6923 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25275 | Glenn CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25276 | Glenn CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 6927 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25277 | Glenn CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 6926 | 6928 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25278 | Glenn CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 6927 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25279 | Glenn CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25280 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25281 | Glenn CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.5
25282 | Glenn CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
25283 | Glenn CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 6934SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
25284 | Glenn CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 6933SS | 6935 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
25285 | Glenn CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 6934 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25286 | Glenn CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
25287 | Glenn CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
25288 | Glenn CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
25289 | Glenn CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 6941 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
25290 | Glenn CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
25291 | Glenn CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 6939 | 6942,6944SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
25292 | Glenn CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 6941 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
25293 | Glenn CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
25294 | Glenn CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 6941SS | 6945SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
25295 | Glenn CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 6944SS | 6946,6949,6947SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25296 | Glenn CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 6945 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25297 | Glenn CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 6945SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25298 | Glenn CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25299 | Glenn CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 6945 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
25300 | Glenn CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.77000000000000002
25301 | Glenn CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 6952SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
25302 | Glenn CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 6951SS | 6953SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
25303 | Glenn CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 6952SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.40000000000000002
25304 | Glenn CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
25305 | Glenn CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
25306 | Glenn CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 6962 | 6957SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
25307 | Glenn CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 6956SS | 6959 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
25308 | Glenn CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
25309 | Glenn CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 6957 | 6960 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
25310 | Glenn CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 6959 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
25311 | Glenn CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.37
25312 | Glenn CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 6956,6963SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
25313 | Glenn CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 6962SS | 6967,6964 | As Soon As Possible | NA | 210 | 0d | NA | NA | 0 days? | No | 7/1/25 | 5/1/26 | NA | 1
25314 | Glenn CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 6963 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25315 | Glenn CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25316 | Glenn CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25317 | Glenn CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 6963 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
25318 | Glenn CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25319 | Glenn CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25320 | Glenn CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25321 | Glenn CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25322 | Glenn CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25323 | Glenn CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25324 | Glenn CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25325 | Glenn CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25326 | Glenn CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25327 | Glenn CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25328 | Glenn CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25329 | Glenn CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25330 | Glenn CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
25331 | Glenn CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
25332 | Glenn CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 6989 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
25333 | Glenn CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
25334 | Glenn CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
25335 | Glenn CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
25336 | Glenn CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
25337 | Glenn CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 6996 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25338 | Glenn CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 6997 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25339 | Glenn CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 6982 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
25340 | Glenn CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25341 | Glenn CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7002SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25342 | Glenn CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7003SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25343 | Glenn CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7004SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25344 | Glenn CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7005SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25345 | Glenn CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7006SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25346 | Glenn CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 6987 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25347 | Glenn CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 6988 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25348 | Glenn CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
25349 | Glenn CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 7008FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25350 | Glenn CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
25351 | Glenn CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 7008SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
25352 | Glenn CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6991SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25353 | Glenn CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6992SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25354 | Glenn CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6993SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25355 | Glenn CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6994SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25356 | Glenn CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 6995SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25357 | Glenn CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25358 | Glenn CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 6999FS+12d,7001SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25359 | CARES V1 - Humboldt CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.33000000000000002
25360 | Humboldt CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
25361 | Humboldt CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
25362 | Humboldt CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
25363 | Humboldt CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
25364 | Humboldt CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
25365 | Humboldt CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
25366 | Humboldt CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25367 | Humboldt CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
25368 | Humboldt CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
25369 | Humboldt CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
25370 | Humboldt CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
25371 | Humboldt CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
25372 | Humboldt CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
25373 | Humboldt CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
25374 | Humboldt CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
25375 | Humboldt CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
25376 | Humboldt CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
25377 | Humboldt CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
25378 | Humboldt CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
25379 | Humboldt CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
25380 | Humboldt CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
25381 | Humboldt CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
25382 | Humboldt CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
25383 | Humboldt CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
25384 | Humboldt CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
25385 | Humboldt CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
25386 | Humboldt CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
25387 | Humboldt CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
25388 | Humboldt CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
25389 | Humboldt CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
25390 | Humboldt CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
25391 | Humboldt CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
25392 | Humboldt CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
25393 | Humboldt CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
25394 | Humboldt CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
25395 | Humboldt CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
25396 | Humboldt CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
25397 | Humboldt CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
25398 | Humboldt CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
25399 | Humboldt CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
25400 | Humboldt CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
25401 | Humboldt CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
25402 | Humboldt CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
25403 | Humboldt CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25404 | Humboldt CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
25405 | Humboldt CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25406 | Humboldt CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
25407 | Humboldt CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
25408 | Humboldt CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
25409 | Humboldt CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
25410 | Humboldt CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
25411 | Humboldt CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
25412 | Humboldt CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
25413 | Humboldt CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
25414 | Humboldt CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 7065SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
25415 | Humboldt CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 7064SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
25416 | Humboldt CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 7067SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25417 | Humboldt CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 7066SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25418 | Humboldt CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
25419 | Humboldt CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 7070SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
25420 | Humboldt CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 7069SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
25421 | Humboldt CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25422 | Humboldt CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 7073SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
25423 | Humboldt CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 7072SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
25424 | Humboldt CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25425 | Humboldt CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 7076SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25426 | Humboldt CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 7075SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25427 | Humboldt CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25428 | Humboldt CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 7079SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
25429 | Humboldt CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 7078SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
25430 | Humboldt CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
25431 | Humboldt CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.33000000000000002
25432 | Humboldt CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
25433 | Humboldt CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 7084 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
25434 | Humboldt CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 7083 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
25435 | Humboldt CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
25436 | Humboldt CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
25437 | Humboldt CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
25438 | Humboldt CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25439 | Humboldt CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 7090 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
25440 | Humboldt CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 7089 | 7091 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
25441 | Humboldt CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 7090 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
25442 | Humboldt CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25443 | Humboldt CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 7094 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
25444 | Humboldt CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 7093 | 7095 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25445 | Humboldt CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 7094 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25446 | Humboldt CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25447 | Humboldt CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 7098 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.59999999999999998
25448 | Humboldt CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 7097 | 7099 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25449 | Humboldt CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 7098 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25450 | Humboldt CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25451 | Humboldt CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 7102 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25452 | Humboldt CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 7101 | 7103 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25453 | Humboldt CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 7102 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25454 | Humboldt CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25455 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25456 | Humboldt CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.46000000000000002
25457 | Humboldt CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
25458 | Humboldt CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 7109SS | Start No Earlier Than | 3/19/24 | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
25459 | Humboldt CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 7108SS | 7110 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
25460 | Humboldt CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 7109 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25461 | Humboldt CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
25462 | Humboldt CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
25463 | Humboldt CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
25464 | Humboldt CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 7116 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
25465 | Humboldt CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
25466 | Humboldt CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 7114 | 7117,7119SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
25467 | Humboldt CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 7116 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
25468 | Humboldt CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
25469 | Humboldt CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 7116SS | 7120SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
25470 | Humboldt CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 7119SS | 7121,7124,7122SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25471 | Humboldt CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 7120 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25472 | Humboldt CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 7120SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25473 | Humboldt CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25474 | Humboldt CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 7120 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
25475 | Humboldt CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.84999999999999998
25476 | Humboldt CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 7127SS | Start No Earlier Than | 2/3/25 | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
25477 | Humboldt CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 7126SS | 7128SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
25478 | Humboldt CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 7127SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.59999999999999998
25479 | Humboldt CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
25480 | Humboldt CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
25481 | Humboldt CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 7137 | 7132SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
25482 | Humboldt CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 7131SS | 7134 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
25483 | Humboldt CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
25484 | Humboldt CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 7132 | 7135 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
25485 | Humboldt CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 7134 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
25486 | Humboldt CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
25487 | Humboldt CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 7131,7138SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
25488 | Humboldt CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 7137SS | 7142,7139 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25489 | Humboldt CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 7138 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25490 | Humboldt CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25491 | Humboldt CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25492 | Humboldt CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 7138 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
25493 | Humboldt CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25494 | Humboldt CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25495 | Humboldt CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25496 | Humboldt CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25497 | Humboldt CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25498 | Humboldt CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25499 | Humboldt CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25500 | Humboldt CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25501 | Humboldt CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25502 | Humboldt CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25503 | Humboldt CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25504 | Humboldt CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25505 | Humboldt CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
25506 | Humboldt CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
25507 | Humboldt CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 7164 | Start No Earlier Than | 7/1/25 | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
25508 | Humboldt CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
25509 | Humboldt CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
25510 | Humboldt CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
25511 | Humboldt CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
25512 | Humboldt CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 7171 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25513 | Humboldt CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 7172 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25514 | Humboldt CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 7157 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
25515 | Humboldt CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25516 | Humboldt CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7177SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25517 | Humboldt CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7178SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25518 | Humboldt CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7179SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25519 | Humboldt CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7180SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25520 | Humboldt CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7181SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25521 | Humboldt CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 7162 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25522 | Humboldt CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 7163 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25523 | Humboldt CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
25524 | Humboldt CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 7183FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25525 | Humboldt CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
25526 | Humboldt CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 7183SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
25527 | Humboldt CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7166SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25528 | Humboldt CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7167SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25529 | Humboldt CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7168SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25530 | Humboldt CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7169SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25531 | Humboldt CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7170SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25532 | Humboldt CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25533 | Humboldt CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 7174FS+12d,7176SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25534 | CARES V1 - Imperial CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.26000000000000001
25535 | Imperial CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
25536 | Imperial CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
25537 | Imperial CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
25538 | Imperial CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
25539 | Imperial CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
25540 | Imperial CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
25541 | Imperial CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25542 | Imperial CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
25543 | Imperial CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
25544 | Imperial CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
25545 | Imperial CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
25546 | Imperial CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
25547 | Imperial CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
25548 | Imperial CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
25549 | Imperial CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
25550 | Imperial CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
25551 | Imperial CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
25552 | Imperial CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
25553 | Imperial CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
25554 | Imperial CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
25555 | Imperial CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
25556 | Imperial CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
25557 | Imperial CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
25558 | Imperial CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
25559 | Imperial CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
25560 | Imperial CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
25561 | Imperial CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
25562 | Imperial CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
25563 | Imperial CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
25564 | Imperial CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
25565 | Imperial CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
25566 | Imperial CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
25567 | Imperial CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
25568 | Imperial CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
25569 | Imperial CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
25570 | Imperial CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
25571 | Imperial CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
25572 | Imperial CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
25573 | Imperial CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
25574 | Imperial CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
25575 | Imperial CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
25576 | Imperial CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
25577 | Imperial CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
25578 | Imperial CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25579 | Imperial CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
25580 | Imperial CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25581 | Imperial CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
25582 | Imperial CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
25583 | Imperial CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
25584 | Imperial CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
25585 | Imperial CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
25586 | Imperial CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
25587 | Imperial CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
25588 | Imperial CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
25589 | Imperial CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 7240SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
25590 | Imperial CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 7239SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
25591 | Imperial CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 7242SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25592 | Imperial CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 7241SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25593 | Imperial CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
25594 | Imperial CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 7245SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
25595 | Imperial CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 7244SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
25596 | Imperial CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25597 | Imperial CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 7248SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
25598 | Imperial CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 7247SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
25599 | Imperial CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25600 | Imperial CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 7251SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25601 | Imperial CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 7250SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25602 | Imperial CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25603 | Imperial CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 7254SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
25604 | Imperial CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 7253SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
25605 | Imperial CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
25606 | Imperial CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.47999999999999998
25607 | Imperial CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
25608 | Imperial CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 7259 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
25609 | Imperial CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 7258 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
25610 | Imperial CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
25611 | Imperial CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
25612 | Imperial CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
25613 | Imperial CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25614 | Imperial CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 7265 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
25615 | Imperial CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 7264 | 7266 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
25616 | Imperial CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 7265 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
25617 | Imperial CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25618 | Imperial CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 7269 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
25619 | Imperial CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 7268 | 7270 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
25620 | Imperial CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 7269 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25621 | Imperial CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25622 | Imperial CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 7273 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
25623 | Imperial CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 7272 | 7274 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25624 | Imperial CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 7273 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25625 | Imperial CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25626 | Imperial CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 7277 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25627 | Imperial CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 7276 | 7278 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25628 | Imperial CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 7277 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25629 | Imperial CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25630 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25631 | Imperial CW-Technical | January 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 398 | 298d | NA | NA | 0 days? | No | 1/1/25 | NA | NA | 0.23000000000000001
25632 | Imperial CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.32000000000000001
25633 | Imperial CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 7284SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.40000000000000002
25634 | Imperial CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 7283SS | 7285SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.40000000000000002
25635 | Imperial CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 7284SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
25636 | Imperial CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
25637 | Imperial CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
25638 | Imperial CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 7294 | 7289SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
25639 | Imperial CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 7288SS | 7291 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
25640 | Imperial CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
25641 | Imperial CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 7289 | 7292 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
25642 | Imperial CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 7291 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
25643 | Imperial CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
25644 | Imperial CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 7288,7295SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
25645 | Imperial CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 7294SS | 7299,7296 | As Soon As Possible | NA | 210 | 3.4d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
25646 | Imperial CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 7295 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25647 | Imperial CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
25648 | Imperial CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25649 | Imperial CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 7295 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | 5/4/26 | NA | NA | 0.20000000000000001
25650 | Imperial CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25651 | Imperial CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25652 | Imperial CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25653 | Imperial CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25654 | Imperial CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25655 | Imperial CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25656 | Imperial CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25657 | Imperial CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25658 | Imperial CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25659 | Imperial CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25660 | Imperial CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25661 | Imperial CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25662 | Imperial CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
25663 | Imperial CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
25664 | Imperial CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 7321 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
25665 | Imperial CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
25666 | Imperial CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
25667 | Imperial CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
25668 | Imperial CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
25669 | Imperial CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 7328 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25670 | Imperial CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 7329 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25671 | Imperial CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 7314 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
25672 | Imperial CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25673 | Imperial CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7334SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25674 | Imperial CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7335SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25675 | Imperial CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7336SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25676 | Imperial CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7337SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25677 | Imperial CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7338SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25678 | Imperial CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 7319 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25679 | Imperial CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 7320 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25680 | Imperial CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
25681 | Imperial CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 7340FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25682 | Imperial CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
25683 | Imperial CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 7340SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
25684 | Imperial CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7323SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25685 | Imperial CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7324SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25686 | Imperial CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7325SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25687 | Imperial CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7326SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25688 | Imperial CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7327SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25689 | Imperial CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25690 | Imperial CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 7331FS+12d,7333SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25691 | CARES V1 - Inyo CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.26000000000000001
25692 | Inyo CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
25693 | Inyo CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
25694 | Inyo CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
25695 | Inyo CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
25696 | Inyo CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
25697 | Inyo CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
25698 | Inyo CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25699 | Inyo CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
25700 | Inyo CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
25701 | Inyo CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
25702 | Inyo CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
25703 | Inyo CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
25704 | Inyo CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
25705 | Inyo CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
25706 | Inyo CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
25707 | Inyo CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
25708 | Inyo CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
25709 | Inyo CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
25710 | Inyo CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
25711 | Inyo CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
25712 | Inyo CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
25713 | Inyo CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
25714 | Inyo CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
25715 | Inyo CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
25716 | Inyo CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
25717 | Inyo CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
25718 | Inyo CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
25719 | Inyo CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
25720 | Inyo CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
25721 | Inyo CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
25722 | Inyo CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
25723 | Inyo CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
25724 | Inyo CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
25725 | Inyo CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
25726 | Inyo CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
25727 | Inyo CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
25728 | Inyo CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
25729 | Inyo CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
25730 | Inyo CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
25731 | Inyo CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
25732 | Inyo CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
25733 | Inyo CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
25734 | Inyo CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
25735 | Inyo CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25736 | Inyo CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
25737 | Inyo CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25738 | Inyo CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
25739 | Inyo CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
25740 | Inyo CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
25741 | Inyo CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
25742 | Inyo CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
25743 | Inyo CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
25744 | Inyo CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
25745 | Inyo CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
25746 | Inyo CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 7397SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
25747 | Inyo CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 7396SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
25748 | Inyo CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 7399SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25749 | Inyo CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 7398SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25750 | Inyo CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
25751 | Inyo CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 7402SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
25752 | Inyo CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 7401SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
25753 | Inyo CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25754 | Inyo CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 7405SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
25755 | Inyo CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 7404SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
25756 | Inyo CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25757 | Inyo CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 7408SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25758 | Inyo CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 7407SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25759 | Inyo CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25760 | Inyo CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 7411SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
25761 | Inyo CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 7410SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
25762 | Inyo CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
25763 | Inyo CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.32000000000000001
25764 | Inyo CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
25765 | Inyo CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 7416 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
25766 | Inyo CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 7415 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
25767 | Inyo CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
25768 | Inyo CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
25769 | Inyo CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
25770 | Inyo CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25771 | Inyo CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 7422 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
25772 | Inyo CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 7421 | 7423 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
25773 | Inyo CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 7422 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
25774 | Inyo CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25775 | Inyo CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 7426 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
25776 | Inyo CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 7425 | 7427 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
25777 | Inyo CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 7426 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25778 | Inyo CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25779 | Inyo CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 7430 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
25780 | Inyo CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 7429 | 7431 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25781 | Inyo CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 7430 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25782 | Inyo CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25783 | Inyo CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 7434 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25784 | Inyo CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 7433 | 7435 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25785 | Inyo CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 7434 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25786 | Inyo CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25787 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25788 | Inyo CW-Technical | January 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 398 | 298d | NA | NA | 0 days? | No | 1/1/25 | NA | NA | 0.34000000000000002
25789 | Inyo CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.77000000000000002
25790 | Inyo CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 7441SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
25791 | Inyo CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 7440SS | 7442SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
25792 | Inyo CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 7441SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.40000000000000002
25793 | Inyo CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
25794 | Inyo CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
25795 | Inyo CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 7451 | 7446SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
25796 | Inyo CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 7445SS | 7448 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
25797 | Inyo CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
25798 | Inyo CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 7446 | 7449 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
25799 | Inyo CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 7448 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
25800 | Inyo CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
25801 | Inyo CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 7445,7452SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
25802 | Inyo CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 7451SS | 7456,7453 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
25803 | Inyo CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 7452 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25804 | Inyo CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
25805 | Inyo CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25806 | Inyo CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 7452 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
25807 | Inyo CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25808 | Inyo CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25809 | Inyo CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25810 | Inyo CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25811 | Inyo CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25812 | Inyo CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25813 | Inyo CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25814 | Inyo CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25815 | Inyo CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25816 | Inyo CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25817 | Inyo CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25818 | Inyo CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25819 | Inyo CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
25820 | Inyo CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 2.9999999999999999E-2
25821 | Inyo CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 7478 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.40000000000000002
25822 | Inyo CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
25823 | Inyo CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
25824 | Inyo CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
25825 | Inyo CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
25826 | Inyo CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 7485 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25827 | Inyo CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 7486 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25828 | Inyo CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 7471 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
25829 | Inyo CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25830 | Inyo CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7491SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25831 | Inyo CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7492SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25832 | Inyo CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7493SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25833 | Inyo CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7494SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25834 | Inyo CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7495SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25835 | Inyo CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 7476 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25836 | Inyo CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 7477 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
25837 | Inyo CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
25838 | Inyo CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 7497FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25839 | Inyo CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
25840 | Inyo CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 7497SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
25841 | Inyo CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7480SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25842 | Inyo CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7481SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25843 | Inyo CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7482SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25844 | Inyo CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7483SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25845 | Inyo CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7484SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25846 | Inyo CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25847 | Inyo CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 7488FS+12d,7490SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
25848 | CARES V1 - Kern CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.31
25849 | Kern CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
25850 | Kern CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
25851 | Kern CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
25852 | Kern CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
25853 | Kern CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
25854 | Kern CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
25855 | Kern CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25856 | Kern CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
25857 | Kern CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
25858 | Kern CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
25859 | Kern CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
25860 | Kern CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
25861 | Kern CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
25862 | Kern CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
25863 | Kern CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
25864 | Kern CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
25865 | Kern CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
25866 | Kern CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
25867 | Kern CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
25868 | Kern CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
25869 | Kern CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
25870 | Kern CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
25871 | Kern CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
25872 | Kern CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
25873 | Kern CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
25874 | Kern CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
25875 | Kern CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
25876 | Kern CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
25877 | Kern CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
25878 | Kern CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
25879 | Kern CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
25880 | Kern CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
25881 | Kern CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
25882 | Kern CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
25883 | Kern CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
25884 | Kern CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
25885 | Kern CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
25886 | Kern CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
25887 | Kern CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
25888 | Kern CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
25889 | Kern CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
25890 | Kern CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
25891 | Kern CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
25892 | Kern CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25893 | Kern CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
25894 | Kern CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25895 | Kern CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
25896 | Kern CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
25897 | Kern CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
25898 | Kern CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
25899 | Kern CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
25900 | Kern CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
25901 | Kern CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
25902 | Kern CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
25903 | Kern CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 7554SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
25904 | Kern CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 7553SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
25905 | Kern CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 7556SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25906 | Kern CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 7555SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25907 | Kern CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
25908 | Kern CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 7559SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
25909 | Kern CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 7558SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
25910 | Kern CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25911 | Kern CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 7562SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
25912 | Kern CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 7561SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
25913 | Kern CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25914 | Kern CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 7565SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25915 | Kern CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 7564SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
25916 | Kern CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
25917 | Kern CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 7568SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
25918 | Kern CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 7567SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
25919 | Kern CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
25920 | Kern CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.31
25921 | Kern CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
25922 | Kern CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 7573 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
25923 | Kern CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 7572 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
25924 | Kern CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
25925 | Kern CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
25926 | Kern CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
25927 | Kern CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25928 | Kern CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 7579 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
25929 | Kern CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 7578 | 7580 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
25930 | Kern CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 7579 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
25931 | Kern CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25932 | Kern CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 7583 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
25933 | Kern CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 7582 | 7584 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25934 | Kern CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 7583 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25935 | Kern CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25936 | Kern CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 7587 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
25937 | Kern CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 7586 | 7588 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25938 | Kern CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 7587 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
25939 | Kern CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25940 | Kern CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 7591 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25941 | Kern CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 7590 | 7592 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25942 | Kern CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 7591 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25943 | Kern CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25944 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
25945 | Kern CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.41999999999999998
25946 | Kern CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
25947 | Kern CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 7598SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
25948 | Kern CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 7597SS | 7599 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
25949 | Kern CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 7598 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
25950 | Kern CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
25951 | Kern CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
25952 | Kern CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
25953 | Kern CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 7605 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
25954 | Kern CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.60999999999999999
25955 | Kern CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 7603 | 7606,7608SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
25956 | Kern CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 7605 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
25957 | Kern CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
25958 | Kern CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 7605SS | 7609SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
25959 | Kern CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 7608SS | 7610,7613,7611SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25960 | Kern CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 7609 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25961 | Kern CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 7609SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25962 | Kern CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25963 | Kern CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 7609 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
25964 | Kern CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.62
25965 | Kern CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 7616SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
25966 | Kern CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 7615SS | 7617SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
25967 | Kern CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 7616SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
25968 | Kern CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
25969 | Kern CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
25970 | Kern CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 7626 | 7621SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
25971 | Kern CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 7620SS | 7623 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
25972 | Kern CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
25973 | Kern CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 7621 | 7624 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
25974 | Kern CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 7623 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
25975 | Kern CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
25976 | Kern CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 7620,7627SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
25977 | Kern CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 7626SS | 7631,7628 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25978 | Kern CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 7627 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25979 | Kern CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
25980 | Kern CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
25981 | Kern CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 7627 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
25982 | Kern CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25983 | Kern CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25984 | Kern CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25985 | Kern CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25986 | Kern CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25987 | Kern CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25988 | Kern CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25989 | Kern CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25990 | Kern CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25991 | Kern CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25992 | Kern CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25993 | Kern CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
25994 | Kern CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
25995 | Kern CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
25996 | Kern CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 7653 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
25997 | Kern CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
25998 | Kern CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
25999 | Kern CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26000 | Kern CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26001 | Kern CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 7660 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26002 | Kern CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 7661 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26003 | Kern CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 7646 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
26004 | Kern CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26005 | Kern CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7666SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26006 | Kern CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7667SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26007 | Kern CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7668SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26008 | Kern CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7669SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26009 | Kern CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7670SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26010 | Kern CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 7651 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26011 | Kern CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 7652 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26012 | Kern CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
26013 | Kern CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 7672FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26014 | Kern CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
26015 | Kern CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 7672SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
26016 | Kern CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7655SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26017 | Kern CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7656SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26018 | Kern CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7657SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26019 | Kern CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7658SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26020 | Kern CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7659SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26021 | Kern CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26022 | Kern CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 7663FS+12d,7665SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26023 | CARES V1 - Lake CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.28000000000000003
26024 | Lake CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.53000000000000003
26025 | Lake CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.59999999999999998
26026 | Lake CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
26027 | Lake CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
26028 | Lake CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
26029 | Lake CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
26030 | Lake CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.40000000000000002
26031 | Lake CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
26032 | Lake CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
26033 | Lake CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
26034 | Lake CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
26035 | Lake CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
26036 | Lake CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
26037 | Lake CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
26038 | Lake CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
26039 | Lake CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
26040 | Lake CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
26041 | Lake CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
26042 | Lake CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
26043 | Lake CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
26044 | Lake CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
26045 | Lake CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
26046 | Lake CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
26047 | Lake CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
26048 | Lake CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
26049 | Lake CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
26050 | Lake CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
26051 | Lake CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
26052 | Lake CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
26053 | Lake CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
26054 | Lake CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
26055 | Lake CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
26056 | Lake CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
26057 | Lake CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
26058 | Lake CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
26059 | Lake CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
26060 | Lake CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
26061 | Lake CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
26062 | Lake CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
26063 | Lake CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
26064 | Lake CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
26065 | Lake CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
26066 | Lake CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26067 | Lake CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26068 | Lake CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
26069 | Lake CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26070 | Lake CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
26071 | Lake CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
26072 | Lake CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
26073 | Lake CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
26074 | Lake CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
26075 | Lake CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
26076 | Lake CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
26077 | Lake CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
26078 | Lake CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 7729SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
26079 | Lake CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 7728SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
26080 | Lake CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 7731 | As Soon As Possible | NA | 63 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26081 | Lake CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | May 4, 2026 8:00 AM | July 31, 2026 5:00 PM | 7730 |  | As Soon As Possible | NA | 63 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26082 | Lake CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
26083 | Lake CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 7734SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
26084 | Lake CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 7733SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
26085 | Lake CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26086 | Lake CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 7737SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
26087 | Lake CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 7736SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
26088 | Lake CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26089 | Lake CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 7740SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26090 | Lake CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 7739SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26091 | Lake CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26092 | Lake CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 7743SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
26093 | Lake CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 7742SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
26094 | Lake CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
26095 | Lake CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.46999999999999997
26096 | Lake CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
26097 | Lake CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 7748 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
26098 | Lake CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 7747 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
26099 | Lake CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
26100 | Lake CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
26101 | Lake CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
26102 | Lake CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26103 | Lake CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 7754 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
26104 | Lake CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 7753 | 7755 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
26105 | Lake CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 7754 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
26106 | Lake CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26107 | Lake CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 7758 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
26108 | Lake CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 7757 | 7759 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26109 | Lake CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 7758 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26110 | Lake CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26111 | Lake CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 7762 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26112 | Lake CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 7761 | 7763 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26113 | Lake CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 7762 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26114 | Lake CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26115 | Lake CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 7766 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26116 | Lake CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 7765 | 7767 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26117 | Lake CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 7766 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26118 | Lake CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26119 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26120 | Lake CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.28999999999999998
26121 | Lake CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.56999999999999995
26122 | Lake CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 7773SS | Start No Earlier Than | 3/19/24 | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
26123 | Lake CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 7772SS | 7774 | As Soon As Possible | NA | 490 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.20000000000000001
26124 | Lake CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 7773 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26125 | Lake CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
26126 | Lake CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
26127 | Lake CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
26128 | Lake CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 7780 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
26129 | Lake CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
26130 | Lake CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 7778 | 7781,7783SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
26131 | Lake CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 7780 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
26132 | Lake CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
26133 | Lake CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 7780SS | 7784SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
26134 | Lake CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 7783SS | 7785,7788,7786SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26135 | Lake CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 7784 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26136 | Lake CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 7784SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26137 | Lake CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26138 | Lake CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 7784 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
26139 | Lake CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.31
26140 | Lake CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 7791SS | Start No Earlier Than | 2/3/25 | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
26141 | Lake CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 7790SS | 7792SS | As Soon As Possible | NA | 190 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
26142 | Lake CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 7791SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
26143 | Lake CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
26144 | Lake CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
26145 | Lake CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 7801 | 7796SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
26146 | Lake CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 7795SS | 7798 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
26147 | Lake CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 508d | NA | NA | 0 days? | No | 7/21/25 | NA | NA | 0.83999999999999997
26148 | Lake CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 7796 | 7799 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
26149 | Lake CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 7798 |  | As Soon As Possible | NA | 21 | 508d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.59999999999999998
26150 | Lake CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 5.0000000000000003E-2
26151 | Lake CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 7795,7802SS | Start No Earlier Than | 7/1/25 | 64 | 508d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.59999999999999998
26152 | Lake CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 7801SS | 7806,7803 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26153 | Lake CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 7802 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26154 | Lake CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26155 | Lake CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26156 | Lake CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 7802 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
26157 | Lake CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26158 | Lake CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26159 | Lake CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26160 | Lake CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26161 | Lake CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26162 | Lake CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26163 | Lake CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26164 | Lake CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26165 | Lake CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26166 | Lake CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26167 | Lake CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26168 | Lake CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26169 | Lake CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
26170 | Lake CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
26171 | Lake CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 7828 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
26172 | Lake CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
26173 | Lake CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
26174 | Lake CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26175 | Lake CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26176 | Lake CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 7835 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26177 | Lake CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 7836 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26178 | Lake CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 7821 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
26179 | Lake CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26180 | Lake CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7841SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26181 | Lake CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7842SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26182 | Lake CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7843SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26183 | Lake CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7844SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26184 | Lake CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 7845SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26185 | Lake CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 7826 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26186 | Lake CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 7827 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26187 | Lake CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
26188 | Lake CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 7847FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26189 | Lake CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
26190 | Lake CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 7847SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
26191 | Lake CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7830SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26192 | Lake CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7831SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26193 | Lake CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7832SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26194 | Lake CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7833SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26195 | Lake CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7834SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26196 | Lake CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26197 | Lake CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 7838FS+12d,7840SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26198 | CARES V1 - Lassen CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.34000000000000002
26199 | Lassen CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
26200 | Lassen CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
26201 | Lassen CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
26202 | Lassen CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
26203 | Lassen CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
26204 | Lassen CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
26205 | Lassen CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26206 | Lassen CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
26207 | Lassen CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
26208 | Lassen CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
26209 | Lassen CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
26210 | Lassen CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
26211 | Lassen CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
26212 | Lassen CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
26213 | Lassen CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
26214 | Lassen CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
26215 | Lassen CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
26216 | Lassen CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
26217 | Lassen CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
26218 | Lassen CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
26219 | Lassen CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
26220 | Lassen CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
26221 | Lassen CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
26222 | Lassen CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
26223 | Lassen CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
26224 | Lassen CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
26225 | Lassen CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
26226 | Lassen CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
26227 | Lassen CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
26228 | Lassen CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
26229 | Lassen CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
26230 | Lassen CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
26231 | Lassen CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
26232 | Lassen CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
26233 | Lassen CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
26234 | Lassen CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
26235 | Lassen CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
26236 | Lassen CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
26237 | Lassen CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
26238 | Lassen CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
26239 | Lassen CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
26240 | Lassen CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
26241 | Lassen CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26242 | Lassen CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26243 | Lassen CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
26244 | Lassen CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26245 | Lassen CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
26246 | Lassen CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
26247 | Lassen CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
26248 | Lassen CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
26249 | Lassen CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
26250 | Lassen CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
26251 | Lassen CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
26252 | Lassen CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
26253 | Lassen CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 7904SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
26254 | Lassen CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 7903SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
26255 | Lassen CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 7906SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26256 | Lassen CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 7905SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26257 | Lassen CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
26258 | Lassen CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 7909SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
26259 | Lassen CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 7908SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
26260 | Lassen CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26261 | Lassen CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 7912SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
26262 | Lassen CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 7911SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
26263 | Lassen CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26264 | Lassen CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 7915SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26265 | Lassen CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 7914SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26266 | Lassen CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26267 | Lassen CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 7918SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
26268 | Lassen CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 7917SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
26269 | Lassen CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
26270 | Lassen CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.52000000000000002
26271 | Lassen CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
26272 | Lassen CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 7923 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
26273 | Lassen CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 7922 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
26274 | Lassen CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
26275 | Lassen CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
26276 | Lassen CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
26277 | Lassen CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26278 | Lassen CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 7929 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
26279 | Lassen CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 7928 | 7930 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
26280 | Lassen CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 7929 |  | As Soon As Possible | NA | 63 | 0d | NA | NA | 0 days? | No | 9/2/25 | 12/1/25 | NA | 1
26281 | Lassen CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26282 | Lassen CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 7933 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
26283 | Lassen CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 7932 | 7934 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26284 | Lassen CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 7933 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26285 | Lassen CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26286 | Lassen CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 7937 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.94999999999999996
26287 | Lassen CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 7936 | 7938 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26288 | Lassen CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 7937 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26289 | Lassen CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26290 | Lassen CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 7941 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26291 | Lassen CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 7940 | 7942 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26292 | Lassen CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 7941 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26293 | Lassen CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26294 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26295 | Lassen CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.41999999999999998
26296 | Lassen CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.56999999999999995
26297 | Lassen CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 7948SS | As Soon As Possible | NA | 490 | 405d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.80000000000000004
26298 | Lassen CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 7947SS | 7949 | As Soon As Possible | NA | 490 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.40000000000000002
26299 | Lassen CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 7948 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26300 | Lassen CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
26301 | Lassen CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
26302 | Lassen CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
26303 | Lassen CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 7955 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
26304 | Lassen CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
26305 | Lassen CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 7953 | 7956,7958SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
26306 | Lassen CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 7955 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
26307 | Lassen CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
26308 | Lassen CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 7955SS | 7959SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
26309 | Lassen CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 7958SS | 7960,7963,7961SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26310 | Lassen CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 7959 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26311 | Lassen CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 7959SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26312 | Lassen CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26313 | Lassen CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 7959 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
26314 | Lassen CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.77000000000000002
26315 | Lassen CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 7966SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
26316 | Lassen CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 7965SS | 7967SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
26317 | Lassen CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 7966SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.40000000000000002
26318 | Lassen CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
26319 | Lassen CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
26320 | Lassen CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 7971SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
26321 | Lassen CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 7970SS | 7973 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
26322 | Lassen CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
26323 | Lassen CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 7971 | 7974 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
26324 | Lassen CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 7973 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
26325 | Lassen CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26326 | Lassen CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26327 | Lassen CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26328 | Lassen CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26329 | Lassen CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26330 | Lassen CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26331 | Lassen CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26332 | Lassen CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26333 | Lassen CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26334 | Lassen CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26335 | Lassen CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26336 | Lassen CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26337 | Lassen CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
26338 | Lassen CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
26339 | Lassen CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 7996 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
26340 | Lassen CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
26341 | Lassen CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
26342 | Lassen CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26343 | Lassen CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26344 | Lassen CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 8003 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26345 | Lassen CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 8004 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26346 | Lassen CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 7989 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
26347 | Lassen CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26348 | Lassen CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8009SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26349 | Lassen CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8010SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26350 | Lassen CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8011SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26351 | Lassen CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8012SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26352 | Lassen CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8013SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26353 | Lassen CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 7994 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26354 | Lassen CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 7995 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26355 | Lassen CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
26356 | Lassen CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 8015FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26357 | Lassen CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
26358 | Lassen CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 8015SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
26359 | Lassen CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7998SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26360 | Lassen CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 7999SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26361 | Lassen CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8000SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26362 | Lassen CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8001SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26363 | Lassen CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8002SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26364 | Lassen CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26365 | Lassen CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 8006FS+12d,8008SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26366 | CARES V1 - Los Angeles CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.25
26367 | Los Angeles CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
26368 | Los Angeles CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
26369 | Los Angeles CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
26370 | Los Angeles CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
26371 | Los Angeles CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
26372 | Los Angeles CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
26373 | Los Angeles CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26374 | Los Angeles CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
26375 | Los Angeles CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
26376 | Los Angeles CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
26377 | Los Angeles CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
26378 | Los Angeles CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
26379 | Los Angeles CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
26380 | Los Angeles CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
26381 | Los Angeles CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
26382 | Los Angeles CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
26383 | Los Angeles CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
26384 | Los Angeles CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
26385 | Los Angeles CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
26386 | Los Angeles CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
26387 | Los Angeles CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
26388 | Los Angeles CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
26389 | Los Angeles CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
26390 | Los Angeles CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
26391 | Los Angeles CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
26392 | Los Angeles CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
26393 | Los Angeles CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
26394 | Los Angeles CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
26395 | Los Angeles CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
26396 | Los Angeles CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
26397 | Los Angeles CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
26398 | Los Angeles CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
26399 | Los Angeles CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
26400 | Los Angeles CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
26401 | Los Angeles CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
26402 | Los Angeles CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
26403 | Los Angeles CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
26404 | Los Angeles CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
26405 | Los Angeles CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
26406 | Los Angeles CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
26407 | Los Angeles CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
26408 | Los Angeles CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
26409 | Los Angeles CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26410 | Los Angeles CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26411 | Los Angeles CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
26412 | Los Angeles CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26413 | Los Angeles CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
26414 | Los Angeles CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
26415 | Los Angeles CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
26416 | Los Angeles CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
26417 | Los Angeles CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
26418 | Los Angeles CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
26419 | Los Angeles CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
26420 | Los Angeles CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
26421 | Los Angeles CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 8072SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
26422 | Los Angeles CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 8071SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
26423 | Los Angeles CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 8074SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26424 | Los Angeles CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 8073SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26425 | Los Angeles CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
26426 | Los Angeles CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 8077SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
26427 | Los Angeles CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 8076SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
26428 | Los Angeles CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26429 | Los Angeles CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 8080SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
26430 | Los Angeles CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 8079SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
26431 | Los Angeles CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26432 | Los Angeles CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 8083SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26433 | Los Angeles CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 8082SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26434 | Los Angeles CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26435 | Los Angeles CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 8086SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
26436 | Los Angeles CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 8085SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
26437 | Los Angeles CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
26438 | Los Angeles CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.39000000000000001
26439 | Los Angeles CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
26440 | Los Angeles CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 8091 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
26441 | Los Angeles CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 8090 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.40000000000000002
26442 | Los Angeles CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
26443 | Los Angeles CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
26444 | Los Angeles CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
26445 | Los Angeles CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26446 | Los Angeles CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 8097 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
26447 | Los Angeles CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 8096 | 8098 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
26448 | Los Angeles CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 8097 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
26449 | Los Angeles CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26450 | Los Angeles CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 8101 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
26451 | Los Angeles CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 8100 | 8102 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26452 | Los Angeles CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 8101 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26453 | Los Angeles CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26454 | Los Angeles CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 8105 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26455 | Los Angeles CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 8104 | 8106 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26456 | Los Angeles CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 8105 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26457 | Los Angeles CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26458 | Los Angeles CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 8109 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26459 | Los Angeles CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 8108 | 8110 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26460 | Los Angeles CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 8109 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26461 | Los Angeles CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26462 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26463 | Los Angeles CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.26000000000000001
26464 | Los Angeles CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.28999999999999998
26465 | Los Angeles CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 8116SS | As Soon As Possible | NA | 490 | 405d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.40000000000000002
26466 | Los Angeles CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 8115SS | 8117 | As Soon As Possible | NA | 490 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.20000000000000001
26467 | Los Angeles CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 8116 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26468 | Los Angeles CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
26469 | Los Angeles CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
26470 | Los Angeles CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
26471 | Los Angeles CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 8123 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
26472 | Los Angeles CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.12
26473 | Los Angeles CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 8121 | 8124,8126SS | As Soon As Possible | NA | 36 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
26474 | Los Angeles CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 8123 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
26475 | Los Angeles CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.01
26476 | Los Angeles CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 8123SS | 8127SS | As Soon As Possible | NA | 36 | 508d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
26477 | Los Angeles CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 8126SS | 8128,8131,8129SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26478 | Los Angeles CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 8127 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26479 | Los Angeles CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 8127SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26480 | Los Angeles CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26481 | Los Angeles CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 8127 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
26482 | Los Angeles CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.62
26483 | Los Angeles CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 8134SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
26484 | Los Angeles CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 8133SS | 8135SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
26485 | Los Angeles CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 8134SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
26486 | Los Angeles CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
26487 | Los Angeles CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
26488 | Los Angeles CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 8144 | 8139SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
26489 | Los Angeles CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 8138SS | 8141 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
26490 | Los Angeles CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
26491 | Los Angeles CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 8139 | 8142 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
26492 | Los Angeles CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 8141 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
26493 | Los Angeles CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.11
26494 | Los Angeles CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 8138,8145SS | Start No Earlier Than | 7/1/25 | 64 | 508d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.59999999999999998
26495 | Los Angeles CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 8144SS | 8149,8146 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
26496 | Los Angeles CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 8145 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26497 | Los Angeles CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26498 | Los Angeles CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26499 | Los Angeles CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 8145 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
26500 | Los Angeles CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26501 | Los Angeles CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26502 | Los Angeles CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26503 | Los Angeles CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26504 | Los Angeles CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26505 | Los Angeles CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26506 | Los Angeles CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26507 | Los Angeles CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26508 | Los Angeles CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26509 | Los Angeles CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26510 | Los Angeles CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26511 | Los Angeles CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26512 | Los Angeles CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
26513 | Los Angeles CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
26514 | Los Angeles CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 8171 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
26515 | Los Angeles CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
26516 | Los Angeles CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
26517 | Los Angeles CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26518 | Los Angeles CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26519 | Los Angeles CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 8178 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26520 | Los Angeles CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 8179 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26521 | Los Angeles CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 8164 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
26522 | Los Angeles CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26523 | Los Angeles CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8184SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26524 | Los Angeles CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8185SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26525 | Los Angeles CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8186SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26526 | Los Angeles CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8187SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26527 | Los Angeles CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8188SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26528 | Los Angeles CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 8169 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26529 | Los Angeles CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 8170 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26530 | Los Angeles CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
26531 | Los Angeles CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 8190FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26532 | Los Angeles CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
26533 | Los Angeles CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 8190SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
26534 | Los Angeles CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8173SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26535 | Los Angeles CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8174SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26536 | Los Angeles CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8175SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26537 | Los Angeles CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8176SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26538 | Los Angeles CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8177SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26539 | Los Angeles CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26540 | Los Angeles CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 8181FS+12d,8183SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26541 | CARES V1 - Madera CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.35999999999999999
26542 | Madera CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
26543 | Madera CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
26544 | Madera CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
26545 | Madera CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
26546 | Madera CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
26547 | Madera CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
26548 | Madera CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26549 | Madera CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
26550 | Madera CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
26551 | Madera CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
26552 | Madera CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
26553 | Madera CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
26554 | Madera CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
26555 | Madera CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
26556 | Madera CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
26557 | Madera CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
26558 | Madera CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
26559 | Madera CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
26560 | Madera CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
26561 | Madera CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
26562 | Madera CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
26563 | Madera CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
26564 | Madera CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
26565 | Madera CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
26566 | Madera CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
26567 | Madera CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
26568 | Madera CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
26569 | Madera CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
26570 | Madera CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
26571 | Madera CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
26572 | Madera CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
26573 | Madera CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
26574 | Madera CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
26575 | Madera CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
26576 | Madera CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
26577 | Madera CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
26578 | Madera CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
26579 | Madera CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
26580 | Madera CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
26581 | Madera CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
26582 | Madera CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
26583 | Madera CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
26584 | Madera CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26585 | Madera CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26586 | Madera CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
26587 | Madera CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26588 | Madera CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
26589 | Madera CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
26590 | Madera CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
26591 | Madera CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
26592 | Madera CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
26593 | Madera CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
26594 | Madera CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
26595 | Madera CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
26596 | Madera CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 8247SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
26597 | Madera CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 8246SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
26598 | Madera CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 8249SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26599 | Madera CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 8248SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26600 | Madera CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
26601 | Madera CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 8252SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
26602 | Madera CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 8251SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
26603 | Madera CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26604 | Madera CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 8255SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
26605 | Madera CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 8254SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
26606 | Madera CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26607 | Madera CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 8258SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26608 | Madera CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 8257SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26609 | Madera CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26610 | Madera CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 8261SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
26611 | Madera CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 8260SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
26612 | Madera CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
26613 | Madera CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.47999999999999998
26614 | Madera CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
26615 | Madera CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 8266 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
26616 | Madera CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 8265 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
26617 | Madera CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
26618 | Madera CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
26619 | Madera CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
26620 | Madera CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26621 | Madera CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 8272 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
26622 | Madera CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 8271 | 8273 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
26623 | Madera CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 8272 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
26624 | Madera CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26625 | Madera CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 8276 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
26626 | Madera CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 8275 | 8277 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
26627 | Madera CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 8276 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26628 | Madera CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26629 | Madera CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 8280 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
26630 | Madera CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 8279 | 8281 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26631 | Madera CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 8280 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26632 | Madera CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26633 | Madera CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 8284 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26634 | Madera CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 8283 | 8285 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26635 | Madera CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 8284 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26636 | Madera CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26637 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26638 | Madera CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.47999999999999998
26639 | Madera CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 0d | NA | NA | 0 days? | No | 3/19/24 | 5/8/26 | NA | 1
26640 | Madera CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 8291SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
26641 | Madera CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 8290SS | 8292 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
26642 | Madera CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 8291 |  | As Soon As Possible | NA | 48 | 0d | NA | NA | 0 days? | No | 3/3/26 | 5/8/26 | NA | 1
26643 | Madera CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
26644 | Madera CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
26645 | Madera CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
26646 | Madera CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.68999999999999995
26647 | Madera CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 8298,8300SS | Start No Earlier Than | 8/11/25 | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
26648 | Madera CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 8297 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
26649 | Madera CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
26650 | Madera CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 8297SS | 8301SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
26651 | Madera CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 8300SS | 8302,8305,8303SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26652 | Madera CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 8301 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26653 | Madera CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 8301SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26654 | Madera CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26655 | Madera CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 8301 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
26656 | Madera CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 0d | NA | NA | 0 days? | No | 2/3/25 | 12/31/25 | NA | 1
26657 | Madera CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 8308SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
26658 | Madera CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 8307SS | 8309SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
26659 | Madera CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 8308SS |  | As Soon As Possible | NA | 230 | 0d | NA | NA | 0 days? | No | 2/3/25 | 12/31/25 | NA | 1
26660 | Madera CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
26661 | Madera CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
26662 | Madera CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 8318 | 8313SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
26663 | Madera CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 8312SS | 8315 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
26664 | Madera CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
26665 | Madera CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 8313 | 8316 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
26666 | Madera CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 8315 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
26667 | Madera CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
26668 | Madera CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 8312,8319SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
26669 | Madera CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 8318SS | 8323,8320 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26670 | Madera CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 8319 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26671 | Madera CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26672 | Madera CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26673 | Madera CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 8319 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
26674 | Madera CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26675 | Madera CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26676 | Madera CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26677 | Madera CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26678 | Madera CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26679 | Madera CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26680 | Madera CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26681 | Madera CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26682 | Madera CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26683 | Madera CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26684 | Madera CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26685 | Madera CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26686 | Madera CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
26687 | Madera CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
26688 | Madera CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 8345 | Start No Earlier Than | 7/1/25 | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
26689 | Madera CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
26690 | Madera CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
26691 | Madera CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26692 | Madera CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26693 | Madera CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 8352 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26694 | Madera CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 8353 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26695 | Madera CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 8338 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
26696 | Madera CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26697 | Madera CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8358SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26698 | Madera CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8359SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26699 | Madera CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8360SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26700 | Madera CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8361SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26701 | Madera CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8362SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26702 | Madera CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 8343 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26703 | Madera CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 8344 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26704 | Madera CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
26705 | Madera CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 8364FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26706 | Madera CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
26707 | Madera CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 8364SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
26708 | Madera CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8347SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26709 | Madera CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8348SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26710 | Madera CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8349SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26711 | Madera CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8350SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26712 | Madera CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8351SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26713 | Madera CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26714 | Madera CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 8355FS+12d,8357SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26715 | CARES V1 - Marin CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.37
26716 | Marin CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
26717 | Marin CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
26718 | Marin CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
26719 | Marin CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
26720 | Marin CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
26721 | Marin CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
26722 | Marin CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26723 | Marin CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
26724 | Marin CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
26725 | Marin CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
26726 | Marin CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
26727 | Marin CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
26728 | Marin CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
26729 | Marin CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
26730 | Marin CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
26731 | Marin CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
26732 | Marin CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
26733 | Marin CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
26734 | Marin CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
26735 | Marin CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
26736 | Marin CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
26737 | Marin CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
26738 | Marin CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
26739 | Marin CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
26740 | Marin CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
26741 | Marin CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
26742 | Marin CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
26743 | Marin CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
26744 | Marin CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
26745 | Marin CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
26746 | Marin CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
26747 | Marin CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
26748 | Marin CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
26749 | Marin CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
26750 | Marin CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
26751 | Marin CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
26752 | Marin CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
26753 | Marin CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
26754 | Marin CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
26755 | Marin CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
26756 | Marin CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
26757 | Marin CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
26758 | Marin CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26759 | Marin CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26760 | Marin CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
26761 | Marin CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26762 | Marin CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
26763 | Marin CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
26764 | Marin CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
26765 | Marin CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
26766 | Marin CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
26767 | Marin CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
26768 | Marin CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
26769 | Marin CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
26770 | Marin CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 8421SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
26771 | Marin CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 8420SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
26772 | Marin CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 8423SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26773 | Marin CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 8422SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26774 | Marin CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
26775 | Marin CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 8426SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
26776 | Marin CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 8425SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
26777 | Marin CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26778 | Marin CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 8429SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
26779 | Marin CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 8428SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
26780 | Marin CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26781 | Marin CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 8432SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26782 | Marin CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 8431SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26783 | Marin CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26784 | Marin CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 8435SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
26785 | Marin CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 8434SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
26786 | Marin CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
26787 | Marin CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.57999999999999996
26788 | Marin CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
26789 | Marin CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 8440 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
26790 | Marin CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 8439 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.80000000000000004
26791 | Marin CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
26792 | Marin CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
26793 | Marin CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
26794 | Marin CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26795 | Marin CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 8446 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
26796 | Marin CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 8445 | 8447 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
26797 | Marin CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 8446 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
26798 | Marin CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26799 | Marin CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 8450 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
26800 | Marin CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 8449 | 8451 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
26801 | Marin CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 8450 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26802 | Marin CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26803 | Marin CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 8454 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
26804 | Marin CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 8453 | 8455 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26805 | Marin CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 8454 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26806 | Marin CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26807 | Marin CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 8458 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26808 | Marin CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 8457 | 8459 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26809 | Marin CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 8458 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26810 | Marin CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26811 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26812 | Marin CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.46000000000000002
26813 | Marin CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.97999999999999998
26814 | Marin CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 8465SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
26815 | Marin CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 8464SS | 8466 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
26816 | Marin CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 8465 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.59999999999999998
26817 | Marin CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
26818 | Marin CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
26819 | Marin CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
26820 | Marin CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 8472 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
26821 | Marin CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
26822 | Marin CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 8470 | 8473,8475SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
26823 | Marin CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 8472 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
26824 | Marin CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
26825 | Marin CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 8472SS | 8476SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
26826 | Marin CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 8475SS | 8477,8480,8478SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
26827 | Marin CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 8476 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26828 | Marin CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 8476SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26829 | Marin CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26830 | Marin CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 8476 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
26831 | Marin CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.56999999999999995
26832 | Marin CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 8483SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
26833 | Marin CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 8482SS | 8484SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.59999999999999998
26834 | Marin CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 8483SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
26835 | Marin CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
26836 | Marin CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
26837 | Marin CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 8493 | 8488SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
26838 | Marin CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 8487SS | 8490 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
26839 | Marin CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
26840 | Marin CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 8488 | 8491 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
26841 | Marin CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 8490 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
26842 | Marin CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
26843 | Marin CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 8487,8494SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
26844 | Marin CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 8493SS | 8498,8495 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
26845 | Marin CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 8494 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
26846 | Marin CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
26847 | Marin CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26848 | Marin CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 8494 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
26849 | Marin CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26850 | Marin CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26851 | Marin CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26852 | Marin CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26853 | Marin CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26854 | Marin CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26855 | Marin CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26856 | Marin CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26857 | Marin CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26858 | Marin CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26859 | Marin CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26860 | Marin CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26861 | Marin CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
26862 | Marin CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 4.0000000000000001E-2
26863 | Marin CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 8520 | Start No Earlier Than | 7/1/25 | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
26864 | Marin CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
26865 | Marin CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
26866 | Marin CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26867 | Marin CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26868 | Marin CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 8527 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26869 | Marin CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 8528 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26870 | Marin CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 8513 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
26871 | Marin CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26872 | Marin CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8533SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26873 | Marin CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8534SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26874 | Marin CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8535SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26875 | Marin CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8536SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26876 | Marin CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8537SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26877 | Marin CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 8518 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26878 | Marin CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 8519 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
26879 | Marin CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
26880 | Marin CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 8539FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26881 | Marin CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
26882 | Marin CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 8539SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
26883 | Marin CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8522SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26884 | Marin CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8523SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26885 | Marin CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8524SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26886 | Marin CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8525SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26887 | Marin CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8526SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26888 | Marin CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26889 | Marin CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 8530FS+12d,8532SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
26890 | CARES V1 - Mariposa CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.32000000000000001
26891 | Mariposa CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
26892 | Mariposa CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
26893 | Mariposa CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
26894 | Mariposa CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
26895 | Mariposa CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
26896 | Mariposa CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
26897 | Mariposa CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26898 | Mariposa CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
26899 | Mariposa CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
26900 | Mariposa CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
26901 | Mariposa CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
26902 | Mariposa CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
26903 | Mariposa CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
26904 | Mariposa CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
26905 | Mariposa CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
26906 | Mariposa CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
26907 | Mariposa CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
26908 | Mariposa CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
26909 | Mariposa CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
26910 | Mariposa CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
26911 | Mariposa CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
26912 | Mariposa CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
26913 | Mariposa CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
26914 | Mariposa CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
26915 | Mariposa CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
26916 | Mariposa CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
26917 | Mariposa CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
26918 | Mariposa CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
26919 | Mariposa CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
26920 | Mariposa CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
26921 | Mariposa CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
26922 | Mariposa CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
26923 | Mariposa CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
26924 | Mariposa CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
26925 | Mariposa CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
26926 | Mariposa CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
26927 | Mariposa CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
26928 | Mariposa CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
26929 | Mariposa CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
26930 | Mariposa CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
26931 | Mariposa CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
26932 | Mariposa CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
26933 | Mariposa CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
26934 | Mariposa CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
26935 | Mariposa CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
26936 | Mariposa CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26937 | Mariposa CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
26938 | Mariposa CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
26939 | Mariposa CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
26940 | Mariposa CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
26941 | Mariposa CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
26942 | Mariposa CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
26943 | Mariposa CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
26944 | Mariposa CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
26945 | Mariposa CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 8596SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
26946 | Mariposa CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 8595SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
26947 | Mariposa CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 8598SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26948 | Mariposa CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 8597SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26949 | Mariposa CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
26950 | Mariposa CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 8601SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
26951 | Mariposa CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 8600SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
26952 | Mariposa CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26953 | Mariposa CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 8604SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
26954 | Mariposa CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 8603SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
26955 | Mariposa CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26956 | Mariposa CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 8607SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26957 | Mariposa CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 8606SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
26958 | Mariposa CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
26959 | Mariposa CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 8610SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
26960 | Mariposa CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 8609SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
26961 | Mariposa CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
26962 | Mariposa CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.33000000000000002
26963 | Mariposa CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
26964 | Mariposa CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 8615 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
26965 | Mariposa CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 8614 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
26966 | Mariposa CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
26967 | Mariposa CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
26968 | Mariposa CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
26969 | Mariposa CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26970 | Mariposa CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 8621 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
26971 | Mariposa CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 8620 | 8622 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
26972 | Mariposa CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 8621 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
26973 | Mariposa CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26974 | Mariposa CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 8625 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
26975 | Mariposa CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 8624 | 8626 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
26976 | Mariposa CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 8625 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26977 | Mariposa CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26978 | Mariposa CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 8629 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
26979 | Mariposa CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 8628 | 8630 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26980 | Mariposa CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 8629 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
26981 | Mariposa CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26982 | Mariposa CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 8633 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26983 | Mariposa CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 8632 | 8634 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26984 | Mariposa CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 8633 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
26985 | Mariposa CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26986 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
26987 | Mariposa CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.42999999999999999
26988 | Mariposa CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
26989 | Mariposa CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 8640SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
26990 | Mariposa CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 8639SS | 8641 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
26991 | Mariposa CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 8640 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
26992 | Mariposa CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
26993 | Mariposa CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
26994 | Mariposa CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
26995 | Mariposa CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 8647 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
26996 | Mariposa CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
26997 | Mariposa CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 8645 | 8648,8650SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
26998 | Mariposa CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 8647 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
26999 | Mariposa CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
27000 | Mariposa CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 8647SS | 8651SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
27001 | Mariposa CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 8650SS | 8652,8655,8653SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27002 | Mariposa CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 8651 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27003 | Mariposa CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 8651SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27004 | Mariposa CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27005 | Mariposa CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 8651 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
27006 | Mariposa CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.62
27007 | Mariposa CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 8658SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
27008 | Mariposa CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 8657SS | 8659SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
27009 | Mariposa CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 8658SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
27010 | Mariposa CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
27011 | Mariposa CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
27012 | Mariposa CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 8668 | 8663SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
27013 | Mariposa CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 8662SS | 8665 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
27014 | Mariposa CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
27015 | Mariposa CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 8663 | 8666 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
27016 | Mariposa CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 8665 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
27017 | Mariposa CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
27018 | Mariposa CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 8662,8669SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
27019 | Mariposa CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 8668SS | 8673,8670 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27020 | Mariposa CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 8669 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27021 | Mariposa CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27022 | Mariposa CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27023 | Mariposa CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 8669 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
27024 | Mariposa CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27025 | Mariposa CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27026 | Mariposa CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27027 | Mariposa CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27028 | Mariposa CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27029 | Mariposa CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27030 | Mariposa CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27031 | Mariposa CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27032 | Mariposa CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27033 | Mariposa CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27034 | Mariposa CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27035 | Mariposa CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27036 | Mariposa CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
27037 | Mariposa CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
27038 | Mariposa CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 8695 | Start No Earlier Than | 7/1/25 | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
27039 | Mariposa CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
27040 | Mariposa CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
27041 | Mariposa CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27042 | Mariposa CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27043 | Mariposa CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 8702 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27044 | Mariposa CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 8703 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27045 | Mariposa CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 8688 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
27046 | Mariposa CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27047 | Mariposa CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8708SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27048 | Mariposa CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8709SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27049 | Mariposa CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8710SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27050 | Mariposa CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8711SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27051 | Mariposa CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8712SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27052 | Mariposa CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 8693 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27053 | Mariposa CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 8694 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27054 | Mariposa CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
27055 | Mariposa CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 8714FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27056 | Mariposa CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
27057 | Mariposa CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 8714SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
27058 | Mariposa CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8697SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27059 | Mariposa CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8698SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27060 | Mariposa CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8699SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27061 | Mariposa CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8700SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27062 | Mariposa CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8701SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27063 | Mariposa CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27064 | Mariposa CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 8705FS+12d,8707SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27065 | CARES V1 - Mendocino CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.17000000000000001
27066 | Mendocino CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
27067 | Mendocino CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
27068 | Mendocino CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
27069 | Mendocino CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
27070 | Mendocino CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
27071 | Mendocino CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
27072 | Mendocino CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27073 | Mendocino CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
27074 | Mendocino CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
27075 | Mendocino CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
27076 | Mendocino CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
27077 | Mendocino CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
27078 | Mendocino CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
27079 | Mendocino CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
27080 | Mendocino CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
27081 | Mendocino CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
27082 | Mendocino CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
27083 | Mendocino CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
27084 | Mendocino CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
27085 | Mendocino CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
27086 | Mendocino CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
27087 | Mendocino CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
27088 | Mendocino CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
27089 | Mendocino CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
27090 | Mendocino CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
27091 | Mendocino CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
27092 | Mendocino CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
27093 | Mendocino CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
27094 | Mendocino CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
27095 | Mendocino CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
27096 | Mendocino CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
27097 | Mendocino CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
27098 | Mendocino CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
27099 | Mendocino CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
27100 | Mendocino CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
27101 | Mendocino CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
27102 | Mendocino CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
27103 | Mendocino CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
27104 | Mendocino CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
27105 | Mendocino CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
27106 | Mendocino CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
27107 | Mendocino CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
27108 | Mendocino CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27109 | Mendocino CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27110 | Mendocino CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
27111 | Mendocino CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27112 | Mendocino CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
27113 | Mendocino CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
27114 | Mendocino CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
27115 | Mendocino CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
27116 | Mendocino CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
27117 | Mendocino CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
27118 | Mendocino CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
27119 | Mendocino CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
27120 | Mendocino CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 8771SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
27121 | Mendocino CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 8770SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
27122 | Mendocino CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 8773SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27123 | Mendocino CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 8772SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27124 | Mendocino CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
27125 | Mendocino CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 8776SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
27126 | Mendocino CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 8775SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
27127 | Mendocino CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27128 | Mendocino CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 8779SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
27129 | Mendocino CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 8778SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
27130 | Mendocino CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27131 | Mendocino CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 8782SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27132 | Mendocino CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 8781SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27133 | Mendocino CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27134 | Mendocino CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 8785SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
27135 | Mendocino CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 8784SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
27136 | Mendocino CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
27137 | Mendocino CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.41999999999999998
27138 | Mendocino CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
27139 | Mendocino CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 8790 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
27140 | Mendocino CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 8789 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.40000000000000002
27141 | Mendocino CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
27142 | Mendocino CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
27143 | Mendocino CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
27144 | Mendocino CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27145 | Mendocino CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 8796 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
27146 | Mendocino CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 8795 | 8797 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
27147 | Mendocino CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 8796 |  | As Soon As Possible | NA | 63 | 0d | NA | NA | 0 days? | No | 9/2/25 | 12/1/25 | NA | 1
27148 | Mendocino CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27149 | Mendocino CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 8800 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
27150 | Mendocino CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 8799 | 8801 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27151 | Mendocino CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 8800 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27152 | Mendocino CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27153 | Mendocino CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 8804 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27154 | Mendocino CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 8803 | 8805 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27155 | Mendocino CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 8804 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27156 | Mendocino CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27157 | Mendocino CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 8808 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27158 | Mendocino CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 8807 | 8809 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27159 | Mendocino CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 8808 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27160 | Mendocino CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27161 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27162 | Mendocino CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 5.0000000000000003E-2
27163 | Mendocino CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27164 | Mendocino CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 8815SS | Start No Earlier Than | 3/19/24 | 490 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27165 | Mendocino CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 8814SS | 8816 | As Soon As Possible | NA | 490 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27166 | Mendocino CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 8815 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27167 | Mendocino CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 592d | NA | NA | 0 days? | No | 4/1/25 | NA | NA | 0.59999999999999998
27168 | Mendocino CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 544d | NA | NA | 0 days? | No | 1/6/25 | NA | NA | 0.14000000000000001
27169 | Mendocino CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | January 6, 2025 8:00 AM | April 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 630d | NA | NA | 0 days? | No | 1/6/25 | NA | NA | 0.20000000000000001
27170 | Mendocino CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | January 6, 2025 8:00 AM | February 13, 2025 5:00 PM |  | 8822 | As Soon As Possible | NA | 28 | 420d | NA | NA | 0 days? | No | NA | NA | NA | 0
27171 | Mendocino CW-Determine priority for Organization-specific custom reports | February 14, 2025 8:00 AM | May 9, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 420d | NA | NA | 0 days? | No | NA | NA | NA | 0
27172 | Mendocino CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | February 14, 2025 8:00 AM | April 8, 2025 5:00 PM | 8820 | 8823,8825SS | As Soon As Possible | NA | 36 | 420d | NA | NA | 0 days? | No | NA | NA | NA | 0
27173 | Mendocino CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | April 9, 2025 8:00 AM | May 9, 2025 5:00 PM | 8822 |  | As Soon As Possible | NA | 23 | 607d | NA | NA | 0 days? | No | NA | NA | NA | 0
27174 | Mendocino CW-Execute plan for transition of custom reports from Business Objects to Tableau | February 14, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 368 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27175 | Mendocino CW-Develop Plan for Timeline of Reports Creation in Tableau | February 14, 2025 8:00 AM | April 8, 2025 5:00 PM | 8822SS | 8826SS | As Soon As Possible | NA | 36 | 420d | NA | NA | 0 days? | No | NA | NA | NA | 0
27176 | Mendocino CW-Create organization-specific reports for process simulation bulk upload | February 14, 2025 8:00 AM | November 3, 2025 5:00 PM | 8825SS | 8827,8830,8828SF+30d | As Soon As Possible | NA | 182 | 420d | NA | NA | 0 days? | No | NA | NA | NA | 0
27177 | Mendocino CW-Continue development of organization-specific reports for production bulk upload, if necessary | November 4, 2025 8:00 AM | February 6, 2026 5:00 PM | 8826 |  | As Soon As Possible | NA | 64 | 420d | NA | NA | 0 days? | No | NA | NA | NA | 0
27178 | Mendocino CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 8826SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27179 | Mendocino CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27180 | Mendocino CW-POC or Organization Leadership to sign off on report creation completion | November 4, 2025 8:00 AM | November 28, 2025 5:00 PM | 8826 |  | As Soon As Possible | NA | 17 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
27181 | Mendocino CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
27182 | Mendocino CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 8833SS | Start No Earlier Than | 2/3/25 | 190 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
27183 | Mendocino CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 8832SS | 8834SS | As Soon As Possible | NA | 190 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
27184 | Mendocino CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 8833SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
27185 | Mendocino CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
27186 | Mendocino CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
27187 | Mendocino CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 8843 | 8838SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
27188 | Mendocino CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 8837SS | 8840 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
27189 | Mendocino CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 508d | NA | NA | 0 days? | No | NA | NA | NA | 0
27190 | Mendocino CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 8838 | 8841 | As Soon As Possible | NA | 30 | 508d | NA | NA | 0 days? | No | NA | NA | NA | 0
27191 | Mendocino CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 8840 |  | As Soon As Possible | NA | 21 | 508d | NA | NA | 0 days? | No | NA | NA | NA | 0
27192 | Mendocino CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27193 | Mendocino CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 8837,8844SS | Start No Earlier Than | 7/1/25 | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27194 | Mendocino CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 8843SS | 8848,8845 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27195 | Mendocino CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 8844 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27196 | Mendocino CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27197 | Mendocino CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27198 | Mendocino CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 8844 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
27199 | Mendocino CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27200 | Mendocino CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27201 | Mendocino CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27202 | Mendocino CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27203 | Mendocino CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27204 | Mendocino CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27205 | Mendocino CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27206 | Mendocino CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27207 | Mendocino CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27208 | Mendocino CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27209 | Mendocino CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27210 | Mendocino CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27211 | Mendocino CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
27212 | Mendocino CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
27213 | Mendocino CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 8870 | Start No Earlier Than | 7/1/25 | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
27214 | Mendocino CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
27215 | Mendocino CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
27216 | Mendocino CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27217 | Mendocino CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27218 | Mendocino CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 8877 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27219 | Mendocino CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 8878 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27220 | Mendocino CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 8863 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
27221 | Mendocino CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27222 | Mendocino CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8883SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27223 | Mendocino CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8884SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27224 | Mendocino CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8885SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27225 | Mendocino CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8886SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27226 | Mendocino CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 8887SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27227 | Mendocino CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 8868 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27228 | Mendocino CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 8869 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27229 | Mendocino CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
27230 | Mendocino CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 8889FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27231 | Mendocino CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
27232 | Mendocino CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 8889SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
27233 | Mendocino CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8872SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27234 | Mendocino CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8873SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27235 | Mendocino CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8874SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27236 | Mendocino CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8875SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27237 | Mendocino CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 8876SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27238 | Mendocino CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27239 | Mendocino CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 8880FS+12d,8882SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27240 | CARES V1 - Merced CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.33000000000000002
27241 | Merced CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
27242 | Merced CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
27243 | Merced CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
27244 | Merced CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
27245 | Merced CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
27246 | Merced CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
27247 | Merced CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27248 | Merced CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
27249 | Merced CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
27250 | Merced CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
27251 | Merced CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
27252 | Merced CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
27253 | Merced CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
27254 | Merced CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
27255 | Merced CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
27256 | Merced CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
27257 | Merced CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
27258 | Merced CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
27259 | Merced CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
27260 | Merced CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
27261 | Merced CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
27262 | Merced CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
27263 | Merced CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
27264 | Merced CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
27265 | Merced CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
27266 | Merced CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
27267 | Merced CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
27268 | Merced CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
27269 | Merced CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
27270 | Merced CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
27271 | Merced CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
27272 | Merced CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
27273 | Merced CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
27274 | Merced CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
27275 | Merced CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
27276 | Merced CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
27277 | Merced CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
27278 | Merced CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
27279 | Merced CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
27280 | Merced CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
27281 | Merced CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
27282 | Merced CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
27283 | Merced CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27284 | Merced CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27285 | Merced CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
27286 | Merced CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27287 | Merced CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
27288 | Merced CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
27289 | Merced CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
27290 | Merced CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
27291 | Merced CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
27292 | Merced CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
27293 | Merced CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
27294 | Merced CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
27295 | Merced CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 8946SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
27296 | Merced CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 8945SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
27297 | Merced CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 8948SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27298 | Merced CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 8947SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27299 | Merced CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
27300 | Merced CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 8951SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
27301 | Merced CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 8950SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
27302 | Merced CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27303 | Merced CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 8954SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
27304 | Merced CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 8953SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
27305 | Merced CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27306 | Merced CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 8957SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27307 | Merced CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 8956SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27308 | Merced CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27309 | Merced CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 8960SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
27310 | Merced CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 8959SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
27311 | Merced CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
27312 | Merced CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.44
27313 | Merced CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
27314 | Merced CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 8965 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
27315 | Merced CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 8964 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.40000000000000002
27316 | Merced CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
27317 | Merced CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
27318 | Merced CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
27319 | Merced CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27320 | Merced CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 8971 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
27321 | Merced CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 8970 | 8972 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
27322 | Merced CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 8971 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
27323 | Merced CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27324 | Merced CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 8975 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
27325 | Merced CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 8974 | 8976 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
27326 | Merced CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 8975 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27327 | Merced CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27328 | Merced CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 8979 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
27329 | Merced CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 8978 | 8980 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27330 | Merced CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 8979 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27331 | Merced CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27332 | Merced CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 8983 | Start No Earlier Than | 11/3/25 | 40 | 0d | NA | NA | 0 days? | No | 11/3/25 | 12/31/25 | NA | 1
27333 | Merced CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 8982 | 8984 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27334 | Merced CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 8983 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27335 | Merced CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27336 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27337 | Merced CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.40999999999999998
27338 | Merced CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.65000000000000002
27339 | Merced CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 8990SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
27340 | Merced CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 8989SS | 8991 | As Soon As Possible | NA | 490 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.35999999999999999
27341 | Merced CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 8990 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27342 | Merced CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
27343 | Merced CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
27344 | Merced CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
27345 | Merced CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 8997 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
27346 | Merced CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
27347 | Merced CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 8995 | 8998,9000SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
27348 | Merced CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 8997 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
27349 | Merced CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
27350 | Merced CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 8997SS | 9001SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
27351 | Merced CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 9000SS | 9002,9005,9003SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
27352 | Merced CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 9001 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27353 | Merced CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 9001SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27354 | Merced CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27355 | Merced CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 9001 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
27356 | Merced CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.77000000000000002
27357 | Merced CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 9008SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
27358 | Merced CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 9007SS | 9009SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
27359 | Merced CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 9008SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.40000000000000002
27360 | Merced CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
27361 | Merced CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
27362 | Merced CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 9018 | 9013SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
27363 | Merced CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 9012SS | 9015 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
27364 | Merced CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
27365 | Merced CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 9013 | 9016 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
27366 | Merced CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 9015 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
27367 | Merced CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
27368 | Merced CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 9012,9019SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
27369 | Merced CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 9018SS | 9023,9020 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
27370 | Merced CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 9019 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27371 | Merced CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
27372 | Merced CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27373 | Merced CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 9019 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
27374 | Merced CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27375 | Merced CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27376 | Merced CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27377 | Merced CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27378 | Merced CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27379 | Merced CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27380 | Merced CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27381 | Merced CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27382 | Merced CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27383 | Merced CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27384 | Merced CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27385 | Merced CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27386 | Merced CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
27387 | Merced CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
27388 | Merced CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 9045 | Start No Earlier Than | 7/1/25 | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
27389 | Merced CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
27390 | Merced CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
27391 | Merced CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27392 | Merced CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27393 | Merced CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 9052 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27394 | Merced CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 9053 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27395 | Merced CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 9038 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
27396 | Merced CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27397 | Merced CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9058SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27398 | Merced CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9059SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27399 | Merced CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9060SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27400 | Merced CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9061SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27401 | Merced CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9062SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27402 | Merced CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 9043 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27403 | Merced CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 9044 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27404 | Merced CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
27405 | Merced CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 9064FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27406 | Merced CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
27407 | Merced CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 9064SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
27408 | Merced CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9047SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27409 | Merced CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9048SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27410 | Merced CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9049SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27411 | Merced CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9050SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27412 | Merced CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9051SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27413 | Merced CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27414 | Merced CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 9055FS+12d,9057SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27415 | CARES V1 - Modoc CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.28000000000000003
27416 | Modoc CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
27417 | Modoc CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
27418 | Modoc CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
27419 | Modoc CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
27420 | Modoc CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
27421 | Modoc CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
27422 | Modoc CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27423 | Modoc CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
27424 | Modoc CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
27425 | Modoc CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
27426 | Modoc CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
27427 | Modoc CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.40000000000000002
27428 | Modoc CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.65000000000000002
27429 | Modoc CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
27430 | Modoc CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
27431 | Modoc CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
27432 | Modoc CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
27433 | Modoc CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
27434 | Modoc CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
27435 | Modoc CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
27436 | Modoc CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
27437 | Modoc CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
27438 | Modoc CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
27439 | Modoc CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
27440 | Modoc CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
27441 | Modoc CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
27442 | Modoc CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
27443 | Modoc CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
27444 | Modoc CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
27445 | Modoc CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
27446 | Modoc CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
27447 | Modoc CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
27448 | Modoc CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
27449 | Modoc CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
27450 | Modoc CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/30/25 | NA | 1
27451 | Modoc CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
27452 | Modoc CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
27453 | Modoc CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
27454 | Modoc CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
27455 | Modoc CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
27456 | Modoc CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
27457 | Modoc CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
27458 | Modoc CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27459 | Modoc CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27460 | Modoc CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
27461 | Modoc CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27462 | Modoc CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
27463 | Modoc CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
27464 | Modoc CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
27465 | Modoc CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
27466 | Modoc CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
27467 | Modoc CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
27468 | Modoc CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
27469 | Modoc CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
27470 | Modoc CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 9121SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
27471 | Modoc CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 9120SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
27472 | Modoc CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 9123SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27473 | Modoc CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 9122SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27474 | Modoc CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
27475 | Modoc CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 9126SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
27476 | Modoc CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 9125SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
27477 | Modoc CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27478 | Modoc CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 9129SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
27479 | Modoc CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 9128SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
27480 | Modoc CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27481 | Modoc CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 9132SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27482 | Modoc CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 9131SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27483 | Modoc CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27484 | Modoc CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 9135SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
27485 | Modoc CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 9134SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
27486 | Modoc CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
27487 | Modoc CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.54000000000000004
27488 | Modoc CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
27489 | Modoc CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 9140 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
27490 | Modoc CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 9139 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
27491 | Modoc CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
27492 | Modoc CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
27493 | Modoc CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
27494 | Modoc CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27495 | Modoc CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 9146 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
27496 | Modoc CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 9145 | 9147 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
27497 | Modoc CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 9146 |  | As Soon As Possible | NA | 63 | 0d | NA | NA | 0 days? | No | 9/2/25 | 12/1/25 | NA | 1
27498 | Modoc CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27499 | Modoc CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 9150 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
27500 | Modoc CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 9149 | 9151 | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
27501 | Modoc CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 9150 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27502 | Modoc CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27503 | Modoc CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 9154 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.80000000000000004
27504 | Modoc CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 9153 | 9155 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27505 | Modoc CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 9154 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27506 | Modoc CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27507 | Modoc CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 9158 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27508 | Modoc CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 9157 | 9159 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27509 | Modoc CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 9158 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27510 | Modoc CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27511 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27512 | Modoc CW-Technical | January 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 398 | 298d | NA | NA | 0 days? | No | 1/1/25 | NA | NA | 0.22
27513 | Modoc CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
27514 | Modoc CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
27515 | Modoc CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
27516 | Modoc CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
27517 | Modoc CW-Determine priority for Organization-specific custom reports | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
27518 | Modoc CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
27519 | Modoc CW-Execute plan for transition of custom reports from Business Objects to Tableau | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 2.9999999999999999E-2
27520 | Modoc CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 64 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27521 | Modoc CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27522 | Modoc CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27523 | Modoc CW-POC or Organization Leadership to sign off on report creation completion | May 1, 2026 8:00 AM | May 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 17 | 346d | NA | NA | 0 days? | No | 5/1/26 | NA | NA | 0.80000000000000004
27524 | Modoc CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
27525 | Modoc CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
27526 | Modoc CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 9177SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
27527 | Modoc CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 9176SS |  | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
27528 | Modoc CW-Determine priority for Organization-specific custom Forms | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
27529 | Modoc CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
27530 | Modoc CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27531 | Modoc CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27532 | Modoc CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27533 | Modoc CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27534 | Modoc CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27535 | Modoc CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27536 | Modoc CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27537 | Modoc CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27538 | Modoc CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27539 | Modoc CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27540 | Modoc CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27541 | Modoc CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27542 | Modoc CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
27543 | Modoc CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
27544 | Modoc CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 9201 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
27545 | Modoc CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
27546 | Modoc CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
27547 | Modoc CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27548 | Modoc CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27549 | Modoc CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 9208 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27550 | Modoc CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 9209 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27551 | Modoc CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 9194 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
27552 | Modoc CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27553 | Modoc CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9214SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27554 | Modoc CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9215SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27555 | Modoc CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9216SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27556 | Modoc CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9217SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27557 | Modoc CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9218SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27558 | Modoc CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 9199 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27559 | Modoc CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 9200 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27560 | Modoc CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
27561 | Modoc CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 9220FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27562 | Modoc CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
27563 | Modoc CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 9220SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
27564 | Modoc CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9203SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27565 | Modoc CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9204SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27566 | Modoc CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9205SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27567 | Modoc CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9206SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27568 | Modoc CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9207SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27569 | Modoc CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27570 | Modoc CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 9211FS+12d,9213SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27571 | CARES V1 - Mono CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.25
27572 | Mono CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
27573 | Mono CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
27574 | Mono CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
27575 | Mono CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
27576 | Mono CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
27577 | Mono CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
27578 | Mono CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27579 | Mono CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
27580 | Mono CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
27581 | Mono CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
27582 | Mono CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
27583 | Mono CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.40000000000000002
27584 | Mono CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.65000000000000002
27585 | Mono CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
27586 | Mono CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
27587 | Mono CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
27588 | Mono CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
27589 | Mono CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
27590 | Mono CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
27591 | Mono CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
27592 | Mono CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
27593 | Mono CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
27594 | Mono CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
27595 | Mono CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
27596 | Mono CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
27597 | Mono CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
27598 | Mono CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
27599 | Mono CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
27600 | Mono CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
27601 | Mono CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
27602 | Mono CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
27603 | Mono CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
27604 | Mono CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
27605 | Mono CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
27606 | Mono CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/30/25 | NA | 1
27607 | Mono CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
27608 | Mono CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
27609 | Mono CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
27610 | Mono CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
27611 | Mono CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
27612 | Mono CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
27613 | Mono CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
27614 | Mono CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27615 | Mono CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27616 | Mono CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
27617 | Mono CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27618 | Mono CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
27619 | Mono CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
27620 | Mono CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
27621 | Mono CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
27622 | Mono CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
27623 | Mono CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
27624 | Mono CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
27625 | Mono CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
27626 | Mono CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 9277SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
27627 | Mono CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 9276SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
27628 | Mono CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 9279SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27629 | Mono CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 9278SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27630 | Mono CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
27631 | Mono CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 9282SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
27632 | Mono CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 9281SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
27633 | Mono CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27634 | Mono CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 9285SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
27635 | Mono CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 9284SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
27636 | Mono CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27637 | Mono CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 9288SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27638 | Mono CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 9287SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27639 | Mono CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27640 | Mono CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 9291SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
27641 | Mono CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 9290SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
27642 | Mono CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
27643 | Mono CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.33000000000000002
27644 | Mono CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
27645 | Mono CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 9296 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
27646 | Mono CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 9295 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
27647 | Mono CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
27648 | Mono CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
27649 | Mono CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
27650 | Mono CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27651 | Mono CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 9302 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
27652 | Mono CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 9301 | 9303 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
27653 | Mono CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 9302 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
27654 | Mono CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27655 | Mono CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 9306 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
27656 | Mono CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 9305 | 9307 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
27657 | Mono CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 9306 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27658 | Mono CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27659 | Mono CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 9310 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
27660 | Mono CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 9309 | 9311 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27661 | Mono CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 9310 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27662 | Mono CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27663 | Mono CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 9314 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27664 | Mono CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 9313 | 9315 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27665 | Mono CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 9314 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27666 | Mono CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27667 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27668 | Mono CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.27000000000000002
27669 | Mono CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.47999999999999998
27670 | Mono CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 9321SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
27671 | Mono CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 9320SS | 9322 | As Soon As Possible | NA | 490 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27672 | Mono CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 9321 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27673 | Mono CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
27674 | Mono CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
27675 | Mono CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
27676 | Mono CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 9328 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
27677 | Mono CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
27678 | Mono CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 9326 | 9329,9331SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
27679 | Mono CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 9328 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
27680 | Mono CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
27681 | Mono CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 9328SS | 9332SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
27682 | Mono CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 9331SS | 9333,9336,9334SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27683 | Mono CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 9332 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27684 | Mono CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 9332SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27685 | Mono CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27686 | Mono CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 9332 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
27687 | Mono CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
27688 | Mono CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
27689 | Mono CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 9345 | 9340SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
27690 | Mono CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 9339SS | 9342 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
27691 | Mono CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
27692 | Mono CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 9340 | 9343 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
27693 | Mono CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 9342 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
27694 | Mono CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
27695 | Mono CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 9339,9346SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
27696 | Mono CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 9345SS | 9350,9347 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27697 | Mono CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 9346 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27698 | Mono CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27699 | Mono CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27700 | Mono CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 9346 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
27701 | Mono CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27702 | Mono CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27703 | Mono CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27704 | Mono CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27705 | Mono CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27706 | Mono CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27707 | Mono CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27708 | Mono CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27709 | Mono CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27710 | Mono CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27711 | Mono CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27712 | Mono CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27713 | Mono CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
27714 | Mono CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 2.9999999999999999E-2
27715 | Mono CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 9372 | Start No Earlier Than | 7/1/25 | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
27716 | Mono CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
27717 | Mono CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
27718 | Mono CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27719 | Mono CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27720 | Mono CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 9379 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27721 | Mono CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 9380 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27722 | Mono CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 9365 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
27723 | Mono CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27724 | Mono CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9385SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27725 | Mono CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9386SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27726 | Mono CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9387SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27727 | Mono CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9388SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27728 | Mono CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9389SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27729 | Mono CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 9370 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27730 | Mono CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 9371 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27731 | Mono CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
27732 | Mono CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 9391FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27733 | Mono CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
27734 | Mono CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 9391SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
27735 | Mono CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9374SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27736 | Mono CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9375SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27737 | Mono CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9376SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27738 | Mono CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9377SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27739 | Mono CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9378SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27740 | Mono CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27741 | Mono CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 9382FS+12d,9384SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27742 | CARES V1 - Monterey CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.39000000000000001
27743 | Monterey CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
27744 | Monterey CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
27745 | Monterey CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
27746 | Monterey CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
27747 | Monterey CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
27748 | Monterey CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
27749 | Monterey CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27750 | Monterey CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
27751 | Monterey CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
27752 | Monterey CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
27753 | Monterey CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
27754 | Monterey CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.42999999999999999
27755 | Monterey CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.65000000000000002
27756 | Monterey CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
27757 | Monterey CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
27758 | Monterey CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
27759 | Monterey CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
27760 | Monterey CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
27761 | Monterey CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
27762 | Monterey CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
27763 | Monterey CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
27764 | Monterey CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
27765 | Monterey CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
27766 | Monterey CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
27767 | Monterey CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
27768 | Monterey CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
27769 | Monterey CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
27770 | Monterey CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
27771 | Monterey CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
27772 | Monterey CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
27773 | Monterey CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
27774 | Monterey CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
27775 | Monterey CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
27776 | Monterey CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
27777 | Monterey CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/30/25 | NA | 1
27778 | Monterey CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
27779 | Monterey CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
27780 | Monterey CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
27781 | Monterey CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
27782 | Monterey CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
27783 | Monterey CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
27784 | Monterey CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
27785 | Monterey CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27786 | Monterey CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27787 | Monterey CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
27788 | Monterey CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27789 | Monterey CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
27790 | Monterey CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
27791 | Monterey CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
27792 | Monterey CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
27793 | Monterey CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
27794 | Monterey CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
27795 | Monterey CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
27796 | Monterey CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.94999999999999996
27797 | Monterey CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 9448SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
27798 | Monterey CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 9447SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
27799 | Monterey CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 9450SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27800 | Monterey CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 9449SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27801 | Monterey CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
27802 | Monterey CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 9453SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
27803 | Monterey CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 9452SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
27804 | Monterey CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27805 | Monterey CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 9456SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
27806 | Monterey CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 9455SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
27807 | Monterey CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27808 | Monterey CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 9459SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27809 | Monterey CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 9458SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27810 | Monterey CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27811 | Monterey CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 9462SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
27812 | Monterey CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 9461SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
27813 | Monterey CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
27814 | Monterey CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.5
27815 | Monterey CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
27816 | Monterey CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 9467 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
27817 | Monterey CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 9466 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
27818 | Monterey CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
27819 | Monterey CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
27820 | Monterey CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
27821 | Monterey CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27822 | Monterey CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 9473 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
27823 | Monterey CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 9472 | 9474 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
27824 | Monterey CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 9473 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
27825 | Monterey CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27826 | Monterey CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 9477 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
27827 | Monterey CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 9476 | 9478 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
27828 | Monterey CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 9477 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27829 | Monterey CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27830 | Monterey CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 9481 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
27831 | Monterey CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 9480 | 9482 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27832 | Monterey CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 9481 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
27833 | Monterey CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27834 | Monterey CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 9485 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27835 | Monterey CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 9484 | 9486 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27836 | Monterey CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 9485 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27837 | Monterey CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27838 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27839 | Monterey CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.51000000000000001
27840 | Monterey CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.93000000000000005
27841 | Monterey CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 9492SS | As Soon As Possible | NA | 490 | 405d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
27842 | Monterey CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 9491SS | 9493 | As Soon As Possible | NA | 490 | 28.8d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
27843 | Monterey CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 9492 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.59999999999999998
27844 | Monterey CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
27845 | Monterey CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
27846 | Monterey CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
27847 | Monterey CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 9499 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
27848 | Monterey CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.68999999999999995
27849 | Monterey CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 9497 | 9500,9502SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
27850 | Monterey CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 9499 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
27851 | Monterey CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
27852 | Monterey CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 9499SS | 9503SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
27853 | Monterey CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 9502SS | 9504,9507,9505SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
27854 | Monterey CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 9503 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27855 | Monterey CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 9503SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27856 | Monterey CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27857 | Monterey CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 9503 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
27858 | Monterey CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 0d | NA | NA | 0 days? | No | 2/3/25 | 12/31/25 | NA | 1
27859 | Monterey CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 9510SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
27860 | Monterey CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 9509SS | 9511SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
27861 | Monterey CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 9510SS |  | As Soon As Possible | NA | 230 | 0d | NA | NA | 0 days? | No | 2/3/25 | 12/31/25 | NA | 1
27862 | Monterey CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
27863 | Monterey CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
27864 | Monterey CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 9520 | 9515SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
27865 | Monterey CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 9514SS | 9517 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
27866 | Monterey CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
27867 | Monterey CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 9515 | 9518 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
27868 | Monterey CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 9517 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
27869 | Monterey CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.25
27870 | Monterey CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 9514,9521SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
27871 | Monterey CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 9520SS | 9525,9522 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.59999999999999998
27872 | Monterey CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 9521 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27873 | Monterey CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
27874 | Monterey CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27875 | Monterey CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 9521 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
27876 | Monterey CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27877 | Monterey CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27878 | Monterey CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27879 | Monterey CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27880 | Monterey CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27881 | Monterey CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27882 | Monterey CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27883 | Monterey CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27884 | Monterey CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27885 | Monterey CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27886 | Monterey CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27887 | Monterey CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27888 | Monterey CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
27889 | Monterey CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 2.9999999999999999E-2
27890 | Monterey CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 9547 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
27891 | Monterey CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
27892 | Monterey CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
27893 | Monterey CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27894 | Monterey CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27895 | Monterey CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 9554 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27896 | Monterey CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 9555 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27897 | Monterey CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 9540 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
27898 | Monterey CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27899 | Monterey CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9560SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27900 | Monterey CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9561SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27901 | Monterey CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9562SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27902 | Monterey CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9563SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27903 | Monterey CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9564SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
27904 | Monterey CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 9545 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27905 | Monterey CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 9546 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
27906 | Monterey CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
27907 | Monterey CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 9566FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27908 | Monterey CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
27909 | Monterey CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 9566SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
27910 | Monterey CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9549SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27911 | Monterey CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9550SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27912 | Monterey CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9551SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27913 | Monterey CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9552SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27914 | Monterey CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9553SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27915 | Monterey CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27916 | Monterey CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 9557FS+12d,9559SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
27917 | CARES V1 - Napa CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.34999999999999998
27918 | Napa CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.56000000000000005
27919 | Napa CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.63
27920 | Napa CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
27921 | Napa CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
27922 | Napa CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
27923 | Napa CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
27924 | Napa CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.59999999999999998
27925 | Napa CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
27926 | Napa CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
27927 | Napa CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
27928 | Napa CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
27929 | Napa CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
27930 | Napa CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
27931 | Napa CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
27932 | Napa CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
27933 | Napa CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
27934 | Napa CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
27935 | Napa CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
27936 | Napa CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
27937 | Napa CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
27938 | Napa CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
27939 | Napa CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
27940 | Napa CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
27941 | Napa CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
27942 | Napa CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
27943 | Napa CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
27944 | Napa CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
27945 | Napa CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
27946 | Napa CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
27947 | Napa CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
27948 | Napa CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
27949 | Napa CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
27950 | Napa CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
27951 | Napa CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
27952 | Napa CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
27953 | Napa CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
27954 | Napa CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
27955 | Napa CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
27956 | Napa CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
27957 | Napa CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
27958 | Napa CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
27959 | Napa CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
27960 | Napa CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
27961 | Napa CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
27962 | Napa CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
27963 | Napa CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27964 | Napa CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
27965 | Napa CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
27966 | Napa CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
27967 | Napa CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
27968 | Napa CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
27969 | Napa CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
27970 | Napa CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
27971 | Napa CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
27972 | Napa CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 9623SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
27973 | Napa CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 9622SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
27974 | Napa CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 9625SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27975 | Napa CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 9624SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
27976 | Napa CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
27977 | Napa CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 9628SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
27978 | Napa CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 9627SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
27979 | Napa CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27980 | Napa CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 9631SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
27981 | Napa CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 9630SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
27982 | Napa CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27983 | Napa CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 9634SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27984 | Napa CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 9633SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
27985 | Napa CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
27986 | Napa CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 9637SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
27987 | Napa CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 9636SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
27988 | Napa CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
27989 | Napa CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.46000000000000002
27990 | Napa CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
27991 | Napa CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 9642 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
27992 | Napa CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 9641 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
27993 | Napa CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
27994 | Napa CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
27995 | Napa CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
27996 | Napa CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
27997 | Napa CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 9648 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
27998 | Napa CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 9647 | 9649 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
27999 | Napa CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 9648 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
28000 | Napa CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28001 | Napa CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 9652 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
28002 | Napa CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 9651 | 9653 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28003 | Napa CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 9652 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28004 | Napa CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28005 | Napa CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 9656 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28006 | Napa CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 9655 | 9657 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28007 | Napa CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 9656 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28008 | Napa CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28009 | Napa CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 9660 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28010 | Napa CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 9659 | 9661 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28011 | Napa CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 9660 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28012 | Napa CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28013 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28014 | Napa CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.45000000000000001
28015 | Napa CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.95999999999999996
28016 | Napa CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 9667SS | Start No Earlier Than | 3/19/24 | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
28017 | Napa CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 9666SS | 9668 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
28018 | Napa CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 9667 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.20000000000000001
28019 | Napa CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
28020 | Napa CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
28021 | Napa CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
28022 | Napa CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 9674 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
28023 | Napa CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.60999999999999999
28024 | Napa CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 9672 | 9675,9677SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
28025 | Napa CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 9674 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
28026 | Napa CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
28027 | Napa CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 9674SS | 9678SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
28028 | Napa CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 9677SS | 9679,9682,9680SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28029 | Napa CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 9678 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28030 | Napa CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 9678SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28031 | Napa CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28032 | Napa CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 9678 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
28033 | Napa CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.77000000000000002
28034 | Napa CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 9685SS | Start No Earlier Than | 2/3/25 | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
28035 | Napa CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 9684SS | 9686SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
28036 | Napa CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 9685SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.40000000000000002
28037 | Napa CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
28038 | Napa CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
28039 | Napa CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 9695 | 9690SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
28040 | Napa CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 9689SS | 9692 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
28041 | Napa CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
28042 | Napa CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 9690 | 9693 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
28043 | Napa CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 9692 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
28044 | Napa CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
28045 | Napa CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 9689,9696SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
28046 | Napa CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 9695SS | 9700,9697 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28047 | Napa CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 9696 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28048 | Napa CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28049 | Napa CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28050 | Napa CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 9696 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
28051 | Napa CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28052 | Napa CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28053 | Napa CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28054 | Napa CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28055 | Napa CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28056 | Napa CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28057 | Napa CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28058 | Napa CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28059 | Napa CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28060 | Napa CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28061 | Napa CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28062 | Napa CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28063 | Napa CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
28064 | Napa CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
28065 | Napa CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 9722 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
28066 | Napa CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
28067 | Napa CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
28068 | Napa CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28069 | Napa CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28070 | Napa CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 9729 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28071 | Napa CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 9730 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28072 | Napa CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 9715 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
28073 | Napa CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28074 | Napa CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9735SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28075 | Napa CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9736SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28076 | Napa CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9737SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28077 | Napa CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9738SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28078 | Napa CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9739SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28079 | Napa CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 9720 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28080 | Napa CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 9721 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28081 | Napa CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
28082 | Napa CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 9741FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28083 | Napa CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
28084 | Napa CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 9741SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
28085 | Napa CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9724SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28086 | Napa CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9725SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28087 | Napa CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9726SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28088 | Napa CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9727SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28089 | Napa CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9728SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28090 | Napa CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28091 | Napa CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 9732FS+12d,9734SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28092 | CARES V1 - Nevada CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.39000000000000001
28093 | Nevada CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
28094 | Nevada CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
28095 | Nevada CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
28096 | Nevada CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
28097 | Nevada CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
28098 | Nevada CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
28099 | Nevada CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28100 | Nevada CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
28101 | Nevada CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
28102 | Nevada CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
28103 | Nevada CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
28104 | Nevada CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
28105 | Nevada CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
28106 | Nevada CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
28107 | Nevada CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
28108 | Nevada CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
28109 | Nevada CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
28110 | Nevada CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
28111 | Nevada CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
28112 | Nevada CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
28113 | Nevada CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
28114 | Nevada CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
28115 | Nevada CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
28116 | Nevada CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
28117 | Nevada CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
28118 | Nevada CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
28119 | Nevada CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
28120 | Nevada CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
28121 | Nevada CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
28122 | Nevada CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
28123 | Nevada CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
28124 | Nevada CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
28125 | Nevada CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
28126 | Nevada CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
28127 | Nevada CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
28128 | Nevada CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
28129 | Nevada CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
28130 | Nevada CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
28131 | Nevada CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
28132 | Nevada CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
28133 | Nevada CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
28134 | Nevada CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
28135 | Nevada CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28136 | Nevada CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28137 | Nevada CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
28138 | Nevada CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
28139 | Nevada CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
28140 | Nevada CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
28141 | Nevada CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
28142 | Nevada CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
28143 | Nevada CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
28144 | Nevada CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
28145 | Nevada CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
28146 | Nevada CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
28147 | Nevada CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 9798SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
28148 | Nevada CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 9797SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
28149 | Nevada CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 9800SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28150 | Nevada CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 9799SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28151 | Nevada CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
28152 | Nevada CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 9803SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
28153 | Nevada CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 9802SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
28154 | Nevada CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
28155 | Nevada CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 9806SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
28156 | Nevada CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 9805SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
28157 | Nevada CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
28158 | Nevada CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 9809SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
28159 | Nevada CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 9808SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
28160 | Nevada CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
28161 | Nevada CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 9812SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
28162 | Nevada CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 9811SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
28163 | Nevada CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
28164 | Nevada CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.48999999999999999
28165 | Nevada CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
28166 | Nevada CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 9817 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
28167 | Nevada CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 9816 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
28168 | Nevada CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
28169 | Nevada CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
28170 | Nevada CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
28171 | Nevada CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28172 | Nevada CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 9823 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
28173 | Nevada CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 9822 | 9824 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
28174 | Nevada CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 9823 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
28175 | Nevada CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28176 | Nevada CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 9827 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
28177 | Nevada CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 9826 | 9828 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.80000000000000004
28178 | Nevada CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 9827 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28179 | Nevada CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28180 | Nevada CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 9831 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
28181 | Nevada CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 9830 | 9832 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28182 | Nevada CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 9831 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28183 | Nevada CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28184 | Nevada CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 9835 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28185 | Nevada CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 9834 | 9836 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28186 | Nevada CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 9835 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28187 | Nevada CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28188 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28189 | Nevada CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.55000000000000004
28190 | Nevada CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.95999999999999996
28191 | Nevada CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 9842SS | Start No Earlier Than | 3/19/24 | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
28192 | Nevada CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 9841SS | 9843 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
28193 | Nevada CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 9842 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.20000000000000001
28194 | Nevada CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
28195 | Nevada CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
28196 | Nevada CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
28197 | Nevada CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 9849 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
28198 | Nevada CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
28199 | Nevada CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 9847 | 9850,9852SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
28200 | Nevada CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 9849 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
28201 | Nevada CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
28202 | Nevada CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 9849SS | 9853SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
28203 | Nevada CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 9852SS | 9854,9857,9855SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
28204 | Nevada CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 9853 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28205 | Nevada CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 9853SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28206 | Nevada CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28207 | Nevada CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 9853 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
28208 | Nevada CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 0d | NA | NA | 0 days? | No | 2/3/25 | 12/31/25 | NA | 1
28209 | Nevada CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 9860SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
28210 | Nevada CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 9859SS | 9861SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
28211 | Nevada CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 9860SS |  | As Soon As Possible | NA | 230 | 0d | NA | NA | 0 days? | No | 2/3/25 | 12/31/25 | NA | 1
28212 | Nevada CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
28213 | Nevada CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
28214 | Nevada CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 9870 | 9865SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
28215 | Nevada CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 9864SS | 9867 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
28216 | Nevada CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
28217 | Nevada CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 9865 | 9868 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
28218 | Nevada CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 9867 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
28219 | Nevada CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
28220 | Nevada CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 9864,9871SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
28221 | Nevada CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 9870SS | 9875,9872 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
28222 | Nevada CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 9871 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28223 | Nevada CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
28224 | Nevada CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28225 | Nevada CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 9871 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
28226 | Nevada CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 363d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28227 | Nevada CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28228 | Nevada CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28229 | Nevada CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28230 | Nevada CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28231 | Nevada CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28232 | Nevada CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28233 | Nevada CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28234 | Nevada CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28235 | Nevada CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28236 | Nevada CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28237 | Nevada CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28238 | Nevada CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
28239 | Nevada CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
28240 | Nevada CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 9897 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
28241 | Nevada CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
28242 | Nevada CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
28243 | Nevada CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28244 | Nevada CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28245 | Nevada CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 9904 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28246 | Nevada CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 9905 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28247 | Nevada CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 9890 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
28248 | Nevada CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28249 | Nevada CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9910SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28250 | Nevada CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9911SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28251 | Nevada CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9912SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28252 | Nevada CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9913SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28253 | Nevada CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 9914SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28254 | Nevada CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 9895 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28255 | Nevada CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 9896 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28256 | Nevada CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
28257 | Nevada CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 9916FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28258 | Nevada CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
28259 | Nevada CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 9916SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
28260 | Nevada CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9899SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28261 | Nevada CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9900SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28262 | Nevada CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9901SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28263 | Nevada CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9902SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28264 | Nevada CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 9903SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28265 | Nevada CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28266 | Nevada CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 9907FS+12d,9909SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28267 | CARES V1 - Orange CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.31
28268 | Orange CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
28269 | Orange CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
28270 | Orange CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
28271 | Orange CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
28272 | Orange CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
28273 | Orange CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
28274 | Orange CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28275 | Orange CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
28276 | Orange CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
28277 | Orange CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
28278 | Orange CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
28279 | Orange CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
28280 | Orange CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
28281 | Orange CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
28282 | Orange CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
28283 | Orange CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
28284 | Orange CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
28285 | Orange CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
28286 | Orange CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
28287 | Orange CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
28288 | Orange CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
28289 | Orange CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
28290 | Orange CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
28291 | Orange CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
28292 | Orange CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
28293 | Orange CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
28294 | Orange CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
28295 | Orange CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
28296 | Orange CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
28297 | Orange CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
28298 | Orange CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
28299 | Orange CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
28300 | Orange CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
28301 | Orange CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
28302 | Orange CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
28303 | Orange CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
28304 | Orange CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
28305 | Orange CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
28306 | Orange CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
28307 | Orange CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
28308 | Orange CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
28309 | Orange CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
28310 | Orange CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28311 | Orange CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28312 | Orange CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
28313 | Orange CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
28314 | Orange CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
28315 | Orange CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
28316 | Orange CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
28317 | Orange CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
28318 | Orange CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
28319 | Orange CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
28320 | Orange CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
28321 | Orange CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
28322 | Orange CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 9973SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
28323 | Orange CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 9972SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
28324 | Orange CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 9975SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28325 | Orange CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 9974SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28326 | Orange CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
28327 | Orange CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 9978SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
28328 | Orange CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 9977SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
28329 | Orange CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
28330 | Orange CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 9981SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
28331 | Orange CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 9980SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
28332 | Orange CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
28333 | Orange CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 9984SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
28334 | Orange CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 9983SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
28335 | Orange CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
28336 | Orange CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 9987SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
28337 | Orange CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 9986SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
28338 | Orange CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
28339 | Orange CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.47999999999999998
28340 | Orange CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
28341 | Orange CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 9992 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
28342 | Orange CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 9991 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
28343 | Orange CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
28344 | Orange CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
28345 | Orange CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
28346 | Orange CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28347 | Orange CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 9998 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
28348 | Orange CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 9997 | 9999 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
28349 | Orange CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 9998 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
28350 | Orange CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28351 | Orange CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 10002 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
28352 | Orange CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 10001 | 10003 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
28353 | Orange CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 10002 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28354 | Orange CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28355 | Orange CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 10006 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
28356 | Orange CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 10005 | 10007 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28357 | Orange CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 10006 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28358 | Orange CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28359 | Orange CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 10010 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28360 | Orange CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 10009 | 10011 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28361 | Orange CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 10010 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28362 | Orange CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28363 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28364 | Orange CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.37
28365 | Orange CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.67000000000000004
28366 | Orange CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 10017SS | As Soon As Possible | NA | 490 | 405d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.80000000000000004
28367 | Orange CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 10016SS | 10018 | As Soon As Possible | NA | 490 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.59999999999999998
28368 | Orange CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 10017 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28369 | Orange CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
28370 | Orange CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
28371 | Orange CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
28372 | Orange CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 10024 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
28373 | Orange CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.68999999999999995
28374 | Orange CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 10022 | 10025,10027SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
28375 | Orange CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 10024 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
28376 | Orange CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
28377 | Orange CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 10024SS | 10028SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
28378 | Orange CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 10027SS | 10029,10032,10030SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28379 | Orange CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 10028 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28380 | Orange CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 10028SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28381 | Orange CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28382 | Orange CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 10028 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
28383 | Orange CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.70999999999999996
28384 | Orange CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 10035SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
28385 | Orange CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 10034SS | 10036SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.80000000000000004
28386 | Orange CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 10035SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.40000000000000002
28387 | Orange CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
28388 | Orange CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
28389 | Orange CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 10045 | 10040SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
28390 | Orange CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 10039SS | 10042 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
28391 | Orange CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 508d | NA | NA | 0 days? | No | 7/21/25 | NA | NA | 0.75
28392 | Orange CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 10040 | 10043 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
28393 | Orange CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 10042 |  | As Soon As Possible | NA | 21 | 508d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
28394 | Orange CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
28395 | Orange CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 10039,10046SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
28396 | Orange CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 10045SS | 10050,10047 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28397 | Orange CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 10046 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28398 | Orange CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28399 | Orange CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28400 | Orange CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 10046 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
28401 | Orange CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28402 | Orange CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28403 | Orange CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28404 | Orange CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28405 | Orange CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28406 | Orange CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28407 | Orange CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28408 | Orange CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28409 | Orange CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28410 | Orange CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28411 | Orange CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28412 | Orange CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28413 | Orange CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
28414 | Orange CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
28415 | Orange CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 10072 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
28416 | Orange CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
28417 | Orange CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
28418 | Orange CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28419 | Orange CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28420 | Orange CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 10079 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28421 | Orange CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 10080 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28422 | Orange CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 10065 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
28423 | Orange CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28424 | Orange CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10085SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28425 | Orange CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10086SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28426 | Orange CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10087SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28427 | Orange CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10088SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28428 | Orange CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10089SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28429 | Orange CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 10070 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28430 | Orange CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 10071 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28431 | Orange CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
28432 | Orange CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 10091FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28433 | Orange CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
28434 | Orange CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 10091SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
28435 | Orange CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10074SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28436 | Orange CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10075SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28437 | Orange CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10076SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28438 | Orange CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10077SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28439 | Orange CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10078SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28440 | Orange CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28441 | Orange CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 10082FS+12d,10084SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28442 | CARES V1 - Placer CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.42999999999999999
28443 | Placer CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
28444 | Placer CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
28445 | Placer CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
28446 | Placer CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
28447 | Placer CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
28448 | Placer CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
28449 | Placer CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28450 | Placer CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
28451 | Placer CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
28452 | Placer CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
28453 | Placer CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
28454 | Placer CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
28455 | Placer CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
28456 | Placer CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
28457 | Placer CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
28458 | Placer CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
28459 | Placer CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
28460 | Placer CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
28461 | Placer CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
28462 | Placer CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
28463 | Placer CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
28464 | Placer CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
28465 | Placer CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
28466 | Placer CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
28467 | Placer CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
28468 | Placer CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
28469 | Placer CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
28470 | Placer CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
28471 | Placer CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
28472 | Placer CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
28473 | Placer CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
28474 | Placer CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
28475 | Placer CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
28476 | Placer CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
28477 | Placer CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
28478 | Placer CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
28479 | Placer CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
28480 | Placer CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
28481 | Placer CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
28482 | Placer CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
28483 | Placer CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
28484 | Placer CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
28485 | Placer CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28486 | Placer CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28487 | Placer CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
28488 | Placer CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
28489 | Placer CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
28490 | Placer CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
28491 | Placer CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
28492 | Placer CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
28493 | Placer CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
28494 | Placer CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
28495 | Placer CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
28496 | Placer CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
28497 | Placer CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 10148SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
28498 | Placer CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 10147SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
28499 | Placer CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 10150SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28500 | Placer CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 10149SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28501 | Placer CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
28502 | Placer CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 10153SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
28503 | Placer CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 10152SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
28504 | Placer CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
28505 | Placer CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 10156SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
28506 | Placer CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 10155SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
28507 | Placer CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
28508 | Placer CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 10159SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
28509 | Placer CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 10158SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
28510 | Placer CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
28511 | Placer CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 10162SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
28512 | Placer CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 10161SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
28513 | Placer CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
28514 | Placer CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.66000000000000003
28515 | Placer CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
28516 | Placer CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 10167 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
28517 | Placer CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 10166 |  | As Soon As Possible | NA | 631 | 0d | NA | NA | 0 days? | No | 5/1/24 | 11/2/26 | NA | 1
28518 | Placer CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
28519 | Placer CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
28520 | Placer CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
28521 | Placer CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28522 | Placer CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 10173 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
28523 | Placer CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 10172 | 10174 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
28524 | Placer CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 10173 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
28525 | Placer CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28526 | Placer CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 10177 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
28527 | Placer CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 10176 | 10178 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.80000000000000004
28528 | Placer CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 10177 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28529 | Placer CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28530 | Placer CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 10181 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
28531 | Placer CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 10180 | 10182 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28532 | Placer CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 10181 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28533 | Placer CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28534 | Placer CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 10185 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28535 | Placer CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 10184 | 10186 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28536 | Placer CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 10185 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28537 | Placer CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28538 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28539 | Placer CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.56999999999999995
28540 | Placer CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.98999999999999999
28541 | Placer CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 10192SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
28542 | Placer CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 10191SS | 10193 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
28543 | Placer CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 10192 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.80000000000000004
28544 | Placer CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
28545 | Placer CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
28546 | Placer CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
28547 | Placer CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 10199 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
28548 | Placer CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
28549 | Placer CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 10197 | 10200,10202SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
28550 | Placer CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 10199 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
28551 | Placer CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
28552 | Placer CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 10199SS | 10203SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
28553 | Placer CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 10202SS | 10204,10207,10205SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
28554 | Placer CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 10203 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28555 | Placer CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 10203SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28556 | Placer CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28557 | Placer CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 10203 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
28558 | Placer CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.77000000000000002
28559 | Placer CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 10210SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
28560 | Placer CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 10209SS | 10211SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
28561 | Placer CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 10210SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.40000000000000002
28562 | Placer CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
28563 | Placer CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
28564 | Placer CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 10220 | 10215SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
28565 | Placer CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 10214SS | 10217 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
28566 | Placer CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
28567 | Placer CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 10215 | 10218 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
28568 | Placer CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 10217 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
28569 | Placer CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.42999999999999999
28570 | Placer CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 10214,10221SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
28571 | Placer CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 10220SS | 10225,10222 | As Soon As Possible | NA | 210 | 0d | NA | NA | 0 days? | No | 7/1/25 | 5/1/26 | NA | 1
28572 | Placer CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 10221 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28573 | Placer CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
28574 | Placer CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28575 | Placer CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 10221 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
28576 | Placer CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 363d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28577 | Placer CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28578 | Placer CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28579 | Placer CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28580 | Placer CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28581 | Placer CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28582 | Placer CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28583 | Placer CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28584 | Placer CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28585 | Placer CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28586 | Placer CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28587 | Placer CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
28588 | Placer CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
28589 | Placer CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
28590 | Placer CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 10247 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
28591 | Placer CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
28592 | Placer CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
28593 | Placer CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28594 | Placer CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28595 | Placer CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 10254 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28596 | Placer CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 10255 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28597 | Placer CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 10240 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
28598 | Placer CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28599 | Placer CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10260SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28600 | Placer CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10261SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28601 | Placer CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10262SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28602 | Placer CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10263SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28603 | Placer CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10264SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28604 | Placer CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 10245 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28605 | Placer CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 10246 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28606 | Placer CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
28607 | Placer CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 10266FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28608 | Placer CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
28609 | Placer CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 10266SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
28610 | Placer CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10249SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28611 | Placer CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10250SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28612 | Placer CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10251SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28613 | Placer CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10252SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28614 | Placer CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10253SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28615 | Placer CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28616 | Placer CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 10257FS+12d,10259SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28617 | CARES V1 - Plumas CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.35999999999999999
28618 | Plumas CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
28619 | Plumas CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
28620 | Plumas CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
28621 | Plumas CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
28622 | Plumas CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
28623 | Plumas CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
28624 | Plumas CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28625 | Plumas CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
28626 | Plumas CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
28627 | Plumas CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
28628 | Plumas CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
28629 | Plumas CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
28630 | Plumas CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
28631 | Plumas CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
28632 | Plumas CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
28633 | Plumas CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
28634 | Plumas CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
28635 | Plumas CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
28636 | Plumas CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
28637 | Plumas CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
28638 | Plumas CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
28639 | Plumas CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
28640 | Plumas CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
28641 | Plumas CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
28642 | Plumas CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
28643 | Plumas CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
28644 | Plumas CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
28645 | Plumas CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
28646 | Plumas CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
28647 | Plumas CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
28648 | Plumas CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
28649 | Plumas CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
28650 | Plumas CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
28651 | Plumas CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
28652 | Plumas CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
28653 | Plumas CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
28654 | Plumas CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
28655 | Plumas CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
28656 | Plumas CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
28657 | Plumas CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
28658 | Plumas CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
28659 | Plumas CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
28660 | Plumas CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28661 | Plumas CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28662 | Plumas CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
28663 | Plumas CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
28664 | Plumas CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
28665 | Plumas CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
28666 | Plumas CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
28667 | Plumas CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
28668 | Plumas CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
28669 | Plumas CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
28670 | Plumas CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
28671 | Plumas CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
28672 | Plumas CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 10323SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
28673 | Plumas CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 10322SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
28674 | Plumas CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 10325SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28675 | Plumas CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 10324SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28676 | Plumas CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
28677 | Plumas CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 10328SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
28678 | Plumas CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 10327SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
28679 | Plumas CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
28680 | Plumas CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 10331SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
28681 | Plumas CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 10330SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
28682 | Plumas CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
28683 | Plumas CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 10334SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
28684 | Plumas CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 10333SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
28685 | Plumas CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
28686 | Plumas CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 10337SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
28687 | Plumas CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 10336SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
28688 | Plumas CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
28689 | Plumas CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.41999999999999998
28690 | Plumas CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
28691 | Plumas CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 10342 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
28692 | Plumas CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 10341 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.40000000000000002
28693 | Plumas CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
28694 | Plumas CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
28695 | Plumas CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
28696 | Plumas CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28697 | Plumas CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 10348 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
28698 | Plumas CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 10347 | 10349 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
28699 | Plumas CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 10348 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
28700 | Plumas CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28701 | Plumas CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 10352 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
28702 | Plumas CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 10351 | 10353 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
28703 | Plumas CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 10352 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28704 | Plumas CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28705 | Plumas CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 10356 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
28706 | Plumas CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 10355 | 10357 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28707 | Plumas CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 10356 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28708 | Plumas CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28709 | Plumas CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 10360 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28710 | Plumas CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 10359 | 10361 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28711 | Plumas CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 10360 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28712 | Plumas CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28713 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28714 | Plumas CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.5
28715 | Plumas CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
28716 | Plumas CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 10367SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
28717 | Plumas CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 10366SS | 10368 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
28718 | Plumas CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 10367 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28719 | Plumas CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
28720 | Plumas CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
28721 | Plumas CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
28722 | Plumas CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 10374 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
28723 | Plumas CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.60999999999999999
28724 | Plumas CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 10372 | 10375,10377SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
28725 | Plumas CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 10374 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
28726 | Plumas CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
28727 | Plumas CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 10374SS | 10378SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
28728 | Plumas CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 10377SS | 10379,10382,10380SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
28729 | Plumas CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 10378 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28730 | Plumas CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 10378SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28731 | Plumas CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28732 | Plumas CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 10378 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
28733 | Plumas CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 0d | NA | NA | 0 days? | No | 2/3/25 | 12/31/25 | NA | 1
28734 | Plumas CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 10385SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
28735 | Plumas CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 10384SS | 10386SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
28736 | Plumas CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 10385SS |  | As Soon As Possible | NA | 230 | 0d | NA | NA | 0 days? | No | 2/3/25 | 12/31/25 | NA | 1
28737 | Plumas CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
28738 | Plumas CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
28739 | Plumas CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 10395 | 10390SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
28740 | Plumas CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 10389SS | 10392 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
28741 | Plumas CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
28742 | Plumas CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 10390 | 10393 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
28743 | Plumas CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 10392 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
28744 | Plumas CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
28745 | Plumas CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 10389,10396SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
28746 | Plumas CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 10395SS | 10400,10397 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
28747 | Plumas CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 10396 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28748 | Plumas CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
28749 | Plumas CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28750 | Plumas CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 10396 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
28751 | Plumas CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28752 | Plumas CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28753 | Plumas CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28754 | Plumas CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28755 | Plumas CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28756 | Plumas CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28757 | Plumas CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28758 | Plumas CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28759 | Plumas CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28760 | Plumas CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28761 | Plumas CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28762 | Plumas CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28763 | Plumas CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
28764 | Plumas CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
28765 | Plumas CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 10422 | Start No Earlier Than | 7/1/25 | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
28766 | Plumas CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
28767 | Plumas CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
28768 | Plumas CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28769 | Plumas CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28770 | Plumas CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 10429 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28771 | Plumas CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 10430 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28772 | Plumas CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 10415 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
28773 | Plumas CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28774 | Plumas CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10435SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28775 | Plumas CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10436SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28776 | Plumas CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10437SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28777 | Plumas CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10438SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28778 | Plumas CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10439SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28779 | Plumas CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 10420 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28780 | Plumas CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 10421 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28781 | Plumas CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
28782 | Plumas CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 10441FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28783 | Plumas CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
28784 | Plumas CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 10441SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
28785 | Plumas CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10424SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28786 | Plumas CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10425SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28787 | Plumas CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10426SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28788 | Plumas CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10427SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28789 | Plumas CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10428SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28790 | Plumas CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28791 | Plumas CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 10432FS+12d,10434SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28792 | CARES V1 - Sacramento CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.34000000000000002
28793 | Sacramento CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
28794 | Sacramento CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
28795 | Sacramento CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
28796 | Sacramento CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
28797 | Sacramento CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
28798 | Sacramento CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
28799 | Sacramento CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28800 | Sacramento CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
28801 | Sacramento CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
28802 | Sacramento CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
28803 | Sacramento CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
28804 | Sacramento CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
28805 | Sacramento CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
28806 | Sacramento CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
28807 | Sacramento CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
28808 | Sacramento CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
28809 | Sacramento CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
28810 | Sacramento CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
28811 | Sacramento CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
28812 | Sacramento CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
28813 | Sacramento CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
28814 | Sacramento CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
28815 | Sacramento CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
28816 | Sacramento CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
28817 | Sacramento CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
28818 | Sacramento CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
28819 | Sacramento CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
28820 | Sacramento CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
28821 | Sacramento CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
28822 | Sacramento CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
28823 | Sacramento CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
28824 | Sacramento CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
28825 | Sacramento CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
28826 | Sacramento CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
28827 | Sacramento CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
28828 | Sacramento CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
28829 | Sacramento CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
28830 | Sacramento CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
28831 | Sacramento CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
28832 | Sacramento CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
28833 | Sacramento CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
28834 | Sacramento CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
28835 | Sacramento CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28836 | Sacramento CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28837 | Sacramento CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
28838 | Sacramento CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
28839 | Sacramento CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
28840 | Sacramento CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
28841 | Sacramento CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
28842 | Sacramento CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
28843 | Sacramento CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
28844 | Sacramento CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
28845 | Sacramento CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
28846 | Sacramento CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
28847 | Sacramento CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 10498SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
28848 | Sacramento CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 10497SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
28849 | Sacramento CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 10500SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28850 | Sacramento CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 10499SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28851 | Sacramento CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
28852 | Sacramento CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 10503SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
28853 | Sacramento CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 10502SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
28854 | Sacramento CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
28855 | Sacramento CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 10506SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
28856 | Sacramento CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 10505SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
28857 | Sacramento CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
28858 | Sacramento CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 10509SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
28859 | Sacramento CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 10508SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
28860 | Sacramento CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
28861 | Sacramento CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 10512SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
28862 | Sacramento CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 10511SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
28863 | Sacramento CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
28864 | Sacramento CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.48999999999999999
28865 | Sacramento CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
28866 | Sacramento CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 10517 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
28867 | Sacramento CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 10516 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
28868 | Sacramento CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
28869 | Sacramento CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
28870 | Sacramento CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
28871 | Sacramento CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28872 | Sacramento CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 10523 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
28873 | Sacramento CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 10522 | 10524 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
28874 | Sacramento CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 10523 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
28875 | Sacramento CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28876 | Sacramento CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 10527 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
28877 | Sacramento CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 10526 | 10528 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28878 | Sacramento CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 10527 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28879 | Sacramento CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28880 | Sacramento CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 10531 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
28881 | Sacramento CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 10530 | 10532 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28882 | Sacramento CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 10531 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28883 | Sacramento CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28884 | Sacramento CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 10535 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28885 | Sacramento CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 10534 | 10536 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28886 | Sacramento CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 10535 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28887 | Sacramento CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28888 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28889 | Sacramento CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.41999999999999998
28890 | Sacramento CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
28891 | Sacramento CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 10542SS | Start No Earlier Than | 3/19/24 | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
28892 | Sacramento CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 10541SS | 10543 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
28893 | Sacramento CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 10542 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28894 | Sacramento CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
28895 | Sacramento CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
28896 | Sacramento CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
28897 | Sacramento CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 10549 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
28898 | Sacramento CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.60999999999999999
28899 | Sacramento CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 10547 | 10550,10552SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
28900 | Sacramento CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 10549 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
28901 | Sacramento CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
28902 | Sacramento CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 10549SS | 10553SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
28903 | Sacramento CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 10552SS | 10554,10557,10555SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28904 | Sacramento CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 10553 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28905 | Sacramento CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 10553SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28906 | Sacramento CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28907 | Sacramento CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 10553 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
28908 | Sacramento CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.62
28909 | Sacramento CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 10560SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
28910 | Sacramento CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 10559SS | 10561SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
28911 | Sacramento CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 10560SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
28912 | Sacramento CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
28913 | Sacramento CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
28914 | Sacramento CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 10570 | 10565SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
28915 | Sacramento CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 10564SS | 10567 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
28916 | Sacramento CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
28917 | Sacramento CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 10565 | 10568 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
28918 | Sacramento CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 10567 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
28919 | Sacramento CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
28920 | Sacramento CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 10564,10571SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
28921 | Sacramento CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 10570SS | 10575,10572 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28922 | Sacramento CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 10571 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28923 | Sacramento CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
28924 | Sacramento CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28925 | Sacramento CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 10571 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
28926 | Sacramento CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28927 | Sacramento CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28928 | Sacramento CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28929 | Sacramento CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28930 | Sacramento CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28931 | Sacramento CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28932 | Sacramento CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28933 | Sacramento CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28934 | Sacramento CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28935 | Sacramento CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28936 | Sacramento CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28937 | Sacramento CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
28938 | Sacramento CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
28939 | Sacramento CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
28940 | Sacramento CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 10597 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
28941 | Sacramento CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
28942 | Sacramento CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
28943 | Sacramento CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28944 | Sacramento CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
28945 | Sacramento CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 10604 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28946 | Sacramento CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 10605 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28947 | Sacramento CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 10590 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
28948 | Sacramento CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
28949 | Sacramento CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10610SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28950 | Sacramento CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10611SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28951 | Sacramento CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10612SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28952 | Sacramento CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10613SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28953 | Sacramento CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10614SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
28954 | Sacramento CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 10595 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28955 | Sacramento CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 10596 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
28956 | Sacramento CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
28957 | Sacramento CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 10616FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28958 | Sacramento CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
28959 | Sacramento CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 10616SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
28960 | Sacramento CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10599SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28961 | Sacramento CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10600SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28962 | Sacramento CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10601SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28963 | Sacramento CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10602SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28964 | Sacramento CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10603SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28965 | Sacramento CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
28966 | Sacramento CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 10607FS+12d,10609SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
28967 | CARES V1 - San Benito CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.37
28968 | San Benito CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
28969 | San Benito CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
28970 | San Benito CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
28971 | San Benito CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
28972 | San Benito CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
28973 | San Benito CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
28974 | San Benito CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
28975 | San Benito CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
28976 | San Benito CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
28977 | San Benito CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
28978 | San Benito CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
28979 | San Benito CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
28980 | San Benito CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
28981 | San Benito CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
28982 | San Benito CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
28983 | San Benito CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
28984 | San Benito CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
28985 | San Benito CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
28986 | San Benito CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
28987 | San Benito CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
28988 | San Benito CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
28989 | San Benito CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
28990 | San Benito CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
28991 | San Benito CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
28992 | San Benito CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
28993 | San Benito CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
28994 | San Benito CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
28995 | San Benito CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
28996 | San Benito CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
28997 | San Benito CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
28998 | San Benito CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
28999 | San Benito CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
29000 | San Benito CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
29001 | San Benito CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
29002 | San Benito CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
29003 | San Benito CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
29004 | San Benito CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
29005 | San Benito CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
29006 | San Benito CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
29007 | San Benito CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
29008 | San Benito CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
29009 | San Benito CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
29010 | San Benito CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29011 | San Benito CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29012 | San Benito CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
29013 | San Benito CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29014 | San Benito CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
29015 | San Benito CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
29016 | San Benito CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
29017 | San Benito CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
29018 | San Benito CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
29019 | San Benito CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
29020 | San Benito CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
29021 | San Benito CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
29022 | San Benito CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 10673SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
29023 | San Benito CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 10672SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
29024 | San Benito CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 10675SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29025 | San Benito CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 10674SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29026 | San Benito CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
29027 | San Benito CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 10678SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
29028 | San Benito CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 10677SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
29029 | San Benito CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29030 | San Benito CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 10681SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
29031 | San Benito CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 10680SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
29032 | San Benito CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29033 | San Benito CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 10684SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29034 | San Benito CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 10683SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29035 | San Benito CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29036 | San Benito CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 10687SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
29037 | San Benito CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 10686SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
29038 | San Benito CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
29039 | San Benito CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.41999999999999998
29040 | San Benito CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
29041 | San Benito CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 10692 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
29042 | San Benito CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 10691 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.40000000000000002
29043 | San Benito CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
29044 | San Benito CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
29045 | San Benito CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
29046 | San Benito CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29047 | San Benito CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 10698 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
29048 | San Benito CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 10697 | 10699 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
29049 | San Benito CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 10698 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
29050 | San Benito CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29051 | San Benito CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 10702 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
29052 | San Benito CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 10701 | 10703 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
29053 | San Benito CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 10702 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29054 | San Benito CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29055 | San Benito CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 10706 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
29056 | San Benito CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 10705 | 10707 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29057 | San Benito CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 10706 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29058 | San Benito CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29059 | San Benito CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 10710 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29060 | San Benito CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 10709 | 10711 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29061 | San Benito CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 10710 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29062 | San Benito CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29063 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29064 | San Benito CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.53000000000000003
29065 | San Benito CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
29066 | San Benito CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 10717SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
29067 | San Benito CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 10716SS | 10718 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
29068 | San Benito CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 10717 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29069 | San Benito CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
29070 | San Benito CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
29071 | San Benito CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
29072 | San Benito CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 10724 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
29073 | San Benito CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.68999999999999995
29074 | San Benito CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 10722 | 10725,10727SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
29075 | San Benito CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 10724 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
29076 | San Benito CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.66000000000000003
29077 | San Benito CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 10724SS | 10728SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
29078 | San Benito CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 10727SS | 10729,10732,10730SF+30d | As Soon As Possible | NA | 182 | 0d | NA | NA | 0 days? | No | 8/11/25 | 5/1/26 | NA | 1
29079 | San Benito CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 10728 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29080 | San Benito CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 10728SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 0d | NA | NA | 0 days? | No | 10/1/25 | 8/3/26 | NA | 1
29081 | San Benito CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29082 | San Benito CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 10728 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
29083 | San Benito CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.68000000000000005
29084 | San Benito CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 10735SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
29085 | San Benito CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 10734SS | 10736SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.94999999999999996
29086 | San Benito CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 10735SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
29087 | San Benito CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
29088 | San Benito CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
29089 | San Benito CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 10745 | 10740SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
29090 | San Benito CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 10739SS | 10742 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
29091 | San Benito CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 508d | NA | NA | 0 days? | No | 7/21/25 | NA | NA | 0.67000000000000004
29092 | San Benito CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 10740 | 10743 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
29093 | San Benito CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 10742 |  | As Soon As Possible | NA | 21 | 508d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
29094 | San Benito CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.14000000000000001
29095 | San Benito CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 10739,10746SS | Start No Earlier Than | 7/1/25 | 64 | 508d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
29096 | San Benito CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 10745SS | 10750,10747 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
29097 | San Benito CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 10746 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29098 | San Benito CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
29099 | San Benito CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29100 | San Benito CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 10746 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
29101 | San Benito CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29102 | San Benito CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29103 | San Benito CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29104 | San Benito CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29105 | San Benito CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29106 | San Benito CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29107 | San Benito CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29108 | San Benito CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29109 | San Benito CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29110 | San Benito CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29111 | San Benito CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29112 | San Benito CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29113 | San Benito CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
29114 | San Benito CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
29115 | San Benito CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 10772 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
29116 | San Benito CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
29117 | San Benito CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
29118 | San Benito CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29119 | San Benito CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29120 | San Benito CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 10779 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29121 | San Benito CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 10780 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29122 | San Benito CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 10765 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
29123 | San Benito CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29124 | San Benito CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10785SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29125 | San Benito CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10786SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29126 | San Benito CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10787SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29127 | San Benito CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10788SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29128 | San Benito CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10789SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29129 | San Benito CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 10770 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29130 | San Benito CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 10771 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29131 | San Benito CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
29132 | San Benito CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 10791FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29133 | San Benito CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
29134 | San Benito CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 10791SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
29135 | San Benito CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10774SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29136 | San Benito CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10775SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29137 | San Benito CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10776SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29138 | San Benito CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10777SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29139 | San Benito CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10778SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29140 | San Benito CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29141 | San Benito CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 10782FS+12d,10784SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29142 | CARES V1 - San Bernardino CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.34000000000000002
29143 | San Bernardino CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
29144 | San Bernardino CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
29145 | San Bernardino CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
29146 | San Bernardino CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
29147 | San Bernardino CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
29148 | San Bernardino CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
29149 | San Bernardino CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29150 | San Bernardino CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
29151 | San Bernardino CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
29152 | San Bernardino CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
29153 | San Bernardino CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
29154 | San Bernardino CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
29155 | San Bernardino CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
29156 | San Bernardino CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
29157 | San Bernardino CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
29158 | San Bernardino CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
29159 | San Bernardino CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
29160 | San Bernardino CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
29161 | San Bernardino CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
29162 | San Bernardino CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
29163 | San Bernardino CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
29164 | San Bernardino CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
29165 | San Bernardino CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
29166 | San Bernardino CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
29167 | San Bernardino CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
29168 | San Bernardino CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
29169 | San Bernardino CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
29170 | San Bernardino CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
29171 | San Bernardino CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
29172 | San Bernardino CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
29173 | San Bernardino CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
29174 | San Bernardino CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
29175 | San Bernardino CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
29176 | San Bernardino CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
29177 | San Bernardino CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
29178 | San Bernardino CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
29179 | San Bernardino CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
29180 | San Bernardino CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
29181 | San Bernardino CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
29182 | San Bernardino CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
29183 | San Bernardino CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
29184 | San Bernardino CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
29185 | San Bernardino CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29186 | San Bernardino CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29187 | San Bernardino CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
29188 | San Bernardino CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29189 | San Bernardino CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
29190 | San Bernardino CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
29191 | San Bernardino CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
29192 | San Bernardino CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
29193 | San Bernardino CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
29194 | San Bernardino CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
29195 | San Bernardino CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
29196 | San Bernardino CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
29197 | San Bernardino CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 10848SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
29198 | San Bernardino CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 10847SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
29199 | San Bernardino CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 10850SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29200 | San Bernardino CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 10849SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29201 | San Bernardino CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
29202 | San Bernardino CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 10853SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
29203 | San Bernardino CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 10852SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
29204 | San Bernardino CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29205 | San Bernardino CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 10856SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
29206 | San Bernardino CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 10855SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
29207 | San Bernardino CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29208 | San Bernardino CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 10859SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29209 | San Bernardino CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 10858SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29210 | San Bernardino CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29211 | San Bernardino CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 10862SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
29212 | San Bernardino CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 10861SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
29213 | San Bernardino CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
29214 | San Bernardino CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.32000000000000001
29215 | San Bernardino CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
29216 | San Bernardino CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 10867 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
29217 | San Bernardino CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 10866 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
29218 | San Bernardino CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
29219 | San Bernardino CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
29220 | San Bernardino CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
29221 | San Bernardino CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29222 | San Bernardino CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for ea | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 10873 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
29223 | San Bernardino CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 10872 | 10874 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
29224 | San Bernardino CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 10873 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
29225 | San Bernardino CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29226 | San Bernardino CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manu | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 10877 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
29227 | San Bernardino CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 10876 | 10878 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
29228 | San Bernardino CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 10877 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29229 | San Bernardino CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29230 | San Bernardino CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 10881 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
29231 | San Bernardino CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 10880 | 10882 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29232 | San Bernardino CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 10881 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29233 | San Bernardino CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29234 | San Bernardino CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and oper | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 10885 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29235 | San Bernardino CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 10884 | 10886 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29236 | San Bernardino CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 10885 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29237 | San Bernardino CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29238 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29239 | San Bernardino CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.47999999999999998
29240 | San Bernardino CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.97999999999999998
29241 | San Bernardino CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 10892SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
29242 | San Bernardino CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 10891SS | 10893 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
29243 | San Bernardino CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 10892 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.59999999999999998
29244 | San Bernardino CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
29245 | San Bernardino CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
29246 | San Bernardino CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
29247 | San Bernardino CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 10899 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
29248 | San Bernardino CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.97999999999999998
29249 | San Bernardino CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 10897 | 10900,10902SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
29250 | San Bernardino CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 10899 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.94999999999999996
29251 | San Bernardino CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
29252 | San Bernardino CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 10899SS | 10903SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
29253 | San Bernardino CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 10902SS | 10904,10907,10905SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
29254 | San Bernardino CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 10903 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29255 | San Bernardino CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 10903SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29256 | San Bernardino CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29257 | San Bernardino CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 10903 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
29258 | San Bernardino CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.70999999999999996
29259 | San Bernardino CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 10910SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.80000000000000004
29260 | San Bernardino CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 10909SS | 10911SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
29261 | San Bernardino CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 10910SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.40000000000000002
29262 | San Bernardino CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
29263 | San Bernardino CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
29264 | San Bernardino CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 10920 | 10915SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
29265 | San Bernardino CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 10914SS | 10917 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
29266 | San Bernardino CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
29267 | San Bernardino CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 10915 | 10918 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
29268 | San Bernardino CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 10917 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
29269 | San Bernardino CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
29270 | San Bernardino CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 10914,10921SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
29271 | San Bernardino CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 10920SS | 10925,10922 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
29272 | San Bernardino CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 10921 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29273 | San Bernardino CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
29274 | San Bernardino CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29275 | San Bernardino CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 10921 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
29276 | San Bernardino CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29277 | San Bernardino CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29278 | San Bernardino CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29279 | San Bernardino CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29280 | San Bernardino CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29281 | San Bernardino CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29282 | San Bernardino CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29283 | San Bernardino CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29284 | San Bernardino CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29285 | San Bernardino CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29286 | San Bernardino CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29287 | San Bernardino CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29288 | San Bernardino CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
29289 | San Bernardino CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 2.9999999999999999E-2
29290 | San Bernardino CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 10947 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.40000000000000002
29291 | San Bernardino CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
29292 | San Bernardino CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
29293 | San Bernardino CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29294 | San Bernardino CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29295 | San Bernardino CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 10954 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29296 | San Bernardino CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 10955 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29297 | San Bernardino CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 10940 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
29298 | San Bernardino CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29299 | San Bernardino CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10960SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29300 | San Bernardino CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10961SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29301 | San Bernardino CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10962SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29302 | San Bernardino CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10963SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29303 | San Bernardino CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 10964SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29304 | San Bernardino CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 10945 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29305 | San Bernardino CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 10946 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29306 | San Bernardino CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
29307 | San Bernardino CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 10966FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29308 | San Bernardino CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
29309 | San Bernardino CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 10966SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
29310 | San Bernardino CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10949SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29311 | San Bernardino CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10950SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29312 | San Bernardino CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10951SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29313 | San Bernardino CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10952SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29314 | San Bernardino CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 10953SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29315 | San Bernardino CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29316 | San Bernardino CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 10957FS+12d,10959SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29317 | CARES V1 - San Francisco CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.35999999999999999
29318 | San Francisco CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
29319 | San Francisco CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
29320 | San Francisco CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
29321 | San Francisco CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
29322 | San Francisco CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
29323 | San Francisco CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
29324 | San Francisco CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29325 | San Francisco CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
29326 | San Francisco CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
29327 | San Francisco CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
29328 | San Francisco CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
29329 | San Francisco CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
29330 | San Francisco CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
29331 | San Francisco CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
29332 | San Francisco CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
29333 | San Francisco CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
29334 | San Francisco CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
29335 | San Francisco CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
29336 | San Francisco CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
29337 | San Francisco CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
29338 | San Francisco CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
29339 | San Francisco CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
29340 | San Francisco CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
29341 | San Francisco CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
29342 | San Francisco CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
29343 | San Francisco CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
29344 | San Francisco CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
29345 | San Francisco CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
29346 | San Francisco CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
29347 | San Francisco CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
29348 | San Francisco CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
29349 | San Francisco CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
29350 | San Francisco CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
29351 | San Francisco CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
29352 | San Francisco CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
29353 | San Francisco CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
29354 | San Francisco CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
29355 | San Francisco CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
29356 | San Francisco CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
29357 | San Francisco CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
29358 | San Francisco CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
29359 | San Francisco CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
29360 | San Francisco CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29361 | San Francisco CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29362 | San Francisco CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
29363 | San Francisco CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29364 | San Francisco CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
29365 | San Francisco CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
29366 | San Francisco CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
29367 | San Francisco CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
29368 | San Francisco CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
29369 | San Francisco CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
29370 | San Francisco CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
29371 | San Francisco CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
29372 | San Francisco CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 11023SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
29373 | San Francisco CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 11022SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
29374 | San Francisco CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 11025SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29375 | San Francisco CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 11024SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29376 | San Francisco CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
29377 | San Francisco CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 11028SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
29378 | San Francisco CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 11027SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
29379 | San Francisco CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29380 | San Francisco CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 11031SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
29381 | San Francisco CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 11030SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
29382 | San Francisco CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29383 | San Francisco CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 11034SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29384 | San Francisco CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 11033SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29385 | San Francisco CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29386 | San Francisco CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 11037SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
29387 | San Francisco CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 11036SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
29388 | San Francisco CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
29389 | San Francisco CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.57999999999999996
29390 | San Francisco CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
29391 | San Francisco CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 11042 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
29392 | San Francisco CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 11041 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.80000000000000004
29393 | San Francisco CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
29394 | San Francisco CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
29395 | San Francisco CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
29396 | San Francisco CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29397 | San Francisco CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for ea | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 11048 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
29398 | San Francisco CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 11047 | 11049 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
29399 | San Francisco CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 11048 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
29400 | San Francisco CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29401 | San Francisco CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manu | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 11052 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
29402 | San Francisco CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 11051 | 11053 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
29403 | San Francisco CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 11052 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29404 | San Francisco CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29405 | San Francisco CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 11056 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.80000000000000004
29406 | San Francisco CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 11055 | 11057 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29407 | San Francisco CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 11056 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29408 | San Francisco CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29409 | San Francisco CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and oper | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 11060 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29410 | San Francisco CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 11059 | 11061 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29411 | San Francisco CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 11060 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29412 | San Francisco CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29413 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29414 | San Francisco CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.45000000000000001
29415 | San Francisco CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 0d | NA | NA | 0 days? | No | 3/19/24 | 5/8/26 | NA | 1
29416 | San Francisco CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 11067SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
29417 | San Francisco CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 11066SS | 11068 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
29418 | San Francisco CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 11067 |  | As Soon As Possible | NA | 48 | 0d | NA | NA | 0 days? | No | 3/3/26 | 5/8/26 | NA | 1
29419 | San Francisco CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
29420 | San Francisco CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
29421 | San Francisco CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
29422 | San Francisco CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 11074 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
29423 | San Francisco CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
29424 | San Francisco CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 11072 | 11075,11077SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
29425 | San Francisco CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 11074 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
29426 | San Francisco CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
29427 | San Francisco CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 11074SS | 11078SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
29428 | San Francisco CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 11077SS | 11079,11082,11080SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
29429 | San Francisco CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 11078 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29430 | San Francisco CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 11078SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29431 | San Francisco CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29432 | San Francisco CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 11078 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
29433 | San Francisco CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.62
29434 | San Francisco CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 11085SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
29435 | San Francisco CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 11084SS | 11086SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
29436 | San Francisco CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 11085SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
29437 | San Francisco CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
29438 | San Francisco CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
29439 | San Francisco CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 11095 | 11090SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
29440 | San Francisco CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 11089SS | 11092 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
29441 | San Francisco CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
29442 | San Francisco CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 11090 | 11093 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
29443 | San Francisco CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 11092 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
29444 | San Francisco CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
29445 | San Francisco CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 11089,11096SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
29446 | San Francisco CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 11095SS | 11100,11097 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29447 | San Francisco CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 11096 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29448 | San Francisco CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29449 | San Francisco CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29450 | San Francisco CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 11096 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
29451 | San Francisco CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29452 | San Francisco CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29453 | San Francisco CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29454 | San Francisco CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29455 | San Francisco CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29456 | San Francisco CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29457 | San Francisco CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29458 | San Francisco CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29459 | San Francisco CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29460 | San Francisco CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29461 | San Francisco CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29462 | San Francisco CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29463 | San Francisco CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
29464 | San Francisco CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
29465 | San Francisco CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 11122 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
29466 | San Francisco CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
29467 | San Francisco CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
29468 | San Francisco CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29469 | San Francisco CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29470 | San Francisco CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 11129 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29471 | San Francisco CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 11130 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29472 | San Francisco CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 11115 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
29473 | San Francisco CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29474 | San Francisco CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11135SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29475 | San Francisco CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11136SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29476 | San Francisco CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11137SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29477 | San Francisco CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11138SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29478 | San Francisco CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11139SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29479 | San Francisco CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 11120 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29480 | San Francisco CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 11121 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29481 | San Francisco CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
29482 | San Francisco CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 11141FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29483 | San Francisco CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
29484 | San Francisco CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 11141SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
29485 | San Francisco CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11124SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29486 | San Francisco CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11125SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29487 | San Francisco CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11126SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29488 | San Francisco CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11127SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29489 | San Francisco CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11128SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29490 | San Francisco CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29491 | San Francisco CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 11132FS+12d,11134SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29492 | CARES V1 - San Joaquin CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.40000000000000002
29493 | San Joaquin CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
29494 | San Joaquin CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
29495 | San Joaquin CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
29496 | San Joaquin CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
29497 | San Joaquin CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
29498 | San Joaquin CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
29499 | San Joaquin CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29500 | San Joaquin CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
29501 | San Joaquin CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
29502 | San Joaquin CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
29503 | San Joaquin CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
29504 | San Joaquin CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
29505 | San Joaquin CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
29506 | San Joaquin CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
29507 | San Joaquin CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
29508 | San Joaquin CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
29509 | San Joaquin CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
29510 | San Joaquin CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
29511 | San Joaquin CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
29512 | San Joaquin CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
29513 | San Joaquin CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
29514 | San Joaquin CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
29515 | San Joaquin CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
29516 | San Joaquin CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
29517 | San Joaquin CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
29518 | San Joaquin CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
29519 | San Joaquin CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
29520 | San Joaquin CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
29521 | San Joaquin CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
29522 | San Joaquin CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
29523 | San Joaquin CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
29524 | San Joaquin CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
29525 | San Joaquin CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
29526 | San Joaquin CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
29527 | San Joaquin CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
29528 | San Joaquin CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
29529 | San Joaquin CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
29530 | San Joaquin CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
29531 | San Joaquin CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
29532 | San Joaquin CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
29533 | San Joaquin CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
29534 | San Joaquin CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
29535 | San Joaquin CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29536 | San Joaquin CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29537 | San Joaquin CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
29538 | San Joaquin CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29539 | San Joaquin CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
29540 | San Joaquin CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
29541 | San Joaquin CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
29542 | San Joaquin CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
29543 | San Joaquin CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
29544 | San Joaquin CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
29545 | San Joaquin CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
29546 | San Joaquin CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
29547 | San Joaquin CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 11198SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
29548 | San Joaquin CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 11197SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
29549 | San Joaquin CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 11200 | Start No Earlier Than | 2/2/26 | 63 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29550 | San Joaquin CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | May 4, 2026 8:00 AM | July 31, 2026 5:00 PM | 11199 |  | As Soon As Possible | NA | 63 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29551 | San Joaquin CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
29552 | San Joaquin CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 11203SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
29553 | San Joaquin CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 11202SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
29554 | San Joaquin CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29555 | San Joaquin CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 11206SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
29556 | San Joaquin CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 11205SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
29557 | San Joaquin CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29558 | San Joaquin CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 11209SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29559 | San Joaquin CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 11208SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29560 | San Joaquin CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29561 | San Joaquin CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 11212SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
29562 | San Joaquin CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 11211SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
29563 | San Joaquin CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
29564 | San Joaquin CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.52000000000000002
29565 | San Joaquin CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
29566 | San Joaquin CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 11217 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
29567 | San Joaquin CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 11216 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
29568 | San Joaquin CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
29569 | San Joaquin CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
29570 | San Joaquin CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
29571 | San Joaquin CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29572 | San Joaquin CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for ea | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 11223 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
29573 | San Joaquin CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 11222 | 11224 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
29574 | San Joaquin CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 11223 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.59999999999999998
29575 | San Joaquin CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29576 | San Joaquin CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manu | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 11227 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
29577 | San Joaquin CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 11226 | 11228 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
29578 | San Joaquin CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 11227 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29579 | San Joaquin CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29580 | San Joaquin CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 11231 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
29581 | San Joaquin CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 11230 | 11232 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29582 | San Joaquin CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 11231 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29583 | San Joaquin CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29584 | San Joaquin CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and oper | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 11235 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29585 | San Joaquin CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 11234 | 11236 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29586 | San Joaquin CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 11235 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29587 | San Joaquin CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29588 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29589 | San Joaquin CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.56000000000000005
29590 | San Joaquin CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 0d | NA | NA | 0 days? | No | 3/19/24 | 5/8/26 | NA | 1
29591 | San Joaquin CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 11242SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
29592 | San Joaquin CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 11241SS | 11243 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
29593 | San Joaquin CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 11242 |  | As Soon As Possible | NA | 48 | 0d | NA | NA | 0 days? | No | 3/3/26 | 5/8/26 | NA | 1
29594 | San Joaquin CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
29595 | San Joaquin CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
29596 | San Joaquin CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
29597 | San Joaquin CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 11249 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
29598 | San Joaquin CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
29599 | San Joaquin CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 11247 | 11250,11252SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
29600 | San Joaquin CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 11249 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
29601 | San Joaquin CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
29602 | San Joaquin CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 11249SS | 11253SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
29603 | San Joaquin CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 11252SS | 11254,11257,11255SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
29604 | San Joaquin CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 11253 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29605 | San Joaquin CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 11253SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29606 | San Joaquin CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29607 | San Joaquin CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 11253 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
29608 | San Joaquin CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 0d | NA | NA | 0 days? | No | 2/3/25 | 12/31/25 | NA | 1
29609 | San Joaquin CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 11260SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
29610 | San Joaquin CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 11259SS | 11261SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
29611 | San Joaquin CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 11260SS |  | As Soon As Possible | NA | 230 | 0d | NA | NA | 0 days? | No | 2/3/25 | 12/31/25 | NA | 1
29612 | San Joaquin CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
29613 | San Joaquin CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
29614 | San Joaquin CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 11270 | 11265SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
29615 | San Joaquin CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 11264SS | 11267 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
29616 | San Joaquin CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
29617 | San Joaquin CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 11265 | 11268 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
29618 | San Joaquin CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 11267 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
29619 | San Joaquin CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.46000000000000002
29620 | San Joaquin CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 11264,11271SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
29621 | San Joaquin CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 11270SS | 11275,11272 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.59999999999999998
29622 | San Joaquin CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 11271 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29623 | San Joaquin CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.59999999999999998
29624 | San Joaquin CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29625 | San Joaquin CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 11271 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
29626 | San Joaquin CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29627 | San Joaquin CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29628 | San Joaquin CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29629 | San Joaquin CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29630 | San Joaquin CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29631 | San Joaquin CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29632 | San Joaquin CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29633 | San Joaquin CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29634 | San Joaquin CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29635 | San Joaquin CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29636 | San Joaquin CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29637 | San Joaquin CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29638 | San Joaquin CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
29639 | San Joaquin CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
29640 | San Joaquin CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 11297 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
29641 | San Joaquin CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
29642 | San Joaquin CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
29643 | San Joaquin CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29644 | San Joaquin CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29645 | San Joaquin CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 11304 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29646 | San Joaquin CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 11305 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29647 | San Joaquin CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 11290 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
29648 | San Joaquin CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29649 | San Joaquin CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11310SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29650 | San Joaquin CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11311SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29651 | San Joaquin CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11312SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29652 | San Joaquin CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11313SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29653 | San Joaquin CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11314SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29654 | San Joaquin CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 11295 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29655 | San Joaquin CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 11296 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29656 | San Joaquin CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
29657 | San Joaquin CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 11316FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29658 | San Joaquin CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
29659 | San Joaquin CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 11316SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
29660 | San Joaquin CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11299SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29661 | San Joaquin CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11300SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29662 | San Joaquin CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11301SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29663 | San Joaquin CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11302SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29664 | San Joaquin CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11303SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29665 | San Joaquin CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29666 | San Joaquin CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 11307FS+12d,11309SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29667 | CARES V1 - San Luis Obispo CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.33000000000000002
29668 | San Luis Obispo CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
29669 | San Luis Obispo CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
29670 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
29671 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
29672 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
29673 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
29674 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29675 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
29676 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
29677 | San Luis Obispo CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
29678 | San Luis Obispo CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
29679 | San Luis Obispo CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
29680 | San Luis Obispo CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
29681 | San Luis Obispo CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
29682 | San Luis Obispo CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
29683 | San Luis Obispo CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
29684 | San Luis Obispo CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
29685 | San Luis Obispo CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
29686 | San Luis Obispo CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
29687 | San Luis Obispo CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
29688 | San Luis Obispo CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
29689 | San Luis Obispo CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
29690 | San Luis Obispo CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
29691 | San Luis Obispo CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
29692 | San Luis Obispo CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
29693 | San Luis Obispo CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
29694 | San Luis Obispo CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
29695 | San Luis Obispo CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
29696 | San Luis Obispo CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
29697 | San Luis Obispo CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
29698 | San Luis Obispo CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
29699 | San Luis Obispo CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
29700 | San Luis Obispo CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
29701 | San Luis Obispo CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
29702 | San Luis Obispo CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
29703 | San Luis Obispo CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
29704 | San Luis Obispo CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
29705 | San Luis Obispo CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
29706 | San Luis Obispo CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
29707 | San Luis Obispo CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
29708 | San Luis Obispo CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
29709 | San Luis Obispo CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
29710 | San Luis Obispo CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29711 | San Luis Obispo CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29712 | San Luis Obispo CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
29713 | San Luis Obispo CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29714 | San Luis Obispo CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
29715 | San Luis Obispo CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
29716 | San Luis Obispo CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
29717 | San Luis Obispo CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
29718 | San Luis Obispo CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
29719 | San Luis Obispo CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
29720 | San Luis Obispo CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
29721 | San Luis Obispo CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
29722 | San Luis Obispo CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 11373SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
29723 | San Luis Obispo CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 11372SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
29724 | San Luis Obispo CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 11375SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29725 | San Luis Obispo CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 11374SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29726 | San Luis Obispo CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
29727 | San Luis Obispo CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 11378SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
29728 | San Luis Obispo CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 11377SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
29729 | San Luis Obispo CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29730 | San Luis Obispo CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 11381SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
29731 | San Luis Obispo CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 11380SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
29732 | San Luis Obispo CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29733 | San Luis Obispo CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 11384SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29734 | San Luis Obispo CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 11383SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29735 | San Luis Obispo CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29736 | San Luis Obispo CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 11387SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
29737 | San Luis Obispo CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 11386SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
29738 | San Luis Obispo CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
29739 | San Luis Obispo CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.40000000000000002
29740 | San Luis Obispo CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
29741 | San Luis Obispo CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 11392 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
29742 | San Luis Obispo CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 11391 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.40000000000000002
29743 | San Luis Obispo CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
29744 | San Luis Obispo CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
29745 | San Luis Obispo CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
29746 | San Luis Obispo CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29747 | San Luis Obispo CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 11398 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
29748 | San Luis Obispo CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 11397 | 11399 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
29749 | San Luis Obispo CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 11398 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
29750 | San Luis Obispo CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29751 | San Luis Obispo CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 11402 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
29752 | San Luis Obispo CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 11401 | 11403 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
29753 | San Luis Obispo CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 11402 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29754 | San Luis Obispo CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29755 | San Luis Obispo CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 11406 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
29756 | San Luis Obispo CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 11405 | 11407 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29757 | San Luis Obispo CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 11406 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29758 | San Luis Obispo CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29759 | San Luis Obispo CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 11410 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29760 | San Luis Obispo CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 11409 | 11411 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29761 | San Luis Obispo CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 11410 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29762 | San Luis Obispo CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29763 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29764 | San Luis Obispo CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.44
29765 | San Luis Obispo CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.97999999999999998
29766 | San Luis Obispo CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 11417SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
29767 | San Luis Obispo CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 11416SS | 11418 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
29768 | San Luis Obispo CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 11417 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.59999999999999998
29769 | San Luis Obispo CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
29770 | San Luis Obispo CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
29771 | San Luis Obispo CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
29772 | San Luis Obispo CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 11424 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
29773 | San Luis Obispo CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
29774 | San Luis Obispo CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 11422 | 11425,11427SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
29775 | San Luis Obispo CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 11424 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
29776 | San Luis Obispo CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 2.9999999999999999E-2
29777 | San Luis Obispo CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 11424SS | 11428SS | As Soon As Possible | NA | 36 | 508d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.59999999999999998
29778 | San Luis Obispo CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 11427SS | 11429,11432,11430SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29779 | San Luis Obispo CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 11428 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29780 | San Luis Obispo CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 11428SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29781 | San Luis Obispo CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29782 | San Luis Obispo CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 11428 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
29783 | San Luis Obispo CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.69999999999999996
29784 | San Luis Obispo CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 11435SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
29785 | San Luis Obispo CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 11434SS | 11436SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
29786 | San Luis Obispo CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 11435SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
29787 | San Luis Obispo CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
29788 | San Luis Obispo CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
29789 | San Luis Obispo CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 11445 | 11440SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
29790 | San Luis Obispo CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 11439SS | 11442 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
29791 | San Luis Obispo CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
29792 | San Luis Obispo CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 11440 | 11443 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
29793 | San Luis Obispo CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 11442 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
29794 | San Luis Obispo CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
29795 | San Luis Obispo CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 11439,11446SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
29796 | San Luis Obispo CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 11445SS | 11450,11447 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29797 | San Luis Obispo CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 11446 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29798 | San Luis Obispo CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29799 | San Luis Obispo CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29800 | San Luis Obispo CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 11446 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
29801 | San Luis Obispo CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29802 | San Luis Obispo CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29803 | San Luis Obispo CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29804 | San Luis Obispo CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29805 | San Luis Obispo CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29806 | San Luis Obispo CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29807 | San Luis Obispo CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29808 | San Luis Obispo CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29809 | San Luis Obispo CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29810 | San Luis Obispo CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29811 | San Luis Obispo CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29812 | San Luis Obispo CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29813 | San Luis Obispo CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
29814 | San Luis Obispo CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
29815 | San Luis Obispo CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 11472 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
29816 | San Luis Obispo CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
29817 | San Luis Obispo CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
29818 | San Luis Obispo CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29819 | San Luis Obispo CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29820 | San Luis Obispo CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 11479 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29821 | San Luis Obispo CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 11480 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29822 | San Luis Obispo CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 11465 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
29823 | San Luis Obispo CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29824 | San Luis Obispo CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11485SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29825 | San Luis Obispo CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11486SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29826 | San Luis Obispo CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11487SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29827 | San Luis Obispo CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11488SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29828 | San Luis Obispo CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11489SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29829 | San Luis Obispo CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 11470 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29830 | San Luis Obispo CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 11471 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29831 | San Luis Obispo CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
29832 | San Luis Obispo CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 11491FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29833 | San Luis Obispo CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
29834 | San Luis Obispo CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 11491SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
29835 | San Luis Obispo CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11474SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29836 | San Luis Obispo CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11475SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29837 | San Luis Obispo CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11476SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29838 | San Luis Obispo CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11477SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29839 | San Luis Obispo CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11478SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29840 | San Luis Obispo CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29841 | San Luis Obispo CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 11482FS+12d,11484SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
29842 | CARES V1 - Santa Barbara CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.34000000000000002
29843 | Santa Barbara CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
29844 | Santa Barbara CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
29845 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
29846 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
29847 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
29848 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
29849 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29850 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
29851 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
29852 | Santa Barbara CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
29853 | Santa Barbara CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
29854 | Santa Barbara CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
29855 | Santa Barbara CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
29856 | Santa Barbara CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
29857 | Santa Barbara CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
29858 | Santa Barbara CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
29859 | Santa Barbara CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
29860 | Santa Barbara CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
29861 | Santa Barbara CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
29862 | Santa Barbara CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
29863 | Santa Barbara CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
29864 | Santa Barbara CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
29865 | Santa Barbara CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
29866 | Santa Barbara CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
29867 | Santa Barbara CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
29868 | Santa Barbara CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
29869 | Santa Barbara CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
29870 | Santa Barbara CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
29871 | Santa Barbara CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
29872 | Santa Barbara CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
29873 | Santa Barbara CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
29874 | Santa Barbara CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
29875 | Santa Barbara CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
29876 | Santa Barbara CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
29877 | Santa Barbara CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
29878 | Santa Barbara CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
29879 | Santa Barbara CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
29880 | Santa Barbara CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
29881 | Santa Barbara CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
29882 | Santa Barbara CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
29883 | Santa Barbara CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
29884 | Santa Barbara CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
29885 | Santa Barbara CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29886 | Santa Barbara CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29887 | Santa Barbara CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
29888 | Santa Barbara CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29889 | Santa Barbara CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
29890 | Santa Barbara CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
29891 | Santa Barbara CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
29892 | Santa Barbara CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
29893 | Santa Barbara CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
29894 | Santa Barbara CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
29895 | Santa Barbara CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
29896 | Santa Barbara CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
29897 | Santa Barbara CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 11548SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
29898 | Santa Barbara CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 11547SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
29899 | Santa Barbara CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 11550SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29900 | Santa Barbara CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 11549SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29901 | Santa Barbara CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
29902 | Santa Barbara CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 11553SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
29903 | Santa Barbara CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 11552SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
29904 | Santa Barbara CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29905 | Santa Barbara CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 11556SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
29906 | Santa Barbara CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 11555SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
29907 | Santa Barbara CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29908 | Santa Barbara CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 11559SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29909 | Santa Barbara CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 11558SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
29910 | Santa Barbara CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
29911 | Santa Barbara CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 11562SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
29912 | Santa Barbara CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 11561SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
29913 | Santa Barbara CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
29914 | Santa Barbara CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.37
29915 | Santa Barbara CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
29916 | Santa Barbara CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 11567 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
29917 | Santa Barbara CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 11566 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.40000000000000002
29918 | Santa Barbara CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
29919 | Santa Barbara CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
29920 | Santa Barbara CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 550d | NA | NA | 0 days? | No | 6/2/25 | NA | NA | 0.40000000000000002
29921 | Santa Barbara CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29922 | Santa Barbara CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 11573 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
29923 | Santa Barbara CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 11572 | 11574 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
29924 | Santa Barbara CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 11573 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
29925 | Santa Barbara CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29926 | Santa Barbara CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 11577 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
29927 | Santa Barbara CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 11576 | 11578 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
29928 | Santa Barbara CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 11577 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29929 | Santa Barbara CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29930 | Santa Barbara CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 11581 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
29931 | Santa Barbara CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 11580 | 11582 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29932 | Santa Barbara CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 11581 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
29933 | Santa Barbara CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29934 | Santa Barbara CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 11585 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29935 | Santa Barbara CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 11584 | 11586 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29936 | Santa Barbara CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 11585 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29937 | Santa Barbara CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29938 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
29939 | Santa Barbara CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.46999999999999997
29940 | Santa Barbara CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 0d | NA | NA | 0 days? | No | 3/19/24 | 5/8/26 | NA | 1
29941 | Santa Barbara CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 11592SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
29942 | Santa Barbara CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 11591SS | 11593 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
29943 | Santa Barbara CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 11592 |  | As Soon As Possible | NA | 48 | 0d | NA | NA | 0 days? | No | 3/3/26 | 5/8/26 | NA | 1
29944 | Santa Barbara CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
29945 | Santa Barbara CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
29946 | Santa Barbara CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
29947 | Santa Barbara CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 11599 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
29948 | Santa Barbara CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
29949 | Santa Barbara CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 11597 | 11600,11602SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
29950 | Santa Barbara CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 11599 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
29951 | Santa Barbara CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 2.9999999999999999E-2
29952 | Santa Barbara CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 11599SS | 11603SS | As Soon As Possible | NA | 36 | 508d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.59999999999999998
29953 | Santa Barbara CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 11602SS | 11604,11607,11605SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29954 | Santa Barbara CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 11603 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29955 | Santa Barbara CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 11603SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29956 | Santa Barbara CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29957 | Santa Barbara CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 11603 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
29958 | Santa Barbara CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.92000000000000004
29959 | Santa Barbara CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 11610SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
29960 | Santa Barbara CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 11609SS | 11611SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
29961 | Santa Barbara CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 11610SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.80000000000000004
29962 | Santa Barbara CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
29963 | Santa Barbara CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
29964 | Santa Barbara CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 11620 | 11615SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
29965 | Santa Barbara CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 11614SS | 11617 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
29966 | Santa Barbara CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
29967 | Santa Barbara CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 11615 | 11618 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
29968 | Santa Barbara CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 11617 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
29969 | Santa Barbara CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 5.0000000000000003E-2
29970 | Santa Barbara CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 11614,11621SS | Start No Earlier Than | 7/1/25 | 64 | 508d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.59999999999999998
29971 | Santa Barbara CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 11620SS | 11625,11622 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29972 | Santa Barbara CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 11621 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29973 | Santa Barbara CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
29974 | Santa Barbara CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
29975 | Santa Barbara CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 11621 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
29976 | Santa Barbara CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29977 | Santa Barbara CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29978 | Santa Barbara CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29979 | Santa Barbara CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29980 | Santa Barbara CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29981 | Santa Barbara CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29982 | Santa Barbara CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29983 | Santa Barbara CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29984 | Santa Barbara CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29985 | Santa Barbara CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29986 | Santa Barbara CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29987 | Santa Barbara CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
29988 | Santa Barbara CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
29989 | Santa Barbara CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
29990 | Santa Barbara CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 11647 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
29991 | Santa Barbara CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
29992 | Santa Barbara CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
29993 | Santa Barbara CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29994 | Santa Barbara CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
29995 | Santa Barbara CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 11654 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29996 | Santa Barbara CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 11655 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
29997 | Santa Barbara CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 11640 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
29998 | Santa Barbara CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
29999 | Santa Barbara CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11660SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30000 | Santa Barbara CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11661SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30001 | Santa Barbara CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11662SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30002 | Santa Barbara CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11663SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30003 | Santa Barbara CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11664SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30004 | Santa Barbara CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 11645 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30005 | Santa Barbara CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 11646 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30006 | Santa Barbara CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
30007 | Santa Barbara CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 11666FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30008 | Santa Barbara CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
30009 | Santa Barbara CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 11666SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
30010 | Santa Barbara CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11649SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30011 | Santa Barbara CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11650SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30012 | Santa Barbara CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11651SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30013 | Santa Barbara CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11652SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30014 | Santa Barbara CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11653SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30015 | Santa Barbara CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30016 | Santa Barbara CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 11657FS+12d,11659SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30017 | CARES V1 - Santa Clara CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.34000000000000002
30018 | Santa Clara CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
30019 | Santa Clara CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
30020 | Santa Clara CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
30021 | Santa Clara CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
30022 | Santa Clara CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
30023 | Santa Clara CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
30024 | Santa Clara CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30025 | Santa Clara CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
30026 | Santa Clara CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
30027 | Santa Clara CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
30028 | Santa Clara CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
30029 | Santa Clara CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
30030 | Santa Clara CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
30031 | Santa Clara CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
30032 | Santa Clara CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
30033 | Santa Clara CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
30034 | Santa Clara CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
30035 | Santa Clara CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
30036 | Santa Clara CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
30037 | Santa Clara CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
30038 | Santa Clara CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
30039 | Santa Clara CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
30040 | Santa Clara CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
30041 | Santa Clara CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
30042 | Santa Clara CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
30043 | Santa Clara CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
30044 | Santa Clara CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
30045 | Santa Clara CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
30046 | Santa Clara CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
30047 | Santa Clara CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
30048 | Santa Clara CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
30049 | Santa Clara CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
30050 | Santa Clara CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
30051 | Santa Clara CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
30052 | Santa Clara CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
30053 | Santa Clara CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
30054 | Santa Clara CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
30055 | Santa Clara CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
30056 | Santa Clara CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
30057 | Santa Clara CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
30058 | Santa Clara CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
30059 | Santa Clara CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
30060 | Santa Clara CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
30061 | Santa Clara CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30062 | Santa Clara CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
30063 | Santa Clara CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30064 | Santa Clara CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
30065 | Santa Clara CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
30066 | Santa Clara CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
30067 | Santa Clara CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
30068 | Santa Clara CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
30069 | Santa Clara CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
30070 | Santa Clara CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
30071 | Santa Clara CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
30072 | Santa Clara CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 11723SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
30073 | Santa Clara CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 11722SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
30074 | Santa Clara CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 11725SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30075 | Santa Clara CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 11724SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30076 | Santa Clara CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
30077 | Santa Clara CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 11728SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
30078 | Santa Clara CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 11727SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
30079 | Santa Clara CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30080 | Santa Clara CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 11731SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
30081 | Santa Clara CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 11730SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
30082 | Santa Clara CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30083 | Santa Clara CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 11734SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30084 | Santa Clara CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 11733SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30085 | Santa Clara CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30086 | Santa Clara CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 11737SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
30087 | Santa Clara CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 11736SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
30088 | Santa Clara CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
30089 | Santa Clara CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.5
30090 | Santa Clara CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
30091 | Santa Clara CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 11742 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
30092 | Santa Clara CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 11741 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
30093 | Santa Clara CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
30094 | Santa Clara CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
30095 | Santa Clara CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
30096 | Santa Clara CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30097 | Santa Clara CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 11748 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
30098 | Santa Clara CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 11747 | 11749 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
30099 | Santa Clara CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 11748 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
30100 | Santa Clara CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30101 | Santa Clara CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 11752 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
30102 | Santa Clara CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 11751 | 11753 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
30103 | Santa Clara CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 11752 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30104 | Santa Clara CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30105 | Santa Clara CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 11756 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
30106 | Santa Clara CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 11755 | 11757 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30107 | Santa Clara CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 11756 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30108 | Santa Clara CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30109 | Santa Clara CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 11760 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30110 | Santa Clara CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 11759 | 11761 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30111 | Santa Clara CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 11760 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30112 | Santa Clara CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30113 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30114 | Santa Clara CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.41999999999999998
30115 | Santa Clara CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.76000000000000001
30116 | Santa Clara CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 11767SS | As Soon As Possible | NA | 490 | 405d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.80000000000000004
30117 | Santa Clara CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 11766SS | 11768 | As Soon As Possible | NA | 490 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.80000000000000004
30118 | Santa Clara CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 11767 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30119 | Santa Clara CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
30120 | Santa Clara CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
30121 | Santa Clara CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
30122 | Santa Clara CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 11774 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
30123 | Santa Clara CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
30124 | Santa Clara CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 11772 | 11775,11777SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
30125 | Santa Clara CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 11774 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
30126 | Santa Clara CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
30127 | Santa Clara CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 11774SS | 11778SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
30128 | Santa Clara CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 11777SS | 11779,11782,11780SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
30129 | Santa Clara CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 11778 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30130 | Santa Clara CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 11778SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30131 | Santa Clara CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30132 | Santa Clara CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 11778 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
30133 | Santa Clara CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.77000000000000002
30134 | Santa Clara CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 11785SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
30135 | Santa Clara CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 11784SS | 11786SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
30136 | Santa Clara CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 11785SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.40000000000000002
30137 | Santa Clara CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
30138 | Santa Clara CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
30139 | Santa Clara CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 11795 | 11790SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
30140 | Santa Clara CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 11789SS | 11792 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
30141 | Santa Clara CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
30142 | Santa Clara CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 11790 | 11793 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
30143 | Santa Clara CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 11792 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
30144 | Santa Clara CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.14000000000000001
30145 | Santa Clara CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 11789,11796SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
30146 | Santa Clara CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 11795SS | 11800,11797 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
30147 | Santa Clara CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 11796 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30148 | Santa Clara CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30149 | Santa Clara CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30150 | Santa Clara CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 11796 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
30151 | Santa Clara CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30152 | Santa Clara CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30153 | Santa Clara CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30154 | Santa Clara CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30155 | Santa Clara CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30156 | Santa Clara CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30157 | Santa Clara CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30158 | Santa Clara CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30159 | Santa Clara CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30160 | Santa Clara CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30161 | Santa Clara CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30162 | Santa Clara CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30163 | Santa Clara CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
30164 | Santa Clara CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
30165 | Santa Clara CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 11822 | Start No Earlier Than | 7/1/25 | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
30166 | Santa Clara CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
30167 | Santa Clara CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
30168 | Santa Clara CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
30169 | Santa Clara CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
30170 | Santa Clara CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 11829 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30171 | Santa Clara CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 11830 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30172 | Santa Clara CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 11815 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
30173 | Santa Clara CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30174 | Santa Clara CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11835SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30175 | Santa Clara CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11836SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30176 | Santa Clara CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11837SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30177 | Santa Clara CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11838SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30178 | Santa Clara CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 11839SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30179 | Santa Clara CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 11820 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30180 | Santa Clara CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 11821 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30181 | Santa Clara CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
30182 | Santa Clara CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 11841FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30183 | Santa Clara CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
30184 | Santa Clara CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 11841SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
30185 | Santa Clara CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11824SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30186 | Santa Clara CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11825SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30187 | Santa Clara CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11826SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30188 | Santa Clara CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11827SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30189 | Santa Clara CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11828SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30190 | Santa Clara CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30191 | Santa Clara CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 11832FS+12d,11834SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30192 | CARES V1 - Santa Cruz CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.28999999999999998
30193 | Santa Cruz CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
30194 | Santa Cruz CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
30195 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
30196 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
30197 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
30198 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
30199 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30200 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
30201 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
30202 | Santa Cruz CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
30203 | Santa Cruz CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
30204 | Santa Cruz CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
30205 | Santa Cruz CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
30206 | Santa Cruz CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
30207 | Santa Cruz CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
30208 | Santa Cruz CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
30209 | Santa Cruz CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
30210 | Santa Cruz CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
30211 | Santa Cruz CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
30212 | Santa Cruz CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
30213 | Santa Cruz CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
30214 | Santa Cruz CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
30215 | Santa Cruz CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
30216 | Santa Cruz CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
30217 | Santa Cruz CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
30218 | Santa Cruz CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
30219 | Santa Cruz CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
30220 | Santa Cruz CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
30221 | Santa Cruz CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
30222 | Santa Cruz CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
30223 | Santa Cruz CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
30224 | Santa Cruz CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
30225 | Santa Cruz CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
30226 | Santa Cruz CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
30227 | Santa Cruz CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
30228 | Santa Cruz CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
30229 | Santa Cruz CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
30230 | Santa Cruz CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
30231 | Santa Cruz CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
30232 | Santa Cruz CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
30233 | Santa Cruz CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
30234 | Santa Cruz CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
30235 | Santa Cruz CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
30236 | Santa Cruz CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30237 | Santa Cruz CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
30238 | Santa Cruz CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30239 | Santa Cruz CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
30240 | Santa Cruz CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
30241 | Santa Cruz CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
30242 | Santa Cruz CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
30243 | Santa Cruz CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
30244 | Santa Cruz CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
30245 | Santa Cruz CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
30246 | Santa Cruz CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
30247 | Santa Cruz CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 11898SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
30248 | Santa Cruz CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 11897SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
30249 | Santa Cruz CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 11900SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30250 | Santa Cruz CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 11899SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30251 | Santa Cruz CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
30252 | Santa Cruz CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 11903SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
30253 | Santa Cruz CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 11902SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
30254 | Santa Cruz CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30255 | Santa Cruz CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 11906SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
30256 | Santa Cruz CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 11905SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
30257 | Santa Cruz CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30258 | Santa Cruz CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 11909SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30259 | Santa Cruz CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 11908SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30260 | Santa Cruz CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30261 | Santa Cruz CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 11912SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
30262 | Santa Cruz CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 11911SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
30263 | Santa Cruz CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
30264 | Santa Cruz CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.42999999999999999
30265 | Santa Cruz CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
30266 | Santa Cruz CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 11917 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
30267 | Santa Cruz CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 11916 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.40000000000000002
30268 | Santa Cruz CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
30269 | Santa Cruz CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
30270 | Santa Cruz CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
30271 | Santa Cruz CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30272 | Santa Cruz CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 11923 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
30273 | Santa Cruz CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 11922 | 11924 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
30274 | Santa Cruz CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 11923 |  | As Soon As Possible | NA | 63 | 0d | NA | NA | 0 days? | No | 9/2/25 | 12/1/25 | NA | 1
30275 | Santa Cruz CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30276 | Santa Cruz CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 11927 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
30277 | Santa Cruz CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 11926 | 11928 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
30278 | Santa Cruz CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 11927 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30279 | Santa Cruz CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30280 | Santa Cruz CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 11931 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
30281 | Santa Cruz CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 11930 | 11932 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30282 | Santa Cruz CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 11931 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30283 | Santa Cruz CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30284 | Santa Cruz CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 11935 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30285 | Santa Cruz CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 11934 | 11936 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30286 | Santa Cruz CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 11935 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30287 | Santa Cruz CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30288 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30289 | Santa Cruz CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.33000000000000002
30290 | Santa Cruz CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.56999999999999995
30291 | Santa Cruz CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 11942SS | As Soon As Possible | NA | 490 | 405d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.59999999999999998
30292 | Santa Cruz CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 11941SS | 11943 | As Soon As Possible | NA | 490 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.59999999999999998
30293 | Santa Cruz CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 11942 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30294 | Santa Cruz CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
30295 | Santa Cruz CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
30296 | Santa Cruz CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
30297 | Santa Cruz CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 11949 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
30298 | Santa Cruz CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.68999999999999995
30299 | Santa Cruz CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 11947 | 11950,11952SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
30300 | Santa Cruz CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 11949 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
30301 | Santa Cruz CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 7.0000000000000007E-2
30302 | Santa Cruz CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 11949SS | 11953SS | As Soon As Possible | NA | 36 | 508d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
30303 | Santa Cruz CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 11952SS | 11954,11957,11955SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
30304 | Santa Cruz CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 11953 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30305 | Santa Cruz CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 11953SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30306 | Santa Cruz CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30307 | Santa Cruz CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 11953 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
30308 | Santa Cruz CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.51000000000000001
30309 | Santa Cruz CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 11960SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.59999999999999998
30310 | Santa Cruz CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 11959SS | 11961SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.80000000000000004
30311 | Santa Cruz CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 11960SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
30312 | Santa Cruz CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
30313 | Santa Cruz CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
30314 | Santa Cruz CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 11970 | 11965SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
30315 | Santa Cruz CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 11964SS | 11967 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
30316 | Santa Cruz CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
30317 | Santa Cruz CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 11965 | 11968 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
30318 | Santa Cruz CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 11967 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
30319 | Santa Cruz CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.14000000000000001
30320 | Santa Cruz CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 11964,11971SS | Start No Earlier Than | 7/1/25 | 64 | 508d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
30321 | Santa Cruz CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 11970SS | 11975,11972 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
30322 | Santa Cruz CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 11971 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30323 | Santa Cruz CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
30324 | Santa Cruz CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30325 | Santa Cruz CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 11971 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
30326 | Santa Cruz CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30327 | Santa Cruz CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30328 | Santa Cruz CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30329 | Santa Cruz CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30330 | Santa Cruz CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30331 | Santa Cruz CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30332 | Santa Cruz CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30333 | Santa Cruz CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30334 | Santa Cruz CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30335 | Santa Cruz CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30336 | Santa Cruz CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30337 | Santa Cruz CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30338 | Santa Cruz CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
30339 | Santa Cruz CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
30340 | Santa Cruz CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 11997 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
30341 | Santa Cruz CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
30342 | Santa Cruz CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
30343 | Santa Cruz CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
30344 | Santa Cruz CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
30345 | Santa Cruz CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 12004 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30346 | Santa Cruz CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 12005 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30347 | Santa Cruz CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 11990 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
30348 | Santa Cruz CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30349 | Santa Cruz CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12010SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30350 | Santa Cruz CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12011SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30351 | Santa Cruz CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12012SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30352 | Santa Cruz CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12013SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30353 | Santa Cruz CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12014SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30354 | Santa Cruz CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 11995 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30355 | Santa Cruz CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 11996 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30356 | Santa Cruz CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
30357 | Santa Cruz CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 12016FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30358 | Santa Cruz CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
30359 | Santa Cruz CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 12016SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
30360 | Santa Cruz CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 11999SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30361 | Santa Cruz CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12000SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30362 | Santa Cruz CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12001SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30363 | Santa Cruz CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12002SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30364 | Santa Cruz CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12003SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30365 | Santa Cruz CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30366 | Santa Cruz CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 12007FS+12d,12009SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30367 | CARES V1 - Shasta CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.32000000000000001
30368 | Shasta CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
30369 | Shasta CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
30370 | Shasta CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
30371 | Shasta CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
30372 | Shasta CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
30373 | Shasta CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
30374 | Shasta CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30375 | Shasta CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
30376 | Shasta CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
30377 | Shasta CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
30378 | Shasta CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
30379 | Shasta CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
30380 | Shasta CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.65000000000000002
30381 | Shasta CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
30382 | Shasta CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
30383 | Shasta CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
30384 | Shasta CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
30385 | Shasta CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
30386 | Shasta CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
30387 | Shasta CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
30388 | Shasta CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
30389 | Shasta CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
30390 | Shasta CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
30391 | Shasta CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
30392 | Shasta CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
30393 | Shasta CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
30394 | Shasta CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
30395 | Shasta CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
30396 | Shasta CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
30397 | Shasta CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
30398 | Shasta CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
30399 | Shasta CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
30400 | Shasta CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
30401 | Shasta CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
30402 | Shasta CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/30/25 | NA | 1
30403 | Shasta CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
30404 | Shasta CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
30405 | Shasta CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
30406 | Shasta CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
30407 | Shasta CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
30408 | Shasta CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
30409 | Shasta CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
30410 | Shasta CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
30411 | Shasta CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30412 | Shasta CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
30413 | Shasta CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30414 | Shasta CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
30415 | Shasta CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
30416 | Shasta CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
30417 | Shasta CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
30418 | Shasta CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
30419 | Shasta CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
30420 | Shasta CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
30421 | Shasta CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
30422 | Shasta CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 12073SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
30423 | Shasta CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 12072SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
30424 | Shasta CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 12075SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30425 | Shasta CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 12074SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30426 | Shasta CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
30427 | Shasta CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 12078SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
30428 | Shasta CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 12077SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
30429 | Shasta CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30430 | Shasta CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 12081SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
30431 | Shasta CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 12080SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
30432 | Shasta CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30433 | Shasta CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 12084SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30434 | Shasta CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 12083SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30435 | Shasta CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30436 | Shasta CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 12087SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
30437 | Shasta CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 12086SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
30438 | Shasta CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
30439 | Shasta CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.31
30440 | Shasta CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
30441 | Shasta CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 12092 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
30442 | Shasta CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 12091 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
30443 | Shasta CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
30444 | Shasta CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
30445 | Shasta CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
30446 | Shasta CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30447 | Shasta CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 12098 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
30448 | Shasta CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 12097 | 12099 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
30449 | Shasta CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 12098 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
30450 | Shasta CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30451 | Shasta CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 12102 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
30452 | Shasta CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 12101 | 12103 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
30453 | Shasta CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 12102 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30454 | Shasta CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30455 | Shasta CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 12106 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30456 | Shasta CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 12105 | 12107 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30457 | Shasta CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 12106 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30458 | Shasta CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30459 | Shasta CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 12110 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30460 | Shasta CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 12109 | 12111 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30461 | Shasta CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 12110 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30462 | Shasta CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30463 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30464 | Shasta CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.42999999999999999
30465 | Shasta CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.95999999999999996
30466 | Shasta CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 12117SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
30467 | Shasta CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 12116SS | 12118 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
30468 | Shasta CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 12117 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.20000000000000001
30469 | Shasta CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
30470 | Shasta CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
30471 | Shasta CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
30472 | Shasta CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 12124 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
30473 | Shasta CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.68999999999999995
30474 | Shasta CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 12122 | 12125,12127SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
30475 | Shasta CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 12124 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
30476 | Shasta CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
30477 | Shasta CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 12124SS | 12128SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
30478 | Shasta CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 12127SS | 12129,12132,12130SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
30479 | Shasta CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 12128 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30480 | Shasta CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 12128SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30481 | Shasta CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30482 | Shasta CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 12128 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
30483 | Shasta CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.45000000000000001
30484 | Shasta CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 12135SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
30485 | Shasta CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 12134SS | 12136SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
30486 | Shasta CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 12135SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
30487 | Shasta CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
30488 | Shasta CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
30489 | Shasta CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 12145 | 12140SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
30490 | Shasta CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 12139SS | 12142 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
30491 | Shasta CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 508d | NA | NA | 0 days? | No | 7/21/25 | NA | NA | 0.97999999999999998
30492 | Shasta CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 12140 | 12143 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
30493 | Shasta CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 12142 |  | As Soon As Possible | NA | 21 | 508d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.94999999999999996
30494 | Shasta CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
30495 | Shasta CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 12139,12146SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
30496 | Shasta CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 12145SS | 12150,12147 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
30497 | Shasta CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 12146 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30498 | Shasta CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
30499 | Shasta CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30500 | Shasta CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 12146 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
30501 | Shasta CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30502 | Shasta CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30503 | Shasta CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30504 | Shasta CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30505 | Shasta CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30506 | Shasta CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30507 | Shasta CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30508 | Shasta CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30509 | Shasta CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30510 | Shasta CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30511 | Shasta CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30512 | Shasta CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30513 | Shasta CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
30514 | Shasta CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
30515 | Shasta CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 12172 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
30516 | Shasta CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
30517 | Shasta CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
30518 | Shasta CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
30519 | Shasta CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
30520 | Shasta CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 12179 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30521 | Shasta CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 12180 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30522 | Shasta CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 12165 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
30523 | Shasta CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30524 | Shasta CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12185SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30525 | Shasta CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12186SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30526 | Shasta CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12187SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30527 | Shasta CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12188SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30528 | Shasta CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12189SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30529 | Shasta CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 12170 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30530 | Shasta CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 12171 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30531 | Shasta CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
30532 | Shasta CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 12191FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30533 | Shasta CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
30534 | Shasta CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 12191SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
30535 | Shasta CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12174SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30536 | Shasta CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12175SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30537 | Shasta CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12176SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30538 | Shasta CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12177SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30539 | Shasta CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12178SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30540 | Shasta CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30541 | Shasta CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 12182FS+12d,12184SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30542 | CARES V1 - Sierra CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.28000000000000003
30543 | Sierra CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
30544 | Sierra CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
30545 | Sierra CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
30546 | Sierra CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
30547 | Sierra CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
30548 | Sierra CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
30549 | Sierra CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30550 | Sierra CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
30551 | Sierra CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
30552 | Sierra CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
30553 | Sierra CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
30554 | Sierra CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
30555 | Sierra CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
30556 | Sierra CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
30557 | Sierra CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
30558 | Sierra CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
30559 | Sierra CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
30560 | Sierra CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
30561 | Sierra CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
30562 | Sierra CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
30563 | Sierra CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
30564 | Sierra CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
30565 | Sierra CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
30566 | Sierra CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
30567 | Sierra CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
30568 | Sierra CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
30569 | Sierra CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
30570 | Sierra CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
30571 | Sierra CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
30572 | Sierra CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
30573 | Sierra CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
30574 | Sierra CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
30575 | Sierra CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
30576 | Sierra CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
30577 | Sierra CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
30578 | Sierra CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
30579 | Sierra CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
30580 | Sierra CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
30581 | Sierra CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
30582 | Sierra CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
30583 | Sierra CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
30584 | Sierra CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
30585 | Sierra CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
30586 | Sierra CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30587 | Sierra CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
30588 | Sierra CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30589 | Sierra CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
30590 | Sierra CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
30591 | Sierra CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
30592 | Sierra CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
30593 | Sierra CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
30594 | Sierra CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
30595 | Sierra CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
30596 | Sierra CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
30597 | Sierra CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 12248SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
30598 | Sierra CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 12247SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
30599 | Sierra CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 3885FS+29d | 12250SS | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30600 | Sierra CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 12249SS |  | As Soon As Possible | NA | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30601 | Sierra CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
30602 | Sierra CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 12253SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
30603 | Sierra CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 12252SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
30604 | Sierra CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30605 | Sierra CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 12256SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
30606 | Sierra CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 12255SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
30607 | Sierra CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30608 | Sierra CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 12259SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30609 | Sierra CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 12258SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30610 | Sierra CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30611 | Sierra CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 12262SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
30612 | Sierra CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 12261SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
30613 | Sierra CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
30614 | Sierra CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.5
30615 | Sierra CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
30616 | Sierra CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 12267 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
30617 | Sierra CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 12266 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
30618 | Sierra CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
30619 | Sierra CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
30620 | Sierra CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
30621 | Sierra CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30622 | Sierra CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 12273 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
30623 | Sierra CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 12272 | 12274 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
30624 | Sierra CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 12273 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
30625 | Sierra CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30626 | Sierra CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 12277 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
30627 | Sierra CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 12276 | 12278 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
30628 | Sierra CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 12277 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30629 | Sierra CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30630 | Sierra CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 12281 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
30631 | Sierra CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 12280 | 12282 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30632 | Sierra CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 12281 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30633 | Sierra CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30634 | Sierra CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 12285 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30635 | Sierra CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 12284 | 12286 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30636 | Sierra CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 12285 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30637 | Sierra CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30638 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30639 | Sierra CW-Technical | January 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 398 | 298d | NA | NA | 0 days? | No | 1/1/25 | NA | NA | 0.27000000000000002
30640 | Sierra CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
30641 | Sierra CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.83999999999999997
30642 | Sierra CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 12293,12295SS | Start No Earlier Than | 8/11/25 | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
30643 | Sierra CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 12292 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.59999999999999998
30644 | Sierra CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
30645 | Sierra CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 12292SS | 12296SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
30646 | Sierra CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 12295SS | 12297,12300,12298SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30647 | Sierra CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 12296 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30648 | Sierra CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 12296SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30649 | Sierra CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30650 | Sierra CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 12296 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
30651 | Sierra CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
30652 | Sierra CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
30653 | Sierra CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
30654 | Sierra CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
30655 | Sierra CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 12306SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
30656 | Sierra CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 12305SS |  | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
30657 | Sierra CW-Determine priority for Organization-specific custom Forms | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 508d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.59999999999999998
30658 | Sierra CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/2/25 | 21 | 508d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.59999999999999998
30659 | Sierra CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30660 | Sierra CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 64 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30661 | Sierra CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30662 | Sierra CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30663 | Sierra CW-POC or Organization Leadership to sign off on form completion | May 1, 2026 8:00 AM | May 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 17 | 346d | NA | NA | 0 days? | No | NA | NA | NA | 0
30664 | Sierra CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 363d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
30665 | Sierra CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
30666 | Sierra CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
30667 | Sierra CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
30668 | Sierra CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
30669 | Sierra CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
30670 | Sierra CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
30671 | Sierra CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
30672 | Sierra CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
30673 | Sierra CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
30674 | Sierra CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
30675 | Sierra CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
30676 | Sierra CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
30677 | Sierra CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
30678 | Sierra CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 12335 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
30679 | Sierra CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
30680 | Sierra CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
30681 | Sierra CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
30682 | Sierra CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
30683 | Sierra CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 12342 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30684 | Sierra CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 12343 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30685 | Sierra CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 12328 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
30686 | Sierra CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30687 | Sierra CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12348SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30688 | Sierra CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12349SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30689 | Sierra CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12350SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30690 | Sierra CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12351SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30691 | Sierra CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12352SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30692 | Sierra CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 12333 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30693 | Sierra CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 12334 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30694 | Sierra CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
30695 | Sierra CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 12354FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30696 | Sierra CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
30697 | Sierra CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 12354SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
30698 | Sierra CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12337SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30699 | Sierra CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12338SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30700 | Sierra CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12339SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30701 | Sierra CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12340SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30702 | Sierra CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12341SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30703 | Sierra CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30704 | Sierra CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 12345FS+12d,12347SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30705 | CARES V1 - Siskiyou CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.34000000000000002
30706 | Siskiyou CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
30707 | Siskiyou CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
30708 | Siskiyou CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
30709 | Siskiyou CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
30710 | Siskiyou CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
30711 | Siskiyou CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
30712 | Siskiyou CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30713 | Siskiyou CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
30714 | Siskiyou CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
30715 | Siskiyou CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
30716 | Siskiyou CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
30717 | Siskiyou CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
30718 | Siskiyou CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.65000000000000002
30719 | Siskiyou CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
30720 | Siskiyou CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
30721 | Siskiyou CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
30722 | Siskiyou CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
30723 | Siskiyou CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
30724 | Siskiyou CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
30725 | Siskiyou CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
30726 | Siskiyou CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
30727 | Siskiyou CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
30728 | Siskiyou CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
30729 | Siskiyou CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
30730 | Siskiyou CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
30731 | Siskiyou CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
30732 | Siskiyou CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
30733 | Siskiyou CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
30734 | Siskiyou CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
30735 | Siskiyou CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
30736 | Siskiyou CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
30737 | Siskiyou CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
30738 | Siskiyou CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
30739 | Siskiyou CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
30740 | Siskiyou CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/30/25 | NA | 1
30741 | Siskiyou CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
30742 | Siskiyou CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
30743 | Siskiyou CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
30744 | Siskiyou CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
30745 | Siskiyou CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
30746 | Siskiyou CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
30747 | Siskiyou CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
30748 | Siskiyou CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
30749 | Siskiyou CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30750 | Siskiyou CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
30751 | Siskiyou CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30752 | Siskiyou CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
30753 | Siskiyou CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
30754 | Siskiyou CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
30755 | Siskiyou CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
30756 | Siskiyou CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
30757 | Siskiyou CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
30758 | Siskiyou CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
30759 | Siskiyou CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
30760 | Siskiyou CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 12411SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
30761 | Siskiyou CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 12410SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
30762 | Siskiyou CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30763 | Siskiyou CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30764 | Siskiyou CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
30765 | Siskiyou CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 12416SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
30766 | Siskiyou CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 12415SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
30767 | Siskiyou CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30768 | Siskiyou CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 12419SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
30769 | Siskiyou CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 12418SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
30770 | Siskiyou CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30771 | Siskiyou CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 12422SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30772 | Siskiyou CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 12421SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30773 | Siskiyou CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30774 | Siskiyou CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 12425SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
30775 | Siskiyou CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 12424SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
30776 | Siskiyou CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
30777 | Siskiyou CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.40000000000000002
30778 | Siskiyou CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
30779 | Siskiyou CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 12430 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
30780 | Siskiyou CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 12429 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.40000000000000002
30781 | Siskiyou CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
30782 | Siskiyou CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
30783 | Siskiyou CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
30784 | Siskiyou CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30785 | Siskiyou CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 12436 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
30786 | Siskiyou CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 12435 | 12437 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
30787 | Siskiyou CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 12436 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
30788 | Siskiyou CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30789 | Siskiyou CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 12440 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
30790 | Siskiyou CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 12439 | 12441 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
30791 | Siskiyou CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 12440 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30792 | Siskiyou CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30793 | Siskiyou CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 12444 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
30794 | Siskiyou CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 12443 | 12445 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30795 | Siskiyou CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 12444 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30796 | Siskiyou CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30797 | Siskiyou CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 12448 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30798 | Siskiyou CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 12447 | 12449 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30799 | Siskiyou CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 12448 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30800 | Siskiyou CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30801 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30802 | Siskiyou CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.45000000000000001
30803 | Siskiyou CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.97999999999999998
30804 | Siskiyou CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 12455SS | Start No Earlier Than | 3/19/24 | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
30805 | Siskiyou CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 12454SS | 12456 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
30806 | Siskiyou CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 12455 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.59999999999999998
30807 | Siskiyou CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
30808 | Siskiyou CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
30809 | Siskiyou CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
30810 | Siskiyou CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 12462 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
30811 | Siskiyou CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.68999999999999995
30812 | Siskiyou CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 12460 | 12463,12465SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
30813 | Siskiyou CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 12462 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
30814 | Siskiyou CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
30815 | Siskiyou CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 12462SS | 12466SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
30816 | Siskiyou CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 12465SS | 12467,12470,12468SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
30817 | Siskiyou CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 12466 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30818 | Siskiyou CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 12466SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30819 | Siskiyou CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30820 | Siskiyou CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 12466 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
30821 | Siskiyou CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.56999999999999995
30822 | Siskiyou CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 12473SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
30823 | Siskiyou CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 12472SS | 12474SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.59999999999999998
30824 | Siskiyou CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 12473SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
30825 | Siskiyou CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
30826 | Siskiyou CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
30827 | Siskiyou CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 12483 | 12478SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
30828 | Siskiyou CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 12477SS | 12480 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
30829 | Siskiyou CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 508d | NA | NA | 0 days? | No | 7/21/25 | NA | NA | 0.83999999999999997
30830 | Siskiyou CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 12478 | 12481 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
30831 | Siskiyou CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 12480 |  | As Soon As Possible | NA | 21 | 508d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.59999999999999998
30832 | Siskiyou CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
30833 | Siskiyou CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 12477,12484SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
30834 | Siskiyou CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 12483SS | 12488,12485 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
30835 | Siskiyou CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 12484 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30836 | Siskiyou CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
30837 | Siskiyou CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30838 | Siskiyou CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 12484 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
30839 | Siskiyou CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30840 | Siskiyou CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30841 | Siskiyou CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30842 | Siskiyou CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30843 | Siskiyou CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30844 | Siskiyou CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30845 | Siskiyou CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30846 | Siskiyou CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30847 | Siskiyou CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30848 | Siskiyou CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30849 | Siskiyou CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30850 | Siskiyou CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30851 | Siskiyou CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
30852 | Siskiyou CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
30853 | Siskiyou CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 12510 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
30854 | Siskiyou CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
30855 | Siskiyou CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
30856 | Siskiyou CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
30857 | Siskiyou CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
30858 | Siskiyou CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 12517 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30859 | Siskiyou CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 12518 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30860 | Siskiyou CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 12503 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
30861 | Siskiyou CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30862 | Siskiyou CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12523SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30863 | Siskiyou CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12524SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30864 | Siskiyou CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12525SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30865 | Siskiyou CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12526SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30866 | Siskiyou CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12527SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30867 | Siskiyou CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 12508 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30868 | Siskiyou CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 12509 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
30869 | Siskiyou CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
30870 | Siskiyou CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 12529FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30871 | Siskiyou CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
30872 | Siskiyou CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 12529SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
30873 | Siskiyou CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12512SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30874 | Siskiyou CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12513SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30875 | Siskiyou CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12514SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30876 | Siskiyou CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12515SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30877 | Siskiyou CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12516SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30878 | Siskiyou CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30879 | Siskiyou CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 12520FS+12d,12522SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
30880 | CARES V1 - Solano CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.38
30881 | Solano CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
30882 | Solano CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
30883 | Solano CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
30884 | Solano CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
30885 | Solano CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
30886 | Solano CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
30887 | Solano CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30888 | Solano CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
30889 | Solano CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
30890 | Solano CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
30891 | Solano CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
30892 | Solano CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
30893 | Solano CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
30894 | Solano CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
30895 | Solano CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
30896 | Solano CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
30897 | Solano CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
30898 | Solano CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
30899 | Solano CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
30900 | Solano CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
30901 | Solano CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
30902 | Solano CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
30903 | Solano CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
30904 | Solano CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
30905 | Solano CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
30906 | Solano CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
30907 | Solano CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
30908 | Solano CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
30909 | Solano CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
30910 | Solano CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
30911 | Solano CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
30912 | Solano CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
30913 | Solano CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
30914 | Solano CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
30915 | Solano CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
30916 | Solano CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
30917 | Solano CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
30918 | Solano CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
30919 | Solano CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
30920 | Solano CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
30921 | Solano CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
30922 | Solano CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
30923 | Solano CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
30924 | Solano CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30925 | Solano CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
30926 | Solano CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30927 | Solano CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
30928 | Solano CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
30929 | Solano CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
30930 | Solano CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
30931 | Solano CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
30932 | Solano CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
30933 | Solano CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
30934 | Solano CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
30935 | Solano CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 12586SS | Start No Earlier Than | 1/5/26 | 20 | 424d | NA | NA | 0 days? | No | 1/5/26 | NA | NA | 0.20000000000000001
30936 | Solano CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 12585SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
30937 | Solano CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30938 | Solano CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30939 | Solano CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
30940 | Solano CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 12591SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
30941 | Solano CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 12590SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
30942 | Solano CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30943 | Solano CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 12594SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
30944 | Solano CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 12593SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
30945 | Solano CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30946 | Solano CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 12597SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30947 | Solano CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 12596SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
30948 | Solano CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
30949 | Solano CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 12600SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
30950 | Solano CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 12599SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
30951 | Solano CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
30952 | Solano CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.57999999999999996
30953 | Solano CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
30954 | Solano CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 12605 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
30955 | Solano CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 12604 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.80000000000000004
30956 | Solano CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
30957 | Solano CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
30958 | Solano CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
30959 | Solano CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30960 | Solano CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 12611 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
30961 | Solano CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 12610 | 12612 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
30962 | Solano CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 12611 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
30963 | Solano CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30964 | Solano CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 12615 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
30965 | Solano CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 12614 | 12616 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
30966 | Solano CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 12615 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30967 | Solano CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30968 | Solano CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 12619 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
30969 | Solano CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 12618 | 12620 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | 11/3/25 | NA | NA | 0.20000000000000001
30970 | Solano CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 12619 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
30971 | Solano CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30972 | Solano CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 12623 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30973 | Solano CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 12622 | 12624 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30974 | Solano CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 12623 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
30975 | Solano CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30976 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
30977 | Solano CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.47999999999999998
30978 | Solano CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
30979 | Solano CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 12630SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
30980 | Solano CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 12629SS | 12631 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
30981 | Solano CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 12630 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
30982 | Solano CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
30983 | Solano CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
30984 | Solano CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
30985 | Solano CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 12637 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
30986 | Solano CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
30987 | Solano CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 12635 | 12638,12640SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
30988 | Solano CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 12637 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
30989 | Solano CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.17999999999999999
30990 | Solano CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 12637SS | 12641SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
30991 | Solano CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 12640SS | 12642,12645,12643SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
30992 | Solano CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 12641 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
30993 | Solano CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 12641SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
30994 | Solano CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
30995 | Solano CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 12641 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
30996 | Solano CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.69999999999999996
30997 | Solano CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 12648SS | Start No Earlier Than | 2/3/25 | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
30998 | Solano CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 12647SS | 12649SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
30999 | Solano CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 12648SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
31000 | Solano CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
31001 | Solano CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
31002 | Solano CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 12658 | 12653SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
31003 | Solano CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 12652SS | 12655 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
31004 | Solano CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
31005 | Solano CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 12653 | 12656 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
31006 | Solano CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 12655 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
31007 | Solano CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
31008 | Solano CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 12652,12659SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
31009 | Solano CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 12658SS | 12663,12660 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
31010 | Solano CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 12659 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31011 | Solano CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
31012 | Solano CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31013 | Solano CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 12659 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
31014 | Solano CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31015 | Solano CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31016 | Solano CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31017 | Solano CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31018 | Solano CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31019 | Solano CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31020 | Solano CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31021 | Solano CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31022 | Solano CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31023 | Solano CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31024 | Solano CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31025 | Solano CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31026 | Solano CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
31027 | Solano CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 4.0000000000000001E-2
31028 | Solano CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 12685 | Start No Earlier Than | 7/1/25 | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
31029 | Solano CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
31030 | Solano CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
31031 | Solano CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31032 | Solano CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31033 | Solano CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 12692 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31034 | Solano CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 12693 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31035 | Solano CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 12678 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
31036 | Solano CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31037 | Solano CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12698SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31038 | Solano CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12699SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31039 | Solano CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12700SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31040 | Solano CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12701SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31041 | Solano CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12702SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31042 | Solano CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 12683 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31043 | Solano CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 12684 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31044 | Solano CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
31045 | Solano CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 12704FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31046 | Solano CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
31047 | Solano CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 12704SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
31048 | Solano CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12687SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31049 | Solano CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12688SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31050 | Solano CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12689SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31051 | Solano CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12690SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31052 | Solano CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12691SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31053 | Solano CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31054 | Solano CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 12695FS+12d,12697SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31055 | CARES V1 - Sonoma CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.28999999999999998
31056 | Sonoma CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
31057 | Sonoma CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
31058 | Sonoma CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
31059 | Sonoma CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
31060 | Sonoma CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
31061 | Sonoma CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
31062 | Sonoma CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31063 | Sonoma CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
31064 | Sonoma CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
31065 | Sonoma CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
31066 | Sonoma CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
31067 | Sonoma CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
31068 | Sonoma CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
31069 | Sonoma CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
31070 | Sonoma CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
31071 | Sonoma CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
31072 | Sonoma CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
31073 | Sonoma CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
31074 | Sonoma CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
31075 | Sonoma CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
31076 | Sonoma CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
31077 | Sonoma CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
31078 | Sonoma CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
31079 | Sonoma CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
31080 | Sonoma CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
31081 | Sonoma CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
31082 | Sonoma CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
31083 | Sonoma CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
31084 | Sonoma CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
31085 | Sonoma CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
31086 | Sonoma CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
31087 | Sonoma CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
31088 | Sonoma CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
31089 | Sonoma CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
31090 | Sonoma CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
31091 | Sonoma CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
31092 | Sonoma CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
31093 | Sonoma CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
31094 | Sonoma CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
31095 | Sonoma CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
31096 | Sonoma CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
31097 | Sonoma CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
31098 | Sonoma CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31099 | Sonoma CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31100 | Sonoma CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
31101 | Sonoma CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31102 | Sonoma CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
31103 | Sonoma CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
31104 | Sonoma CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
31105 | Sonoma CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
31106 | Sonoma CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
31107 | Sonoma CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
31108 | Sonoma CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
31109 | Sonoma CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
31110 | Sonoma CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 12761SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
31111 | Sonoma CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 12760SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
31112 | Sonoma CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31113 | Sonoma CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31114 | Sonoma CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
31115 | Sonoma CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 12766SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
31116 | Sonoma CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 12765SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
31117 | Sonoma CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31118 | Sonoma CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 12769SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
31119 | Sonoma CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 12768SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
31120 | Sonoma CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31121 | Sonoma CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 12772SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31122 | Sonoma CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 12771SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31123 | Sonoma CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31124 | Sonoma CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 12775SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
31125 | Sonoma CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 12774SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
31126 | Sonoma CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
31127 | Sonoma CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.47999999999999998
31128 | Sonoma CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
31129 | Sonoma CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 12780 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
31130 | Sonoma CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 12779 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
31131 | Sonoma CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
31132 | Sonoma CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
31133 | Sonoma CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
31134 | Sonoma CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31135 | Sonoma CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 12786 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
31136 | Sonoma CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 12785 | 12787 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
31137 | Sonoma CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 12786 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
31138 | Sonoma CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31139 | Sonoma CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 12790 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
31140 | Sonoma CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 12789 | 12791 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31141 | Sonoma CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 12790 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31142 | Sonoma CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31143 | Sonoma CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 12794 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31144 | Sonoma CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 12793 | 12795 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31145 | Sonoma CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 12794 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31146 | Sonoma CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31147 | Sonoma CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 12798 | Start No Earlier Than | 11/3/25 | 40 | 0d | NA | NA | 0 days? | No | 11/3/25 | 12/31/25 | NA | 1
31148 | Sonoma CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 12797 | 12799 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31149 | Sonoma CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 12798 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31150 | Sonoma CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31151 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31152 | Sonoma CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.32000000000000001
31153 | Sonoma CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.76000000000000001
31154 | Sonoma CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 12805SS | Start No Earlier Than | 3/19/24 | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
31155 | Sonoma CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 12804SS | 12806 | As Soon As Possible | NA | 490 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.59999999999999998
31156 | Sonoma CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 12805 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31157 | Sonoma CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
31158 | Sonoma CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
31159 | Sonoma CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
31160 | Sonoma CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 12812 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
31161 | Sonoma CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.60999999999999999
31162 | Sonoma CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 12810 | 12813,12815SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
31163 | Sonoma CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 12812 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
31164 | Sonoma CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 4.0000000000000001E-2
31165 | Sonoma CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 12812SS | 12816SS | As Soon As Possible | NA | 36 | 508d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.80000000000000004
31166 | Sonoma CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 12815SS | 12817,12820,12818SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31167 | Sonoma CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 12816 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31168 | Sonoma CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 12816SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31169 | Sonoma CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31170 | Sonoma CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 12816 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
31171 | Sonoma CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.31
31172 | Sonoma CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 12823SS | Start No Earlier Than | 2/3/25 | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
31173 | Sonoma CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 12822SS | 12824SS | As Soon As Possible | NA | 190 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
31174 | Sonoma CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 12823SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
31175 | Sonoma CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
31176 | Sonoma CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
31177 | Sonoma CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 12833 | 12828SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
31178 | Sonoma CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 12827SS | 12830 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
31179 | Sonoma CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 508d | NA | NA | 0 days? | No | 7/21/25 | NA | NA | 0.64000000000000001
31180 | Sonoma CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 12828 | 12831 | As Soon As Possible | NA | 30 | 4.2d | NA | NA | 0 days? | No | 7/21/25 | NA | NA | 0.94999999999999996
31181 | Sonoma CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 12830 |  | As Soon As Possible | NA | 21 | 508d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
31182 | Sonoma CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
31183 | Sonoma CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 12827,12834SS | Start No Earlier Than | 7/1/25 | 64 | 508d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
31184 | Sonoma CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 12833SS | 12838,12835 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31185 | Sonoma CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 12834 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31186 | Sonoma CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31187 | Sonoma CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31188 | Sonoma CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 12834 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
31189 | Sonoma CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31190 | Sonoma CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31191 | Sonoma CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31192 | Sonoma CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31193 | Sonoma CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31194 | Sonoma CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31195 | Sonoma CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31196 | Sonoma CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31197 | Sonoma CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31198 | Sonoma CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31199 | Sonoma CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31200 | Sonoma CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31201 | Sonoma CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
31202 | Sonoma CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
31203 | Sonoma CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 12860 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
31204 | Sonoma CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
31205 | Sonoma CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
31206 | Sonoma CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31207 | Sonoma CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31208 | Sonoma CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 12867 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31209 | Sonoma CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 12868 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31210 | Sonoma CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 12853 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
31211 | Sonoma CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31212 | Sonoma CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12873SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31213 | Sonoma CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12874SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31214 | Sonoma CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12875SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31215 | Sonoma CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12876SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31216 | Sonoma CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 12877SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31217 | Sonoma CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 12858 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31218 | Sonoma CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 12859 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31219 | Sonoma CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
31220 | Sonoma CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 12879FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31221 | Sonoma CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
31222 | Sonoma CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 12879SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
31223 | Sonoma CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12862SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31224 | Sonoma CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12863SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31225 | Sonoma CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12864SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31226 | Sonoma CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12865SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31227 | Sonoma CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 12866SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31228 | Sonoma CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31229 | Sonoma CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 12870FS+12d,12872SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31230 | CARES V1 - Stanislaus CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.38
31231 | Stanislaus CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
31232 | Stanislaus CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
31233 | Stanislaus CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
31234 | Stanislaus CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
31235 | Stanislaus CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
31236 | Stanislaus CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
31237 | Stanislaus CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31238 | Stanislaus CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
31239 | Stanislaus CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
31240 | Stanislaus CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
31241 | Stanislaus CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
31242 | Stanislaus CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
31243 | Stanislaus CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
31244 | Stanislaus CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
31245 | Stanislaus CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
31246 | Stanislaus CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
31247 | Stanislaus CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
31248 | Stanislaus CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
31249 | Stanislaus CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
31250 | Stanislaus CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
31251 | Stanislaus CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
31252 | Stanislaus CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
31253 | Stanislaus CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
31254 | Stanislaus CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
31255 | Stanislaus CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
31256 | Stanislaus CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
31257 | Stanislaus CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
31258 | Stanislaus CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
31259 | Stanislaus CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
31260 | Stanislaus CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
31261 | Stanislaus CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
31262 | Stanislaus CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
31263 | Stanislaus CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
31264 | Stanislaus CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
31265 | Stanislaus CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
31266 | Stanislaus CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
31267 | Stanislaus CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
31268 | Stanislaus CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
31269 | Stanislaus CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
31270 | Stanislaus CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
31271 | Stanislaus CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
31272 | Stanislaus CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
31273 | Stanislaus CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31274 | Stanislaus CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31275 | Stanislaus CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
31276 | Stanislaus CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31277 | Stanislaus CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
31278 | Stanislaus CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
31279 | Stanislaus CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
31280 | Stanislaus CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
31281 | Stanislaus CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
31282 | Stanislaus CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
31283 | Stanislaus CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
31284 | Stanislaus CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
31285 | Stanislaus CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 12936SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
31286 | Stanislaus CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 12935SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
31287 | Stanislaus CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31288 | Stanislaus CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31289 | Stanislaus CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
31290 | Stanislaus CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 12941SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
31291 | Stanislaus CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 12940SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
31292 | Stanislaus CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31293 | Stanislaus CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 12944SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
31294 | Stanislaus CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 12943SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
31295 | Stanislaus CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31296 | Stanislaus CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 12947SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31297 | Stanislaus CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 12946SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31298 | Stanislaus CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31299 | Stanislaus CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 12950SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
31300 | Stanislaus CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 12949SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
31301 | Stanislaus CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
31302 | Stanislaus CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.37
31303 | Stanislaus CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
31304 | Stanislaus CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 12955 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
31305 | Stanislaus CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 12954 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
31306 | Stanislaus CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
31307 | Stanislaus CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
31308 | Stanislaus CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
31309 | Stanislaus CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31310 | Stanislaus CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 12961 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
31311 | Stanislaus CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 12960 | 12962 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
31312 | Stanislaus CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 12961 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
31313 | Stanislaus CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31314 | Stanislaus CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 12965 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
31315 | Stanislaus CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 12964 | 12966 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
31316 | Stanislaus CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 12965 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31317 | Stanislaus CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31318 | Stanislaus CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 12969 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
31319 | Stanislaus CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 12968 | 12970 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31320 | Stanislaus CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 12969 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31321 | Stanislaus CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31322 | Stanislaus CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 12973 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | 11/3/25 | NA | NA | 0.94999999999999996
31323 | Stanislaus CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 12972 | 12974 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31324 | Stanislaus CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 12973 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31325 | Stanislaus CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31326 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31327 | Stanislaus CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.54000000000000004
31328 | Stanislaus CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
31329 | Stanislaus CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 12980SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
31330 | Stanislaus CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 12979SS | 12981 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
31331 | Stanislaus CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 12980 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31332 | Stanislaus CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
31333 | Stanislaus CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
31334 | Stanislaus CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
31335 | Stanislaus CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 12987 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
31336 | Stanislaus CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.60999999999999999
31337 | Stanislaus CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 12985 | 12988,12990SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
31338 | Stanislaus CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 12987 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
31339 | Stanislaus CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.17000000000000001
31340 | Stanislaus CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 12987SS | 12991SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
31341 | Stanislaus CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 12990SS | 12992,12995,12993SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.40000000000000002
31342 | Stanislaus CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 12991 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31343 | Stanislaus CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 12991SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31344 | Stanislaus CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31345 | Stanislaus CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 12991 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
31346 | Stanislaus CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 0d | NA | NA | 0 days? | No | 2/3/25 | 12/31/25 | NA | 1
31347 | Stanislaus CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 12998SS | Start No Earlier Than | 2/3/25 | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
31348 | Stanislaus CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 12997SS | 12999SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
31349 | Stanislaus CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 12998SS |  | As Soon As Possible | NA | 230 | 0d | NA | NA | 0 days? | No | 2/3/25 | 12/31/25 | NA | 1
31350 | Stanislaus CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
31351 | Stanislaus CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
31352 | Stanislaus CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 13008 | 13003SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
31353 | Stanislaus CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 13002SS | 13005 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
31354 | Stanislaus CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
31355 | Stanislaus CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 13003 | 13006 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
31356 | Stanislaus CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 13005 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
31357 | Stanislaus CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.38
31358 | Stanislaus CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 13002,13009SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
31359 | Stanislaus CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 13008SS | 13013,13010 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.80000000000000004
31360 | Stanislaus CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 13009 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31361 | Stanislaus CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
31362 | Stanislaus CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31363 | Stanislaus CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 13009 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
31364 | Stanislaus CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31365 | Stanislaus CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31366 | Stanislaus CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31367 | Stanislaus CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31368 | Stanislaus CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31369 | Stanislaus CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31370 | Stanislaus CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31371 | Stanislaus CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31372 | Stanislaus CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31373 | Stanislaus CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31374 | Stanislaus CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31375 | Stanislaus CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31376 | Stanislaus CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
31377 | Stanislaus CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 5.0000000000000003E-2
31378 | Stanislaus CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 13035 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.59999999999999998
31379 | Stanislaus CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
31380 | Stanislaus CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
31381 | Stanislaus CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31382 | Stanislaus CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31383 | Stanislaus CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 13042 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31384 | Stanislaus CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 13043 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31385 | Stanislaus CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 13028 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
31386 | Stanislaus CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31387 | Stanislaus CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13048SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31388 | Stanislaus CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13049SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31389 | Stanislaus CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13050SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31390 | Stanislaus CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13051SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31391 | Stanislaus CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13052SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31392 | Stanislaus CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 13033 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31393 | Stanislaus CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 13034 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31394 | Stanislaus CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
31395 | Stanislaus CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 13054FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31396 | Stanislaus CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
31397 | Stanislaus CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 13054SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
31398 | Stanislaus CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13037SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31399 | Stanislaus CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13038SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31400 | Stanislaus CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13039SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31401 | Stanislaus CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13040SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31402 | Stanislaus CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13041SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31403 | Stanislaus CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31404 | Stanislaus CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 13045FS+12d,13047SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31405 | CARES V1 - Sutter CW | April 1, 2021 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 1443 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 4/1/21 | NA | NA | 0.34000000000000002
31406 | Sutter CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
31407 | Sutter CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
31408 | Sutter CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
31409 | Sutter CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
31410 | Sutter CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
31411 | Sutter CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
31412 | Sutter CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31413 | Sutter CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
31414 | Sutter CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
31415 | Sutter CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
31416 | Sutter CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
31417 | Sutter CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
31418 | Sutter CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
31419 | Sutter CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
31420 | Sutter CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
31421 | Sutter CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
31422 | Sutter CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
31423 | Sutter CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
31424 | Sutter CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
31425 | Sutter CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
31426 | Sutter CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
31427 | Sutter CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
31428 | Sutter CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
31429 | Sutter CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
31430 | Sutter CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
31431 | Sutter CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
31432 | Sutter CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
31433 | Sutter CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
31434 | Sutter CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
31435 | Sutter CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
31436 | Sutter CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
31437 | Sutter CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
31438 | Sutter CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
31439 | Sutter CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
31440 | Sutter CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
31441 | Sutter CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
31442 | Sutter CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
31443 | Sutter CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
31444 | Sutter CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
31445 | Sutter CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
31446 | Sutter CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
31447 | Sutter CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
31448 | Sutter CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31449 | Sutter CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31450 | Sutter CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
31451 | Sutter CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31452 | Sutter CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
31453 | Sutter CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
31454 | Sutter CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
31455 | Sutter CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
31456 | Sutter CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
31457 | Sutter CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
31458 | Sutter CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
31459 | Sutter CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
31460 | Sutter CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 13111SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
31461 | Sutter CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 13110SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
31462 | Sutter CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31463 | Sutter CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31464 | Sutter CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
31465 | Sutter CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 13116SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
31466 | Sutter CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 13115SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
31467 | Sutter CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31468 | Sutter CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 13119SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
31469 | Sutter CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 13118SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
31470 | Sutter CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31471 | Sutter CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 13122SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31472 | Sutter CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 13121SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31473 | Sutter CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31474 | Sutter CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 13125SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
31475 | Sutter CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 13124SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
31476 | Sutter CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
31477 | Sutter CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.40000000000000002
31478 | Sutter CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
31479 | Sutter CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 13130 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
31480 | Sutter CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 13129 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.40000000000000002
31481 | Sutter CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
31482 | Sutter CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
31483 | Sutter CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
31484 | Sutter CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31485 | Sutter CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 13136 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
31486 | Sutter CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 13135 | 13137 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
31487 | Sutter CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 13136 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
31488 | Sutter CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31489 | Sutter CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 13140 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
31490 | Sutter CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 13139 | 13141 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
31491 | Sutter CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 13140 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31492 | Sutter CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31493 | Sutter CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 13144 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
31494 | Sutter CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 13143 | 13145 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31495 | Sutter CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 13144 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31496 | Sutter CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31497 | Sutter CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 13148 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31498 | Sutter CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 13147 | 13149 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31499 | Sutter CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 13148 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31500 | Sutter CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31501 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31502 | Sutter CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.46000000000000002
31503 | Sutter CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
31504 | Sutter CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 13155SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
31505 | Sutter CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 13154SS | 13156 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
31506 | Sutter CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 13155 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31507 | Sutter CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
31508 | Sutter CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
31509 | Sutter CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
31510 | Sutter CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 13162 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
31511 | Sutter CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.60999999999999999
31512 | Sutter CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 13160 | 13163,13165SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
31513 | Sutter CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 13162 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
31514 | Sutter CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
31515 | Sutter CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 13162SS | 13166SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
31516 | Sutter CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 13165SS | 13167,13170,13168SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
31517 | Sutter CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 13166 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31518 | Sutter CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 13166SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31519 | Sutter CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31520 | Sutter CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 13166 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
31521 | Sutter CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.69999999999999996
31522 | Sutter CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 13173SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
31523 | Sutter CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 13172SS | 13174SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
31524 | Sutter CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 13173SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
31525 | Sutter CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
31526 | Sutter CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
31527 | Sutter CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 13183 | 13178SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
31528 | Sutter CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 13177SS | 13180 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
31529 | Sutter CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
31530 | Sutter CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 13178 | 13181 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
31531 | Sutter CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 13180 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
31532 | Sutter CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
31533 | Sutter CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 13177,13184SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
31534 | Sutter CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 13183SS | 13188,13185 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
31535 | Sutter CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 13184 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31536 | Sutter CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
31537 | Sutter CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31538 | Sutter CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 13184 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
31539 | Sutter CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31540 | Sutter CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31541 | Sutter CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31542 | Sutter CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31543 | Sutter CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31544 | Sutter CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31545 | Sutter CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31546 | Sutter CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31547 | Sutter CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31548 | Sutter CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31549 | Sutter CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31550 | Sutter CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31551 | Sutter CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
31552 | Sutter CW-Training | April 1, 2021 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 1404 | 234d | NA | NA | 0 days? | No | 4/1/21 | NA | NA | 0.02
31553 | Sutter CW-Develop the CARES V1 Organization Training Plan | April 1, 2021 8:00 AM | December 28, 2021 5:00 PM |  | 13210 | As Soon As Possible | NA | 188 | 1261d | NA | NA | 0 days? | No | 4/1/21 | NA | NA | 0.20000000000000001
31554 | Sutter CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
31555 | Sutter CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
31556 | Sutter CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31557 | Sutter CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31558 | Sutter CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 13217 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31559 | Sutter CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 13218 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31560 | Sutter CW-Execute the CARES V1 Organization Training Plan | December 29, 2021 8:00 AM | September 27, 2022 5:00 PM | 13203 |  | As Soon As Possible | NA | 189 | 1261d | NA | NA | 0 days? | No | NA | NA | NA | 0
31561 | Sutter CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31562 | Sutter CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13223SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31563 | Sutter CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13224SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31564 | Sutter CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13225SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31565 | Sutter CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13226SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31566 | Sutter CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13227SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31567 | Sutter CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 13208 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31568 | Sutter CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 13209 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31569 | Sutter CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
31570 | Sutter CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 13229FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31571 | Sutter CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
31572 | Sutter CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 13229SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
31573 | Sutter CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13212SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31574 | Sutter CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13213SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31575 | Sutter CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13214SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31576 | Sutter CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13215SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31577 | Sutter CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13216SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31578 | Sutter CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31579 | Sutter CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 13220FS+12d,13222SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31580 | CARES V1 - Tehama CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.42999999999999999
31581 | Tehama CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
31582 | Tehama CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
31583 | Tehama CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
31584 | Tehama CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
31585 | Tehama CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
31586 | Tehama CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
31587 | Tehama CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31588 | Tehama CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
31589 | Tehama CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
31590 | Tehama CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
31591 | Tehama CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
31592 | Tehama CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
31593 | Tehama CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
31594 | Tehama CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
31595 | Tehama CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
31596 | Tehama CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
31597 | Tehama CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
31598 | Tehama CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
31599 | Tehama CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
31600 | Tehama CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
31601 | Tehama CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
31602 | Tehama CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
31603 | Tehama CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
31604 | Tehama CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
31605 | Tehama CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
31606 | Tehama CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
31607 | Tehama CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
31608 | Tehama CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
31609 | Tehama CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
31610 | Tehama CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
31611 | Tehama CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
31612 | Tehama CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
31613 | Tehama CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
31614 | Tehama CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
31615 | Tehama CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
31616 | Tehama CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
31617 | Tehama CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
31618 | Tehama CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
31619 | Tehama CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
31620 | Tehama CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
31621 | Tehama CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
31622 | Tehama CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
31623 | Tehama CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31624 | Tehama CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31625 | Tehama CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
31626 | Tehama CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31627 | Tehama CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
31628 | Tehama CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
31629 | Tehama CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
31630 | Tehama CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
31631 | Tehama CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
31632 | Tehama CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
31633 | Tehama CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
31634 | Tehama CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
31635 | Tehama CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 13286SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
31636 | Tehama CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 13285SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
31637 | Tehama CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31638 | Tehama CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31639 | Tehama CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
31640 | Tehama CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 13291SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
31641 | Tehama CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 13290SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
31642 | Tehama CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31643 | Tehama CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 13294SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
31644 | Tehama CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 13293SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
31645 | Tehama CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31646 | Tehama CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 13297SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31647 | Tehama CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 13296SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31648 | Tehama CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31649 | Tehama CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 13300SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
31650 | Tehama CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 13299SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
31651 | Tehama CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
31652 | Tehama CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.51000000000000001
31653 | Tehama CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
31654 | Tehama CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 13305 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
31655 | Tehama CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 13304 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
31656 | Tehama CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
31657 | Tehama CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
31658 | Tehama CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
31659 | Tehama CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31660 | Tehama CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 13311 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
31661 | Tehama CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 13310 | 13312 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
31662 | Tehama CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 13311 |  | As Soon As Possible | NA | 63 | 0d | NA | NA | 0 days? | No | 9/2/25 | 12/1/25 | NA | 1
31663 | Tehama CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31664 | Tehama CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 13315 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
31665 | Tehama CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 13314 | 13316 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
31666 | Tehama CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 13315 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31667 | Tehama CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31668 | Tehama CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 13319 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31669 | Tehama CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 13318 | 13320 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31670 | Tehama CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 13319 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31671 | Tehama CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31672 | Tehama CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 13323 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31673 | Tehama CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 13322 | 13324 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31674 | Tehama CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 13323 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31675 | Tehama CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31676 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31677 | Tehama CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.63
31678 | Tehama CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
31679 | Tehama CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 13330SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
31680 | Tehama CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 13329SS | 13331 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
31681 | Tehama CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 13330 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31682 | Tehama CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
31683 | Tehama CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
31684 | Tehama CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
31685 | Tehama CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 13337 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
31686 | Tehama CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
31687 | Tehama CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 13335 | 13338,13340SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
31688 | Tehama CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 13337 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
31689 | Tehama CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
31690 | Tehama CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 13337SS | 13341SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
31691 | Tehama CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 13340SS | 13342,13345,13343SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31692 | Tehama CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 13341 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31693 | Tehama CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 13341SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31694 | Tehama CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31695 | Tehama CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 13341 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
31696 | Tehama CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 0d | NA | NA | 0 days? | No | 2/3/25 | 12/31/25 | NA | 1
31697 | Tehama CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 13348SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
31698 | Tehama CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 13347SS | 13349SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
31699 | Tehama CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 13348SS |  | As Soon As Possible | NA | 230 | 0d | NA | NA | 0 days? | No | 2/3/25 | 12/31/25 | NA | 1
31700 | Tehama CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
31701 | Tehama CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
31702 | Tehama CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 13358 | 13353SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
31703 | Tehama CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 13352SS | 13355 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
31704 | Tehama CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
31705 | Tehama CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 13353 | 13356 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
31706 | Tehama CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 13355 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
31707 | Tehama CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.69999999999999996
31708 | Tehama CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 13352,13359SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
31709 | Tehama CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 13358SS | 13363,13360 | As Soon As Possible | NA | 210 | 0d | NA | NA | 0 days? | No | 7/1/25 | 5/1/26 | NA | 1
31710 | Tehama CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 13359 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31711 | Tehama CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/3/26 | NA | 1
31712 | Tehama CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31713 | Tehama CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 13359 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
31714 | Tehama CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 363d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
31715 | Tehama CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
31716 | Tehama CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
31717 | Tehama CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
31718 | Tehama CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
31719 | Tehama CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
31720 | Tehama CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
31721 | Tehama CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
31722 | Tehama CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
31723 | Tehama CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
31724 | Tehama CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
31725 | Tehama CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
31726 | Tehama CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
31727 | Tehama CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
31728 | Tehama CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 13385 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
31729 | Tehama CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
31730 | Tehama CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
31731 | Tehama CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31732 | Tehama CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31733 | Tehama CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 13392 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31734 | Tehama CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 13393 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31735 | Tehama CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 13378 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
31736 | Tehama CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31737 | Tehama CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13398SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31738 | Tehama CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13399SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31739 | Tehama CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13400SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31740 | Tehama CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13401SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31741 | Tehama CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13402SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31742 | Tehama CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 13383 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31743 | Tehama CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 13384 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31744 | Tehama CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
31745 | Tehama CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 13404FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31746 | Tehama CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
31747 | Tehama CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 13404SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
31748 | Tehama CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13387SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31749 | Tehama CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13388SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31750 | Tehama CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13389SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31751 | Tehama CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13390SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31752 | Tehama CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13391SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31753 | Tehama CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31754 | Tehama CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 13395FS+12d,13397SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31755 | CARES V1 - Trinity CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.23000000000000001
31756 | Trinity CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
31757 | Trinity CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
31758 | Trinity CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
31759 | Trinity CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
31760 | Trinity CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
31761 | Trinity CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
31762 | Trinity CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31763 | Trinity CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
31764 | Trinity CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
31765 | Trinity CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
31766 | Trinity CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
31767 | Trinity CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
31768 | Trinity CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
31769 | Trinity CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
31770 | Trinity CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
31771 | Trinity CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
31772 | Trinity CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
31773 | Trinity CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
31774 | Trinity CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
31775 | Trinity CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
31776 | Trinity CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
31777 | Trinity CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
31778 | Trinity CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
31779 | Trinity CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
31780 | Trinity CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
31781 | Trinity CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
31782 | Trinity CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
31783 | Trinity CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
31784 | Trinity CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
31785 | Trinity CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
31786 | Trinity CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
31787 | Trinity CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
31788 | Trinity CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
31789 | Trinity CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
31790 | Trinity CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
31791 | Trinity CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
31792 | Trinity CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
31793 | Trinity CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
31794 | Trinity CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
31795 | Trinity CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
31796 | Trinity CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
31797 | Trinity CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
31798 | Trinity CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31799 | Trinity CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31800 | Trinity CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
31801 | Trinity CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31802 | Trinity CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
31803 | Trinity CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
31804 | Trinity CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
31805 | Trinity CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
31806 | Trinity CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
31807 | Trinity CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
31808 | Trinity CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
31809 | Trinity CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
31810 | Trinity CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 13461SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
31811 | Trinity CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 13460SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
31812 | Trinity CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31813 | Trinity CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31814 | Trinity CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
31815 | Trinity CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 13466SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
31816 | Trinity CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 13465SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
31817 | Trinity CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31818 | Trinity CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 13469SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
31819 | Trinity CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 13468SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
31820 | Trinity CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31821 | Trinity CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 13472SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31822 | Trinity CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 13471SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31823 | Trinity CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31824 | Trinity CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 13475SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
31825 | Trinity CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 13474SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
31826 | Trinity CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
31827 | Trinity CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.37
31828 | Trinity CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
31829 | Trinity CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 13480 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
31830 | Trinity CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 13479 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
31831 | Trinity CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
31832 | Trinity CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
31833 | Trinity CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
31834 | Trinity CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31835 | Trinity CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 13486 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
31836 | Trinity CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 13485 | 13487 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
31837 | Trinity CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 13486 |  | As Soon As Possible | NA | 63 | 0d | NA | NA | 0 days? | No | 9/2/25 | 12/1/25 | NA | 1
31838 | Trinity CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31839 | Trinity CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 13490 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
31840 | Trinity CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 13489 | 13491 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
31841 | Trinity CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 13490 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31842 | Trinity CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31843 | Trinity CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 13494 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
31844 | Trinity CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 13493 | 13495 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31845 | Trinity CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 13494 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31846 | Trinity CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31847 | Trinity CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 13498 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31848 | Trinity CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 13497 | 13499 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31849 | Trinity CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 13498 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31850 | Trinity CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31851 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31852 | Trinity CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.22
31853 | Trinity CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.19
31854 | Trinity CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 13505SS | Start No Earlier Than | 3/19/24 | 490 | 405d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.20000000000000001
31855 | Trinity CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 13504SS | 13506 | As Soon As Possible | NA | 490 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.20000000000000001
31856 | Trinity CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 13505 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31857 | Trinity CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
31858 | Trinity CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
31859 | Trinity CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
31860 | Trinity CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 13512 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
31861 | Trinity CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
31862 | Trinity CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 13510 | 13513,13515SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
31863 | Trinity CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 13512 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
31864 | Trinity CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
31865 | Trinity CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 13512SS | 13516SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
31866 | Trinity CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 13515SS | 13517,13520,13518SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
31867 | Trinity CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 13516 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31868 | Trinity CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 13516SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31869 | Trinity CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31870 | Trinity CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 13516 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
31871 | Trinity CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
31872 | Trinity CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 13523SS | Start No Earlier Than | 2/3/25 | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
31873 | Trinity CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 13522SS | 13524SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
31874 | Trinity CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 13523SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
31875 | Trinity CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
31876 | Trinity CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
31877 | Trinity CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 13533 | 13528SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
31878 | Trinity CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 13527SS | 13530 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
31879 | Trinity CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
31880 | Trinity CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 13528 | 13531 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
31881 | Trinity CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 13530 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
31882 | Trinity CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
31883 | Trinity CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 13527,13534SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
31884 | Trinity CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 13533SS | 13538,13535 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
31885 | Trinity CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 13534 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
31886 | Trinity CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
31887 | Trinity CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31888 | Trinity CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 13534 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
31889 | Trinity CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31890 | Trinity CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31891 | Trinity CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31892 | Trinity CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31893 | Trinity CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31894 | Trinity CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31895 | Trinity CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31896 | Trinity CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31897 | Trinity CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31898 | Trinity CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31899 | Trinity CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31900 | Trinity CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31901 | Trinity CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
31902 | Trinity CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
31903 | Trinity CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 13560 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
31904 | Trinity CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
31905 | Trinity CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
31906 | Trinity CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31907 | Trinity CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31908 | Trinity CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 13567 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31909 | Trinity CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 13568 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31910 | Trinity CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 13553 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
31911 | Trinity CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
31912 | Trinity CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13573SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31913 | Trinity CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13574SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31914 | Trinity CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13575SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31915 | Trinity CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13576SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31916 | Trinity CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13577SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
31917 | Trinity CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 13558 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31918 | Trinity CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 13559 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
31919 | Trinity CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
31920 | Trinity CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 13579FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31921 | Trinity CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
31922 | Trinity CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 13579SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
31923 | Trinity CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13562SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31924 | Trinity CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13563SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31925 | Trinity CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13564SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31926 | Trinity CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13565SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31927 | Trinity CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13566SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31928 | Trinity CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31929 | Trinity CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 13570FS+12d,13572SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
31930 | CARES V1 - Tulare CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.33000000000000002
31931 | Tulare CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
31932 | Tulare CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
31933 | Tulare CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
31934 | Tulare CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
31935 | Tulare CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
31936 | Tulare CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
31937 | Tulare CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
31938 | Tulare CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
31939 | Tulare CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
31940 | Tulare CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
31941 | Tulare CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
31942 | Tulare CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
31943 | Tulare CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
31944 | Tulare CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
31945 | Tulare CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
31946 | Tulare CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
31947 | Tulare CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
31948 | Tulare CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
31949 | Tulare CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
31950 | Tulare CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
31951 | Tulare CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
31952 | Tulare CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
31953 | Tulare CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
31954 | Tulare CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
31955 | Tulare CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
31956 | Tulare CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
31957 | Tulare CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
31958 | Tulare CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
31959 | Tulare CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
31960 | Tulare CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
31961 | Tulare CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
31962 | Tulare CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
31963 | Tulare CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
31964 | Tulare CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
31965 | Tulare CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
31966 | Tulare CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
31967 | Tulare CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
31968 | Tulare CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
31969 | Tulare CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
31970 | Tulare CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
31971 | Tulare CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
31972 | Tulare CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
31973 | Tulare CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
31974 | Tulare CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
31975 | Tulare CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
31976 | Tulare CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31977 | Tulare CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
31978 | Tulare CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
31979 | Tulare CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
31980 | Tulare CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
31981 | Tulare CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
31982 | Tulare CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
31983 | Tulare CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
31984 | Tulare CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
31985 | Tulare CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 13636SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
31986 | Tulare CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 13635SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
31987 | Tulare CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31988 | Tulare CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
31989 | Tulare CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
31990 | Tulare CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 13641SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
31991 | Tulare CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 13640SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
31992 | Tulare CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31993 | Tulare CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 13644SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
31994 | Tulare CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 13643SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
31995 | Tulare CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31996 | Tulare CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 13647SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31997 | Tulare CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 13646SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
31998 | Tulare CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
31999 | Tulare CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 13650SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
32000 | Tulare CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 13649SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
32001 | Tulare CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
32002 | Tulare CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.39000000000000001
32003 | Tulare CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
32004 | Tulare CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 13655 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
32005 | Tulare CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 13654 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.40000000000000002
32006 | Tulare CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
32007 | Tulare CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
32008 | Tulare CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
32009 | Tulare CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32010 | Tulare CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 13661 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
32011 | Tulare CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 13660 | 13662 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
32012 | Tulare CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 13661 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
32013 | Tulare CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32014 | Tulare CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 13665 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
32015 | Tulare CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 13664 | 13666 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32016 | Tulare CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 13665 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32017 | Tulare CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32018 | Tulare CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 13669 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
32019 | Tulare CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 13668 | 13670 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32020 | Tulare CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 13669 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32021 | Tulare CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32022 | Tulare CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 13673 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32023 | Tulare CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 13672 | 13674 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32024 | Tulare CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 13673 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32025 | Tulare CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32026 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32027 | Tulare CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.44
32028 | Tulare CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 0d | NA | NA | 0 days? | No | 3/19/24 | 5/8/26 | NA | 1
32029 | Tulare CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 13680SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
32030 | Tulare CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 13679SS | 13681 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
32031 | Tulare CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 13680 |  | As Soon As Possible | NA | 48 | 0d | NA | NA | 0 days? | No | 3/3/26 | 5/8/26 | NA | 1
32032 | Tulare CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
32033 | Tulare CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
32034 | Tulare CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
32035 | Tulare CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 13687 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
32036 | Tulare CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
32037 | Tulare CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 13685 | 13688,13690SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
32038 | Tulare CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 13687 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
32039 | Tulare CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
32040 | Tulare CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 13687SS | 13691SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
32041 | Tulare CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 13690SS | 13692,13695,13693SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32042 | Tulare CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 13691 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32043 | Tulare CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 13691SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32044 | Tulare CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32045 | Tulare CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 13691 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
32046 | Tulare CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.62
32047 | Tulare CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 13698SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
32048 | Tulare CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 13697SS | 13699SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
32049 | Tulare CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 13698SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
32050 | Tulare CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
32051 | Tulare CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
32052 | Tulare CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 13708 | 13703SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
32053 | Tulare CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 13702SS | 13705 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
32054 | Tulare CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
32055 | Tulare CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 13703 | 13706 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
32056 | Tulare CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 13705 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
32057 | Tulare CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
32058 | Tulare CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 13702,13709SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
32059 | Tulare CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 13708SS | 13713,13710 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32060 | Tulare CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 13709 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32061 | Tulare CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32062 | Tulare CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32063 | Tulare CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 13709 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
32064 | Tulare CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32065 | Tulare CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32066 | Tulare CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32067 | Tulare CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32068 | Tulare CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32069 | Tulare CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32070 | Tulare CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32071 | Tulare CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32072 | Tulare CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32073 | Tulare CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32074 | Tulare CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32075 | Tulare CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32076 | Tulare CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
32077 | Tulare CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
32078 | Tulare CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 13735 | Start No Earlier Than | 7/1/25 | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
32079 | Tulare CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
32080 | Tulare CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
32081 | Tulare CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32082 | Tulare CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32083 | Tulare CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 13742 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
32084 | Tulare CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 13743 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
32085 | Tulare CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 13728 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
32086 | Tulare CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32087 | Tulare CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13748SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32088 | Tulare CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13749SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32089 | Tulare CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13750SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32090 | Tulare CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13751SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32091 | Tulare CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13752SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32092 | Tulare CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 13733 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
32093 | Tulare CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 13734 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
32094 | Tulare CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
32095 | Tulare CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 13754FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32096 | Tulare CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
32097 | Tulare CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 13754SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
32098 | Tulare CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13737SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32099 | Tulare CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13738SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32100 | Tulare CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13739SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32101 | Tulare CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13740SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32102 | Tulare CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13741SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32103 | Tulare CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32104 | Tulare CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 13745FS+12d,13747SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32105 | CARES V1 - Yolo CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.34000000000000002
32106 | Yolo CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.51000000000000001
32107 | Yolo CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.57999999999999996
32108 | Yolo CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
32109 | Yolo CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
32110 | Yolo CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
32111 | Yolo CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
32112 | Yolo CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
32113 | Yolo CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
32114 | Yolo CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
32115 | Yolo CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
32116 | Yolo CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
32117 | Yolo CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
32118 | Yolo CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
32119 | Yolo CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
32120 | Yolo CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
32121 | Yolo CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
32122 | Yolo CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
32123 | Yolo CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
32124 | Yolo CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
32125 | Yolo CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
32126 | Yolo CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
32127 | Yolo CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
32128 | Yolo CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
32129 | Yolo CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
32130 | Yolo CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
32131 | Yolo CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
32132 | Yolo CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
32133 | Yolo CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
32134 | Yolo CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
32135 | Yolo CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
32136 | Yolo CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
32137 | Yolo CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
32138 | Yolo CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
32139 | Yolo CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
32140 | Yolo CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
32141 | Yolo CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
32142 | Yolo CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
32143 | Yolo CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
32144 | Yolo CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
32145 | Yolo CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
32146 | Yolo CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
32147 | Yolo CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
32148 | Yolo CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32149 | Yolo CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32150 | Yolo CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
32151 | Yolo CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
32152 | Yolo CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
32153 | Yolo CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
32154 | Yolo CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
32155 | Yolo CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
32156 | Yolo CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
32157 | Yolo CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
32158 | Yolo CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
32159 | Yolo CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
32160 | Yolo CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 13811SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
32161 | Yolo CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 13810SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
32162 | Yolo CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32163 | Yolo CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32164 | Yolo CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
32165 | Yolo CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 13816SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
32166 | Yolo CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 13815SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
32167 | Yolo CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
32168 | Yolo CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 13819SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
32169 | Yolo CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 13818SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
32170 | Yolo CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
32171 | Yolo CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 13822SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
32172 | Yolo CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 13821SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
32173 | Yolo CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
32174 | Yolo CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 13825SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
32175 | Yolo CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 13824SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
32176 | Yolo CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
32177 | Yolo CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.53000000000000003
32178 | Yolo CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
32179 | Yolo CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 13830 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
32180 | Yolo CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 13829 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
32181 | Yolo CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
32182 | Yolo CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
32183 | Yolo CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
32184 | Yolo CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32185 | Yolo CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 13836 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
32186 | Yolo CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 13835 | 13837 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
32187 | Yolo CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 13836 |  | As Soon As Possible | NA | 63 | 0d | NA | NA | 0 days? | No | 9/2/25 | 12/1/25 | NA | 1
32188 | Yolo CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32189 | Yolo CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 13840 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
32190 | Yolo CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 13839 | 13841 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
32191 | Yolo CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 13840 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32192 | Yolo CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32193 | Yolo CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 13844 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
32194 | Yolo CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 13843 | 13845 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32195 | Yolo CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 13844 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32196 | Yolo CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32197 | Yolo CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 13848 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32198 | Yolo CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 13847 | 13849 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32199 | Yolo CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 13848 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32200 | Yolo CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32201 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32202 | Yolo CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.41999999999999998
32203 | Yolo CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.93999999999999995
32204 | Yolo CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 13855SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
32205 | Yolo CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 13854SS | 13856 | As Soon As Possible | NA | 490 | 9.6d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
32206 | Yolo CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 13855 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.20000000000000001
32207 | Yolo CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
32208 | Yolo CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
32209 | Yolo CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
32210 | Yolo CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 13862 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
32211 | Yolo CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.68999999999999995
32212 | Yolo CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 13860 | 13863,13865SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
32213 | Yolo CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 13862 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
32214 | Yolo CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.01
32215 | Yolo CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 13862SS | 13866SS | As Soon As Possible | NA | 36 | 508d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
32216 | Yolo CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 13865SS | 13867,13870,13868SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32217 | Yolo CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 13866 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32218 | Yolo CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 13866SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32219 | Yolo CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32220 | Yolo CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 13866 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
32221 | Yolo CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.68000000000000005
32222 | Yolo CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 13873SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
32223 | Yolo CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 13872SS | 13874SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.94999999999999996
32224 | Yolo CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 13873SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
32225 | Yolo CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
32226 | Yolo CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
32227 | Yolo CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 13883 | 13878SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
32228 | Yolo CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 13877SS | 13880 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
32229 | Yolo CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
32230 | Yolo CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 13878 | 13881 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
32231 | Yolo CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 13880 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
32232 | Yolo CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 5.0000000000000003E-2
32233 | Yolo CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 13877,13884SS | Start No Earlier Than | 7/1/25 | 64 | 508d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.59999999999999998
32234 | Yolo CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 13883SS | 13888,13885 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32235 | Yolo CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 13884 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32236 | Yolo CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32237 | Yolo CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32238 | Yolo CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 13884 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
32239 | Yolo CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32240 | Yolo CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32241 | Yolo CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32242 | Yolo CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32243 | Yolo CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32244 | Yolo CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32245 | Yolo CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32246 | Yolo CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32247 | Yolo CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32248 | Yolo CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32249 | Yolo CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32250 | Yolo CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32251 | Yolo CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
32252 | Yolo CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
32253 | Yolo CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 13910 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
32254 | Yolo CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
32255 | Yolo CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
32256 | Yolo CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32257 | Yolo CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32258 | Yolo CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 13917 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
32259 | Yolo CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 13918 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
32260 | Yolo CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 13903 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
32261 | Yolo CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32262 | Yolo CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13923SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32263 | Yolo CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13924SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32264 | Yolo CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13925SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32265 | Yolo CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13926SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32266 | Yolo CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 13927SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32267 | Yolo CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 13908 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
32268 | Yolo CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 13909 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
32269 | Yolo CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
32270 | Yolo CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 13929FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32271 | Yolo CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
32272 | Yolo CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 13929SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
32273 | Yolo CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13912SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32274 | Yolo CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13913SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32275 | Yolo CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13914SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32276 | Yolo CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13915SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32277 | Yolo CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 13916SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32278 | Yolo CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32279 | Yolo CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 13920FS+12d,13922SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32280 | CARES V1 - Yuba CW | July 17, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 868 | 195d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.39000000000000001
32281 | Yuba CW-Data Quality | January 2, 2024 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 753 | 195d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.48999999999999999
32282 | Yuba CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 703 | 245d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.55000000000000004
32283 | Yuba CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
32284 | Yuba CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
32285 | Yuba CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
32286 | Yuba CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
32287 | Yuba CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32288 | Yuba CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
32289 | Yuba CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
32290 | Yuba CW-Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 12 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
32291 | Yuba CW-Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
32292 | Yuba CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
32293 | Yuba CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
32294 | Yuba CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
32295 | Yuba CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
32296 | Yuba CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
32297 | Yuba CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
32298 | Yuba CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
32299 | Yuba CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
32300 | Yuba CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
32301 | Yuba CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
32302 | Yuba CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
32303 | Yuba CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
32304 | Yuba CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
32305 | Yuba CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
32306 | Yuba CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
32307 | Yuba CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
32308 | Yuba CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
32309 | Yuba CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
32310 | Yuba CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
32311 | Yuba CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
32312 | Yuba CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
32313 | Yuba CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
32314 | Yuba CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
32315 | Yuba CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
32316 | Yuba CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
32317 | Yuba CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
32318 | Yuba CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
32319 | Yuba CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
32320 | Yuba CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
32321 | Yuba CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
32322 | Yuba CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
32323 | Yuba CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32324 | Yuba CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32325 | Yuba CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
32326 | Yuba CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
32327 | Yuba CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
32328 | Yuba CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
32329 | Yuba CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
32330 | Yuba CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
32331 | Yuba CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
32332 | Yuba CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
32333 | Yuba CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
32334 | Yuba CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
32335 | Yuba CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 13986SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
32336 | Yuba CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 13985SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
32337 | Yuba CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32338 | Yuba CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32339 | Yuba CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
32340 | Yuba CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  | 13991SS | Start No Earlier Than | 4/1/26 | 22 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
32341 | Yuba CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM | 13990SS |  | As Soon As Possible | NA | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
32342 | Yuba CW-Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
32343 | Yuba CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 13994SS | Start No Earlier Than | 7/1/26 | 22 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
32344 | Yuba CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 13993SS |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
32345 | Yuba CW-Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
32346 | Yuba CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  | 13997SS | Start No Earlier Than | 8/3/26 | 21 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
32347 | Yuba CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 13996SS |  | As Soon As Possible | NA | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
32348 | Yuba CW-Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
32349 | Yuba CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 14000SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
32350 | Yuba CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 13999SS |  | As Soon As Possible | NA | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
32351 | Yuba CW-Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
32352 | Yuba CW-Organization Change Management | March 1, 2024 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 673 | 234d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.48999999999999999
32353 | Yuba CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
32354 | Yuba CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 14005 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
32355 | Yuba CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | November 2, 2026 5:00 PM | 14004 |  | As Soon As Possible | NA | 631 | 234d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
32356 | Yuba CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
32357 | Yuba CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
32358 | Yuba CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
32359 | Yuba CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32360 | Yuba CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 14011 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
32361 | Yuba CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 14010 | 14012 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
32362 | Yuba CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 14011 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
32363 | Yuba CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32364 | Yuba CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 14015 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
32365 | Yuba CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 14014 | 14016 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.80000000000000004
32366 | Yuba CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 14015 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32367 | Yuba CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32368 | Yuba CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 14019 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
32369 | Yuba CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 14018 | 14020 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32370 | Yuba CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 14019 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32371 | Yuba CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32372 | Yuba CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 14023 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32373 | Yuba CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 14022 | 14024 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32374 | Yuba CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 14023 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32375 | Yuba CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32376 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32377 | Yuba CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.55000000000000004
32378 | Yuba CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.98999999999999999
32379 | Yuba CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 14030SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
32380 | Yuba CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 14029SS | 14031 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
32381 | Yuba CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 14030 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.80000000000000004
32382 | Yuba CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
32383 | Yuba CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
32384 | Yuba CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
32385 | Yuba CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 14037 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
32386 | Yuba CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
32387 | Yuba CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 14035 | 14038,14040SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
32388 | Yuba CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 14037 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
32389 | Yuba CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
32390 | Yuba CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 14037SS | 14041SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
32391 | Yuba CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 14040SS | 14042,14045,14043SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
32392 | Yuba CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 14041 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32393 | Yuba CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 14041SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32394 | Yuba CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32395 | Yuba CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 14041 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
32396 | Yuba CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.92000000000000004
32397 | Yuba CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 14048SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
32398 | Yuba CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 14047SS | 14049SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
32399 | Yuba CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 14048SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.80000000000000004
32400 | Yuba CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
32401 | Yuba CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
32402 | Yuba CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 14058 | 14053SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
32403 | Yuba CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 14052SS | 14055 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
32404 | Yuba CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
32405 | Yuba CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 14053 | 14056 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
32406 | Yuba CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 14055 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
32407 | Yuba CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
32408 | Yuba CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 14052,14059SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
32409 | Yuba CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 14058SS | 14063,14060 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
32410 | Yuba CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 14059 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32411 | Yuba CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
32412 | Yuba CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32413 | Yuba CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 14059 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
32414 | Yuba CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 363d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
32415 | Yuba CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
32416 | Yuba CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
32417 | Yuba CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
32418 | Yuba CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
32419 | Yuba CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
32420 | Yuba CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
32421 | Yuba CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
32422 | Yuba CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
32423 | Yuba CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
32424 | Yuba CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
32425 | Yuba CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | 1/2/26 | NA | NA | 0.20000000000000001
32426 | Yuba CW-Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
32427 | Yuba CW-Training | July 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 377 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
32428 | Yuba CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 14085 | As Soon As Possible | NA | 188 | 195d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
32429 | Yuba CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
32430 | Yuba CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
32431 | Yuba CW-Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32432 | Yuba CW-Receive Project-developed User Guides for FFPSA portal for providers | June 2, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/2/26 | 21 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32433 | Yuba CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 14092 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
32434 | Yuba CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 14093 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
32435 | Yuba CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 14078 |  | As Soon As Possible | NA | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
32436 | Yuba CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32437 | Yuba CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 14098SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32438 | Yuba CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 14099SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32439 | Yuba CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 14100SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32440 | Yuba CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 14101SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32441 | Yuba CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 14102SF+30d |  | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32442 | Yuba CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 14083 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
32443 | Yuba CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 14084 |  | As Soon As Possible | NA | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
32444 | Yuba CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
32445 | Yuba CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 14104FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32446 | Yuba CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
32447 | Yuba CW-Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 14104SF+60d | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
32448 | Yuba CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 14087SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32449 | Yuba CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 14088SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32450 | Yuba CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 14089SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32451 | Yuba CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 14090SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32452 | Yuba CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 14091SF+30d | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32453 | Yuba CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32454 | Yuba CW-Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 14095FS+12d,14097SF+60d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
32455 | CARES V1 - Butte CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.35999999999999999
32456 | Butte CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.5
32457 | Butte CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 669 | 279d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.57999999999999996
32458 | Butte CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
32459 | Butte CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
32460 | Butte CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
32461 | Butte CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
32462 | Butte CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32463 | Butte CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
32464 | Butte CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Finish No Earlier Than | 8/28/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
32465 | Butte CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/30/26 | 43 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
32466 | Butte CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
32467 | Butte CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
32468 | Butte CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
32469 | Butte CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
32470 | Butte CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
32471 | Butte CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
32472 | Butte CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
32473 | Butte CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
32474 | Butte CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
32475 | Butte CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
32476 | Butte CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
32477 | Butte CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
32478 | Butte CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
32479 | Butte CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
32480 | Butte CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
32481 | Butte CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
32482 | Butte CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
32483 | Butte CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
32484 | Butte CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
32485 | Butte CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
32486 | Butte CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
32487 | Butte CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
32488 | Butte CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
32489 | Butte CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
32490 | Butte CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
32491 | Butte CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
32492 | Butte CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
32493 | Butte CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
32494 | Butte CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
32495 | Butte CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
32496 | Butte CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
32497 | Butte CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32498 | Butte CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32499 | Butte CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
32500 | Butte CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
32501 | Butte CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
32502 | Butte CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
32503 | Butte CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
32504 | Butte CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
32505 | Butte CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
32506 | Butte CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
32507 | Butte CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
32508 | Butte CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
32509 | Butte CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 14160SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
32510 | Butte CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 14159SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
32511 | Butte CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32512 | Butte CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32513 | Butte CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
32514 | Butte CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  | 14165SS | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
32515 | Butte CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 14164SS |  | Start No Earlier Than | 3/2/26 | 35 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
32516 | Butte CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
32517 | Butte CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 14168SS | Finish No Earlier Than | 5/29/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
32518 | Butte CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 14167SS |  | Finish No Earlier Than | 6/15/26 | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
32519 | Butte CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
32520 | Butte CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 14171SS | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32521 | Butte CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 14170SS |  | Finish No Earlier Than | 7/15/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
32522 | Butte CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
32523 | Butte CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 14174SS | Finish No Earlier Than | 7/31/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32524 | Butte CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 14173SS |  | Start No Earlier Than | 7/1/26 | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
32525 | Butte CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
32526 | Butte CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 630 | 277d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.34999999999999998
32527 | Butte CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
32528 | Butte CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 14179 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
32529 | Butte CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 14178 |  | Finish No Earlier Than | 8/31/26 | 588 | 277d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
32530 | Butte CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
32531 | Butte CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
32532 | Butte CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
32533 | Butte CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32534 | Butte CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 14185 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
32535 | Butte CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 14184 | 14186 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
32536 | Butte CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 14185 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
32537 | Butte CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32538 | Butte CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals (if | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 14189 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
32539 | Butte CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 14188 | 14190 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
32540 | Butte CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 14189 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32541 | Butte CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32542 | Butte CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 14193 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
32543 | Butte CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 14192 | 14194 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32544 | Butte CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 14193 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32545 | Butte CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32546 | Butte CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 14197 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32547 | Butte CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 14196 | 14198 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32548 | Butte CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 14197 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32549 | Butte CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32550 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32551 | Butte CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.46000000000000002
32552 | Butte CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
32553 | Butte CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 14204SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
32554 | Butte CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 14203SS | 14205 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
32555 | Butte CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 14204 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32556 | Butte CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
32557 | Butte CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
32558 | Butte CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
32559 | Butte CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 14211 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
32560 | Butte CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.60999999999999999
32561 | Butte CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 14209 | 14212,14214SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
32562 | Butte CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 14211 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
32563 | Butte CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
32564 | Butte CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 14211SS | 14215SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
32565 | Butte CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 14214SS | 14216,14219,14217SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
32566 | Butte CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 14215 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32567 | Butte CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 14215SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32568 | Butte CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32569 | Butte CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 14215 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
32570 | Butte CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.69999999999999996
32571 | Butte CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 14222SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
32572 | Butte CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 14221SS | 14223SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
32573 | Butte CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 14222SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
32574 | Butte CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
32575 | Butte CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
32576 | Butte CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 14232 | 14227SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
32577 | Butte CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 14226SS | 14229 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
32578 | Butte CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
32579 | Butte CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 14227 | 14230 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
32580 | Butte CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 14229 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
32581 | Butte CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
32582 | Butte CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 14226,14233SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
32583 | Butte CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 14232SS | 14237,14234 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
32584 | Butte CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 14233 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32585 | Butte CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
32586 | Butte CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32587 | Butte CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 14233 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
32588 | Butte CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32589 | Butte CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32590 | Butte CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32591 | Butte CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32592 | Butte CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32593 | Butte CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32594 | Butte CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32595 | Butte CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32596 | Butte CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32597 | Butte CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32598 | Butte CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32599 | Butte CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32600 | Butte CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32601 | Butte CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 316 | 256d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
32602 | Butte CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 14259 | Start No Earlier Than | 7/1/25 | 188 | 256d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
32603 | Butte CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
32604 | Butte CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
32605 | Butte CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32606 | Butte CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32607 | Butte CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 14266 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
32608 | Butte CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 14267 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
32609 | Butte CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 14252 |  | As Soon As Possible | NA | 128 | 256d | NA | NA | 0 days? | No | NA | NA | NA | 0
32610 | Butte CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32611 | Butte CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14272SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32612 | Butte CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14273SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32613 | Butte CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14274SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32614 | Butte CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14275SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32615 | Butte CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14276SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32616 | Butte CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 14257 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
32617 | Butte CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 14258 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
32618 | Butte CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
32619 | Butte CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 14278FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
32620 | Butte CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32621 | Butte CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 14278SF+60d | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32622 | Butte CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14261SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32623 | Butte CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14262SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32624 | Butte CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14263SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32625 | Butte CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14264SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32626 | Butte CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14265SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32627 | Butte CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32628 | Butte CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 14269FS+12d,14271SF+60d |  | Finish No Earlier Than | 8/28/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
32629 | CARES V1 - Fresno CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.39000000000000001
32630 | Fresno CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.5
32631 | Fresno CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 669 | 279d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.57999999999999996
32632 | Fresno CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
32633 | Fresno CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
32634 | Fresno CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
32635 | Fresno CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
32636 | Fresno CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32637 | Fresno CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
32638 | Fresno CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Finish No Earlier Than | 8/28/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
32639 | Fresno CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/30/26 | 43 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
32640 | Fresno CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
32641 | Fresno CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
32642 | Fresno CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
32643 | Fresno CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
32644 | Fresno CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
32645 | Fresno CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
32646 | Fresno CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
32647 | Fresno CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
32648 | Fresno CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
32649 | Fresno CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
32650 | Fresno CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
32651 | Fresno CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
32652 | Fresno CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
32653 | Fresno CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
32654 | Fresno CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
32655 | Fresno CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
32656 | Fresno CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
32657 | Fresno CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
32658 | Fresno CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
32659 | Fresno CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
32660 | Fresno CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
32661 | Fresno CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
32662 | Fresno CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
32663 | Fresno CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
32664 | Fresno CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
32665 | Fresno CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
32666 | Fresno CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
32667 | Fresno CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
32668 | Fresno CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
32669 | Fresno CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
32670 | Fresno CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
32671 | Fresno CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32672 | Fresno CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32673 | Fresno CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
32674 | Fresno CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
32675 | Fresno CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
32676 | Fresno CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
32677 | Fresno CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
32678 | Fresno CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
32679 | Fresno CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
32680 | Fresno CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
32681 | Fresno CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
32682 | Fresno CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
32683 | Fresno CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 14334SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
32684 | Fresno CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 14333SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
32685 | Fresno CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32686 | Fresno CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32687 | Fresno CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
32688 | Fresno CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  | 14339SS | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
32689 | Fresno CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 14338SS |  | Start No Earlier Than | 3/2/26 | 35 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
32690 | Fresno CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
32691 | Fresno CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 14342SS | Finish No Earlier Than | 5/29/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
32692 | Fresno CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 14341SS |  | Finish No Earlier Than | 6/15/26 | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
32693 | Fresno CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
32694 | Fresno CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 14345SS | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32695 | Fresno CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 14344SS |  | Finish No Earlier Than | 7/15/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
32696 | Fresno CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
32697 | Fresno CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 14348SS | Finish No Earlier Than | 7/31/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32698 | Fresno CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 14347SS |  | Start No Earlier Than | 7/1/26 | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
32699 | Fresno CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
32700 | Fresno CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 630 | 277d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.47999999999999998
32701 | Fresno CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
32702 | Fresno CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 14353 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
32703 | Fresno CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 14352 |  | Finish No Earlier Than | 8/31/26 | 588 | 277d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
32704 | Fresno CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
32705 | Fresno CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
32706 | Fresno CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
32707 | Fresno CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32708 | Fresno CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OC | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 14359 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
32709 | Fresno CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 14358 | 14360 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
32710 | Fresno CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 14359 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
32711 | Fresno CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32712 | Fresno CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 14363 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
32713 | Fresno CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 14362 | 14364 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
32714 | Fresno CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 14363 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32715 | Fresno CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32716 | Fresno CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 14367 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
32717 | Fresno CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 14366 | 14368 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32718 | Fresno CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 14367 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32719 | Fresno CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32720 | Fresno CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 14371 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32721 | Fresno CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 14370 | 14372 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32722 | Fresno CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 14371 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32723 | Fresno CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32724 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32725 | Fresno CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.48999999999999999
32726 | Fresno CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 0d | NA | NA | 0 days? | No | 3/19/24 | 5/8/26 | NA | 1
32727 | Fresno CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 14378SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
32728 | Fresno CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 14377SS | 14379 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
32729 | Fresno CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 14378 |  | As Soon As Possible | NA | 48 | 0d | NA | NA | 0 days? | No | 3/3/26 | 5/8/26 | NA | 1
32730 | Fresno CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
32731 | Fresno CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
32732 | Fresno CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
32733 | Fresno CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 14385 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
32734 | Fresno CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
32735 | Fresno CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 14383 | 14386,14388SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
32736 | Fresno CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 14385 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
32737 | Fresno CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
32738 | Fresno CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 14385SS | 14389SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
32739 | Fresno CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 14388SS | 14390,14393,14391SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32740 | Fresno CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 14389 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32741 | Fresno CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 14389SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32742 | Fresno CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32743 | Fresno CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 14389 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
32744 | Fresno CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 0d | NA | NA | 0 days? | No | 2/3/25 | 12/31/25 | NA | 1
32745 | Fresno CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 14396SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
32746 | Fresno CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 14395SS | 14397SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
32747 | Fresno CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 14396SS |  | As Soon As Possible | NA | 230 | 0d | NA | NA | 0 days? | No | 2/3/25 | 12/31/25 | NA | 1
32748 | Fresno CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
32749 | Fresno CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
32750 | Fresno CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 14406 | 14401SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
32751 | Fresno CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 14400SS | 14403 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
32752 | Fresno CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
32753 | Fresno CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 14401 | 14404 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
32754 | Fresno CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 14403 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
32755 | Fresno CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
32756 | Fresno CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 14400,14407SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
32757 | Fresno CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 14406SS | 14411,14408 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32758 | Fresno CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 14407 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32759 | Fresno CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32760 | Fresno CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32761 | Fresno CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 14407 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
32762 | Fresno CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32763 | Fresno CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32764 | Fresno CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32765 | Fresno CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32766 | Fresno CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32767 | Fresno CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32768 | Fresno CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32769 | Fresno CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32770 | Fresno CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32771 | Fresno CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32772 | Fresno CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32773 | Fresno CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32774 | Fresno CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32775 | Fresno CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 316 | 256d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
32776 | Fresno CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 14433 | As Soon As Possible | NA | 188 | 256d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
32777 | Fresno CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
32778 | Fresno CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
32779 | Fresno CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32780 | Fresno CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32781 | Fresno CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 14440 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
32782 | Fresno CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 14441 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
32783 | Fresno CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 14426 |  | As Soon As Possible | NA | 128 | 256d | NA | NA | 0 days? | No | NA | NA | NA | 0
32784 | Fresno CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32785 | Fresno CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14446SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32786 | Fresno CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14447SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32787 | Fresno CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14448SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32788 | Fresno CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14449SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32789 | Fresno CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14450SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32790 | Fresno CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 14431 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
32791 | Fresno CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 14432 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
32792 | Fresno CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
32793 | Fresno CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 14452FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
32794 | Fresno CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32795 | Fresno CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 14452SF+60d | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32796 | Fresno CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14435SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32797 | Fresno CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14436SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32798 | Fresno CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14437SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32799 | Fresno CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14438SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32800 | Fresno CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14439SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32801 | Fresno CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32802 | Fresno CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 14443FS+12d,14445SF+60d |  | Finish No Earlier Than | 8/28/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
32803 | CARES V1 - San Diego CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.33000000000000002
32804 | San Diego CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.5
32805 | San Diego CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 669 | 279d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.57999999999999996
32806 | San Diego CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
32807 | San Diego CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
32808 | San Diego CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
32809 | San Diego CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
32810 | San Diego CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32811 | San Diego CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
32812 | San Diego CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Finish No Earlier Than | 8/28/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
32813 | San Diego CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/30/26 | 43 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
32814 | San Diego CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.40000000000000002
32815 | San Diego CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.65000000000000002
32816 | San Diego CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
32817 | San Diego CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
32818 | San Diego CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
32819 | San Diego CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
32820 | San Diego CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
32821 | San Diego CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
32822 | San Diego CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
32823 | San Diego CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
32824 | San Diego CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
32825 | San Diego CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
32826 | San Diego CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
32827 | San Diego CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
32828 | San Diego CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
32829 | San Diego CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
32830 | San Diego CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
32831 | San Diego CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
32832 | San Diego CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
32833 | San Diego CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
32834 | San Diego CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
32835 | San Diego CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
32836 | San Diego CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
32837 | San Diego CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/30/25 | NA | 1
32838 | San Diego CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
32839 | San Diego CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
32840 | San Diego CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
32841 | San Diego CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
32842 | San Diego CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
32843 | San Diego CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
32844 | San Diego CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
32845 | San Diego CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32846 | San Diego CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32847 | San Diego CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
32848 | San Diego CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
32849 | San Diego CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
32850 | San Diego CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
32851 | San Diego CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
32852 | San Diego CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
32853 | San Diego CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
32854 | San Diego CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
32855 | San Diego CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
32856 | San Diego CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
32857 | San Diego CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 14508SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
32858 | San Diego CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 14507SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
32859 | San Diego CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32860 | San Diego CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32861 | San Diego CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
32862 | San Diego CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  | 14513SS | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
32863 | San Diego CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 14512SS |  | Start No Earlier Than | 3/2/26 | 35 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
32864 | San Diego CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
32865 | San Diego CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 14516SS | Finish No Earlier Than | 5/29/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
32866 | San Diego CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 14515SS |  | Finish No Earlier Than | 6/15/26 | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
32867 | San Diego CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
32868 | San Diego CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 14519SS | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32869 | San Diego CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 14518SS |  | Finish No Earlier Than | 7/15/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
32870 | San Diego CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
32871 | San Diego CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 14522SS | Finish No Earlier Than | 7/31/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32872 | San Diego CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 14521SS |  | Start No Earlier Than | 7/1/26 | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
32873 | San Diego CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
32874 | San Diego CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 630 | 277d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.33000000000000002
32875 | San Diego CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
32876 | San Diego CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 14527 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
32877 | San Diego CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 14526 |  | Finish No Earlier Than | 8/31/26 | 588 | 277d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
32878 | San Diego CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
32879 | San Diego CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
32880 | San Diego CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
32881 | San Diego CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32882 | San Diego CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OC | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 14533 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
32883 | San Diego CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 14532 | 14534 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
32884 | San Diego CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 14533 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
32885 | San Diego CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32886 | San Diego CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 14537 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
32887 | San Diego CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 14536 | 14538 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
32888 | San Diego CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 14537 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32889 | San Diego CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32890 | San Diego CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 14541 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.59999999999999998
32891 | San Diego CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 14540 | 14542 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32892 | San Diego CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 14541 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32893 | San Diego CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32894 | San Diego CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 14545 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32895 | San Diego CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 14544 | 14546 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32896 | San Diego CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 14545 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32897 | San Diego CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32898 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
32899 | San Diego CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.40999999999999998
32900 | San Diego CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
32901 | San Diego CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 14552SS | Start No Earlier Than | 3/19/24 | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
32902 | San Diego CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 14551SS | 14553 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
32903 | San Diego CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 14552 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32904 | San Diego CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
32905 | San Diego CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
32906 | San Diego CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
32907 | San Diego CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 14559 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
32908 | San Diego CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
32909 | San Diego CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 14557 | 14560,14562SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
32910 | San Diego CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 14559 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
32911 | San Diego CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.01
32912 | San Diego CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 14559SS | 14563SS | As Soon As Possible | NA | 36 | 508d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
32913 | San Diego CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 14562SS | 14564,14567,14565SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32914 | San Diego CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 14563 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32915 | San Diego CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 14563SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32916 | San Diego CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32917 | San Diego CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 14563 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
32918 | San Diego CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.62
32919 | San Diego CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 14570SS | Start No Earlier Than | 2/3/25 | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
32920 | San Diego CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 14569SS | 14571SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
32921 | San Diego CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 14570SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
32922 | San Diego CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
32923 | San Diego CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
32924 | San Diego CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 14580 | 14575SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
32925 | San Diego CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 14574SS | 14577 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
32926 | San Diego CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
32927 | San Diego CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 14575 | 14578 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
32928 | San Diego CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 14577 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
32929 | San Diego CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
32930 | San Diego CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 14574,14581SS | Start No Earlier Than | 7/1/25 | 64 | 508d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
32931 | San Diego CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 14580SS | 14585,14582 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32932 | San Diego CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 14581 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32933 | San Diego CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
32934 | San Diego CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32935 | San Diego CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 14581 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
32936 | San Diego CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32937 | San Diego CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32938 | San Diego CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32939 | San Diego CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32940 | San Diego CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32941 | San Diego CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32942 | San Diego CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32943 | San Diego CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32944 | San Diego CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32945 | San Diego CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32946 | San Diego CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32947 | San Diego CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
32948 | San Diego CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32949 | San Diego CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 316 | 256d | NA | NA | 0 days? | No | NA | NA | NA | 0
32950 | San Diego CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 14607 | Start No Earlier Than | 7/1/25 | 188 | 256d | NA | NA | 0 days? | No | NA | NA | NA | 0
32951 | San Diego CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
32952 | San Diego CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
32953 | San Diego CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32954 | San Diego CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32955 | San Diego CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 14614 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
32956 | San Diego CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 14615 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
32957 | San Diego CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 14600 |  | As Soon As Possible | NA | 128 | 256d | NA | NA | 0 days? | No | NA | NA | NA | 0
32958 | San Diego CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
32959 | San Diego CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14620SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32960 | San Diego CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14621SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32961 | San Diego CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14622SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32962 | San Diego CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14623SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32963 | San Diego CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14624SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
32964 | San Diego CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 14605 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
32965 | San Diego CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 14606 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
32966 | San Diego CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
32967 | San Diego CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 14626FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
32968 | San Diego CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
32969 | San Diego CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 14626SF+60d | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32970 | San Diego CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14609SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32971 | San Diego CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14610SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32972 | San Diego CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14611SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32973 | San Diego CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14612SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32974 | San Diego CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14613SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32975 | San Diego CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
32976 | San Diego CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 14617FS+12d,14619SF+60d |  | Finish No Earlier Than | 8/28/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
32977 | CARES V1 - San Mateo CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.37
32978 | San Mateo CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.5
32979 | San Mateo CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 669 | 279d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.57999999999999996
32980 | San Mateo CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
32981 | San Mateo CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
32982 | San Mateo CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
32983 | San Mateo CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
32984 | San Mateo CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
32985 | San Mateo CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
32986 | San Mateo CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Finish No Earlier Than | 8/28/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
32987 | San Mateo CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/30/26 | 43 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
32988 | San Mateo CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
32989 | San Mateo CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
32990 | San Mateo CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
32991 | San Mateo CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
32992 | San Mateo CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
32993 | San Mateo CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
32994 | San Mateo CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
32995 | San Mateo CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
32996 | San Mateo CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
32997 | San Mateo CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
32998 | San Mateo CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
32999 | San Mateo CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
33000 | San Mateo CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
33001 | San Mateo CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
33002 | San Mateo CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
33003 | San Mateo CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
33004 | San Mateo CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
33005 | San Mateo CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
33006 | San Mateo CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
33007 | San Mateo CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
33008 | San Mateo CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
33009 | San Mateo CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
33010 | San Mateo CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
33011 | San Mateo CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
33012 | San Mateo CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
33013 | San Mateo CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
33014 | San Mateo CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
33015 | San Mateo CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
33016 | San Mateo CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
33017 | San Mateo CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
33018 | San Mateo CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33019 | San Mateo CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33020 | San Mateo CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33021 | San Mateo CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
33022 | San Mateo CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
33023 | San Mateo CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
33024 | San Mateo CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
33025 | San Mateo CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
33026 | San Mateo CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
33027 | San Mateo CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
33028 | San Mateo CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
33029 | San Mateo CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
33030 | San Mateo CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
33031 | San Mateo CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 14682SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
33032 | San Mateo CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 14681SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
33033 | San Mateo CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33034 | San Mateo CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33035 | San Mateo CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
33036 | San Mateo CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  | 14687SS | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
33037 | San Mateo CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 14686SS |  | Start No Earlier Than | 3/2/26 | 35 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
33038 | San Mateo CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
33039 | San Mateo CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 14690SS | Finish No Earlier Than | 5/29/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33040 | San Mateo CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 14689SS |  | Finish No Earlier Than | 6/15/26 | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
33041 | San Mateo CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
33042 | San Mateo CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 14693SS | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33043 | San Mateo CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 14692SS |  | Finish No Earlier Than | 7/15/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
33044 | San Mateo CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
33045 | San Mateo CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 14696SS | Finish No Earlier Than | 7/31/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33046 | San Mateo CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 14695SS |  | Start No Earlier Than | 7/1/26 | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
33047 | San Mateo CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
33048 | San Mateo CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 630 | 277d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.53000000000000003
33049 | San Mateo CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
33050 | San Mateo CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 14701 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
33051 | San Mateo CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 14700 |  | Finish No Earlier Than | 8/31/26 | 588 | 277d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.59999999999999998
33052 | San Mateo CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
33053 | San Mateo CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
33054 | San Mateo CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
33055 | San Mateo CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33056 | San Mateo CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OC | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 14707 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
33057 | San Mateo CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 14706 | 14708 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
33058 | San Mateo CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 14707 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
33059 | San Mateo CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33060 | San Mateo CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 14711 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
33061 | San Mateo CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 14710 | 14712 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
33062 | San Mateo CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 14711 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33063 | San Mateo CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33064 | San Mateo CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 14715 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
33065 | San Mateo CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 14714 | 14716 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33066 | San Mateo CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 14715 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33067 | San Mateo CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33068 | San Mateo CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 14719 | Start No Earlier Than | 11/3/25 | 40 | 0d | NA | NA | 0 days? | No | 11/3/25 | 12/31/25 | NA | 1
33069 | San Mateo CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 14718 | 14720 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33070 | San Mateo CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 14719 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33071 | San Mateo CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33072 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
33073 | San Mateo CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.42999999999999999
33074 | San Mateo CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.79000000000000004
33075 | San Mateo CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 14726SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
33076 | San Mateo CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 14725SS | 14727 | As Soon As Possible | NA | 490 | 28.8d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.59999999999999998
33077 | San Mateo CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 14726 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.59999999999999998
33078 | San Mateo CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
33079 | San Mateo CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
33080 | San Mateo CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
33081 | San Mateo CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 14733 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
33082 | San Mateo CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.77000000000000002
33083 | San Mateo CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 14731 | 14734,14736SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
33084 | San Mateo CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 14733 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.40000000000000002
33085 | San Mateo CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
33086 | San Mateo CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 14733SS | 14737SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
33087 | San Mateo CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 14736SS | 14738,14741,14739SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
33088 | San Mateo CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 14737 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33089 | San Mateo CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 14737SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33090 | San Mateo CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33091 | San Mateo CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 14737 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
33092 | San Mateo CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.69999999999999996
33093 | San Mateo CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 14744SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
33094 | San Mateo CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 14743SS | 14745SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
33095 | San Mateo CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 14744SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
33096 | San Mateo CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
33097 | San Mateo CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
33098 | San Mateo CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 14754 | 14749SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
33099 | San Mateo CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 14748SS | 14751 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
33100 | San Mateo CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
33101 | San Mateo CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 14749 | 14752 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
33102 | San Mateo CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 14751 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
33103 | San Mateo CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
33104 | San Mateo CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 14748,14755SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
33105 | San Mateo CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 14754SS | 14759,14756 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
33106 | San Mateo CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 14755 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33107 | San Mateo CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
33108 | San Mateo CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33109 | San Mateo CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 14755 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
33110 | San Mateo CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33111 | San Mateo CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33112 | San Mateo CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33113 | San Mateo CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33114 | San Mateo CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33115 | San Mateo CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33116 | San Mateo CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33117 | San Mateo CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33118 | San Mateo CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33119 | San Mateo CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33120 | San Mateo CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33121 | San Mateo CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33122 | San Mateo CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33123 | San Mateo CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 316 | 256d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 5.0000000000000003E-2
33124 | San Mateo CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 14781 | As Soon As Possible | NA | 188 | 256d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.40000000000000002
33125 | San Mateo CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
33126 | San Mateo CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
33127 | San Mateo CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33128 | San Mateo CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33129 | San Mateo CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 14788 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33130 | San Mateo CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 14789 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33131 | San Mateo CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 14774 |  | As Soon As Possible | NA | 128 | 256d | NA | NA | 0 days? | No | NA | NA | NA | 0
33132 | San Mateo CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33133 | San Mateo CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14794SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33134 | San Mateo CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14795SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33135 | San Mateo CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14796SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33136 | San Mateo CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14797SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33137 | San Mateo CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14798SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33138 | San Mateo CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 14779 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33139 | San Mateo CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 14780 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33140 | San Mateo CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33141 | San Mateo CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 14800FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
33142 | San Mateo CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33143 | San Mateo CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 14800SF+60d | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33144 | San Mateo CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14783SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33145 | San Mateo CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14784SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33146 | San Mateo CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14785SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33147 | San Mateo CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14786SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33148 | San Mateo CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14787SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33149 | San Mateo CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33150 | San Mateo CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 14791FS+12d,14793SF+60d |  | Finish No Earlier Than | 8/28/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
33151 | CARES V1 - Tuolumne CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.29999999999999999
33152 | Tuolumne CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.5
33153 | Tuolumne CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 669 | 279d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.57999999999999996
33154 | Tuolumne CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
33155 | Tuolumne CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
33156 | Tuolumne CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
33157 | Tuolumne CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
33158 | Tuolumne CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33159 | Tuolumne CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
33160 | Tuolumne CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Finish No Earlier Than | 8/28/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
33161 | Tuolumne CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/30/26 | 43 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
33162 | Tuolumne CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.39000000000000001
33163 | Tuolumne CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.65000000000000002
33164 | Tuolumne CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
33165 | Tuolumne CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
33166 | Tuolumne CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
33167 | Tuolumne CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
33168 | Tuolumne CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
33169 | Tuolumne CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
33170 | Tuolumne CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
33171 | Tuolumne CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
33172 | Tuolumne CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
33173 | Tuolumne CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
33174 | Tuolumne CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
33175 | Tuolumne CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
33176 | Tuolumne CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
33177 | Tuolumne CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
33178 | Tuolumne CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
33179 | Tuolumne CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
33180 | Tuolumne CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
33181 | Tuolumne CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
33182 | Tuolumne CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
33183 | Tuolumne CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
33184 | Tuolumne CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
33185 | Tuolumne CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/30/25 | NA | 1
33186 | Tuolumne CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
33187 | Tuolumne CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
33188 | Tuolumne CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
33189 | Tuolumne CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
33190 | Tuolumne CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
33191 | Tuolumne CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
33192 | Tuolumne CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33193 | Tuolumne CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33194 | Tuolumne CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33195 | Tuolumne CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
33196 | Tuolumne CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
33197 | Tuolumne CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
33198 | Tuolumne CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
33199 | Tuolumne CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
33200 | Tuolumne CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
33201 | Tuolumne CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
33202 | Tuolumne CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
33203 | Tuolumne CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
33204 | Tuolumne CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
33205 | Tuolumne CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 14856SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
33206 | Tuolumne CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 14855SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
33207 | Tuolumne CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33208 | Tuolumne CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33209 | Tuolumne CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
33210 | Tuolumne CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  | 14861SS | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
33211 | Tuolumne CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 14860SS |  | Start No Earlier Than | 3/2/26 | 35 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
33212 | Tuolumne CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
33213 | Tuolumne CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 14864SS | Finish No Earlier Than | 5/29/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33214 | Tuolumne CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 14863SS |  | Finish No Earlier Than | 6/15/26 | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
33215 | Tuolumne CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
33216 | Tuolumne CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 14867SS | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33217 | Tuolumne CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 14866SS |  | Finish No Earlier Than | 7/15/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
33218 | Tuolumne CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
33219 | Tuolumne CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 14870SS | Finish No Earlier Than | 7/31/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33220 | Tuolumne CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 14869SS |  | Start No Earlier Than | 7/1/26 | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
33221 | Tuolumne CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
33222 | Tuolumne CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 630 | 277d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.33000000000000002
33223 | Tuolumne CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
33224 | Tuolumne CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 14875 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
33225 | Tuolumne CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 14874 |  | Finish No Earlier Than | 8/31/26 | 588 | 277d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
33226 | Tuolumne CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
33227 | Tuolumne CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
33228 | Tuolumne CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
33229 | Tuolumne CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33230 | Tuolumne CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OC | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 14881 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
33231 | Tuolumne CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 14880 | 14882 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
33232 | Tuolumne CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 14881 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
33233 | Tuolumne CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33234 | Tuolumne CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 14885 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
33235 | Tuolumne CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 14884 | 14886 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
33236 | Tuolumne CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 14885 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33237 | Tuolumne CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33238 | Tuolumne CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 14889 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.59999999999999998
33239 | Tuolumne CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 14888 | 14890 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33240 | Tuolumne CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 14889 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33241 | Tuolumne CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33242 | Tuolumne CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 14893 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33243 | Tuolumne CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 14892 | 14894 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33244 | Tuolumne CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 14893 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33245 | Tuolumne CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33246 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
33247 | Tuolumne CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.34000000000000002
33248 | Tuolumne CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.76000000000000001
33249 | Tuolumne CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 14900SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
33250 | Tuolumne CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 14899SS | 14901 | As Soon As Possible | NA | 490 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.59999999999999998
33251 | Tuolumne CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 14900 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33252 | Tuolumne CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
33253 | Tuolumne CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
33254 | Tuolumne CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
33255 | Tuolumne CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 14907 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
33256 | Tuolumne CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
33257 | Tuolumne CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 14905 | 14908,14910SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
33258 | Tuolumne CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 14907 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
33259 | Tuolumne CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
33260 | Tuolumne CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 14907SS | 14911SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
33261 | Tuolumne CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 14910SS | 14912,14915,14913SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33262 | Tuolumne CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 14911 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33263 | Tuolumne CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 14911SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33264 | Tuolumne CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33265 | Tuolumne CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 14911 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
33266 | Tuolumne CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.31
33267 | Tuolumne CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 14918SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
33268 | Tuolumne CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 14917SS | 14919SS | As Soon As Possible | NA | 190 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
33269 | Tuolumne CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 14918SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
33270 | Tuolumne CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
33271 | Tuolumne CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
33272 | Tuolumne CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 14928 | 14923SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
33273 | Tuolumne CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 14922SS | 14925 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
33274 | Tuolumne CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
33275 | Tuolumne CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 14923 | 14926 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
33276 | Tuolumne CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 14925 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
33277 | Tuolumne CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
33278 | Tuolumne CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 14922,14929SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
33279 | Tuolumne CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 14928SS | 14933,14930 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33280 | Tuolumne CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 14929 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33281 | Tuolumne CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33282 | Tuolumne CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33283 | Tuolumne CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 14929 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
33284 | Tuolumne CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33285 | Tuolumne CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33286 | Tuolumne CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33287 | Tuolumne CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33288 | Tuolumne CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33289 | Tuolumne CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33290 | Tuolumne CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33291 | Tuolumne CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33292 | Tuolumne CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33293 | Tuolumne CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33294 | Tuolumne CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33295 | Tuolumne CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33296 | Tuolumne CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33297 | Tuolumne CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 316 | 256d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
33298 | Tuolumne CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 14955 | Start No Earlier Than | 7/1/25 | 188 | 256d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
33299 | Tuolumne CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
33300 | Tuolumne CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
33301 | Tuolumne CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33302 | Tuolumne CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33303 | Tuolumne CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 14962 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33304 | Tuolumne CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 14963 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33305 | Tuolumne CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 14948 |  | As Soon As Possible | NA | 128 | 256d | NA | NA | 0 days? | No | NA | NA | NA | 0
33306 | Tuolumne CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33307 | Tuolumne CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14968SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33308 | Tuolumne CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14969SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33309 | Tuolumne CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14970SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33310 | Tuolumne CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14971SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33311 | Tuolumne CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 14972SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33312 | Tuolumne CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 14953 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33313 | Tuolumne CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 14954 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33314 | Tuolumne CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33315 | Tuolumne CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 14974FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
33316 | Tuolumne CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33317 | Tuolumne CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 14974SF+60d | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33318 | Tuolumne CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14957SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33319 | Tuolumne CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14958SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33320 | Tuolumne CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14959SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33321 | Tuolumne CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14960SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33322 | Tuolumne CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 14961SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33323 | Tuolumne CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33324 | Tuolumne CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 14965FS+12d,14967SF+60d |  | Finish No Earlier Than | 8/28/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
33325 | CARES V1 - Calaveras CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.32000000000000001
33326 | Calaveras CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.5
33327 | Calaveras CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 669 | 279d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.57999999999999996
33328 | Calaveras CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
33329 | Calaveras CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
33330 | Calaveras CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
33331 | Calaveras CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
33332 | Calaveras CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33333 | Calaveras CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
33334 | Calaveras CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Finish No Earlier Than | 8/28/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
33335 | Calaveras CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/30/26 | 43 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
33336 | Calaveras CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
33337 | Calaveras CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
33338 | Calaveras CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
33339 | Calaveras CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
33340 | Calaveras CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
33341 | Calaveras CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
33342 | Calaveras CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
33343 | Calaveras CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
33344 | Calaveras CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
33345 | Calaveras CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
33346 | Calaveras CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
33347 | Calaveras CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
33348 | Calaveras CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
33349 | Calaveras CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
33350 | Calaveras CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
33351 | Calaveras CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
33352 | Calaveras CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
33353 | Calaveras CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
33354 | Calaveras CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
33355 | Calaveras CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
33356 | Calaveras CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
33357 | Calaveras CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
33358 | Calaveras CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
33359 | Calaveras CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
33360 | Calaveras CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
33361 | Calaveras CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
33362 | Calaveras CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
33363 | Calaveras CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
33364 | Calaveras CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
33365 | Calaveras CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
33366 | Calaveras CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33367 | Calaveras CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33368 | Calaveras CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33369 | Calaveras CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
33370 | Calaveras CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
33371 | Calaveras CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
33372 | Calaveras CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
33373 | Calaveras CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
33374 | Calaveras CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
33375 | Calaveras CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
33376 | Calaveras CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
33377 | Calaveras CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
33378 | Calaveras CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
33379 | Calaveras CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 15030SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
33380 | Calaveras CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 15029SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
33381 | Calaveras CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33382 | Calaveras CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33383 | Calaveras CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
33384 | Calaveras CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  | 15035SS | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
33385 | Calaveras CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 15034SS |  | Start No Earlier Than | 3/2/26 | 35 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
33386 | Calaveras CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
33387 | Calaveras CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 15038SS | Finish No Earlier Than | 5/29/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33388 | Calaveras CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 15037SS |  | Finish No Earlier Than | 6/15/26 | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
33389 | Calaveras CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
33390 | Calaveras CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 15041SS | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33391 | Calaveras CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 15040SS |  | Finish No Earlier Than | 7/15/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
33392 | Calaveras CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
33393 | Calaveras CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 15044SS | Finish No Earlier Than | 7/31/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33394 | Calaveras CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 15043SS |  | Start No Earlier Than | 7/1/26 | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
33395 | Calaveras CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
33396 | Calaveras CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 630 | 277d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.34999999999999998
33397 | Calaveras CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
33398 | Calaveras CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 15049 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
33399 | Calaveras CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 15048 |  | Finish No Earlier Than | 8/31/26 | 588 | 277d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
33400 | Calaveras CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
33401 | Calaveras CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
33402 | Calaveras CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
33403 | Calaveras CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33404 | Calaveras CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OC | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 15055 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
33405 | Calaveras CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 15054 | 15056 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
33406 | Calaveras CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 15055 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
33407 | Calaveras CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33408 | Calaveras CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 15059 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
33409 | Calaveras CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 15058 | 15060 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.59999999999999998
33410 | Calaveras CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 15059 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33411 | Calaveras CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33412 | Calaveras CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 15063 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.59999999999999998
33413 | Calaveras CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 15062 | 15064 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33414 | Calaveras CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 15063 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33415 | Calaveras CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33416 | Calaveras CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 15067 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33417 | Calaveras CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 15066 | 15068 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33418 | Calaveras CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15067 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33419 | Calaveras CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33420 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
33421 | Calaveras CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.38
33422 | Calaveras CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.56999999999999995
33423 | Calaveras CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 15074SS | Start No Earlier Than | 3/19/24 | 490 | 405d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.59999999999999998
33424 | Calaveras CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 15073SS | 15075 | As Soon As Possible | NA | 490 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.59999999999999998
33425 | Calaveras CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 15074 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33426 | Calaveras CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
33427 | Calaveras CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
33428 | Calaveras CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
33429 | Calaveras CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 15081 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
33430 | Calaveras CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.60999999999999999
33431 | Calaveras CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 15079 | 15082,15084SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
33432 | Calaveras CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 15081 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
33433 | Calaveras CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.11
33434 | Calaveras CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 15081SS | 15085SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
33435 | Calaveras CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 15084SS | 15086,15089,15087SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
33436 | Calaveras CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 15085 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33437 | Calaveras CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 15085SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33438 | Calaveras CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33439 | Calaveras CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 15085 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
33440 | Calaveras CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.71999999999999997
33441 | Calaveras CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 15092SS | Start No Earlier Than | 2/3/25 | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.80000000000000004
33442 | Calaveras CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 15091SS | 15093SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.80000000000000004
33443 | Calaveras CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 15092SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.59999999999999998
33444 | Calaveras CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
33445 | Calaveras CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
33446 | Calaveras CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 15102 | 15097SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
33447 | Calaveras CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 15096SS | 15099 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
33448 | Calaveras CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 508d | NA | NA | 0 days? | No | 7/21/25 | NA | NA | 0.97999999999999998
33449 | Calaveras CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 15097 | 15100 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
33450 | Calaveras CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 15099 |  | As Soon As Possible | NA | 21 | 508d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.94999999999999996
33451 | Calaveras CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
33452 | Calaveras CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 15096,15103SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
33453 | Calaveras CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 15102SS | 15107,15104 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
33454 | Calaveras CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 15103 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33455 | Calaveras CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | 8/1/25 | NA | NA | 0.20000000000000001
33456 | Calaveras CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33457 | Calaveras CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 15103 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
33458 | Calaveras CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33459 | Calaveras CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33460 | Calaveras CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33461 | Calaveras CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33462 | Calaveras CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33463 | Calaveras CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33464 | Calaveras CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33465 | Calaveras CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33466 | Calaveras CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33467 | Calaveras CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33468 | Calaveras CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33469 | Calaveras CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33470 | Calaveras CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33471 | Calaveras CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 316 | 256d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
33472 | Calaveras CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 15129 | Start No Earlier Than | 7/1/25 | 188 | 256d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
33473 | Calaveras CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
33474 | Calaveras CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
33475 | Calaveras CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33476 | Calaveras CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33477 | Calaveras CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15136 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33478 | Calaveras CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15137 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33479 | Calaveras CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 15122 |  | As Soon As Possible | NA | 128 | 256d | NA | NA | 0 days? | No | NA | NA | NA | 0
33480 | Calaveras CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33481 | Calaveras CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15142SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33482 | Calaveras CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15143SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33483 | Calaveras CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15144SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33484 | Calaveras CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15145SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33485 | Calaveras CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15146SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33486 | Calaveras CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 15127 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33487 | Calaveras CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 15128 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33488 | Calaveras CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33489 | Calaveras CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 15148FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
33490 | Calaveras CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33491 | Calaveras CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 15148SF+60d | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33492 | Calaveras CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15131SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33493 | Calaveras CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15132SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33494 | Calaveras CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15133SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33495 | Calaveras CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15134SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33496 | Calaveras CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15135SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33497 | Calaveras CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33498 | Calaveras CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 15139FS+12d,15141SF+60d |  | Finish No Earlier Than | 8/28/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
33499 | CARES V1 - Kings CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.35999999999999999
33500 | Kings CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.5
33501 | Kings CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 669 | 279d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.57999999999999996
33502 | Kings CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
33503 | Kings CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
33504 | Kings CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
33505 | Kings CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
33506 | Kings CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33507 | Kings CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
33508 | Kings CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Finish No Earlier Than | 8/28/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
33509 | Kings CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/30/26 | 43 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
33510 | Kings CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.40000000000000002
33511 | Kings CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.65000000000000002
33512 | Kings CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
33513 | Kings CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
33514 | Kings CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
33515 | Kings CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
33516 | Kings CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
33517 | Kings CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
33518 | Kings CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
33519 | Kings CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
33520 | Kings CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
33521 | Kings CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
33522 | Kings CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
33523 | Kings CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
33524 | Kings CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
33525 | Kings CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
33526 | Kings CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
33527 | Kings CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
33528 | Kings CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
33529 | Kings CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
33530 | Kings CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
33531 | Kings CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
33532 | Kings CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
33533 | Kings CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/30/25 | NA | 1
33534 | Kings CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
33535 | Kings CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
33536 | Kings CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
33537 | Kings CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
33538 | Kings CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
33539 | Kings CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
33540 | Kings CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33541 | Kings CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33542 | Kings CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33543 | Kings CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
33544 | Kings CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
33545 | Kings CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
33546 | Kings CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
33547 | Kings CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
33548 | Kings CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
33549 | Kings CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
33550 | Kings CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
33551 | Kings CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
33552 | Kings CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
33553 | Kings CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 15204SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
33554 | Kings CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 15203SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
33555 | Kings CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33556 | Kings CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33557 | Kings CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
33558 | Kings CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  | 15209SS | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
33559 | Kings CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 15208SS |  | Start No Earlier Than | 3/2/26 | 35 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
33560 | Kings CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
33561 | Kings CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 15212SS | Finish No Earlier Than | 5/29/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33562 | Kings CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 15211SS |  | Finish No Earlier Than | 6/15/26 | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
33563 | Kings CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
33564 | Kings CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 15215SS | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33565 | Kings CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 15214SS |  | Finish No Earlier Than | 7/15/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
33566 | Kings CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
33567 | Kings CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 15218SS | Finish No Earlier Than | 7/31/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33568 | Kings CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 15217SS |  | Start No Earlier Than | 7/1/26 | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
33569 | Kings CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
33570 | Kings CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 630 | 277d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.32000000000000001
33571 | Kings CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
33572 | Kings CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 15223 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
33573 | Kings CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 15222 |  | Finish No Earlier Than | 8/31/26 | 588 | 277d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.20000000000000001
33574 | Kings CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
33575 | Kings CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
33576 | Kings CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
33577 | Kings CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33578 | Kings CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OC | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 15229 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
33579 | Kings CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 15228 | 15230 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
33580 | Kings CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 15229 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
33581 | Kings CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33582 | Kings CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 15233 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
33583 | Kings CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 15232 | 15234 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
33584 | Kings CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 15233 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33585 | Kings CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33586 | Kings CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 15237 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
33587 | Kings CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 15236 | 15238 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33588 | Kings CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 15237 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33589 | Kings CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33590 | Kings CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 15241 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33591 | Kings CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 15240 | 15242 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33592 | Kings CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15241 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33593 | Kings CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33594 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
33595 | Kings CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.46999999999999997
33596 | Kings CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.97999999999999998
33597 | Kings CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 15248SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
33598 | Kings CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 15247SS | 15249 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
33599 | Kings CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 15248 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.59999999999999998
33600 | Kings CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
33601 | Kings CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
33602 | Kings CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
33603 | Kings CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 15255 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
33604 | Kings CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
33605 | Kings CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 15253 | 15256,15258SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
33606 | Kings CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 15255 |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
33607 | Kings CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
33608 | Kings CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 15255SS | 15259SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
33609 | Kings CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 15258SS | 15260,15263,15261SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33610 | Kings CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 15259 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33611 | Kings CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 15259SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33612 | Kings CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33613 | Kings CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 15259 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
33614 | Kings CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.84999999999999998
33615 | Kings CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 15266SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
33616 | Kings CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 15265SS | 15267SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
33617 | Kings CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 15266SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.59999999999999998
33618 | Kings CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
33619 | Kings CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
33620 | Kings CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 15276 | 15271SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
33621 | Kings CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 15270SS | 15273 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
33622 | Kings CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
33623 | Kings CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 15271 | 15274 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
33624 | Kings CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 15273 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
33625 | Kings CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
33626 | Kings CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 15270,15277SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
33627 | Kings CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 15276SS | 15281,15278 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33628 | Kings CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 15277 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33629 | Kings CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33630 | Kings CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33631 | Kings CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 15277 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
33632 | Kings CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33633 | Kings CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33634 | Kings CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33635 | Kings CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33636 | Kings CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33637 | Kings CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33638 | Kings CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33639 | Kings CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33640 | Kings CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33641 | Kings CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33642 | Kings CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33643 | Kings CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33644 | Kings CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33645 | Kings CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 316 | 256d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
33646 | Kings CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 15303 | Start No Earlier Than | 7/1/25 | 188 | 256d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
33647 | Kings CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
33648 | Kings CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
33649 | Kings CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33650 | Kings CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33651 | Kings CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15310 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33652 | Kings CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15311 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33653 | Kings CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 15296 |  | As Soon As Possible | NA | 128 | 256d | NA | NA | 0 days? | No | NA | NA | NA | 0
33654 | Kings CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33655 | Kings CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15316SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33656 | Kings CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15317SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33657 | Kings CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15318SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33658 | Kings CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15319SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33659 | Kings CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15320SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33660 | Kings CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 15301 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33661 | Kings CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 15302 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33662 | Kings CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33663 | Kings CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 15322FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
33664 | Kings CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33665 | Kings CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 15322SF+60d | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33666 | Kings CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15305SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33667 | Kings CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15306SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33668 | Kings CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15307SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33669 | Kings CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15308SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33670 | Kings CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15309SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33671 | Kings CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33672 | Kings CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 15313FS+12d,15315SF+60d |  | Finish No Earlier Than | 8/28/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
33673 | CARES V1 - Riverside CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.34999999999999998
33674 | Riverside CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.5
33675 | Riverside CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 669 | 279d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.57999999999999996
33676 | Riverside CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
33677 | Riverside CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
33678 | Riverside CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
33679 | Riverside CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
33680 | Riverside CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33681 | Riverside CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
33682 | Riverside CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Finish No Earlier Than | 8/28/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
33683 | Riverside CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/30/26 | 43 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
33684 | Riverside CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
33685 | Riverside CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
33686 | Riverside CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
33687 | Riverside CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
33688 | Riverside CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
33689 | Riverside CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
33690 | Riverside CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
33691 | Riverside CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
33692 | Riverside CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
33693 | Riverside CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
33694 | Riverside CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
33695 | Riverside CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
33696 | Riverside CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
33697 | Riverside CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
33698 | Riverside CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
33699 | Riverside CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
33700 | Riverside CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
33701 | Riverside CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
33702 | Riverside CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
33703 | Riverside CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
33704 | Riverside CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
33705 | Riverside CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
33706 | Riverside CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
33707 | Riverside CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
33708 | Riverside CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
33709 | Riverside CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
33710 | Riverside CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
33711 | Riverside CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
33712 | Riverside CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
33713 | Riverside CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
33714 | Riverside CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33715 | Riverside CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33716 | Riverside CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33717 | Riverside CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
33718 | Riverside CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
33719 | Riverside CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
33720 | Riverside CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
33721 | Riverside CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
33722 | Riverside CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
33723 | Riverside CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
33724 | Riverside CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
33725 | Riverside CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
33726 | Riverside CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
33727 | Riverside CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 15378SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
33728 | Riverside CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 15377SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
33729 | Riverside CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33730 | Riverside CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33731 | Riverside CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
33732 | Riverside CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  | 15383SS | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
33733 | Riverside CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 15382SS |  | Start No Earlier Than | 3/2/26 | 35 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
33734 | Riverside CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
33735 | Riverside CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 15386SS | Finish No Earlier Than | 5/29/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33736 | Riverside CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 15385SS |  | Finish No Earlier Than | 6/15/26 | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
33737 | Riverside CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
33738 | Riverside CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 15389SS | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33739 | Riverside CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 15388SS |  | Finish No Earlier Than | 7/15/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
33740 | Riverside CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
33741 | Riverside CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 15392SS | Finish No Earlier Than | 7/31/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33742 | Riverside CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 15391SS |  | Start No Earlier Than | 7/1/26 | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
33743 | Riverside CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
33744 | Riverside CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 630 | 277d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.40999999999999998
33745 | Riverside CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
33746 | Riverside CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 15397 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
33747 | Riverside CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 15396 |  | Finish No Earlier Than | 8/31/26 | 588 | 277d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.40000000000000002
33748 | Riverside CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
33749 | Riverside CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
33750 | Riverside CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
33751 | Riverside CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33752 | Riverside CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OC | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 15403 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
33753 | Riverside CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 15402 | 15404 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
33754 | Riverside CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 15403 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.59999999999999998
33755 | Riverside CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33756 | Riverside CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 15407 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
33757 | Riverside CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 15406 | 15408 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
33758 | Riverside CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 15407 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33759 | Riverside CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33760 | Riverside CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 15411 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
33761 | Riverside CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 15410 | 15412 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33762 | Riverside CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 15411 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33763 | Riverside CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33764 | Riverside CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 15415 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33765 | Riverside CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 15414 | 15416 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33766 | Riverside CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15415 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33767 | Riverside CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33768 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
33769 | Riverside CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.41999999999999998
33770 | Riverside CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.91000000000000003
33771 | Riverside CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 15422SS | As Soon As Possible | NA | 490 | 405d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
33772 | Riverside CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 15421SS | 15423 | As Soon As Possible | NA | 490 | 9.6d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
33773 | Riverside CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 15422 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.20000000000000001
33774 | Riverside CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
33775 | Riverside CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
33776 | Riverside CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
33777 | Riverside CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 15429 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
33778 | Riverside CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.60999999999999999
33779 | Riverside CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 15427 | 15430,15432SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
33780 | Riverside CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 15429 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
33781 | Riverside CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 5.9999999999999998E-2
33782 | Riverside CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 15429SS | 15433SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
33783 | Riverside CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 15432SS | 15434,15437,15435SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33784 | Riverside CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 15433 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33785 | Riverside CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 15433SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33786 | Riverside CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33787 | Riverside CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 15433 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
33788 | Riverside CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.64000000000000001
33789 | Riverside CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 15440SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
33790 | Riverside CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 15439SS | 15441SS | As Soon As Possible | NA | 190 | 485d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.80000000000000004
33791 | Riverside CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 15440SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
33792 | Riverside CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
33793 | Riverside CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
33794 | Riverside CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 15450 | 15445SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
33795 | Riverside CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 15444SS | 15447 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
33796 | Riverside CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 508d | NA | NA | 0 days? | No | 7/21/25 | NA | NA | 0.92000000000000004
33797 | Riverside CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 15445 | 15448 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
33798 | Riverside CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 15447 |  | As Soon As Possible | NA | 21 | 508d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.80000000000000004
33799 | Riverside CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
33800 | Riverside CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 15444,15451SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
33801 | Riverside CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 15450SS | 15455,15452 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33802 | Riverside CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 15451 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33803 | Riverside CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33804 | Riverside CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33805 | Riverside CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 15451 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
33806 | Riverside CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33807 | Riverside CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33808 | Riverside CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33809 | Riverside CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33810 | Riverside CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33811 | Riverside CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33812 | Riverside CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33813 | Riverside CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33814 | Riverside CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33815 | Riverside CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33816 | Riverside CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33817 | Riverside CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33818 | Riverside CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33819 | Riverside CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 316 | 256d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
33820 | Riverside CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 15477 | Start No Earlier Than | 7/1/25 | 188 | 256d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
33821 | Riverside CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
33822 | Riverside CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
33823 | Riverside CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33824 | Riverside CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33825 | Riverside CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15484 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33826 | Riverside CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15485 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33827 | Riverside CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 15470 |  | As Soon As Possible | NA | 128 | 256d | NA | NA | 0 days? | No | NA | NA | NA | 0
33828 | Riverside CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33829 | Riverside CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15490SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33830 | Riverside CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15491SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33831 | Riverside CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15492SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33832 | Riverside CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15493SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33833 | Riverside CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15494SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33834 | Riverside CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 15475 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33835 | Riverside CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 15476 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
33836 | Riverside CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33837 | Riverside CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 15496FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
33838 | Riverside CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33839 | Riverside CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 15496SF+60d | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33840 | Riverside CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15479SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33841 | Riverside CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15480SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33842 | Riverside CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15481SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33843 | Riverside CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15482SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33844 | Riverside CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15483SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33845 | Riverside CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33846 | Riverside CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 15487FS+12d,15489SF+60d |  | Finish No Earlier Than | 8/28/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
33847 | CARES V1 - Ventura CW | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | April 1, 2021 8:00 AM | April 19, 2027 5:00 PM | 1516 days | No | 7/17/23 | NA | NA | 0.37
33848 | Ventura CW-Data Quality | January 2, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.5
33849 | Ventura CW-Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2024 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 669 | 279d | NA | NA | 0 days? | No | 1/2/24 | NA | NA | 0.57999999999999996
33850 | Ventura CW-Participate in data cleanup initiatives/activities_Jan24 | January 2, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 41 | 0d | NA | NA | 0 days? | No | 1/2/24 | 2/29/24 | NA | 1
33851 | Ventura CW-Participate in data cleanup initiatives/activities_Jul24 | July 1, 2024 8:00 AM | September 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 45 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/2/24 | NA | 1
33852 | Ventura CW-Participate in data cleanup initiatives/activities_Jan25 | January 2, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/2/25 | 2/28/25 | NA | 1
33853 | Ventura CW-Participate in data cleanup initiatives/activities_Jul25 | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
33854 | Ventura CW-Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33855 | Ventura CW-Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
33856 | Ventura CW-Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Finish No Earlier Than | 8/28/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
33857 | Ventura CW-Begin post conversion data cleanup | September 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/30/26 | 43 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
33858 | Ventura CW-Implementation Management | July 17, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.38
33859 | Ventura CW-Monthly Readiness Meetings | January 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 713 | 235d | NA | NA | 0 days? | No | 1/1/24 | NA | NA | 0.62
33860 | Ventura CW-Participate in monthly readiness meetings | January 1, 2024 8:00 AM | January 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/24 | 1/31/24 | NA | 1
33861 | Ventura CW-Participate in monthly readiness meetings | February 1, 2024 8:00 AM | February 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 20 | 0d | NA | NA | 0 days? | No | 2/1/24 | 2/29/24 | NA | 1
33862 | Ventura CW-Participate in monthly readiness meetings | March 1, 2024 8:00 AM | March 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/1/24 | 3/29/24 | NA | 1
33863 | Ventura CW-Participate in monthly readiness meetings | April 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/24 | 4/30/24 | NA | 1
33864 | Ventura CW-Participate in monthly readiness meetings | May 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 5/1/24 | 5/31/24 | NA | 1
33865 | Ventura CW-Participate in monthly readiness meetings | June 3, 2024 8:00 AM | July 1, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/3/24 | 7/1/24 | NA | 1
33866 | Ventura CW-Participate in monthly readiness meetings | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
33867 | Ventura CW-Participate in monthly readiness meetings | August 1, 2024 8:00 AM | August 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 8/1/24 | 8/30/24 | NA | 1
33868 | Ventura CW-Participate in monthly readiness meetings | September 2, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/24 | 9/30/24 | NA | 1
33869 | Ventura CW-Participate in monthly readiness meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
33870 | Ventura CW-Participate in monthly readiness meetings | November 1, 2024 8:00 AM | November 29, 2024 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 11/29/24 | NA | 1
33871 | Ventura CW-Participate in monthly readiness meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
33872 | Ventura CW-Participate in monthly readiness meetings | January 1, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 1/1/25 | 1/31/25 | NA | 1
33873 | Ventura CW-Participate in monthly readiness meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
33874 | Ventura CW-Participate in monthly readiness meetings | March 3, 2025 8:00 AM | March 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 3/31/25 | NA | 1
33875 | Ventura CW-Participate in monthly readiness meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
33876 | Ventura CW-Participate in monthly readiness meetings | May 1, 2025 8:00 AM | May 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 5/1/25 | 5/30/25 | NA | 1
33877 | Ventura CW-Participate in monthly readiness meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
33878 | Ventura CW-Participate in monthly readiness meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
33879 | Ventura CW-Participate in monthly readiness meetings | August 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 21 | 0d | NA | NA | 0 days? | No | 8/1/25 | 8/29/25 | NA | 1
33880 | Ventura CW-Participate in monthly readiness meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
33881 | Ventura CW-Participate in monthly readiness meetings | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
33882 | Ventura CW-Participate in monthly readiness meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
33883 | Ventura CW-Participate in monthly readiness meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
33884 | Ventura CW-Participate in monthly readiness meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
33885 | Ventura CW-Participate in monthly readiness meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
33886 | Ventura CW-Participate in monthly readiness meetings | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
33887 | Ventura CW-Participate in monthly readiness meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
33888 | Ventura CW-Participate in monthly readiness meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33889 | Ventura CW-Participate in monthly readiness meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33890 | Ventura CW-Participate in monthly readiness meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33891 | Ventura CW-Participate in monthly readiness meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
33892 | Ventura CW-Participate in monthly readiness meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
33893 | Ventura CW-Participate in monthly readiness meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
33894 | Ventura CW-Attend Executive Briefing Meeting | July 17, 2023 8:00 AM | July 28, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 7/17/23 | 7/28/23 | NA | 1
33895 | Ventura CW-Schedule Kickoff Meeting | September 11, 2023 8:00 AM | September 22, 2023 5:00 PM |  |  | As Soon As Possible | NA | 10 | 0d | NA | NA | 0 days? | No | 9/11/23 | 9/22/23 | NA | 1
33896 | Ventura CW-Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | As Soon As Possible | NA | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
33897 | Ventura CW-Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
33898 | Ventura CW-Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
33899 | Ventura CW-IL to demonstrate how to access Imp Portal throughcwds.ca.gov | July 1, 2024 8:00 AM | July 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 7/1/24 | 7/31/24 | NA | 1
33900 | Ventura CW-Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
33901 | Ventura CW-Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 15552SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
33902 | Ventura CW-Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 15551SS |  | As Soon As Possible | NA | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
33903 | Ventura CW-Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33904 | Ventura CW-Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33905 | Ventura CW-Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 64 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
33906 | Ventura CW-Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 31, 2026 5:00 PM |  | 15557SS | Finish No Earlier Than | 3/31/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
33907 | Ventura CW-Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | March 2, 2026 8:00 AM | April 20, 2026 5:00 PM | 15556SS |  | Start No Earlier Than | 3/2/26 | 35 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
33908 | Ventura CW-Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
33909 | Ventura CW-Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 15560SS | Finish No Earlier Than | 5/29/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
33910 | Ventura CW-Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 15559SS |  | Finish No Earlier Than | 6/15/26 | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
33911 | Ventura CW-Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
33912 | Ventura CW-Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 15563SS | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
33913 | Ventura CW-Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 15562SS |  | Finish No Earlier Than | 7/15/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
33914 | Ventura CW-Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
33915 | Ventura CW-Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 15566SS | Finish No Earlier Than | 7/31/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33916 | Ventura CW-Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 15565SS |  | Start No Earlier Than | 7/1/26 | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
33917 | Ventura CW-Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
33918 | Ventura CW-Organization Change Management | March 1, 2024 8:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 630 | 277d | NA | NA | 0 days? | No | 3/1/24 | NA | NA | 0.40000000000000002
33919 | Ventura CW-Participate in regional OCM overview education session | March 1, 2024 8:00 AM | May 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 3/1/24 | 5/31/24 | NA | 1
33920 | Ventura CW-Review and customize Organization Communication Plan template | March 1, 2024 8:00 AM | April 30, 2024 5:00 PM |  | 15571 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/1/24 | 4/30/24 | NA | 1
33921 | Ventura CW-Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2024 8:00 AM | September 1, 2026 5:00 PM | 15570 |  | Finish No Earlier Than | 8/31/26 | 588 | 277d | NA | NA | 0 days? | No | 5/1/24 | NA | NA | 0.40000000000000002
33922 | Ventura CW-Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5 | October 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 10/1/24 | 12/2/24 | NA | 1
33923 | Ventura CW-Participate in OCM led Process Information Session for Intake | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
33924 | Ventura CW-Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/31/25 | NA | 1
33925 | Ventura CW-Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33926 | Ventura CW-Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OC | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 15577 | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
33927 | Ventura CW-Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM | 15576 | 15578 | As Soon As Possible | NA | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
33928 | Ventura CW-Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 15577 |  | As Soon As Possible | NA | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
33929 | Ventura CW-Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33930 | Ventura CW-Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals ( | July 1, 2025 8:00 AM | August 29, 2025 5:00 PM |  | 15581 | Start No Earlier Than | 7/1/25 | 43 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/29/25 | NA | 1
33931 | Ventura CW-Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 15580 | 15582 | As Soon As Possible | NA | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
33932 | Ventura CW-Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 15581 |  | As Soon As Possible | NA | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33933 | Ventura CW-Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33934 | Ventura CW-Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 15585 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
33935 | Ventura CW-Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 15584 | 15586 | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33936 | Ventura CW-Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 15585 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33937 | Ventura CW-Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33938 | Ventura CW-Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 15589 | Start No Earlier Than | 11/3/25 | 40 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33939 | Ventura CW-Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | February 27, 2026 5:00 PM | 15588 | 15590 | As Soon As Possible | NA | 39 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33940 | Ventura CW-Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15589 |  | As Soon As Possible | NA | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33941 | Ventura CW-Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
33942 | Review, update as needed and finalize all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/17/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
33943 | Ventura CW-Technical | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.46000000000000002
33944 | Ventura CW-Complete Tableau Training | March 19, 2024 8:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.97999999999999998
33945 | Ventura CW-Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 15596SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
33946 | Ventura CW-Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 15595SS | 15597 | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
33947 | Ventura CW-IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 8, 2026 5:00 PM | 15596 |  | As Soon As Possible | NA | 48 | 357d | NA | NA | 0 days? | No | 3/3/26 | NA | NA | 0.59999999999999998
33948 | Ventura CW-Review disposition of statewide reports | April 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
33949 | Ventura CW-Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | January 6, 2025 8:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 150 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
33950 | Ventura CW-Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
33951 | Ventura CW-Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | July 1, 2025 8:00 AM | August 8, 2025 5:00 PM |  | 15603 | As Soon As Possible | NA | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
33952 | Ventura CW-Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 59 | 485d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.60999999999999999
33953 | Ventura CW-Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 15601 | 15604,15606SS | As Soon As Possible | NA | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
33954 | Ventura CW-POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM | 15603 |  | As Soon As Possible | NA | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
33955 | Ventura CW-Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.01
33956 | Ventura CW-Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 15603SS | 15607SS | As Soon As Possible | NA | 36 | 508d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
33957 | Ventura CW-Create organization-specific reports for process simulation bulk upload | August 11, 2025 8:00 AM | May 1, 2026 5:00 PM | 15606SS | 15608,15611,15609SF+30d | As Soon As Possible | NA | 182 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33958 | Ventura CW-Continue development of organization-specific reports for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 15607 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33959 | Ventura CW-Test reports in development environment | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM | 15607SF+30d |  | Start No Earlier Than | 10/1/25 | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33960 | Ventura CW-Test reports in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33961 | Ventura CW-POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 15607 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
33962 | Ventura CW-Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.92000000000000004
33963 | Ventura CW-Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 15614SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
33964 | Ventura CW-Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | October 31, 2025 5:00 PM | 15613SS | 15615SS | As Soon As Possible | NA | 190 | 0d | NA | NA | 0 days? | No | 2/3/25 | 10/31/25 | NA | 1
33965 | Ventura CW-Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | February 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 15614SS |  | As Soon As Possible | NA | 230 | 445d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.80000000000000004
33966 | Ventura CW-Review disposition of statewide Forms provided by Project | January 1, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 1/1/25 | 2/28/25 | NA | 1
33967 | Ventura CW-Identify Organization-specific forms by completing the Forms Inventory Workbooks | January 6, 2025 8:00 AM | July 18, 2025 5:00 PM |  |  | As Soon As Possible | NA | 135 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
33968 | Ventura CW-Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 8:00 AM | June 30, 2025 5:00 PM | 15624 | 15619SS | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
33969 | Ventura CW-Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | April 1, 2025 8:00 AM | July 18, 2025 5:00 PM | 15618SS | 15621 | As Soon As Possible | NA | 77 | 0d | NA | NA | 0 days? | No | 4/1/25 | 7/18/25 | NA | 1
33970 | Ventura CW-Determine priority for Organization-specific custom Forms | July 21, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 51 | 0d | NA | NA | 0 days? | No | 7/21/25 | 9/30/25 | NA | 1
33971 | Ventura CW-Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | July 21, 2025 8:00 AM | August 29, 2025 5:00 PM | 15619 | 15622 | As Soon As Possible | NA | 30 | 0d | NA | NA | 0 days? | No | 7/21/25 | 8/29/25 | NA | 1
33972 | Ventura CW-POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM | 15621 |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
33973 | Ventura CW-Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | July 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 274 | 298d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 8.9999999999999997E-2
33974 | Ventura CW-Develop Plan for Timeline of Form Creation in AEM/Word | July 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 15618,15625SS | Start No Earlier Than | 7/1/25 | 64 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/30/25 | NA | 1
33975 | Ventura CW-Create organization-specific forms for process simulation bulk upload | July 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 15624SS | 15629,15626 | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33976 | Ventura CW-Continue development of organization-specific forms for production bulk upload, if necessary | May 4, 2026 8:00 AM | August 3, 2026 5:00 PM | 15625 |  | As Soon As Possible | NA | 64 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33977 | Ventura CW-Test forms in development environment | August 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 252 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
33978 | Ventura CW-Test forms in environment with converted data | January 9, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/31/26 | 141 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
33979 | Ventura CW-POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 15625 |  | As Soon As Possible | NA | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
33980 | Ventura CW-Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 82 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33981 | Ventura CW-Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33982 | Ventura CW-Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33983 | Ventura CW-Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33984 | Ventura CW-Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33985 | Ventura CW-Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33986 | Ventura CW-Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33987 | Ventura CW-Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33988 | Ventura CW-Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33989 | Ventura CW-Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33990 | Ventura CW-Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33991 | Ventura CW-Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
33992 | Ventura CW-Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
33993 | Ventura CW-Training | July 1, 2025 8:00 AM | October 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 316 | 256d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
33994 | Ventura CW-Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 15651 | As Soon As Possible | NA | 188 | 256d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
33995 | Ventura CW-Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
33996 | Ventura CW-Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
33997 | Ventura CW-Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33998 | Ventura CW-Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
33999 | Ventura CW-Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15658 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
34000 | Ventura CW-Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15659 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
34001 | Ventura CW-Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | October 1, 2026 5:00 PM | 15644 |  | As Soon As Possible | NA | 128 | 256d | NA | NA | 0 days? | No | NA | NA | NA | 0
34002 | Ventura CW-Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34003 | Ventura CW-Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15664SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
34004 | Ventura CW-Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15665SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
34005 | Ventura CW-Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15666SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
34006 | Ventura CW-Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15667SF+30d | Start No Earlier Than | 5/1/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
34007 | Ventura CW-Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 15668SF+30d | Finish No Earlier Than | 6/12/26 | 30 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
34008 | Ventura CW-Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 15649 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
34009 | Ventura CW-Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 15650 |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
34010 | Ventura CW-Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
34011 | Ventura CW-Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 15670FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34012 | Ventura CW-Validate access to on-demand self-paced training materials | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/30/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34013 | Ventura CW-Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 15670SF+60d | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34014 | Ventura CW-Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15653SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34015 | Ventura CW-Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15654SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34016 | Ventura CW-Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15655SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34017 | Ventura CW-Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15656SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34018 | Ventura CW-Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 15657SF+30d |  | Finish No Earlier Than | 7/31/26 | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34019 | Ventura CW-Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34020 | Ventura CW-Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 15661FS+12d,15663SF+60d |  | Finish No Earlier Than | 8/28/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34026 | Probation Departments | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 7.0000000000000007E-2
34027 | Alameda PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
34028 | Alameda PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
34029 | Alameda PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
34030 | Alameda PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
34031 | Alameda PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34032 | Alameda PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
34033 | Alameda PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
34034 | Alameda PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
34035 | Alameda PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34036 | Alameda PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
34037 | Alameda PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
34038 | Alameda PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
34039 | Alameda PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34040 | Alameda PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
34041 | Alameda PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34042 | Alameda PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34043 | Alameda PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
34044 | Alameda PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34045 | Alameda PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
34046 | Alameda PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
34047 | Alameda PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1