34048 | Alameda PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
34049 | Alameda PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
34050 | Alameda PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
34051 | Alameda PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
34052 | Alameda PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
34053 | Alameda PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34054 | Alameda PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34055 | Alameda PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 15701SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
34056 | Alameda PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 15700SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
34057 | Alameda PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15703SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34058 | Alameda PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15702SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34059 | Alameda PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
34060 | Alameda PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 15706SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
34061 | Alameda PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 15705SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
34062 | Alameda PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
34063 | Alameda PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 15709SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
34064 | Alameda PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 15708SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
34065 | Alameda PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34066 | Alameda PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 15712SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34067 | Alameda PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 15711SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
34068 | Alameda PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 15714SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
34069 | Alameda PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 15713SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
34070 | Alameda PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34071 | Alameda PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
34072 | Alameda PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34073 | Alameda PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
34074 | Alameda PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34075 | Alameda PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
34076 | Alameda PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
34077 | Alameda PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 15723FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34078 | Alameda PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 15722FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34079 | Alameda PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
34080 | Alameda PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 15727FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
34081 | Alameda PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34082 | Alameda PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 15725FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
34083 | Alameda PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
34084 | Alameda PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 15730 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
34085 | Alameda PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 15729 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34086 | Alameda PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34087 | Alameda PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 15733FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34088 | Alameda PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 15732FS+19d | 15734 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34089 | Alameda PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 15733 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34090 | Alameda PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34091 | Alameda PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 15737 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34092 | Alameda PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 15736 | 15738FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34093 | Alameda PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 15737FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34094 | Alameda PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34095 | Alameda PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34096 | Alameda PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34097 | Alameda PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34098 | Alameda PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 15744SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34099 | Alameda PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 15743SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
34100 | Alameda PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34101 | Alameda PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34102 | Alameda PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34103 | Alameda PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 15749SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34104 | Alameda PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 15748SS | 15763SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34105 | Alameda PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34106 | Alameda PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34107 | Alameda PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34108 | Alameda PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34109 | Alameda PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 15755SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34110 | Alameda PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 15754SS | 15756SS,15757 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34111 | Alameda PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 15755SS | 15757 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34112 | Alameda PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 15755,15756 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34113 | Alameda PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34114 | Alameda PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34115 | Alameda PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 15761SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34116 | Alameda PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 15760SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
34117 | Alameda PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34118 | Alameda PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 15749SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34119 | Alameda PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34120 | Alameda PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 15766SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34121 | Alameda PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 15765SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34122 | Alameda PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34123 | Alameda PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 15769SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34124 | Alameda PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 15768SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34125 | Alameda PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34126 | Alameda PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 15772SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34127 | Alameda PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 15771SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34128 | Alameda PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 15774 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34129 | Alameda PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 15773 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34130 | Alameda PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34131 | Alameda PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34132 | Alameda PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15778SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34133 | Alameda PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15777SS | 15779SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34134 | Alameda PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15778SS | 15780SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34135 | Alameda PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15779SS | 15781SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34136 | Alameda PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15780SS | 15782SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34137 | Alameda PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15781SS | 15783SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34138 | Alameda PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15782SS | 15784SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34139 | Alameda PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15783SS | 15785SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34140 | Alameda PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15784SS | 15786SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34141 | Alameda PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15785SS | 15787SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34142 | Alameda PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15786SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34143 | Alameda PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
34144 | Alameda PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
34145 | Alameda PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34146 | Alameda PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 15792SS,15796 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34147 | Alameda PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 15791SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
34148 | Alameda PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
34149 | Alameda PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15802 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34150 | Alameda PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15803 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34151 | Alameda PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 15791 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34152 | Alameda PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
34153 | Alameda PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 15799SS,15807SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34154 | Alameda PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 15798SS | 15800SS,15808SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34155 | Alameda PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 15799SS | 15809SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34156 | Alameda PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
34157 | Alameda PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 15794 | 15803SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34158 | Alameda PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 15795,15802SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34159 | Alameda PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 15812FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34160 | Alameda PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 15806SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34161 | Alameda PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 15805SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34162 | Alameda PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 15798SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34163 | Alameda PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 15799SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34164 | Alameda PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 15800SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34165 | Alameda PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 15812SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34166 | Alameda PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34167 | Alameda PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 15804FS+12d,15810SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34168 | Alpine PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 8.0000000000000002E-2
34169 | Alpine PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
34170 | Alpine PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
34171 | Alpine PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
34172 | Alpine PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34173 | Alpine PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
34174 | Alpine PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
34175 | Alpine PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
34176 | Alpine PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34177 | Alpine PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
34178 | Alpine PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
34179 | Alpine PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
34180 | Alpine PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34181 | Alpine PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
34182 | Alpine PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34183 | Alpine PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34184 | Alpine PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
34185 | Alpine PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34186 | Alpine PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
34187 | Alpine PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
34188 | Alpine PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
34189 | Alpine PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
34190 | Alpine PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
34191 | Alpine PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
34192 | Alpine PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
34193 | Alpine PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
34194 | Alpine PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34195 | Alpine PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34196 | Alpine PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 15842SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
34197 | Alpine PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 15841SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
34198 | Alpine PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15844SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34199 | Alpine PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15843SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34200 | Alpine PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
34201 | Alpine PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 15847SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
34202 | Alpine PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 15846SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
34203 | Alpine PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
34204 | Alpine PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 15850SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
34205 | Alpine PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 15849SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
34206 | Alpine PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34207 | Alpine PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 15853SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34208 | Alpine PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 15852SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
34209 | Alpine PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 15855SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
34210 | Alpine PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 15854SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
34211 | Alpine PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34212 | Alpine PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
34213 | Alpine PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34214 | Alpine PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
34215 | Alpine PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34216 | Alpine PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
34217 | Alpine PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
34218 | Alpine PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 15864FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34219 | Alpine PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 15863FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34220 | Alpine PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.34000000000000002
34221 | Alpine PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 15868FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
34222 | Alpine PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34223 | Alpine PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 15866FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.59999999999999998
34224 | Alpine PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
34225 | Alpine PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 15871 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
34226 | Alpine PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 15870 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34227 | Alpine PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34228 | Alpine PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 15874FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34229 | Alpine PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 15873FS+19d | 15875 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34230 | Alpine PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 15874 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34231 | Alpine PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34232 | Alpine PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 15878 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34233 | Alpine PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 15877 | 15879FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34234 | Alpine PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 15878FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34235 | Alpine PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34236 | Alpine PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34237 | Alpine PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34238 | Alpine PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34239 | Alpine PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 15885SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34240 | Alpine PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 15884SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
34241 | Alpine PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34242 | Alpine PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34243 | Alpine PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34244 | Alpine PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 15890SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34245 | Alpine PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 15889SS | 15904SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34246 | Alpine PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34247 | Alpine PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34248 | Alpine PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34249 | Alpine PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34250 | Alpine PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 15896SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34251 | Alpine PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 15895SS | 15897SS,15898 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34252 | Alpine PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 15896SS | 15898 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34253 | Alpine PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 15896,15897 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34254 | Alpine PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34255 | Alpine PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34256 | Alpine PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 15902SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34257 | Alpine PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 15901SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
34258 | Alpine PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34259 | Alpine PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 15890SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34260 | Alpine PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34261 | Alpine PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 15907SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34262 | Alpine PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 15906SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34263 | Alpine PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34264 | Alpine PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 15910SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34265 | Alpine PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 15909SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34266 | Alpine PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34267 | Alpine PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 15913SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34268 | Alpine PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 15912SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34269 | Alpine PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 15915 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34270 | Alpine PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 15914 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34271 | Alpine PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34272 | Alpine PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34273 | Alpine PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15919SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34274 | Alpine PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15918SS | 15920SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34275 | Alpine PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15919SS | 15921SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34276 | Alpine PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15920SS | 15922SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34277 | Alpine PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15921SS | 15923SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34278 | Alpine PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15922SS | 15924SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34279 | Alpine PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15923SS | 15925SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34280 | Alpine PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15924SS | 15926SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34281 | Alpine PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15925SS | 15927SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34282 | Alpine PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15926SS | 15928SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34283 | Alpine PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15927SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34284 | Alpine PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
34285 | Alpine PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
34286 | Alpine PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34287 | Alpine PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 15933SS,15937 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34288 | Alpine PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 15932SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
34289 | Alpine PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
34290 | Alpine PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15943 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34291 | Alpine PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15944 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34292 | Alpine PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 15932 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34293 | Alpine PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
34294 | Alpine PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 15940SS,15948SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34295 | Alpine PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 15939SS | 15941SS,15949SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34296 | Alpine PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 15940SS | 15950SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34297 | Alpine PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
34298 | Alpine PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 15935 | 15944SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34299 | Alpine PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 15936,15943SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34300 | Alpine PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 15953FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34301 | Alpine PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 15947SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34302 | Alpine PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 15946SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34303 | Alpine PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 15939SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34304 | Alpine PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 15940SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34305 | Alpine PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 15941SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34306 | Alpine PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 15953SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34307 | Alpine PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34308 | Alpine PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 15945FS+12d,15951SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34309 | Amador PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 8.0000000000000002E-2
34310 | Amador PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
34311 | Amador PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
34312 | Amador PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
34313 | Amador PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34314 | Amador PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
34315 | Amador PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
34316 | Amador PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
34317 | Amador PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34318 | Amador PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
34319 | Amador PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
34320 | Amador PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
34321 | Amador PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34322 | Amador PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
34323 | Amador PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34324 | Amador PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34325 | Amador PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
34326 | Amador PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34327 | Amador PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
34328 | Amador PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
34329 | Amador PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
34330 | Amador PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
34331 | Amador PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
34332 | Amador PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
34333 | Amador PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
34334 | Amador PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
34335 | Amador PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34336 | Amador PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34337 | Amador PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 15983SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
34338 | Amador PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 15982SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
34339 | Amador PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 15985SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34340 | Amador PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 15984SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34341 | Amador PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
34342 | Amador PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 15988SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
34343 | Amador PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 15987SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
34344 | Amador PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
34345 | Amador PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 15991SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
34346 | Amador PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 15990SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
34347 | Amador PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34348 | Amador PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 15994SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34349 | Amador PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 15993SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
34350 | Amador PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 15996SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
34351 | Amador PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 15995SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
34352 | Amador PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34353 | Amador PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
34354 | Amador PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34355 | Amador PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
34356 | Amador PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34357 | Amador PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
34358 | Amador PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
34359 | Amador PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 16005FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34360 | Amador PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 16004FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34361 | Amador PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.34000000000000002
34362 | Amador PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 16009FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
34363 | Amador PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34364 | Amador PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 16007FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.59999999999999998
34365 | Amador PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
34366 | Amador PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 16012 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
34367 | Amador PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16011 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34368 | Amador PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34369 | Amador PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16015FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34370 | Amador PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 16014FS+19d | 16016 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34371 | Amador PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 16015 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34372 | Amador PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34373 | Amador PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 16019 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34374 | Amador PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 16018 | 16020FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34375 | Amador PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 16019FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34376 | Amador PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34377 | Amador PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34378 | Amador PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34379 | Amador PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34380 | Amador PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16026SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34381 | Amador PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 16025SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
34382 | Amador PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34383 | Amador PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34384 | Amador PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34385 | Amador PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16031SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34386 | Amador PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16030SS | 16045SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34387 | Amador PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34388 | Amador PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34389 | Amador PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34390 | Amador PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34391 | Amador PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 16037SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34392 | Amador PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16036SS | 16038SS,16039 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34393 | Amador PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16037SS | 16039 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34394 | Amador PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 16037,16038 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34395 | Amador PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34396 | Amador PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34397 | Amador PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16043SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34398 | Amador PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 16042SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
34399 | Amador PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34400 | Amador PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16031SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34401 | Amador PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34402 | Amador PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16048SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34403 | Amador PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16047SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34404 | Amador PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34405 | Amador PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 16051SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34406 | Amador PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 16050SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34407 | Amador PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34408 | Amador PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 16054SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34409 | Amador PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16053SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34410 | Amador PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 16056 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34411 | Amador PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 16055 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34412 | Amador PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34413 | Amador PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34414 | Amador PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16060SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34415 | Amador PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16059SS | 16061SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34416 | Amador PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16060SS | 16062SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34417 | Amador PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16061SS | 16063SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34418 | Amador PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16062SS | 16064SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34419 | Amador PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16063SS | 16065SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34420 | Amador PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16064SS | 16066SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34421 | Amador PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16065SS | 16067SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34422 | Amador PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16066SS | 16068SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34423 | Amador PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16067SS | 16069SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34424 | Amador PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16068SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34425 | Amador PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
34426 | Amador PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
34427 | Amador PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34428 | Amador PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 16074SS,16078 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34429 | Amador PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 16073SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
34430 | Amador PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
34431 | Amador PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16084 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34432 | Amador PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16085 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34433 | Amador PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 16073 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34434 | Amador PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
34435 | Amador PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 16081SS,16089SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34436 | Amador PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 16080SS | 16082SS,16090SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34437 | Amador PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 16081SS | 16091SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34438 | Amador PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
34439 | Amador PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 16076 | 16085SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34440 | Amador PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 16077,16084SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34441 | Amador PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 16094FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34442 | Amador PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 16088SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34443 | Amador PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 16087SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34444 | Amador PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 16080SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34445 | Amador PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 16081SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34446 | Amador PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 16082SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34447 | Amador PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 16094SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34448 | Amador PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34449 | Amador PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 16086FS+12d,16092SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34450 | Butte PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
34451 | Butte PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
34452 | Butte PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
34453 | Butte PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
34454 | Butte PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34455 | Butte PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
34456 | Butte PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
34457 | Butte PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
34458 | Butte PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34459 | Butte PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
34460 | Butte PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
34461 | Butte PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
34462 | Butte PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34463 | Butte PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
34464 | Butte PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34465 | Butte PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34466 | Butte PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
34467 | Butte PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34468 | Butte PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
34469 | Butte PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
34470 | Butte PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
34471 | Butte PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
34472 | Butte PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
34473 | Butte PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
34474 | Butte PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
34475 | Butte PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
34476 | Butte PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34477 | Butte PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34478 | Butte PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 16124SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
34479 | Butte PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 16123SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
34480 | Butte PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16126SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34481 | Butte PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16125SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34482 | Butte PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 16129SS,16128SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
34483 | Butte PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 16127SS |  | As Soon As Possible | NA | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
34484 | Butte PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 16127SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
34485 | Butte PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
34486 | Butte PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 16132SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
34487 | Butte PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 16131SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
34488 | Butte PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
34489 | Butte PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 16135SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
34490 | Butte PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 16134SS |  | Start No Earlier Than | 6/1/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
34491 | Butte PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 16137SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
34492 | Butte PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 16136SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
34493 | Butte PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
34494 | Butte PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
34495 | Butte PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 211 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34496 | Butte PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 166 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34497 | Butte PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34498 | Butte PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
34499 | Butte PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34500 | Butte PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 44 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34501 | Butte PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 295 | 277d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
34502 | Butte PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 16149FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
34503 | Butte PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34504 | Butte PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 16147FS-1d |  | Start No Earlier Than | 9/2/25 | 252 | 277d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
34505 | Butte PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
34506 | Butte PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 16152 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
34507 | Butte PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16151 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34508 | Butte PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34509 | Butte PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16155FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34510 | Butte PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 16154FS+19d | 16156 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34511 | Butte PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 16155 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34512 | Butte PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34513 | Butte PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 16159 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34514 | Butte PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 16158 | 16160FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34515 | Butte PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 16159FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34516 | Butte PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34517 | Butte PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34518 | Butte PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34519 | Butte PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34520 | Butte PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16166SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34521 | Butte PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 16165SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
34522 | Butte PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34523 | Butte PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34524 | Butte PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34525 | Butte PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16171SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34526 | Butte PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16170SS | 16185SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34527 | Butte PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34528 | Butte PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34529 | Butte PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34530 | Butte PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34531 | Butte PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 16177SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34532 | Butte PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16176SS | 16178SS,16179 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34533 | Butte PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16177SS | 16179 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34534 | Butte PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 16177,16178 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34535 | Butte PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34536 | Butte PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34537 | Butte PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16183SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34538 | Butte PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 16182SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
34539 | Butte PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34540 | Butte PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16171SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34541 | Butte PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34542 | Butte PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16188SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34543 | Butte PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16187SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34544 | Butte PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34545 | Butte PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 16191SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34546 | Butte PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 16190SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34547 | Butte PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34548 | Butte PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 16194SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34549 | Butte PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16193SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34550 | Butte PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 16196 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34551 | Butte PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 16195 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34552 | Butte PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34553 | Butte PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34554 | Butte PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16200SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34555 | Butte PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16199SS | 16201SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34556 | Butte PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16200SS | 16202SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34557 | Butte PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16201SS | 16203SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34558 | Butte PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16202SS | 16204SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34559 | Butte PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16203SS | 16205SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34560 | Butte PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16204SS | 16206SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34561 | Butte PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16205SS | 16207SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34562 | Butte PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16206SS | 16208SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34563 | Butte PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16207SS | 16209SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34564 | Butte PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16208SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34565 | Butte PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
34566 | Butte PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
34567 | Butte PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34568 | Butte PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 16214SS,16218 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34569 | Butte PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 16213SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
34570 | Butte PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
34571 | Butte PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16224 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
34572 | Butte PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16225 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
34573 | Butte PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 16213 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34574 | Butte PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
34575 | Butte PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 16221SS,16229SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34576 | Butte PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 16220SS | 16222SS,16230SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34577 | Butte PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 16221SS | 16231SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34578 | Butte PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
34579 | Butte PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 16216 | 16225SS | Start No Earlier Than | 5/1/26 | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
34580 | Butte PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 16217,16224SS |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
34581 | Butte PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 16234FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34582 | Butte PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 16228SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34583 | Butte PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 16227SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34584 | Butte PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 16220SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34585 | Butte PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 16221SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34586 | Butte PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 16222SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34587 | Butte PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 16234SS+44d | Start No Earlier Than | 6/1/26 | 44 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34588 | Butte PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34589 | Butte PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 16226FS+12d,16232SS+44d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34590 | Calaveras PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 7.0000000000000007E-2
34591 | Calaveras PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
34592 | Calaveras PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
34593 | Calaveras PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
34594 | Calaveras PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34595 | Calaveras PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
34596 | Calaveras PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
34597 | Calaveras PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
34598 | Calaveras PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34599 | Calaveras PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
34600 | Calaveras PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
34601 | Calaveras PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
34602 | Calaveras PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34603 | Calaveras PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
34604 | Calaveras PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34605 | Calaveras PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34606 | Calaveras PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
34607 | Calaveras PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34608 | Calaveras PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
34609 | Calaveras PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
34610 | Calaveras PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
34611 | Calaveras PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
34612 | Calaveras PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
34613 | Calaveras PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
34614 | Calaveras PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
34615 | Calaveras PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
34616 | Calaveras PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34617 | Calaveras PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34618 | Calaveras PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 16264SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
34619 | Calaveras PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 16263SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
34620 | Calaveras PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16266SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34621 | Calaveras PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16265SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34622 | Calaveras PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 16269SS,16268SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
34623 | Calaveras PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 16267SS |  | As Soon As Possible | NA | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
34624 | Calaveras PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 16267SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
34625 | Calaveras PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
34626 | Calaveras PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 16272SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
34627 | Calaveras PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 16271SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
34628 | Calaveras PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
34629 | Calaveras PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 16275SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
34630 | Calaveras PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 16274SS |  | Start No Earlier Than | 6/1/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
34631 | Calaveras PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 16277SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
34632 | Calaveras PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 16276SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
34633 | Calaveras PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
34634 | Calaveras PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
34635 | Calaveras PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 211 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34636 | Calaveras PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 166 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34637 | Calaveras PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34638 | Calaveras PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
34639 | Calaveras PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34640 | Calaveras PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 44 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34641 | Calaveras PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 295 | 277d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.26000000000000001
34642 | Calaveras PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 16289FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
34643 | Calaveras PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34644 | Calaveras PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 16287FS-1d |  | Start No Earlier Than | 9/2/25 | 252 | 277d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
34645 | Calaveras PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
34646 | Calaveras PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 16292 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
34647 | Calaveras PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16291 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34648 | Calaveras PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34649 | Calaveras PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16295FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34650 | Calaveras PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 16294FS+19d | 16296 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34651 | Calaveras PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 16295 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34652 | Calaveras PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34653 | Calaveras PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 16299 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34654 | Calaveras PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 16298 | 16300FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34655 | Calaveras PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 16299FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34656 | Calaveras PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34657 | Calaveras PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34658 | Calaveras PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34659 | Calaveras PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34660 | Calaveras PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16306SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34661 | Calaveras PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 16305SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
34662 | Calaveras PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34663 | Calaveras PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34664 | Calaveras PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34665 | Calaveras PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16311SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34666 | Calaveras PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16310SS | 16325SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34667 | Calaveras PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34668 | Calaveras PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34669 | Calaveras PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34670 | Calaveras PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34671 | Calaveras PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 16317SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34672 | Calaveras PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16316SS | 16318SS,16319 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34673 | Calaveras PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16317SS | 16319 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34674 | Calaveras PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 16317,16318 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34675 | Calaveras PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34676 | Calaveras PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34677 | Calaveras PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16323SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34678 | Calaveras PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 16322SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
34679 | Calaveras PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34680 | Calaveras PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16311SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34681 | Calaveras PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34682 | Calaveras PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16328SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34683 | Calaveras PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16327SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34684 | Calaveras PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34685 | Calaveras PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 16331SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34686 | Calaveras PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 16330SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34687 | Calaveras PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34688 | Calaveras PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 16334SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34689 | Calaveras PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16333SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34690 | Calaveras PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 16336 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34691 | Calaveras PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 16335 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34692 | Calaveras PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34693 | Calaveras PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34694 | Calaveras PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16340SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34695 | Calaveras PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16339SS | 16341SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34696 | Calaveras PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16340SS | 16342SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34697 | Calaveras PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16341SS | 16343SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34698 | Calaveras PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16342SS | 16344SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34699 | Calaveras PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16343SS | 16345SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34700 | Calaveras PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16344SS | 16346SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34701 | Calaveras PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16345SS | 16347SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34702 | Calaveras PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16346SS | 16348SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34703 | Calaveras PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16347SS | 16349SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34704 | Calaveras PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16348SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34705 | Calaveras PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
34706 | Calaveras PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
34707 | Calaveras PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34708 | Calaveras PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 16354SS,16358 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34709 | Calaveras PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 16353SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
34710 | Calaveras PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
34711 | Calaveras PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16364 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
34712 | Calaveras PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16365 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
34713 | Calaveras PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 16353 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34714 | Calaveras PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
34715 | Calaveras PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 16361SS,16369SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34716 | Calaveras PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 16360SS | 16362SS,16370SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34717 | Calaveras PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 16361SS | 16371SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34718 | Calaveras PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
34719 | Calaveras PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 16356 | 16365SS | Start No Earlier Than | 5/1/26 | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
34720 | Calaveras PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 16357,16364SS |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
34721 | Calaveras PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 16374FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34722 | Calaveras PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 16368SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34723 | Calaveras PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 16367SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34724 | Calaveras PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 16360SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34725 | Calaveras PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 16361SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34726 | Calaveras PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 16362SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34727 | Calaveras PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 16374SS+44d | Start No Earlier Than | 6/1/26 | 44 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34728 | Calaveras PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34729 | Calaveras PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 16366FS+12d,16372SS+44d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34730 | Colusa PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 8.0000000000000002E-2
34731 | Colusa PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
34732 | Colusa PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
34733 | Colusa PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
34734 | Colusa PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34735 | Colusa PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
34736 | Colusa PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
34737 | Colusa PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
34738 | Colusa PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34739 | Colusa PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
34740 | Colusa PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
34741 | Colusa PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
34742 | Colusa PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34743 | Colusa PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
34744 | Colusa PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34745 | Colusa PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34746 | Colusa PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
34747 | Colusa PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34748 | Colusa PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
34749 | Colusa PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
34750 | Colusa PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
34751 | Colusa PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
34752 | Colusa PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
34753 | Colusa PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
34754 | Colusa PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
34755 | Colusa PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
34756 | Colusa PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34757 | Colusa PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34758 | Colusa PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 16404SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
34759 | Colusa PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 16403SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
34760 | Colusa PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16406SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34761 | Colusa PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16405SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34762 | Colusa PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
34763 | Colusa PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 16409SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
34764 | Colusa PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 16408SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
34765 | Colusa PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
34766 | Colusa PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 16412SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
34767 | Colusa PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 16411SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
34768 | Colusa PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34769 | Colusa PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 16415SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34770 | Colusa PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 16414SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
34771 | Colusa PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 16417SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
34772 | Colusa PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 16416SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
34773 | Colusa PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34774 | Colusa PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
34775 | Colusa PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34776 | Colusa PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
34777 | Colusa PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34778 | Colusa PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
34779 | Colusa PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
34780 | Colusa PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 16426FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34781 | Colusa PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 16425FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34782 | Colusa PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
34783 | Colusa PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 16430FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
34784 | Colusa PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34785 | Colusa PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 16428FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
34786 | Colusa PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
34787 | Colusa PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 16433 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
34788 | Colusa PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16432 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34789 | Colusa PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34790 | Colusa PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16436FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34791 | Colusa PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 16435FS+19d | 16437 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34792 | Colusa PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 16436 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34793 | Colusa PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34794 | Colusa PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 16440 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34795 | Colusa PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 16439 | 16441FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34796 | Colusa PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 16440FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34797 | Colusa PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34798 | Colusa PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34799 | Colusa PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 131 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
34800 | Colusa PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34801 | Colusa PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16447SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34802 | Colusa PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16446SS | 16448SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34803 | Colusa PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16447SS | 16449SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34804 | Colusa PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16448SS | 16450SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34805 | Colusa PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16449SS | 16451SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34806 | Colusa PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16450SS | 16452SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34807 | Colusa PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16451SS | 16453SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34808 | Colusa PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16452SS | 16454SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34809 | Colusa PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16453SS | 16455SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34810 | Colusa PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16454SS | 16456SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34811 | Colusa PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16455SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34812 | Colusa PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
34813 | Colusa PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
34814 | Colusa PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34815 | Colusa PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 16461SS,16465 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34816 | Colusa PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 16460SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
34817 | Colusa PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
34818 | Colusa PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16471 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34819 | Colusa PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16472 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34820 | Colusa PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 16460 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34821 | Colusa PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
34822 | Colusa PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 16468SS,16476SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34823 | Colusa PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 16467SS | 16469SS,16477SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34824 | Colusa PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 16468SS | 16478SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34825 | Colusa PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
34826 | Colusa PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 16463 | 16472SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34827 | Colusa PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 16464,16471SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34828 | Colusa PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 16481FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34829 | Colusa PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 16475SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34830 | Colusa PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 16474SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34831 | Colusa PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 16467SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34832 | Colusa PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 16468SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34833 | Colusa PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 16469SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34834 | Colusa PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 16481SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34835 | Colusa PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34836 | Colusa PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 16473FS+12d,16479SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34837 | Contra Costa PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 7.0000000000000007E-2
34838 | Contra Costa PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20999999999999999
34839 | Contra Costa PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
34840 | Contra Costa PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
34841 | Contra Costa PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34842 | Contra Costa PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
34843 | Contra Costa PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
34844 | Contra Costa PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
34845 | Contra Costa PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34846 | Contra Costa PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
34847 | Contra Costa PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
34848 | Contra Costa PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
34849 | Contra Costa PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34850 | Contra Costa PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
34851 | Contra Costa PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34852 | Contra Costa PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34853 | Contra Costa PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
34854 | Contra Costa PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34855 | Contra Costa PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
34856 | Contra Costa PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
34857 | Contra Costa PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
34858 | Contra Costa PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
34859 | Contra Costa PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
34860 | Contra Costa PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
34861 | Contra Costa PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
34862 | Contra Costa PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
34863 | Contra Costa PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34864 | Contra Costa PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
34865 | Contra Costa PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 16511SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
34866 | Contra Costa PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 16510SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
34867 | Contra Costa PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16513SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34868 | Contra Costa PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16512SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34869 | Contra Costa PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
34870 | Contra Costa PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 16516SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
34871 | Contra Costa PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 16515SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
34872 | Contra Costa PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
34873 | Contra Costa PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 16519SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
34874 | Contra Costa PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 16518SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
34875 | Contra Costa PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34876 | Contra Costa PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 16522SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
34877 | Contra Costa PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 16521SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
34878 | Contra Costa PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 16524SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
34879 | Contra Costa PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 16523SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
34880 | Contra Costa PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34881 | Contra Costa PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
34882 | Contra Costa PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34883 | Contra Costa PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
34884 | Contra Costa PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34885 | Contra Costa PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
34886 | Contra Costa PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
34887 | Contra Costa PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 16533FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34888 | Contra Costa PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 16532FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34889 | Contra Costa PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.27000000000000002
34890 | Contra Costa PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 16537FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
34891 | Contra Costa PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34892 | Contra Costa PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 16535FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
34893 | Contra Costa PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | November 20, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 100 | 0d | NA | NA | 0 days? | No | 7/1/25 | 11/20/25 | NA | 1
34894 | Contra Costa PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 16540 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
34895 | Contra Costa PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16539 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34896 | Contra Costa PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34897 | Contra Costa PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applica | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16543FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34898 | Contra Costa PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 16542FS+19d | 16544 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34899 | Contra Costa PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 16543 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
34900 | Contra Costa PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34901 | Contra Costa PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and oper | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 16547 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34902 | Contra Costa PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 16546 | 16548FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34903 | Contra Costa PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 16547FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34904 | Contra Costa PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
34905 | Contra Costa PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34906 | Contra Costa PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34907 | Contra Costa PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34908 | Contra Costa PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16554SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34909 | Contra Costa PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 16553SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
34910 | Contra Costa PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34911 | Contra Costa PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34912 | Contra Costa PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34913 | Contra Costa PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16559SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34914 | Contra Costa PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16558SS | 16573SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34915 | Contra Costa PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34916 | Contra Costa PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34917 | Contra Costa PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34918 | Contra Costa PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34919 | Contra Costa PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 16565SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34920 | Contra Costa PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16564SS | 16566SS,16567 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34921 | Contra Costa PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16565SS | 16567 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34922 | Contra Costa PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 16565,16566 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34923 | Contra Costa PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34924 | Contra Costa PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34925 | Contra Costa PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16571SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34926 | Contra Costa PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 16570SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
34927 | Contra Costa PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34928 | Contra Costa PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16559SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34929 | Contra Costa PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34930 | Contra Costa PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16576SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
34931 | Contra Costa PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16575SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
34932 | Contra Costa PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34933 | Contra Costa PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 16579SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34934 | Contra Costa PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 16578SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
34935 | Contra Costa PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34936 | Contra Costa PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 16582SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34937 | Contra Costa PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16581SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34938 | Contra Costa PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 16584 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34939 | Contra Costa PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 16583 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
34940 | Contra Costa PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
34941 | Contra Costa PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34942 | Contra Costa PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16588SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34943 | Contra Costa PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16587SS | 16589SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34944 | Contra Costa PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16588SS | 16590SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34945 | Contra Costa PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16589SS | 16591SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34946 | Contra Costa PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16590SS | 16592SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34947 | Contra Costa PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16591SS | 16593SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34948 | Contra Costa PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16592SS | 16594SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34949 | Contra Costa PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16593SS | 16595SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34950 | Contra Costa PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16594SS | 16596SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34951 | Contra Costa PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16595SS | 16597SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34952 | Contra Costa PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16596SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
34953 | Contra Costa PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
34954 | Contra Costa PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
34955 | Contra Costa PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.01
34956 | Contra Costa PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 16602SS,16606 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
34957 | Contra Costa PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 16601SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
34958 | Contra Costa PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
34959 | Contra Costa PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16612 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34960 | Contra Costa PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16613 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34961 | Contra Costa PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 16601 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
34962 | Contra Costa PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
34963 | Contra Costa PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 16609SS,16617SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34964 | Contra Costa PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 16608SS | 16610SS,16618SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34965 | Contra Costa PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 16609SS | 16619SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
34966 | Contra Costa PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
34967 | Contra Costa PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 16604 | 16613SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34968 | Contra Costa PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 16605,16612SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
34969 | Contra Costa PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 16622FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34970 | Contra Costa PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 16616SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34971 | Contra Costa PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 16615SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34972 | Contra Costa PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 16608SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34973 | Contra Costa PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 16609SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34974 | Contra Costa PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 16610SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34975 | Contra Costa PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 16622SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34976 | Contra Costa PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34977 | Contra Costa PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 16614FS+12d,16620SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
34978 | Del Norte PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
34979 | Del Norte PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
34980 | Del Norte PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
34981 | Del Norte PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
34982 | Del Norte PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
34983 | Del Norte PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
34984 | Del Norte PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
34985 | Del Norte PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | November 28, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 18 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
34986 | Del Norte PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
34987 | Del Norte PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
34988 | Del Norte PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
34989 | Del Norte PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
34990 | Del Norte PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
34991 | Del Norte PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
34992 | Del Norte PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
34993 | Del Norte PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
34994 | Del Norte PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
34995 | Del Norte PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
34996 | Del Norte PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
34997 | Del Norte PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
34998 | Del Norte PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
34999 | Del Norte PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
35000 | Del Norte PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
35001 | Del Norte PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
35002 | Del Norte PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
35003 | Del Norte PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
35004 | Del Norte PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35005 | Del Norte PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35006 | Del Norte PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 16652SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
35007 | Del Norte PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 16651SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
35008 | Del Norte PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16654SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35009 | Del Norte PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16653SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35010 | Del Norte PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35011 | Del Norte PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 16657SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
35012 | Del Norte PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 16656SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
35013 | Del Norte PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
35014 | Del Norte PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 16660SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
35015 | Del Norte PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 16659SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
35016 | Del Norte PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35017 | Del Norte PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 16663SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
35018 | Del Norte PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 16662SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
35019 | Del Norte PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 16665SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35020 | Del Norte PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 16664SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35021 | Del Norte PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35022 | Del Norte PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35023 | Del Norte PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35024 | Del Norte PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
35025 | Del Norte PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35026 | Del Norte PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35027 | Del Norte PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
35028 | Del Norte PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 16674FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35029 | Del Norte PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 16673FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35030 | Del Norte PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
35031 | Del Norte PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 16678FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
35032 | Del Norte PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35033 | Del Norte PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 16676FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
35034 | Del Norte PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
35035 | Del Norte PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 16681 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
35036 | Del Norte PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16680 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35037 | Del Norte PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35038 | Del Norte PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16684FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35039 | Del Norte PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 16683FS+19d | 16685 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35040 | Del Norte PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 16684 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35041 | Del Norte PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35042 | Del Norte PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 16688 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35043 | Del Norte PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 16687 | 16689FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35044 | Del Norte PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 16688FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35045 | Del Norte PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35046 | Del Norte PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35047 | Del Norte PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35048 | Del Norte PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35049 | Del Norte PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16695SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35050 | Del Norte PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 16694SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35051 | Del Norte PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35052 | Del Norte PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35053 | Del Norte PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35054 | Del Norte PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16700SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35055 | Del Norte PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16699SS | 16714SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35056 | Del Norte PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35057 | Del Norte PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35058 | Del Norte PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35059 | Del Norte PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35060 | Del Norte PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 16706SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35061 | Del Norte PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16705SS | 16707SS,16708 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35062 | Del Norte PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16706SS | 16708 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35063 | Del Norte PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 16706,16707 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35064 | Del Norte PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35065 | Del Norte PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35066 | Del Norte PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16712SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35067 | Del Norte PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 16711SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35068 | Del Norte PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35069 | Del Norte PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16700SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35070 | Del Norte PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35071 | Del Norte PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16717SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35072 | Del Norte PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16716SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35073 | Del Norte PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35074 | Del Norte PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 16720SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35075 | Del Norte PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 16719SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35076 | Del Norte PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35077 | Del Norte PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 16723SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35078 | Del Norte PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16722SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35079 | Del Norte PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 16725 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35080 | Del Norte PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 16724 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35081 | Del Norte PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35082 | Del Norte PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35083 | Del Norte PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16729SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35084 | Del Norte PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16728SS | 16730SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35085 | Del Norte PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16729SS | 16731SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35086 | Del Norte PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16730SS | 16732SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35087 | Del Norte PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16731SS | 16733SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35088 | Del Norte PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16732SS | 16734SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35089 | Del Norte PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16733SS | 16735SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35090 | Del Norte PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16734SS | 16736SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35091 | Del Norte PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16735SS | 16737SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35092 | Del Norte PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16736SS | 16738SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35093 | Del Norte PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16737SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35094 | Del Norte PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
35095 | Del Norte PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
35096 | Del Norte PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35097 | Del Norte PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 16743SS,16747 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35098 | Del Norte PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 16742SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
35099 | Del Norte PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
35100 | Del Norte PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16753 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35101 | Del Norte PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16754 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35102 | Del Norte PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 16742 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35103 | Del Norte PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
35104 | Del Norte PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 16750SS,16758SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35105 | Del Norte PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 16749SS | 16751SS,16759SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35106 | Del Norte PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 16750SS | 16760SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35107 | Del Norte PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
35108 | Del Norte PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 16745 | 16754SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35109 | Del Norte PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 16746,16753SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35110 | Del Norte PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 16763FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35111 | Del Norte PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 16757SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35112 | Del Norte PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 16756SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35113 | Del Norte PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 16749SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35114 | Del Norte PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 16750SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35115 | Del Norte PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 16751SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35116 | Del Norte PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 16763SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35117 | Del Norte PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35118 | Del Norte PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 16755FS+12d,16761SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35119 | El Dorado PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
35120 | El Dorado PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
35121 | El Dorado PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
35122 | El Dorado PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
35123 | El Dorado PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35124 | El Dorado PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
35125 | El Dorado PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
35126 | El Dorado PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35127 | El Dorado PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35128 | El Dorado PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35129 | El Dorado PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35130 | El Dorado PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
35131 | El Dorado PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35132 | El Dorado PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35133 | El Dorado PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35134 | El Dorado PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35135 | El Dorado PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
35136 | El Dorado PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35137 | El Dorado PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
35138 | El Dorado PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
35139 | El Dorado PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
35140 | El Dorado PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
35141 | El Dorado PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
35142 | El Dorado PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
35143 | El Dorado PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
35144 | El Dorado PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
35145 | El Dorado PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35146 | El Dorado PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35147 | El Dorado PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 16793SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
35148 | El Dorado PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 16792SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
35149 | El Dorado PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16795SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35150 | El Dorado PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16794SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35151 | El Dorado PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35152 | El Dorado PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 16798SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
35153 | El Dorado PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 16797SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
35154 | El Dorado PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
35155 | El Dorado PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 16801SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
35156 | El Dorado PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 16800SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
35157 | El Dorado PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35158 | El Dorado PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 16804SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
35159 | El Dorado PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 16803SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
35160 | El Dorado PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 16806SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35161 | El Dorado PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 16805SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35162 | El Dorado PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35163 | El Dorado PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35164 | El Dorado PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35165 | El Dorado PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
35166 | El Dorado PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35167 | El Dorado PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35168 | El Dorado PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
35169 | El Dorado PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 16815FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35170 | El Dorado PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 16814FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35171 | El Dorado PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
35172 | El Dorado PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 16819FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
35173 | El Dorado PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35174 | El Dorado PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 16817FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
35175 | El Dorado PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
35176 | El Dorado PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 16822 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
35177 | El Dorado PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16821 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35178 | El Dorado PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35179 | El Dorado PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16825FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35180 | El Dorado PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 16824FS+19d | 16826 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35181 | El Dorado PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 16825 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35182 | El Dorado PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35183 | El Dorado PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 16829 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35184 | El Dorado PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 16828 | 16830FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35185 | El Dorado PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 16829FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35186 | El Dorado PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35187 | El Dorado PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35188 | El Dorado PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35189 | El Dorado PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35190 | El Dorado PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16836SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35191 | El Dorado PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 16835SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35192 | El Dorado PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35193 | El Dorado PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35194 | El Dorado PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35195 | El Dorado PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16841SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35196 | El Dorado PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16840SS | 16855SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35197 | El Dorado PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35198 | El Dorado PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35199 | El Dorado PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35200 | El Dorado PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35201 | El Dorado PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 16847SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35202 | El Dorado PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16846SS | 16848SS,16849 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35203 | El Dorado PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16847SS | 16849 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35204 | El Dorado PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 16847,16848 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35205 | El Dorado PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35206 | El Dorado PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35207 | El Dorado PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16853SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35208 | El Dorado PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 16852SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35209 | El Dorado PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35210 | El Dorado PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16841SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35211 | El Dorado PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35212 | El Dorado PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16858SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35213 | El Dorado PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16857SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35214 | El Dorado PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35215 | El Dorado PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 16861SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35216 | El Dorado PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 16860SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35217 | El Dorado PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35218 | El Dorado PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 16864SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35219 | El Dorado PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 16863SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35220 | El Dorado PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 16866 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35221 | El Dorado PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 16865 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35222 | El Dorado PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35223 | El Dorado PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35224 | El Dorado PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16870SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35225 | El Dorado PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16869SS | 16871SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35226 | El Dorado PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16870SS | 16872SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35227 | El Dorado PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16871SS | 16873SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35228 | El Dorado PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16872SS | 16874SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35229 | El Dorado PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16873SS | 16875SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35230 | El Dorado PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16874SS | 16876SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35231 | El Dorado PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16875SS | 16877SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35232 | El Dorado PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16876SS | 16878SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35233 | El Dorado PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16877SS | 16879SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35234 | El Dorado PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16878SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35235 | El Dorado PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
35236 | El Dorado PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
35237 | El Dorado PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35238 | El Dorado PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 16884SS,16888 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35239 | El Dorado PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 16883SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
35240 | El Dorado PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
35241 | El Dorado PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16894 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35242 | El Dorado PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16895 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35243 | El Dorado PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 16883 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35244 | El Dorado PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
35245 | El Dorado PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 16891SS,16899SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35246 | El Dorado PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 16890SS | 16892SS,16900SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35247 | El Dorado PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 16891SS | 16901SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35248 | El Dorado PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
35249 | El Dorado PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 16886 | 16895SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35250 | El Dorado PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 16887,16894SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35251 | El Dorado PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 16904FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35252 | El Dorado PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 16898SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35253 | El Dorado PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 16897SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35254 | El Dorado PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 16890SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35255 | El Dorado PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 16891SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35256 | El Dorado PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 16892SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35257 | El Dorado PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 16904SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35258 | El Dorado PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35259 | El Dorado PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 16896FS+12d,16902SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35260 | Fresno PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.11
35261 | Fresno PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
35262 | Fresno PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
35263 | Fresno PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
35264 | Fresno PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35265 | Fresno PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
35266 | Fresno PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
35267 | Fresno PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35268 | Fresno PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35269 | Fresno PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35270 | Fresno PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35271 | Fresno PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
35272 | Fresno PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35273 | Fresno PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35274 | Fresno PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35275 | Fresno PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35276 | Fresno PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
35277 | Fresno PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35278 | Fresno PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
35279 | Fresno PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
35280 | Fresno PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
35281 | Fresno PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
35282 | Fresno PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
35283 | Fresno PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
35284 | Fresno PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
35285 | Fresno PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
35286 | Fresno PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35287 | Fresno PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35288 | Fresno PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 16934SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
35289 | Fresno PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 16933SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
35290 | Fresno PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16936SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35291 | Fresno PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16935SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35292 | Fresno PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 16939SS,16938SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35293 | Fresno PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 16937SS |  | As Soon As Possible | NA | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
35294 | Fresno PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 16937SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
35295 | Fresno PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
35296 | Fresno PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 16942SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
35297 | Fresno PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 16941SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
35298 | Fresno PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
35299 | Fresno PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 16945SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
35300 | Fresno PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 16944SS |  | Start No Earlier Than | 6/1/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
35301 | Fresno PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 16947SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
35302 | Fresno PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 16946SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
35303 | Fresno PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
35304 | Fresno PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
35305 | Fresno PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 211 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35306 | Fresno PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 166 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
35307 | Fresno PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35308 | Fresno PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35309 | Fresno PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
35310 | Fresno PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 44 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35311 | Fresno PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 295 | 277d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.33000000000000002
35312 | Fresno PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 16959FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
35313 | Fresno PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35314 | Fresno PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 16957FS-1d |  | Start No Earlier Than | 9/2/25 | 252 | 277d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.59999999999999998
35315 | Fresno PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
35316 | Fresno PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 16962 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
35317 | Fresno PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16961 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35318 | Fresno PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35319 | Fresno PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16965FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35320 | Fresno PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 16964FS+19d | 16966 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35321 | Fresno PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 16965 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35322 | Fresno PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35323 | Fresno PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 16969 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35324 | Fresno PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 16968 | 16970FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35325 | Fresno PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 16969FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35326 | Fresno PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35327 | Fresno PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35328 | Fresno PR - Technical Activities | October 1, 2025 8:00 AM | June 12, 2026 5:00 PM |  |  | As Soon As Possible | NA | 175 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
35329 | Fresno PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35330 | Fresno PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 16976SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35331 | Fresno PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 16975SS |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35332 | Fresno PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35333 | Fresno PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 16979SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35334 | Fresno PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16978SS | 16980SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35335 | Fresno PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16979SS | 16981SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35336 | Fresno PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16980SS | 16982SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35337 | Fresno PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16981SS | 16983SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35338 | Fresno PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16982SS | 16984SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35339 | Fresno PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16983SS | 16985SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35340 | Fresno PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16984SS | 16986SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35341 | Fresno PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16985SS | 16987SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35342 | Fresno PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16986SS | 16988SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35343 | Fresno PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 16987SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35344 | Fresno PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
35345 | Fresno PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
35346 | Fresno PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35347 | Fresno PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 16993SS,16997 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35348 | Fresno PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 16992SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
35349 | Fresno PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
35350 | Fresno PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17003 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
35351 | Fresno PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17004 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
35352 | Fresno PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 16992 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35353 | Fresno PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
35354 | Fresno PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 17000SS,17008SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35355 | Fresno PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 16999SS | 17001SS,17009SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35356 | Fresno PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 17000SS | 17010SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35357 | Fresno PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
35358 | Fresno PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 16995 | 17004SS | Start No Earlier Than | 5/1/26 | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
35359 | Fresno PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 16996,17003SS |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
35360 | Fresno PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 17013FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
35361 | Fresno PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 17007SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35362 | Fresno PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 17006SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35363 | Fresno PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 16999SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35364 | Fresno PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 17000SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35365 | Fresno PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 17001SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35366 | Fresno PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 17013SS+44d | Start No Earlier Than | 6/1/26 | 44 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
35367 | Fresno PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35368 | Fresno PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 17005FS+12d,17011SS+44d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
35369 | Glenn PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 8.0000000000000002E-2
35370 | Glenn PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
35371 | Glenn PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
35372 | Glenn PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
35373 | Glenn PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35374 | Glenn PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
35375 | Glenn PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
35376 | Glenn PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35377 | Glenn PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35378 | Glenn PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35379 | Glenn PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35380 | Glenn PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
35381 | Glenn PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35382 | Glenn PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35383 | Glenn PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35384 | Glenn PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35385 | Glenn PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
35386 | Glenn PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35387 | Glenn PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
35388 | Glenn PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
35389 | Glenn PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
35390 | Glenn PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
35391 | Glenn PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
35392 | Glenn PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
35393 | Glenn PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
35394 | Glenn PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
35395 | Glenn PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35396 | Glenn PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35397 | Glenn PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 17043SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
35398 | Glenn PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 17042SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
35399 | Glenn PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17045SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35400 | Glenn PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17044SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35401 | Glenn PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35402 | Glenn PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 17048SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
35403 | Glenn PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 17047SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
35404 | Glenn PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
35405 | Glenn PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 17051SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
35406 | Glenn PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 17050SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
35407 | Glenn PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35408 | Glenn PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 17054SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
35409 | Glenn PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 17053SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
35410 | Glenn PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 17056SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35411 | Glenn PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 17055SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35412 | Glenn PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35413 | Glenn PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35414 | Glenn PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35415 | Glenn PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
35416 | Glenn PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35417 | Glenn PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35418 | Glenn PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
35419 | Glenn PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 17065FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35420 | Glenn PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 17064FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35421 | Glenn PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
35422 | Glenn PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 17069FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
35423 | Glenn PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35424 | Glenn PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 17067FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
35425 | Glenn PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
35426 | Glenn PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 17072 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
35427 | Glenn PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17071 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35428 | Glenn PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35429 | Glenn PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17075FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35430 | Glenn PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 17074FS+19d | 17076 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35431 | Glenn PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 17075 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35432 | Glenn PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35433 | Glenn PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 17079 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35434 | Glenn PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 17078 | 17080FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35435 | Glenn PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 17079FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35436 | Glenn PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35437 | Glenn PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35438 | Glenn PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 131 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
35439 | Glenn PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35440 | Glenn PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17086SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35441 | Glenn PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17085SS | 17087SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35442 | Glenn PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17086SS | 17088SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35443 | Glenn PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17087SS | 17089SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35444 | Glenn PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17088SS | 17090SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35445 | Glenn PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17089SS | 17091SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35446 | Glenn PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17090SS | 17092SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35447 | Glenn PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17091SS | 17093SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35448 | Glenn PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17092SS | 17094SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35449 | Glenn PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17093SS | 17095SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35450 | Glenn PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17094SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35451 | Glenn PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
35452 | Glenn PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
35453 | Glenn PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35454 | Glenn PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 17100SS,17104 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35455 | Glenn PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 17099SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
35456 | Glenn PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
35457 | Glenn PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17110 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35458 | Glenn PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17111 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35459 | Glenn PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 17099 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35460 | Glenn PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
35461 | Glenn PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 17107SS,17115SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35462 | Glenn PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 17106SS | 17108SS,17116SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35463 | Glenn PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 17107SS | 17117SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35464 | Glenn PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
35465 | Glenn PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 17102 | 17111SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35466 | Glenn PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 17103,17110SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35467 | Glenn PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 17120FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35468 | Glenn PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 17114SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35469 | Glenn PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 17113SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35470 | Glenn PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17106SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35471 | Glenn PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17107SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35472 | Glenn PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17108SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35473 | Glenn PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 17120SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35474 | Glenn PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35475 | Glenn PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 17112FS+12d,17118SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35476 | Humboldt PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.0000000000000003E-2
35477 | Humboldt PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
35478 | Humboldt PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
35479 | Humboldt PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
35480 | Humboldt PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35481 | Humboldt PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
35482 | Humboldt PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
35483 | Humboldt PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35484 | Humboldt PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35485 | Humboldt PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35486 | Humboldt PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35487 | Humboldt PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
35488 | Humboldt PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35489 | Humboldt PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35490 | Humboldt PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35491 | Humboldt PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35492 | Humboldt PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
35493 | Humboldt PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35494 | Humboldt PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
35495 | Humboldt PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
35496 | Humboldt PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
35497 | Humboldt PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
35498 | Humboldt PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
35499 | Humboldt PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
35500 | Humboldt PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
35501 | Humboldt PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
35502 | Humboldt PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35503 | Humboldt PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35504 | Humboldt PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 17150SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
35505 | Humboldt PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 17149SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
35506 | Humboldt PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17152SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35507 | Humboldt PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17151SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35508 | Humboldt PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35509 | Humboldt PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 17155SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
35510 | Humboldt PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 17154SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
35511 | Humboldt PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
35512 | Humboldt PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 17158SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
35513 | Humboldt PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 17157SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
35514 | Humboldt PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35515 | Humboldt PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 17161SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
35516 | Humboldt PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 17160SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
35517 | Humboldt PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 17163SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35518 | Humboldt PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 17162SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35519 | Humboldt PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35520 | Humboldt PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35521 | Humboldt PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35522 | Humboldt PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
35523 | Humboldt PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35524 | Humboldt PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35525 | Humboldt PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
35526 | Humboldt PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 17172FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35527 | Humboldt PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 17171FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35528 | Humboldt PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.13
35529 | Humboldt PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 17176FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
35530 | Humboldt PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35531 | Humboldt PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 17174FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | NA | NA | NA | 0
35532 | Humboldt PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
35533 | Humboldt PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 17179 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
35534 | Humboldt PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17178 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35535 | Humboldt PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35536 | Humboldt PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17182FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35537 | Humboldt PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 17181FS+19d | 17183 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35538 | Humboldt PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 17182 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35539 | Humboldt PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35540 | Humboldt PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operatio | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 17186 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35541 | Humboldt PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 17185 | 17187FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35542 | Humboldt PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 17186FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35543 | Humboldt PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35544 | Humboldt PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35545 | Humboldt PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35546 | Humboldt PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35547 | Humboldt PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17193SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35548 | Humboldt PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 17192SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35549 | Humboldt PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35550 | Humboldt PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35551 | Humboldt PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35552 | Humboldt PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17198SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35553 | Humboldt PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17197SS | 17212SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35554 | Humboldt PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35555 | Humboldt PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35556 | Humboldt PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35557 | Humboldt PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35558 | Humboldt PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 17204SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35559 | Humboldt PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17203SS | 17205SS,17206 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35560 | Humboldt PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17204SS | 17206 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35561 | Humboldt PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17204,17205 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35562 | Humboldt PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35563 | Humboldt PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35564 | Humboldt PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17210SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35565 | Humboldt PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 17209SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35566 | Humboldt PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35567 | Humboldt PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17198SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35568 | Humboldt PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35569 | Humboldt PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17215SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35570 | Humboldt PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17214SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35571 | Humboldt PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35572 | Humboldt PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 17218SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35573 | Humboldt PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 17217SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35574 | Humboldt PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35575 | Humboldt PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 17221SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35576 | Humboldt PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17220SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35577 | Humboldt PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 17223 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35578 | Humboldt PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17222 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35579 | Humboldt PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35580 | Humboldt PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35581 | Humboldt PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17227SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35582 | Humboldt PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17226SS | 17228SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35583 | Humboldt PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17227SS | 17229SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35584 | Humboldt PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17228SS | 17230SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35585 | Humboldt PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17229SS | 17231SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35586 | Humboldt PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17230SS | 17232SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35587 | Humboldt PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17231SS | 17233SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35588 | Humboldt PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data los | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17232SS | 17234SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35589 | Humboldt PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17233SS | 17235SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35590 | Humboldt PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17234SS | 17236SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35591 | Humboldt PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17235SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35592 | Humboldt PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
35593 | Humboldt PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
35594 | Humboldt PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35595 | Humboldt PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 17241SS,17245 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35596 | Humboldt PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 17240SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
35597 | Humboldt PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
35598 | Humboldt PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17251 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35599 | Humboldt PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17252 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35600 | Humboldt PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 17240 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35601 | Humboldt PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
35602 | Humboldt PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 17248SS,17256SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35603 | Humboldt PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 17247SS | 17249SS,17257SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35604 | Humboldt PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 17248SS | 17258SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35605 | Humboldt PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
35606 | Humboldt PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 17243 | 17252SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35607 | Humboldt PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 17244,17251SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35608 | Humboldt PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 17261FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35609 | Humboldt PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 17255SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35610 | Humboldt PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 17254SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35611 | Humboldt PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17247SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35612 | Humboldt PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17248SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35613 | Humboldt PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17249SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35614 | Humboldt PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 17261SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35615 | Humboldt PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35616 | Humboldt PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 17253FS+12d,17259SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35617 | Imperial PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.0000000000000003E-2
35618 | Imperial PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
35619 | Imperial PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
35620 | Imperial PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
35621 | Imperial PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35622 | Imperial PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
35623 | Imperial PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
35624 | Imperial PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35625 | Imperial PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35626 | Imperial PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35627 | Imperial PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35628 | Imperial PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
35629 | Imperial PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35630 | Imperial PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35631 | Imperial PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35632 | Imperial PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35633 | Imperial PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
35634 | Imperial PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35635 | Imperial PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
35636 | Imperial PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
35637 | Imperial PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
35638 | Imperial PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
35639 | Imperial PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
35640 | Imperial PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
35641 | Imperial PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
35642 | Imperial PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
35643 | Imperial PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35644 | Imperial PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35645 | Imperial PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 17291SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
35646 | Imperial PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 17290SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
35647 | Imperial PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17293SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35648 | Imperial PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17292SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35649 | Imperial PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35650 | Imperial PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 17296SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
35651 | Imperial PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 17295SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
35652 | Imperial PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
35653 | Imperial PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 17299SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
35654 | Imperial PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 17298SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
35655 | Imperial PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35656 | Imperial PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 17302SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
35657 | Imperial PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 17301SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
35658 | Imperial PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 17304SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35659 | Imperial PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 17303SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35660 | Imperial PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35661 | Imperial PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35662 | Imperial PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35663 | Imperial PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
35664 | Imperial PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35665 | Imperial PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35666 | Imperial PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
35667 | Imperial PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 17313FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35668 | Imperial PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 17312FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35669 | Imperial PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.13
35670 | Imperial PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 17317FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
35671 | Imperial PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35672 | Imperial PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 17315FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | NA | NA | NA | 0
35673 | Imperial PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
35674 | Imperial PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 17320 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
35675 | Imperial PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17319 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35676 | Imperial PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35677 | Imperial PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17323FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35678 | Imperial PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 17322FS+19d | 17324 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35679 | Imperial PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 17323 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35680 | Imperial PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35681 | Imperial PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operatio | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 17327 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35682 | Imperial PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 17326 | 17328FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35683 | Imperial PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 17327FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35684 | Imperial PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35685 | Imperial PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35686 | Imperial PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35687 | Imperial PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35688 | Imperial PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17334SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35689 | Imperial PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 17333SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35690 | Imperial PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35691 | Imperial PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35692 | Imperial PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35693 | Imperial PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17339SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35694 | Imperial PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17338SS | 17353SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35695 | Imperial PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35696 | Imperial PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35697 | Imperial PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35698 | Imperial PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35699 | Imperial PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 17345SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35700 | Imperial PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17344SS | 17346SS,17347 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35701 | Imperial PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17345SS | 17347 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35702 | Imperial PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17345,17346 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35703 | Imperial PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35704 | Imperial PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35705 | Imperial PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17351SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35706 | Imperial PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 17350SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35707 | Imperial PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35708 | Imperial PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17339SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35709 | Imperial PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35710 | Imperial PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17356SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35711 | Imperial PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17355SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35712 | Imperial PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35713 | Imperial PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 17359SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35714 | Imperial PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 17358SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35715 | Imperial PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35716 | Imperial PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 17362SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35717 | Imperial PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17361SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35718 | Imperial PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 17364 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35719 | Imperial PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17363 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35720 | Imperial PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35721 | Imperial PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35722 | Imperial PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17368SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35723 | Imperial PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17367SS | 17369SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35724 | Imperial PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17368SS | 17370SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35725 | Imperial PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17369SS | 17371SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35726 | Imperial PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17370SS | 17372SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35727 | Imperial PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17371SS | 17373SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35728 | Imperial PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17372SS | 17374SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35729 | Imperial PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data los | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17373SS | 17375SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35730 | Imperial PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17374SS | 17376SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35731 | Imperial PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17375SS | 17377SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35732 | Imperial PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17376SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35733 | Imperial PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
35734 | Imperial PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
35735 | Imperial PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35736 | Imperial PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 17382SS,17386 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35737 | Imperial PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 17381SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
35738 | Imperial PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
35739 | Imperial PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17392 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35740 | Imperial PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17393 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35741 | Imperial PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 17381 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35742 | Imperial PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
35743 | Imperial PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 17389SS,17397SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35744 | Imperial PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 17388SS | 17390SS,17398SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35745 | Imperial PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 17389SS | 17399SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35746 | Imperial PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
35747 | Imperial PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 17384 | 17393SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35748 | Imperial PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 17385,17392SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35749 | Imperial PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 17402FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35750 | Imperial PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 17396SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35751 | Imperial PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 17395SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35752 | Imperial PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17388SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35753 | Imperial PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17389SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35754 | Imperial PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17390SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35755 | Imperial PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 17402SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35756 | Imperial PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35757 | Imperial PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 17394FS+12d,17400SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35758 | Inyo PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.0000000000000003E-2
35759 | Inyo PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
35760 | Inyo PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
35761 | Inyo PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
35762 | Inyo PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35763 | Inyo PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
35764 | Inyo PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
35765 | Inyo PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35766 | Inyo PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35767 | Inyo PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35768 | Inyo PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35769 | Inyo PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
35770 | Inyo PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35771 | Inyo PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35772 | Inyo PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35773 | Inyo PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35774 | Inyo PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
35775 | Inyo PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35776 | Inyo PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
35777 | Inyo PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
35778 | Inyo PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
35779 | Inyo PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
35780 | Inyo PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
35781 | Inyo PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
35782 | Inyo PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
35783 | Inyo PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
35784 | Inyo PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35785 | Inyo PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35786 | Inyo PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 17432SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
35787 | Inyo PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 17431SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
35788 | Inyo PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17434SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35789 | Inyo PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17433SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35790 | Inyo PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35791 | Inyo PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 17437SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
35792 | Inyo PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 17436SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
35793 | Inyo PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
35794 | Inyo PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 17440SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
35795 | Inyo PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 17439SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
35796 | Inyo PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35797 | Inyo PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 17443SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
35798 | Inyo PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 17442SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
35799 | Inyo PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 17445SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35800 | Inyo PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 17444SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35801 | Inyo PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35802 | Inyo PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35803 | Inyo PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35804 | Inyo PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
35805 | Inyo PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35806 | Inyo PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35807 | Inyo PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
35808 | Inyo PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 17454FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35809 | Inyo PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 17453FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35810 | Inyo PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.13
35811 | Inyo PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 17458FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
35812 | Inyo PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35813 | Inyo PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 17456FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | NA | NA | NA | 0
35814 | Inyo PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
35815 | Inyo PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 17461 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
35816 | Inyo PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17460 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35817 | Inyo PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35818 | Inyo PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17464FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35819 | Inyo PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 17463FS+19d | 17465 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35820 | Inyo PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 17464 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35821 | Inyo PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35822 | Inyo PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 17468 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35823 | Inyo PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 17467 | 17469FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35824 | Inyo PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 17468FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35825 | Inyo PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35826 | Inyo PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35827 | Inyo PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35828 | Inyo PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35829 | Inyo PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17475SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35830 | Inyo PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 17474SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35831 | Inyo PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35832 | Inyo PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35833 | Inyo PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35834 | Inyo PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17480SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35835 | Inyo PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17479SS | 17494SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35836 | Inyo PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35837 | Inyo PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35838 | Inyo PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35839 | Inyo PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35840 | Inyo PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 17486SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35841 | Inyo PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17485SS | 17487SS,17488 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35842 | Inyo PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17486SS | 17488 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35843 | Inyo PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17486,17487 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35844 | Inyo PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35845 | Inyo PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35846 | Inyo PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17492SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35847 | Inyo PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 17491SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35848 | Inyo PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35849 | Inyo PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17480SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35850 | Inyo PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35851 | Inyo PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17497SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35852 | Inyo PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17496SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35853 | Inyo PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35854 | Inyo PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 17500SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35855 | Inyo PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 17499SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35856 | Inyo PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35857 | Inyo PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 17503SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35858 | Inyo PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17502SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35859 | Inyo PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 17505 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35860 | Inyo PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17504 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35861 | Inyo PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35862 | Inyo PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35863 | Inyo PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17509SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35864 | Inyo PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17508SS | 17510SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35865 | Inyo PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17509SS | 17511SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35866 | Inyo PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17510SS | 17512SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35867 | Inyo PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17511SS | 17513SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35868 | Inyo PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17512SS | 17514SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35869 | Inyo PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17513SS | 17515SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35870 | Inyo PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17514SS | 17516SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35871 | Inyo PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17515SS | 17517SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35872 | Inyo PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17516SS | 17518SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35873 | Inyo PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17517SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35874 | Inyo PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
35875 | Inyo PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
35876 | Inyo PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35877 | Inyo PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 17523SS,17527 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35878 | Inyo PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 17522SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
35879 | Inyo PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
35880 | Inyo PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17533 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35881 | Inyo PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17534 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35882 | Inyo PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 17522 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35883 | Inyo PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
35884 | Inyo PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 17530SS,17538SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35885 | Inyo PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 17529SS | 17531SS,17539SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35886 | Inyo PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 17530SS | 17540SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35887 | Inyo PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
35888 | Inyo PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 17525 | 17534SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35889 | Inyo PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 17526,17533SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
35890 | Inyo PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 17543FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35891 | Inyo PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 17537SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35892 | Inyo PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 17536SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35893 | Inyo PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17529SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35894 | Inyo PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17530SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35895 | Inyo PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17531SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35896 | Inyo PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 17543SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35897 | Inyo PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35898 | Inyo PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 17535FS+12d,17541SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
35899 | Kern PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
35900 | Kern PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
35901 | Kern PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
35902 | Kern PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
35903 | Kern PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35904 | Kern PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
35905 | Kern PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
35906 | Kern PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35907 | Kern PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35908 | Kern PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35909 | Kern PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35910 | Kern PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
35911 | Kern PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35912 | Kern PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35913 | Kern PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
35914 | Kern PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
35915 | Kern PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
35916 | Kern PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35917 | Kern PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
35918 | Kern PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
35919 | Kern PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
35920 | Kern PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
35921 | Kern PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
35922 | Kern PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
35923 | Kern PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
35924 | Kern PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
35925 | Kern PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35926 | Kern PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35927 | Kern PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 17573SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
35928 | Kern PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 17572SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
35929 | Kern PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17575SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35930 | Kern PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17574SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35931 | Kern PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35932 | Kern PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 17578SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
35933 | Kern PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 17577SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
35934 | Kern PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
35935 | Kern PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 17581SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
35936 | Kern PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 17580SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
35937 | Kern PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35938 | Kern PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 17584SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
35939 | Kern PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 17583SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
35940 | Kern PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 17586SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35941 | Kern PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 17585SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35942 | Kern PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
35943 | Kern PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
35944 | Kern PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35945 | Kern PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
35946 | Kern PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35947 | Kern PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
35948 | Kern PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
35949 | Kern PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 17595FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35950 | Kern PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 17594FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
35951 | Kern PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
35952 | Kern PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 17599FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
35953 | Kern PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
35954 | Kern PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 17597FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
35955 | Kern PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
35956 | Kern PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 17602 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
35957 | Kern PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17601 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35958 | Kern PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35959 | Kern PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17605FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35960 | Kern PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 17604FS+19d | 17606 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35961 | Kern PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 17605 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
35962 | Kern PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35963 | Kern PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 17609 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35964 | Kern PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 17608 | 17610FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35965 | Kern PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 17609FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
35966 | Kern PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
35967 | Kern PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
35968 | Kern PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35969 | Kern PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35970 | Kern PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17616SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35971 | Kern PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 17615SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35972 | Kern PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35973 | Kern PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35974 | Kern PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35975 | Kern PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17621SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35976 | Kern PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17620SS | 17635SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35977 | Kern PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35978 | Kern PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
35979 | Kern PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35980 | Kern PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35981 | Kern PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 17627SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35982 | Kern PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17626SS | 17628SS,17629 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35983 | Kern PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17627SS | 17629 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35984 | Kern PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17627,17628 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
35985 | Kern PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35986 | Kern PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35987 | Kern PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17633SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35988 | Kern PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 17632SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
35989 | Kern PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35990 | Kern PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17621SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35991 | Kern PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35992 | Kern PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17638SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
35993 | Kern PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17637SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
35994 | Kern PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35995 | Kern PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 17641SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35996 | Kern PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 17640SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
35997 | Kern PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
35998 | Kern PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 17644SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
35999 | Kern PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17643SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36000 | Kern PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 17646 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36001 | Kern PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17645 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36002 | Kern PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36003 | Kern PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36004 | Kern PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17650SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36005 | Kern PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17649SS | 17651SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36006 | Kern PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17650SS | 17652SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36007 | Kern PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17651SS | 17653SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36008 | Kern PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17652SS | 17654SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36009 | Kern PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17653SS | 17655SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36010 | Kern PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17654SS | 17656SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36011 | Kern PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17655SS | 17657SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36012 | Kern PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17656SS | 17658SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36013 | Kern PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17657SS | 17659SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36014 | Kern PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17658SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36015 | Kern PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
36016 | Kern PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
36017 | Kern PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36018 | Kern PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 17664SS,17668 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36019 | Kern PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 17663SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
36020 | Kern PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
36021 | Kern PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17674 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36022 | Kern PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17675 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36023 | Kern PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 17663 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36024 | Kern PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
36025 | Kern PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 17671SS,17679SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36026 | Kern PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 17670SS | 17672SS,17680SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36027 | Kern PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 17671SS | 17681SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36028 | Kern PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
36029 | Kern PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 17666 | 17675SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36030 | Kern PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 17667,17674SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36031 | Kern PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 17684FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36032 | Kern PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 17678SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36033 | Kern PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 17677SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36034 | Kern PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17670SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36035 | Kern PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17671SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36036 | Kern PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17672SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36037 | Kern PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 17684SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36038 | Kern PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36039 | Kern PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 17676FS+12d,17682SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36040 | Kings PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 7.0000000000000007E-2
36041 | Kings PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.22
36042 | Kings PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.26000000000000001
36043 | Kings PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
36044 | Kings PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36045 | Kings PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
36046 | Kings PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
36047 | Kings PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36048 | Kings PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
36049 | Kings PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36050 | Kings PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36051 | Kings PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
36052 | Kings PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36053 | Kings PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36054 | Kings PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36055 | Kings PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36056 | Kings PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
36057 | Kings PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36058 | Kings PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
36059 | Kings PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
36060 | Kings PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
36061 | Kings PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
36062 | Kings PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
36063 | Kings PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
36064 | Kings PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
36065 | Kings PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
36066 | Kings PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36067 | Kings PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
36068 | Kings PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 17714SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
36069 | Kings PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 17713SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
36070 | Kings PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17716SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36071 | Kings PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17715SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36072 | Kings PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 17719SS,17718SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36073 | Kings PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 17717SS |  | As Soon As Possible | NA | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
36074 | Kings PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 17717SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
36075 | Kings PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
36076 | Kings PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 17722SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
36077 | Kings PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 17721SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
36078 | Kings PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
36079 | Kings PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 17725SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
36080 | Kings PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 17724SS |  | Start No Earlier Than | 6/1/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
36081 | Kings PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 17727SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
36082 | Kings PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 17726SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
36083 | Kings PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
36084 | Kings PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
36085 | Kings PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 211 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36086 | Kings PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 166 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
36087 | Kings PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36088 | Kings PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36089 | Kings PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
36090 | Kings PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 44 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36091 | Kings PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 295 | 277d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
36092 | Kings PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 17739FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
36093 | Kings PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36094 | Kings PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 17737FS-1d |  | Start No Earlier Than | 9/2/25 | 252 | 277d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
36095 | Kings PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
36096 | Kings PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 17742 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
36097 | Kings PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17741 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
36098 | Kings PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36099 | Kings PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17745FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
36100 | Kings PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 17744FS+19d | 17746 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36101 | Kings PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 17745 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36102 | Kings PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36103 | Kings PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 17749 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36104 | Kings PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 17748 | 17750FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36105 | Kings PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 17749FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36106 | Kings PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36107 | Kings PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36108 | Kings PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0
36109 | Kings PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36110 | Kings PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17756SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36111 | Kings PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 17755SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36112 | Kings PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36113 | Kings PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
36114 | Kings PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36115 | Kings PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17761SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36116 | Kings PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17760SS | 17775SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36117 | Kings PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36118 | Kings PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
36119 | Kings PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36120 | Kings PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36121 | Kings PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 17767SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36122 | Kings PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17766SS | 17768SS,17769 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36123 | Kings PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17767SS | 17769 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36124 | Kings PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17767,17768 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36125 | Kings PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36126 | Kings PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36127 | Kings PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17773SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36128 | Kings PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 17772SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36129 | Kings PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36130 | Kings PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17761SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36131 | Kings PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36132 | Kings PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17778SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36133 | Kings PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17777SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36134 | Kings PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36135 | Kings PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 17781SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36136 | Kings PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 17780SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36137 | Kings PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36138 | Kings PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 17784SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36139 | Kings PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17783SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36140 | Kings PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 17786 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36141 | Kings PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17785 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36142 | Kings PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36143 | Kings PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36144 | Kings PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17790SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36145 | Kings PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17789SS | 17791SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36146 | Kings PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17790SS | 17792SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36147 | Kings PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17791SS | 17793SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36148 | Kings PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17792SS | 17794SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36149 | Kings PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17793SS | 17795SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36150 | Kings PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17794SS | 17796SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36151 | Kings PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17795SS | 17797SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36152 | Kings PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17796SS | 17798SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36153 | Kings PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17797SS | 17799SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36154 | Kings PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17798SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36155 | Kings PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
36156 | Kings PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
36157 | Kings PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36158 | Kings PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 17804SS,17808 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36159 | Kings PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 17803SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
36160 | Kings PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
36161 | Kings PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17814 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
36162 | Kings PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17815 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
36163 | Kings PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 17803 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36164 | Kings PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
36165 | Kings PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 17811SS,17819SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36166 | Kings PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 17810SS | 17812SS,17820SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36167 | Kings PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 17811SS | 17821SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36168 | Kings PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
36169 | Kings PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 17806 | 17815SS | Start No Earlier Than | 5/1/26 | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
36170 | Kings PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 17807,17814SS |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
36171 | Kings PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 17824FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
36172 | Kings PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 17818SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36173 | Kings PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 17817SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36174 | Kings PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 17810SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36175 | Kings PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 17811SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36176 | Kings PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 17812SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36177 | Kings PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 17824SS+44d | Start No Earlier Than | 6/1/26 | 44 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
36178 | Kings PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36179 | Kings PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 17816FS+12d,17822SS+44d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
36180 | Lake PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
36181 | Lake PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
36182 | Lake PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
36183 | Lake PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
36184 | Lake PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36185 | Lake PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
36186 | Lake PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
36187 | Lake PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36188 | Lake PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
36189 | Lake PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36190 | Lake PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36191 | Lake PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
36192 | Lake PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36193 | Lake PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36194 | Lake PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36195 | Lake PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36196 | Lake PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
36197 | Lake PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36198 | Lake PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
36199 | Lake PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
36200 | Lake PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
36201 | Lake PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
36202 | Lake PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
36203 | Lake PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
36204 | Lake PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
36205 | Lake PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
36206 | Lake PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36207 | Lake PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
36208 | Lake PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 17854SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
36209 | Lake PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 17853SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
36210 | Lake PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17856SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36211 | Lake PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17855SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36212 | Lake PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36213 | Lake PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 17859SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
36214 | Lake PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 17858SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
36215 | Lake PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
36216 | Lake PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 17862SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
36217 | Lake PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 17861SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
36218 | Lake PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36219 | Lake PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 17865SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
36220 | Lake PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 17864SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
36221 | Lake PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 17867SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36222 | Lake PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 17866SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36223 | Lake PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36224 | Lake PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36225 | Lake PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36226 | Lake PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
36227 | Lake PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36228 | Lake PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36229 | Lake PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
36230 | Lake PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 17876FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36231 | Lake PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 17875FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36232 | Lake PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
36233 | Lake PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 17880FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
36234 | Lake PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36235 | Lake PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 17878FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
36236 | Lake PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
36237 | Lake PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 17883 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
36238 | Lake PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17882 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36239 | Lake PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36240 | Lake PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17886FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36241 | Lake PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 17885FS+19d | 17887 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36242 | Lake PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 17886 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36243 | Lake PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36244 | Lake PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 17890 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36245 | Lake PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 17889 | 17891FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36246 | Lake PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 17890FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36247 | Lake PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36248 | Lake PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36249 | Lake PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36250 | Lake PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36251 | Lake PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17897SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36252 | Lake PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 17896SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36253 | Lake PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36254 | Lake PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36255 | Lake PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36256 | Lake PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17902SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36257 | Lake PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17901SS | 17916SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36258 | Lake PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36259 | Lake PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
36260 | Lake PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36261 | Lake PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36262 | Lake PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 17908SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36263 | Lake PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17907SS | 17909SS,17910 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36264 | Lake PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17908SS | 17910 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36265 | Lake PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17908,17909 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36266 | Lake PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36267 | Lake PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36268 | Lake PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17914SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36269 | Lake PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 17913SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36270 | Lake PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36271 | Lake PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17902SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36272 | Lake PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36273 | Lake PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 17919SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36274 | Lake PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 17918SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36275 | Lake PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36276 | Lake PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 17922SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36277 | Lake PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 17921SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36278 | Lake PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36279 | Lake PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 17925SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36280 | Lake PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 17924SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36281 | Lake PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 17927 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36282 | Lake PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 17926 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36283 | Lake PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36284 | Lake PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36285 | Lake PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17931SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36286 | Lake PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17930SS | 17932SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36287 | Lake PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17931SS | 17933SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36288 | Lake PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17932SS | 17934SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36289 | Lake PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17933SS | 17935SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36290 | Lake PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17934SS | 17936SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36291 | Lake PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17935SS | 17937SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36292 | Lake PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17936SS | 17938SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36293 | Lake PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17937SS | 17939SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36294 | Lake PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17938SS | 17940SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36295 | Lake PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17939SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36296 | Lake PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
36297 | Lake PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
36298 | Lake PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36299 | Lake PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 17945SS,17949 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36300 | Lake PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 17944SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
36301 | Lake PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
36302 | Lake PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17955 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36303 | Lake PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17956 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36304 | Lake PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 17944 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36305 | Lake PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
36306 | Lake PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 17952SS,17960SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36307 | Lake PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 17951SS | 17953SS,17961SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36308 | Lake PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 17952SS | 17962SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36309 | Lake PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
36310 | Lake PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 17947 | 17956SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36311 | Lake PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 17948,17955SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36312 | Lake PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 17965FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36313 | Lake PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 17959SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36314 | Lake PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 17958SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36315 | Lake PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17951SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36316 | Lake PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17952SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36317 | Lake PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 17953SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36318 | Lake PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 17965SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36319 | Lake PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36320 | Lake PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 17957FS+12d,17963SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36321 | Lassen PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
36322 | Lassen PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.22
36323 | Lassen PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.26000000000000001
36324 | Lassen PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
36325 | Lassen PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36326 | Lassen PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
36327 | Lassen PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
36328 | Lassen PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36329 | Lassen PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
36330 | Lassen PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36331 | Lassen PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36332 | Lassen PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
36333 | Lassen PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36334 | Lassen PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36335 | Lassen PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36336 | Lassen PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36337 | Lassen PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
36338 | Lassen PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36339 | Lassen PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
36340 | Lassen PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
36341 | Lassen PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
36342 | Lassen PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
36343 | Lassen PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
36344 | Lassen PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
36345 | Lassen PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
36346 | Lassen PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
36347 | Lassen PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36348 | Lassen PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
36349 | Lassen PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 17995SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
36350 | Lassen PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 17994SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
36351 | Lassen PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 17997SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36352 | Lassen PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 17996SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36353 | Lassen PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36354 | Lassen PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 18000SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
36355 | Lassen PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 17999SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
36356 | Lassen PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
36357 | Lassen PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 18003SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
36358 | Lassen PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 18002SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
36359 | Lassen PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36360 | Lassen PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 18006SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
36361 | Lassen PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 18005SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
36362 | Lassen PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 18008SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36363 | Lassen PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 18007SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36364 | Lassen PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36365 | Lassen PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36366 | Lassen PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36367 | Lassen PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
36368 | Lassen PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36369 | Lassen PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36370 | Lassen PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
36371 | Lassen PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 18017FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36372 | Lassen PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 18016FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36373 | Lassen PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.14999999999999999
36374 | Lassen PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36375 | Lassen PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM |  |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
36376 | Lassen PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
36377 | Lassen PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 18023 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
36378 | Lassen PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18022 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36379 | Lassen PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36380 | Lassen PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18026FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36381 | Lassen PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 18025FS+19d | 18027 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36382 | Lassen PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 18026 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36383 | Lassen PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36384 | Lassen PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 18030 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36385 | Lassen PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 18029 | 18031FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36386 | Lassen PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 18030FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36387 | Lassen PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36388 | Lassen PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36389 | Lassen PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36390 | Lassen PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36391 | Lassen PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18037SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36392 | Lassen PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 18036SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36393 | Lassen PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36394 | Lassen PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36395 | Lassen PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36396 | Lassen PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18042SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36397 | Lassen PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18041SS | 18056SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36398 | Lassen PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36399 | Lassen PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
36400 | Lassen PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36401 | Lassen PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36402 | Lassen PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 18048SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36403 | Lassen PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18047SS | 18049SS,18050 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36404 | Lassen PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18048SS | 18050 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36405 | Lassen PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 18048,18049 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36406 | Lassen PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36407 | Lassen PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36408 | Lassen PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18054SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36409 | Lassen PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 18053SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36410 | Lassen PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36411 | Lassen PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18042SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36412 | Lassen PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36413 | Lassen PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18059SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36414 | Lassen PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18058SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36415 | Lassen PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36416 | Lassen PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 18062SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36417 | Lassen PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 18061SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36418 | Lassen PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36419 | Lassen PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 18065SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36420 | Lassen PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18064SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36421 | Lassen PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 18067 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36422 | Lassen PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 18066 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36423 | Lassen PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36424 | Lassen PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36425 | Lassen PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18071SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36426 | Lassen PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18070SS | 18072SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36427 | Lassen PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18071SS | 18073SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36428 | Lassen PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18072SS | 18074SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36429 | Lassen PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18073SS | 18075SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36430 | Lassen PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18074SS | 18076SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36431 | Lassen PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18075SS | 18077SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36432 | Lassen PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18076SS | 18078SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36433 | Lassen PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18077SS | 18079SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36434 | Lassen PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18078SS | 18080SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36435 | Lassen PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18079SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36436 | Lassen PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
36437 | Lassen PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
36438 | Lassen PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36439 | Lassen PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 18085SS,18089 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36440 | Lassen PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 18084SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
36441 | Lassen PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
36442 | Lassen PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18095 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36443 | Lassen PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18096 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36444 | Lassen PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 18084 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36445 | Lassen PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
36446 | Lassen PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 18092SS,18100SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36447 | Lassen PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 18091SS | 18093SS,18101SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36448 | Lassen PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 18092SS | 18102SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36449 | Lassen PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
36450 | Lassen PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 18087 | 18096SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36451 | Lassen PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 18088,18095SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36452 | Lassen PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 18105FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36453 | Lassen PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 18099SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36454 | Lassen PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 18098SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36455 | Lassen PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18091SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36456 | Lassen PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18092SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36457 | Lassen PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18093SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36458 | Lassen PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 18105SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36459 | Lassen PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36460 | Lassen PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 18097FS+12d,18103SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36461 | Los Angeles PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 7.0000000000000007E-2
36462 | Los Angeles PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.22
36463 | Los Angeles PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.26000000000000001
36464 | Los Angeles PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
36465 | Los Angeles PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36466 | Los Angeles PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
36467 | Los Angeles PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
36468 | Los Angeles PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36469 | Los Angeles PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
36470 | Los Angeles PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36471 | Los Angeles PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36472 | Los Angeles PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
36473 | Los Angeles PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36474 | Los Angeles PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36475 | Los Angeles PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36476 | Los Angeles PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36477 | Los Angeles PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
36478 | Los Angeles PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36479 | Los Angeles PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
36480 | Los Angeles PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
36481 | Los Angeles PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
36482 | Los Angeles PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
36483 | Los Angeles PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
36484 | Los Angeles PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
36485 | Los Angeles PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
36486 | Los Angeles PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
36487 | Los Angeles PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36488 | Los Angeles PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
36489 | Los Angeles PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 18135SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
36490 | Los Angeles PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 18134SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
36491 | Los Angeles PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18137SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36492 | Los Angeles PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18136SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36493 | Los Angeles PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36494 | Los Angeles PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 18140SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
36495 | Los Angeles PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 18139SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
36496 | Los Angeles PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
36497 | Los Angeles PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 18143SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
36498 | Los Angeles PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 18142SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
36499 | Los Angeles PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36500 | Los Angeles PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 18146SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
36501 | Los Angeles PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 18145SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
36502 | Los Angeles PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 18148SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36503 | Los Angeles PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 18147SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36504 | Los Angeles PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36505 | Los Angeles PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36506 | Los Angeles PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36507 | Los Angeles PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
36508 | Los Angeles PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36509 | Los Angeles PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36510 | Los Angeles PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
36511 | Los Angeles PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 18157FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36512 | Los Angeles PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 18156FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36513 | Los Angeles PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
36514 | Los Angeles PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 18161FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
36515 | Los Angeles PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36516 | Los Angeles PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 18159FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
36517 | Los Angeles PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
36518 | Los Angeles PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 18164 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
36519 | Los Angeles PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18163 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
36520 | Los Angeles PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36521 | Los Angeles PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicab | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18167FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
36522 | Los Angeles PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 18166FS+19d | 18168 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36523 | Los Angeles PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 18167 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36524 | Los Angeles PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36525 | Los Angeles PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and opera | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 18171 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36526 | Los Angeles PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 18170 | 18172FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36527 | Los Angeles PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 18171FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36528 | Los Angeles PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36529 | Los Angeles PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36530 | Los Angeles PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36531 | Los Angeles PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36532 | Los Angeles PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18178SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36533 | Los Angeles PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 18177SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36534 | Los Angeles PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36535 | Los Angeles PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36536 | Los Angeles PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36537 | Los Angeles PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18183SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36538 | Los Angeles PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18182SS | 18197SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36539 | Los Angeles PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36540 | Los Angeles PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
36541 | Los Angeles PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36542 | Los Angeles PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36543 | Los Angeles PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 18189SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36544 | Los Angeles PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18188SS | 18190SS,18191 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36545 | Los Angeles PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18189SS | 18191 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36546 | Los Angeles PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 18189,18190 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36547 | Los Angeles PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36548 | Los Angeles PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36549 | Los Angeles PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18195SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36550 | Los Angeles PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 18194SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36551 | Los Angeles PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36552 | Los Angeles PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18183SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36553 | Los Angeles PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36554 | Los Angeles PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18200SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36555 | Los Angeles PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18199SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36556 | Los Angeles PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36557 | Los Angeles PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 18203SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36558 | Los Angeles PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 18202SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36559 | Los Angeles PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36560 | Los Angeles PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 18206SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36561 | Los Angeles PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18205SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36562 | Los Angeles PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 18208 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36563 | Los Angeles PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 18207 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36564 | Los Angeles PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36565 | Los Angeles PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36566 | Los Angeles PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18212SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36567 | Los Angeles PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18211SS | 18213SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36568 | Los Angeles PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18212SS | 18214SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36569 | Los Angeles PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18213SS | 18215SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36570 | Los Angeles PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18214SS | 18216SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36571 | Los Angeles PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18215SS | 18217SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36572 | Los Angeles PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18216SS | 18218SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36573 | Los Angeles PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18217SS | 18219SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36574 | Los Angeles PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18218SS | 18220SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36575 | Los Angeles PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18219SS | 18221SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36576 | Los Angeles PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18220SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36577 | Los Angeles PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
36578 | Los Angeles PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
36579 | Los Angeles PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36580 | Los Angeles PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 18226SS,18230 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36581 | Los Angeles PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 18225SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
36582 | Los Angeles PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
36583 | Los Angeles PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18236 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36584 | Los Angeles PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18237 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36585 | Los Angeles PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 18225 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36586 | Los Angeles PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
36587 | Los Angeles PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 18233SS,18241SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36588 | Los Angeles PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 18232SS | 18234SS,18242SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36589 | Los Angeles PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 18233SS | 18243SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36590 | Los Angeles PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
36591 | Los Angeles PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 18228 | 18237SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36592 | Los Angeles PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 18229,18236SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36593 | Los Angeles PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 18246FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36594 | Los Angeles PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 18240SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36595 | Los Angeles PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 18239SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36596 | Los Angeles PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18232SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36597 | Los Angeles PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18233SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36598 | Los Angeles PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18234SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36599 | Los Angeles PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 18246SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36600 | Los Angeles PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36601 | Los Angeles PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 18238FS+12d,18244SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36602 | Madera PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.0000000000000003E-2
36603 | Madera PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
36604 | Madera PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
36605 | Madera PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
36606 | Madera PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36607 | Madera PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
36608 | Madera PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
36609 | Madera PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36610 | Madera PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
36611 | Madera PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36612 | Madera PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36613 | Madera PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
36614 | Madera PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36615 | Madera PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36616 | Madera PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36617 | Madera PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36618 | Madera PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
36619 | Madera PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36620 | Madera PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
36621 | Madera PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
36622 | Madera PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
36623 | Madera PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
36624 | Madera PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
36625 | Madera PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
36626 | Madera PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
36627 | Madera PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
36628 | Madera PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36629 | Madera PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
36630 | Madera PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 18276SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
36631 | Madera PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 18275SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
36632 | Madera PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18278SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36633 | Madera PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18277SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36634 | Madera PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36635 | Madera PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 18281SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
36636 | Madera PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 18280SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
36637 | Madera PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
36638 | Madera PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 18284SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
36639 | Madera PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 18283SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
36640 | Madera PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36641 | Madera PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 18287SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
36642 | Madera PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 18286SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
36643 | Madera PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 18289SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36644 | Madera PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 18288SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36645 | Madera PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36646 | Madera PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36647 | Madera PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36648 | Madera PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
36649 | Madera PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36650 | Madera PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36651 | Madera PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
36652 | Madera PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 18298FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36653 | Madera PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 18297FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36654 | Madera PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.14999999999999999
36655 | Madera PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 18302FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
36656 | Madera PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36657 | Madera PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 18300FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | NA | NA | NA | 0
36658 | Madera PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
36659 | Madera PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 18305 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
36660 | Madera PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18304 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36661 | Madera PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36662 | Madera PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  | 18308FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/30/25 | NA | 1
36663 | Madera PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 18307FS+19d | 18309 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36664 | Madera PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 18308 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36665 | Madera PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36666 | Madera PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 18312 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36667 | Madera PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 18311 | 18313FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36668 | Madera PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 18312FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36669 | Madera PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36670 | Madera PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36671 | Madera PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36672 | Madera PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36673 | Madera PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18319SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36674 | Madera PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 18318SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36675 | Madera PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36676 | Madera PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36677 | Madera PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36678 | Madera PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18324SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36679 | Madera PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18323SS | 18338SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36680 | Madera PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36681 | Madera PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
36682 | Madera PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36683 | Madera PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36684 | Madera PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 18330SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36685 | Madera PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18329SS | 18331SS,18332 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36686 | Madera PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18330SS | 18332 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36687 | Madera PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 18330,18331 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36688 | Madera PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36689 | Madera PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36690 | Madera PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18336SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36691 | Madera PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 18335SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36692 | Madera PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36693 | Madera PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18324SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36694 | Madera PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36695 | Madera PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18341SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36696 | Madera PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18340SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36697 | Madera PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36698 | Madera PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 18344SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36699 | Madera PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 18343SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36700 | Madera PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36701 | Madera PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 18347SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36702 | Madera PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18346SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36703 | Madera PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 18349 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36704 | Madera PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 18348 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36705 | Madera PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36706 | Madera PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36707 | Madera PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18353SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36708 | Madera PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18352SS | 18354SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36709 | Madera PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18353SS | 18355SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36710 | Madera PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18354SS | 18356SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36711 | Madera PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18355SS | 18357SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36712 | Madera PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18356SS | 18358SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36713 | Madera PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18357SS | 18359SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36714 | Madera PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18358SS | 18360SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36715 | Madera PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18359SS | 18361SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36716 | Madera PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18360SS | 18362SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36717 | Madera PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18361SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36718 | Madera PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
36719 | Madera PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
36720 | Madera PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36721 | Madera PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 18367SS,18371 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36722 | Madera PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 18366SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
36723 | Madera PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
36724 | Madera PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18377 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36725 | Madera PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18378 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36726 | Madera PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 18366 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36727 | Madera PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
36728 | Madera PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 18374SS,18382SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36729 | Madera PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 18373SS | 18375SS,18383SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36730 | Madera PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 18374SS | 18384SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36731 | Madera PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
36732 | Madera PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 18369 | 18378SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36733 | Madera PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 18370,18377SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36734 | Madera PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 18387FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36735 | Madera PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 18381SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36736 | Madera PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 18380SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36737 | Madera PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18373SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36738 | Madera PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18374SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36739 | Madera PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18375SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36740 | Madera PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 18387SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36741 | Madera PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36742 | Madera PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 18379FS+12d,18385SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36743 | Marin PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
36744 | Marin PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
36745 | Marin PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
36746 | Marin PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
36747 | Marin PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36748 | Marin PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
36749 | Marin PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
36750 | Marin PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36751 | Marin PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
36752 | Marin PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36753 | Marin PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36754 | Marin PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
36755 | Marin PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36756 | Marin PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36757 | Marin PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36758 | Marin PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36759 | Marin PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
36760 | Marin PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36761 | Marin PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
36762 | Marin PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
36763 | Marin PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
36764 | Marin PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
36765 | Marin PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
36766 | Marin PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
36767 | Marin PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
36768 | Marin PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
36769 | Marin PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36770 | Marin PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
36771 | Marin PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 18417SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
36772 | Marin PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 18416SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
36773 | Marin PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18419SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36774 | Marin PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18418SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36775 | Marin PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36776 | Marin PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 18422SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
36777 | Marin PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 18421SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
36778 | Marin PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
36779 | Marin PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 18425SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
36780 | Marin PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 18424SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
36781 | Marin PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36782 | Marin PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 18428SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
36783 | Marin PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 18427SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
36784 | Marin PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 18430SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36785 | Marin PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 18429SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36786 | Marin PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36787 | Marin PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36788 | Marin PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36789 | Marin PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
36790 | Marin PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36791 | Marin PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36792 | Marin PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
36793 | Marin PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 18439FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36794 | Marin PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 18438FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36795 | Marin PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
36796 | Marin PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 18443FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
36797 | Marin PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36798 | Marin PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 18441FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
36799 | Marin PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
36800 | Marin PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 18446 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
36801 | Marin PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18445 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
36802 | Marin PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36803 | Marin PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18449FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36804 | Marin PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 18448FS+19d | 18450 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36805 | Marin PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 18449 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36806 | Marin PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36807 | Marin PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 18453 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36808 | Marin PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 18452 | 18454FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36809 | Marin PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 18453FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36810 | Marin PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36811 | Marin PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36812 | Marin PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36813 | Marin PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36814 | Marin PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18460SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36815 | Marin PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 18459SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36816 | Marin PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36817 | Marin PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36818 | Marin PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36819 | Marin PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18465SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36820 | Marin PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18464SS | 18479SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36821 | Marin PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36822 | Marin PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
36823 | Marin PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36824 | Marin PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36825 | Marin PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 18471SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36826 | Marin PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18470SS | 18472SS,18473 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36827 | Marin PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18471SS | 18473 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36828 | Marin PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 18471,18472 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36829 | Marin PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36830 | Marin PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36831 | Marin PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18477SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36832 | Marin PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 18476SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36833 | Marin PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36834 | Marin PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18465SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36835 | Marin PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36836 | Marin PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18482SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
36837 | Marin PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18481SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36838 | Marin PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36839 | Marin PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 18485SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36840 | Marin PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 18484SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
36841 | Marin PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36842 | Marin PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 18488SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36843 | Marin PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18487SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36844 | Marin PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 18490 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36845 | Marin PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 18489 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
36846 | Marin PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
36847 | Marin PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36848 | Marin PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18494SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36849 | Marin PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18493SS | 18495SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36850 | Marin PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18494SS | 18496SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36851 | Marin PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18495SS | 18497SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36852 | Marin PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18496SS | 18498SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36853 | Marin PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18497SS | 18499SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36854 | Marin PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18498SS | 18500SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36855 | Marin PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18499SS | 18501SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36856 | Marin PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18500SS | 18502SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36857 | Marin PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18501SS | 18503SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36858 | Marin PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18502SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36859 | Marin PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
36860 | Marin PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
36861 | Marin PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36862 | Marin PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 18508SS,18512 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36863 | Marin PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 18507SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
36864 | Marin PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
36865 | Marin PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18518 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36866 | Marin PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18519 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36867 | Marin PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 18507 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36868 | Marin PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
36869 | Marin PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 18515SS,18523SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36870 | Marin PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 18514SS | 18516SS,18524SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36871 | Marin PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 18515SS | 18525SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36872 | Marin PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
36873 | Marin PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 18510 | 18519SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36874 | Marin PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 18511,18518SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36875 | Marin PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 18528FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36876 | Marin PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 18522SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36877 | Marin PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 18521SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36878 | Marin PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18514SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36879 | Marin PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18515SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36880 | Marin PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18516SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36881 | Marin PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 18528SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36882 | Marin PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36883 | Marin PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 18520FS+12d,18526SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36884 | Mariposa PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 8.0000000000000002E-2
36885 | Mariposa PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
36886 | Mariposa PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
36887 | Mariposa PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
36888 | Mariposa PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36889 | Mariposa PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
36890 | Mariposa PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
36891 | Mariposa PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36892 | Mariposa PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
36893 | Mariposa PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
36894 | Mariposa PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36895 | Mariposa PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
36896 | Mariposa PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36897 | Mariposa PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36898 | Mariposa PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36899 | Mariposa PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36900 | Mariposa PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
36901 | Mariposa PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36902 | Mariposa PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
36903 | Mariposa PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
36904 | Mariposa PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
36905 | Mariposa PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
36906 | Mariposa PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
36907 | Mariposa PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
36908 | Mariposa PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
36909 | Mariposa PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
36910 | Mariposa PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36911 | Mariposa PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
36912 | Mariposa PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 18558SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
36913 | Mariposa PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 18557SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
36914 | Mariposa PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18560SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36915 | Mariposa PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18559SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36916 | Mariposa PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36917 | Mariposa PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 18563SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
36918 | Mariposa PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 18562SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
36919 | Mariposa PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
36920 | Mariposa PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 18566SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
36921 | Mariposa PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 18565SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
36922 | Mariposa PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36923 | Mariposa PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 18569SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
36924 | Mariposa PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 18568SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
36925 | Mariposa PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 18571SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36926 | Mariposa PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 18570SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36927 | Mariposa PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
36928 | Mariposa PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
36929 | Mariposa PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36930 | Mariposa PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
36931 | Mariposa PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36932 | Mariposa PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
36933 | Mariposa PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
36934 | Mariposa PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 18580FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36935 | Mariposa PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 18579FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36936 | Mariposa PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.22
36937 | Mariposa PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 18584FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
36938 | Mariposa PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36939 | Mariposa PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 18582FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
36940 | Mariposa PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
36941 | Mariposa PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 18587 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
36942 | Mariposa PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18586 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36943 | Mariposa PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36944 | Mariposa PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18590FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
36945 | Mariposa PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 18589FS+19d | 18591 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36946 | Mariposa PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 18590 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
36947 | Mariposa PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36948 | Mariposa PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operatio | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 18594 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36949 | Mariposa PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 18593 | 18595FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36950 | Mariposa PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 18594FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
36951 | Mariposa PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
36952 | Mariposa PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36953 | Mariposa PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 131 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
36954 | Mariposa PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36955 | Mariposa PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18601SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36956 | Mariposa PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18600SS | 18602SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36957 | Mariposa PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18601SS | 18603SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36958 | Mariposa PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18602SS | 18604SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36959 | Mariposa PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18603SS | 18605SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36960 | Mariposa PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18604SS | 18606SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36961 | Mariposa PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18605SS | 18607SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36962 | Mariposa PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data los | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18606SS | 18608SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36963 | Mariposa PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18607SS | 18609SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36964 | Mariposa PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18608SS | 18610SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36965 | Mariposa PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18609SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
36966 | Mariposa PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
36967 | Mariposa PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
36968 | Mariposa PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36969 | Mariposa PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 18615SS,18619 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36970 | Mariposa PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 18614SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
36971 | Mariposa PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
36972 | Mariposa PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18625 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36973 | Mariposa PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18626 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36974 | Mariposa PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 18614 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
36975 | Mariposa PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
36976 | Mariposa PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 18622SS,18630SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36977 | Mariposa PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 18621SS | 18623SS,18631SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36978 | Mariposa PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 18622SS | 18632SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
36979 | Mariposa PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
36980 | Mariposa PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 18617 | 18626SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36981 | Mariposa PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 18618,18625SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
36982 | Mariposa PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 18635FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36983 | Mariposa PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 18629SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36984 | Mariposa PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 18628SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
36985 | Mariposa PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18621SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36986 | Mariposa PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18622SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36987 | Mariposa PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18623SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36988 | Mariposa PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 18635SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36989 | Mariposa PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
36990 | Mariposa PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 18627FS+12d,18633SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
36991 | Mendocino PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
36992 | Mendocino PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
36993 | Mendocino PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
36994 | Mendocino PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
36995 | Mendocino PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
36996 | Mendocino PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
36997 | Mendocino PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
36998 | Mendocino PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
36999 | Mendocino PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37000 | Mendocino PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37001 | Mendocino PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37002 | Mendocino PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
37003 | Mendocino PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37004 | Mendocino PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37005 | Mendocino PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37006 | Mendocino PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
37007 | Mendocino PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
37008 | Mendocino PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37009 | Mendocino PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
37010 | Mendocino PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
37011 | Mendocino PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
37012 | Mendocino PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
37013 | Mendocino PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
37014 | Mendocino PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
37015 | Mendocino PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
37016 | Mendocino PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
37017 | Mendocino PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37018 | Mendocino PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37019 | Mendocino PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 18665SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
37020 | Mendocino PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 18664SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
37021 | Mendocino PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18667SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37022 | Mendocino PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18666SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37023 | Mendocino PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37024 | Mendocino PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 18670SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
37025 | Mendocino PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 18669SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
37026 | Mendocino PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
37027 | Mendocino PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 18673SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
37028 | Mendocino PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 18672SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
37029 | Mendocino PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37030 | Mendocino PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 18676SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
37031 | Mendocino PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 18675SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
37032 | Mendocino PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 18678SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37033 | Mendocino PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 18677SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37034 | Mendocino PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37035 | Mendocino PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37036 | Mendocino PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37037 | Mendocino PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
37038 | Mendocino PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37039 | Mendocino PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37040 | Mendocino PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
37041 | Mendocino PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 18687FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37042 | Mendocino PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 18686FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37043 | Mendocino PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.17000000000000001
37044 | Mendocino PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 18691FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
37045 | Mendocino PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 528d | NA | NA | 0 days? | No | NA | NA | NA | 0
37046 | Mendocino PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 18689FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
37047 | Mendocino PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
37048 | Mendocino PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 18694 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
37049 | Mendocino PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18693 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37050 | Mendocino PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37051 | Mendocino PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18697FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37052 | Mendocino PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 18696FS+19d | 18698 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37053 | Mendocino PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 18697 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37054 | Mendocino PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37055 | Mendocino PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 18701 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37056 | Mendocino PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 18700 | 18702FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37057 | Mendocino PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 18701FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37058 | Mendocino PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37059 | Mendocino PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37060 | Mendocino PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37061 | Mendocino PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37062 | Mendocino PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18708SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37063 | Mendocino PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 18707SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37064 | Mendocino PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37065 | Mendocino PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37066 | Mendocino PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37067 | Mendocino PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18713SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37068 | Mendocino PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18712SS | 18727SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37069 | Mendocino PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37070 | Mendocino PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37071 | Mendocino PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37072 | Mendocino PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37073 | Mendocino PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 18719SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37074 | Mendocino PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18718SS | 18720SS,18721 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37075 | Mendocino PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18719SS | 18721 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37076 | Mendocino PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 18719,18720 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37077 | Mendocino PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37078 | Mendocino PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37079 | Mendocino PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18725SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37080 | Mendocino PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 18724SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37081 | Mendocino PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37082 | Mendocino PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18713SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37083 | Mendocino PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37084 | Mendocino PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18730SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37085 | Mendocino PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18729SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37086 | Mendocino PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37087 | Mendocino PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 18733SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37088 | Mendocino PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 18732SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37089 | Mendocino PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37090 | Mendocino PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 18736SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37091 | Mendocino PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18735SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37092 | Mendocino PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 18738 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37093 | Mendocino PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 18737 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37094 | Mendocino PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37095 | Mendocino PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37096 | Mendocino PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18742SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37097 | Mendocino PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18741SS | 18743SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37098 | Mendocino PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18742SS | 18744SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37099 | Mendocino PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18743SS | 18745SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37100 | Mendocino PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18744SS | 18746SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37101 | Mendocino PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18745SS | 18747SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37102 | Mendocino PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18746SS | 18748SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37103 | Mendocino PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18747SS | 18749SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37104 | Mendocino PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18748SS | 18750SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37105 | Mendocino PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18749SS | 18751SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37106 | Mendocino PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18750SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37107 | Mendocino PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
37108 | Mendocino PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
37109 | Mendocino PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37110 | Mendocino PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 18756SS,18760 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37111 | Mendocino PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 18755SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
37112 | Mendocino PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
37113 | Mendocino PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18766 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37114 | Mendocino PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18767 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37115 | Mendocino PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 18755 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37116 | Mendocino PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
37117 | Mendocino PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 18763SS,18771SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37118 | Mendocino PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 18762SS | 18764SS,18772SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37119 | Mendocino PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 18763SS | 18773SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37120 | Mendocino PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
37121 | Mendocino PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 18758 | 18767SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37122 | Mendocino PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 18759,18766SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37123 | Mendocino PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 18776FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37124 | Mendocino PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 18770SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37125 | Mendocino PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 18769SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37126 | Mendocino PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18762SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37127 | Mendocino PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18763SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37128 | Mendocino PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18764SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37129 | Mendocino PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 18776SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37130 | Mendocino PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
37131 | Mendocino PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 18768FS+12d,18774SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37132 | Merced PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 7.0000000000000007E-2
37133 | Merced PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
37134 | Merced PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
37135 | Merced PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
37136 | Merced PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37137 | Merced PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
37138 | Merced PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
37139 | Merced PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37140 | Merced PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37141 | Merced PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37142 | Merced PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37143 | Merced PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
37144 | Merced PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37145 | Merced PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37146 | Merced PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37147 | Merced PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
37148 | Merced PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
37149 | Merced PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37150 | Merced PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
37151 | Merced PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
37152 | Merced PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
37153 | Merced PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
37154 | Merced PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
37155 | Merced PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
37156 | Merced PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
37157 | Merced PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
37158 | Merced PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37159 | Merced PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
37160 | Merced PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 18806SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
37161 | Merced PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 18805SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
37162 | Merced PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18808SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37163 | Merced PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18807SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37164 | Merced PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37165 | Merced PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 18811SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
37166 | Merced PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 18810SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
37167 | Merced PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
37168 | Merced PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 18814SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
37169 | Merced PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 18813SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
37170 | Merced PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37171 | Merced PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 18817SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
37172 | Merced PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 18816SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
37173 | Merced PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 18819SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37174 | Merced PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 18818SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37175 | Merced PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37176 | Merced PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37177 | Merced PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37178 | Merced PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
37179 | Merced PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37180 | Merced PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37181 | Merced PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
37182 | Merced PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 18828FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37183 | Merced PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 18827FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37184 | Merced PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.22
37185 | Merced PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 18832FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
37186 | Merced PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37187 | Merced PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 18830FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
37188 | Merced PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
37189 | Merced PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 18835 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
37190 | Merced PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18834 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37191 | Merced PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37192 | Merced PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18838FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
37193 | Merced PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 18837FS+19d | 18839 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37194 | Merced PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 18838 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37195 | Merced PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37196 | Merced PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 18842 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37197 | Merced PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 18841 | 18843FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37198 | Merced PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 18842FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37199 | Merced PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37200 | Merced PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37201 | Merced PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37202 | Merced PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37203 | Merced PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18849SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37204 | Merced PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 18848SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37205 | Merced PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37206 | Merced PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37207 | Merced PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37208 | Merced PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18854SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37209 | Merced PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18853SS | 18868SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37210 | Merced PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37211 | Merced PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37212 | Merced PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37213 | Merced PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37214 | Merced PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 18860SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37215 | Merced PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18859SS | 18861SS,18862 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37216 | Merced PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18860SS | 18862 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37217 | Merced PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 18860,18861 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37218 | Merced PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37219 | Merced PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37220 | Merced PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18866SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37221 | Merced PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 18865SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37222 | Merced PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37223 | Merced PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18854SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37224 | Merced PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37225 | Merced PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18871SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37226 | Merced PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18870SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37227 | Merced PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37228 | Merced PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 18874SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37229 | Merced PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 18873SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37230 | Merced PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37231 | Merced PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 18877SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37232 | Merced PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 18876SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37233 | Merced PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 18879 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37234 | Merced PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 18878 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37235 | Merced PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37236 | Merced PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37237 | Merced PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18883SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37238 | Merced PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18882SS | 18884SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37239 | Merced PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18883SS | 18885SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37240 | Merced PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18884SS | 18886SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37241 | Merced PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18885SS | 18887SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37242 | Merced PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18886SS | 18888SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37243 | Merced PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18887SS | 18889SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37244 | Merced PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18888SS | 18890SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37245 | Merced PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18889SS | 18891SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37246 | Merced PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18890SS | 18892SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37247 | Merced PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18891SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37248 | Merced PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
37249 | Merced PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
37250 | Merced PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.01
37251 | Merced PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 18897SS,18901 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
37252 | Merced PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 18896SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
37253 | Merced PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
37254 | Merced PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18907 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37255 | Merced PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18908 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37256 | Merced PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 18896 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37257 | Merced PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
37258 | Merced PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 18904SS,18912SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37259 | Merced PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 18903SS | 18905SS,18913SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37260 | Merced PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 18904SS | 18914SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37261 | Merced PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
37262 | Merced PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 18899 | 18908SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37263 | Merced PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 18900,18907SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37264 | Merced PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 18917FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37265 | Merced PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 18911SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37266 | Merced PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 18910SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37267 | Merced PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18903SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37268 | Merced PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18904SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37269 | Merced PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 18905SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37270 | Merced PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 18917SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37271 | Merced PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
37272 | Merced PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 18909FS+12d,18915SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37273 | Modoc PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 7.0000000000000007E-2
37274 | Modoc PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.22
37275 | Modoc PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.26000000000000001
37276 | Modoc PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
37277 | Modoc PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37278 | Modoc PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
37279 | Modoc PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
37280 | Modoc PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37281 | Modoc PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37282 | Modoc PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37283 | Modoc PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37284 | Modoc PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
37285 | Modoc PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37286 | Modoc PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37287 | Modoc PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37288 | Modoc PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
37289 | Modoc PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
37290 | Modoc PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37291 | Modoc PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
37292 | Modoc PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
37293 | Modoc PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
37294 | Modoc PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
37295 | Modoc PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
37296 | Modoc PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
37297 | Modoc PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
37298 | Modoc PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
37299 | Modoc PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37300 | Modoc PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
37301 | Modoc PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 18947SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
37302 | Modoc PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 18946SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
37303 | Modoc PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 18949SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37304 | Modoc PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 18948SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37305 | Modoc PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37306 | Modoc PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 18952SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
37307 | Modoc PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 18951SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
37308 | Modoc PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
37309 | Modoc PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 18955SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
37310 | Modoc PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 18954SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
37311 | Modoc PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37312 | Modoc PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 18958SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
37313 | Modoc PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 18957SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
37314 | Modoc PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 18960SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37315 | Modoc PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 18959SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37316 | Modoc PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37317 | Modoc PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37318 | Modoc PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37319 | Modoc PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
37320 | Modoc PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37321 | Modoc PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37322 | Modoc PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
37323 | Modoc PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 18969FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37324 | Modoc PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 18968FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37325 | Modoc PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.22
37326 | Modoc PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 18973FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
37327 | Modoc PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37328 | Modoc PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 18971FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
37329 | Modoc PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
37330 | Modoc PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 18976 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
37331 | Modoc PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18975 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
37332 | Modoc PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37333 | Modoc PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18979FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.40000000000000002
37334 | Modoc PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 18978FS+19d | 18980 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37335 | Modoc PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 18979 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37336 | Modoc PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37337 | Modoc PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 18983 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37338 | Modoc PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 18982 | 18984FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37339 | Modoc PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 18983FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37340 | Modoc PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37341 | Modoc PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37342 | Modoc PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37343 | Modoc PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37344 | Modoc PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18990SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37345 | Modoc PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 18989SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37346 | Modoc PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37347 | Modoc PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37348 | Modoc PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37349 | Modoc PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 18995SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37350 | Modoc PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18994SS | 19009SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37351 | Modoc PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37352 | Modoc PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37353 | Modoc PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37354 | Modoc PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37355 | Modoc PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 19001SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37356 | Modoc PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19000SS | 19002SS,19003 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37357 | Modoc PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19001SS | 19003 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37358 | Modoc PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 19001,19002 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37359 | Modoc PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37360 | Modoc PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37361 | Modoc PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19007SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37362 | Modoc PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 19006SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37363 | Modoc PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37364 | Modoc PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 18995SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37365 | Modoc PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37366 | Modoc PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19012SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37367 | Modoc PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19011SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37368 | Modoc PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37369 | Modoc PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 19015SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37370 | Modoc PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 19014SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37371 | Modoc PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37372 | Modoc PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 19018SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37373 | Modoc PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19017SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37374 | Modoc PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 19020 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37375 | Modoc PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 19019 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37376 | Modoc PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37377 | Modoc PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37378 | Modoc PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19024SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37379 | Modoc PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19023SS | 19025SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37380 | Modoc PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19024SS | 19026SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37381 | Modoc PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19025SS | 19027SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37382 | Modoc PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19026SS | 19028SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37383 | Modoc PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19027SS | 19029SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37384 | Modoc PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19028SS | 19030SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37385 | Modoc PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19029SS | 19031SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37386 | Modoc PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19030SS | 19032SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37387 | Modoc PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19031SS | 19033SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37388 | Modoc PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19032SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37389 | Modoc PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
37390 | Modoc PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
37391 | Modoc PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37392 | Modoc PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 19038SS,19042 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37393 | Modoc PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 19037SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
37394 | Modoc PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
37395 | Modoc PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19048 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37396 | Modoc PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19049 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37397 | Modoc PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 19037 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37398 | Modoc PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
37399 | Modoc PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 19045SS,19053SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37400 | Modoc PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 19044SS | 19046SS,19054SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37401 | Modoc PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 19045SS | 19055SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37402 | Modoc PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
37403 | Modoc PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 19040 | 19049SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37404 | Modoc PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 19041,19048SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37405 | Modoc PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 19058FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37406 | Modoc PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 19052SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37407 | Modoc PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 19051SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37408 | Modoc PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19044SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37409 | Modoc PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19045SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37410 | Modoc PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19046SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37411 | Modoc PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 19058SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37412 | Modoc PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
37413 | Modoc PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 19050FS+12d,19056SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37414 | Mono PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 8.9999999999999997E-2
37415 | Mono PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.22
37416 | Mono PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.26000000000000001
37417 | Mono PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
37418 | Mono PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37419 | Mono PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
37420 | Mono PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
37421 | Mono PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37422 | Mono PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37423 | Mono PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37424 | Mono PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37425 | Mono PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
37426 | Mono PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37427 | Mono PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37428 | Mono PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37429 | Mono PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
37430 | Mono PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
37431 | Mono PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37432 | Mono PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
37433 | Mono PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
37434 | Mono PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
37435 | Mono PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
37436 | Mono PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
37437 | Mono PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
37438 | Mono PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
37439 | Mono PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
37440 | Mono PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37441 | Mono PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
37442 | Mono PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 19088SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
37443 | Mono PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 19087SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
37444 | Mono PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19090SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37445 | Mono PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19089SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37446 | Mono PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37447 | Mono PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 19093SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
37448 | Mono PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 19092SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
37449 | Mono PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
37450 | Mono PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 19096SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
37451 | Mono PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 19095SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
37452 | Mono PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37453 | Mono PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 19099SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
37454 | Mono PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 19098SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
37455 | Mono PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 19101SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37456 | Mono PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 19100SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37457 | Mono PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37458 | Mono PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37459 | Mono PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37460 | Mono PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
37461 | Mono PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37462 | Mono PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37463 | Mono PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
37464 | Mono PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 19110FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37465 | Mono PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 19109FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37466 | Mono PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
37467 | Mono PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 19114FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
37468 | Mono PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37469 | Mono PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 19112FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
37470 | Mono PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
37471 | Mono PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 19117 | Start No Earlier Than | 9/2/25 | 21 | 8.4d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
37472 | Mono PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19116 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
37473 | Mono PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37474 | Mono PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19120FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
37475 | Mono PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 19119FS+19d | 19121 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37476 | Mono PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 19120 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37477 | Mono PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37478 | Mono PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 19124 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37479 | Mono PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 19123 | 19125FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37480 | Mono PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 19124FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37481 | Mono PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37482 | Mono PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37483 | Mono PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 131 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
37484 | Mono PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37485 | Mono PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19131SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37486 | Mono PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19130SS | 19132SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37487 | Mono PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19131SS | 19133SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37488 | Mono PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19132SS | 19134SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37489 | Mono PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19133SS | 19135SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37490 | Mono PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19134SS | 19136SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37491 | Mono PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19135SS | 19137SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37492 | Mono PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19136SS | 19138SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37493 | Mono PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19137SS | 19139SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37494 | Mono PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19138SS | 19140SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37495 | Mono PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19139SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37496 | Mono PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
37497 | Mono PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
37498 | Mono PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37499 | Mono PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 19145SS,19149 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37500 | Mono PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 19144SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
37501 | Mono PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
37502 | Mono PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19155 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37503 | Mono PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19156 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37504 | Mono PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 19144 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37505 | Mono PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
37506 | Mono PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 19152SS,19160SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37507 | Mono PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 19151SS | 19153SS,19161SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37508 | Mono PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 19152SS | 19162SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37509 | Mono PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
37510 | Mono PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 19147 | 19156SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37511 | Mono PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 19148,19155SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37512 | Mono PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 19165FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37513 | Mono PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 19159SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37514 | Mono PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 19158SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37515 | Mono PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19151SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37516 | Mono PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19152SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37517 | Mono PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19153SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37518 | Mono PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 19165SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37519 | Mono PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
37520 | Mono PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 19157FS+12d,19163SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37521 | Monterey PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.10000000000000001
37522 | Monterey PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.26000000000000001
37523 | Monterey PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.26000000000000001
37524 | Monterey PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
37525 | Monterey PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37526 | Monterey PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
37527 | Monterey PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
37528 | Monterey PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37529 | Monterey PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37530 | Monterey PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37531 | Monterey PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37532 | Monterey PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
37533 | Monterey PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37534 | Monterey PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37535 | Monterey PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37536 | Monterey PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
37537 | Monterey PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
37538 | Monterey PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37539 | Monterey PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
37540 | Monterey PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
37541 | Monterey PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
37542 | Monterey PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
37543 | Monterey PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
37544 | Monterey PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
37545 | Monterey PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
37546 | Monterey PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
37547 | Monterey PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37548 | Monterey PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.94999999999999996
37549 | Monterey PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 19195SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
37550 | Monterey PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 19194SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
37551 | Monterey PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19197SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37552 | Monterey PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19196SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37553 | Monterey PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37554 | Monterey PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 19200SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
37555 | Monterey PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 19199SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
37556 | Monterey PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
37557 | Monterey PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 19203SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
37558 | Monterey PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 19202SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
37559 | Monterey PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37560 | Monterey PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 19206SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
37561 | Monterey PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 19205SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
37562 | Monterey PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 19208SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37563 | Monterey PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 19207SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37564 | Monterey PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37565 | Monterey PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37566 | Monterey PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37567 | Monterey PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
37568 | Monterey PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37569 | Monterey PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37570 | Monterey PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
37571 | Monterey PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 19217FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37572 | Monterey PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 19216FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37573 | Monterey PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.23000000000000001
37574 | Monterey PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 19221FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
37575 | Monterey PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37576 | Monterey PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 19219FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
37577 | Monterey PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
37578 | Monterey PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 19224 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
37579 | Monterey PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19223 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
37580 | Monterey PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37581 | Monterey PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19227FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
37582 | Monterey PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 19226FS+19d | 19228 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37583 | Monterey PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 19227 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37584 | Monterey PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37585 | Monterey PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operatio | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 19231 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37586 | Monterey PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 19230 | 19232FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37587 | Monterey PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 19231FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37588 | Monterey PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37589 | Monterey PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37590 | Monterey PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 131 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
37591 | Monterey PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37592 | Monterey PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19238SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37593 | Monterey PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19237SS | 19239SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37594 | Monterey PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19238SS | 19240SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37595 | Monterey PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19239SS | 19241SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37596 | Monterey PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19240SS | 19242SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37597 | Monterey PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19241SS | 19243SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37598 | Monterey PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19242SS | 19244SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37599 | Monterey PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data los | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19243SS | 19245SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37600 | Monterey PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19244SS | 19246SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37601 | Monterey PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19245SS | 19247SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37602 | Monterey PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19246SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37603 | Monterey PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
37604 | Monterey PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
37605 | Monterey PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37606 | Monterey PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 19252SS,19256 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37607 | Monterey PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 19251SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
37608 | Monterey PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
37609 | Monterey PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19262 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37610 | Monterey PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19263 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37611 | Monterey PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 19251 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37612 | Monterey PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
37613 | Monterey PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 19259SS,19267SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37614 | Monterey PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 19258SS | 19260SS,19268SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37615 | Monterey PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 19259SS | 19269SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37616 | Monterey PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
37617 | Monterey PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 19254 | 19263SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37618 | Monterey PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 19255,19262SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37619 | Monterey PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 19272FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37620 | Monterey PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 19266SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37621 | Monterey PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 19265SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37622 | Monterey PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19258SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37623 | Monterey PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19259SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37624 | Monterey PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19260SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37625 | Monterey PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 19272SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37626 | Monterey PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
37627 | Monterey PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 19264FS+12d,19270SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37628 | Napa PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
37629 | Napa PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
37630 | Napa PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
37631 | Napa PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
37632 | Napa PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37633 | Napa PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
37634 | Napa PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
37635 | Napa PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37636 | Napa PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37637 | Napa PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37638 | Napa PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37639 | Napa PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
37640 | Napa PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37641 | Napa PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37642 | Napa PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37643 | Napa PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
37644 | Napa PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
37645 | Napa PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37646 | Napa PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
37647 | Napa PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
37648 | Napa PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
37649 | Napa PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
37650 | Napa PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
37651 | Napa PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
37652 | Napa PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
37653 | Napa PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
37654 | Napa PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37655 | Napa PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37656 | Napa PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 19302SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
37657 | Napa PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 19301SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
37658 | Napa PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19304SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37659 | Napa PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19303SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37660 | Napa PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37661 | Napa PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 19307SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
37662 | Napa PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 19306SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
37663 | Napa PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
37664 | Napa PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 19310SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
37665 | Napa PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 19309SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
37666 | Napa PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37667 | Napa PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 19313SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
37668 | Napa PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 19312SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
37669 | Napa PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 19315SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37670 | Napa PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 19314SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37671 | Napa PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37672 | Napa PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37673 | Napa PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37674 | Napa PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
37675 | Napa PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37676 | Napa PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37677 | Napa PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
37678 | Napa PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 19324FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37679 | Napa PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 19323FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37680 | Napa PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
37681 | Napa PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 19328FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
37682 | Napa PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37683 | Napa PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 19326FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
37684 | Napa PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
37685 | Napa PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 19331 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
37686 | Napa PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19330 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37687 | Napa PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37688 | Napa PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19334FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37689 | Napa PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 19333FS+19d | 19335 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37690 | Napa PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 19334 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37691 | Napa PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37692 | Napa PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 19338 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37693 | Napa PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 19337 | 19339FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37694 | Napa PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 19338FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37695 | Napa PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37696 | Napa PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37697 | Napa PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37698 | Napa PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37699 | Napa PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19345SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37700 | Napa PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 19344SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37701 | Napa PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37702 | Napa PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37703 | Napa PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37704 | Napa PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19350SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37705 | Napa PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19349SS | 19364SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37706 | Napa PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37707 | Napa PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37708 | Napa PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37709 | Napa PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37710 | Napa PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 19356SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37711 | Napa PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19355SS | 19357SS,19358 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37712 | Napa PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19356SS | 19358 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37713 | Napa PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 19356,19357 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37714 | Napa PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37715 | Napa PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37716 | Napa PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19362SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37717 | Napa PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 19361SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37718 | Napa PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37719 | Napa PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19350SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37720 | Napa PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37721 | Napa PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19367SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37722 | Napa PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19366SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37723 | Napa PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37724 | Napa PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 19370SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37725 | Napa PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 19369SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37726 | Napa PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37727 | Napa PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 19373SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37728 | Napa PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19372SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37729 | Napa PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 19375 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37730 | Napa PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 19374 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37731 | Napa PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37732 | Napa PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37733 | Napa PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19379SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37734 | Napa PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19378SS | 19380SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37735 | Napa PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19379SS | 19381SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37736 | Napa PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19380SS | 19382SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37737 | Napa PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19381SS | 19383SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37738 | Napa PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19382SS | 19384SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37739 | Napa PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19383SS | 19385SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37740 | Napa PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19384SS | 19386SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37741 | Napa PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19385SS | 19387SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37742 | Napa PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19386SS | 19388SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37743 | Napa PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19387SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37744 | Napa PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
37745 | Napa PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
37746 | Napa PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37747 | Napa PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 19393SS,19397 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37748 | Napa PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 19392SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
37749 | Napa PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
37750 | Napa PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19403 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37751 | Napa PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19404 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37752 | Napa PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 19392 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37753 | Napa PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
37754 | Napa PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 19400SS,19408SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37755 | Napa PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 19399SS | 19401SS,19409SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37756 | Napa PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 19400SS | 19410SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37757 | Napa PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
37758 | Napa PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 19395 | 19404SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37759 | Napa PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 19396,19403SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37760 | Napa PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 19413FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37761 | Napa PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 19407SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37762 | Napa PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 19406SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37763 | Napa PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19399SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37764 | Napa PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19400SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37765 | Napa PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19401SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37766 | Napa PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 19413SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37767 | Napa PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
37768 | Napa PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 19405FS+12d,19411SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37769 | Nevada PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 8.9999999999999997E-2
37770 | Nevada PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
37771 | Nevada PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
37772 | Nevada PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
37773 | Nevada PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37774 | Nevada PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
37775 | Nevada PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
37776 | Nevada PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37777 | Nevada PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37778 | Nevada PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37779 | Nevada PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37780 | Nevada PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
37781 | Nevada PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37782 | Nevada PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37783 | Nevada PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37784 | Nevada PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
37785 | Nevada PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
37786 | Nevada PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37787 | Nevada PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
37788 | Nevada PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
37789 | Nevada PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
37790 | Nevada PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
37791 | Nevada PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
37792 | Nevada PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
37793 | Nevada PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
37794 | Nevada PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
37795 | Nevada PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37796 | Nevada PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37797 | Nevada PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 19443SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
37798 | Nevada PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 19442SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
37799 | Nevada PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19445SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37800 | Nevada PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19444SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37801 | Nevada PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37802 | Nevada PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 19448SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
37803 | Nevada PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 19447SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
37804 | Nevada PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
37805 | Nevada PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 19451SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
37806 | Nevada PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 19450SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
37807 | Nevada PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37808 | Nevada PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 19454SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
37809 | Nevada PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 19453SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
37810 | Nevada PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 19456SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37811 | Nevada PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 19455SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37812 | Nevada PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37813 | Nevada PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37814 | Nevada PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37815 | Nevada PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
37816 | Nevada PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37817 | Nevada PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37818 | Nevada PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
37819 | Nevada PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 19465FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37820 | Nevada PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 19464FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37821 | Nevada PR - OCM Activities | July 1, 2025 12:00 AM | July 17, 2026 5:00 PM |  |  | As Soon As Possible | NA | 263 | 309d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.23999999999999999
37822 | Nevada PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
37823 | Nevada PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37824 | Nevada PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
37825 | Nevada PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 19471 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
37826 | Nevada PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19470 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37827 | Nevada PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37828 | Nevada PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19474FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
37829 | Nevada PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 19473FS+19d | 19475 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37830 | Nevada PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 19474 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37831 | Nevada PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37832 | Nevada PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 19478 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37833 | Nevada PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 19477 | 19479FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37834 | Nevada PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 19478FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37835 | Nevada PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37836 | Nevada PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37837 | Nevada PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 7.0000000000000007E-2
37838 | Nevada PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.59999999999999998
37839 | Nevada PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19485SS | Finish No Earlier Than | 10/31/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
37840 | Nevada PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 19484SS |  | Finish No Earlier Than | 1/31/26 | 84 | 0d | NA | NA | 0 days? | No | 10/1/25 | 2/2/26 | NA | 1
37841 | Nevada PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | 12/1/25 | NA | NA | 0.20000000000000001
37842 | Nevada PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 0d | NA | NA | 0 days? | No | 10/1/25 | 12/1/25 | NA | 1
37843 | Nevada PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
37844 | Nevada PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19490SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
37845 | Nevada PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19489SS | 19504SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
37846 | Nevada PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37847 | Nevada PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37848 | Nevada PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37849 | Nevada PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37850 | Nevada PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 19496SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37851 | Nevada PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19495SS | 19497SS,19498 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37852 | Nevada PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19496SS | 19498 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37853 | Nevada PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 19496,19497 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37854 | Nevada PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37855 | Nevada PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37856 | Nevada PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19502SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37857 | Nevada PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 19501SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37858 | Nevada PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37859 | Nevada PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19490SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37860 | Nevada PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
37861 | Nevada PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19507SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
37862 | Nevada PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19506SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
37863 | Nevada PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37864 | Nevada PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 19510SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37865 | Nevada PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 19509SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37866 | Nevada PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37867 | Nevada PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 19513SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37868 | Nevada PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19512SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37869 | Nevada PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 19515 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37870 | Nevada PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 19514 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37871 | Nevada PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37872 | Nevada PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37873 | Nevada PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19519SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37874 | Nevada PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19518SS | 19520SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37875 | Nevada PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19519SS | 19521SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37876 | Nevada PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19520SS | 19522SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37877 | Nevada PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19521SS | 19523SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37878 | Nevada PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19522SS | 19524SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37879 | Nevada PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19523SS | 19525SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37880 | Nevada PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19524SS | 19526SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37881 | Nevada PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19525SS | 19527SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37882 | Nevada PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19526SS | 19528SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37883 | Nevada PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19527SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37884 | Nevada PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
37885 | Nevada PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
37886 | Nevada PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37887 | Nevada PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 19533SS,19537 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37888 | Nevada PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 19532SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
37889 | Nevada PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
37890 | Nevada PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19543 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37891 | Nevada PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19544 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37892 | Nevada PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 19532 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37893 | Nevada PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
37894 | Nevada PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 19540SS,19548SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37895 | Nevada PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 19539SS | 19541SS,19549SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37896 | Nevada PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 19540SS | 19550SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37897 | Nevada PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
37898 | Nevada PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 19535 | 19544SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37899 | Nevada PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 19536,19543SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
37900 | Nevada PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 19553FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37901 | Nevada PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 19547SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37902 | Nevada PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 19546SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37903 | Nevada PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19539SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37904 | Nevada PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19540SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37905 | Nevada PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19541SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37906 | Nevada PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 19553SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37907 | Nevada PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
37908 | Nevada PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 19545FS+12d,19551SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
37909 | Orange PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
37910 | Orange PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
37911 | Orange PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
37912 | Orange PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
37913 | Orange PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37914 | Orange PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
37915 | Orange PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
37916 | Orange PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37917 | Orange PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37918 | Orange PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37919 | Orange PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37920 | Orange PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
37921 | Orange PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37922 | Orange PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37923 | Orange PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
37924 | Orange PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
37925 | Orange PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
37926 | Orange PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37927 | Orange PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
37928 | Orange PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
37929 | Orange PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
37930 | Orange PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
37931 | Orange PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
37932 | Orange PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
37933 | Orange PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
37934 | Orange PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
37935 | Orange PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37936 | Orange PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37937 | Orange PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 19583SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
37938 | Orange PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 19582SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
37939 | Orange PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19585SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37940 | Orange PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19584SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37941 | Orange PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37942 | Orange PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 19588SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
37943 | Orange PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 19587SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
37944 | Orange PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
37945 | Orange PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 19591SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
37946 | Orange PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 19590SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
37947 | Orange PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37948 | Orange PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 19594SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
37949 | Orange PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 19593SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
37950 | Orange PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 19596SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37951 | Orange PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 19595SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37952 | Orange PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
37953 | Orange PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
37954 | Orange PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37955 | Orange PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
37956 | Orange PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37957 | Orange PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
37958 | Orange PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
37959 | Orange PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 19605FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37960 | Orange PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 19604FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
37961 | Orange PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
37962 | Orange PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 19609FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
37963 | Orange PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
37964 | Orange PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 19607FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
37965 | Orange PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
37966 | Orange PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 19612 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
37967 | Orange PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19611 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37968 | Orange PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37969 | Orange PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19615FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37970 | Orange PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 19614FS+19d | 19616 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37971 | Orange PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 19615 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
37972 | Orange PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37973 | Orange PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 19619 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37974 | Orange PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 19618 | 19620FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37975 | Orange PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 19619FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
37976 | Orange PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
37977 | Orange PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
37978 | Orange PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37979 | Orange PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37980 | Orange PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19626SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37981 | Orange PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 19625SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37982 | Orange PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37983 | Orange PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37984 | Orange PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37985 | Orange PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19631SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37986 | Orange PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19630SS | 19645SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
37987 | Orange PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37988 | Orange PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
37989 | Orange PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
37990 | Orange PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37991 | Orange PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 19637SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37992 | Orange PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19636SS | 19638SS,19639 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37993 | Orange PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19637SS | 19639 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37994 | Orange PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 19637,19638 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
37995 | Orange PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
37996 | Orange PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
37997 | Orange PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19643SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
37998 | Orange PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 19642SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
37999 | Orange PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38000 | Orange PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19631SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38001 | Orange PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38002 | Orange PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19648SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38003 | Orange PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19647SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38004 | Orange PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38005 | Orange PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 19651SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38006 | Orange PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 19650SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38007 | Orange PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38008 | Orange PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 19654SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38009 | Orange PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19653SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38010 | Orange PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 19656 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38011 | Orange PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 19655 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38012 | Orange PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38013 | Orange PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38014 | Orange PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19660SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38015 | Orange PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19659SS | 19661SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38016 | Orange PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19660SS | 19662SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38017 | Orange PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19661SS | 19663SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38018 | Orange PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19662SS | 19664SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38019 | Orange PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19663SS | 19665SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38020 | Orange PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19664SS | 19666SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38021 | Orange PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19665SS | 19667SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38022 | Orange PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19666SS | 19668SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38023 | Orange PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19667SS | 19669SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38024 | Orange PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19668SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38025 | Orange PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
38026 | Orange PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
38027 | Orange PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38028 | Orange PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 19674SS,19678 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38029 | Orange PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 19673SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
38030 | Orange PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
38031 | Orange PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19684 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38032 | Orange PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19685 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38033 | Orange PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 19673 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38034 | Orange PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
38035 | Orange PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 19681SS,19689SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38036 | Orange PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 19680SS | 19682SS,19690SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38037 | Orange PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 19681SS | 19691SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38038 | Orange PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
38039 | Orange PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 19676 | 19685SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38040 | Orange PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 19677,19684SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38041 | Orange PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 19694FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38042 | Orange PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 19688SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38043 | Orange PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 19687SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38044 | Orange PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19680SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38045 | Orange PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19681SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38046 | Orange PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19682SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38047 | Orange PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 19694SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38048 | Orange PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38049 | Orange PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 19686FS+12d,19692SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38050 | Placer PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 8.0000000000000002E-2
38051 | Placer PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
38052 | Placer PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
38053 | Placer PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
38054 | Placer PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38055 | Placer PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
38056 | Placer PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
38057 | Placer PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38058 | Placer PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38059 | Placer PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38060 | Placer PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38061 | Placer PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
38062 | Placer PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38063 | Placer PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38064 | Placer PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38065 | Placer PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38066 | Placer PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
38067 | Placer PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38068 | Placer PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
38069 | Placer PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
38070 | Placer PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
38071 | Placer PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
38072 | Placer PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
38073 | Placer PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
38074 | Placer PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
38075 | Placer PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
38076 | Placer PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38077 | Placer PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38078 | Placer PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 19724SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
38079 | Placer PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 19723SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
38080 | Placer PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19726SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38081 | Placer PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19725SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38082 | Placer PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38083 | Placer PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 19729SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
38084 | Placer PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 19728SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
38085 | Placer PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
38086 | Placer PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 19732SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
38087 | Placer PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 19731SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
38088 | Placer PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38089 | Placer PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 19735SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
38090 | Placer PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 19734SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
38091 | Placer PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 19737SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
38092 | Placer PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 19736SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
38093 | Placer PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38094 | Placer PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
38095 | Placer PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38096 | Placer PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
38097 | Placer PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38098 | Placer PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38099 | Placer PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
38100 | Placer PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 19746FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38101 | Placer PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 19745FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38102 | Placer PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
38103 | Placer PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 19750FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
38104 | Placer PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38105 | Placer PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 19748FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
38106 | Placer PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
38107 | Placer PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 19753 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
38108 | Placer PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19752 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38109 | Placer PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38110 | Placer PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19756FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
38111 | Placer PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 19755FS+19d | 19757 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38112 | Placer PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 19756 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38113 | Placer PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38114 | Placer PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 19760 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38115 | Placer PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 19759 | 19761FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38116 | Placer PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 19760FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38117 | Placer PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38118 | Placer PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38119 | Placer PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 4.0000000000000001E-2
38120 | Placer PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38121 | Placer PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19767SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38122 | Placer PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 19766SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38123 | Placer PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38124 | Placer PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
38125 | Placer PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 8.4d | NA | NA | 0 days? | No | NA | NA | NA | 0
38126 | Placer PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19772SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38127 | Placer PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19771SS | 19786SS | Start No Earlier Than | 10/1/25 | 42 | 8.4d | NA | NA | 0 days? | No | NA | NA | NA | 0
38128 | Placer PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | 11/3/25 | NA | NA | 0.29999999999999999
38129 | Placer PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 0d | NA | NA | 0 days? | No | 11/3/25 | 12/31/25 | NA | 1
38130 | Placer PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38131 | Placer PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | 12/1/25 | NA | NA | 0.10000000000000001
38132 | Placer PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 19778SS | Start No Earlier Than | 12/1/25 | 43 | 0d | NA | NA | 0 days? | No | 12/1/25 | 2/2/26 | NA | 1
38133 | Placer PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19777SS | 19779SS,19780 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38134 | Placer PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19778SS | 19780 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38135 | Placer PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 19778,19779 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38136 | Placer PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38137 | Placer PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38138 | Placer PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19784SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38139 | Placer PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 19783SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38140 | Placer PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38141 | Placer PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19772SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
38142 | Placer PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
38143 | Placer PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19789SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
38144 | Placer PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19788SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
38145 | Placer PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38146 | Placer PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 19792SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38147 | Placer PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 19791SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38148 | Placer PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38149 | Placer PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 19795SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38150 | Placer PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19794SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38151 | Placer PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 19797 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38152 | Placer PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 19796 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38153 | Placer PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38154 | Placer PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38155 | Placer PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19801SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38156 | Placer PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19800SS | 19802SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38157 | Placer PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19801SS | 19803SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38158 | Placer PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19802SS | 19804SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38159 | Placer PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19803SS | 19805SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38160 | Placer PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19804SS | 19806SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38161 | Placer PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19805SS | 19807SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38162 | Placer PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19806SS | 19808SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38163 | Placer PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19807SS | 19809SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38164 | Placer PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19808SS | 19810SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38165 | Placer PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19809SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38166 | Placer PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
38167 | Placer PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
38168 | Placer PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.01
38169 | Placer PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 19815SS,19819 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
38170 | Placer PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 19814SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
38171 | Placer PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
38172 | Placer PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19825 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38173 | Placer PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19826 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38174 | Placer PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 19814 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38175 | Placer PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
38176 | Placer PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 19822SS,19830SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38177 | Placer PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 19821SS | 19823SS,19831SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38178 | Placer PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 19822SS | 19832SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38179 | Placer PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
38180 | Placer PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 19817 | 19826SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38181 | Placer PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 19818,19825SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38182 | Placer PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 19835FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38183 | Placer PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 19829SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38184 | Placer PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 19828SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38185 | Placer PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19821SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38186 | Placer PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19822SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38187 | Placer PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19823SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38188 | Placer PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 19835SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38189 | Placer PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38190 | Placer PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 19827FS+12d,19833SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38191 | Plumas PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
38192 | Plumas PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
38193 | Plumas PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
38194 | Plumas PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
38195 | Plumas PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38196 | Plumas PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
38197 | Plumas PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
38198 | Plumas PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38199 | Plumas PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38200 | Plumas PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38201 | Plumas PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38202 | Plumas PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
38203 | Plumas PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38204 | Plumas PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38205 | Plumas PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38206 | Plumas PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38207 | Plumas PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
38208 | Plumas PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38209 | Plumas PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
38210 | Plumas PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
38211 | Plumas PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
38212 | Plumas PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
38213 | Plumas PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
38214 | Plumas PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
38215 | Plumas PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
38216 | Plumas PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
38217 | Plumas PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38218 | Plumas PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38219 | Plumas PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 19865SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
38220 | Plumas PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 19864SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
38221 | Plumas PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19867SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38222 | Plumas PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19866SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38223 | Plumas PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38224 | Plumas PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 19870SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
38225 | Plumas PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 19869SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
38226 | Plumas PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
38227 | Plumas PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 19873SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
38228 | Plumas PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 19872SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
38229 | Plumas PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38230 | Plumas PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 19876SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
38231 | Plumas PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 19875SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
38232 | Plumas PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 19878SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
38233 | Plumas PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 19877SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
38234 | Plumas PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38235 | Plumas PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
38236 | Plumas PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38237 | Plumas PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
38238 | Plumas PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38239 | Plumas PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38240 | Plumas PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
38241 | Plumas PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 19887FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38242 | Plumas PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 19886FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38243 | Plumas PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
38244 | Plumas PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 19891FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
38245 | Plumas PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38246 | Plumas PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 19889FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
38247 | Plumas PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
38248 | Plumas PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 19894 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
38249 | Plumas PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19893 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38250 | Plumas PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38251 | Plumas PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19897FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38252 | Plumas PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 19896FS+19d | 19898 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38253 | Plumas PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 19897 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38254 | Plumas PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38255 | Plumas PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 19901 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38256 | Plumas PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 19900 | 19902FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38257 | Plumas PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 19901FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38258 | Plumas PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38259 | Plumas PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38260 | Plumas PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38261 | Plumas PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38262 | Plumas PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19908SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38263 | Plumas PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 19907SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38264 | Plumas PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38265 | Plumas PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38266 | Plumas PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38267 | Plumas PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19913SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38268 | Plumas PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19912SS | 19927SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38269 | Plumas PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38270 | Plumas PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38271 | Plumas PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38272 | Plumas PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38273 | Plumas PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 19919SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38274 | Plumas PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19918SS | 19920SS,19921 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38275 | Plumas PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19919SS | 19921 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38276 | Plumas PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 19919,19920 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38277 | Plumas PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38278 | Plumas PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38279 | Plumas PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19925SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38280 | Plumas PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 19924SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38281 | Plumas PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38282 | Plumas PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19913SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38283 | Plumas PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38284 | Plumas PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 19930SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38285 | Plumas PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 19929SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38286 | Plumas PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38287 | Plumas PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 19933SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38288 | Plumas PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 19932SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38289 | Plumas PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38290 | Plumas PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 19936SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38291 | Plumas PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 19935SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38292 | Plumas PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 19938 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38293 | Plumas PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 19937 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38294 | Plumas PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38295 | Plumas PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38296 | Plumas PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19942SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38297 | Plumas PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19941SS | 19943SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38298 | Plumas PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19942SS | 19944SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38299 | Plumas PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19943SS | 19945SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38300 | Plumas PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19944SS | 19946SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38301 | Plumas PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19945SS | 19947SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38302 | Plumas PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19946SS | 19948SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38303 | Plumas PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19947SS | 19949SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38304 | Plumas PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19948SS | 19950SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38305 | Plumas PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19949SS | 19951SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38306 | Plumas PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 19950SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38307 | Plumas PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
38308 | Plumas PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
38309 | Plumas PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38310 | Plumas PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 19956SS,19960 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38311 | Plumas PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 19955SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
38312 | Plumas PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
38313 | Plumas PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19966 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38314 | Plumas PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 19967 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38315 | Plumas PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 19955 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38316 | Plumas PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
38317 | Plumas PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 19963SS,19971SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38318 | Plumas PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 19962SS | 19964SS,19972SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38319 | Plumas PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 19963SS | 19973SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38320 | Plumas PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
38321 | Plumas PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 19958 | 19967SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38322 | Plumas PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 19959,19966SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38323 | Plumas PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 19976FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38324 | Plumas PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 19970SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38325 | Plumas PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 19969SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38326 | Plumas PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19962SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38327 | Plumas PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19963SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38328 | Plumas PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 19964SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38329 | Plumas PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 19976SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38330 | Plumas PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38331 | Plumas PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 19968FS+12d,19974SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38332 | Riverside PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
38333 | Riverside PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
38334 | Riverside PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
38335 | Riverside PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
38336 | Riverside PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38337 | Riverside PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
38338 | Riverside PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
38339 | Riverside PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38340 | Riverside PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38341 | Riverside PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38342 | Riverside PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38343 | Riverside PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
38344 | Riverside PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38345 | Riverside PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38346 | Riverside PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38347 | Riverside PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38348 | Riverside PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
38349 | Riverside PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38350 | Riverside PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
38351 | Riverside PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
38352 | Riverside PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
38353 | Riverside PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
38354 | Riverside PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
38355 | Riverside PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
38356 | Riverside PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
38357 | Riverside PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
38358 | Riverside PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38359 | Riverside PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38360 | Riverside PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 20006SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
38361 | Riverside PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 20005SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
38362 | Riverside PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20008SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38363 | Riverside PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20007SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38364 | Riverside PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 20011SS,20010SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38365 | Riverside PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 20009SS |  | As Soon As Possible | NA | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
38366 | Riverside PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 20009SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
38367 | Riverside PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
38368 | Riverside PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 20014SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
38369 | Riverside PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 20013SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
38370 | Riverside PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
38371 | Riverside PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 20017SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
38372 | Riverside PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 20016SS |  | Start No Earlier Than | 6/1/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
38373 | Riverside PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 20019SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
38374 | Riverside PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 20018SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
38375 | Riverside PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
38376 | Riverside PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
38377 | Riverside PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 211 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38378 | Riverside PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 166 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
38379 | Riverside PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38380 | Riverside PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38381 | Riverside PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
38382 | Riverside PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 44 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38383 | Riverside PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 295 | 277d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
38384 | Riverside PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 20031FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
38385 | Riverside PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38386 | Riverside PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 20029FS-1d |  | Start No Earlier Than | 9/2/25 | 252 | 277d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
38387 | Riverside PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
38388 | Riverside PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 20034 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
38389 | Riverside PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20033 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38390 | Riverside PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38391 | Riverside PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20037FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
38392 | Riverside PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 20036FS+19d | 20038 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38393 | Riverside PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20037 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38394 | Riverside PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38395 | Riverside PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 20041 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38396 | Riverside PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20040 | 20042FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38397 | Riverside PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 20041FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38398 | Riverside PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38399 | Riverside PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38400 | Riverside PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38401 | Riverside PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38402 | Riverside PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20048SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38403 | Riverside PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 20047SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38404 | Riverside PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38405 | Riverside PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38406 | Riverside PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38407 | Riverside PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20053SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38408 | Riverside PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20052SS | 20067SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38409 | Riverside PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38410 | Riverside PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38411 | Riverside PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38412 | Riverside PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38413 | Riverside PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 20059SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38414 | Riverside PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20058SS | 20060SS,20061 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38415 | Riverside PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20059SS | 20061 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38416 | Riverside PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 20059,20060 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38417 | Riverside PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38418 | Riverside PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38419 | Riverside PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20065SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38420 | Riverside PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 20064SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38421 | Riverside PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38422 | Riverside PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20053SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38423 | Riverside PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38424 | Riverside PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20070SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38425 | Riverside PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20069SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38426 | Riverside PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38427 | Riverside PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 20073SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38428 | Riverside PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 20072SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38429 | Riverside PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38430 | Riverside PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 20076SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38431 | Riverside PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20075SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38432 | Riverside PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 20078 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38433 | Riverside PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 20077 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38434 | Riverside PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38435 | Riverside PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38436 | Riverside PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20082SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38437 | Riverside PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20081SS | 20083SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38438 | Riverside PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20082SS | 20084SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38439 | Riverside PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20083SS | 20085SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38440 | Riverside PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20084SS | 20086SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38441 | Riverside PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20085SS | 20087SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38442 | Riverside PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20086SS | 20088SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38443 | Riverside PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20087SS | 20089SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38444 | Riverside PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20088SS | 20090SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38445 | Riverside PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20089SS | 20091SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38446 | Riverside PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20090SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38447 | Riverside PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
38448 | Riverside PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
38449 | Riverside PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38450 | Riverside PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 20096SS,20100 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38451 | Riverside PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 20095SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
38452 | Riverside PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
38453 | Riverside PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20106 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
38454 | Riverside PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20107 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
38455 | Riverside PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 20095 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38456 | Riverside PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
38457 | Riverside PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 20103SS,20111SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38458 | Riverside PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 20102SS | 20104SS,20112SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38459 | Riverside PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 20103SS | 20113SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38460 | Riverside PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
38461 | Riverside PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 20098 | 20107SS | Start No Earlier Than | 5/1/26 | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
38462 | Riverside PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 20099,20106SS |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
38463 | Riverside PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 20116FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
38464 | Riverside PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 20110SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38465 | Riverside PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 20109SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38466 | Riverside PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 20102SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38467 | Riverside PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 20103SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38468 | Riverside PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 20104SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38469 | Riverside PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 20116SS+44d | Start No Earlier Than | 6/1/26 | 44 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
38470 | Riverside PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38471 | Riverside PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20108FS+12d,20114SS+44d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
38472 | Sacramento PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
38473 | Sacramento PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
38474 | Sacramento PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
38475 | Sacramento PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
38476 | Sacramento PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38477 | Sacramento PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
38478 | Sacramento PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
38479 | Sacramento PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38480 | Sacramento PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38481 | Sacramento PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38482 | Sacramento PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38483 | Sacramento PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
38484 | Sacramento PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38485 | Sacramento PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38486 | Sacramento PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38487 | Sacramento PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38488 | Sacramento PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
38489 | Sacramento PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38490 | Sacramento PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
38491 | Sacramento PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
38492 | Sacramento PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
38493 | Sacramento PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
38494 | Sacramento PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
38495 | Sacramento PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
38496 | Sacramento PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
38497 | Sacramento PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
38498 | Sacramento PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38499 | Sacramento PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38500 | Sacramento PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 20146SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
38501 | Sacramento PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 20145SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
38502 | Sacramento PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20148SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38503 | Sacramento PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20147SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38504 | Sacramento PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38505 | Sacramento PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 20151SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
38506 | Sacramento PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 20150SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
38507 | Sacramento PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
38508 | Sacramento PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 20154SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
38509 | Sacramento PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 20153SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
38510 | Sacramento PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38511 | Sacramento PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 20157SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
38512 | Sacramento PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 20156SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
38513 | Sacramento PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 20159SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
38514 | Sacramento PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 20158SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
38515 | Sacramento PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38516 | Sacramento PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
38517 | Sacramento PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38518 | Sacramento PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
38519 | Sacramento PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38520 | Sacramento PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38521 | Sacramento PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
38522 | Sacramento PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 20168FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38523 | Sacramento PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 20167FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38524 | Sacramento PR - OCM Activities | July 1, 2025 8:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.25
38525 | Sacramento PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 20172FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
38526 | Sacramento PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38527 | Sacramento PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 20170FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
38528 | Sacramento PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
38529 | Sacramento PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 20175 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
38530 | Sacramento PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20174 |  | Start No Earlier Than | 10/1/25 | 42 | 0d | NA | NA | 0 days? | No | 10/1/25 | 12/1/25 | NA | 1
38531 | Sacramento PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38532 | Sacramento PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicabl | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20178FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38533 | Sacramento PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 20177FS+19d | 20179 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38534 | Sacramento PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20178 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38535 | Sacramento PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38536 | Sacramento PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 20182 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38537 | Sacramento PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20181 | 20183FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38538 | Sacramento PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 20182FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38539 | Sacramento PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38540 | Sacramento PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38541 | Sacramento PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38542 | Sacramento PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38543 | Sacramento PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20189SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38544 | Sacramento PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 20188SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38545 | Sacramento PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38546 | Sacramento PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38547 | Sacramento PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38548 | Sacramento PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20194SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38549 | Sacramento PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20193SS | 20208SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38550 | Sacramento PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38551 | Sacramento PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38552 | Sacramento PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38553 | Sacramento PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38554 | Sacramento PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 20200SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38555 | Sacramento PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20199SS | 20201SS,20202 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38556 | Sacramento PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20200SS | 20202 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38557 | Sacramento PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 20200,20201 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38558 | Sacramento PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38559 | Sacramento PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38560 | Sacramento PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20206SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38561 | Sacramento PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 20205SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38562 | Sacramento PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38563 | Sacramento PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20194SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38564 | Sacramento PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38565 | Sacramento PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20211SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38566 | Sacramento PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20210SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38567 | Sacramento PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38568 | Sacramento PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 20214SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38569 | Sacramento PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 20213SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38570 | Sacramento PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38571 | Sacramento PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 20217SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38572 | Sacramento PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20216SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38573 | Sacramento PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 20219 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38574 | Sacramento PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 20218 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38575 | Sacramento PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38576 | Sacramento PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38577 | Sacramento PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20223SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38578 | Sacramento PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20222SS | 20224SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38579 | Sacramento PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20223SS | 20225SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38580 | Sacramento PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20224SS | 20226SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38581 | Sacramento PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20225SS | 20227SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38582 | Sacramento PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20226SS | 20228SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38583 | Sacramento PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20227SS | 20229SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38584 | Sacramento PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20228SS | 20230SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38585 | Sacramento PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20229SS | 20231SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38586 | Sacramento PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20230SS | 20232SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38587 | Sacramento PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20231SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38588 | Sacramento PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
38589 | Sacramento PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
38590 | Sacramento PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38591 | Sacramento PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 20237SS,20241 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38592 | Sacramento PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 20236SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
38593 | Sacramento PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
38594 | Sacramento PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20247 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38595 | Sacramento PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20248 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38596 | Sacramento PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 20236 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38597 | Sacramento PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
38598 | Sacramento PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 20244SS,20252SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38599 | Sacramento PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 20243SS | 20245SS,20253SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38600 | Sacramento PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 20244SS | 20254SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38601 | Sacramento PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
38602 | Sacramento PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 20239 | 20248SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38603 | Sacramento PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 20240,20247SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38604 | Sacramento PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 20257FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38605 | Sacramento PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 20251SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38606 | Sacramento PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 20250SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38607 | Sacramento PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 20243SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38608 | Sacramento PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 20244SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38609 | Sacramento PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 20245SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38610 | Sacramento PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 20257SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38611 | Sacramento PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38612 | Sacramento PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 20249FS+12d,20255SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38613 | San Benito PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 8.0000000000000002E-2
38614 | San Benito PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
38615 | San Benito PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
38616 | San Benito PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
38617 | San Benito PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38618 | San Benito PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
38619 | San Benito PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
38620 | San Benito PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38621 | San Benito PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38622 | San Benito PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38623 | San Benito PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38624 | San Benito PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
38625 | San Benito PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38626 | San Benito PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38627 | San Benito PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38628 | San Benito PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38629 | San Benito PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
38630 | San Benito PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38631 | San Benito PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
38632 | San Benito PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
38633 | San Benito PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
38634 | San Benito PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
38635 | San Benito PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
38636 | San Benito PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
38637 | San Benito PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
38638 | San Benito PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
38639 | San Benito PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38640 | San Benito PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38641 | San Benito PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 20287SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
38642 | San Benito PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 20286SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
38643 | San Benito PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20289SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38644 | San Benito PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20288SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38645 | San Benito PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38646 | San Benito PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 20292SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
38647 | San Benito PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 20291SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
38648 | San Benito PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
38649 | San Benito PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 20295SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
38650 | San Benito PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 20294SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
38651 | San Benito PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38652 | San Benito PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 20298SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
38653 | San Benito PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 20297SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
38654 | San Benito PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 20300SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
38655 | San Benito PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 20299SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
38656 | San Benito PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38657 | San Benito PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
38658 | San Benito PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38659 | San Benito PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
38660 | San Benito PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38661 | San Benito PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38662 | San Benito PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
38663 | San Benito PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 20309FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38664 | San Benito PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 20308FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38665 | San Benito PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
38666 | San Benito PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 20313FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
38667 | San Benito PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38668 | San Benito PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 20311FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
38669 | San Benito PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
38670 | San Benito PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 20316 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
38671 | San Benito PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20315 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38672 | San Benito PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38673 | San Benito PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicabl | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20319FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38674 | San Benito PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 20318FS+19d | 20320 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38675 | San Benito PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20319 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38676 | San Benito PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38677 | San Benito PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 20323 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38678 | San Benito PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20322 | 20324FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38679 | San Benito PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 20323FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38680 | San Benito PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38681 | San Benito PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38682 | San Benito PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 131 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
38683 | San Benito PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38684 | San Benito PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20330SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38685 | San Benito PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20329SS | 20331SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38686 | San Benito PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20330SS | 20332SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38687 | San Benito PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20331SS | 20333SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38688 | San Benito PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20332SS | 20334SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38689 | San Benito PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20333SS | 20335SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38690 | San Benito PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20334SS | 20336SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38691 | San Benito PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20335SS | 20337SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38692 | San Benito PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20336SS | 20338SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38693 | San Benito PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20337SS | 20339SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38694 | San Benito PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20338SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38695 | San Benito PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
38696 | San Benito PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
38697 | San Benito PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38698 | San Benito PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 20344SS,20348 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38699 | San Benito PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 20343SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
38700 | San Benito PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
38701 | San Benito PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20354 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38702 | San Benito PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20355 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38703 | San Benito PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 20343 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38704 | San Benito PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
38705 | San Benito PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 20351SS,20359SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38706 | San Benito PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 20350SS | 20352SS,20360SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38707 | San Benito PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 20351SS | 20361SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38708 | San Benito PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
38709 | San Benito PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 20346 | 20355SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38710 | San Benito PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 20347,20354SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38711 | San Benito PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 20364FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38712 | San Benito PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 20358SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38713 | San Benito PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 20357SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38714 | San Benito PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 20350SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38715 | San Benito PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 20351SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38716 | San Benito PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 20352SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38717 | San Benito PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 20364SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38718 | San Benito PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38719 | San Benito PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 20356FS+12d,20362SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38720 | San Bernardino PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.0000000000000003E-2
38721 | San Bernardino PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
38722 | San Bernardino PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
38723 | San Bernardino PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
38724 | San Bernardino PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38725 | San Bernardino PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
38726 | San Bernardino PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
38727 | San Bernardino PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38728 | San Bernardino PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38729 | San Bernardino PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38730 | San Bernardino PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38731 | San Bernardino PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
38732 | San Bernardino PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38733 | San Bernardino PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38734 | San Bernardino PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38735 | San Bernardino PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38736 | San Bernardino PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
38737 | San Bernardino PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38738 | San Bernardino PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
38739 | San Bernardino PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
38740 | San Bernardino PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
38741 | San Bernardino PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
38742 | San Bernardino PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
38743 | San Bernardino PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
38744 | San Bernardino PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
38745 | San Bernardino PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
38746 | San Bernardino PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38747 | San Bernardino PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38748 | San Bernardino PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 20394SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
38749 | San Bernardino PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 20393SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
38750 | San Bernardino PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20396SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38751 | San Bernardino PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20395SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38752 | San Bernardino PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38753 | San Bernardino PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 20399SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
38754 | San Bernardino PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 20398SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
38755 | San Bernardino PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
38756 | San Bernardino PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 20402SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
38757 | San Bernardino PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 20401SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
38758 | San Bernardino PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38759 | San Bernardino PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 20405SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
38760 | San Bernardino PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 20404SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
38761 | San Bernardino PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 20407SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
38762 | San Bernardino PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 20406SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
38763 | San Bernardino PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38764 | San Bernardino PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
38765 | San Bernardino PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38766 | San Bernardino PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
38767 | San Bernardino PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38768 | San Bernardino PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38769 | San Bernardino PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
38770 | San Bernardino PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 20416FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38771 | San Bernardino PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 20415FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38772 | San Bernardino PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.13
38773 | San Bernardino PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 20420FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
38774 | San Bernardino PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38775 | San Bernardino PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 20418FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | NA | NA | NA | 0
38776 | San Bernardino PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
38777 | San Bernardino PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 20423 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
38778 | San Bernardino PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20422 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38779 | San Bernardino PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38780 | San Bernardino PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if appli | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20426FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38781 | San Bernardino PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 20425FS+19d | 20427 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38782 | San Bernardino PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20426 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38783 | San Bernardino PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38784 | San Bernardino PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and op | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 20430 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38785 | San Bernardino PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20429 | 20431FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38786 | San Bernardino PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 20430FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38787 | San Bernardino PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38788 | San Bernardino PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38789 | San Bernardino PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38790 | San Bernardino PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38791 | San Bernardino PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20437SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38792 | San Bernardino PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 20436SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38793 | San Bernardino PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38794 | San Bernardino PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38795 | San Bernardino PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38796 | San Bernardino PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20442SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38797 | San Bernardino PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20441SS | 20456SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38798 | San Bernardino PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38799 | San Bernardino PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38800 | San Bernardino PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38801 | San Bernardino PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38802 | San Bernardino PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 20448SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38803 | San Bernardino PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20447SS | 20449SS,20450 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38804 | San Bernardino PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20448SS | 20450 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38805 | San Bernardino PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 20448,20449 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38806 | San Bernardino PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38807 | San Bernardino PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38808 | San Bernardino PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20454SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38809 | San Bernardino PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 20453SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38810 | San Bernardino PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38811 | San Bernardino PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20442SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38812 | San Bernardino PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38813 | San Bernardino PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20459SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38814 | San Bernardino PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20458SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38815 | San Bernardino PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38816 | San Bernardino PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 20462SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38817 | San Bernardino PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 20461SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38818 | San Bernardino PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38819 | San Bernardino PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 20465SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38820 | San Bernardino PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20464SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38821 | San Bernardino PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 20467 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38822 | San Bernardino PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 20466 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38823 | San Bernardino PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38824 | San Bernardino PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38825 | San Bernardino PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20471SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38826 | San Bernardino PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20470SS | 20472SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38827 | San Bernardino PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20471SS | 20473SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38828 | San Bernardino PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20472SS | 20474SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38829 | San Bernardino PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20473SS | 20475SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38830 | San Bernardino PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20474SS | 20476SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38831 | San Bernardino PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20475SS | 20477SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38832 | San Bernardino PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Da | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20476SS | 20478SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38833 | San Bernardino PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20477SS | 20479SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38834 | San Bernardino PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20478SS | 20480SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38835 | San Bernardino PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20479SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38836 | San Bernardino PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
38837 | San Bernardino PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
38838 | San Bernardino PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38839 | San Bernardino PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 20485SS,20489 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38840 | San Bernardino PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 20484SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
38841 | San Bernardino PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
38842 | San Bernardino PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20495 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38843 | San Bernardino PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20496 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38844 | San Bernardino PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 20484 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38845 | San Bernardino PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
38846 | San Bernardino PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 20492SS,20500SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38847 | San Bernardino PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 20491SS | 20493SS,20501SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38848 | San Bernardino PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 20492SS | 20502SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38849 | San Bernardino PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
38850 | San Bernardino PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 20487 | 20496SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38851 | San Bernardino PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 20488,20495SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38852 | San Bernardino PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 20505FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38853 | San Bernardino PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 20499SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38854 | San Bernardino PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 20498SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38855 | San Bernardino PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 20491SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38856 | San Bernardino PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 20492SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38857 | San Bernardino PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 20493SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38858 | San Bernardino PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 20505SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38859 | San Bernardino PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38860 | San Bernardino PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 20497FS+12d,20503SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
38861 | San Diego PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
38862 | San Diego PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
38863 | San Diego PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
38864 | San Diego PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
38865 | San Diego PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38866 | San Diego PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
38867 | San Diego PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
38868 | San Diego PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38869 | San Diego PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38870 | San Diego PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38871 | San Diego PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38872 | San Diego PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
38873 | San Diego PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38874 | San Diego PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38875 | San Diego PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38876 | San Diego PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38877 | San Diego PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
38878 | San Diego PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
38879 | San Diego PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
38880 | San Diego PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
38881 | San Diego PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
38882 | San Diego PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
38883 | San Diego PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
38884 | San Diego PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
38885 | San Diego PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
38886 | San Diego PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
38887 | San Diego PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38888 | San Diego PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38889 | San Diego PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 20535SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
38890 | San Diego PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 20534SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
38891 | San Diego PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20537SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38892 | San Diego PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20536SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38893 | San Diego PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 20540SS,20539SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38894 | San Diego PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 20538SS |  | As Soon As Possible | NA | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
38895 | San Diego PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 20538SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
38896 | San Diego PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
38897 | San Diego PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 20543SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
38898 | San Diego PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 20542SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
38899 | San Diego PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
38900 | San Diego PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 20546SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
38901 | San Diego PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 20545SS |  | Start No Earlier Than | 6/1/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
38902 | San Diego PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 20548SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
38903 | San Diego PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 20547SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
38904 | San Diego PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
38905 | San Diego PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
38906 | San Diego PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 211 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38907 | San Diego PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 166 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
38908 | San Diego PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38909 | San Diego PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
38910 | San Diego PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
38911 | San Diego PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 44 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
38912 | San Diego PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 295 | 277d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
38913 | San Diego PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 20560FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
38914 | San Diego PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
38915 | San Diego PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 20558FS-1d |  | Start No Earlier Than | 9/2/25 | 252 | 277d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
38916 | San Diego PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
38917 | San Diego PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 20563 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
38918 | San Diego PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20562 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38919 | San Diego PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38920 | San Diego PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20566FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38921 | San Diego PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 20565FS+19d | 20567 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38922 | San Diego PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20566 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
38923 | San Diego PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38924 | San Diego PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 20570 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38925 | San Diego PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20569 | 20571FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38926 | San Diego PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 20570FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
38927 | San Diego PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
38928 | San Diego PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
38929 | San Diego PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38930 | San Diego PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38931 | San Diego PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20577SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38932 | San Diego PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 20576SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38933 | San Diego PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38934 | San Diego PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38935 | San Diego PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38936 | San Diego PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20582SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38937 | San Diego PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20581SS | 20596SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38938 | San Diego PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38939 | San Diego PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
38940 | San Diego PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38941 | San Diego PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38942 | San Diego PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 20588SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38943 | San Diego PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20587SS | 20589SS,20590 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38944 | San Diego PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20588SS | 20590 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38945 | San Diego PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 20588,20589 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38946 | San Diego PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38947 | San Diego PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38948 | San Diego PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20594SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38949 | San Diego PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 20593SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
38950 | San Diego PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38951 | San Diego PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20582SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38952 | San Diego PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38953 | San Diego PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20599SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
38954 | San Diego PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20598SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
38955 | San Diego PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38956 | San Diego PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 20602SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38957 | San Diego PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 20601SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
38958 | San Diego PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38959 | San Diego PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 20605SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38960 | San Diego PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20604SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38961 | San Diego PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 20607 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38962 | San Diego PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 20606 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
38963 | San Diego PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
38964 | San Diego PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38965 | San Diego PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20611SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38966 | San Diego PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20610SS | 20612SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38967 | San Diego PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20611SS | 20613SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38968 | San Diego PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20612SS | 20614SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38969 | San Diego PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20613SS | 20615SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38970 | San Diego PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20614SS | 20616SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38971 | San Diego PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20615SS | 20617SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38972 | San Diego PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20616SS | 20618SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38973 | San Diego PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20617SS | 20619SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38974 | San Diego PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20618SS | 20620SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38975 | San Diego PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20619SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
38976 | San Diego PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
38977 | San Diego PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
38978 | San Diego PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38979 | San Diego PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 20625SS,20629 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38980 | San Diego PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 20624SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
38981 | San Diego PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
38982 | San Diego PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20635 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
38983 | San Diego PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20636 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
38984 | San Diego PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 20624 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
38985 | San Diego PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
38986 | San Diego PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 20632SS,20640SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38987 | San Diego PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 20631SS | 20633SS,20641SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38988 | San Diego PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 20632SS | 20642SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38989 | San Diego PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
38990 | San Diego PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 20627 | 20636SS | Start No Earlier Than | 5/1/26 | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
38991 | San Diego PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 20628,20635SS |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
38992 | San Diego PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 20645FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
38993 | San Diego PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 20639SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38994 | San Diego PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 20638SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
38995 | San Diego PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 20631SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38996 | San Diego PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 20632SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38997 | San Diego PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 20633SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
38998 | San Diego PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 20645SS+44d | Start No Earlier Than | 6/1/26 | 44 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
38999 | San Diego PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39000 | San Diego PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 20637FS+12d,20643SS+44d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
39001 | San Francisco PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 7.0000000000000007E-2
39002 | San Francisco PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
39003 | San Francisco PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
39004 | San Francisco PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
39005 | San Francisco PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39006 | San Francisco PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
39007 | San Francisco PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
39008 | San Francisco PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39009 | San Francisco PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39010 | San Francisco PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39011 | San Francisco PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39012 | San Francisco PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
39013 | San Francisco PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39014 | San Francisco PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39015 | San Francisco PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39016 | San Francisco PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39017 | San Francisco PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
39018 | San Francisco PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39019 | San Francisco PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
39020 | San Francisco PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
39021 | San Francisco PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
39022 | San Francisco PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
39023 | San Francisco PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
39024 | San Francisco PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
39025 | San Francisco PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
39026 | San Francisco PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
39027 | San Francisco PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39028 | San Francisco PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39029 | San Francisco PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 20675SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
39030 | San Francisco PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 20674SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
39031 | San Francisco PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20677SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39032 | San Francisco PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20676SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39033 | San Francisco PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39034 | San Francisco PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 20680SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
39035 | San Francisco PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 20679SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
39036 | San Francisco PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
39037 | San Francisco PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 20683SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
39038 | San Francisco PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 20682SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
39039 | San Francisco PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39040 | San Francisco PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 20686SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
39041 | San Francisco PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 20685SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
39042 | San Francisco PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 20688SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39043 | San Francisco PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 20687SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39044 | San Francisco PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39045 | San Francisco PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39046 | San Francisco PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39047 | San Francisco PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
39048 | San Francisco PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39049 | San Francisco PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39050 | San Francisco PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
39051 | San Francisco PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 20697FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39052 | San Francisco PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 20696FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39053 | San Francisco PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.13
39054 | San Francisco PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 20701FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
39055 | San Francisco PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39056 | San Francisco PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 20699FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | NA | NA | NA | 0
39057 | San Francisco PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
39058 | San Francisco PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 20704 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
39059 | San Francisco PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20703 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39060 | San Francisco PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39061 | San Francisco PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applic | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20707FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39062 | San Francisco PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 20706FS+19d | 20708 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39063 | San Francisco PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20707 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39064 | San Francisco PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39065 | San Francisco PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 20711 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39066 | San Francisco PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20710 | 20712FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39067 | San Francisco PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 20711FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39068 | San Francisco PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39069 | San Francisco PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39070 | San Francisco PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 131 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
39071 | San Francisco PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39072 | San Francisco PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20718SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39073 | San Francisco PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20717SS | 20719SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39074 | San Francisco PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20718SS | 20720SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39075 | San Francisco PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20719SS | 20721SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39076 | San Francisco PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20720SS | 20722SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39077 | San Francisco PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20721SS | 20723SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39078 | San Francisco PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20722SS | 20724SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39079 | San Francisco PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20723SS | 20725SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39080 | San Francisco PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20724SS | 20726SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39081 | San Francisco PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20725SS | 20727SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39082 | San Francisco PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20726SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39083 | San Francisco PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
39084 | San Francisco PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
39085 | San Francisco PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39086 | San Francisco PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 20732SS,20736 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39087 | San Francisco PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 20731SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
39088 | San Francisco PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
39089 | San Francisco PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20742 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39090 | San Francisco PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20743 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39091 | San Francisco PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 20731 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39092 | San Francisco PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
39093 | San Francisco PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 20739SS,20747SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39094 | San Francisco PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 20738SS | 20740SS,20748SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39095 | San Francisco PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 20739SS | 20749SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39096 | San Francisco PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
39097 | San Francisco PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 20734 | 20743SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39098 | San Francisco PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 20735,20742SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39099 | San Francisco PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 20752FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39100 | San Francisco PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 20746SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39101 | San Francisco PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 20745SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39102 | San Francisco PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 20738SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39103 | San Francisco PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 20739SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39104 | San Francisco PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 20740SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39105 | San Francisco PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 20752SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39106 | San Francisco PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39107 | San Francisco PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 20744FS+12d,20750SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39108 | San Joaquin PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 7.0000000000000007E-2
39109 | San Joaquin PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.22
39110 | San Joaquin PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
39111 | San Joaquin PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
39112 | San Joaquin PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39113 | San Joaquin PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
39114 | San Joaquin PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
39115 | San Joaquin PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39116 | San Joaquin PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39117 | San Joaquin PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39118 | San Joaquin PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39119 | San Joaquin PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
39120 | San Joaquin PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39121 | San Joaquin PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39122 | San Joaquin PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39123 | San Joaquin PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39124 | San Joaquin PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
39125 | San Joaquin PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39126 | San Joaquin PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
39127 | San Joaquin PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
39128 | San Joaquin PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
39129 | San Joaquin PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
39130 | San Joaquin PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
39131 | San Joaquin PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
39132 | San Joaquin PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
39133 | San Joaquin PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
39134 | San Joaquin PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39135 | San Joaquin PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
39136 | San Joaquin PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 20782SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
39137 | San Joaquin PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 20781SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
39138 | San Joaquin PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20784SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | 2/2/26 | NA | NA | 0.20000000000000001
39139 | San Joaquin PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20783SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39140 | San Joaquin PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39141 | San Joaquin PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 20787SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
39142 | San Joaquin PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 20786SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
39143 | San Joaquin PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
39144 | San Joaquin PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 20790SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
39145 | San Joaquin PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 20789SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
39146 | San Joaquin PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39147 | San Joaquin PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 20793SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
39148 | San Joaquin PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 20792SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
39149 | San Joaquin PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 20795SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39150 | San Joaquin PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 20794SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39151 | San Joaquin PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39152 | San Joaquin PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39153 | San Joaquin PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39154 | San Joaquin PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
39155 | San Joaquin PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39156 | San Joaquin PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39157 | San Joaquin PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
39158 | San Joaquin PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 20804FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39159 | San Joaquin PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 20803FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39160 | San Joaquin PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
39161 | San Joaquin PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 20808FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
39162 | San Joaquin PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39163 | San Joaquin PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 20806FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
39164 | San Joaquin PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
39165 | San Joaquin PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 20811 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
39166 | San Joaquin PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20810 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39167 | San Joaquin PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39168 | San Joaquin PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicab | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20814FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39169 | San Joaquin PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 20813FS+19d | 20815 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39170 | San Joaquin PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20814 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39171 | San Joaquin PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39172 | San Joaquin PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and opera | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 20818 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39173 | San Joaquin PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20817 | 20819FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39174 | San Joaquin PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 20818FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39175 | San Joaquin PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39176 | San Joaquin PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39177 | San Joaquin PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39178 | San Joaquin PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39179 | San Joaquin PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20825SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39180 | San Joaquin PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 20824SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39181 | San Joaquin PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39182 | San Joaquin PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39183 | San Joaquin PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39184 | San Joaquin PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20830SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39185 | San Joaquin PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20829SS | 20844SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39186 | San Joaquin PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39187 | San Joaquin PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39188 | San Joaquin PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39189 | San Joaquin PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39190 | San Joaquin PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 20836SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39191 | San Joaquin PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20835SS | 20837SS,20838 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39192 | San Joaquin PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20836SS | 20838 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39193 | San Joaquin PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 20836,20837 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39194 | San Joaquin PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39195 | San Joaquin PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39196 | San Joaquin PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20842SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39197 | San Joaquin PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 20841SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39198 | San Joaquin PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39199 | San Joaquin PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20830SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39200 | San Joaquin PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39201 | San Joaquin PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20847SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39202 | San Joaquin PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20846SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39203 | San Joaquin PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39204 | San Joaquin PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 20850SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39205 | San Joaquin PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 20849SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39206 | San Joaquin PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39207 | San Joaquin PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 20853SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39208 | San Joaquin PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20852SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39209 | San Joaquin PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 20855 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39210 | San Joaquin PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 20854 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39211 | San Joaquin PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39212 | San Joaquin PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39213 | San Joaquin PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20859SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39214 | San Joaquin PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20858SS | 20860SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39215 | San Joaquin PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20859SS | 20861SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39216 | San Joaquin PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20860SS | 20862SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39217 | San Joaquin PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20861SS | 20863SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39218 | San Joaquin PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20862SS | 20864SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39219 | San Joaquin PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20863SS | 20865SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39220 | San Joaquin PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20864SS | 20866SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39221 | San Joaquin PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20865SS | 20867SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39222 | San Joaquin PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20866SS | 20868SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39223 | San Joaquin PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20867SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39224 | San Joaquin PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
39225 | San Joaquin PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
39226 | San Joaquin PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.01
39227 | San Joaquin PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 20873SS,20877 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
39228 | San Joaquin PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 20872SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
39229 | San Joaquin PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
39230 | San Joaquin PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20883 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39231 | San Joaquin PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20884 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39232 | San Joaquin PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 20872 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39233 | San Joaquin PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
39234 | San Joaquin PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 20880SS,20888SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39235 | San Joaquin PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 20879SS | 20881SS,20889SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39236 | San Joaquin PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 20880SS | 20890SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39237 | San Joaquin PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
39238 | San Joaquin PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 20875 | 20884SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39239 | San Joaquin PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 20876,20883SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39240 | San Joaquin PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 20893FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39241 | San Joaquin PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 20887SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39242 | San Joaquin PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 20886SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39243 | San Joaquin PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 20879SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39244 | San Joaquin PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 20880SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39245 | San Joaquin PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 20881SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39246 | San Joaquin PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 20893SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39247 | San Joaquin PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39248 | San Joaquin PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 20885FS+12d,20891SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39249 | San Luis Obispo PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
39250 | San Luis Obispo PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
39251 | San Luis Obispo PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
39252 | San Luis Obispo PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
39253 | San Luis Obispo PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39254 | San Luis Obispo PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
39255 | San Luis Obispo PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
39256 | San Luis Obispo PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39257 | San Luis Obispo PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39258 | San Luis Obispo PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39259 | San Luis Obispo PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39260 | San Luis Obispo PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
39261 | San Luis Obispo PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39262 | San Luis Obispo PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39263 | San Luis Obispo PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39264 | San Luis Obispo PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39265 | San Luis Obispo PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
39266 | San Luis Obispo PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39267 | San Luis Obispo PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
39268 | San Luis Obispo PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
39269 | San Luis Obispo PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
39270 | San Luis Obispo PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
39271 | San Luis Obispo PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
39272 | San Luis Obispo PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
39273 | San Luis Obispo PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
39274 | San Luis Obispo PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
39275 | San Luis Obispo PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39276 | San Luis Obispo PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39277 | San Luis Obispo PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 20923SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
39278 | San Luis Obispo PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 20922SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
39279 | San Luis Obispo PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20925SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39280 | San Luis Obispo PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20924SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39281 | San Luis Obispo PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39282 | San Luis Obispo PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 20928SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
39283 | San Luis Obispo PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 20927SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
39284 | San Luis Obispo PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
39285 | San Luis Obispo PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 20931SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
39286 | San Luis Obispo PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 20930SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
39287 | San Luis Obispo PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39288 | San Luis Obispo PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 20934SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
39289 | San Luis Obispo PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 20933SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
39290 | San Luis Obispo PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 20936SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39291 | San Luis Obispo PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 20935SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39292 | San Luis Obispo PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39293 | San Luis Obispo PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39294 | San Luis Obispo PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39295 | San Luis Obispo PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
39296 | San Luis Obispo PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39297 | San Luis Obispo PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39298 | San Luis Obispo PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
39299 | San Luis Obispo PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 20945FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39300 | San Luis Obispo PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 20944FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39301 | San Luis Obispo PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.22
39302 | San Luis Obispo PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 20949FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
39303 | San Luis Obispo PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39304 | San Luis Obispo PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 20947FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
39305 | San Luis Obispo PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
39306 | San Luis Obispo PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 20952 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
39307 | San Luis Obispo PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 20951 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39308 | San Luis Obispo PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39309 | San Luis Obispo PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if appl | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  | 20955FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/30/25 | NA | 1
39310 | San Luis Obispo PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 20954FS+19d | 20956 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39311 | San Luis Obispo PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20955 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39312 | San Luis Obispo PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39313 | San Luis Obispo PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and o | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 20959 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39314 | San Luis Obispo PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 20958 | 20960FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39315 | San Luis Obispo PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 20959FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39316 | San Luis Obispo PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39317 | San Luis Obispo PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39318 | San Luis Obispo PR - Technical Activities | September 30, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 211 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39319 | San Luis Obispo PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39320 | San Luis Obispo PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20966SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39321 | San Luis Obispo PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 20965SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39322 | San Luis Obispo PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39323 | San Luis Obispo PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39324 | San Luis Obispo PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39325 | San Luis Obispo PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39326 | San Luis Obispo PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39327 | San Luis Obispo PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39328 | San Luis Obispo PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 20974SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39329 | San Luis Obispo PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20973SS | 20975SS,20976 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39330 | San Luis Obispo PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20974SS | 20976 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39331 | San Luis Obispo PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 20974,20975 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39332 | San Luis Obispo PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39333 | San Luis Obispo PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39334 | San Luis Obispo PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 20980SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39335 | San Luis Obispo PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 20979SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39336 | San Luis Obispo PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39337 | San Luis Obispo PR - Review disposition of statewide Forms provided by Project | September 30, 2025 8:00 AM | November 30, 2025 12:00 AM |  |  | Finish No Earlier Than | 11/30/25 | 42 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
39338 | San Luis Obispo PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39339 | San Luis Obispo PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 20985SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39340 | San Luis Obispo PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 20984SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39341 | San Luis Obispo PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39342 | San Luis Obispo PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 20988SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39343 | San Luis Obispo PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 20987SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39344 | San Luis Obispo PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 20990 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39345 | San Luis Obispo PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 20989 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39346 | San Luis Obispo PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39347 | San Luis Obispo PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39348 | San Luis Obispo PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 20994SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39349 | San Luis Obispo PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20993SS | 20995SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39350 | San Luis Obispo PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20994SS | 20996SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39351 | San Luis Obispo PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20995SS | 20997SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39352 | San Luis Obispo PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20996SS | 20998SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39353 | San Luis Obispo PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20997SS | 20999SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39354 | San Luis Obispo PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20998SS | 21000SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39355 | San Luis Obispo PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), D | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 20999SS | 21001SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39356 | San Luis Obispo PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21000SS | 21002SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39357 | San Luis Obispo PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21001SS | 21003SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39358 | San Luis Obispo PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21002SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39359 | San Luis Obispo PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
39360 | San Luis Obispo PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
39361 | San Luis Obispo PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39362 | San Luis Obispo PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 21008SS,21012 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39363 | San Luis Obispo PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 21007SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
39364 | San Luis Obispo PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
39365 | San Luis Obispo PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21018 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39366 | San Luis Obispo PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21019 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39367 | San Luis Obispo PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 21007 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39368 | San Luis Obispo PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
39369 | San Luis Obispo PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 21015SS,21023SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39370 | San Luis Obispo PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 21014SS | 21016SS,21024SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39371 | San Luis Obispo PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 21015SS | 21025SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39372 | San Luis Obispo PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
39373 | San Luis Obispo PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 21010 | 21019SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39374 | San Luis Obispo PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 21011,21018SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39375 | San Luis Obispo PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 21028FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39376 | San Luis Obispo PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 21022SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39377 | San Luis Obispo PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 21021SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39378 | San Luis Obispo PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21014SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39379 | San Luis Obispo PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21015SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39380 | San Luis Obispo PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21016SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39381 | San Luis Obispo PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 21028SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39382 | San Luis Obispo PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39383 | San Luis Obispo PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 21020FS+12d,21026SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39384 | San Mateo PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 7.0000000000000007E-2
39385 | San Mateo PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
39386 | San Mateo PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
39387 | San Mateo PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
39388 | San Mateo PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39389 | San Mateo PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
39390 | San Mateo PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
39391 | San Mateo PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39392 | San Mateo PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39393 | San Mateo PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39394 | San Mateo PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39395 | San Mateo PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
39396 | San Mateo PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39397 | San Mateo PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39398 | San Mateo PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39399 | San Mateo PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39400 | San Mateo PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
39401 | San Mateo PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39402 | San Mateo PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
39403 | San Mateo PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
39404 | San Mateo PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
39405 | San Mateo PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
39406 | San Mateo PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
39407 | San Mateo PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
39408 | San Mateo PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
39409 | San Mateo PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Start No Earlier Than | 6/2/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
39410 | San Mateo PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39411 | San Mateo PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39412 | San Mateo PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 21058SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
39413 | San Mateo PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 21057SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
39414 | San Mateo PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21060SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39415 | San Mateo PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21059SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39416 | San Mateo PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 21063SS,21062SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39417 | San Mateo PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 21061SS |  | As Soon As Possible | NA | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
39418 | San Mateo PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 21061SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
39419 | San Mateo PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
39420 | San Mateo PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 21066SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
39421 | San Mateo PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 21065SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
39422 | San Mateo PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
39423 | San Mateo PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 21069SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
39424 | San Mateo PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 21068SS |  | Start No Earlier Than | 6/1/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
39425 | San Mateo PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 21071SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
39426 | San Mateo PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 21070SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
39427 | San Mateo PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
39428 | San Mateo PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
39429 | San Mateo PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 211 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39430 | San Mateo PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 166 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
39431 | San Mateo PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39432 | San Mateo PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39433 | San Mateo PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
39434 | San Mateo PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 44 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39435 | San Mateo PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 295 | 277d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
39436 | San Mateo PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 21083FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
39437 | San Mateo PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39438 | San Mateo PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 21081FS-1d |  | Start No Earlier Than | 9/2/25 | 252 | 277d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
39439 | San Mateo PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
39440 | San Mateo PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 21086 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
39441 | San Mateo PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21085 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39442 | San Mateo PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39443 | San Mateo PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21089FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39444 | San Mateo PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 21088FS+19d | 21090 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39445 | San Mateo PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 21089 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39446 | San Mateo PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39447 | San Mateo PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 21093 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39448 | San Mateo PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 21092 | 21094FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39449 | San Mateo PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 21093FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39450 | San Mateo PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39451 | San Mateo PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39452 | San Mateo PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39453 | San Mateo PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39454 | San Mateo PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21100SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39455 | San Mateo PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 21099SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39456 | San Mateo PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39457 | San Mateo PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39458 | San Mateo PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39459 | San Mateo PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21105SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39460 | San Mateo PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21104SS | 21119SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39461 | San Mateo PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39462 | San Mateo PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39463 | San Mateo PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39464 | San Mateo PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39465 | San Mateo PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 21111SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39466 | San Mateo PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21110SS | 21112SS,21113 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39467 | San Mateo PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21111SS | 21113 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39468 | San Mateo PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 21111,21112 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39469 | San Mateo PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39470 | San Mateo PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39471 | San Mateo PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21117SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39472 | San Mateo PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 21116SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39473 | San Mateo PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39474 | San Mateo PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21105SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39475 | San Mateo PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39476 | San Mateo PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21122SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39477 | San Mateo PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21121SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39478 | San Mateo PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39479 | San Mateo PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 21125SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39480 | San Mateo PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 21124SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39481 | San Mateo PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39482 | San Mateo PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 21128SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39483 | San Mateo PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21127SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39484 | San Mateo PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 21130 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39485 | San Mateo PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 21129 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39486 | San Mateo PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39487 | San Mateo PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39488 | San Mateo PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21134SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39489 | San Mateo PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21133SS | 21135SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39490 | San Mateo PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21134SS | 21136SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39491 | San Mateo PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21135SS | 21137SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39492 | San Mateo PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21136SS | 21138SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39493 | San Mateo PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21137SS | 21139SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39494 | San Mateo PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21138SS | 21140SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39495 | San Mateo PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21139SS | 21141SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39496 | San Mateo PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21140SS | 21142SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39497 | San Mateo PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21141SS | 21143SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39498 | San Mateo PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21142SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39499 | San Mateo PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
39500 | San Mateo PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
39501 | San Mateo PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.02
39502 | San Mateo PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 21148SS,21152 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
39503 | San Mateo PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 21147SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
39504 | San Mateo PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
39505 | San Mateo PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21158 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
39506 | San Mateo PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21159 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
39507 | San Mateo PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 21147 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39508 | San Mateo PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
39509 | San Mateo PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 21155SS,21163SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39510 | San Mateo PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 21154SS | 21156SS,21164SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39511 | San Mateo PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 21155SS | 21165SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39512 | San Mateo PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
39513 | San Mateo PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 21150 | 21159SS | Start No Earlier Than | 5/1/26 | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
39514 | San Mateo PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 21151,21158SS |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
39515 | San Mateo PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 21168FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
39516 | San Mateo PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 21162SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39517 | San Mateo PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 21161SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39518 | San Mateo PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 21154SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39519 | San Mateo PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 21155SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39520 | San Mateo PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 21156SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39521 | San Mateo PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 21168SS+44d | Start No Earlier Than | 6/1/26 | 44 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
39522 | San Mateo PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39523 | San Mateo PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 21160FS+12d,21166SS+44d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
39524 | Santa Barbara PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
39525 | Santa Barbara PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
39526 | Santa Barbara PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
39527 | Santa Barbara PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
39528 | Santa Barbara PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39529 | Santa Barbara PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
39530 | Santa Barbara PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
39531 | Santa Barbara PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39532 | Santa Barbara PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39533 | Santa Barbara PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39534 | Santa Barbara PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39535 | Santa Barbara PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
39536 | Santa Barbara PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39537 | Santa Barbara PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39538 | Santa Barbara PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39539 | Santa Barbara PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39540 | Santa Barbara PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
39541 | Santa Barbara PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39542 | Santa Barbara PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
39543 | Santa Barbara PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
39544 | Santa Barbara PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
39545 | Santa Barbara PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
39546 | Santa Barbara PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
39547 | Santa Barbara PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
39548 | Santa Barbara PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
39549 | Santa Barbara PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
39550 | Santa Barbara PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39551 | Santa Barbara PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
39552 | Santa Barbara PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 21198SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
39553 | Santa Barbara PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 21197SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
39554 | Santa Barbara PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21200SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39555 | Santa Barbara PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21199SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39556 | Santa Barbara PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39557 | Santa Barbara PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 21203SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
39558 | Santa Barbara PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 21202SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
39559 | Santa Barbara PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
39560 | Santa Barbara PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 21206SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
39561 | Santa Barbara PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 21205SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
39562 | Santa Barbara PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39563 | Santa Barbara PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 21209SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
39564 | Santa Barbara PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 21208SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
39565 | Santa Barbara PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 21211SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39566 | Santa Barbara PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 21210SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39567 | Santa Barbara PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39568 | Santa Barbara PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39569 | Santa Barbara PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39570 | Santa Barbara PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
39571 | Santa Barbara PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39572 | Santa Barbara PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39573 | Santa Barbara PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
39574 | Santa Barbara PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 21220FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39575 | Santa Barbara PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 21219FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39576 | Santa Barbara PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.13
39577 | Santa Barbara PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 21224FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
39578 | Santa Barbara PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39579 | Santa Barbara PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 21222FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | NA | NA | NA | 0
39580 | Santa Barbara PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
39581 | Santa Barbara PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 21227 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
39582 | Santa Barbara PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21226 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39583 | Santa Barbara PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39584 | Santa Barbara PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applic | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21230FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39585 | Santa Barbara PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 21229FS+19d | 21231 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39586 | Santa Barbara PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 21230 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39587 | Santa Barbara PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39588 | Santa Barbara PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 21234 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39589 | Santa Barbara PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 21233 | 21235FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39590 | Santa Barbara PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 21234FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39591 | Santa Barbara PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39592 | Santa Barbara PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39593 | Santa Barbara PR - Technical Activities | September 30, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 211 | 298d | NA | NA | 0 days? | No | 9/30/25 | NA | NA | 0.02
39594 | Santa Barbara PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39595 | Santa Barbara PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21241SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39596 | Santa Barbara PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 21240SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39597 | Santa Barbara PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39598 | Santa Barbara PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39599 | Santa Barbara PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39600 | Santa Barbara PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39601 | Santa Barbara PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39602 | Santa Barbara PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | 12/1/25 | NA | NA | 5.9999999999999998E-2
39603 | Santa Barbara PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 21249SS | Start No Earlier Than | 12/1/25 | 43 | 424d | NA | NA | 0 days? | No | 12/1/25 | NA | NA | 0.59999999999999998
39604 | Santa Barbara PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21248SS | 21250SS,21251 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39605 | Santa Barbara PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21249SS | 21251 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39606 | Santa Barbara PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 21249,21250 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39607 | Santa Barbara PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39608 | Santa Barbara PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39609 | Santa Barbara PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21255SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39610 | Santa Barbara PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 21254SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39611 | Santa Barbara PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39612 | Santa Barbara PR - Review disposition of statewide Forms provided by Project | September 30, 2025 8:00 AM | November 30, 2025 12:00 AM |  |  | Finish No Earlier Than | 11/30/25 | 42 | 467d | NA | NA | 0 days? | No | NA | NA | NA | 0
39613 | Santa Barbara PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39614 | Santa Barbara PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 21260SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39615 | Santa Barbara PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 21259SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39616 | Santa Barbara PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | 12/1/25 | NA | NA | 5.9999999999999998E-2
39617 | Santa Barbara PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 21263SS | Start No Earlier Than | 12/1/25 | 43 | 424d | NA | NA | 0 days? | No | 12/1/25 | NA | NA | 0.59999999999999998
39618 | Santa Barbara PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21262SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39619 | Santa Barbara PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 21265 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39620 | Santa Barbara PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 21264 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39621 | Santa Barbara PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39622 | Santa Barbara PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39623 | Santa Barbara PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21269SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39624 | Santa Barbara PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21268SS | 21270SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39625 | Santa Barbara PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21269SS | 21271SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39626 | Santa Barbara PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21270SS | 21272SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39627 | Santa Barbara PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21271SS | 21273SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39628 | Santa Barbara PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21272SS | 21274SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39629 | Santa Barbara PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21273SS | 21275SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39630 | Santa Barbara PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Dat | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21274SS | 21276SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39631 | Santa Barbara PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21275SS | 21277SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39632 | Santa Barbara PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21276SS | 21278SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39633 | Santa Barbara PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21277SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39634 | Santa Barbara PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
39635 | Santa Barbara PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
39636 | Santa Barbara PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39637 | Santa Barbara PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 21283SS,21287 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39638 | Santa Barbara PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 21282SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
39639 | Santa Barbara PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
39640 | Santa Barbara PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21293 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39641 | Santa Barbara PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21294 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39642 | Santa Barbara PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 21282 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39643 | Santa Barbara PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
39644 | Santa Barbara PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 21290SS,21298SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39645 | Santa Barbara PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 21289SS | 21291SS,21299SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39646 | Santa Barbara PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 21290SS | 21300SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39647 | Santa Barbara PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
39648 | Santa Barbara PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 21285 | 21294SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39649 | Santa Barbara PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 21286,21293SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39650 | Santa Barbara PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 21303FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39651 | Santa Barbara PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 21297SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39652 | Santa Barbara PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 21296SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39653 | Santa Barbara PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21289SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39654 | Santa Barbara PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21290SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39655 | Santa Barbara PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21291SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39656 | Santa Barbara PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 21303SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39657 | Santa Barbara PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39658 | Santa Barbara PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 21295FS+12d,21301SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39659 | Santa Clara PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
39660 | Santa Clara PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
39661 | Santa Clara PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
39662 | Santa Clara PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
39663 | Santa Clara PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39664 | Santa Clara PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
39665 | Santa Clara PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
39666 | Santa Clara PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39667 | Santa Clara PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39668 | Santa Clara PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39669 | Santa Clara PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39670 | Santa Clara PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
39671 | Santa Clara PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39672 | Santa Clara PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39673 | Santa Clara PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39674 | Santa Clara PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39675 | Santa Clara PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
39676 | Santa Clara PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39677 | Santa Clara PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
39678 | Santa Clara PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
39679 | Santa Clara PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
39680 | Santa Clara PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
39681 | Santa Clara PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
39682 | Santa Clara PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
39683 | Santa Clara PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
39684 | Santa Clara PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
39685 | Santa Clara PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39686 | Santa Clara PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39687 | Santa Clara PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 21333SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
39688 | Santa Clara PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 21332SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
39689 | Santa Clara PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21335SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39690 | Santa Clara PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21334SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39691 | Santa Clara PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39692 | Santa Clara PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 21338SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
39693 | Santa Clara PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 21337SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
39694 | Santa Clara PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
39695 | Santa Clara PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 21341SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
39696 | Santa Clara PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 21340SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
39697 | Santa Clara PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39698 | Santa Clara PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 21344SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
39699 | Santa Clara PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 21343SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
39700 | Santa Clara PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 21346SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39701 | Santa Clara PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 21345SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39702 | Santa Clara PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39703 | Santa Clara PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39704 | Santa Clara PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39705 | Santa Clara PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
39706 | Santa Clara PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39707 | Santa Clara PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39708 | Santa Clara PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
39709 | Santa Clara PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 21355FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39710 | Santa Clara PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 21354FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39711 | Santa Clara PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
39712 | Santa Clara PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 21359FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
39713 | Santa Clara PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39714 | Santa Clara PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 21357FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
39715 | Santa Clara PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
39716 | Santa Clara PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 21362 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
39717 | Santa Clara PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21361 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39718 | Santa Clara PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39719 | Santa Clara PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicab | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21365FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39720 | Santa Clara PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 21364FS+19d | 21366 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39721 | Santa Clara PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 21365 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39722 | Santa Clara PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39723 | Santa Clara PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and opera | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 21369 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39724 | Santa Clara PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 21368 | 21370FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39725 | Santa Clara PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 21369FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39726 | Santa Clara PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39727 | Santa Clara PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39728 | Santa Clara PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39729 | Santa Clara PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39730 | Santa Clara PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21376SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39731 | Santa Clara PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 21375SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39732 | Santa Clara PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39733 | Santa Clara PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39734 | Santa Clara PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39735 | Santa Clara PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21381SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39736 | Santa Clara PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21380SS | 21395SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39737 | Santa Clara PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39738 | Santa Clara PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39739 | Santa Clara PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39740 | Santa Clara PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39741 | Santa Clara PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 21387SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39742 | Santa Clara PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21386SS | 21388SS,21389 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39743 | Santa Clara PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21387SS | 21389 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39744 | Santa Clara PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 21387,21388 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39745 | Santa Clara PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39746 | Santa Clara PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39747 | Santa Clara PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21393SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39748 | Santa Clara PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 21392SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39749 | Santa Clara PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39750 | Santa Clara PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21381SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39751 | Santa Clara PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39752 | Santa Clara PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21398SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39753 | Santa Clara PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21397SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39754 | Santa Clara PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39755 | Santa Clara PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 21401SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39756 | Santa Clara PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 21400SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39757 | Santa Clara PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39758 | Santa Clara PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 21404SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39759 | Santa Clara PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21403SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39760 | Santa Clara PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 21406 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39761 | Santa Clara PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 21405 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39762 | Santa Clara PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39763 | Santa Clara PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39764 | Santa Clara PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21410SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39765 | Santa Clara PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21409SS | 21411SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39766 | Santa Clara PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21410SS | 21412SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39767 | Santa Clara PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21411SS | 21413SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39768 | Santa Clara PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21412SS | 21414SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39769 | Santa Clara PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21413SS | 21415SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39770 | Santa Clara PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21414SS | 21416SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39771 | Santa Clara PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21415SS | 21417SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39772 | Santa Clara PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21416SS | 21418SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39773 | Santa Clara PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21417SS | 21419SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39774 | Santa Clara PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21418SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39775 | Santa Clara PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
39776 | Santa Clara PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
39777 | Santa Clara PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39778 | Santa Clara PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 21424SS,21428 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39779 | Santa Clara PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 21423SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
39780 | Santa Clara PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
39781 | Santa Clara PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21434 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39782 | Santa Clara PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21435 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39783 | Santa Clara PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 21423 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39784 | Santa Clara PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
39785 | Santa Clara PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 21431SS,21439SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39786 | Santa Clara PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 21430SS | 21432SS,21440SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39787 | Santa Clara PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 21431SS | 21441SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39788 | Santa Clara PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
39789 | Santa Clara PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 21426 | 21435SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39790 | Santa Clara PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 21427,21434SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39791 | Santa Clara PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 21444FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39792 | Santa Clara PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 21438SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39793 | Santa Clara PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 21437SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39794 | Santa Clara PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21430SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39795 | Santa Clara PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21431SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39796 | Santa Clara PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21432SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39797 | Santa Clara PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 21444SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39798 | Santa Clara PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39799 | Santa Clara PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 21436FS+12d,21442SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39800 | Santa Cruz PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 8.0000000000000002E-2
39801 | Santa Cruz PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
39802 | Santa Cruz PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
39803 | Santa Cruz PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
39804 | Santa Cruz PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39805 | Santa Cruz PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
39806 | Santa Cruz PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
39807 | Santa Cruz PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39808 | Santa Cruz PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39809 | Santa Cruz PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39810 | Santa Cruz PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39811 | Santa Cruz PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
39812 | Santa Cruz PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39813 | Santa Cruz PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39814 | Santa Cruz PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39815 | Santa Cruz PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39816 | Santa Cruz PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
39817 | Santa Cruz PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39818 | Santa Cruz PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
39819 | Santa Cruz PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
39820 | Santa Cruz PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
39821 | Santa Cruz PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
39822 | Santa Cruz PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
39823 | Santa Cruz PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
39824 | Santa Cruz PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
39825 | Santa Cruz PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
39826 | Santa Cruz PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39827 | Santa Cruz PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39828 | Santa Cruz PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 21474SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
39829 | Santa Cruz PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 21473SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
39830 | Santa Cruz PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21476SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39831 | Santa Cruz PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21475SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39832 | Santa Cruz PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39833 | Santa Cruz PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 21479SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
39834 | Santa Cruz PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 21478SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
39835 | Santa Cruz PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
39836 | Santa Cruz PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 21482SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
39837 | Santa Cruz PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 21481SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
39838 | Santa Cruz PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39839 | Santa Cruz PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 21485SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
39840 | Santa Cruz PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 21484SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
39841 | Santa Cruz PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 21487SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39842 | Santa Cruz PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 21486SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39843 | Santa Cruz PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39844 | Santa Cruz PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39845 | Santa Cruz PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39846 | Santa Cruz PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
39847 | Santa Cruz PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39848 | Santa Cruz PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39849 | Santa Cruz PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
39850 | Santa Cruz PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 21496FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39851 | Santa Cruz PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 21495FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39852 | Santa Cruz PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
39853 | Santa Cruz PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 21500FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
39854 | Santa Cruz PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39855 | Santa Cruz PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 21498FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
39856 | Santa Cruz PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
39857 | Santa Cruz PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 21503 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
39858 | Santa Cruz PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21502 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39859 | Santa Cruz PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39860 | Santa Cruz PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicabl | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21506FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39861 | Santa Cruz PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 21505FS+19d | 21507 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39862 | Santa Cruz PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 21506 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39863 | Santa Cruz PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39864 | Santa Cruz PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 21510 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39865 | Santa Cruz PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 21509 | 21511FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39866 | Santa Cruz PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 21510FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39867 | Santa Cruz PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39868 | Santa Cruz PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39869 | Santa Cruz PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 131 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
39870 | Santa Cruz PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39871 | Santa Cruz PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21517SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39872 | Santa Cruz PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21516SS | 21518SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39873 | Santa Cruz PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21517SS | 21519SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39874 | Santa Cruz PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21518SS | 21520SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39875 | Santa Cruz PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21519SS | 21521SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39876 | Santa Cruz PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21520SS | 21522SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39877 | Santa Cruz PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21521SS | 21523SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39878 | Santa Cruz PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21522SS | 21524SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39879 | Santa Cruz PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21523SS | 21525SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39880 | Santa Cruz PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21524SS | 21526SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39881 | Santa Cruz PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21525SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39882 | Santa Cruz PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
39883 | Santa Cruz PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
39884 | Santa Cruz PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39885 | Santa Cruz PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 21531SS,21535 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39886 | Santa Cruz PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 21530SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
39887 | Santa Cruz PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
39888 | Santa Cruz PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21541 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39889 | Santa Cruz PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21542 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39890 | Santa Cruz PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 21530 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39891 | Santa Cruz PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
39892 | Santa Cruz PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 21538SS,21546SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39893 | Santa Cruz PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 21537SS | 21539SS,21547SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39894 | Santa Cruz PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 21538SS | 21548SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39895 | Santa Cruz PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
39896 | Santa Cruz PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 21533 | 21542SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39897 | Santa Cruz PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 21534,21541SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
39898 | Santa Cruz PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 21551FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39899 | Santa Cruz PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 21545SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39900 | Santa Cruz PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 21544SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39901 | Santa Cruz PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21537SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39902 | Santa Cruz PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21538SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39903 | Santa Cruz PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21539SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39904 | Santa Cruz PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 21551SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39905 | Santa Cruz PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39906 | Santa Cruz PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 21543FS+12d,21549SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
39907 | Shasta PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 7.0000000000000007E-2
39908 | Shasta PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20999999999999999
39909 | Shasta PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.26000000000000001
39910 | Shasta PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
39911 | Shasta PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39912 | Shasta PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
39913 | Shasta PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
39914 | Shasta PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39915 | Shasta PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39916 | Shasta PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39917 | Shasta PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39918 | Shasta PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
39919 | Shasta PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39920 | Shasta PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39921 | Shasta PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
39922 | Shasta PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
39923 | Shasta PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
39924 | Shasta PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39925 | Shasta PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
39926 | Shasta PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
39927 | Shasta PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
39928 | Shasta PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
39929 | Shasta PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
39930 | Shasta PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
39931 | Shasta PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
39932 | Shasta PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
39933 | Shasta PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39934 | Shasta PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39935 | Shasta PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 21581SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
39936 | Shasta PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 21580SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
39937 | Shasta PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21583SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39938 | Shasta PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21582SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39939 | Shasta PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39940 | Shasta PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 21586SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
39941 | Shasta PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 21585SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
39942 | Shasta PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
39943 | Shasta PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 21589SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
39944 | Shasta PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 21588SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
39945 | Shasta PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39946 | Shasta PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 21592SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
39947 | Shasta PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 21591SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
39948 | Shasta PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 21594SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39949 | Shasta PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 21593SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39950 | Shasta PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
39951 | Shasta PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
39952 | Shasta PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39953 | Shasta PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
39954 | Shasta PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39955 | Shasta PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
39956 | Shasta PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
39957 | Shasta PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 21603FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39958 | Shasta PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 21602FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
39959 | Shasta PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.23000000000000001
39960 | Shasta PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 21607FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
39961 | Shasta PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
39962 | Shasta PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 21605FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
39963 | Shasta PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
39964 | Shasta PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 21610 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
39965 | Shasta PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21609 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
39966 | Shasta PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39967 | Shasta PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 30, 2025 5:00 PM |  | 21613FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/30/25 | NA | 1
39968 | Shasta PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 21612FS+19d | 21614 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39969 | Shasta PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 21613 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
39970 | Shasta PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39971 | Shasta PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 21617 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39972 | Shasta PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 21616 | 21618FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39973 | Shasta PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 21617FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
39974 | Shasta PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
39975 | Shasta PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
39976 | Shasta PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39977 | Shasta PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39978 | Shasta PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21624SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39979 | Shasta PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 21623SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39980 | Shasta PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39981 | Shasta PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39982 | Shasta PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39983 | Shasta PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21629SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39984 | Shasta PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21628SS | 21643SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39985 | Shasta PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39986 | Shasta PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
39987 | Shasta PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
39988 | Shasta PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39989 | Shasta PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 21635SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39990 | Shasta PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21634SS | 21636SS,21637 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39991 | Shasta PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21635SS | 21637 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39992 | Shasta PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 21635,21636 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
39993 | Shasta PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
39994 | Shasta PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39995 | Shasta PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21641SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
39996 | Shasta PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 21640SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
39997 | Shasta PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
39998 | Shasta PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21629SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
39999 | Shasta PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40000 | Shasta PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21646SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40001 | Shasta PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21645SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40002 | Shasta PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40003 | Shasta PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 21649SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40004 | Shasta PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 21648SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40005 | Shasta PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40006 | Shasta PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 21652SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40007 | Shasta PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21651SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40008 | Shasta PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 21654 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40009 | Shasta PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 21653 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40010 | Shasta PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40011 | Shasta PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40012 | Shasta PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21658SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40013 | Shasta PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21657SS | 21659SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40014 | Shasta PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21658SS | 21660SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40015 | Shasta PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21659SS | 21661SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40016 | Shasta PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21660SS | 21662SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40017 | Shasta PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21661SS | 21663SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40018 | Shasta PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21662SS | 21664SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40019 | Shasta PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21663SS | 21665SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40020 | Shasta PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21664SS | 21666SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40021 | Shasta PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21665SS | 21667SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40022 | Shasta PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21666SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40023 | Shasta PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
40024 | Shasta PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
40025 | Shasta PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40026 | Shasta PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 21672SS,21676 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40027 | Shasta PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 21671SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
40028 | Shasta PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
40029 | Shasta PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21682 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40030 | Shasta PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21683 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40031 | Shasta PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 21671 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40032 | Shasta PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
40033 | Shasta PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 21679SS,21687SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40034 | Shasta PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 21678SS | 21680SS,21688SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40035 | Shasta PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 21679SS | 21689SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40036 | Shasta PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
40037 | Shasta PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 21674 | 21683SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40038 | Shasta PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 21675,21682SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40039 | Shasta PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 21692FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40040 | Shasta PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 21686SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40041 | Shasta PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 21685SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40042 | Shasta PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21678SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40043 | Shasta PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21679SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40044 | Shasta PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21680SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40045 | Shasta PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 21692SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40046 | Shasta PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
40047 | Shasta PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 21684FS+12d,21690SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40048 | Sierra PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
40049 | Sierra PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
40050 | Sierra PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
40051 | Sierra PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
40052 | Sierra PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40053 | Sierra PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
40054 | Sierra PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
40055 | Sierra PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40056 | Sierra PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40057 | Sierra PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40058 | Sierra PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40059 | Sierra PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
40060 | Sierra PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40061 | Sierra PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40062 | Sierra PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40063 | Sierra PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
40064 | Sierra PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
40065 | Sierra PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40066 | Sierra PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
40067 | Sierra PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
40068 | Sierra PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
40069 | Sierra PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
40070 | Sierra PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
40071 | Sierra PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
40072 | Sierra PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
40073 | Sierra PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
40074 | Sierra PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40075 | Sierra PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40076 | Sierra PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 21722SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
40077 | Sierra PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 21721SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
40078 | Sierra PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21724SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40079 | Sierra PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21723SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40080 | Sierra PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40081 | Sierra PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 21727SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
40082 | Sierra PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 21726SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
40083 | Sierra PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
40084 | Sierra PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 21730SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
40085 | Sierra PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 21729SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
40086 | Sierra PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40087 | Sierra PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 21733SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
40088 | Sierra PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 21732SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
40089 | Sierra PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 21735SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40090 | Sierra PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 21734SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40091 | Sierra PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40092 | Sierra PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40093 | Sierra PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40094 | Sierra PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
40095 | Sierra PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40096 | Sierra PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40097 | Sierra PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
40098 | Sierra PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 21744FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40099 | Sierra PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 21743FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40100 | Sierra PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
40101 | Sierra PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 21748FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
40102 | Sierra PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40103 | Sierra PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 21746FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
40104 | Sierra PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
40105 | Sierra PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 21751 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
40106 | Sierra PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21750 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40107 | Sierra PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40108 | Sierra PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21754FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40109 | Sierra PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 21753FS+19d | 21755 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40110 | Sierra PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 21754 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40111 | Sierra PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40112 | Sierra PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 21758 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40113 | Sierra PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 21757 | 21759FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40114 | Sierra PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 21758FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40115 | Sierra PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40116 | Sierra PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40117 | Sierra PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.01
40118 | Sierra PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40119 | Sierra PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21765SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40120 | Sierra PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 21764SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40121 | Sierra PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40122 | Sierra PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40123 | Sierra PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40124 | Sierra PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21770SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40125 | Sierra PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21769SS | 21784SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40126 | Sierra PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40127 | Sierra PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40128 | Sierra PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40129 | Sierra PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40130 | Sierra PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 21776SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40131 | Sierra PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21775SS | 21777SS,21778 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40132 | Sierra PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21776SS | 21778 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40133 | Sierra PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 21776,21777 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40134 | Sierra PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40135 | Sierra PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40136 | Sierra PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21782SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40137 | Sierra PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 21781SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40138 | Sierra PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40139 | Sierra PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21770SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40140 | Sierra PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40141 | Sierra PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21787SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40142 | Sierra PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21786SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40143 | Sierra PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | 11/3/25 | NA | NA | 0.14000000000000001
40144 | Sierra PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 21790SS+18d | Start No Earlier Than | 11/3/25 | 40 | 18.8d | NA | NA | 0 days? | No | NA | NA | NA | 0
40145 | Sierra PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 21789SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | 12/1/25 | NA | NA | 0.20000000000000001
40146 | Sierra PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | 12/1/25 | NA | NA | 0.01
40147 | Sierra PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 21793SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40148 | Sierra PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21792SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40149 | Sierra PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 21795 | Start No Earlier Than | 12/1/25 | 105 | 3.4d | NA | NA | 0 days? | No | NA | NA | NA | 0
40150 | Sierra PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 21794 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | 5/4/26 | NA | NA | 0.20000000000000001
40151 | Sierra PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40152 | Sierra PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40153 | Sierra PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21799SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40154 | Sierra PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21798SS | 21800SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40155 | Sierra PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21799SS | 21801SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40156 | Sierra PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21800SS | 21802SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40157 | Sierra PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21801SS | 21803SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40158 | Sierra PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21802SS | 21804SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40159 | Sierra PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21803SS | 21805SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40160 | Sierra PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21804SS | 21806SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40161 | Sierra PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21805SS | 21807SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40162 | Sierra PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21806SS | 21808SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40163 | Sierra PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21807SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40164 | Sierra PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
40165 | Sierra PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
40166 | Sierra PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40167 | Sierra PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 21813SS,21817 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40168 | Sierra PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 21812SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
40169 | Sierra PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
40170 | Sierra PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21823 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40171 | Sierra PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21824 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40172 | Sierra PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 21812 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40173 | Sierra PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
40174 | Sierra PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 21820SS,21828SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40175 | Sierra PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 21819SS | 21821SS,21829SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40176 | Sierra PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 21820SS | 21830SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40177 | Sierra PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
40178 | Sierra PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 21815 | 21824SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40179 | Sierra PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 21816,21823SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40180 | Sierra PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 21833FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40181 | Sierra PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 21827SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40182 | Sierra PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 21826SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40183 | Sierra PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21819SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40184 | Sierra PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21820SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40185 | Sierra PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21821SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40186 | Sierra PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 21833SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40187 | Sierra PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
40188 | Sierra PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 21825FS+12d,21831SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40189 | Siskiyou PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
40190 | Siskiyou PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
40191 | Siskiyou PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
40192 | Siskiyou PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
40193 | Siskiyou PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40194 | Siskiyou PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
40195 | Siskiyou PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
40196 | Siskiyou PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40197 | Siskiyou PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40198 | Siskiyou PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40199 | Siskiyou PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40200 | Siskiyou PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
40201 | Siskiyou PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40202 | Siskiyou PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40203 | Siskiyou PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40204 | Siskiyou PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
40205 | Siskiyou PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
40206 | Siskiyou PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40207 | Siskiyou PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
40208 | Siskiyou PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
40209 | Siskiyou PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
40210 | Siskiyou PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
40211 | Siskiyou PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
40212 | Siskiyou PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
40213 | Siskiyou PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
40214 | Siskiyou PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
40215 | Siskiyou PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40216 | Siskiyou PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40217 | Siskiyou PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 21863SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
40218 | Siskiyou PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 21862SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
40219 | Siskiyou PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21865SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40220 | Siskiyou PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21864SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40221 | Siskiyou PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40222 | Siskiyou PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 21868SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
40223 | Siskiyou PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 21867SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
40224 | Siskiyou PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
40225 | Siskiyou PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 21871SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
40226 | Siskiyou PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 21870SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
40227 | Siskiyou PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40228 | Siskiyou PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 21874SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
40229 | Siskiyou PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 21873SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
40230 | Siskiyou PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 21876SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40231 | Siskiyou PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 21875SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40232 | Siskiyou PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40233 | Siskiyou PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40234 | Siskiyou PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40235 | Siskiyou PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
40236 | Siskiyou PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40237 | Siskiyou PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40238 | Siskiyou PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
40239 | Siskiyou PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 21885FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40240 | Siskiyou PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 21884FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40241 | Siskiyou PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
40242 | Siskiyou PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 21889FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
40243 | Siskiyou PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40244 | Siskiyou PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 21887FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
40245 | Siskiyou PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
40246 | Siskiyou PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 21892 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
40247 | Siskiyou PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21891 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40248 | Siskiyou PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40249 | Siskiyou PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21895FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40250 | Siskiyou PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 21894FS+19d | 21896 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40251 | Siskiyou PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 21895 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40252 | Siskiyou PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40253 | Siskiyou PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operatio | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 21899 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40254 | Siskiyou PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 21898 | 21900FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40255 | Siskiyou PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 21899FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40256 | Siskiyou PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40257 | Siskiyou PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40258 | Siskiyou PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40259 | Siskiyou PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40260 | Siskiyou PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21906SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40261 | Siskiyou PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 21905SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40262 | Siskiyou PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40263 | Siskiyou PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40264 | Siskiyou PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40265 | Siskiyou PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21911SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40266 | Siskiyou PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21910SS | 21925SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40267 | Siskiyou PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40268 | Siskiyou PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40269 | Siskiyou PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40270 | Siskiyou PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40271 | Siskiyou PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 21917SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40272 | Siskiyou PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21916SS | 21918SS,21919 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40273 | Siskiyou PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21917SS | 21919 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40274 | Siskiyou PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 21917,21918 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40275 | Siskiyou PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40276 | Siskiyou PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40277 | Siskiyou PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21923SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40278 | Siskiyou PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 21922SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40279 | Siskiyou PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40280 | Siskiyou PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21911SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40281 | Siskiyou PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40282 | Siskiyou PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 21928SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40283 | Siskiyou PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 21927SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40284 | Siskiyou PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40285 | Siskiyou PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 21931SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40286 | Siskiyou PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 21930SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40287 | Siskiyou PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40288 | Siskiyou PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 21934SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40289 | Siskiyou PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 21933SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40290 | Siskiyou PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 21936 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40291 | Siskiyou PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 21935 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40292 | Siskiyou PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40293 | Siskiyou PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40294 | Siskiyou PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21940SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40295 | Siskiyou PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21939SS | 21941SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40296 | Siskiyou PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21940SS | 21942SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40297 | Siskiyou PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21941SS | 21943SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40298 | Siskiyou PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21942SS | 21944SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40299 | Siskiyou PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21943SS | 21945SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40300 | Siskiyou PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21944SS | 21946SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40301 | Siskiyou PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data los | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21945SS | 21947SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40302 | Siskiyou PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21946SS | 21948SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40303 | Siskiyou PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21947SS | 21949SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40304 | Siskiyou PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 21948SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40305 | Siskiyou PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
40306 | Siskiyou PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
40307 | Siskiyou PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40308 | Siskiyou PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 21954SS,21958 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40309 | Siskiyou PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 21953SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
40310 | Siskiyou PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
40311 | Siskiyou PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21964 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40312 | Siskiyou PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 21965 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40313 | Siskiyou PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 21953 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40314 | Siskiyou PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
40315 | Siskiyou PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 21961SS,21969SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40316 | Siskiyou PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 21960SS | 21962SS,21970SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40317 | Siskiyou PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 21961SS | 21971SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40318 | Siskiyou PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
40319 | Siskiyou PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 21956 | 21965SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40320 | Siskiyou PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 21957,21964SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40321 | Siskiyou PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 21974FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40322 | Siskiyou PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 21968SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40323 | Siskiyou PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 21967SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40324 | Siskiyou PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21960SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40325 | Siskiyou PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21961SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40326 | Siskiyou PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 21962SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40327 | Siskiyou PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 21974SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40328 | Siskiyou PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
40329 | Siskiyou PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 21966FS+12d,21972SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40330 | Solano PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 7.0000000000000007E-2
40331 | Solano PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20000000000000001
40332 | Solano PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
40333 | Solano PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
40334 | Solano PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40335 | Solano PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
40336 | Solano PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
40337 | Solano PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40338 | Solano PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40339 | Solano PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40340 | Solano PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40341 | Solano PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
40342 | Solano PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40343 | Solano PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40344 | Solano PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40345 | Solano PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
40346 | Solano PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
40347 | Solano PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40348 | Solano PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
40349 | Solano PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
40350 | Solano PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
40351 | Solano PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
40352 | Solano PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
40353 | Solano PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
40354 | Solano PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
40355 | Solano PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
40356 | Solano PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40357 | Solano PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
40358 | Solano PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 22004SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
40359 | Solano PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 22003SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
40360 | Solano PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22006SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40361 | Solano PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22005SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40362 | Solano PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40363 | Solano PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 22009SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
40364 | Solano PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 22008SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
40365 | Solano PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
40366 | Solano PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 22012SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
40367 | Solano PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 22011SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
40368 | Solano PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40369 | Solano PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 22015SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
40370 | Solano PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 22014SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
40371 | Solano PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 22017SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40372 | Solano PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 22016SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40373 | Solano PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40374 | Solano PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40375 | Solano PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40376 | Solano PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
40377 | Solano PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40378 | Solano PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40379 | Solano PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
40380 | Solano PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 22026FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40381 | Solano PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 22025FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40382 | Solano PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
40383 | Solano PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 22030FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
40384 | Solano PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40385 | Solano PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 22028FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
40386 | Solano PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
40387 | Solano PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 22033 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
40388 | Solano PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22032 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
40389 | Solano PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40390 | Solano PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22036FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40391 | Solano PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22035FS+19d | 22037 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40392 | Solano PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 22036 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40393 | Solano PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40394 | Solano PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 22040 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40395 | Solano PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 22039 | 22041FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40396 | Solano PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 22040FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40397 | Solano PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40398 | Solano PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40399 | Solano PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40400 | Solano PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40401 | Solano PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22047SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40402 | Solano PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 22046SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40403 | Solano PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40404 | Solano PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40405 | Solano PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40406 | Solano PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22052SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40407 | Solano PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22051SS | 22066SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40408 | Solano PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40409 | Solano PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40410 | Solano PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40411 | Solano PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40412 | Solano PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 22058SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40413 | Solano PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 22057SS | 22059SS,22060 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40414 | Solano PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 22058SS | 22060 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40415 | Solano PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 22058,22059 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40416 | Solano PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40417 | Solano PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40418 | Solano PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22064SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40419 | Solano PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 22063SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40420 | Solano PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40421 | Solano PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22052SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40422 | Solano PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40423 | Solano PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22069SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40424 | Solano PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22068SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40425 | Solano PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40426 | Solano PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 22072SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40427 | Solano PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 22071SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40428 | Solano PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40429 | Solano PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 22075SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40430 | Solano PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 22074SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40431 | Solano PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 22077 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40432 | Solano PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 22076 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40433 | Solano PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40434 | Solano PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40435 | Solano PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22081SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40436 | Solano PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22080SS | 22082SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40437 | Solano PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22081SS | 22083SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40438 | Solano PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22082SS | 22084SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40439 | Solano PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22083SS | 22085SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40440 | Solano PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22084SS | 22086SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40441 | Solano PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22085SS | 22087SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40442 | Solano PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22086SS | 22088SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40443 | Solano PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22087SS | 22089SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40444 | Solano PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22088SS | 22090SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40445 | Solano PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22089SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40446 | Solano PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
40447 | Solano PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
40448 | Solano PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.01
40449 | Solano PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 22095SS,22099 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
40450 | Solano PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 22094SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
40451 | Solano PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
40452 | Solano PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22105 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40453 | Solano PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22106 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40454 | Solano PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 22094 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40455 | Solano PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
40456 | Solano PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 22102SS,22110SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40457 | Solano PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 22101SS | 22103SS,22111SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40458 | Solano PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 22102SS | 22112SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40459 | Solano PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
40460 | Solano PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 22097 | 22106SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40461 | Solano PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 22098,22105SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40462 | Solano PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 22115FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40463 | Solano PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 22109SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40464 | Solano PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22108SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40465 | Solano PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22101SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40466 | Solano PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22102SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40467 | Solano PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22103SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40468 | Solano PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 22115SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40469 | Solano PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
40470 | Solano PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 22107FS+12d,22113SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40471 | Sonoma PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
40472 | Sonoma PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
40473 | Sonoma PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
40474 | Sonoma PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
40475 | Sonoma PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40476 | Sonoma PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
40477 | Sonoma PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
40478 | Sonoma PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40479 | Sonoma PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40480 | Sonoma PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40481 | Sonoma PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40482 | Sonoma PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
40483 | Sonoma PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40484 | Sonoma PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40485 | Sonoma PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40486 | Sonoma PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
40487 | Sonoma PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
40488 | Sonoma PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40489 | Sonoma PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
40490 | Sonoma PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
40491 | Sonoma PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
40492 | Sonoma PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
40493 | Sonoma PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
40494 | Sonoma PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
40495 | Sonoma PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
40496 | Sonoma PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
40497 | Sonoma PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40498 | Sonoma PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40499 | Sonoma PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 22145SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
40500 | Sonoma PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 22144SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
40501 | Sonoma PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22147SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40502 | Sonoma PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22146SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40503 | Sonoma PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40504 | Sonoma PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 22150SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
40505 | Sonoma PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 22149SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
40506 | Sonoma PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
40507 | Sonoma PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 22153SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
40508 | Sonoma PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 22152SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
40509 | Sonoma PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40510 | Sonoma PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 22156SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
40511 | Sonoma PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 22155SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
40512 | Sonoma PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 22158SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40513 | Sonoma PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 22157SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40514 | Sonoma PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40515 | Sonoma PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40516 | Sonoma PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40517 | Sonoma PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
40518 | Sonoma PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40519 | Sonoma PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40520 | Sonoma PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
40521 | Sonoma PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 22167FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40522 | Sonoma PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 22166FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40523 | Sonoma PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.17000000000000001
40524 | Sonoma PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 22171FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
40525 | Sonoma PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40526 | Sonoma PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 22169FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
40527 | Sonoma PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
40528 | Sonoma PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 22174 | Start No Earlier Than | 9/2/25 | 21 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40529 | Sonoma PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22173 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40530 | Sonoma PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40531 | Sonoma PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22177FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40532 | Sonoma PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22176FS+19d | 22178 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40533 | Sonoma PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 22177 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40534 | Sonoma PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40535 | Sonoma PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 22181 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40536 | Sonoma PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 22180 | 22182FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40537 | Sonoma PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 22181FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40538 | Sonoma PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40539 | Sonoma PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40540 | Sonoma PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40541 | Sonoma PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40542 | Sonoma PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22188SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40543 | Sonoma PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 22187SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40544 | Sonoma PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40545 | Sonoma PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40546 | Sonoma PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40547 | Sonoma PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22193SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40548 | Sonoma PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22192SS | 22207SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40549 | Sonoma PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40550 | Sonoma PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40551 | Sonoma PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40552 | Sonoma PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40553 | Sonoma PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 22199SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40554 | Sonoma PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 22198SS | 22200SS,22201 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40555 | Sonoma PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 22199SS | 22201 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40556 | Sonoma PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 22199,22200 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40557 | Sonoma PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40558 | Sonoma PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40559 | Sonoma PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22205SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40560 | Sonoma PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 22204SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40561 | Sonoma PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40562 | Sonoma PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22193SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40563 | Sonoma PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40564 | Sonoma PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22210SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40565 | Sonoma PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22209SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40566 | Sonoma PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40567 | Sonoma PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 22213SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40568 | Sonoma PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 22212SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40569 | Sonoma PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40570 | Sonoma PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 22216SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40571 | Sonoma PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 22215SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40572 | Sonoma PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 22218 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40573 | Sonoma PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 22217 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40574 | Sonoma PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40575 | Sonoma PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40576 | Sonoma PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22222SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40577 | Sonoma PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22221SS | 22223SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40578 | Sonoma PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22222SS | 22224SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40579 | Sonoma PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22223SS | 22225SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40580 | Sonoma PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22224SS | 22226SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40581 | Sonoma PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22225SS | 22227SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40582 | Sonoma PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22226SS | 22228SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40583 | Sonoma PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22227SS | 22229SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40584 | Sonoma PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22228SS | 22230SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40585 | Sonoma PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22229SS | 22231SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40586 | Sonoma PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22230SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40587 | Sonoma PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
40588 | Sonoma PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
40589 | Sonoma PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40590 | Sonoma PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 22236SS,22240 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40591 | Sonoma PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 22235SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
40592 | Sonoma PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
40593 | Sonoma PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22246 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40594 | Sonoma PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22247 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40595 | Sonoma PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 22235 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40596 | Sonoma PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
40597 | Sonoma PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 22243SS,22251SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40598 | Sonoma PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 22242SS | 22244SS,22252SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40599 | Sonoma PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 22243SS | 22253SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40600 | Sonoma PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
40601 | Sonoma PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 22238 | 22247SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40602 | Sonoma PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 22239,22246SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40603 | Sonoma PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 22256FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40604 | Sonoma PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 22250SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40605 | Sonoma PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22249SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40606 | Sonoma PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22242SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40607 | Sonoma PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22243SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40608 | Sonoma PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22244SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40609 | Sonoma PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 22256SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40610 | Sonoma PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
40611 | Sonoma PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 22248FS+12d,22254SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40612 | Stanislaus PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 8.0000000000000002E-2
40613 | Stanislaus PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.22
40614 | Stanislaus PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.26000000000000001
40615 | Stanislaus PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
40616 | Stanislaus PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40617 | Stanislaus PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
40618 | Stanislaus PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
40619 | Stanislaus PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40620 | Stanislaus PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40621 | Stanislaus PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40622 | Stanislaus PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40623 | Stanislaus PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
40624 | Stanislaus PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40625 | Stanislaus PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40626 | Stanislaus PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40627 | Stanislaus PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
40628 | Stanislaus PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
40629 | Stanislaus PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40630 | Stanislaus PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
40631 | Stanislaus PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
40632 | Stanislaus PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
40633 | Stanislaus PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
40634 | Stanislaus PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
40635 | Stanislaus PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
40636 | Stanislaus PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
40637 | Stanislaus PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
40638 | Stanislaus PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40639 | Stanislaus PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.10000000000000001
40640 | Stanislaus PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 22286SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
40641 | Stanislaus PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 22285SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
40642 | Stanislaus PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22288SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40643 | Stanislaus PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22287SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40644 | Stanislaus PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40645 | Stanislaus PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 22291SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
40646 | Stanislaus PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 22290SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
40647 | Stanislaus PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
40648 | Stanislaus PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 22294SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
40649 | Stanislaus PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 22293SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
40650 | Stanislaus PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40651 | Stanislaus PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 22297SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
40652 | Stanislaus PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 22296SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
40653 | Stanislaus PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 22299SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40654 | Stanislaus PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 22298SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40655 | Stanislaus PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40656 | Stanislaus PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40657 | Stanislaus PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40658 | Stanislaus PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
40659 | Stanislaus PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40660 | Stanislaus PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40661 | Stanislaus PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
40662 | Stanislaus PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 22308FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40663 | Stanislaus PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 22307FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40664 | Stanislaus PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.28000000000000003
40665 | Stanislaus PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 22312FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
40666 | Stanislaus PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40667 | Stanislaus PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 22310FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
40668 | Stanislaus PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
40669 | Stanislaus PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 22315 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
40670 | Stanislaus PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22314 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
40671 | Stanislaus PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40672 | Stanislaus PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicabl | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22318FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
40673 | Stanislaus PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22317FS+19d | 22319 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40674 | Stanislaus PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 22318 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40675 | Stanislaus PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40676 | Stanislaus PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 22322 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40677 | Stanislaus PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 22321 | 22323FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40678 | Stanislaus PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 22322FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40679 | Stanislaus PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40680 | Stanislaus PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40681 | Stanislaus PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40682 | Stanislaus PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40683 | Stanislaus PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22329SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40684 | Stanislaus PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 22328SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40685 | Stanislaus PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40686 | Stanislaus PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40687 | Stanislaus PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40688 | Stanislaus PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22334SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40689 | Stanislaus PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22333SS | 22348SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40690 | Stanislaus PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40691 | Stanislaus PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40692 | Stanislaus PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40693 | Stanislaus PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40694 | Stanislaus PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 22340SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40695 | Stanislaus PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 22339SS | 22341SS,22342 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40696 | Stanislaus PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 22340SS | 22342 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40697 | Stanislaus PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 22340,22341 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40698 | Stanislaus PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40699 | Stanislaus PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40700 | Stanislaus PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22346SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40701 | Stanislaus PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 22345SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40702 | Stanislaus PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40703 | Stanislaus PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22334SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40704 | Stanislaus PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40705 | Stanislaus PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22351SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40706 | Stanislaus PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22350SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40707 | Stanislaus PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40708 | Stanislaus PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 22354SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40709 | Stanislaus PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 22353SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40710 | Stanislaus PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40711 | Stanislaus PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 22357SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40712 | Stanislaus PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 22356SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40713 | Stanislaus PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 22359 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40714 | Stanislaus PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 22358 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40715 | Stanislaus PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40716 | Stanislaus PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40717 | Stanislaus PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22363SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40718 | Stanislaus PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22362SS | 22364SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40719 | Stanislaus PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22363SS | 22365SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40720 | Stanislaus PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22364SS | 22366SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40721 | Stanislaus PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22365SS | 22367SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40722 | Stanislaus PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22366SS | 22368SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40723 | Stanislaus PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22367SS | 22369SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40724 | Stanislaus PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data l | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22368SS | 22370SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40725 | Stanislaus PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22369SS | 22371SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40726 | Stanislaus PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22370SS | 22372SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40727 | Stanislaus PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22371SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40728 | Stanislaus PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
40729 | Stanislaus PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
40730 | Stanislaus PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.01
40731 | Stanislaus PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 22377SS,22381 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
40732 | Stanislaus PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 22376SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
40733 | Stanislaus PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
40734 | Stanislaus PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22387 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40735 | Stanislaus PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22388 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40736 | Stanislaus PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 22376 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40737 | Stanislaus PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
40738 | Stanislaus PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 22384SS,22392SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40739 | Stanislaus PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 22383SS | 22385SS,22393SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40740 | Stanislaus PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 22384SS | 22394SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40741 | Stanislaus PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
40742 | Stanislaus PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 22379 | 22388SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40743 | Stanislaus PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 22380,22387SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40744 | Stanislaus PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 22397FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40745 | Stanislaus PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 22391SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40746 | Stanislaus PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22390SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40747 | Stanislaus PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22383SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40748 | Stanislaus PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22384SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40749 | Stanislaus PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22385SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40750 | Stanislaus PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 22397SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40751 | Stanislaus PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
40752 | Stanislaus PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 22389FS+12d,22395SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40753 | Sutter PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
40754 | Sutter PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
40755 | Sutter PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
40756 | Sutter PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
40757 | Sutter PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40758 | Sutter PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
40759 | Sutter PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
40760 | Sutter PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40761 | Sutter PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40762 | Sutter PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40763 | Sutter PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40764 | Sutter PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
40765 | Sutter PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40766 | Sutter PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40767 | Sutter PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40768 | Sutter PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
40769 | Sutter PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
40770 | Sutter PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40771 | Sutter PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
40772 | Sutter PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
40773 | Sutter PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
40774 | Sutter PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
40775 | Sutter PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
40776 | Sutter PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
40777 | Sutter PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
40778 | Sutter PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
40779 | Sutter PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40780 | Sutter PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40781 | Sutter PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 22427SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
40782 | Sutter PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 22426SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
40783 | Sutter PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22429SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40784 | Sutter PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22428SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40785 | Sutter PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40786 | Sutter PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 22432SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
40787 | Sutter PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 22431SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
40788 | Sutter PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
40789 | Sutter PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 22435SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
40790 | Sutter PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 22434SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
40791 | Sutter PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40792 | Sutter PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 22438SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
40793 | Sutter PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 22437SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
40794 | Sutter PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 22440SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40795 | Sutter PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 22439SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40796 | Sutter PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40797 | Sutter PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40798 | Sutter PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40799 | Sutter PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
40800 | Sutter PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40801 | Sutter PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40802 | Sutter PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
40803 | Sutter PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 22449FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40804 | Sutter PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 22448FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40805 | Sutter PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.22
40806 | Sutter PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 22453FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
40807 | Sutter PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40808 | Sutter PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 22451FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
40809 | Sutter PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
40810 | Sutter PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 22456 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
40811 | Sutter PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22455 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40812 | Sutter PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40813 | Sutter PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22459FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
40814 | Sutter PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22458FS+19d | 22460 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40815 | Sutter PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 22459 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40816 | Sutter PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40817 | Sutter PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 22463 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40818 | Sutter PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 22462 | 22464FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40819 | Sutter PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 22463FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40820 | Sutter PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40821 | Sutter PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40822 | Sutter PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40823 | Sutter PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40824 | Sutter PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22470SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40825 | Sutter PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 22469SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40826 | Sutter PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40827 | Sutter PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40828 | Sutter PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40829 | Sutter PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22475SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40830 | Sutter PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22474SS | 22489SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40831 | Sutter PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40832 | Sutter PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40833 | Sutter PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40834 | Sutter PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40835 | Sutter PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 22481SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40836 | Sutter PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 22480SS | 22482SS,22483 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40837 | Sutter PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 22481SS | 22483 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40838 | Sutter PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 22481,22482 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40839 | Sutter PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40840 | Sutter PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40841 | Sutter PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22487SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40842 | Sutter PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 22486SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40843 | Sutter PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40844 | Sutter PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22475SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40845 | Sutter PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40846 | Sutter PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22492SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
40847 | Sutter PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22491SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40848 | Sutter PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40849 | Sutter PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 22495SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40850 | Sutter PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 22494SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
40851 | Sutter PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40852 | Sutter PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 22498SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40853 | Sutter PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 22497SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40854 | Sutter PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 22500 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40855 | Sutter PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 22499 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
40856 | Sutter PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
40857 | Sutter PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40858 | Sutter PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22504SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40859 | Sutter PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22503SS | 22505SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40860 | Sutter PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22504SS | 22506SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40861 | Sutter PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22505SS | 22507SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40862 | Sutter PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22506SS | 22508SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40863 | Sutter PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22507SS | 22509SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40864 | Sutter PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22508SS | 22510SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40865 | Sutter PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22509SS | 22511SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40866 | Sutter PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22510SS | 22512SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40867 | Sutter PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22511SS | 22513SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40868 | Sutter PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22512SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40869 | Sutter PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
40870 | Sutter PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
40871 | Sutter PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40872 | Sutter PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 22518SS,22522 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40873 | Sutter PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 22517SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
40874 | Sutter PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
40875 | Sutter PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22528 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40876 | Sutter PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22529 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40877 | Sutter PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 22517 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40878 | Sutter PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
40879 | Sutter PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 22525SS,22533SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40880 | Sutter PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 22524SS | 22526SS,22534SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40881 | Sutter PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 22525SS | 22535SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40882 | Sutter PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
40883 | Sutter PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 22520 | 22529SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40884 | Sutter PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 22521,22528SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40885 | Sutter PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 22538FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40886 | Sutter PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 22532SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40887 | Sutter PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22531SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40888 | Sutter PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22524SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40889 | Sutter PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22525SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40890 | Sutter PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22526SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40891 | Sutter PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 22538SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40892 | Sutter PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
40893 | Sutter PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 22530FS+12d,22536SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40894 | Tehama PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 8.0000000000000002E-2
40895 | Tehama PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
40896 | Tehama PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
40897 | Tehama PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
40898 | Tehama PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40899 | Tehama PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
40900 | Tehama PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
40901 | Tehama PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40902 | Tehama PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40903 | Tehama PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
40904 | Tehama PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40905 | Tehama PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
40906 | Tehama PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40907 | Tehama PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40908 | Tehama PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40909 | Tehama PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
40910 | Tehama PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
40911 | Tehama PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40912 | Tehama PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
40913 | Tehama PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
40914 | Tehama PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
40915 | Tehama PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
40916 | Tehama PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
40917 | Tehama PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
40918 | Tehama PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
40919 | Tehama PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
40920 | Tehama PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40921 | Tehama PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
40922 | Tehama PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 22568SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
40923 | Tehama PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 22567SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
40924 | Tehama PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22570SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40925 | Tehama PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22569SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40926 | Tehama PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40927 | Tehama PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 22573SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
40928 | Tehama PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 22572SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
40929 | Tehama PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
40930 | Tehama PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 22576SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
40931 | Tehama PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 22575SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
40932 | Tehama PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40933 | Tehama PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 22579SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
40934 | Tehama PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 22578SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
40935 | Tehama PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 22581SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40936 | Tehama PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 22580SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40937 | Tehama PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
40938 | Tehama PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
40939 | Tehama PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40940 | Tehama PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
40941 | Tehama PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40942 | Tehama PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
40943 | Tehama PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
40944 | Tehama PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 22590FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40945 | Tehama PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 22589FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40946 | Tehama PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
40947 | Tehama PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 22594FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
40948 | Tehama PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
40949 | Tehama PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 22592FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
40950 | Tehama PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
40951 | Tehama PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 22597 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
40952 | Tehama PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22596 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
40953 | Tehama PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40954 | Tehama PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22600FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40955 | Tehama PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22599FS+19d | 22601 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40956 | Tehama PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 22600 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
40957 | Tehama PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40958 | Tehama PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 22604 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40959 | Tehama PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 22603 | 22605FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40960 | Tehama PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 22604FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
40961 | Tehama PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
40962 | Tehama PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40963 | Tehama PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 131 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
40964 | Tehama PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40965 | Tehama PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22611SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40966 | Tehama PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22610SS | 22612SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40967 | Tehama PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22611SS | 22613SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40968 | Tehama PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22612SS | 22614SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40969 | Tehama PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22613SS | 22615SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40970 | Tehama PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22614SS | 22616SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40971 | Tehama PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22615SS | 22617SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40972 | Tehama PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22616SS | 22618SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40973 | Tehama PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22617SS | 22619SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40974 | Tehama PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22618SS | 22620SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40975 | Tehama PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22619SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
40976 | Tehama PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
40977 | Tehama PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
40978 | Tehama PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40979 | Tehama PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 22625SS,22629 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40980 | Tehama PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 22624SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
40981 | Tehama PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
40982 | Tehama PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22635 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40983 | Tehama PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22636 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40984 | Tehama PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 22624 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
40985 | Tehama PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
40986 | Tehama PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 22632SS,22640SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40987 | Tehama PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 22631SS | 22633SS,22641SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40988 | Tehama PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 22632SS | 22642SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
40989 | Tehama PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
40990 | Tehama PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 22627 | 22636SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40991 | Tehama PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 22628,22635SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
40992 | Tehama PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 22645FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40993 | Tehama PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 22639SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40994 | Tehama PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22638SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
40995 | Tehama PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22631SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40996 | Tehama PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22632SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40997 | Tehama PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22633SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40998 | Tehama PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 22645SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
40999 | Tehama PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41000 | Tehama PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 22637FS+12d,22643SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41001 | Trinity PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 8.0000000000000002E-2
41002 | Trinity PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
41003 | Trinity PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
41004 | Trinity PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
41005 | Trinity PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41006 | Trinity PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
41007 | Trinity PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
41008 | Trinity PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41009 | Trinity PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41010 | Trinity PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
41011 | Trinity PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41012 | Trinity PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
41013 | Trinity PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41014 | Trinity PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41015 | Trinity PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41016 | Trinity PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41017 | Trinity PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
41018 | Trinity PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41019 | Trinity PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
41020 | Trinity PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
41021 | Trinity PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
41022 | Trinity PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
41023 | Trinity PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
41024 | Trinity PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
41025 | Trinity PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
41026 | Trinity PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
41027 | Trinity PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41028 | Trinity PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41029 | Trinity PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 22675SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
41030 | Trinity PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 22674SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
41031 | Trinity PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22677SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41032 | Trinity PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22676SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41033 | Trinity PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41034 | Trinity PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 22680SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
41035 | Trinity PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 22679SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
41036 | Trinity PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
41037 | Trinity PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 22683SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
41038 | Trinity PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 22682SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
41039 | Trinity PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41040 | Trinity PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 22686SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41041 | Trinity PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 22685SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
41042 | Trinity PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 22688SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
41043 | Trinity PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 22687SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
41044 | Trinity PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41045 | Trinity PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
41046 | Trinity PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41047 | Trinity PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
41048 | Trinity PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41049 | Trinity PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41050 | Trinity PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
41051 | Trinity PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 22697FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41052 | Trinity PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 22696FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41053 | Trinity PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
41054 | Trinity PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 22701FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
41055 | Trinity PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41056 | Trinity PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 22699FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
41057 | Trinity PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
41058 | Trinity PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 22704 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
41059 | Trinity PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22703 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41060 | Trinity PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41061 | Trinity PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22707FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41062 | Trinity PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22706FS+19d | 22708 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41063 | Trinity PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 22707 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41064 | Trinity PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41065 | Trinity PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operation | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 22711 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41066 | Trinity PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 22710 | 22712FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41067 | Trinity PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 22711FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41068 | Trinity PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41069 | Trinity PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
41070 | Trinity PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 131 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
41071 | Trinity PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41072 | Trinity PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22718SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41073 | Trinity PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22717SS | 22719SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41074 | Trinity PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22718SS | 22720SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41075 | Trinity PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22719SS | 22721SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41076 | Trinity PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22720SS | 22722SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41077 | Trinity PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22721SS | 22723SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41078 | Trinity PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22722SS | 22724SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41079 | Trinity PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22723SS | 22725SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41080 | Trinity PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22724SS | 22726SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41081 | Trinity PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22725SS | 22727SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41082 | Trinity PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22726SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41083 | Trinity PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
41084 | Trinity PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
41085 | Trinity PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41086 | Trinity PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 22732SS,22736 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41087 | Trinity PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 22731SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
41088 | Trinity PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
41089 | Trinity PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22742 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41090 | Trinity PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22743 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41091 | Trinity PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 22731 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41092 | Trinity PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
41093 | Trinity PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 22739SS,22747SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41094 | Trinity PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 22738SS | 22740SS,22748SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
41095 | Trinity PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 22739SS | 22749SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
41096 | Trinity PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
41097 | Trinity PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 22734 | 22743SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41098 | Trinity PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 22735,22742SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41099 | Trinity PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 22752FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41100 | Trinity PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 22746SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41101 | Trinity PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22745SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41102 | Trinity PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22738SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41103 | Trinity PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22739SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41104 | Trinity PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22740SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41105 | Trinity PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 22752SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41106 | Trinity PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41107 | Trinity PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 22744FS+12d,22750SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41108 | Tulare PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
41109 | Tulare PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
41110 | Tulare PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
41111 | Tulare PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
41112 | Tulare PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41113 | Tulare PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
41114 | Tulare PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
41115 | Tulare PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41116 | Tulare PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41117 | Tulare PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
41118 | Tulare PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41119 | Tulare PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
41120 | Tulare PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41121 | Tulare PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41122 | Tulare PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41123 | Tulare PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41124 | Tulare PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
41125 | Tulare PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41126 | Tulare PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
41127 | Tulare PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
41128 | Tulare PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
41129 | Tulare PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
41130 | Tulare PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
41131 | Tulare PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
41132 | Tulare PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
41133 | Tulare PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
41134 | Tulare PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41135 | Tulare PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41136 | Tulare PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 22782SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
41137 | Tulare PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 22781SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
41138 | Tulare PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22784SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41139 | Tulare PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22783SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41140 | Tulare PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41141 | Tulare PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 22787SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
41142 | Tulare PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 22786SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
41143 | Tulare PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
41144 | Tulare PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 22790SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
41145 | Tulare PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 22789SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
41146 | Tulare PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41147 | Tulare PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 22793SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41148 | Tulare PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 22792SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
41149 | Tulare PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 22795SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
41150 | Tulare PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 22794SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
41151 | Tulare PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41152 | Tulare PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
41153 | Tulare PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41154 | Tulare PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
41155 | Tulare PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41156 | Tulare PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41157 | Tulare PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
41158 | Tulare PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 22804FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41159 | Tulare PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 22803FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41160 | Tulare PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
41161 | Tulare PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 22808FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
41162 | Tulare PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41163 | Tulare PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 22806FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
41164 | Tulare PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
41165 | Tulare PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 22811 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
41166 | Tulare PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22810 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41167 | Tulare PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41168 | Tulare PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22814FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41169 | Tulare PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22813FS+19d | 22815 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41170 | Tulare PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 22814 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41171 | Tulare PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41172 | Tulare PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 22818 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41173 | Tulare PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 22817 | 22819FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41174 | Tulare PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 22818FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41175 | Tulare PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41176 | Tulare PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
41177 | Tulare PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41178 | Tulare PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41179 | Tulare PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22825SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
41180 | Tulare PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 22824SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
41181 | Tulare PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41182 | Tulare PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41183 | Tulare PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41184 | Tulare PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22830SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
41185 | Tulare PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22829SS | 22844SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41186 | Tulare PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41187 | Tulare PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41188 | Tulare PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41189 | Tulare PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41190 | Tulare PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 22836SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41191 | Tulare PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 22835SS | 22837SS,22838 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41192 | Tulare PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 22836SS | 22838 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41193 | Tulare PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 22836,22837 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41194 | Tulare PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41195 | Tulare PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41196 | Tulare PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22842SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
41197 | Tulare PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 22841SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
41198 | Tulare PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41199 | Tulare PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22830SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41200 | Tulare PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41201 | Tulare PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22847SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
41202 | Tulare PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22846SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41203 | Tulare PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41204 | Tulare PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 22850SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41205 | Tulare PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 22849SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41206 | Tulare PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41207 | Tulare PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 22853SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41208 | Tulare PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 22852SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41209 | Tulare PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 22855 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41210 | Tulare PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 22854 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41211 | Tulare PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41212 | Tulare PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41213 | Tulare PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22859SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41214 | Tulare PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22858SS | 22860SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41215 | Tulare PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22859SS | 22861SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41216 | Tulare PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22860SS | 22862SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41217 | Tulare PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22861SS | 22863SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41218 | Tulare PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22862SS | 22864SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41219 | Tulare PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22863SS | 22865SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41220 | Tulare PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22864SS | 22866SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41221 | Tulare PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22865SS | 22867SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41222 | Tulare PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22866SS | 22868SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41223 | Tulare PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22867SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41224 | Tulare PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
41225 | Tulare PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
41226 | Tulare PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41227 | Tulare PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 22873SS,22877 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41228 | Tulare PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 22872SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
41229 | Tulare PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
41230 | Tulare PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22883 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41231 | Tulare PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22884 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41232 | Tulare PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 22872 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41233 | Tulare PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
41234 | Tulare PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 22880SS,22888SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41235 | Tulare PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 22879SS | 22881SS,22889SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
41236 | Tulare PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 22880SS | 22890SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
41237 | Tulare PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
41238 | Tulare PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 22875 | 22884SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41239 | Tulare PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 22876,22883SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41240 | Tulare PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 22893FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41241 | Tulare PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 22887SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41242 | Tulare PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22886SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41243 | Tulare PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22879SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41244 | Tulare PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22880SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41245 | Tulare PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 22881SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41246 | Tulare PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 22893SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41247 | Tulare PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41248 | Tulare PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 22885FS+12d,22891SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41249 | Tuolumne PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 8.0000000000000002E-2
41250 | Tuolumne PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.20999999999999999
41251 | Tuolumne PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.26000000000000001
41252 | Tuolumne PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
41253 | Tuolumne PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41254 | Tuolumne PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
41255 | Tuolumne PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
41256 | Tuolumne PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41257 | Tuolumne PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41258 | Tuolumne PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
41259 | Tuolumne PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41260 | Tuolumne PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
41261 | Tuolumne PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41262 | Tuolumne PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41263 | Tuolumne PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41264 | Tuolumne PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41265 | Tuolumne PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
41266 | Tuolumne PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41267 | Tuolumne PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
41268 | Tuolumne PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
41269 | Tuolumne PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
41270 | Tuolumne PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
41271 | Tuolumne PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
41272 | Tuolumne PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
41273 | Tuolumne PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
41274 | Tuolumne PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
41275 | Tuolumne PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41276 | Tuolumne PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41277 | Tuolumne PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 22923SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
41278 | Tuolumne PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 22922SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
41279 | Tuolumne PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22925SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41280 | Tuolumne PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22924SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41281 | Tuolumne PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 22928SS,22927SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41282 | Tuolumne PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 22926SS |  | As Soon As Possible | NA | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
41283 | Tuolumne PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 22926SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
41284 | Tuolumne PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
41285 | Tuolumne PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 22931SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
41286 | Tuolumne PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 22930SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
41287 | Tuolumne PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
41288 | Tuolumne PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 22934SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
41289 | Tuolumne PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 22933SS |  | Start No Earlier Than | 6/1/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
41290 | Tuolumne PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 22936SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
41291 | Tuolumne PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 22935SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
41292 | Tuolumne PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
41293 | Tuolumne PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
41294 | Tuolumne PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 211 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41295 | Tuolumne PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 166 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41296 | Tuolumne PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41297 | Tuolumne PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41298 | Tuolumne PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41299 | Tuolumne PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 44 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41300 | Tuolumne PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 295 | 277d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.13
41301 | Tuolumne PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 22948FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
41302 | Tuolumne PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41303 | Tuolumne PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 22946FS-1d |  | Start No Earlier Than | 9/2/25 | 252 | 277d | NA | NA | 0 days? | No | NA | NA | NA | 0
41304 | Tuolumne PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
41305 | Tuolumne PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 22951 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
41306 | Tuolumne PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 22950 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41307 | Tuolumne PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41308 | Tuolumne PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 22954FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41309 | Tuolumne PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 22953FS+19d | 22955 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41310 | Tuolumne PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 22954 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41311 | Tuolumne PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41312 | Tuolumne PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 22958 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41313 | Tuolumne PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 22957 | 22959FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41314 | Tuolumne PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 22958FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41315 | Tuolumne PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41316 | Tuolumne PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
41317 | Tuolumne PR - Technical Activities | January 2, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
41318 | Tuolumne PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41319 | Tuolumne PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22965SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41320 | Tuolumne PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22964SS | 22966SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41321 | Tuolumne PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22965SS | 22967SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41322 | Tuolumne PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22966SS | 22968SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41323 | Tuolumne PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22967SS | 22969SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41324 | Tuolumne PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22968SS | 22970SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41325 | Tuolumne PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22969SS | 22971SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41326 | Tuolumne PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22970SS | 22972SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41327 | Tuolumne PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22971SS | 22973SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41328 | Tuolumne PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22972SS | 22974SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41329 | Tuolumne PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 22973SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41330 | Tuolumne PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
41331 | Tuolumne PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
41332 | Tuolumne PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41333 | Tuolumne PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 22979SS,22983 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41334 | Tuolumne PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 22978SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
41335 | Tuolumne PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
41336 | Tuolumne PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22989 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
41337 | Tuolumne PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 22990 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
41338 | Tuolumne PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 22978 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41339 | Tuolumne PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
41340 | Tuolumne PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 22986SS,22994SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41341 | Tuolumne PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 22985SS | 22987SS,22995SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41342 | Tuolumne PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 22986SS | 22996SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41343 | Tuolumne PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
41344 | Tuolumne PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 22981 | 22990SS | Start No Earlier Than | 5/1/26 | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
41345 | Tuolumne PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 22982,22989SS |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
41346 | Tuolumne PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 22999FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41347 | Tuolumne PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 22993SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41348 | Tuolumne PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 22992SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41349 | Tuolumne PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22985SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41350 | Tuolumne PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22986SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41351 | Tuolumne PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 22987SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41352 | Tuolumne PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 22999SS+44d | Start No Earlier Than | 6/1/26 | 44 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41353 | Tuolumne PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41354 | Tuolumne PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 22991FS+12d,22997SS+44d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41355 | Ventura PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 5.9999999999999998E-2
41356 | Ventura PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
41357 | Ventura PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
41358 | Ventura PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
41359 | Ventura PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41360 | Ventura PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
41361 | Ventura PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
41362 | Ventura PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41363 | Ventura PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41364 | Ventura PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
41365 | Ventura PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41366 | Ventura PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
41367 | Ventura PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41368 | Ventura PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41369 | Ventura PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41370 | Ventura PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41371 | Ventura PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
41372 | Ventura PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41373 | Ventura PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
41374 | Ventura PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
41375 | Ventura PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
41376 | Ventura PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
41377 | Ventura PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
41378 | Ventura PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
41379 | Ventura PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
41380 | Ventura PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
41381 | Ventura PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41382 | Ventura PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41383 | Ventura PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 23029SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
41384 | Ventura PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 23028SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
41385 | Ventura PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 23031SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41386 | Ventura PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23030SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41387 | Ventura PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 23034SS,23033SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41388 | Ventura PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 23032SS |  | As Soon As Possible | NA | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
41389 | Ventura PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 23032SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
41390 | Ventura PR - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
41391 | Ventura PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 23037SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
41392 | Ventura PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 23036SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
41393 | Ventura PR - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
41394 | Ventura PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 23040SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
41395 | Ventura PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 23039SS |  | Start No Earlier Than | 6/1/26 | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
41396 | Ventura PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 23042SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
41397 | Ventura PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 23041SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
41398 | Ventura PR - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
41399 | Ventura PR - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
41400 | Ventura PR - Data Quality | January 2, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 211 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41401 | Ventura PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | As Soon As Possible | NA | 166 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41402 | Ventura PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41403 | Ventura PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41404 | Ventura PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 28, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 42 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41405 | Ventura PR - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 44 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41406 | Ventura PR - OCM Activities | July 1, 2025 12:00 AM | September 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 295 | 277d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
41407 | Ventura PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 23054FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
41408 | Ventura PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41409 | Ventura PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | September 1, 2026 5:00 PM | 23052FS-1d |  | Start No Earlier Than | 9/2/25 | 252 | 277d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
41410 | Ventura PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
41411 | Ventura PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 23057 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
41412 | Ventura PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 23056 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41413 | Ventura PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41414 | Ventura PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 23060FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41415 | Ventura PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 23059FS+19d | 23061 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41416 | Ventura PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 23060 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41417 | Ventura PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41418 | Ventura PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operati | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 23064 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41419 | Ventura PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 23063 | 23065FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41420 | Ventura PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 23064FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41421 | Ventura PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41422 | Ventura PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
41423 | Ventura PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41424 | Ventura PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41425 | Ventura PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 23071SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
41426 | Ventura PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 23070SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
41427 | Ventura PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41428 | Ventura PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41429 | Ventura PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41430 | Ventura PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 23076SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
41431 | Ventura PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 23075SS | 23090SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41432 | Ventura PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41433 | Ventura PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41434 | Ventura PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41435 | Ventura PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41436 | Ventura PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 23082SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41437 | Ventura PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 23081SS | 23083SS,23084 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41438 | Ventura PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 23082SS | 23084 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41439 | Ventura PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 23082,23083 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41440 | Ventura PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41441 | Ventura PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41442 | Ventura PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 23088SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
41443 | Ventura PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 23087SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
41444 | Ventura PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41445 | Ventura PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 23076SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41446 | Ventura PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41447 | Ventura PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 23093SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
41448 | Ventura PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 23092SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41449 | Ventura PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41450 | Ventura PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 23096SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41451 | Ventura PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 23095SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41452 | Ventura PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41453 | Ventura PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 23099SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41454 | Ventura PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 23098SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41455 | Ventura PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 23101 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41456 | Ventura PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 23100 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41457 | Ventura PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41458 | Ventura PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41459 | Ventura PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 23105SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41460 | Ventura PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23104SS | 23106SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41461 | Ventura PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23105SS | 23107SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41462 | Ventura PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23106SS | 23108SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41463 | Ventura PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23107SS | 23109SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41464 | Ventura PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23108SS | 23110SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41465 | Ventura PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23109SS | 23111SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41466 | Ventura PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data lo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23110SS | 23112SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41467 | Ventura PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23111SS | 23113SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41468 | Ventura PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23112SS | 23114SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41469 | Ventura PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23113SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41470 | Ventura PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
41471 | Ventura PR - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
41472 | Ventura PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41473 | Ventura PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 23119SS,23123 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41474 | Ventura PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 23118SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
41475 | Ventura PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
41476 | Ventura PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 23129 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
41477 | Ventura PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 23130 | Start No Earlier Than | 2/2/26 | 63 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
41478 | Ventura PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 23118 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41479 | Ventura PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
41480 | Ventura PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 23126SS,23134SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41481 | Ventura PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 23125SS | 23127SS,23135SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41482 | Ventura PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 23126SS | 23136SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41483 | Ventura PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
41484 | Ventura PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 23121 | 23130SS | Start No Earlier Than | 5/1/26 | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
41485 | Ventura PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | September 8, 2026 5:00 PM | 23122,23129SS |  | As Soon As Possible | NA | 89 | 273d | NA | NA | 0 days? | No | NA | NA | NA | 0
41486 | Ventura PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 23139FS+12d | Start No Earlier Than | 5/4/26 | 51 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41487 | Ventura PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 23133SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41488 | Ventura PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 23132SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41489 | Ventura PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23125SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41490 | Ventura PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23126SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41491 | Ventura PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23127SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41492 | Ventura PR - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 23139SS+44d | Start No Earlier Than | 6/1/26 | 44 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41493 | Ventura PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41494 | Ventura PR - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 23131FS+12d,23137SS+44d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41495 | Yolo PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 8.0000000000000002E-2
41496 | Yolo PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
41497 | Yolo PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
41498 | Yolo PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
41499 | Yolo PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41500 | Yolo PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
41501 | Yolo PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
41502 | Yolo PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41503 | Yolo PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41504 | Yolo PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
41505 | Yolo PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41506 | Yolo PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
41507 | Yolo PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41508 | Yolo PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41509 | Yolo PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41510 | Yolo PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41511 | Yolo PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
41512 | Yolo PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41513 | Yolo PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
41514 | Yolo PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
41515 | Yolo PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
41516 | Yolo PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
41517 | Yolo PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
41518 | Yolo PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
41519 | Yolo PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
41520 | Yolo PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
41521 | Yolo PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41522 | Yolo PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41523 | Yolo PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 23169SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
41524 | Yolo PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 23168SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
41525 | Yolo PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 23171SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41526 | Yolo PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23170SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41527 | Yolo PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41528 | Yolo PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 23174SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
41529 | Yolo PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 23173SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
41530 | Yolo PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
41531 | Yolo PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 23177SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
41532 | Yolo PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 23176SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
41533 | Yolo PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41534 | Yolo PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 23180SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41535 | Yolo PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 23179SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
41536 | Yolo PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 23182SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
41537 | Yolo PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 23181SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
41538 | Yolo PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41539 | Yolo PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
41540 | Yolo PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41541 | Yolo PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
41542 | Yolo PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41543 | Yolo PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41544 | Yolo PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
41545 | Yolo PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 23191FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41546 | Yolo PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 23190FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41547 | Yolo PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20999999999999999
41548 | Yolo PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 23195FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
41549 | Yolo PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41550 | Yolo PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 23193FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
41551 | Yolo PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
41552 | Yolo PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 23198 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
41553 | Yolo PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 23197 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
41554 | Yolo PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41555 | Yolo PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 23201FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41556 | Yolo PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 23200FS+19d | 23202 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41557 | Yolo PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 23201 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41558 | Yolo PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41559 | Yolo PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 23205 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41560 | Yolo PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 23204 | 23206FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41561 | Yolo PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 23205FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41562 | Yolo PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41563 | Yolo PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
41564 | Yolo PR - Technical Activities | January 2, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 131 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
41565 | Yolo PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41566 | Yolo PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 23212SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41567 | Yolo PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23211SS | 23213SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41568 | Yolo PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23212SS | 23214SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41569 | Yolo PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23213SS | 23215SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41570 | Yolo PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23214SS | 23216SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41571 | Yolo PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23215SS | 23217SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41572 | Yolo PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23216SS | 23218SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41573 | Yolo PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23217SS | 23219SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41574 | Yolo PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23218SS | 23220SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41575 | Yolo PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23219SS | 23221SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41576 | Yolo PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23220SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41577 | Yolo PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
41578 | Yolo PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
41579 | Yolo PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41580 | Yolo PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 23226SS,23230 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41581 | Yolo PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 23225SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
41582 | Yolo PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
41583 | Yolo PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 23236 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41584 | Yolo PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 23237 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41585 | Yolo PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 23225 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41586 | Yolo PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
41587 | Yolo PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 23233SS,23241SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41588 | Yolo PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 23232SS | 23234SS,23242SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
41589 | Yolo PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 23233SS | 23243SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
41590 | Yolo PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
41591 | Yolo PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 23228 | 23237SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41592 | Yolo PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 23229,23236SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41593 | Yolo PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 23246FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41594 | Yolo PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 23240SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41595 | Yolo PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 23239SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41596 | Yolo PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 23232SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41597 | Yolo PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 23233SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41598 | Yolo PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 23234SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41599 | Yolo PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 23246SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41600 | Yolo PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41601 | Yolo PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 23238FS+12d,23244SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41602 | Yuba PR - Implementation | February 3, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 480 | 195d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 7.0000000000000007E-2
41603 | Yuba PR - Implementation Management | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.19
41604 | Yuba PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 235d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
41605 | Yuba PR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
41606 | Yuba PR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41607 | Yuba PR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
41608 | Yuba PR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
41609 | Yuba PR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41610 | Yuba PR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41611 | Yuba PR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
41612 | Yuba PR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41613 | Yuba PR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
41614 | Yuba PR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41615 | Yuba PR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41616 | Yuba PR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41617 | Yuba PR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41618 | Yuba PR - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
41619 | Yuba PR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41620 | Yuba PR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
41621 | Yuba PR - Attend Executive Briefing Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
41622 | Yuba PR - Confirm Probation Implementation Teams | February 21, 2025 12:00 AM | March 14, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/14/25 | 16 | 0d | NA | NA | 0 days? | No | 2/21/25 | 3/14/25 | NA | 1
41623 | Yuba PR - Schedule Kickoff Meeting | March 17, 2025 12:00 AM | April 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/15/25 | 21 | 0d | NA | NA | 0 days? | No | 3/17/25 | 4/15/25 | NA | 1
41624 | Yuba PR - Attend Kickoff Meeting | April 16, 2025 12:00 AM | May 15, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/16/25 | 20 | 0d | NA | NA | 0 days? | No | 4/16/25 | 5/15/25 | NA | 1
41625 | Yuba PR - First Probation Orientation Meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
41626 | Yuba PR - Schedule Organization Assessment spreadsheet review meeting | May 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 5/31/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
41627 | Yuba PR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
41628 | Yuba PR - IL to demonstrate how to access Implementation Portal through cwds.ca.gov | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41629 | Yuba PR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41630 | Yuba PR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 23276SS | Start No Earlier Than | 1/5/26 | 20 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
41631 | Yuba PR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM | 23275SS |  | Finish No Earlier Than | 2/17/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
41632 | Yuba PR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 23278SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41633 | Yuba PR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23277SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41634 | Yuba PR - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41635 | Yuba PR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 23281SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
41636 | Yuba PR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 23280SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
41637 | Yuba PR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
41638 | Yuba PR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 23284SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
41639 | Yuba PR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 23283SS |  | As Soon As Possible | NA | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
41640 | Yuba PR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41641 | Yuba PR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 23287SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41642 | Yuba PR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 23286SS |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
41643 | Yuba PR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 23289SS | Start No Earlier Than | 9/1/26 | 21 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
41644 | Yuba PR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 23288SS |  | Start No Earlier Than | 9/1/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
41645 | Yuba PR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41646 | Yuba PR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
41647 | Yuba PR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41648 | Yuba PR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 200 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
41649 | Yuba PR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41650 | Yuba PR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41651 | Yuba PR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
41652 | Yuba PR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | October 16, 2026 5:00 PM |  | 23298FS+10d | Start No Earlier Than | 10/1/26 | 12 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41653 | Yuba PR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 23297FS+10d |  | Start No Earlier Than | 10/15/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41654 | Yuba PR - OCM Activities | July 1, 2025 12:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 339 | 233d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
41655 | Yuba PR - Review and customize Organization Communication Plan template | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 23302FS-1d | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
41656 | Yuba PR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41657 | Yuba PR - Execute Organization Communication Plan template and continue revisions, as necessary | September 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 23300FS-1d |  | Start No Earlier Than | 9/2/25 | 296 | 233d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
41658 | Yuba PR - Identify staff with expertise in Case Management to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | July 1, 2025 12:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 20 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/30/25 | NA | 1
41659 | Yuba PR - Participate in OCM led Process Information Session for Case Management | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 23305 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
41660 | Yuba PR - Review Change Impact Assessment for Case Management and draft necessary revisions to internal business processes/procedures and operational manuals | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 23304 |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41661 | Yuba PR - Review, update as needed, and FINALIZE Case Management processes/procedures | January 21, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 76 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41662 | Yuba PR - Identify staff with expertise in Court Processing (Warrants, Jurisdiction and Disposition Hearing, Status Reviews, Other Hearings) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 23308FS+19d | Finish No Earlier Than | 10/31/25 | 22 | 405d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
41663 | Yuba PR - Participate in OCM led Process Information Session for Court Processing | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM | 23307FS+19d | 23309 | Start No Earlier Than | 12/1/25 | 22 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41664 | Yuba PR - Review Change Impact Assessment for Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 23308 |  | As Soon As Possible | NA | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41665 | Yuba PR - Review, update as needed, and FINALIZE Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41666 | Yuba PR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operationa | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 23312 | Start No Earlier Than | 11/3/25 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41667 | Yuba PR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 23311 | 23313FS-1d | Start No Earlier Than | 1/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41668 | Yuba PR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 23312FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41669 | Yuba PR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41670 | Yuba PR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
41671 | Yuba PR - Technical Activities | October 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 210 | 298d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.02
41672 | Yuba PR - Complete Tableau Training | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41673 | Yuba PR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 23319SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
41674 | Yuba PR - Enroll in Tableau training cohorts by responding to workgroup survey | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 23318SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
41675 | Yuba PR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41676 | Yuba PR - Review disposition of statewide reports | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41677 | Yuba PR - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41678 | Yuba PR - Identify additional organization-specific reports and external system reports and add to workbook inventory | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 23324SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
41679 | Yuba PR - Review the CARES Reports Tracker list of state reports offered in the CARES Analytics Transition Workgroup Teams Channel to identify duplicative organization reports, or reports no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 23323SS | 23338SS | Start No Earlier Than | 10/1/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41680 | Yuba PR - Determine priority for Organization-specific custom reports | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41681 | Yuba PR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41682 | Yuba PR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41683 | Yuba PR - Execute plan for transition of custom reports from Business Objects to Tableau | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41684 | Yuba PR - Develop Plan for Timeline of Reports Creation in Tableau | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 23330SS | Start No Earlier Than | 12/1/25 | 43 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41685 | Yuba PR - Create organization-specific reports | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 23329SS | 23331SS,23332 | Finish No Earlier Than | 4/30/26 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41686 | Yuba PR - Test reports in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 23330SS | 23332 | As Soon As Possible | NA | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41687 | Yuba PR - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 23330,23331 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41688 | Yuba PR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41689 | Yuba PR - Complete Training for Creation of Forms in CARES | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41690 | Yuba PR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 23336SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
41691 | Yuba PR - Respond to Survey for enrollment in training cohorts | October 1, 2025 8:00 AM | February 2, 2026 5:00 PM | 23335SS |  | Finish No Earlier Than | 1/31/26 | 84 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
41692 | Yuba PR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41693 | Yuba PR - Review disposition of statewide Forms provided by Project | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 23324SS |  | Finish No Earlier Than | 11/30/25 | 42 | 0d | NA | NA | 0 days? | No | 10/1/25 | 12/1/25 | NA | 1
41694 | Yuba PR - Identify Organization-specific forms by completing the Forms Inventory Workbooks | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | As Soon As Possible | NA | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41695 | Yuba PR - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | October 1, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 23341SS | Finish No Earlier Than | 10/31/25 | 22 | 486d | NA | NA | 0 days? | No | NA | NA | NA | 0
41696 | Yuba PR - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | October 1, 2025 8:00 AM | December 1, 2025 5:00 PM | 23340SS |  | Finish No Earlier Than | 11/30/25 | 42 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41697 | Yuba PR - Determine priority for Organization-specific custom Forms | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41698 | Yuba PR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  | 23344SS+18d | Start No Earlier Than | 11/3/25 | 40 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41699 | Yuba PR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | December 1, 2025 8:00 AM | April 16, 2026 5:00 PM | 23343SS+18d |  | Finish No Earlier Than | 4/15/26 | 94 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41700 | Yuba PR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | December 1, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 169 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41701 | Yuba PR - Develop Plan for Timeline of Form Creation in AEM/Word | December 1, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 23347SS | Start No Earlier Than | 12/1/25 | 43 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41702 | Yuba PR - Create organization-specific forms | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 23346SS |  | Finish No Earlier Than | 4/30/26 | 105 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41703 | Yuba PR - Test forms in development environment | December 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 23349 | Start No Earlier Than | 12/1/25 | 105 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41704 | Yuba PR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 23348 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41705 | Yuba PR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41706 | Yuba PR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41707 | Yuba PR - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 23353SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41708 | Yuba PR - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23352SS | 23354SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41709 | Yuba PR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23353SS | 23355SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41710 | Yuba PR - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23354SS | 23356SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41711 | Yuba PR - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23355SS | 23357SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41712 | Yuba PR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23356SS | 23358SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41713 | Yuba PR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23357SS | 23359SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41714 | Yuba PR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss/ | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23358SS | 23360SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41715 | Yuba PR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23359SS | 23361SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41716 | Yuba PR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23360SS | 23362SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41717 | Yuba PR - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23361SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41718 | Yuba PR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
41719 | Yuba PR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
41720 | Yuba PR - Training | October 1, 2025 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41721 | Yuba PR - Develop the CARES V1 Organization Training Plan | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  | 23367SS,23371 | Start No Earlier Than | 10/1/25 | 124 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41722 | Yuba PR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM | 23366SS |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
41723 | Yuba PR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
41724 | Yuba PR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 23377 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41725 | Yuba PR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 23378 | Start No Earlier Than | 2/2/26 | 63 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41726 | Yuba PR - Execute the CARES V1 Organization Training Plan | April 2, 2026 8:00 AM | December 31, 2026 5:00 PM | 23366 |  | Start No Earlier Than | 4/1/26 | 189 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
41727 | Yuba PR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
41728 | Yuba PR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 23374SS,23382SS+20d | Start No Earlier Than | 5/1/26 | 54 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41729 | Yuba PR - Prepare training on Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 23373SS | 23375SS,23383SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
41730 | Yuba PR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 23374SS | 23384SS+20d | Finish No Earlier Than | 7/17/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
41731 | Yuba PR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
41732 | Yuba PR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 23369 | 23378SS | Start No Earlier Than | 5/1/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41733 | Yuba PR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 4, 2026 8:00 AM | November 2, 2026 5:00 PM | 23370,23377SS |  | Finish No Earlier Than | 10/30/26 | 128 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
41734 | Yuba PR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  | 23387FS+12d | Start No Earlier Than | 5/4/26 | 51 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41735 | Yuba PR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 23381SS | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41736 | Yuba PR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM | 23380SS |  | Start No Earlier Than | 1/2/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41737 | Yuba PR - Deliver processes/procedures training (if applicable) for Case Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 23373SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41738 | Yuba PR - Deliver processes/procedures training (if applicable) for Court Processing | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 23374SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41739 | Yuba PR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 23375SS+20d |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41740 | Yuba PR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  | 23387SS+44d | Start No Earlier Than | 6/1/26 | 93 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
41741 | Yuba PR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41742 | Yuba PR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM | 23379FS+12d,23385SS+44d |  | As Soon As Possible | NA | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
43074 | Implementation - CDSS | July 17, 2023 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 867 | 196d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.33000000000000002
41743 | CCLD CDSS - Implementation | July 17, 2023 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 867 | 196d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.28000000000000003
41744 | CCLD CDSS - Implementation Management | July 17, 2023 12:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.48999999999999999
41745 | CCLD CDSS - Monthly Readiness Meetings | October 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 523 | 0d | NA | NA | 0 days? | No | 10/1/24 | NA | NA | 0.47999999999999998
41746 | CCLD CDSS - Monthly Readiness Meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | Start No Earlier Than | 10/1/24 | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
41747 | CCLD CDSS - Monthly Readiness Meetings | November 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | Start No Earlier Than | 11/1/24 | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 12/2/24 | NA | 1
41748 | CCLD CDSS - Monthly Readiness Meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | Start No Earlier Than | 12/2/24 | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
41749 | CCLD CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | Start No Earlier Than | 1/2/25 | 21 | 0d | NA | NA | 0 days? | No | 1/2/25 | 1/31/25 | NA | 1
41750 | CCLD CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Start No Earlier Than | 2/3/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
41751 | CCLD CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Start No Earlier Than | 3/3/25 | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 4/1/25 | NA | 1
41752 | CCLD CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | Start No Earlier Than | 4/1/25 | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
41753 | CCLD CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | Start No Earlier Than | 5/1/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
41754 | CCLD CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Start No Earlier Than | 6/2/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
41755 | CCLD CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
41756 | CCLD CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41757 | CCLD CDSS - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
41758 | CCLD CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
41759 | CCLD CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41760 | CCLD CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41761 | CCLD CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
41762 | CCLD CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41763 | CCLD CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
41764 | CCLD CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41765 | CCLD CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41766 | CCLD CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41767 | CCLD CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41768 | CCLD CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
41769 | CCLD CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41770 | CCLD CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
41771 | CCLD CDSS - Attend Executive Briefing Meeting | July 17, 2023 12:00 AM | September 10, 2024 5:00 PM |  |  | As Soon As Possible | NA | 291 | 0d | NA | NA | 0 days? | No | 7/17/23 | 9/10/24 | NA | 1
41772 | CCLD CDSS - Conduct Discovery Conversations | October 2, 2023 8:00 AM | April 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 124 | 0d | NA | NA | 0 days? | No | 10/2/23 | 4/2/24 | NA | 1
41773 | CCLD CDSS - Schedule Kickoff Meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
41774 | CCLD CDSS - Attend Kickoff Meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
41775 | CCLD CDSS - Schedule Organization Assessment spreadsheet review meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
41776 | CCLD CDSS - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
41777 | CCLD CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
41778 | CCLD CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
41779 | CCLD CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 62 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
41780 | CCLD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 23427SS | Finish No Earlier Than | 2/2/26 | 20 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
41781 | CCLD CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 23426SS |  | Finish No Earlier Than | 2/16/26 | 29 | 415d | NA | NA | 0 days? | No | NA | NA | NA | 0
41782 | CCLD CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
41783 | CCLD CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
41784 | CCLD CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 23431SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41785 | CCLD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 23430SS | 23432SS | As Soon As Possible | NA | 22 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
41786 | CCLD CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 23431SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
41787 | CCLD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 23434SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
41788 | CCLD CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 23433SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
41789 | CCLD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 23436SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
41790 | CCLD CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 23435SS |  | As Soon As Possible | NA | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
41791 | CCLD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 23438SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
41792 | CCLD CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 23437SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
41793 | CCLD CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
41794 | CCLD CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
41795 | CCLD CDSS - OCM Activities | February 3, 2025 8:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 442 | 233d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.34999999999999998
41796 | CCLD CDSS - Review and customize Organization Communication Plan template | February 3, 2025 8:00 AM | April 30, 2025 5:00 PM |  | 23444SS+40d | As Soon As Possible | NA | 61 | 0d | NA | NA | 0 days? | No | 2/3/25 | 4/30/25 | NA | 1
41797 | CCLD CDSS - Participate in OCM overview education session for CDSS | April 1, 2025 12:00 AM | April 29, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/30/25 | 21 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/29/25 | NA | 1
41798 | CCLD CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 23442SS+40d |  | As Soon As Possible | NA | 380 | 233d | NA | NA | 0 days? | No | 5/1/25 | NA | NA | 0.40000000000000002
41799 | CCLD CDSS - Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5. | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/28/25 | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 4/1/25 | NA | 1
41800 | CCLD CDSS - Participate in OCM led Process Information Session for Intake | April 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/2/25 | 43 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
41801 | CCLD CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41802 | CCLD CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  | 23449 | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
41803 | CCLD CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 23448 | 23450FS-1d | As Soon As Possible | NA | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
41804 | CCLD CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 23449FS-1d |  | Start No Earlier Than | 9/2/25 | 63 | 0d | NA | NA | 0 days? | No | 9/2/25 | 12/1/25 | NA | 1
41805 | CCLD CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41806 | CCLD CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  | 23453FS-1d | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
41807 | CCLD CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 23452FS-1d | 23454 | Finish No Earlier Than | 10/31/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41808 | CCLD CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 23453 |  | Finish No Earlier Than | 3/2/26 | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41809 | CCLD CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41810 | CCLD CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 23457 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41811 | CCLD CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 23456 | 23458 | Finish No Earlier Than | 12/31/25 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41812 | CCLD CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 23457 |  | Finish No Earlier Than | 3/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41813 | CCLD CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41814 | CCLD CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  | 23461 | Finish No Earlier Than | 12/31/25 | 39 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
41815 | CCLD CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 23460 | 23463FS-1d | Finish No Earlier Than | 3/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41816 | CCLD CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41817 | CCLD CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 23461FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41818 | CCLD CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 39 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
41819 | CCLD CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41820 | CCLD CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 43 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
41821 | CCLD CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
41822 | CCLD CDSS - Technical Activities | April 1, 2025 12:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 338 | 298d | NA | NA | 0 days? | No | 4/1/25 | NA | NA | 0.23999999999999999
41823 | CCLD CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 23470SS,23473 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
41824 | CCLD CDSS - Participate in discovery session with RADD to gain a better understanding of future state data needs | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 23469SS | 23471SS | As Soon As Possible | NA | 32 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/15/25 | NA | 1
41825 | CCLD CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 23470SS |  | As Soon As Possible | NA | 32 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/15/25 | NA | 1
41826 | CCLD CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 52 | 0d | NA | NA | 0 days? | No | 10/1/25 | 12/15/25 | NA | 1
41827 | CCLD CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 23469 | 23474 | As Soon As Possible | NA | 52 | 0d | NA | NA | 0 days? | No | 10/1/25 | 12/15/25 | NA | 1
41828 | CCLD CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 23473 |  | As Soon As Possible | NA | 158 | 0d | NA | NA | 0 days? | No | 12/16/25 | 8/3/26 | NA | 1
41829 | CCLD CDSS - Review disposition of statewide Forms provided by Project | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
41830 | CCLD CDSS - Identify Organization-specific forms by completing the Forms Inventory Workbooks | April 1, 2025 12:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 92 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
41831 | CCLD CDSS - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  | 23478 | Finish No Earlier Than | 6/30/25 | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
41832 | CCLD CDSS - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | July 1, 2025 12:00 AM | August 8, 2025 5:00 PM | 23477 | 23480 | Finish No Earlier Than | 8/8/25 | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
41833 | CCLD CDSS - Determine priority for Organization-specific custom Forms | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 171 | 373d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20999999999999999
41834 | CCLD CDSS - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 23478 | 23481FS+1d | Finish No Earlier Than | 10/31/25 | 59 | 373d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.59999999999999998
41835 | CCLD CDSS - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | November 4, 2025 8:00 AM | April 16, 2026 5:00 PM | 23480FS+1d |  | Start No Earlier Than | 11/3/25 | 111 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41836 | CCLD CDSS - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 7.0000000000000007E-2
41837 | CCLD CDSS - Develop Plan for Timeline of Form Creation in AEM/Word | August 11, 2025 8:00 AM | September 30, 2025 12:00 AM |  | 23484 | Finish No Earlier Than | 9/30/25 | 35 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
41838 | CCLD CDSS - Create organization-specific forms | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 23483 | 23485FF | Start No Earlier Than | 10/1/25 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41839 | CCLD CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 23484FF | 23486 | Finish No Earlier Than | 4/30/26 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41840 | CCLD CDSS - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 23485 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41841 | CCLD CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41842 | CCLD CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41843 | CCLD CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 23490SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41844 | CCLD CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23489SS | 23491SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41845 | CCLD CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23490SS | 23492SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41846 | CCLD CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23491SS | 23493SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41847 | CCLD CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23492SS | 23494SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41848 | CCLD CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23493SS | 23495SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41849 | CCLD CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23494SS | 23496SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41850 | CCLD CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23495SS | 23497SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41851 | CCLD CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23496SS | 23498SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41852 | CCLD CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23497SS | 23499SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41853 | CCLD CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23498SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
41854 | CCLD CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
41855 | CCLD CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
41856 | CCLD CDSS - Training | July 1, 2025 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 376 | 196d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
41857 | CCLD CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 188 | 384d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
41858 | CCLD CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM |  | 23510 | Finish No Earlier Than | 3/31/26 | 123 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
41859 | CCLD CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 6/30/26 | 187 | 322d | NA | NA | 0 days? | No | NA | NA | NA | 0
41860 | CCLD CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41861 | CCLD CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41862 | CCLD CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 23518 | Finish No Earlier Than | 4/30/26 | 62 | 275d | NA | NA | 0 days? | No | NA | NA | NA | 0
41863 | CCLD CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 23519 | Finish No Earlier Than | 4/30/26 | 62 | 275d | NA | NA | 0 days? | No | NA | NA | NA | 0
41864 | CCLD CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 23504 |  | Start No Earlier Than | 4/1/26 | 189 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
41865 | CCLD CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
41866 | CCLD CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 23513SS,23521SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41867 | CCLD CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 23512SS | 23514SS,23522SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41868 | CCLD CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 23513SS | 23515SS,23523SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41869 | CCLD CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 23514SS | 23516SS,23524SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41870 | CCLD CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 23515SS | 23525SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41871 | CCLD CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
41872 | CCLD CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 23508 |  | Start No Earlier Than | 5/1/26 | 89 | 274d | NA | NA | 0 days? | No | NA | NA | NA | 0
41873 | CCLD CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 23509 |  | Start No Earlier Than | 5/1/26 | 89 | 274d | NA | NA | 0 days? | No | NA | NA | NA | 0
41874 | CCLD CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM |  | 23528FS+13d | Finish No Earlier Than | 7/15/26 | 50 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41875 | CCLD CDSS - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23512SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41876 | CCLD CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23513SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41877 | CCLD CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23514SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41878 | CCLD CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23515SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41879 | CCLD CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23516SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41880 | CCLD CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 23528SS+40d | Start No Earlier Than | 6/1/26 | 44 | 283d | NA | NA | 0 days? | No | NA | NA | NA | 0
41881 | CCLD CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM |  |  | Finish No Earlier Than | 7/31/26 | 33 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
41882 | CCLD CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 23520FS+13d,23526SS+40d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41883 | CFSD_Adoptions CDSS - Implementation | July 17, 2023 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 867 | 196d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.40000000000000002
41884 | CFSD_Adoptions CDSS - Implementation Management | July 17, 2023 12:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.44
41885 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | November 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 500 | 0d | NA | NA | 0 days? | No | 11/1/24 | NA | NA | 0.5
41886 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | November 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | Start No Earlier Than | 11/1/24 | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 12/2/24 | NA | 1
41887 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | Start No Earlier Than | 12/2/24 | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
41888 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | Start No Earlier Than | 1/2/25 | 21 | 0d | NA | NA | 0 days? | No | 1/2/25 | 1/31/25 | NA | 1
41889 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Start No Earlier Than | 2/3/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
41890 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Start No Earlier Than | 3/3/25 | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 4/1/25 | NA | 1
41891 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | Start No Earlier Than | 4/1/25 | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
41892 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | Start No Earlier Than | 5/1/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
41893 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Start No Earlier Than | 6/2/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
41894 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
41895 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
41896 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
41897 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 0d | NA | NA | 0 days? | No | 10/1/25 | 10/31/25 | NA | 1
41898 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
41899 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
41900 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
41901 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41902 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
41903 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41904 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41905 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
41906 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
41907 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
41908 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41909 | CFSD_Adoptions CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
41910 | CFSD_Adoptions CDSS - Attend Executive Briefing Meeting | July 17, 2023 12:00 AM | September 10, 2024 5:00 PM |  |  | As Soon As Possible | NA | 291 | 0d | NA | NA | 0 days? | No | 7/17/23 | 9/10/24 | NA | 1
41911 | CFSD_Adoptions CDSS - Conduct Discovery Conversations | October 2, 2023 8:00 AM | April 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 124 | 0d | NA | NA | 0 days? | No | 10/2/23 | 4/2/24 | NA | 1
41912 | CFSD_Adoptions CDSS - Schedule Kickoff Meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
41913 | CFSD_Adoptions CDSS - Attend Kickoff Meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
41914 | CFSD_Adoptions CDSS - Schedule Organization Assessment spreadsheet review meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
41915 | CFSD_Adoptions CDSS - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
41916 | CFSD_Adoptions CDSS - Establish method for keeping interim processes and release notes current (if applicable) | May 30, 2025 8:00 AM | September 15, 2026 12:00 AM |  |  | Finish No Earlier Than | 9/15/26 | 325 | 269d | NA | NA | 0 days? | No | NA | NA | NA | 0
41917 | CFSD_Adoptions CDSS - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 9/30/26 | 54 | 258d | NA | NA | 0 days? | No | NA | NA | NA | 0
41918 | CFSD_Adoptions CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 62 | 446d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
41919 | CFSD_Adoptions CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 23566SS | Finish No Earlier Than | 2/2/26 | 20 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
41920 | CFSD_Adoptions CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 23565SS |  | Finish No Earlier Than | 2/16/26 | 29 | 415d | NA | NA | 0 days? | No | NA | NA | NA | 0
41921 | CFSD_Adoptions CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
41922 | CFSD_Adoptions CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
41923 | CFSD_Adoptions CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
41924 | CFSD_Adoptions CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 23571SS | Finish No Earlier Than | 4/30/26 | 21 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
41925 | CFSD_Adoptions CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 12:00 AM | 23570SS |  | Finish No Earlier Than | 5/15/26 | 32 | 353d | NA | NA | 0 days? | No | NA | NA | NA | 0
41926 | CFSD_Adoptions CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 12:00 AM |  | 23573SS | Finish No Earlier Than | 7/31/26 | 21 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
41927 | CFSD_Adoptions CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM | 23572SS |  | Finish No Earlier Than | 8/17/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
41928 | CFSD_Adoptions CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | August 31, 2026 12:00 AM |  | 23575SS | Finish No Earlier Than | 8/31/26 | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
41929 | CFSD_Adoptions CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM | 23574SS |  | Finish No Earlier Than | 9/15/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
41930 | CFSD_Adoptions CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 12:00 AM |  | 23577SS | Finish No Earlier Than | 9/30/26 | 20 | 258d | NA | NA | 0 days? | No | NA | NA | NA | 0
41931 | CFSD_Adoptions CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 23576SS |  | Finish No Earlier Than | 10/15/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
41932 | CFSD_Adoptions CDSS - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
41933 | CFSD_Adoptions CDSS - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 12:00 AM |  |  | Finish No Earlier Than | 10/16/26 | 4 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
41934 | CFSD_Adoptions CDSS - OCM Activities | February 3, 2025 8:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 442 | 233d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.37
41935 | CFSD_Adoptions CDSS - Review and customize Organization Communication Plan template | February 3, 2025 8:00 AM | April 30, 2025 5:00 PM |  | 23583SS+40d | Finish No Earlier Than | 4/30/25 | 61 | 0d | NA | NA | 0 days? | No | 2/3/25 | 4/30/25 | NA | 1
41936 | CFSD_Adoptions CDSS - Participate in OCM overview education session for CDSS | April 1, 2025 12:00 AM | April 29, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/30/25 | 21 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/29/25 | NA | 1
41937 | CFSD_Adoptions CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | April 1, 2025 8:00 AM | November 3, 2026 5:00 PM | 23581SS+40d |  | As Soon As Possible | NA | 402 | 233d | NA | NA | 0 days? | No | 4/1/25 | NA | NA | 0.40000000000000002
41938 | CFSD_Adoptions CDSS - Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5. | February 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/28/25 | 40 | 0d | NA | NA | 0 days? | No | 2/3/25 | 4/1/25 | NA | 1
41939 | CFSD_Adoptions CDSS - Participate in OCM led Process Information Session for Intake | April 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/2/25 | 43 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
41940 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41941 | CFSD_Adoptions CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) f | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  | 23588 | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
41942 | CFSD_Adoptions CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 23587 |  | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
41943 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41944 | CFSD_Adoptions CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  | 23591FS-1d | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
41945 | CFSD_Adoptions CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 23590FS-1d | 23592 | Finish No Earlier Than | 10/31/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
41946 | CFSD_Adoptions CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 23591 |  | Finish No Earlier Than | 3/2/26 | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41947 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41948 | CFSD_Adoptions CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 23595 | Start No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/31/25 | NA | 1
41949 | CFSD_Adoptions CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 23594 | 23596 | Finish No Earlier Than | 12/31/25 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41950 | CFSD_Adoptions CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 23595 |  | Finish No Earlier Than | 3/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41951 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41952 | CFSD_Adoptions CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  | 23599 | Finish No Earlier Than | 12/31/25 | 39 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
41953 | CFSD_Adoptions CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 23598 | 23601FS-1d | Finish No Earlier Than | 3/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41954 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
41955 | CFSD_Adoptions CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 23599FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
41956 | CFSD_Adoptions CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 39 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
41957 | CFSD_Adoptions CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
41958 | CFSD_Adoptions CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 43 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
41959 | CFSD_Adoptions CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
41960 | CFSD_Adoptions CDSS - Technical Activities | March 19, 2024 12:00 AM | August 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 602 | 293d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.57999999999999996
41961 | CFSD_Adoptions CDSS - Complete Tableau Training | March 19, 2024 12:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 0d | NA | NA | 0 days? | No | 3/19/24 | 5/8/26 | NA | 1
41962 | CFSD_Adoptions CDSS - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM |  | 23609SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
41963 | CFSD_Adoptions CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 23608SS |  | Finish No Earlier Than | 3/2/26 | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
41964 | CFSD_Adoptions CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 49 | 0d | NA | NA | 0 days? | No | 3/2/26 | 5/8/26 | NA | 1
41965 | CFSD_Adoptions CDSS - Review disposition of statewide reports | May 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 86 | 0d | NA | NA | 0 days? | No | 5/1/25 | 9/2/25 | NA | 1
41966 | CFSD_Adoptions CDSS - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 108 | 0d | NA | NA | 0 days? | No | 4/1/25 | NA | NA | 0.98999999999999999
41967 | CFSD_Adoptions CDSS - Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 9/2/25 | 108 | 0d | NA | NA | 0 days? | No | 4/1/25 | 9/2/25 | NA | 1
41968 | CFSD_Adoptions CDSS - Complete CDSS Child Welfare Data Usage Questionnaire to determine recommended data path | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
41969 | CFSD_Adoptions CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 23616SS,23619 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
41970 | CFSD_Adoptions CDSS - Participate in discovery session with RADD to gain a better understanding of future state data needs | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 23615SS | 23617SS | As Soon As Possible | NA | 32 | 6.4d | NA | NA | 0 days? | No | NA | NA | NA | 0
41971 | CFSD_Adoptions CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 23616SS |  | As Soon As Possible | NA | 32 | 497d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
41972 | CFSD_Adoptions CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 52 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41973 | CFSD_Adoptions CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 23615 | 23620 | As Soon As Possible | NA | 52 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41974 | CFSD_Adoptions CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 23619 |  | As Soon As Possible | NA | 158 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
41975 | CFSD_Adoptions CDSS - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 171 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41976 | CFSD_Adoptions CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 23623FS+1d,23625SS | Finish No Earlier Than | 10/31/25 | 58 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41977 | CFSD_Adoptions CDSS - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 23622FS+1d |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
41978 | CFSD_Adoptions CDSS - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 251 | 293d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 7.0000000000000007E-2
41979 | CFSD_Adoptions CDSS - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 23622SS | 23626 | Finish No Earlier Than | 9/30/25 | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
41980 | CFSD_Adoptions CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 23625 | 23627SS,23628 | Finish No Earlier Than | 4/30/26 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41981 | CFSD_Adoptions CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 23626SS | 23628 | Finish No Earlier Than | 4/30/26 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41982 | CFSD_Adoptions CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 23626,23627 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
41983 | CFSD_Adoptions CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 146 | 293d | NA | NA | 0 days? | No | NA | NA | NA | 0
41984 | CFSD_Adoptions CDSS - Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | April 30, 2026 12:00 AM |  |  | As Soon As Possible | NA | 311 | 0d | NA | NA | 0 days? | No | 2/3/25 | 4/30/26 | NA | 1
41985 | CFSD_Adoptions CDSS - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 23632SS | Finish No Earlier Than | 2/2/26 | 251 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/2/26 | NA | 1
41986 | CFSD_Adoptions CDSS - Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 23631SS |  | Finish No Earlier Than | 1/1/26 | 251 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/2/26 | NA | 1
41987 | CFSD_Adoptions CDSS - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | March 28, 2025 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 273 | 0d | NA | NA | 0 days? | No | 3/28/25 | 4/30/26 | NA | 1
41988 | CFSD_Adoptions CDSS - Review disposition of statewide Forms provided by Project | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
41989 | CFSD_Adoptions CDSS - Identify Organization-specific forms by completing the Forms Inventory Workbooks | April 1, 2025 12:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 92 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
41990 | CFSD_Adoptions CDSS - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  | 23637 | Finish No Earlier Than | 6/30/25 | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
41991 | CFSD_Adoptions CDSS - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | July 1, 2025 12:00 AM | August 8, 2025 5:00 PM | 23636 | 23639 | Finish No Earlier Than | 8/8/25 | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
41992 | CFSD_Adoptions CDSS - Determine priority for Organization-specific custom Forms | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 171 | 0d | NA | NA | 0 days? | No | 8/11/25 | 4/16/26 | NA | 1
41993 | CFSD_Adoptions CDSS - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 23637 | 23640FS+1d | Finish No Earlier Than | 10/31/25 | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
41994 | CFSD_Adoptions CDSS - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | November 4, 2025 8:00 AM | April 16, 2026 5:00 PM | 23639FS+1d |  | Start No Earlier Than | 11/3/25 | 111 | 0d | NA | NA | 0 days? | No | 11/4/25 | 4/16/26 | NA | 1
41995 | CFSD_Adoptions CDSS - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.70999999999999996
41996 | CFSD_Adoptions CDSS - Develop Plan for Timeline of Form Creation in AEM/Word | August 11, 2025 8:00 AM | September 30, 2025 12:00 AM |  | 23643 | Finish No Earlier Than | 9/30/25 | 35 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
41997 | CFSD_Adoptions CDSS - Create organization-specific forms | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 23642 | 23644FF | Start No Earlier Than | 10/1/25 | 146 | 0d | NA | NA | 0 days? | No | 10/1/25 | 5/1/26 | NA | 1
41998 | CFSD_Adoptions CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 23643FF | 23645 | Finish No Earlier Than | 4/30/26 | 146 | 0d | NA | NA | 0 days? | No | 10/1/25 | 5/1/26 | NA | 1
41999 | CFSD_Adoptions CDSS - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 23644 |  | Finish No Earlier Than | 5/26/26 | 17 | 0d | NA | NA | 0 days? | No | 5/4/26 | 5/27/26 | NA | 1
42000 | CFSD_Adoptions CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42001 | CFSD_Adoptions CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42002 | CFSD_Adoptions CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 23649SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42003 | CFSD_Adoptions CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23648SS | 23650SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42004 | CFSD_Adoptions CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23649SS | 23651SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42005 | CFSD_Adoptions CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23650SS | 23652SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42006 | CFSD_Adoptions CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23651SS | 23653SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42007 | CFSD_Adoptions CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23652SS | 23654SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42008 | CFSD_Adoptions CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23653SS | 23655SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42009 | CFSD_Adoptions CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23654SS | 23656SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42010 | CFSD_Adoptions CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23655SS | 23657SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42011 | CFSD_Adoptions CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23656SS | 23658SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42012 | CFSD_Adoptions CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23657SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42013 | CFSD_Adoptions CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 12:00 AM |  |  | Finish No Earlier Than | 6/26/26 | 38 | 324d | NA | NA | 0 days? | No | NA | NA | NA | 0
42014 | CFSD_Adoptions CDSS - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 12:00 AM |  |  | Finish No Earlier Than | 7/10/26 | 28 | 315d | NA | NA | 0 days? | No | NA | NA | NA | 0
42015 | CFSD_Adoptions CDSS - Training | July 1, 2025 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 376 | 196d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 2.9999999999999999E-2
42016 | CFSD_Adoptions CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 188 | 384d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
42017 | CFSD_Adoptions CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM |  | 23669 | Finish No Earlier Than | 3/31/26 | 123 | 196d | NA | NA | 0 days? | No | 10/1/25 | NA | NA | 0.20000000000000001
42018 | CFSD_Adoptions CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 6/30/26 | 187 | 322d | NA | NA | 0 days? | No | NA | NA | NA | 0
42019 | CFSD_Adoptions CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42020 | CFSD_Adoptions CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42021 | CFSD_Adoptions CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 23677 | Finish No Earlier Than | 4/30/26 | 62 | 236d | NA | NA | 0 days? | No | NA | NA | NA | 0
42022 | CFSD_Adoptions CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 23678 | Finish No Earlier Than | 4/30/26 | 62 | 236d | NA | NA | 0 days? | No | NA | NA | NA | 0
42023 | CFSD_Adoptions CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 23663 |  | Start No Earlier Than | 4/1/26 | 189 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
42024 | CFSD_Adoptions CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
42025 | CFSD_Adoptions CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 12:00 AM |  | 23672SS,23680SS+21d | Finish No Earlier Than | 7/17/26 | 53 | 310d | NA | NA | 0 days? | No | NA | NA | NA | 0
42026 | CFSD_Adoptions CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 12:00 AM | 23671SS | 23673SS,23681SS+21d | Finish No Earlier Than | 7/17/26 | 53 | 310d | NA | NA | 0 days? | No | NA | NA | NA | 0
42027 | CFSD_Adoptions CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 12:00 AM | 23672SS | 23674SS,23682SS+21d | Finish No Earlier Than | 7/17/26 | 53 | 310d | NA | NA | 0 days? | No | NA | NA | NA | 0
42028 | CFSD_Adoptions CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 12:00 AM | 23673SS | 23675SS,23683SS+21d | Finish No Earlier Than | 7/17/26 | 53 | 310d | NA | NA | 0 days? | No | NA | NA | NA | 0
42029 | CFSD_Adoptions CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 12:00 AM | 23674SS | 23684SS+21d | Finish No Earlier Than | 7/17/26 | 53 | 310d | NA | NA | 0 days? | No | NA | NA | NA | 0
42030 | CFSD_Adoptions CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
42031 | CFSD_Adoptions CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 23667 |  | Start No Earlier Than | 5/1/26 | 128 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
42032 | CFSD_Adoptions CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 23668 |  | Start No Earlier Than | 5/1/26 | 128 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
42033 | CFSD_Adoptions CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM |  | 23687FS+12d | Finish No Earlier Than | 7/15/26 | 50 | 242d | NA | NA | 0 days? | No | NA | NA | NA | 0
42034 | CFSD_Adoptions CDSS - Deliver processes/procedures training (if applicable) for Intake | June 2, 2026 8:00 AM | October 26, 2026 5:00 PM | 23671SS+21d |  | As Soon As Possible | NA | 103 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
42035 | CFSD_Adoptions CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 2, 2026 8:00 AM | October 26, 2026 5:00 PM | 23672SS+21d |  | As Soon As Possible | NA | 103 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
42036 | CFSD_Adoptions CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 2, 2026 8:00 AM | October 26, 2026 5:00 PM | 23673SS+21d |  | As Soon As Possible | NA | 103 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
42037 | CFSD_Adoptions CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 2, 2026 8:00 AM | October 26, 2026 5:00 PM | 23674SS+21d |  | As Soon As Possible | NA | 103 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
42038 | CFSD_Adoptions CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 2, 2026 8:00 AM | October 26, 2026 5:00 PM | 23675SS+21d |  | As Soon As Possible | NA | 103 | 239d | NA | NA | 0 days? | No | NA | NA | NA | 0
42039 | CFSD_Adoptions CDSS - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 12:00 AM |  | 23687SS+40d | Finish No Earlier Than | 10/9/26 | 92 | 251d | NA | NA | 0 days? | No | NA | NA | NA | 0
42040 | CFSD_Adoptions CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM |  |  | Finish No Earlier Than | 7/31/26 | 33 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
42041 | CFSD_Adoptions CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 12:00 AM | 23679FS+12d,23685SS+40d |  | Finish No Earlier Than | 10/23/26 | 58 | 241d | NA | NA | 0 days? | No | NA | NA | NA | 0
42042 | CFSD_CSQMB CDSS - Implementation | July 17, 2023 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 867 | 196d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.34000000000000002
42043 | CFSD_CSQMB CDSS - Implementation Management | July 17, 2023 12:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.5
42044 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | November 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 500 | 0d | NA | NA | 0 days? | No | 11/1/24 | NA | NA | 0.45000000000000001
42045 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | November 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | Start No Earlier Than | 11/1/24 | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 12/2/24 | NA | 1
42046 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | Start No Earlier Than | 12/2/24 | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
42047 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | Start No Earlier Than | 1/2/25 | 21 | 0d | NA | NA | 0 days? | No | 1/2/25 | 1/31/25 | NA | 1
42048 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Start No Earlier Than | 2/3/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
42049 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Start No Earlier Than | 3/3/25 | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 4/1/25 | NA | 1
42050 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | Start No Earlier Than | 4/1/25 | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
42051 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | Start No Earlier Than | 5/1/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
42052 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Start No Earlier Than | 6/2/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
42053 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
42054 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
42055 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
42056 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
42057 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
42058 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
42059 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
42060 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42061 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
42062 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42063 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
42064 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
42065 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42066 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
42067 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
42068 | CFSD_CSQMB CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
42069 | CFSD_CSQMB CDSS - Attend Executive Briefing Meeting | July 17, 2023 12:00 AM | September 10, 2024 5:00 PM |  |  | As Soon As Possible | NA | 291 | 0d | NA | NA | 0 days? | No | 7/17/23 | 9/10/24 | NA | 1
42070 | CFSD_CSQMB CDSS - Conduct Discovery Conversations | October 2, 2023 8:00 AM | April 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 124 | 0d | NA | NA | 0 days? | No | 10/2/23 | 4/2/24 | NA | 1
42071 | CFSD_CSQMB CDSS - Schedule Kickoff Meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
42072 | CFSD_CSQMB CDSS - Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | Start No Earlier Than | 9/25/23 | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
42073 | CFSD_CSQMB CDSS - Schedule Organization Assessment spreadsheet review meeting | September 3, 2024 8:00 AM | January 31, 2025 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 103 | 0d | NA | NA | 0 days? | No | 9/3/24 | 1/31/25 | NA | 1
42074 | CFSD_CSQMB CDSS - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | September 3, 2024 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 122 | 0d | NA | NA | 0 days? | No | 9/3/24 | 2/28/25 | NA | 1
42075 | CFSD_CSQMB CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
42076 | CFSD_CSQMB CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
42077 | CFSD_CSQMB CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 62 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
42078 | CFSD_CSQMB CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 23725SS | Finish No Earlier Than | 2/2/26 | 20 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
42079 | CFSD_CSQMB CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 23724SS |  | Finish No Earlier Than | 2/16/26 | 29 | 415d | NA | NA | 0 days? | No | NA | NA | NA | 0
42080 | CFSD_CSQMB CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42081 | CFSD_CSQMB CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42082 | CFSD_CSQMB CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 23729SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
42083 | CFSD_CSQMB CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 23728SS | 23730SS | As Soon As Possible | NA | 22 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
42084 | CFSD_CSQMB CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 23729SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
42085 | CFSD_CSQMB CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 23732SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
42086 | CFSD_CSQMB CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 23731SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
42087 | CFSD_CSQMB CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 23734SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
42088 | CFSD_CSQMB CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 23733SS |  | As Soon As Possible | NA | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
42089 | CFSD_CSQMB CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 23736SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
42090 | CFSD_CSQMB CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 23735SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
42091 | CFSD_CSQMB CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
42092 | CFSD_CSQMB CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
42093 | CFSD_CSQMB CDSS - OCM Activities | February 3, 2025 8:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 442 | 233d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.33000000000000002
42094 | CFSD_CSQMB CDSS - Review and customize Organization Communication Plan template | March 3, 2025 8:00 AM | April 30, 2025 5:00 PM |  | 23742SS+40d | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/3/25 | 4/30/25 | NA | 1
42095 | CFSD_CSQMB CDSS - Participate in OCM overview education session for CDSS | April 1, 2025 12:00 AM | April 29, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/30/25 | 21 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/29/25 | NA | 1
42096 | CFSD_CSQMB CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 23740SS+40d |  | As Soon As Possible | NA | 380 | 233d | NA | NA | 0 days? | No | 5/1/25 | NA | NA | 0.40000000000000002
42097 | CFSD_CSQMB CDSS - Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5. | February 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/28/25 | 40 | 0d | NA | NA | 0 days? | No | 2/3/25 | 4/1/25 | NA | 1
42098 | CFSD_CSQMB CDSS - Participate in OCM led Process Information Session for Intake | April 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/2/25 | 43 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
42099 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42100 | CFSD_CSQMB CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for e | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  | 23747 | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
42101 | CFSD_CSQMB CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 23746 | 23748FS-1d | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
42102 | CFSD_CSQMB CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 23747FS-1d |  | Start No Earlier Than | 9/2/25 | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
42103 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42104 | CFSD_CSQMB CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational man | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  | 23751FS-1d | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
42105 | CFSD_CSQMB CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 23750FS-1d | 23752 | Finish No Earlier Than | 10/31/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
42106 | CFSD_CSQMB CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 23751 |  | Finish No Earlier Than | 3/2/26 | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42107 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42108 | CFSD_CSQMB CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 23755 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42109 | CFSD_CSQMB CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 23754 | 23756 | Finish No Earlier Than | 12/31/25 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42110 | CFSD_CSQMB CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 23755 |  | Finish No Earlier Than | 3/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42111 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42112 | CFSD_CSQMB CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and ope | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  | 23759 | Finish No Earlier Than | 12/31/25 | 39 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42113 | CFSD_CSQMB CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 23758 | 23761FS-1d | Finish No Earlier Than | 3/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42114 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42115 | CFSD_CSQMB CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 23759FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42116 | CFSD_CSQMB CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 39 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
42117 | CFSD_CSQMB CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42118 | CFSD_CSQMB CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 43 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42119 | CFSD_CSQMB CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
42120 | CFSD_CSQMB CDSS - Technical Activities | March 19, 2024 12:00 AM | August 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 602 | 293d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.40999999999999998
42121 | CFSD_CSQMB CDSS - Complete Tableau Training | March 19, 2024 12:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
42122 | CFSD_CSQMB CDSS - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM |  | 23769SS | As Soon As Possible | NA | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
42123 | CFSD_CSQMB CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 23768SS |  | Finish No Earlier Than | 3/2/26 | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
42124 | CFSD_CSQMB CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 49 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42125 | CFSD_CSQMB CDSS - Review disposition of statewide reports | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
42126 | CFSD_CSQMB CDSS - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 108 | 0d | NA | NA | 0 days? | No | 4/1/25 | NA | NA | 0.98999999999999999
42127 | CFSD_CSQMB CDSS - Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 9/2/25 | 108 | 0d | NA | NA | 0 days? | No | 4/1/25 | 9/2/25 | NA | 1
42128 | CFSD_CSQMB CDSS - Complete CDSS Child Welfare Data Usage Questionnaire to determine recommended data path | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
42129 | CFSD_CSQMB CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 23776SS,23779 | Start No Earlier Than | 9/2/25 | 21 | 298d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.40000000000000002
42130 | CFSD_CSQMB CDSS - Participate in discovery session with RADD to gain a better understanding of future state data needs | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 23775SS | 23777SS | As Soon As Possible | NA | 32 | 497d | NA | NA | 0 days? | No | NA | NA | NA | 0
42131 | CFSD_CSQMB CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 23776SS |  | As Soon As Possible | NA | 32 | 497d | NA | NA | 0 days? | No | NA | NA | NA | 0
42132 | CFSD_CSQMB CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 52 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42133 | CFSD_CSQMB CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 23775 | 23780 | As Soon As Possible | NA | 52 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42134 | CFSD_CSQMB CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 23779 |  | As Soon As Possible | NA | 158 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42135 | CFSD_CSQMB CDSS - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 171 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
42136 | CFSD_CSQMB CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 23783FS+1d,23785SS | Finish No Earlier Than | 10/31/25 | 58 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
42137 | CFSD_CSQMB CDSS - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 23782FS+1d |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
42138 | CFSD_CSQMB CDSS - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 251 | 293d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 7.0000000000000007E-2
42139 | CFSD_CSQMB CDSS - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 23782SS | 23786 | Finish No Earlier Than | 9/30/25 | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
42140 | CFSD_CSQMB CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 23785 | 23787SS,23788 | Finish No Earlier Than | 4/30/26 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42141 | CFSD_CSQMB CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 23786SS | 23788 | Finish No Earlier Than | 4/30/26 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42142 | CFSD_CSQMB CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 23786,23787 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42143 | CFSD_CSQMB CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 146 | 293d | NA | NA | 0 days? | No | NA | NA | NA | 0
42144 | CFSD_CSQMB CDSS - Review disposition of statewide Forms provided by Project | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
42145 | CFSD_CSQMB CDSS - Identify Organization-specific forms by completing the Forms Inventory Workbooks | April 1, 2025 12:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 92 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
42146 | CFSD_CSQMB CDSS - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  | 23793 | Finish No Earlier Than | 6/30/25 | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
42147 | CFSD_CSQMB CDSS - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | July 1, 2025 12:00 AM | August 8, 2025 5:00 PM | 23792 |  | Finish No Earlier Than | 8/8/25 | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
42148 | CFSD_CSQMB CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42149 | CFSD_CSQMB CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 23796SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42150 | CFSD_CSQMB CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23795SS | 23797SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42151 | CFSD_CSQMB CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23796SS | 23798SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42152 | CFSD_CSQMB CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23797SS | 23799SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42153 | CFSD_CSQMB CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23798SS | 23800SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42154 | CFSD_CSQMB CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23799SS | 23801SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42155 | CFSD_CSQMB CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23800SS | 23802SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42156 | CFSD_CSQMB CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), D | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23801SS | 23803SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42157 | CFSD_CSQMB CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23802SS | 23804SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42158 | CFSD_CSQMB CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23803SS | 23805SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42159 | CFSD_CSQMB CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23804SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42160 | CFSD_CSQMB CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
42161 | CFSD_CSQMB CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
42162 | CFSD_CSQMB CDSS - Training | July 1, 2025 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 376 | 196d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
42163 | CFSD_CSQMB CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 188 | 384d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
42164 | CFSD_CSQMB CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM |  | 23816 | Finish No Earlier Than | 3/31/26 | 123 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
42165 | CFSD_CSQMB CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 6/30/26 | 187 | 322d | NA | NA | 0 days? | No | NA | NA | NA | 0
42166 | CFSD_CSQMB CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42167 | CFSD_CSQMB CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42168 | CFSD_CSQMB CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 23824 | Finish No Earlier Than | 4/30/26 | 62 | 275d | NA | NA | 0 days? | No | NA | NA | NA | 0
42169 | CFSD_CSQMB CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 23825 | Finish No Earlier Than | 4/30/26 | 62 | 275d | NA | NA | 0 days? | No | NA | NA | NA | 0
42170 | CFSD_CSQMB CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 23810 |  | Start No Earlier Than | 4/1/26 | 189 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
42171 | CFSD_CSQMB CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
42172 | CFSD_CSQMB CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 23819SS,23827SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42173 | CFSD_CSQMB CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 23818SS | 23820SS,23828SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42174 | CFSD_CSQMB CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 23819SS | 23821SS,23829SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42175 | CFSD_CSQMB CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 23820SS | 23822SS,23830SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42176 | CFSD_CSQMB CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 23821SS | 23831SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42177 | CFSD_CSQMB CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
42178 | CFSD_CSQMB CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 23814 |  | Start No Earlier Than | 5/1/26 | 89 | 274d | NA | NA | 0 days? | No | NA | NA | NA | 0
42179 | CFSD_CSQMB CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 23815 |  | Start No Earlier Than | 5/1/26 | 89 | 274d | NA | NA | 0 days? | No | NA | NA | NA | 0
42180 | CFSD_CSQMB CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM |  | 23834FS+13d | Finish No Earlier Than | 7/15/26 | 50 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
42181 | CFSD_CSQMB CDSS - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23818SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42182 | CFSD_CSQMB CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23819SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42183 | CFSD_CSQMB CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23820SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42184 | CFSD_CSQMB CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23821SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42185 | CFSD_CSQMB CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23822SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42186 | CFSD_CSQMB CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 23834SS+40d | Start No Earlier Than | 6/1/26 | 44 | 283d | NA | NA | 0 days? | No | NA | NA | NA | 0
42187 | CFSD_CSQMB CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM |  |  | Finish No Earlier Than | 7/31/26 | 33 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
42188 | CFSD_CSQMB CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 23826FS+13d,23832SS+40d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
42189 | CFSD_Permanency CDSS - Implementation | July 17, 2023 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 867 | 196d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.28999999999999998
42190 | CFSD_Permanency CDSS - Implementation Management | July 17, 2023 12:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.46999999999999997
42191 | CFSD_Permanency CDSS - Monthly Readiness Meetings | October 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 523 | 0d | NA | NA | 0 days? | No | 10/1/24 | NA | NA | 0.47999999999999998
42192 | CFSD_Permanency CDSS - Monthly Readiness Meetings | October 1, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | Start No Earlier Than | 10/1/24 | 23 | 0d | NA | NA | 0 days? | No | 10/1/24 | 10/31/24 | NA | 1
42193 | CFSD_Permanency CDSS - Monthly Readiness Meetings | November 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | Start No Earlier Than | 11/1/24 | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 12/2/24 | NA | 1
42194 | CFSD_Permanency CDSS - Monthly Readiness Meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | Start No Earlier Than | 12/2/24 | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
42195 | CFSD_Permanency CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | Start No Earlier Than | 1/2/25 | 21 | 0d | NA | NA | 0 days? | No | 1/2/25 | 1/31/25 | NA | 1
42196 | CFSD_Permanency CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Start No Earlier Than | 2/3/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
42197 | CFSD_Permanency CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Start No Earlier Than | 3/3/25 | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 4/1/25 | NA | 1
42198 | CFSD_Permanency CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | Start No Earlier Than | 4/1/25 | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
42199 | CFSD_Permanency CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | Start No Earlier Than | 5/1/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
42200 | CFSD_Permanency CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Start No Earlier Than | 6/2/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
42201 | CFSD_Permanency CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
42202 | CFSD_Permanency CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
42203 | CFSD_Permanency CDSS - Monthly Readiness Meetings | September 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 22 | 0d | NA | NA | 0 days? | No | 9/1/25 | 9/30/25 | NA | 1
42204 | CFSD_Permanency CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
42205 | CFSD_Permanency CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
42206 | CFSD_Permanency CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
42207 | CFSD_Permanency CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
42208 | CFSD_Permanency CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42209 | CFSD_Permanency CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
42210 | CFSD_Permanency CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42211 | CFSD_Permanency CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
42212 | CFSD_Permanency CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
42213 | CFSD_Permanency CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42214 | CFSD_Permanency CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
42215 | CFSD_Permanency CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
42216 | CFSD_Permanency CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
42217 | CFSD_Permanency CDSS - Attend Executive Briefing Meeting | July 17, 2023 12:00 AM | September 10, 2024 5:00 PM |  |  | As Soon As Possible | NA | 291 | 0d | NA | NA | 0 days? | No | 7/17/23 | 9/10/24 | NA | 1
42218 | CFSD_Permanency CDSS - Conduct Discovery Conversations | October 2, 2023 8:00 AM | April 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 124 | 0d | NA | NA | 0 days? | No | 10/2/23 | 4/2/24 | NA | 1
42219 | CFSD_Permanency CDSS - Schedule Kickoff Meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
42220 | CFSD_Permanency CDSS - Attend Kickoff Meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
42221 | CFSD_Permanency CDSS - Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | November 7, 2023 5:00 PM |  |  | As Soon As Possible | NA | 22 | 0d | NA | NA | 0 days? | No | 10/9/23 | 11/7/23 | NA | 1
42222 | CFSD_Permanency CDSS - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | Start No Earlier Than | 10/23/23 | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
42223 | CFSD_Permanency CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
42224 | CFSD_Permanency CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
42225 | CFSD_Permanency CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 62 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
42226 | CFSD_Permanency CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 23873SS | Finish No Earlier Than | 2/2/26 | 20 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
42227 | CFSD_Permanency CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 23872SS |  | Finish No Earlier Than | 2/16/26 | 29 | 415d | NA | NA | 0 days? | No | NA | NA | NA | 0
42228 | CFSD_Permanency CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42229 | CFSD_Permanency CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42230 | CFSD_Permanency CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 23877SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
42231 | CFSD_Permanency CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 23876SS | 23878SS | As Soon As Possible | NA | 22 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
42232 | CFSD_Permanency CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 23877SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
42233 | CFSD_Permanency CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 23880SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
42234 | CFSD_Permanency CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 23879SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
42235 | CFSD_Permanency CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 23882SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
42236 | CFSD_Permanency CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 23881SS |  | As Soon As Possible | NA | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
42237 | CFSD_Permanency CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 23884SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
42238 | CFSD_Permanency CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 23883SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
42239 | CFSD_Permanency CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
42240 | CFSD_Permanency CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
42241 | CFSD_Permanency CDSS - OCM Activities | February 3, 2025 8:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 442 | 233d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.33000000000000002
42242 | CFSD_Permanency CDSS - Review and customize Organization Communication Plan template | February 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  | 23890SS+40d | As Soon As Possible | NA | 40 | 0d | NA | NA | 0 days? | No | 2/3/25 | 4/1/25 | NA | 1
42243 | CFSD_Permanency CDSS - Participate in OCM overview education session for CDSS | April 1, 2025 12:00 AM | April 29, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/30/25 | 21 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/29/25 | NA | 1
42244 | CFSD_Permanency CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 23888SS+40d |  | As Soon As Possible | NA | 380 | 233d | NA | NA | 0 days? | No | 5/1/25 | NA | NA | 0.40000000000000002
42245 | CFSD_Permanency CDSS - Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5. | February 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/28/25 | 40 | 0d | NA | NA | 0 days? | No | 2/3/25 | 4/1/25 | NA | 1
42246 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42247 | CFSD_Permanency CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  | 23894 | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
42248 | CFSD_Permanency CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 23893 | 23895FS-1d | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
42249 | CFSD_Permanency CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 23894FS-1d |  | Start No Earlier Than | 9/2/25 | 63 | 466d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.80000000000000004
42250 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42251 | CFSD_Permanency CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operationa | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  | 23898FS-1d | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
42252 | CFSD_Permanency CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 23897FS-1d | 23899 | Finish No Earlier Than | 10/31/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
42253 | CFSD_Permanency CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 23898 |  | Finish No Earlier Than | 3/2/26 | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42254 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42255 | CFSD_Permanency CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 23902 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42256 | CFSD_Permanency CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 23901 | 23903 | Finish No Earlier Than | 12/31/25 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42257 | CFSD_Permanency CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 23902 |  | Finish No Earlier Than | 3/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42258 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42259 | CFSD_Permanency CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures an | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  | 23906 | Finish No Earlier Than | 12/31/25 | 39 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42260 | CFSD_Permanency CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 23905 | 23908FS-1d | Finish No Earlier Than | 3/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42261 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42262 | CFSD_Permanency CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 23906FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42263 | CFSD_Permanency CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 39 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
42264 | CFSD_Permanency CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42265 | CFSD_Permanency CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 43 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42266 | CFSD_Permanency CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
42267 | CFSD_Permanency CDSS - Technical Activities | March 19, 2024 12:00 AM | August 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 602 | 293d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.31
42268 | CFSD_Permanency CDSS - Complete Tableau Training | March 19, 2024 12:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.56999999999999995
42269 | CFSD_Permanency CDSS - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM |  | 23916SS | Finish No Earlier Than | 3/2/26 | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
42270 | CFSD_Permanency CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 23915SS |  | Finish No Earlier Than | 3/2/26 | 490 | 405d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.20000000000000001
42271 | CFSD_Permanency CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 49 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42272 | CFSD_Permanency CDSS - Review disposition of statewide reports | May 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 86 | 0d | NA | NA | 0 days? | No | 5/1/25 | 9/2/25 | NA | 1
42273 | CFSD_Permanency CDSS - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 108 | 0d | NA | NA | 0 days? | No | 4/1/25 | NA | NA | 0.98999999999999999
42274 | CFSD_Permanency CDSS - Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 9/2/25 | 108 | 0d | NA | NA | 0 days? | No | 4/1/25 | 9/2/25 | NA | 1
42275 | CFSD_Permanency CDSS - Complete CDSS Child Welfare Data Usage Questionnaire to determine recommended data path | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
42276 | CFSD_Permanency CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 23923SS,23926 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
42277 | CFSD_Permanency CDSS - Participate in discovery session with RADD to gain a better understanding of future state data needs | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 23922SS | 23924SS | As Soon As Possible | NA | 32 | 497d | NA | NA | 0 days? | No | NA | NA | NA | 0
42278 | CFSD_Permanency CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 23923SS |  | As Soon As Possible | NA | 32 | 497d | NA | NA | 0 days? | No | NA | NA | NA | 0
42279 | CFSD_Permanency CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 52 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42280 | CFSD_Permanency CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 23922 | 23927 | As Soon As Possible | NA | 52 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42281 | CFSD_Permanency CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 23926 |  | As Soon As Possible | NA | 158 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42282 | CFSD_Permanency CDSS - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 171 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
42283 | CFSD_Permanency CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 23930FS+1d,23932SS | Finish No Earlier Than | 10/31/25 | 58 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
42284 | CFSD_Permanency CDSS - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 23929FS+1d |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
42285 | CFSD_Permanency CDSS - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 251 | 293d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 7.0000000000000007E-2
42286 | CFSD_Permanency CDSS - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 23929SS | 23933 | Finish No Earlier Than | 9/30/25 | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
42287 | CFSD_Permanency CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 23932 | 23934SS,23935 | Finish No Earlier Than | 4/30/26 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42288 | CFSD_Permanency CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 23933SS | 23935 | Finish No Earlier Than | 4/30/26 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42289 | CFSD_Permanency CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 23933,23934 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42290 | CFSD_Permanency CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 146 | 293d | NA | NA | 0 days? | No | NA | NA | NA | 0
42291 | CFSD_Permanency CDSS - Review disposition of statewide Forms provided by Project | May 1, 2025 12:00 AM | July 31, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 64 | 0d | NA | NA | 0 days? | No | 5/1/25 | 7/31/25 | NA | 1
42292 | CFSD_Permanency CDSS - Identify Organization-specific forms by completing the Forms Inventory Workbooks | April 1, 2025 12:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 92 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
42293 | CFSD_Permanency CDSS - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  | 23940 | Finish No Earlier Than | 6/30/25 | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
42294 | CFSD_Permanency CDSS - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | July 1, 2025 12:00 AM | August 8, 2025 5:00 PM | 23939 |  | Finish No Earlier Than | 8/8/25 | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
42295 | CFSD_Permanency CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42296 | CFSD_Permanency CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 23943SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42297 | CFSD_Permanency CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23942SS | 23944SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42298 | CFSD_Permanency CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23943SS | 23945SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42299 | CFSD_Permanency CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23944SS | 23946SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42300 | CFSD_Permanency CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23945SS | 23947SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42301 | CFSD_Permanency CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23946SS | 23948SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42302 | CFSD_Permanency CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23947SS | 23949SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42303 | CFSD_Permanency CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alt | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23948SS | 23950SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42304 | CFSD_Permanency CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23949SS | 23951SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42305 | CFSD_Permanency CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23950SS | 23952SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42306 | CFSD_Permanency CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 23951SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42307 | CFSD_Permanency CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
42308 | CFSD_Permanency CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
42309 | CFSD_Permanency CDSS - Training | July 1, 2025 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 376 | 196d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
42310 | CFSD_Permanency CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 188 | 384d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
42311 | CFSD_Permanency CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM |  | 23963 | Finish No Earlier Than | 3/31/26 | 123 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
42312 | CFSD_Permanency CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 6/30/26 | 187 | 322d | NA | NA | 0 days? | No | NA | NA | NA | 0
42313 | CFSD_Permanency CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42314 | CFSD_Permanency CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42315 | CFSD_Permanency CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 23971 | Finish No Earlier Than | 4/30/26 | 62 | 275d | NA | NA | 0 days? | No | NA | NA | NA | 0
42316 | CFSD_Permanency CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 23972 | Finish No Earlier Than | 4/30/26 | 62 | 275d | NA | NA | 0 days? | No | NA | NA | NA | 0
42317 | CFSD_Permanency CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 23957 |  | Start No Earlier Than | 4/1/26 | 189 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
42318 | CFSD_Permanency CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
42319 | CFSD_Permanency CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 23966SS,23974SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42320 | CFSD_Permanency CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 23965SS | 23967SS,23975SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42321 | CFSD_Permanency CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 23966SS | 23968SS,23976SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42322 | CFSD_Permanency CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 23967SS | 23969SS,23977SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42323 | CFSD_Permanency CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 23968SS | 23978SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42324 | CFSD_Permanency CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
42325 | CFSD_Permanency CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 23961 |  | Start No Earlier Than | 5/1/26 | 89 | 274d | NA | NA | 0 days? | No | NA | NA | NA | 0
42326 | CFSD_Permanency CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 23962 |  | Start No Earlier Than | 5/1/26 | 89 | 274d | NA | NA | 0 days? | No | NA | NA | NA | 0
42327 | CFSD_Permanency CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM |  | 23981FS+13d | Finish No Earlier Than | 7/15/26 | 50 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
42328 | CFSD_Permanency CDSS - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23965SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42329 | CFSD_Permanency CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23966SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42330 | CFSD_Permanency CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23967SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42331 | CFSD_Permanency CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23968SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42332 | CFSD_Permanency CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 23969SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42333 | CFSD_Permanency CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 23981SS+40d | Start No Earlier Than | 6/1/26 | 44 | 283d | NA | NA | 0 days? | No | NA | NA | NA | 0
42334 | CFSD_Permanency CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM |  |  | Finish No Earlier Than | 7/31/26 | 33 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
42335 | CFSD_Permanency CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 23973FS+13d,23979SS+40d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
42336 | CFSD_System of Care CDSS - Implementation | July 17, 2023 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 867 | 196d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.28999999999999998
42337 | CFSD_System of Care CDSS - Implementation Management | July 17, 2023 12:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.46999999999999997
42338 | CFSD_System of Care CDSS - Monthly Readiness Meetings | November 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 500 | 0d | NA | NA | 0 days? | No | 11/1/24 | NA | NA | 0.45000000000000001
42339 | CFSD_System of Care CDSS - Monthly Readiness Meetings | November 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | Start No Earlier Than | 11/1/24 | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 12/2/24 | NA | 1
42340 | CFSD_System of Care CDSS - Monthly Readiness Meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | Start No Earlier Than | 12/2/24 | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
42341 | CFSD_System of Care CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | Start No Earlier Than | 1/2/25 | 21 | 0d | NA | NA | 0 days? | No | 1/2/25 | 1/31/25 | NA | 1
42342 | CFSD_System of Care CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Start No Earlier Than | 2/3/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
42343 | CFSD_System of Care CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Start No Earlier Than | 3/3/25 | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 4/1/25 | NA | 1
42344 | CFSD_System of Care CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | Start No Earlier Than | 4/1/25 | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
42345 | CFSD_System of Care CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | Start No Earlier Than | 5/1/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
42346 | CFSD_System of Care CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Start No Earlier Than | 6/2/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
42347 | CFSD_System of Care CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
42348 | CFSD_System of Care CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
42349 | CFSD_System of Care CDSS - Monthly Readiness Meetings | September 1, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 22 | 0d | NA | NA | 0 days? | No | 9/1/25 | 9/30/25 | NA | 1
42350 | CFSD_System of Care CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
42351 | CFSD_System of Care CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
42352 | CFSD_System of Care CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
42353 | CFSD_System of Care CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
42354 | CFSD_System of Care CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42355 | CFSD_System of Care CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
42356 | CFSD_System of Care CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42357 | CFSD_System of Care CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
42358 | CFSD_System of Care CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
42359 | CFSD_System of Care CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42360 | CFSD_System of Care CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
42361 | CFSD_System of Care CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
42362 | CFSD_System of Care CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
42363 | CFSD_System of Care CDSS - Attend Executive Briefing Meeting | July 17, 2023 12:00 AM | September 10, 2024 5:00 PM |  |  | As Soon As Possible | NA | 291 | 0d | NA | NA | 0 days? | No | 7/17/23 | 9/10/24 | NA | 1
42364 | CFSD_System of Care CDSS - Conduct Discovery Conversations | October 2, 2023 8:00 AM | April 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 124 | 0d | NA | NA | 0 days? | No | 10/2/23 | 4/2/24 | NA | 1
42365 | CFSD_System of Care CDSS - Schedule Kickoff Meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
42366 | CFSD_System of Care CDSS - Attend Kickoff Meeting | August 1, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 43 | 0d | NA | NA | 0 days? | No | 8/1/24 | 9/30/24 | NA | 1
42367 | CFSD_System of Care CDSS - Schedule Organization Assessment spreadsheet review meeting | September 3, 2024 8:00 AM | October 31, 2024 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 43 | 0d | NA | NA | 0 days? | No | 9/3/24 | 10/31/24 | NA | 1
42368 | CFSD_System of Care CDSS - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 15, 2023 5:00 PM |  |  | As Soon As Possible | NA | 37 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/15/23 | NA | 1
42369 | CFSD_System of Care CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
42370 | CFSD_System of Care CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
42371 | CFSD_System of Care CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 62 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
42372 | CFSD_System of Care CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 24019SS | Finish No Earlier Than | 2/2/26 | 20 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
42373 | CFSD_System of Care CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 24018SS |  | Finish No Earlier Than | 2/16/26 | 29 | 415d | NA | NA | 0 days? | No | NA | NA | NA | 0
42374 | CFSD_System of Care CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42375 | CFSD_System of Care CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42376 | CFSD_System of Care CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 24023SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
42377 | CFSD_System of Care CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 24022SS | 24024SS | As Soon As Possible | NA | 22 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
42378 | CFSD_System of Care CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 24023SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
42379 | CFSD_System of Care CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 24026SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
42380 | CFSD_System of Care CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 24025SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
42381 | CFSD_System of Care CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 24028SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
42382 | CFSD_System of Care CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 24027SS |  | As Soon As Possible | NA | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
42383 | CFSD_System of Care CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 24030SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
42384 | CFSD_System of Care CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 24029SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
42385 | CFSD_System of Care CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
42386 | CFSD_System of Care CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
42387 | CFSD_System of Care CDSS - OCM Activities | February 3, 2025 8:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 442 | 233d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.33000000000000002
42388 | CFSD_System of Care CDSS - Review and customize Organization Communication Plan template | March 3, 2025 8:00 AM | June 2, 2025 5:00 PM |  | 24036SS+40d | Finish No Earlier Than | 4/30/25 | 64 | 0d | NA | NA | 0 days? | No | 3/3/25 | 6/2/25 | NA | 1
42389 | CFSD_System of Care CDSS - Participate in OCM overview education session for CDSS | April 2, 2025 8:00 AM | April 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 4/2/25 | 4/2/25 | NA | 1
42390 | CFSD_System of Care CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 24034SS+40d |  | As Soon As Possible | NA | 380 | 233d | NA | NA | 0 days? | No | 5/1/25 | NA | NA | 0.40000000000000002
42391 | CFSD_System of Care CDSS - Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5. | February 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/28/25 | 40 | 0d | NA | NA | 0 days? | No | 2/3/25 | 4/1/25 | NA | 1
42392 | CFSD_System of Care CDSS - Participate in OCM led Process Information Session for Intake | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/2/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
42393 | CFSD_System of Care CDSS - Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 40 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/30/25 | NA | 1
42394 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42395 | CFSD_System of Care CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicab | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  | 24042 | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
42396 | CFSD_System of Care CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 24041 | 24043FS-1d | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
42397 | CFSD_System of Care CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 24042FS-1d |  | Start No Earlier Than | 9/2/25 | 63 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
42398 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42399 | CFSD_System of Care CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operat | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  | 24046FS-1d | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
42400 | CFSD_System of Care CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 24045FS-1d | 24047 | Finish No Earlier Than | 10/31/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
42401 | CFSD_System of Care CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 24046 |  | Finish No Earlier Than | 3/2/26 | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42402 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42403 | CFSD_System of Care CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 24050 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42404 | CFSD_System of Care CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 24049 | 24051 | Finish No Earlier Than | 12/31/25 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42405 | CFSD_System of Care CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 24050 |  | Finish No Earlier Than | 3/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42406 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42407 | CFSD_System of Care CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedure | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  | 24054 | Finish No Earlier Than | 12/31/25 | 39 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42408 | CFSD_System of Care CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 24053 | 24056FS-1d | Finish No Earlier Than | 3/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42409 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42410 | CFSD_System of Care CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 24054FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42411 | CFSD_System of Care CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 39 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
42412 | CFSD_System of Care CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42413 | CFSD_System of Care CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 43 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42414 | CFSD_System of Care CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
42415 | CFSD_System of Care CDSS - Technical Activities | March 19, 2024 12:00 AM | August 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 602 | 293d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.29999999999999999
42416 | CFSD_System of Care CDSS - Complete Tableau Training | March 19, 2024 12:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
42417 | CFSD_System of Care CDSS - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM |  | 24064SS | Finish No Earlier Than | 3/2/26 | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
42418 | CFSD_System of Care CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 24063SS |  | Finish No Earlier Than | 3/2/26 | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
42419 | CFSD_System of Care CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 49 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42420 | CFSD_System of Care CDSS - Review disposition of statewide reports | May 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 86 | 0d | NA | NA | 0 days? | No | 5/1/25 | 9/2/25 | NA | 1
42421 | CFSD_System of Care CDSS - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 108 | 0d | NA | NA | 0 days? | No | 4/1/25 | NA | NA | 0.98999999999999999
42422 | CFSD_System of Care CDSS - Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 9/2/25 | 108 | 0d | NA | NA | 0 days? | No | 4/1/25 | 9/2/25 | NA | 1
42423 | CFSD_System of Care CDSS - Complete CDSS Child Welfare Data Usage Questionnaire to determine recommended data path | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
42424 | CFSD_System of Care CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 24071SS,24074 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
42425 | CFSD_System of Care CDSS - Participate in discovery session with RADD to gain a better understanding of future state data needs | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 24070SS | 24072SS | As Soon As Possible | NA | 32 | 497d | NA | NA | 0 days? | No | NA | NA | NA | 0
42426 | CFSD_System of Care CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 24071SS |  | As Soon As Possible | NA | 32 | 497d | NA | NA | 0 days? | No | NA | NA | NA | 0
42427 | CFSD_System of Care CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 52 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42428 | CFSD_System of Care CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 24070 | 24075 | As Soon As Possible | NA | 52 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42429 | CFSD_System of Care CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 24074 |  | As Soon As Possible | NA | 158 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42430 | CFSD_System of Care CDSS - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 171 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
42431 | CFSD_System of Care CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 24078FS+1d,24080SS | Finish No Earlier Than | 10/31/25 | 58 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
42432 | CFSD_System of Care CDSS - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 24077FS+1d |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
42433 | CFSD_System of Care CDSS - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 251 | 293d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 7.0000000000000007E-2
42434 | CFSD_System of Care CDSS - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 24077SS | 24081 | Finish No Earlier Than | 9/30/25 | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
42435 | CFSD_System of Care CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24080 | 24082SS,24083 | Finish No Earlier Than | 4/30/26 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42436 | CFSD_System of Care CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24081SS | 24083 | Finish No Earlier Than | 4/30/26 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42437 | CFSD_System of Care CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 24081,24082 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42438 | CFSD_System of Care CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 146 | 293d | NA | NA | 0 days? | No | NA | NA | NA | 0
42439 | CFSD_System of Care CDSS - Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | April 30, 2026 12:00 AM |  |  | As Soon As Possible | NA | 311 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42440 | CFSD_System of Care CDSS - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 24087SS | Finish No Earlier Than | 2/2/26 | 251 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
42441 | CFSD_System of Care CDSS - Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 24086SS |  | Finish No Earlier Than | 1/1/26 | 251 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
42442 | CFSD_System of Care CDSS - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | March 28, 2025 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 273 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42443 | CFSD_System of Care CDSS - Review disposition of statewide Forms provided by Project | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
42444 | CFSD_System of Care CDSS - Identify Organization-specific forms by completing the Forms Inventory Workbooks | April 1, 2025 12:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 92 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
42445 | CFSD_System of Care CDSS - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  | 24092 | Finish No Earlier Than | 6/30/25 | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
42446 | CFSD_System of Care CDSS - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | July 1, 2025 12:00 AM | August 8, 2025 5:00 PM | 24091 | 24094 | Finish No Earlier Than | 8/8/25 | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
42447 | CFSD_System of Care CDSS - Determine priority for Organization-specific custom Forms | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 171 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
42448 | CFSD_System of Care CDSS - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 24092 | 24095FS+1d | Finish No Earlier Than | 10/31/25 | 59 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
42449 | CFSD_System of Care CDSS - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | November 4, 2025 8:00 AM | April 16, 2026 5:00 PM | 24094FS+1d |  | Start No Earlier Than | 11/3/25 | 111 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
42450 | CFSD_System of Care CDSS - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 7.0000000000000007E-2
42451 | CFSD_System of Care CDSS - Develop Plan for Timeline of Form Creation in AEM/Word | August 11, 2025 8:00 AM | September 30, 2025 12:00 AM |  | 24098 | Finish No Earlier Than | 9/30/25 | 35 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
42452 | CFSD_System of Care CDSS - Create organization-specific forms | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24097 | 24099FF | Start No Earlier Than | 10/1/25 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42453 | CFSD_System of Care CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24098FF | 24100 | Finish No Earlier Than | 4/30/26 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42454 | CFSD_System of Care CDSS - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 24099 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42455 | CFSD_System of Care CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42456 | CFSD_System of Care CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42457 | CFSD_System of Care CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 24104SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42458 | CFSD_System of Care CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24103SS | 24105SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42459 | CFSD_System of Care CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24104SS | 24106SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42460 | CFSD_System of Care CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24105SS | 24107SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42461 | CFSD_System of Care CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24106SS | 24108SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42462 | CFSD_System of Care CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24107SS | 24109SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42463 | CFSD_System of Care CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24108SS | 24110SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42464 | CFSD_System of Care CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24109SS | 24111SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42465 | CFSD_System of Care CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24110SS | 24112SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42466 | CFSD_System of Care CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24111SS | 24113SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42467 | CFSD_System of Care CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24112SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42468 | CFSD_System of Care CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
42469 | CFSD_System of Care CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
42470 | CFSD_System of Care CDSS - Training | July 1, 2025 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 376 | 196d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
42471 | CFSD_System of Care CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 188 | 384d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
42472 | CFSD_System of Care CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM |  | 24124 | Finish No Earlier Than | 3/31/26 | 123 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
42473 | CFSD_System of Care CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 6/30/26 | 187 | 322d | NA | NA | 0 days? | No | NA | NA | NA | 0
42474 | CFSD_System of Care CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42475 | CFSD_System of Care CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42476 | CFSD_System of Care CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 24132 | Finish No Earlier Than | 4/30/26 | 62 | 275d | NA | NA | 0 days? | No | NA | NA | NA | 0
42477 | CFSD_System of Care CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 24133 | Finish No Earlier Than | 4/30/26 | 62 | 275d | NA | NA | 0 days? | No | NA | NA | NA | 0
42478 | CFSD_System of Care CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 24118 |  | Start No Earlier Than | 4/1/26 | 189 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
42479 | CFSD_System of Care CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
42480 | CFSD_System of Care CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 24127SS,24135SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42481 | CFSD_System of Care CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24126SS | 24128SS,24136SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42482 | CFSD_System of Care CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24127SS | 24129SS,24137SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42483 | CFSD_System of Care CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24128SS | 24130SS,24138SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42484 | CFSD_System of Care CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24129SS | 24139SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42485 | CFSD_System of Care CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
42486 | CFSD_System of Care CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 24122 |  | Start No Earlier Than | 5/1/26 | 89 | 274d | NA | NA | 0 days? | No | NA | NA | NA | 0
42487 | CFSD_System of Care CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 24123 |  | Start No Earlier Than | 5/1/26 | 89 | 274d | NA | NA | 0 days? | No | NA | NA | NA | 0
42488 | CFSD_System of Care CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM |  | 24142FS+13d | Finish No Earlier Than | 7/15/26 | 50 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
42489 | CFSD_System of Care CDSS - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24126SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42490 | CFSD_System of Care CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24127SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42491 | CFSD_System of Care CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24128SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42492 | CFSD_System of Care CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24129SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42493 | CFSD_System of Care CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24130SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42494 | CFSD_System of Care CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 24142SS+40d | Start No Earlier Than | 6/1/26 | 44 | 283d | NA | NA | 0 days? | No | NA | NA | NA | 0
42495 | CFSD_System of Care CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM |  |  | Finish No Earlier Than | 7/31/26 | 33 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
42496 | CFSD_System of Care CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 24134FS+13d,24140SS+40d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
42497 | FAD CDSS - Implementation | July 17, 2023 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 867 | 196d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.27000000000000002
42498 | FAD CDSS - Implementation Management | July 17, 2023 12:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.40999999999999998
42499 | FAD CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 461 | 235d | NA | NA | 0 days? | No | 1/2/25 | NA | NA | 0.40999999999999998
42500 | FAD CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | Start No Earlier Than | 1/2/25 | 21 | 0d | NA | NA | 0 days? | No | 1/2/25 | 1/31/25 | NA | 1
42501 | FAD CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Start No Earlier Than | 2/1/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
42502 | FAD CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Start No Earlier Than | 3/1/25 | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 4/1/25 | NA | 1
42503 | FAD CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | Start No Earlier Than | 4/1/25 | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
42504 | FAD CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | Start No Earlier Than | 5/1/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
42505 | FAD CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Start No Earlier Than | 6/1/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
42506 | FAD CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
42507 | FAD CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
42508 | FAD CDSS - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
42509 | FAD CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
42510 | FAD CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
42511 | FAD CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
42512 | FAD CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
42513 | FAD CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
42514 | FAD CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/1/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
42515 | FAD CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42516 | FAD CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
42517 | FAD CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
42518 | FAD CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42519 | FAD CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
42520 | FAD CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
42521 | FAD CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
42522 | FAD CDSS - Attend Executive Briefing Meeting | July 17, 2023 12:00 AM | September 10, 2024 5:00 PM |  |  | As Soon As Possible | NA | 291 | 0d | NA | NA | 0 days? | No | 7/17/23 | 9/10/24 | NA | 1
42523 | FAD CDSS - Conduct Discovery Conversations | September 3, 2024 8:00 AM | September 30, 2024 5:00 PM |  |  | Start No Earlier Than | 9/3/24 | 20 | 0d | NA | NA | 0 days? | No | 9/3/24 | 9/30/24 | NA | 1
42524 | FAD CDSS - Schedule Kickoff Meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
42525 | FAD CDSS - Attend Kickoff Meeting | September 25, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 66 | 0d | NA | NA | 0 days? | No | 9/25/24 | 12/31/24 | NA | 1
42526 | FAD CDSS - Schedule Organization Assessment spreadsheet review meeting | December 16, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 11 | 0d | NA | NA | 0 days? | No | 12/16/24 | 12/31/24 | NA | 1
42527 | FAD CDSS - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 21 | 0d | NA | NA | 0 days? | No | 1/2/25 | 1/31/25 | NA | 1
42528 | FAD CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
42529 | FAD CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
42530 | FAD CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 62 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
42531 | FAD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 24178SS | Finish No Earlier Than | 2/2/26 | 20 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
42532 | FAD CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 24177SS |  | Finish No Earlier Than | 2/16/26 | 29 | 415d | NA | NA | 0 days? | No | NA | NA | NA | 0
42533 | FAD CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42534 | FAD CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42535 | FAD CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 24182SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
42536 | FAD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 24181SS | 24183SS | As Soon As Possible | NA | 22 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
42537 | FAD CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 24182SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
42538 | FAD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 24185SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
42539 | FAD CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 24184SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
42540 | FAD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 24187SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
42541 | FAD CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 24186SS |  | As Soon As Possible | NA | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
42542 | FAD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 24189SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
42543 | FAD CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 24188SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
42544 | FAD CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
42545 | FAD CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
42546 | FAD CDSS - OCM Activities | March 3, 2025 8:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 423 | 233d | NA | NA | 0 days? | No | 3/3/25 | NA | NA | 0.29999999999999999
42547 | FAD CDSS - Review and customize Organization Communication Plan template | March 3, 2025 8:00 AM | September 2, 2025 5:00 PM |  | 24195SS+40d | Finish No Earlier Than | 4/30/25 | 128 | 0d | NA | NA | 0 days? | No | 3/3/25 | 9/2/25 | NA | 1
42548 | FAD CDSS - Participate in OCM overview education session for CDSS | April 2, 2025 8:00 AM | April 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 4/2/25 | 4/2/25 | NA | 1
42549 | FAD CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | June 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 24193SS+40d |  | As Soon As Possible | NA | 360 | 233d | NA | NA | 0 days? | No | 6/2/25 | NA | NA | 0.20000000000000001
42550 | FAD CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42551 | FAD CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  | 24198 | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
42552 | FAD CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 24197 | 24199FS-1d | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
42553 | FAD CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 24198FS-1d |  | Start No Earlier Than | 9/2/25 | 63 | 0d | NA | NA | 0 days? | No | 9/2/25 | 12/1/25 | NA | 1
42554 | FAD CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42555 | FAD CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  | 24202FS-1d | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
42556 | FAD CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 24201FS-1d | 24203 | Finish No Earlier Than | 10/31/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
42557 | FAD CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 24202 |  | Finish No Earlier Than | 3/2/26 | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42558 | FAD CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42559 | FAD CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 24206 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42560 | FAD CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 24205 | 24207 | Finish No Earlier Than | 12/31/25 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42561 | FAD CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 24206 |  | Finish No Earlier Than | 3/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42562 | FAD CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42563 | FAD CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  | 24210 | Finish No Earlier Than | 12/31/25 | 39 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42564 | FAD CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 24209 | 24212FS-1d | Finish No Earlier Than | 3/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42565 | FAD CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42566 | FAD CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 24210FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42567 | FAD CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 39 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
42568 | FAD CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42569 | FAD CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 43 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42570 | FAD CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
42571 | FAD CDSS - Technical Activities | March 19, 2024 12:00 AM | August 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 602 | 293d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.32000000000000001
42572 | FAD CDSS - Complete Tableau Training | March 19, 2024 12:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.5
42573 | FAD CDSS - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 12:00 AM | July 21, 2025 5:00 PM |  | 24220SS | Finish No Earlier Than | 3/2/26 | 337 | 0d | NA | NA | 0 days? | No | 3/19/24 | 7/21/25 | NA | 1
42574 | FAD CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 24219SS |  | Finish No Earlier Than | 3/2/26 | 490 | 405d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.20000000000000001
42575 | FAD CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 49 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42576 | FAD CDSS - Review disposition of statewide reports | May 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 86 | 0d | NA | NA | 0 days? | No | 5/1/25 | 9/2/25 | NA | 1
42577 | FAD CDSS - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 108 | 0d | NA | NA | 0 days? | No | 4/1/25 | NA | NA | 0.98999999999999999
42578 | FAD CDSS - Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 9/2/25 | 108 | 0d | NA | NA | 0 days? | No | 4/1/25 | 9/2/25 | NA | 1
42579 | FAD CDSS - Complete CDSS Child Welfare Data Usage Questionnaire to determine recommended data path | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
42580 | FAD CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 24227SS,24230 | Start No Earlier Than | 9/2/25 | 21 | 298d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
42581 | FAD CDSS - Participate in discovery session with RADD to gain a better understanding of future state data needs | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 24226SS | 24228SS | As Soon As Possible | NA | 32 | 497d | NA | NA | 0 days? | No | NA | NA | NA | 0
42582 | FAD CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 24227SS |  | As Soon As Possible | NA | 32 | 497d | NA | NA | 0 days? | No | NA | NA | NA | 0
42583 | FAD CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 52 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42584 | FAD CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 24226 | 24231 | As Soon As Possible | NA | 52 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42585 | FAD CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 24230 |  | As Soon As Possible | NA | 158 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42586 | FAD CDSS - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 171 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
42587 | FAD CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 24234FS+1d,24236SS | Finish No Earlier Than | 10/31/25 | 58 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
42588 | FAD CDSS - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 24233FS+1d |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
42589 | FAD CDSS - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 251 | 293d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 7.0000000000000007E-2
42590 | FAD CDSS - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 24233SS | 24237 | Finish No Earlier Than | 9/30/25 | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
42591 | FAD CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24236 | 24238SS,24239 | Finish No Earlier Than | 4/30/26 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42592 | FAD CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24237SS | 24239 | Finish No Earlier Than | 4/30/26 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42593 | FAD CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 24237,24238 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42594 | FAD CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 146 | 293d | NA | NA | 0 days? | No | NA | NA | NA | 0
42595 | FAD CDSS - Review disposition of statewide Forms provided by Project | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
42596 | FAD CDSS - Identify Organization-specific forms by completing the Forms Inventory Workbooks | April 1, 2025 12:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 92 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
42597 | FAD CDSS - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  | 24244 | Finish No Earlier Than | 6/30/25 | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
42598 | FAD CDSS - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | July 1, 2025 12:00 AM | August 8, 2025 5:00 PM | 24243 |  | Finish No Earlier Than | 8/8/25 | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
42599 | FAD CDSS - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.70999999999999996
42600 | FAD CDSS - Develop Plan for Timeline of Form Creation in AEM/Word | August 11, 2025 8:00 AM | September 30, 2025 12:00 AM |  | 24247 | Finish No Earlier Than | 9/30/25 | 35 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
42601 | FAD CDSS - Create organization-specific forms | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24246 | 24248FF | Start No Earlier Than | 10/1/25 | 146 | 0d | NA | NA | 0 days? | No | 10/1/25 | 5/1/26 | NA | 1
42602 | FAD CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24247FF | 24249 | Finish No Earlier Than | 4/30/26 | 146 | 0d | NA | NA | 0 days? | No | 10/1/25 | 5/1/26 | NA | 1
42603 | FAD CDSS - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 24248 |  | Finish No Earlier Than | 5/26/26 | 17 | 0d | NA | NA | 0 days? | No | 5/4/26 | 5/27/26 | NA | 1
42604 | FAD CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42605 | FAD CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42606 | FAD CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 24253SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42607 | FAD CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24252SS | 24254SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42608 | FAD CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24253SS | 24255SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42609 | FAD CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24254SS | 24256SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42610 | FAD CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24255SS | 24257SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42611 | FAD CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24256SS | 24258SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42612 | FAD CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24257SS | 24259SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42613 | FAD CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24258SS | 24260SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42614 | FAD CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24259SS | 24261SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42615 | FAD CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24260SS | 24262SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42616 | FAD CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24261SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42617 | FAD CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
42618 | FAD CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
42619 | FAD CDSS - Training | July 1, 2025 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 376 | 196d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
42620 | FAD CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 188 | 384d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
42621 | FAD CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM |  | 24273 | Finish No Earlier Than | 3/31/26 | 123 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
42622 | FAD CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 6/30/26 | 187 | 322d | NA | NA | 0 days? | No | NA | NA | NA | 0
42623 | FAD CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42624 | FAD CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42625 | FAD CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 24281 | Finish No Earlier Than | 4/30/26 | 62 | 275d | NA | NA | 0 days? | No | NA | NA | NA | 0
42626 | FAD CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 24282 | Finish No Earlier Than | 4/30/26 | 62 | 275d | NA | NA | 0 days? | No | NA | NA | NA | 0
42627 | FAD CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 24267 |  | Start No Earlier Than | 4/1/26 | 189 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
42628 | FAD CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
42629 | FAD CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 24276SS,24284SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42630 | FAD CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24275SS | 24277SS,24285SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42631 | FAD CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24276SS | 24278SS,24286SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42632 | FAD CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24277SS | 24279SS,24287SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42633 | FAD CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24278SS | 24288SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42634 | FAD CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
42635 | FAD CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 24271 |  | Start No Earlier Than | 5/1/26 | 89 | 274d | NA | NA | 0 days? | No | NA | NA | NA | 0
42636 | FAD CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 24272 |  | Start No Earlier Than | 5/1/26 | 89 | 274d | NA | NA | 0 days? | No | NA | NA | NA | 0
42637 | FAD CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM |  | 24291FS+13d | Finish No Earlier Than | 7/15/26 | 50 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
42638 | FAD CDSS - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24275SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42639 | FAD CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24276SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42640 | FAD CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24277SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42641 | FAD CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24278SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42642 | FAD CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24279SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42643 | FAD CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 24291SS+40d | Start No Earlier Than | 6/1/26 | 44 | 283d | NA | NA | 0 days? | No | NA | NA | NA | 0
42644 | FAD CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM |  |  | Finish No Earlier Than | 7/31/26 | 33 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
42645 | FAD CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 24283FS+13d,24289SS+40d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
42646 | OOE CDSS - Implementation | July 17, 2023 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 867 | 196d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.23000000000000001
42647 | OOE CDSS - Implementation Management | July 17, 2023 12:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.5
42648 | OOE CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 440 | 235d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.38
42649 | OOE CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Start No Earlier Than | 2/1/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
42650 | OOE CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Start No Earlier Than | 3/1/25 | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 4/1/25 | NA | 1
42651 | OOE CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | Start No Earlier Than | 4/1/25 | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
42652 | OOE CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | Start No Earlier Than | 5/1/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
42653 | OOE CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Start No Earlier Than | 6/1/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
42654 | OOE CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
42655 | OOE CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
42656 | OOE CDSS - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
42657 | OOE CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
42658 | OOE CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
42659 | OOE CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
42660 | OOE CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | January 30, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 20 | 425d | NA | NA | 0 days? | No | NA | NA | NA | 0
42661 | OOE CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | February 27, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 19 | 406d | NA | NA | 0 days? | No | NA | NA | NA | 0
42662 | OOE CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/1/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
42663 | OOE CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42664 | OOE CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 20 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
42665 | OOE CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
42666 | OOE CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42667 | OOE CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
42668 | OOE CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
42669 | OOE CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
42670 | OOE CDSS - Attend Executive Briefing Meeting | July 17, 2023 12:00 AM | September 10, 2024 5:00 PM |  |  | As Soon As Possible | NA | 291 | 0d | NA | NA | 0 days? | No | 7/17/23 | 9/10/24 | NA | 1
42671 | OOE CDSS - Conduct Discovery Conversations | October 2, 2023 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 293 | 0d | NA | NA | 0 days? | No | 10/2/23 | 12/2/24 | NA | 1
42672 | OOE CDSS - Schedule Kickoff Meeting | July 1, 2024 12:00 AM | December 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 127 | 0d | NA | NA | 0 days? | No | 7/1/24 | 12/31/24 | NA | 1
42673 | OOE CDSS - Attend Kickoff Meeting | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 21 | 0d | NA | NA | 0 days? | No | 1/2/25 | 1/31/25 | NA | 1
42674 | OOE CDSS - Schedule Organization Assessment spreadsheet review meeting | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 21 | 0d | NA | NA | 0 days? | No | 1/2/25 | 1/31/25 | NA | 1
42675 | OOE CDSS - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
42676 | OOE CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
42677 | OOE CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
42678 | OOE CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 62 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
42679 | OOE CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 24326SS | Finish No Earlier Than | 2/2/26 | 20 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
42680 | OOE CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 24325SS |  | Finish No Earlier Than | 2/16/26 | 29 | 415d | NA | NA | 0 days? | No | NA | NA | NA | 0
42681 | OOE CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42682 | OOE CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42683 | OOE CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 24330SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
42684 | OOE CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 24329SS | 24331SS | As Soon As Possible | NA | 22 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
42685 | OOE CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 24330SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
42686 | OOE CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 24333SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
42687 | OOE CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 24332SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
42688 | OOE CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 24335SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
42689 | OOE CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 24334SS |  | As Soon As Possible | NA | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
42690 | OOE CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 24337SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
42691 | OOE CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 24336SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
42692 | OOE CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
42693 | OOE CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
42694 | OOE CDSS - OCM Activities | February 3, 2025 8:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 442 | 233d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.29999999999999999
42695 | OOE CDSS - Review and customize Organization Communication Plan template | May 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  | 24343SS+21d | As Soon As Possible | NA | 64 | 0d | NA | NA | 0 days? | No | 5/1/25 | 7/31/25 | NA | 1
42696 | OOE CDSS - Participate in OCM overview education session for CDSS | April 2, 2025 8:00 AM | April 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 4/2/25 | 4/2/25 | NA | 1
42697 | OOE CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | June 2, 2025 8:00 AM | November 3, 2026 5:00 PM | 24341SS+21d |  | Start No Earlier Than | 3/3/25 | 360 | 233d | NA | NA | 0 days? | No | 6/2/25 | NA | NA | 0.40000000000000002
42698 | OOE CDSS - Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5. | February 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/28/25 | 40 | 0d | NA | NA | 0 days? | No | 2/3/25 | 4/1/25 | NA | 1
42699 | OOE CDSS - Participate in OCM led Process Information Session for Intake | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/2/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
42700 | OOE CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42701 | OOE CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  | 24348 | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
42702 | OOE CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 24347 | 24349FS-1d | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
42703 | OOE CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 24348FS-1d |  | Start No Earlier Than | 9/2/25 | 63 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
42704 | OOE CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42705 | OOE CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  | 24352FS-1d | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
42706 | OOE CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 24351FS-1d | 24353 | Finish No Earlier Than | 10/31/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42707 | OOE CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 24352 |  | Finish No Earlier Than | 3/2/26 | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42708 | OOE CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42709 | OOE CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 24356 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42710 | OOE CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 24355 | 24357 | Finish No Earlier Than | 12/31/25 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42711 | OOE CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 24356 |  | Finish No Earlier Than | 3/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42712 | OOE CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42713 | OOE CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  | 24360 | Finish No Earlier Than | 12/31/25 | 39 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42714 | OOE CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 24359 | 24362FS-1d | Finish No Earlier Than | 3/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42715 | OOE CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42716 | OOE CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 24360FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42717 | OOE CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 39 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
42718 | OOE CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42719 | OOE CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 43 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42720 | OOE CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
42721 | OOE CDSS - Technical Activities | May 1, 2025 12:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 316 | 298d | NA | NA | 0 days? | No | 5/1/25 | NA | NA | 5.0000000000000003E-2
42722 | OOE CDSS - Review disposition of statewide reports | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
42723 | OOE CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 24370SS,24373 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
42724 | OOE CDSS - Participate in discovery session with RADD to gain a better understanding of future state data needs | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 24369SS | 24371SS | As Soon As Possible | NA | 32 | 497d | NA | NA | 0 days? | No | NA | NA | NA | 0
42725 | OOE CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 24370SS |  | As Soon As Possible | NA | 32 | 497d | NA | NA | 0 days? | No | NA | NA | NA | 0
42726 | OOE CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 52 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42727 | OOE CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 24369 | 24374 | As Soon As Possible | NA | 52 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42728 | OOE CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 24373 |  | As Soon As Possible | NA | 158 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42729 | OOE CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42730 | OOE CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 24377SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42731 | OOE CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24376SS | 24378SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42732 | OOE CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24377SS | 24379SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42733 | OOE CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24378SS | 24380SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42734 | OOE CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24379SS | 24381SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42735 | OOE CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24380SS | 24382SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42736 | OOE CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24381SS | 24383SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42737 | OOE CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24382SS | 24384SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42738 | OOE CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24383SS | 24385SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42739 | OOE CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24384SS | 24386SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42740 | OOE CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24385SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42741 | OOE CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
42742 | OOE CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
42743 | OOE CDSS - Training | July 1, 2025 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 376 | 196d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
42744 | OOE CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 188 | 384d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
42745 | OOE CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM |  | 24397 | Finish No Earlier Than | 3/31/26 | 123 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
42746 | OOE CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 6/30/26 | 187 | 322d | NA | NA | 0 days? | No | NA | NA | NA | 0
42747 | OOE CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42748 | OOE CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42749 | OOE CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 24405 | Finish No Earlier Than | 4/30/26 | 62 | 275d | NA | NA | 0 days? | No | NA | NA | NA | 0
42750 | OOE CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 24406 | Finish No Earlier Than | 4/30/26 | 62 | 275d | NA | NA | 0 days? | No | NA | NA | NA | 0
42751 | OOE CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 24391 |  | Start No Earlier Than | 4/1/26 | 189 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
42752 | OOE CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
42753 | OOE CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 24400SS,24408SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42754 | OOE CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24399SS | 24401SS,24409SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42755 | OOE CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24400SS | 24402SS,24410SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42756 | OOE CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24401SS | 24403SS,24411SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42757 | OOE CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24402SS | 24412SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42758 | OOE CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
42759 | OOE CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 24395 |  | Start No Earlier Than | 5/1/26 | 89 | 274d | NA | NA | 0 days? | No | NA | NA | NA | 0
42760 | OOE CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 24396 |  | Start No Earlier Than | 5/1/26 | 89 | 274d | NA | NA | 0 days? | No | NA | NA | NA | 0
42761 | OOE CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM |  | 24415FS+13d | Finish No Earlier Than | 7/15/26 | 50 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
42762 | OOE CDSS - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24399SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42763 | OOE CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24400SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42764 | OOE CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24401SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42765 | OOE CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24402SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42766 | OOE CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24403SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42767 | OOE CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 24415SS+40d | Start No Earlier Than | 6/1/26 | 44 | 283d | NA | NA | 0 days? | No | NA | NA | NA | 0
42768 | OOE CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM |  |  | Finish No Earlier Than | 7/31/26 | 33 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
42769 | OOE CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 24407FS+13d,24413SS+40d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
42770 | RADD CDSS - Implementation | July 17, 2023 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 867 | 196d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.33000000000000002
42771 | RADD CDSS - Implementation Management | July 17, 2023 12:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 828 | 235d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.59999999999999998
42772 | RADD CDSS - Monthly Readiness Meetings | November 1, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 500 | 0d | NA | NA | 0 days? | No | 11/1/24 | NA | NA | 0.45000000000000001
42773 | RADD CDSS - Monthly Readiness Meetings | November 1, 2024 8:00 AM | December 2, 2024 5:00 PM |  |  | Start No Earlier Than | 11/1/24 | 19 | 0d | NA | NA | 0 days? | No | 11/1/24 | 12/2/24 | NA | 1
42774 | RADD CDSS - Monthly Readiness Meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | Start No Earlier Than | 12/2/24 | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
42775 | RADD CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | Start No Earlier Than | 1/2/25 | 21 | 0d | NA | NA | 0 days? | No | 1/2/25 | 1/31/25 | NA | 1
42776 | RADD CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Start No Earlier Than | 2/3/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
42777 | RADD CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Start No Earlier Than | 3/3/25 | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 4/1/25 | NA | 1
42778 | RADD CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | Start No Earlier Than | 4/1/25 | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
42779 | RADD CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | Start No Earlier Than | 5/1/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
42780 | RADD CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Start No Earlier Than | 6/2/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
42781 | RADD CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
42782 | RADD CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
42783 | RADD CDSS - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
42784 | RADD CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
42785 | RADD CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
42786 | RADD CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
42787 | RADD CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
42788 | RADD CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42789 | RADD CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
42790 | RADD CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42791 | RADD CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
42792 | RADD CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
42793 | RADD CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42794 | RADD CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
42795 | RADD CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
42796 | RADD CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
42797 | RADD CDSS - Attend Executive Briefing Meeting | July 17, 2023 12:00 AM | September 10, 2024 5:00 PM |  |  | As Soon As Possible | NA | 291 | 0d | NA | NA | 0 days? | No | 7/17/23 | 9/10/24 | NA | 1
42798 | RADD CDSS - Conduct Discovery Conversations | October 2, 2023 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 293 | 0d | NA | NA | 0 days? | No | 10/2/23 | 12/2/24 | NA | 1
42799 | RADD CDSS - Schedule Kickoff Meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
42800 | RADD CDSS - Attend Kickoff Meeting | September 25, 2023 8:00 AM | October 31, 2023 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 27 | 0d | NA | NA | 0 days? | No | 9/25/23 | 10/31/23 | NA | 1
42801 | RADD CDSS - Schedule Organization Assessment spreadsheet review meeting | October 9, 2023 8:00 AM | October 31, 2024 5:00 PM |  |  | As Soon As Possible | NA | 269 | 0d | NA | NA | 0 days? | No | 10/9/23 | 10/31/24 | NA | 1
42802 | RADD CDSS - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | October 23, 2023 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 278 | 0d | NA | NA | 0 days? | No | 10/23/23 | 12/2/24 | NA | 1
42803 | RADD CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
42804 | RADD CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
42805 | RADD CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 62 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
42806 | RADD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 24453SS | Finish No Earlier Than | 2/2/26 | 20 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
42807 | RADD CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 24452SS |  | Finish No Earlier Than | 2/16/26 | 29 | 415d | NA | NA | 0 days? | No | NA | NA | NA | 0
42808 | RADD CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42809 | RADD CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42810 | RADD CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 24457SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
42811 | RADD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 24456SS | 24458SS | As Soon As Possible | NA | 22 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
42812 | RADD CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 24457SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
42813 | RADD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 24460SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
42814 | RADD CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 24459SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
42815 | RADD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 24462SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
42816 | RADD CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 24461SS |  | As Soon As Possible | NA | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
42817 | RADD CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 24464SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
42818 | RADD CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 24463SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
42819 | RADD CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
42820 | RADD CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
42821 | RADD CDSS - OCM Activities | January 2, 2025 8:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 463 | 233d | NA | NA | 0 days? | No | 1/2/25 | NA | NA | 0.32000000000000001
42822 | RADD CDSS - Review and customize Organization Communication Plan template | January 2, 2025 8:00 AM | April 1, 2025 5:00 PM |  | 24470SS+40d | As Soon As Possible | NA | 61 | 0d | NA | NA | 0 days? | No | 1/2/25 | 4/1/25 | NA | 1
42823 | RADD CDSS - Participate in OCM overview education session for CDSS | April 2, 2025 8:00 AM | April 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 1 | 0d | NA | NA | 0 s? | No | 4/2/25 | 4/2/25 | NA | 1
42824 | RADD CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | March 3, 2025 8:00 AM | November 3, 2026 5:00 PM | 24468SS+40d |  | As Soon As Possible | NA | 422 | 233d | NA | NA | 0 days? | No | 3/3/25 | NA | NA | 0.40000000000000002
42825 | RADD CDSS - Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5. | February 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/28/25 | 40 | 0d | NA | NA | 0 days? | No | 2/3/25 | 4/1/25 | NA | 1
42826 | RADD CDSS - Participate in OCM led Process Information Session for Intake | April 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/2/25 | 43 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
42827 | RADD CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42828 | RADD CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  | 24475 | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
42829 | RADD CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 24474 | 24476FS-1d | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
42830 | RADD CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 24475FS-1d |  | Start No Earlier Than | 9/2/25 | 63 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
42831 | RADD CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42832 | RADD CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  | 24479FS-1d | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
42833 | RADD CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 24478FS-1d | 24480 | Finish No Earlier Than | 10/31/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
42834 | RADD CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 24479 |  | Finish No Earlier Than | 3/2/26 | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42835 | RADD CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42836 | RADD CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 24483 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42837 | RADD CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 24482 | 24484 | Finish No Earlier Than | 12/31/25 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42838 | RADD CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 24483 |  | Finish No Earlier Than | 3/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42839 | RADD CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42840 | RADD CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  | 24487 | Finish No Earlier Than | 12/31/25 | 39 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42841 | RADD CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 24486 | 24489FS-1d | Finish No Earlier Than | 3/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42842 | RADD CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42843 | RADD CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 24487FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42844 | RADD CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 39 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
42845 | RADD CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42846 | RADD CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 43 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42847 | RADD CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
42848 | RADD CDSS - Technical Activities | March 19, 2024 12:00 AM | August 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 602 | 293d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.28000000000000003
42849 | RADD CDSS - Complete Tableau Training | March 19, 2024 12:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.56999999999999995
42850 | RADD CDSS - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM |  | 24497SS | Finish No Earlier Than | 3/2/26 | 490 | 405d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.59999999999999998
42851 | RADD CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 24496SS |  | Finish No Earlier Than | 3/2/26 | 490 | 405d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.59999999999999998
42852 | RADD CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 49 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42853 | RADD CDSS - Review disposition of statewide reports | May 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 86 | 0d | NA | NA | 0 days? | No | 5/1/25 | 9/2/25 | NA | 1
42854 | RADD CDSS - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 108 | 0d | NA | NA | 0 days? | No | 4/1/25 | NA | NA | 0.98999999999999999
42855 | RADD CDSS - Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 9/2/25 | 108 | 0d | NA | NA | 0 days? | No | 4/1/25 | 9/2/25 | NA | 1
42856 | RADD CDSS - Complete CDSS Child Welfare Data Usage Questionnaire to determine recommended data path | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
42857 | RADD CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 24504SS,24507 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
42858 | RADD CDSS - Participate in discovery session with RADD to gain a better understanding of future state data needs | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 24503SS | 24505SS | As Soon As Possible | NA | 32 | 497d | NA | NA | 0 days? | No | NA | NA | NA | 0
42859 | RADD CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 24504SS |  | As Soon As Possible | NA | 32 | 497d | NA | NA | 0 days? | No | NA | NA | NA | 0
42860 | RADD CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 52 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42861 | RADD CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 24503 | 24508 | As Soon As Possible | NA | 52 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42862 | RADD CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 24507 |  | As Soon As Possible | NA | 158 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
42863 | RADD CDSS - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 171 | 373d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.20000000000000001
42864 | RADD CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 24511FS+1d,24513SS | Finish No Earlier Than | 10/31/25 | 58 | 373d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.59999999999999998
42865 | RADD CDSS - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 24510FS+1d |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
42866 | RADD CDSS - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 251 | 293d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 7.0000000000000007E-2
42867 | RADD CDSS - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 24510SS | 24514 | Finish No Earlier Than | 9/30/25 | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
42868 | RADD CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24513 | 24515SS,24516 | Finish No Earlier Than | 4/30/26 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42869 | RADD CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24514SS | 24516 | Finish No Earlier Than | 4/30/26 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42870 | RADD CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 24514,24515 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
42871 | RADD CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 146 | 293d | NA | NA | 0 days? | No | NA | NA | NA | 0
42872 | RADD CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42873 | RADD CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 24520SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42874 | RADD CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24519SS | 24521SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42875 | RADD CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24520SS | 24522SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42876 | RADD CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24521SS | 24523SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42877 | RADD CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24522SS | 24524SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42878 | RADD CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24523SS | 24525SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42879 | RADD CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24524SS | 24526SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42880 | RADD CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24525SS | 24527SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42881 | RADD CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24526SS | 24528SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42882 | RADD CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24527SS | 24529SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42883 | RADD CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24528SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
42884 | RADD CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
42885 | RADD CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
42886 | RADD CDSS - Training | July 1, 2025 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 376 | 196d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
42887 | RADD CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 188 | 384d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
42888 | RADD CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM |  | 24540 | Finish No Earlier Than | 3/31/26 | 123 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
42889 | RADD CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 6/30/26 | 187 | 322d | NA | NA | 0 days? | No | NA | NA | NA | 0
42890 | RADD CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42891 | RADD CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42892 | RADD CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 24548 | Finish No Earlier Than | 4/30/26 | 62 | 275d | NA | NA | 0 days? | No | NA | NA | NA | 0
42893 | RADD CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 24549 | Finish No Earlier Than | 4/30/26 | 62 | 275d | NA | NA | 0 days? | No | NA | NA | NA | 0
42894 | RADD CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 24534 |  | Start No Earlier Than | 4/1/26 | 189 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
42895 | RADD CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
42896 | RADD CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 24543SS,24551SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42897 | RADD CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24542SS | 24544SS,24552SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42898 | RADD CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24543SS | 24545SS,24553SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42899 | RADD CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24544SS | 24546SS,24554SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42900 | RADD CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24545SS | 24555SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42901 | RADD CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
42902 | RADD CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 24538 |  | Start No Earlier Than | 5/1/26 | 89 | 274d | NA | NA | 0 days? | No | NA | NA | NA | 0
42903 | RADD CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 24539 |  | Start No Earlier Than | 5/1/26 | 89 | 274d | NA | NA | 0 days? | No | NA | NA | NA | 0
42904 | RADD CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM |  | 24558FS+13d | Finish No Earlier Than | 7/15/26 | 50 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
42905 | RADD CDSS - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24542SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42906 | RADD CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24543SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42907 | RADD CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24544SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42908 | RADD CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24545SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42909 | RADD CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24546SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42910 | RADD CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 24558SS+40d | Start No Earlier Than | 6/1/26 | 44 | 283d | NA | NA | 0 days? | No | NA | NA | NA | 0
42911 | RADD CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM |  |  | Finish No Earlier Than | 7/31/26 | 33 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
42912 | RADD CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 24550FS+13d,24556SS+40d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
42913 | SPEI CDSS - Implementation | July 17, 2023 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 867 | 196d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.44
42914 | SPEI CDSS - Implementation Management | July 17, 2023 12:00 AM | November 2, 2026 5:00 PM |  |  | As Soon As Possible | NA | 829 | 234d | NA | NA | 0 days? | No | 7/17/23 | NA | NA | 0.51000000000000001
42915 | SPEI CDSS - Monthly Readiness Meetings | December 2, 2024 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 482 | 235d | NA | NA | 0 days? | No | 12/2/24 | NA | NA | 0.42999999999999999
42916 | SPEI CDSS - Monthly Readiness Meetings | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | Start No Earlier Than | 12/1/24 | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
42917 | SPEI CDSS - Monthly Readiness Meetings | January 2, 2025 8:00 AM | January 31, 2025 5:00 PM |  |  | Start No Earlier Than | 1/2/25 | 21 | 0d | NA | NA | 0 days? | No | 1/2/25 | 1/31/25 | NA | 1
42918 | SPEI CDSS - Monthly Readiness Meetings | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  |  | Start No Earlier Than | 2/1/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
42919 | SPEI CDSS - Monthly Readiness Meetings | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Start No Earlier Than | 3/1/25 | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 4/1/25 | NA | 1
42920 | SPEI CDSS - Monthly Readiness Meetings | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | Start No Earlier Than | 4/1/25 | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
42921 | SPEI CDSS - Monthly Readiness Meetings | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | Start No Earlier Than | 5/1/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
42922 | SPEI CDSS - Monthly Readiness Meetings | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Start No Earlier Than | 6/1/25 | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
42923 | SPEI CDSS - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
42924 | SPEI CDSS - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
42925 | SPEI CDSS - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
42926 | SPEI CDSS - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
42927 | SPEI CDSS - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
42928 | SPEI CDSS - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
42929 | SPEI CDSS - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
42930 | SPEI CDSS - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/1/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42931 | SPEI CDSS - Monthly Readiness Meetings | March 2, 2026 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/1/26 | 22 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
42932 | SPEI CDSS - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42933 | SPEI CDSS - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
42934 | SPEI CDSS - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
42935 | SPEI CDSS - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
42936 | SPEI CDSS - Monthly Readiness Meetings | August 3, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 21 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
42937 | SPEI CDSS - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
42938 | SPEI CDSS - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
42939 | SPEI CDSS - Attend Executive Briefing Meeting | July 17, 2023 12:00 AM | September 10, 2024 5:00 PM |  |  | As Soon As Possible | NA | 291 | 0d | NA | NA | 0 days? | No | 7/17/23 | 9/10/24 | NA | 1
42940 | SPEI CDSS - Conduct Discovery Conversations | October 2, 2023 8:00 AM | December 2, 2024 5:00 PM |  |  | As Soon As Possible | NA | 293 | 0d | NA | NA | 0 days? | No | 10/2/23 | 12/2/24 | NA | 1
42941 | SPEI CDSS - Schedule Kickoff Meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM |  |  | As Soon As Possible | NA | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
42942 | SPEI CDSS - Attend Kickoff Meeting | July 1, 2024 12:00 AM | September 27, 2024 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 63 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/27/24 | NA | 1
42943 | SPEI CDSS - Schedule Organization Assessment spreadsheet review meeting | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
42944 | SPEI CDSS - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | July 1, 2024 12:00 AM | September 30, 2024 5:00 PM |  |  | Finish No Earlier Than | 9/30/24 | 65 | 0d | NA | NA | 0 days? | No | 7/1/24 | 9/30/24 | NA | 1
42945 | SPEI CDSS - Establish method for keeping interim processes and release notes current (if applicable) | April 6, 2026 8:00 AM | July 21, 2026 5:00 PM |  |  | Start No Earlier Than | 4/6/26 | 75 | 307d | NA | NA | 0 days? | No | NA | NA | NA | 0
42946 | SPEI CDSS - Receive and communicate interim processes and release notes to users (if applicable) | May 20, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 5/20/26 | 54 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
42947 | SPEI CDSS - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 62 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
42948 | SPEI CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 2, 2026 5:00 PM |  | 24595SS | Finish No Earlier Than | 2/2/26 | 20 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
42949 | SPEI CDSS - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 16, 2026 5:00 PM | 24594SS |  | Finish No Earlier Than | 2/16/26 | 29 | 415d | NA | NA | 0 days? | No | NA | NA | NA | 0
42950 | SPEI CDSS - Develop Go-Live Support Plan | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42951 | SPEI CDSS - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 62 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42952 | SPEI CDSS - Complete & Submit Production user spreadsheet | February 27, 2026 8:00 AM | June 1, 2026 5:00 PM |  | 24599SS | Finish No Earlier Than | 6/1/26 | 65 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
42953 | SPEI CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | February 27, 2026 8:00 AM | March 30, 2026 5:00 PM | 24598SS | 24600SS | As Soon As Possible | NA | 22 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
42954 | SPEI CDSS - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | February 27, 2026 8:00 AM | April 20, 2026 5:00 PM | 24599SS |  | As Soon As Possible | NA | 36 | 371d | NA | NA | 0 days? | No | NA | NA | NA | 0
42955 | SPEI CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | May 1, 2026 8:00 AM | May 29, 2026 5:00 PM |  | 24602SS | Start No Earlier Than | 5/1/26 | 20 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
42956 | SPEI CDSS - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | May 1, 2026 8:00 AM | June 15, 2026 5:00 PM | 24601SS |  | As Soon As Possible | NA | 31 | 332d | NA | NA | 0 days? | No | NA | NA | NA | 0
42957 | SPEI CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  | 24604SS | Start No Earlier Than | 6/1/26 | 22 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
42958 | SPEI CDSS - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | June 1, 2026 8:00 AM | July 15, 2026 5:00 PM | 24603SS |  | As Soon As Possible | NA | 32 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
42959 | SPEI CDSS - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 24606SS | Start No Earlier Than | 7/1/26 | 22 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
42960 | SPEI CDSS - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 14, 2026 5:00 PM | 24605SS |  | As Soon As Possible | NA | 32 | 289d | NA | NA | 0 days? | No | NA | NA | NA | 0
42961 | SPEI CDSS - Participate in Login Day to mitigate Go-Live Day access issues | July 7, 2026 8:00 AM | August 5, 2026 5:00 PM |  |  | Start No Earlier Than | 7/7/26 | 22 | 296d | NA | NA | 0 days? | No | NA | NA | NA | 0
42962 | SPEI CDSS - Validate readiness for Go-Live one (1) week prior | August 17, 2026 8:00 AM | August 21, 2026 5:00 PM |  |  | Start No Earlier Than | 8/17/26 | 5 | 284d | NA | NA | 0 days? | No | NA | NA | NA | 0
42963 | SPEI CDSS - Begin post conversion data cleanup | September 1, 2026 8:00 AM | November 2, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 44 | 234d | NA | NA | 0 days? | No | NA | NA | NA | 0
42964 | SPEI CDSS - OCM Activities | February 3, 2025 8:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 442 | 233d | NA | NA | 0 days? | No | 2/3/25 | NA | NA | 0.38
42965 | SPEI CDSS - Review and customize Organization Communication Plan template | March 3, 2025 8:00 AM | April 30, 2025 5:00 PM |  | 24613SS+40d | As Soon As Possible | NA | 42 | 0d | NA | NA | 0 days? | No | 3/3/25 | 4/30/25 | NA | 1
42966 | SPEI CDSS - Participate in OCM overview education session for CDSS | April 1, 2025 12:00 AM | April 29, 2025 5:00 PM |  |  | Finish No Earlier Than | 4/30/25 | 21 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/29/25 | NA | 1
42967 | SPEI CDSS - Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2025 12:00 AM | November 3, 2026 5:00 PM | 24611SS+40d |  | As Soon As Possible | NA | 380 | 233d | NA | NA | 0 days? | No | 5/1/25 | NA | NA | 0.40000000000000002
42968 | SPEI CDSS - Identify staff with expertise in Intake to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task MS 3, 4, 5. | February 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Finish No Earlier Than | 3/28/25 | 40 | 0d | NA | NA | 0 days? | No | 2/3/25 | 4/1/25 | NA | 1
42969 | SPEI CDSS - Participate in OCM led Process Information Session for Intake | April 1, 2025 12:00 AM | June 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/2/25 | 43 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/2/25 | NA | 1
42970 | SPEI CDSS - Review Change Impact Assessment for Intake and draft necessary revisions to internal business processes/procedures and operational manuals | June 2, 2025 8:00 AM | July 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 7/31/25 | 40 | 0d | NA | NA | 0 days? | No | 6/2/25 | 7/30/25 | NA | 1
42971 | SPEI CDSS - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42972 | SPEI CDSS - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  | 24619 | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
42973 | SPEI CDSS - Participate in OCM led Process Information Session for Case Management - Placement & Eligibility | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM | 24618 | 24620FS-1d | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
42974 | SPEI CDSS - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM | 24619FS-1d |  | As Soon As Possible | NA | 63 | 0d | NA | NA | 0 days? | No | 9/2/25 | 12/1/25 | NA | 1
42975 | SPEI CDSS - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42976 | SPEI CDSS - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manual | July 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  | 24623FS-1d | Finish No Earlier Than | 9/2/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
42977 | SPEI CDSS - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM | 24622FS-1d | 24624 | Finish No Earlier Than | 10/31/25 | 44 | 405d | NA | NA | 0 days? | No | 9/2/25 | NA | NA | 0.20000000000000001
42978 | SPEI CDSS - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM | 24623 |  | Finish No Earlier Than | 3/2/26 | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42979 | SPEI CDSS - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42980 | SPEI CDSS - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 24627 | Start No Earlier Than | 9/2/25 | 44 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42981 | SPEI CDSS - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM | 24626 | 24628 | Finish No Earlier Than | 12/31/25 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42982 | SPEI CDSS - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 24627 |  | Finish No Earlier Than | 3/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42983 | SPEI CDSS - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42984 | SPEI CDSS - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operat | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  | 24631 | Finish No Earlier Than | 12/31/25 | 39 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42985 | SPEI CDSS - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM | 24630 | 24633FS-1d | Finish No Earlier Than | 3/2/26 | 40 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42986 | SPEI CDSS - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/8/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42987 | SPEI CDSS - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | April 30, 2026 5:00 PM | 24631FS-1d |  | Finish No Earlier Than | 4/30/26 | 43 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
42988 | SPEI CDSS - Identify appropriate staff to participate in OCM-Led process information session for CDSS | November 3, 2025 8:00 AM | December 31, 2025 12:00 AM |  |  | Finish No Earlier Than | 12/31/25 | 39 | 446d | NA | NA | 0 days? | No | NA | NA | NA | 0
42989 | SPEI CDSS - Participate in OCM led Process Information Session for CDSS | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
42990 | SPEI CDSS - Review Change Impact Assessment for CDSS and draft necessary revisions to desk guides | February 27, 2026 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 43 | 364d | NA | NA | 0 days? | No | NA | NA | NA | 0
42991 | SPEI CDSS - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
42992 | SPEI CDSS - Technical Activities | March 19, 2024 12:00 AM | August 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 602 | 293d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.56999999999999995
42993 | SPEI CDSS - Complete Tableau Training | March 19, 2024 12:00 AM | May 8, 2026 5:00 PM |  |  | As Soon As Possible | NA | 538 | 357d | NA | NA | 0 days? | No | 3/19/24 | NA | NA | 0.94999999999999996
42994 | SPEI CDSS - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM |  | 24641SS | Finish No Earlier Than | 3/2/26 | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
42995 | SPEI CDSS - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 12:00 AM | March 2, 2026 5:00 PM | 24640SS |  | Finish No Earlier Than | 3/2/26 | 490 | 0d | NA | NA | 0 days? | No | 3/19/24 | 3/2/26 | NA | 1
42996 | SPEI CDSS - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 2, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 49 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
42997 | SPEI CDSS - Review disposition of statewide reports | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
42998 | SPEI CDSS - Identify Business Objects Organization-specific custom reports by completing the Organization Reports Inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | As Soon As Possible | NA | 108 | 0d | NA | NA | 0 days? | No | 4/1/25 | NA | NA | 0.98999999999999999
42999 | SPEI CDSS - Identify additional organization-specific reports and external system reports and add to workbook inventory | April 1, 2025 12:00 AM | September 2, 2025 5:00 PM |  |  | Finish No Earlier Than | 9/2/25 | 108 | 0d | NA | NA | 0 days? | No | 4/1/25 | 9/2/25 | NA | 1
43000 | SPEI CDSS - Complete CDSS Child Welfare Data Usage Questionnaire to determine recommended data path | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
43001 | SPEI CDSS - Complete Inventory for all other Reports/Extracts. | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 24648SS,24651 | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
43002 | SPEI CDSS - Participate in discovery session with RADD to gain a better understanding of future state data needs | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 24647SS | 24649SS | As Soon As Possible | NA | 32 | 0d | NA | NA | 0 days? | No | 9/2/25 | 10/15/25 | NA | 1
43003 | SPEI CDSS - Attend data pathways informational session to learn about the future plan for all report and extract types | September 2, 2025 8:00 AM | October 15, 2025 5:00 PM | 24648SS |  | As Soon As Possible | NA | 32 | 497d | NA | NA | 0 days? | No | NA | NA | NA | 0
43004 | SPEI CDSS - Use the guidance developed by RADD/CDI for each data path (Tableau or EDP) to develop a plan for preparing all reports and extracts | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM |  |  | As Soon As Possible | NA | 52 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
43005 | SPEI CDSS - Crosswalk Business Objects Reports with CARES Reports Tracker, SM Reports, RADD-Maintained Reports Development List, and RADD Plan for Curated Analytic Files to Identify Gaps | October 1, 2025 8:00 AM | December 15, 2025 5:00 PM | 24647 | 24652 | As Soon As Possible | NA | 52 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
43006 | SPEI CDSS - Execute Plan for Transition | December 16, 2025 8:00 AM | August 3, 2026 5:00 PM | 24651 |  | As Soon As Possible | NA | 158 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
43007 | SPEI CDSS - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 171 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
43008 | SPEI CDSS - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 12:00 AM |  | 24655FS+1d,24657SS | Finish No Earlier Than | 10/31/25 | 58 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
43009 | SPEI CDSS - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 24654FS+1d |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
43010 | SPEI CDSS - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 10, 2026 5:00 PM |  |  | As Soon As Possible | NA | 251 | 293d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 7.0000000000000007E-2
43011 | SPEI CDSS - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM | 24654SS | 24658 | Finish No Earlier Than | 9/30/25 | 36 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
43012 | SPEI CDSS - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24657 | 24659SS,24660 | Finish No Earlier Than | 4/30/26 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
43013 | SPEI CDSS - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24658SS | 24660 | Finish No Earlier Than | 4/30/26 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
43014 | SPEI CDSS - POC or Organization Leadership to sign off on report creation completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 24658,24659 |  | Finish No Earlier Than | 5/26/26 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
43015 | SPEI CDSS - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 10, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 146 | 293d | NA | NA | 0 days? | No | NA | NA | NA | 0
43016 | SPEI CDSS - Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | April 30, 2026 12:00 AM |  |  | As Soon As Possible | NA | 311 | 0d | NA | NA | 0 days? | No | 2/3/25 | 4/30/26 | NA | 1
43017 | SPEI CDSS - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 24664SS | Finish No Earlier Than | 2/2/26 | 251 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/2/26 | NA | 1
43018 | SPEI CDSS - Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 24663SS |  | Finish No Earlier Than | 1/1/26 | 251 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/2/26 | NA | 1
43019 | SPEI CDSS - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | March 28, 2025 8:00 AM | April 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 4/30/26 | 273 | 0d | NA | NA | 0 days? | No | 3/28/25 | 4/30/26 | NA | 1
43020 | SPEI CDSS - Review disposition of statewide Forms provided by Project | May 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
43021 | SPEI CDSS - Identify Organization-specific forms by completing the Forms Inventory Workbooks | April 1, 2025 12:00 AM | August 8, 2025 5:00 PM |  |  | As Soon As Possible | NA | 92 | 0d | NA | NA | 0 days? | No | 4/1/25 | 8/8/25 | NA | 1
43022 | SPEI CDSS - Add forms to Inventory Workbook including legacy, external systems, other applicable child welfare forms | April 1, 2025 12:00 AM | June 30, 2025 5:00 PM |  | 24669 | Finish No Earlier Than | 6/30/25 | 64 | 0d | NA | NA | 0 days? | No | 4/1/25 | 6/30/25 | NA | 1
43023 | SPEI CDSS - Review the CARES Forms Tracker list of state forms offered in the CARES Forms Workgroup Teams Channel to identify duplicative organization forms, or forms no longer needed | July 1, 2025 12:00 AM | August 8, 2025 5:00 PM | 24668 | 24671 | Finish No Earlier Than | 8/8/25 | 28 | 0d | NA | NA | 0 days? | No | 7/1/25 | 8/8/25 | NA | 1
43024 | SPEI CDSS - Determine priority for Organization-specific custom Forms | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 171 | 0d | NA | NA | 0 days? | No | 8/11/25 | 4/16/26 | NA | 1
43025 | SPEI CDSS - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM | 24669 | 24672FS+1d | Finish No Earlier Than | 10/31/25 | 59 | 0d | NA | NA | 0 days? | No | 8/11/25 | 10/31/25 | NA | 1
43026 | SPEI CDSS - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | November 4, 2025 8:00 AM | April 16, 2026 5:00 PM | 24671FS+1d |  | Start No Earlier Than | 11/3/25 | 111 | 0d | NA | NA | 0 days? | No | 11/4/25 | 4/16/26 | NA | 1
43027 | SPEI CDSS - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | 8/11/25 | NA | NA | 0.70999999999999996
43028 | SPEI CDSS - Develop Plan for Timeline of Form Creation in AEM/Word | August 11, 2025 8:00 AM | September 30, 2025 12:00 AM |  | 24675 | Finish No Earlier Than | 9/30/25 | 35 | 0d | NA | NA | 0 days? | No | 8/11/25 | 9/30/25 | NA | 1
43029 | SPEI CDSS - Create organization-specific forms | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24674 | 24676FF | Start No Earlier Than | 10/1/25 | 146 | 0d | NA | NA | 0 days? | No | 10/1/25 | 5/1/26 | NA | 1
43030 | SPEI CDSS - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24675FF | 24677 | Finish No Earlier Than | 4/30/26 | 146 | 0d | NA | NA | 0 days? | No | 10/1/25 | 5/1/26 | NA | 1
43031 | SPEI CDSS - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 24676 |  | Finish No Earlier Than | 5/26/26 | 17 | 0d | NA | NA | 0 days? | No | 5/4/26 | 5/27/26 | NA | 1
43032 | SPEI CDSS - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
43033 | SPEI CDSS - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43034 | SPEI CDSS - Confirm Organization’s workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 24681SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43035 | SPEI CDSS - Confirm Organization’s e-mail server won’t filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24680SS | 24682SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43036 | SPEI CDSS - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24681SS | 24683SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43037 | SPEI CDSS - Confirm Organization’s IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24682SS | 24684SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43038 | SPEI CDSS - Verify Organization’s workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24683SS | 24685SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43039 | SPEI CDSS - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24684SS | 24686SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43040 | SPEI CDSS - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24685SS | 24687SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43041 | SPEI CDSS - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24686SS | 24688SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43042 | SPEI CDSS - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24687SS | 24689SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43043 | SPEI CDSS - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24688SS | 24690SS | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43044 | SPEI CDSS - Confirm Organization’s CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24689SS |  | Finish No Earlier Than | 4/30/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43045 | SPEI CDSS - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | May 29, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 19 | 343d | NA | NA | 0 days? | No | NA | NA | NA | 0
43046 | SPEI CDSS - Identify and implement the process by which staff will access the Production environment | May 4, 2026 8:00 AM | June 12, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 29 | 333d | NA | NA | 0 days? | No | NA | NA | NA | 0
43047 | SPEI CDSS - Training | July 1, 2025 12:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 376 | 196d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
43048 | SPEI CDSS - Develop the CARES V1 Organization Training Plan | July 1, 2025 12:00 AM | April 1, 2026 5:00 PM |  |  | Finish No Earlier Than | 3/31/26 | 188 | 384d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
43049 | SPEI CDSS - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | March 31, 2026 12:00 AM |  | 24701 | Finish No Earlier Than | 3/31/26 | 123 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
43050 | SPEI CDSS - Assess and add Organization-specific information to ILT materials (if needed) | September 30, 2025 8:00 AM | June 30, 2026 12:00 AM |  |  | Finish No Earlier Than | 6/30/26 | 187 | 322d | NA | NA | 0 days? | No | NA | NA | NA | 0
43051 | SPEI CDSS - Receive Project-developed User Guides for RFA portal for applicants | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
43052 | SPEI CDSS - Receive Project-developed User Guides for FFPSA portal for providers | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
43053 | SPEI CDSS - Identify Support Structure needed for RFA Applicants | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 24709 | Finish No Earlier Than | 4/30/26 | 62 | 275d | NA | NA | 0 days? | No | NA | NA | NA | 0
43054 | SPEI CDSS - Identify support structure needed for FFPSA providers | January 30, 2026 8:00 AM | April 30, 2026 12:00 AM |  | 24710 | Finish No Earlier Than | 4/30/26 | 62 | 275d | NA | NA | 0 days? | No | NA | NA | NA | 0
43055 | SPEI CDSS - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM | 24695 |  | Start No Earlier Than | 4/1/26 | 189 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
43056 | SPEI CDSS - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 12:00 AM |  |  | Finish No Earlier Than | 5/8/26 | 19 | 358d | NA | NA | 0 days? | No | NA | NA | NA | 0
43057 | SPEI CDSS - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM |  | 24704SS,24712SS+20d | Start No Earlier Than | 5/1/26 | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
43058 | SPEI CDSS - Prepare training on Case Management - Placement and Eligibility processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24703SS | 24705SS,24713SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
43059 | SPEI CDSS - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24704SS | 24706SS,24714SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
43060 | SPEI CDSS - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24705SS | 24707SS,24715SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
43061 | SPEI CDSS - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | June 12, 2026 5:00 PM | 24706SS | 24716SS+20d | As Soon As Possible | NA | 30 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
43062 | SPEI CDSS - Validate access to all training materials | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Finish No Earlier Than | 10/2/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
43063 | SPEI CDSS - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 24699 |  | Start No Earlier Than | 5/1/26 | 89 | 274d | NA | NA | 0 days? | No | NA | NA | NA | 0
43064 | SPEI CDSS - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | September 4, 2026 5:00 PM | 24700 |  | Start No Earlier Than | 5/1/26 | 89 | 274d | NA | NA | 0 days? | No | NA | NA | NA | 0
43065 | SPEI CDSS - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 12:00 AM |  | 24719FS+13d | Finish No Earlier Than | 7/15/26 | 50 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
43066 | SPEI CDSS - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24703SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
43067 | SPEI CDSS - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24704SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
43068 | SPEI CDSS - Deliver processes/procedures training (if applicable) for Case Management - Ongoing Case Work and Case Management - Finish a Case | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24705SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
43069 | SPEI CDSS - Deliver processes/procedures training (if applicable) for Other Court Processing | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24706SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
43070 | SPEI CDSS - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM | 24707SS+20d |  | As Soon As Possible | NA | 44 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
43071 | SPEI CDSS - Complete on-demand training | June 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  | 24719SS+40d | Start No Earlier Than | 6/1/26 | 44 | 283d | NA | NA | 0 days? | No | NA | NA | NA | 0
43072 | SPEI CDSS - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 12:00 AM |  |  | Finish No Earlier Than | 7/31/26 | 33 | 300d | NA | NA | 0 days? | No | NA | NA | NA | 0
43073 | SPEI CDSS - Complete instructor-led training | August 3, 2026 8:00 AM | August 28, 2026 5:00 PM | 24711FS+13d,24717SS+40d |  | As Soon As Possible | NA | 20 | 279d | NA | NA | 0 days? | No | NA | NA | NA | 0
43075 | Tribes | November 1, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 792 | 195d | NA | NA | 0 days? | No | 11/1/23 | NA | NA | 5.0000000000000003E-2
43076 | Karuk TR - Implementation | November 1, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 792 | 195d | NA | NA | 0 days? | No | 11/1/23 | NA | NA | 5.0000000000000003E-2
43077 | Karuk TR - Implementation Management | November 1, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 752 | 235d | NA | NA | 0 days? | No | 11/1/23 | NA | NA | 0.17000000000000001
43078 | Karuk TR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 0d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
43079 | Karuk TR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
43080 | Karuk TR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
43081 | Karuk TR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
43082 | Karuk TR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
43083 | Karuk TR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
43084 | Karuk TR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
43085 | Karuk TR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
43086 | Karuk TR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
43087 | Karuk TR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
43088 | Karuk TR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
43089 | Karuk TR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
43090 | Karuk TR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
43091 | Karuk TR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
43092 | Karuk TR - Monthly Readiness Meetings | August 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 22 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
43093 | Karuk TR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
43094 | Karuk TR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
43095 | Karuk TR - Attend Executive Briefing Meeting | November 1, 2023 8:00 AM | November 30, 2023 5:00 PM |  |  | Start No Earlier Than | 11/1/23 | 19 | 0d | NA | NA | 0 days? | No | 11/1/23 | 11/30/23 | NA | 1
43096 | Karuk TR - Schedule Kickoff Meeting | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | Start No Earlier Than | 12/2/24 | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
43097 | Karuk TR - Attend Kickoff Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  | 24743FS-1d | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
43098 | Karuk TR - Schedule Organization Assessment spreadsheet review meeting | February 19, 2025 8:00 AM | March 7, 2025 5:00 PM | 24742FS-1d |  | As Soon As Possible | NA | 13 | 0d | NA | NA | 0 days? | No | 2/19/25 | 3/7/25 | NA | 1
43099 | Karuk TR - Confirm Tribal Implementation Team | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Start No Earlier Than | 3/3/25 | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 4/1/25 | NA | 1
43100 | Karuk TR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | Start No Earlier Than | 4/1/25 | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
43101 | Karuk TR - IL to demonstrate how to access Imp Portal throughÂ cwds.ca.gov | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | Start No Earlier Than | 5/1/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
43102 | Karuk TR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
43103 | Karuk TR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/5/26 | 21 | 423d | NA | NA | 0 days? | No | NA | NA | NA | 0
43104 | Karuk TR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM |  |  | Start No Earlier Than | 1/5/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
43105 | Karuk TR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 24751SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43106 | Karuk TR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24750SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43107 | Karuk TR - Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 2, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 65 | 341d | NA | NA | 0 days? | No | NA | NA | NA | 0
43108 | Karuk TR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
43109 | Karuk TR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
43110 | Karuk TR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
43111 | Karuk TR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
43112 | Karuk TR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
43113 | Karuk TR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
43114 | Karuk TR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | September 1, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 22 | 277d | NA | NA | 0 days? | No | NA | NA | NA | 0
43115 | Karuk TR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
43116 | Karuk TR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 24762SS | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
43117 | Karuk TR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 24761SS | 24763SS | Finish No Earlier Than | 9/30/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
43118 | Karuk TR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 24762SS |  | Finish No Earlier Than | 10/15/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
43119 | Karuk TR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
43120 | Karuk TR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
43121 | Karuk TR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | November 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 228 | 217d | NA | NA | 0 days? | No | NA | NA | NA | 0
43122 | Karuk TR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/1/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
43123 | Karuk TR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
43124 | Karuk TR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
43125 | Karuk TR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | November 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 40 | 217d | NA | NA | 0 days? | No | NA | NA | NA | 0
43126 | Karuk TR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
43127 | Karuk TR - OCM Activities | May 1, 2025 8:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 381 | 233d | NA | NA | 0 days? | No | 5/1/25 | NA | NA | 0.17999999999999999
43128 | Karuk TR - Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2025 8:00 AM | November 3, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/25 | 381 | 233d | NA | NA | 0 days? | No | 5/1/25 | NA | NA | 0.20000000000000001
43129 | Karuk TR - Review and customize Organization Communication Plan template | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
43130 | Karuk TR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
43131 | Karuk TR - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
43132 | Karuk TR - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
43133 | Karuk TR - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 9/2/25 | 63 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
43134 | Karuk TR - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
43135 | Karuk TR - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals (if | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
43136 | Karuk TR - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 44 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
43137 | Karuk TR - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
43138 | Karuk TR - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
43139 | Karuk TR - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 44 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
43140 | Karuk TR - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
43141 | Karuk TR - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
43142 | Karuk TR - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
43143 | Karuk TR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
43144 | Karuk TR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
43145 | Karuk TR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
43146 | Karuk TR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/1/26 | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43147 | Karuk TR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
43148 | Karuk TR - Technical Activities | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
43149 | Karuk TR - Complete Tableau Training | March 19, 2024 8:00 AM | May 11, 2026 5:00 PM |  |  | As Soon As Possible | NA | 539 | 356d | NA | NA | 0 days? | No | NA | NA | NA | 0
43150 | Karuk TR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 24796SS,24797 | Start No Earlier Than | 3/19/24 | 490 | 356d | NA | NA | 0 days? | No | NA | NA | NA | 0
43151 | Karuk TR - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 24795SS | 24797 | As Soon As Possible | NA | 490 | 356d | NA | NA | 0 days? | No | NA | NA | NA | 0
43152 | Karuk TR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 11, 2026 5:00 PM | 24795,24796 |  | As Soon As Possible | NA | 49 | 356d | NA | NA | 0 days? | No | NA | NA | NA | 0
43153 | Karuk TR - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 171 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
43154 | Karuk TR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 24800 | Start No Earlier Than | 8/11/25 | 59 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
43155 | Karuk TR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 24799 |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
43156 | Karuk TR - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
43157 | Karuk TR - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 8/11/25 | 36 | 508d | NA | NA | 0 days? | No | NA | NA | NA | 0
43158 | Karuk TR - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 24804SS | Start No Earlier Than | 10/1/25 | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43159 | Karuk TR - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24803SS |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43160 | Karuk TR - POC or Organization Leadership to sign off on report creation completion | May 1, 2026 8:00 AM | May 26, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/26/26 | 17 | 346d | NA | NA | 0 days? | No | NA | NA | NA | 0
43161 | Karuk TR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
43162 | Karuk TR - Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43163 | Karuk TR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 24809SS | Start No Earlier Than | 2/1/25 | 251 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
43164 | Karuk TR - Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 24808SS |  | As Soon As Possible | NA | 251 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
43165 | Karuk TR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | April 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/25 | 274 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43166 | Karuk TR - Determine priority for Organization-specific custom Forms | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 171 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
43167 | Karuk TR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 24813 | Start No Earlier Than | 8/11/25 | 59 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
43168 | Karuk TR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 24812 |  | Start No Earlier Than | 11/1/25 | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
43169 | Karuk TR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
43170 | Karuk TR - Develop Plan for Timeline of Form Creation in AEM/Word | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 24816 | Start No Earlier Than | 8/11/25 | 36 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
43171 | Karuk TR - Create organization-specific forms | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24815 | 24817SS,24818 | As Soon As Possible | NA | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
43172 | Karuk TR - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24816SS | 24818 | Start No Earlier Than | 10/1/25 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
43173 | Karuk TR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 24816,24817 |  | Start No Earlier Than | 6/30/25 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
43174 | Karuk TR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
43175 | Karuk TR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43176 | Karuk TR - Confirm Organizations workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 24822SS | Start No Earlier Than | 1/1/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43177 | Karuk TR - Confirm Organizations e-mail server won't filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24821SS | 24823SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43178 | Karuk TR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24822SS | 24824SS | Start No Earlier Than | 1/1/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43179 | Karuk TR - Confirm Organizations IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24823SS | 24825SS | Start No Earlier Than | 1/1/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43180 | Karuk TR - Verify Organizations workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24824SS | 24826SS | Start No Earlier Than | 1/1/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43181 | Karuk TR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24825SS | 24827SS | Start No Earlier Than | 1/1/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43182 | Karuk TR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24826SS | 24828SS | Start No Earlier Than | 1/1/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43183 | Karuk TR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24827SS | 24829SS | Start No Earlier Than | 1/1/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43184 | Karuk TR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24828SS | 24830SS | Start No Earlier Than | 1/1/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43185 | Karuk TR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24829SS | 24831SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43186 | Karuk TR - Confirm Organizations CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24830SS |  | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43187 | Karuk TR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
43188 | Karuk TR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/10/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
43189 | Karuk TR - Training | July 1, 2025 8:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 376 | 196d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
43190 | Karuk TR - Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 188 | 384d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
43191 | Karuk TR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
43192 | Karuk TR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
43193 | Karuk TR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43194 | Karuk TR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43195 | Karuk TR - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 189 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
43196 | Karuk TR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
43197 | Karuk TR - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 24843SS | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
43198 | Karuk TR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 24842SS | 24844SS | As Soon As Possible | NA | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
43199 | Karuk TR - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 24843SS | 24845SS | As Soon As Possible | NA | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
43200 | Karuk TR - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 24844SS | 24846SS | As Soon As Possible | NA | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
43201 | Karuk TR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 24845SS |  | As Soon As Possible | NA | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
43202 | Karuk TR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  | 24848SS | Start No Earlier Than | 5/1/26 | 128 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
43203 | Karuk TR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 24847SS |  | Start No Earlier Than | 5/1/26 | 128 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
43204 | Karuk TR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 51 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
43205 | Karuk TR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
43206 | Karuk TR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
43207 | Karuk TR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
43208 | Karuk TR - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 24854SS | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
43209 | Karuk TR - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 24853SS | 24857SS | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
43210 | Karuk TR - Deliver processes/procedures training (if applicable) for Courts | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 24857SS | 24856SS | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
43211 | Karuk TR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 24855SS |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
43212 | Karuk TR - Deliver processes/procedures training (if applicable) for Resource Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 24854SS | 24855SS | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
43213 | Karuk TR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
43214 | Karuk TR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
43215 | Karuk TR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
43216 | Yurok TR - Implementation | November 1, 2023 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 792 | 195d | NA | NA | 0 days? | No | 11/1/23 | NA | NA | 5.0000000000000003E-2
43217 | Yurok TR - Implementation Management | November 1, 2023 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 752 | 235d | NA | NA | 0 days? | No | 11/1/23 | NA | NA | 0.17000000000000001
43218 | Yurok TR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | October 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 337 | 0d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.19
43219 | Yurok TR - Monthly Readiness Meetings | July 1, 2025 8:00 AM | July 31, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 22 | 0d | NA | NA | 0 days? | No | 7/1/25 | 7/31/25 | NA | 1
43220 | Yurok TR - Monthly Readiness Meetings | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
43221 | Yurok TR - Monthly Readiness Meetings | September 2, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 9/2/25 | 21 | 0d | NA | NA | 0 days? | No | 9/2/25 | 9/30/25 | NA | 1
43222 | Yurok TR - Monthly Readiness Meetings | October 1, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 23 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
43223 | Yurok TR - Monthly Readiness Meetings | November 3, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 11/3/25 | 19 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
43224 | Yurok TR - Monthly Readiness Meetings | December 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 12/1/25 | 22 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
43225 | Yurok TR - Monthly Readiness Meetings | January 2, 2026 8:00 AM | February 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 21 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
43226 | Yurok TR - Monthly Readiness Meetings | February 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 20 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
43227 | Yurok TR - Monthly Readiness Meetings | March 2, 2026 8:00 AM | March 31, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 22 | 385d | NA | NA | 0 days? | No | NA | NA | NA | 0
43228 | Yurok TR - Monthly Readiness Meetings | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
43229 | Yurok TR - Monthly Readiness Meetings | May 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 21 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
43230 | Yurok TR - Monthly Readiness Meetings | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
43231 | Yurok TR - Monthly Readiness Meetings | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
43232 | Yurok TR - Monthly Readiness Meetings | August 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 22 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
43233 | Yurok TR - Monthly Readiness Meetings | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
43234 | Yurok TR - Monthly Readiness Meetings | October 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 22 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
43235 | Yurok TR - Attend Executive Briefing Meeting | November 1, 2023 8:00 AM | November 30, 2023 5:00 PM |  |  | Start No Earlier Than | 11/1/23 | 19 | 0d | NA | NA | 0 days? | No | 11/1/23 | 11/30/23 | NA | 1
43236 | Yurok TR - Schedule Kickoff Meeting | December 2, 2024 8:00 AM | December 31, 2024 5:00 PM |  |  | Start No Earlier Than | 12/2/24 | 21 | 0d | NA | NA | 0 days? | No | 12/2/24 | 12/31/24 | NA | 1
43237 | Yurok TR - Attend Kickoff Meeting | February 3, 2025 8:00 AM | February 28, 2025 5:00 PM |  | 24883FS-1d | Finish No Earlier Than | 2/28/25 | 19 | 0d | NA | NA | 0 days? | No | 2/3/25 | 2/28/25 | NA | 1
43238 | Yurok TR - Schedule Organization Assessment spreadsheet review meeting | February 19, 2025 8:00 AM | March 7, 2025 5:00 PM | 24882FS-1d |  | As Soon As Possible | NA | 13 | 0d | NA | NA | 0 days? | No | 2/19/25 | 3/7/25 | NA | 1
43239 | Yurok TR - Confirm Tribal Implementation Team | March 3, 2025 8:00 AM | April 1, 2025 5:00 PM |  |  | Start No Earlier Than | 3/3/25 | 21 | 0d | NA | NA | 0 days? | No | 3/3/25 | 4/1/25 | NA | 1
43240 | Yurok TR - Attend the Organization Assessment spreadsheet meeting and review and update the spreadsheet | April 1, 2025 8:00 AM | April 30, 2025 5:00 PM |  |  | Start No Earlier Than | 4/1/25 | 22 | 0d | NA | NA | 0 days? | No | 4/1/25 | 4/30/25 | NA | 1
43241 | Yurok TR - IL to demonstrate how to access Imp Portal throughÂ cwds.ca.gov | May 1, 2025 8:00 AM | June 2, 2025 5:00 PM |  |  | Start No Earlier Than | 5/1/25 | 22 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/2/25 | NA | 1
43242 | Yurok TR - Update Disaster Recovery Plan to include CARES | October 1, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 63 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
43243 | Yurok TR - Participate in Readiness Checkpoint and provide validation of readiness - 9 months prior to Go-Live | January 5, 2026 8:00 AM | February 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/5/26 | 21 | 423d | NA | NA | 0 days? | No | NA | NA | NA | 0
43244 | Yurok TR - Document mitigation plan for readiness tasks that are not on track based on 9 month readiness checkpoint results. | January 5, 2026 8:00 AM | February 17, 2026 5:00 PM |  |  | Start No Earlier Than | 1/5/26 | 30 | 414d | NA | NA | 0 days? | No | NA | NA | NA | 0
43245 | Yurok TR - Develop Go-Live Support Plan | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 24891SS | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43246 | Yurok TR - Determine CARES support and escalation process (e.g., local Help Desk, CARES Service Desk) | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24890SS |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43247 | Yurok TR - Complete & Submit Production user spreadsheet | March 2, 2026 8:00 AM | June 2, 2026 5:00 PM |  |  | Start No Earlier Than | 3/2/26 | 65 | 341d | NA | NA | 0 days? | No | NA | NA | NA | 0
43248 | Yurok TR - Participate in Readiness Checkpoint and provide validation of readiness - 6 months prior to Go-Live | April 1, 2026 8:00 AM | April 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 22 | 363d | NA | NA | 0 days? | No | NA | NA | NA | 0
43249 | Yurok TR - Document mitigation plan for readiness tasks that are not on track based on 6 month readiness checkpoint results. | April 1, 2026 8:00 AM | May 15, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 33 | 352d | NA | NA | 0 days? | No | NA | NA | NA | 0
43250 | Yurok TR - Establish method for keeping interim processes and release notes current (if applicable) | June 1, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 75 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
43251 | Yurok TR - Participate in Readiness Checkpoint and provide validation of readiness - 3 months prior to Go-Live | July 1, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 22 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
43252 | Yurok TR - Document mitigation plan for readiness tasks that are not on track based on 3 month readiness checkpoint results. | July 1, 2026 8:00 AM | August 17, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 33 | 288d | NA | NA | 0 days? | No | NA | NA | NA | 0
43253 | Yurok TR - Receive and communicate interim processes and release notes to users (if applicable) | July 15, 2026 8:00 AM | September 30, 2026 5:00 PM |  |  | Start No Earlier Than | 7/15/26 | 55 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
43254 | Yurok TR - Participate in Readiness Checkpoint and provide validation of readiness - 2 months prior to Go-Live | August 3, 2026 8:00 AM | September 1, 2026 5:00 PM |  |  | Start No Earlier Than | 8/1/26 | 22 | 277d | NA | NA | 0 days? | No | NA | NA | NA | 0
43255 | Yurok TR - Document mitigation plan for readiness tasks that are not on track based on 2 month readiness checkpoint results. | August 3, 2026 8:00 AM | September 15, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 31 | 268d | NA | NA | 0 days? | No | NA | NA | NA | 0
43256 | Yurok TR - Participate in Readiness Checkpoint and provide validation of readiness - 1 month prior to Go-Live | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM |  | 24902SS | Start No Earlier Than | 9/1/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
43257 | Yurok TR - Participate in Login Day to mitigate Go-Live Day access issues | September 1, 2026 8:00 AM | September 30, 2026 5:00 PM | 24901SS | 24903SS | Finish No Earlier Than | 9/30/26 | 21 | 257d | NA | NA | 0 days? | No | NA | NA | NA | 0
43258 | Yurok TR - Document mitigation plan for readiness tasks that are not on track based on 1 month readiness checkpoint results. | September 1, 2026 8:00 AM | October 15, 2026 5:00 PM | 24902SS |  | Finish No Earlier Than | 10/15/26 | 32 | 246d | NA | NA | 0 days? | No | NA | NA | NA | 0
43259 | Yurok TR - Validate readiness for Go-Live one (1) week prior | October 12, 2026 8:00 AM | October 16, 2026 5:00 PM |  |  | Start No Earlier Than | 10/12/26 | 5 | 245d | NA | NA | 0 days? | No | NA | NA | NA | 0
43260 | Yurok TR - Data Quality | January 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | As Soon As Possible | NA | 250 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
43261 | Yurok TR - Participate in Data Cleanup Initiatives/Activities Through Go-Live | January 2, 2026 8:00 AM | November 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 228 | 217d | NA | NA | 0 days? | No | NA | NA | NA | 0
43262 | Yurok TR - Participate in data cleanup initiatives/activities_Jan26 | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/1/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
43263 | Yurok TR - Participate in data cleanup initiatives/activities_Apr26 | April 1, 2026 8:00 AM | June 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 43 | 342d | NA | NA | 0 days? | No | NA | NA | NA | 0
43264 | Yurok TR - Participate in data cleanup initiatives/activities_Jul26 | July 1, 2026 8:00 AM | August 31, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/26 | 43 | 278d | NA | NA | 0 days? | No | NA | NA | NA | 0
43265 | Yurok TR - Participate in data cleanup initiatives/activities_Oct26 | October 1, 2026 8:00 AM | November 30, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/26 | 40 | 217d | NA | NA | 0 days? | No | NA | NA | NA | 0
43266 | Yurok TR - Begin post conversion data cleanup | November 2, 2026 8:00 AM | December 31, 2026 5:00 PM |  |  | Start No Earlier Than | 11/2/26 | 40 | 195d | NA | NA | 0 days? | No | NA | NA | NA | 0
43267 | Yurok TR - OCM Activities | May 1, 2025 8:00 AM | November 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 381 | 233d | NA | NA | 0 days? | No | 5/1/25 | NA | NA | 0.17999999999999999
43268 | Yurok TR - Execute Organization Communication Plan template and continue revisions, as necessary | May 1, 2025 8:00 AM | November 3, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/25 | 381 | 233d | NA | NA | 0 days? | No | 5/1/25 | NA | NA | 0.20000000000000001
43269 | Yurok TR - Review and customize Organization Communication Plan template | June 2, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | As Soon As Possible | NA | 21 | 0d | NA | NA | 0 days? | No | 6/2/25 | 6/30/25 | NA | 1
43270 | Yurok TR - Participate in OCM overview education session | August 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 8/1/25 | 22 | 0d | NA | NA | 0 days? | No | 8/1/25 | 9/2/25 | NA | 1
43271 | Yurok TR - Review, update as needed, and FINALIZE Intake processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
43272 | Yurok TR - Identify staff with expertise in Case Management - Placement & Eligibility (MS 1, 2, 6, 8, 15, 15.1, 19, 20, 20.1, 21 ) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM | May 1, 2025 8:00 AM | June 30, 2025 5:00 PM |  |  | Finish No Earlier Than | 6/30/25 | 42 | 0d | NA | NA | 0 days? | No | 5/1/25 | 6/30/25 | NA | 1
43273 | Yurok TR - Review Change Impact Assessment for Case Management - Placement & Eligibility and draft necessary revisions to internal business processes/procedures and operational manuals | September 2, 2025 8:00 AM | December 1, 2025 5:00 PM |  |  | Start No Earlier Than | 9/2/25 | 63 | 466d | NA | NA | 0 days? | No | NA | NA | NA | 0
43274 | Yurok TR - Review, update as needed, and FINALIZE Case Management - Placement & Eligibility processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
43275 | Yurok TR - Identify staff with expertise in Case Management - Ongoing Case Work (MS 6.1, 7, 7.1, 9) and Case Management - Finish a Case (MS 10, 10.1, 11,13) to assist with updating documentation of business processes/procedures and operational manuals (if | July 1, 2025 8:00 AM | September 2, 2025 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 44 | 0d | NA | NA | 0 days? | No | 7/1/25 | 9/2/25 | NA | 1
43276 | Yurok TR - Participate in OCM led Process Information Session for Case Management - Ongoing Case Work and Case Management - Finish a Case | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 44 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
43277 | Yurok TR - Review Change Impact Assessment for Case Management - Ongoing Case Work and Case Management - Finish a Case and draft necessary revisions to internal business processes/procedures and operational manuals | November 3, 2025 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 80 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
43278 | Yurok TR - Review, update as needed, and FINALIZE Case Management - Ongoing Case Work and Case Management - Finish a Case processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
43279 | Yurok TR - Identify staff with expertise in Other Court Processing (MS 16, 17, 18) to assist with updating documentation of business processes/procedures and operational manuals (if applicable) for each OCM business process task | September 2, 2025 8:00 AM | October 31, 2025 5:00 PM |  |  | Start No Earlier Than | 9/1/25 | 44 | 485d | NA | NA | 0 days? | No | NA | NA | NA | 0
43280 | Yurok TR - Participate in OCM led Process Information Session for Other Court Processing | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
43281 | Yurok TR - Review Change Impact Assessment for Other Court Processing and draft necessary revisions to internal business processes/procedures and operational manuals | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
43282 | Yurok TR - Review, update as needed, and FINALIZE Other Court Processing processes/procedures | April 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 28 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
43283 | Yurok TR - Identify staff with expertise in Resource Management (MS 26, 26.1, 27, 28), Financial Management (MS 23, 23.1, 24), Admin (MS 32) and Reports (MS 29, 30, 31) to assist with updating documentation of business processes/procedures and operational | November 3, 2025 8:00 AM | December 31, 2025 5:00 PM |  |  | Start No Earlier Than | 11/1/25 | 40 | 445d | NA | NA | 0 days? | No | NA | NA | NA | 0
43284 | Yurok TR - Participate in OCM led Process Information Session for RM, FM, Admin, Reports | January 2, 2026 8:00 AM | March 2, 2026 5:00 PM |  |  | Start No Earlier Than | 1/2/26 | 40 | 405d | NA | NA | 0 days? | No | NA | NA | NA | 0
43285 | Yurok TR - Review, update as needed, and FINALIZE RM, FM, Admin, Reports processes/procedures | May 1, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 5/1/26 | 6 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
43286 | Yurok TR - Review Change Impact Assessment for RM, FM, Admin, Reports and draft necessary revisions to internal business processes/procedures and operational manuals | March 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 3/1/26 | 44 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43287 | Yurok TR - Review, update as needed, and FINALIZE all business processes/procedures | April 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 76 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
43288 | Yurok TR - Technical Activities | March 19, 2024 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 597 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
43289 | Yurok TR - Complete Tableau Training | March 19, 2024 8:00 AM | May 11, 2026 5:00 PM |  |  | As Soon As Possible | NA | 539 | 356d | NA | NA | 0 days? | No | NA | NA | NA | 0
43290 | Yurok TR - Confirm Tableau training participants in the Teams Channel CAT Workgroup Participants list | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM |  | 24936SS,24937 | Start No Earlier Than | 3/19/24 | 490 | 356d | NA | NA | 0 days? | No | NA | NA | NA | 0
43291 | Yurok TR - Enroll in Tableau training cohorts by responding to workgroup survey | March 19, 2024 8:00 AM | March 2, 2026 5:00 PM | 24935SS | 24937 | As Soon As Possible | NA | 490 | 356d | NA | NA | 0 days? | No | NA | NA | NA | 0
43292 | Yurok TR - IC Confirm all participant training completion of self-paced and instructor-led training for Tableau for reports creators | March 3, 2026 8:00 AM | May 11, 2026 5:00 PM | 24935,24936 |  | As Soon As Possible | NA | 49 | 356d | NA | NA | 0 days? | No | NA | NA | NA | 0
43293 | Yurok TR - Determine priority for Organization-specific custom reports | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 171 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
43294 | Yurok TR - Prioritize list of reports in inventory by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 24940 | Start No Earlier Than | 8/11/25 | 59 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
43295 | Yurok TR - POC or Organization Leadership to review priority and sign-off on what reports will be developed by the organization prior to CWS-CARES V1 Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 24939 |  | As Soon As Possible | NA | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
43296 | Yurok TR - Execute plan for transition of custom reports from Business Objects to Tableau | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
43297 | Yurok TR - Develop Plan for Timeline of Reports Creation in Tableau | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM |  |  | Start No Earlier Than | 8/11/25 | 36 | 508d | NA | NA | 0 days? | No | NA | NA | NA | 0
43298 | Yurok TR - Create organization-specific reports | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  | 24944SS | Start No Earlier Than | 10/1/25 | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43299 | Yurok TR - Test reports in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24943SS |  | As Soon As Possible | NA | 146 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43300 | Yurok TR - POC or Organization Leadership to sign off on report creation completion | May 1, 2026 8:00 AM | May 26, 2026 5:00 PM |  |  | Finish No Earlier Than | 5/26/26 | 17 | 346d | NA | NA | 0 days? | No | NA | NA | NA | 0
43301 | Yurok TR - Test reports in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
43302 | Yurok TR - Complete Training for Creation of Forms in CARES | February 3, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 313 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43303 | Yurok TR - Confirm training participants are listed in the Teams Channel Forms Workgroup Participants list as forms authors. | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM |  | 24949SS | Start No Earlier Than | 2/1/25 | 251 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
43304 | Yurok TR - Respond to Survey for enrollment in training cohorts | February 3, 2025 8:00 AM | February 2, 2026 5:00 PM | 24948SS |  | As Soon As Possible | NA | 251 | 424d | NA | NA | 0 days? | No | NA | NA | NA | 0
43305 | Yurok TR - Organization Implementation Coordinator to confirm completion of self-paced online training, and instructor-led AEM & Word training for all identified forms creators. | April 1, 2025 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/25 | 274 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43306 | Yurok TR - Determine priority for Organization-specific custom Forms | August 11, 2025 8:00 AM | April 16, 2026 5:00 PM |  |  | As Soon As Possible | NA | 171 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
43307 | Yurok TR - Prioritize list of forms by timeframe needed (day 1 of go-live, week 1 of go-live, month 1 of go-live, etc.) in workbook | August 11, 2025 8:00 AM | October 31, 2025 5:00 PM |  | 24953 | Start No Earlier Than | 8/11/25 | 59 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
43308 | Yurok TR - POC or Organization Leadership to review priority and sign-off on what forms will be developed by the organization prior to CARES Version 1 (V1) Go-Live. | November 3, 2025 8:00 AM | April 16, 2026 5:00 PM | 24952 |  | Start No Earlier Than | 11/1/25 | 112 | 373d | NA | NA | 0 days? | No | NA | NA | NA | 0
43309 | Yurok TR - Execute plan for transition of Organization-specific custom Forms to CARES AEM or Word format | August 11, 2025 8:00 AM | August 3, 2026 5:00 PM |  |  | As Soon As Possible | NA | 246 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
43310 | Yurok TR - Develop Plan for Timeline of Form Creation in AEM/Word | August 11, 2025 8:00 AM | September 30, 2025 5:00 PM |  | 24956 | Start No Earlier Than | 8/11/25 | 36 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
43311 | Yurok TR - Create organization-specific forms | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24955 | 24957SS,24958 | As Soon As Possible | NA | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
43312 | Yurok TR - Test forms in development environment | October 1, 2025 8:00 AM | May 1, 2026 5:00 PM | 24956SS | 24958 | Start No Earlier Than | 10/1/25 | 146 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
43313 | Yurok TR - POC or Organization Leadership to sign off on form completion | May 4, 2026 8:00 AM | May 27, 2026 5:00 PM | 24956,24957 |  | Start No Earlier Than | 6/30/25 | 17 | 345d | NA | NA | 0 days? | No | NA | NA | NA | 0
43314 | Yurok TR - Test forms in environment with converted data | January 12, 2026 8:00 AM | August 3, 2026 5:00 PM |  |  | Start No Earlier Than | 1/12/26 | 141 | 298d | NA | NA | 0 days? | No | NA | NA | NA | 0
43315 | Yurok TR - Technical Readiness Validation (All tasks may not apply for dedicated counties.) | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | As Soon As Possible | NA | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43316 | Yurok TR - Confirm Organizations workstations/laptops have completed setting changes and actions for either Chrome or MS Edge Chromium, as outlined in the Technical Readiness Resource document. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  | 24962SS | Start No Earlier Than | 1/1/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43317 | Yurok TR - Confirm Organizations e-mail server won't filter out CARES Training and Production email messages as spam. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24961SS | 24963SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43318 | Yurok TR - Confirm all computers needing to access CWS-CARES meet the minimum supported desktop hardware and software requirements. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24962SS | 24964SS | Start No Earlier Than | 1/1/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43319 | Yurok TR - Confirm Organizations IP range has been whitelisted. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24963SS | 24965SS | Start No Earlier Than | 1/1/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43320 | Yurok TR - Verify Organizations workstations can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24964SS | 24966SS | Start No Earlier Than | 1/1/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43321 | Yurok TR - Confirm users who use Organization-provided remote access solutions (VPN) can access CARES Production URLs. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24965SS | 24967SS | Start No Earlier Than | 1/1/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43322 | Yurok TR - Confirm Organization software updates have been applied to systems. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24966SS | 24968SS | Start No Earlier Than | 1/1/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43323 | Yurok TR - Confirm Organization has the following security software installed/configured within its environment: Intrusion Detection System (IDS) / Intrusion Prevention System (IPS) (e.g., Cisco), Layer 7 (next gen) firewall (e.g., Palo Alto), Data loss | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24967SS | 24969SS | Start No Earlier Than | 1/1/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43324 | Yurok TR - Confirm Organization has any of the following proxy software installed/ configured within its environment: Web Proxy (e.g., WebSense) and Email proxy. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24968SS | 24970SS | Start No Earlier Than | 1/1/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43325 | Yurok TR - Confirm Organization has appropriate anti-malware/anti-virus software. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24969SS | 24971SS | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43326 | Yurok TR - Confirm Organizations CARES Technical Contact is correct. | January 2, 2026 8:00 AM | May 1, 2026 5:00 PM | 24970SS |  | Start No Earlier Than | 1/2/26 | 83 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43327 | Yurok TR - Validate connectivity to Training Environment | May 4, 2026 8:00 AM | June 26, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 39 | 323d | NA | NA | 0 days? | No | NA | NA | NA | 0
43328 | Yurok TR - Identify and implement the process by which staff will access the Production environment | June 1, 2026 8:00 AM | July 10, 2026 5:00 PM |  |  | Finish No Earlier Than | 7/10/26 | 29 | 314d | NA | NA | 0 days? | No | NA | NA | NA | 0
43329 | Yurok TR - Training | July 1, 2025 8:00 AM | December 30, 2026 5:00 PM |  |  | As Soon As Possible | NA | 376 | 196d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.02
43330 | Yurok TR - Develop the CARES V1 Organization Training Plan | July 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 7/1/25 | 188 | 384d | NA | NA | 0 days? | No | 7/1/25 | NA | NA | 0.20000000000000001
43331 | Yurok TR - Complete the Organization Training Curriculum Assignments | October 1, 2025 8:00 AM | April 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 124 | 384d | NA | NA | 0 days? | No | NA | NA | NA | 0
43332 | Yurok TR - Assess and add Organization-specific information to ILT materials (if needed) | October 1, 2025 8:00 AM | July 1, 2026 5:00 PM |  |  | Start No Earlier Than | 10/1/25 | 188 | 320d | NA | NA | 0 days? | No | NA | NA | NA | 0
43333 | Yurok TR - Identify Support Structure needed for RFA Applicants | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43334 | Yurok TR - Identify support structure needed for FFPSA providers | February 2, 2026 8:00 AM | May 1, 2026 5:00 PM |  |  | Start No Earlier Than | 2/2/26 | 63 | 362d | NA | NA | 0 days? | No | NA | NA | NA | 0
43335 | Yurok TR - Execute the CARES V1 Organization Training Plan | April 1, 2026 8:00 AM | December 30, 2026 5:00 PM |  |  | Start No Earlier Than | 4/1/26 | 189 | 196d | NA | NA | 0 days? | No | NA | NA | NA | 0
43336 | Yurok TR - Complete & Submit Training user spreadsheet | April 13, 2026 8:00 AM | May 8, 2026 5:00 PM |  |  | Start No Earlier Than | 4/13/26 | 20 | 357d | NA | NA | 0 days? | No | NA | NA | NA | 0
43337 | Yurok TR - Prepare training on Intake processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM |  | 24983SS | Start No Earlier Than | 5/1/26 | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
43338 | Yurok TR - Prepare training on Case Management processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 24982SS | 24984SS | As Soon As Possible | NA | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
43339 | Yurok TR - Prepare training on Case Management - Ongoing Case Work and Case Management - Finish a Case | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 24983SS | 24985SS | As Soon As Possible | NA | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
43340 | Yurok TR - Prepare training on Other Court Processing processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 24984SS | 24986SS | As Soon As Possible | NA | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
43341 | Yurok TR - Prepare training on RFA, Financial Management, Resource Management, Admin processes/procedures (if applicable) | May 1, 2026 8:00 AM | July 17, 2026 5:00 PM | 24985SS |  | As Soon As Possible | NA | 54 | 309d | NA | NA | 0 days? | No | NA | NA | NA | 0
43342 | Yurok TR - Provide Project-developed User Guides and developed training materials to RFA applicants | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM |  | 24988SS | Start No Earlier Than | 5/1/26 | 128 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
43343 | Yurok TR - Provide Project-developed User Guides and developed training materials to FFPSA providers | May 1, 2026 8:00 AM | October 30, 2026 5:00 PM | 24987SS |  | Start No Earlier Than | 5/1/26 | 128 | 235d | NA | NA | 0 days? | No | NA | NA | NA | 0
43344 | Yurok TR - Register users for instructor-led training (in State LMS) | May 4, 2026 8:00 AM | July 15, 2026 5:00 PM |  |  | Start No Earlier Than | 5/4/26 | 51 | 311d | NA | NA | 0 days? | No | NA | NA | NA | 0
43345 | Yurok TR - Receive Project-developed User Guides for RFA portal for applicants | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
43346 | Yurok TR - Receive Project-developed User Guides for FFPSA portal for providers | June 1, 2026 8:00 AM | June 30, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 22 | 321d | NA | NA | 0 days? | No | NA | NA | NA | 0
43347 | Yurok TR - Validate access to on-demand self-paced training | June 1, 2026 8:00 AM | October 2, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 88 | 255d | NA | NA | 0 days? | No | NA | NA | NA | 0
43348 | Yurok TR - Deliver processes/procedures training (if applicable) for Intake | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM |  | 24994SS | Start No Earlier Than | 6/1/26 | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
43349 | Yurok TR - Deliver processes/procedures training (if applicable) for Case Management Placement and Eligibility | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 24993SS | 24997SS | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
43350 | Yurok TR - Deliver processes/procedures training (if applicable) for Courts | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 24997SS | 24996SS | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
43351 | Yurok TR - Deliver processes/procedures training (if applicable) for RFA, Financial Management, Resource Management, Admin | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 24995SS |  | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
43352 | Yurok TR - Deliver processes/procedures training (if applicable) for Resource Management | June 1, 2026 8:00 AM | October 23, 2026 5:00 PM | 24994SS | 24995SS | As Soon As Possible | NA | 103 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0
43353 | Yurok TR - Complete on-demand training | June 1, 2026 8:00 AM | October 9, 2026 5:00 PM |  |  | Start No Earlier Than | 6/1/26 | 93 | 250d | NA | NA | 0 days? | No | NA | NA | NA | 0
43354 | Yurok TR - Attend Training for Organization Training (includes Super Users identified to support Organization ILT sessions) | June 15, 2026 8:00 AM | July 31, 2026 5:00 PM |  |  | Start No Earlier Than | 6/15/26 | 34 | 299d | NA | NA | 0 days? | No | NA | NA | NA | 0
43355 | Yurok TR - Complete instructor-led training | August 3, 2026 8:00 AM | October 23, 2026 5:00 PM |  |  | Start No Earlier Than | 8/3/26 | 59 | 240d | NA | NA | 0 days? | No | NA | NA | NA | 0